## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Demand
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Skill Demand | Baseline duration (in calendar days)
1 | Brain-Le-Compte spoor 5 |  | FS2 | 2019-09-23 08:00 | 2019-09-23 08:00 | / |  | 0
2 | Voorbereiden (snelheidsbeperkingen, netten voor perron,…) | 1FS | FS3 | 2019-09-23 08:00 | 2019-09-30 17:00 | 6d | Kraanbestuurder [1]; Chauffeur [1]; Spoorwegarbeider [3] | 8
3 | Dwarsliggers lossen | 2FS | FS4,FS5 | 2019-09-30 23:00 | 2019-10-01 04:00 | 1d (1 nacht) | Kraanbestuurder [1]; Spoorwegarbeider [1] | 1
4 | Spoor losmaken (met de hand) | 3FS | FS6 | 2019-10-01 08:00 | 2019-10-02 17:00 | 2d | Spoorwegarbeider [4] | 2
5 | Uitbreken en opladen | 3FS | FS6,FS7 | 2019-10-01 23:00 | 2019-10-03 04:00 | 2d (2 nachten) | Kraanbestuurder [1]; Spoorwegarbeider [1] | 2
6 | Lossen en laden materiaal | 4FS,5FS | FS19 | 2019-10-03 08:00 | 2019-10-23 17:00 | 13d | Kraanbestuurder [1]; Chauffeur [1] | 21
7 | Uitgraven bedding | 5FS | FS8,FS9,FS10 | 2019-10-03 23:00 | 2019-10-08 04:00 | 4d (4 nachten) | Kraanbestuurder [2]; Spoorwegarbeider [1] | 5
8 | Ballast lossen | 7FS | FS11 | 2019-10-08 23:00 | 2019-10-20 04:00 | 9d (9 nachten) | Kraanbestuurder [2]; Spoorwegarbeider [1] | 12
9 | Dwarsliggers plaatsen | 7FS | FS11 | 2019-10-11 08:00 | 2019-10-17 17:00 | 5d (5 nachten) | Kraanbestuurder [1]; Chauffeur [1] | 7
10 | Monteren van spoor | 7FS | FS11 | 2019-10-14 08:00 | 2019-10-16 17:00 | 3d | Spoorwegarbeider [7] | 3
11 | Onderstoppen | 8FS,9FS,10FS | FS12,FS13,FS14 | 2019-10-21 23:00 | 2019-10-22 04:00 | 1d (1 nacht) | Kraanbestuurder [2]; Spoorwegarbeider [1]; Machinewerker [1] | 1
12 | Kwaliteitscontrole | 11FS | FS19 | 2019-10-22 23:00 | 2019-10-31 04:00 | 4d (4 nachten) | Kraanbestuurder [1]; Spoorwegarbeider [1] | 9
13 | Terugplaasten van elementen in het spoor | 11FS | FS15 | 2019-10-23 08:00 | 2019-10-24 17:00 | 2d | Spoorwegarbeider [3] | 2
14 | Laswerk | 11FS | FS15 | 2019-10-23 08:00 | 2019-10-24 17:00 | 2d | Lasser [2] | 2
15 | Afvoer materiaal | 13FS,14FS | FS16 | 2019-10-25 08:00 | 2019-10-25 17:00 | 1d | Chauffeur [1] | 1
16 | Herzien van onderstoppen | 15FS | FS17 | 2019-10-25 23:00 | 2019-10-26 04:00 | 1d (1 nacht) | Machinewerker [1] | 1
17 | Spanningsregeling | 16FS | FS18 | 2019-10-31 08:00 | 2019-10-31 17:00 | 1d | Spoorwegarbeider [8]; Lasser [2] | 1
18 | Tijdelijke seinen, snelheidsbeperkingen,… weghalen | 17FS | FS19 | 2019-11-03 08:00 | 2019-11-03 17:00 | 1d | Spoorwegarbeider [5] | 1
19 | Brain-Le-Compte spoor 5 | 6FS,12FS,18FS |  | 2019-11-03 17:00 | 2019-11-03 17:00 | / |  | 0

## Resources
General |  |  | Skill Distribution |  |  |  |  | Skill Demand
ID | Name(generated) | Type | Kraanbestuurder | Chauffeur | Spoorwegarbeider | Machinewerker | Lasser | Assigned to
1 | Albert Cooper | Renewable | 0 | 0 | 1 | 0 | 0
2 | Oliver Foster | Renewable | 0 | 1 | 1 | 0 | 0
3 | Kate Harrison | Renewable | 1 | 1 | 0 | 0 | 0
4 | Dominik Andrews | Renewable | 0 | 0 | 1 | 0 | 0
5 | Grace Murray | Renewable | 1 | 1 | 0 | 0 | 0
6 | Maddie Thompson | Renewable | 1 | 1 | 0 | 0 | 0
7 | Valeria Williams | Renewable | 1 | 1 | 0 | 0 | 0
8 | George Farrell | Renewable | 0 | 0 | 1 | 0 | 0
9 | Jared Perry | Renewable | 1 | 0 | 0 | 0 | 0
10 | Aldus Spencer | Renewable | 0 | 0 | 1 | 0 | 0
11 | Elise Spencer | Renewable | 1 | 0 | 0 | 0 | 0
12 | Eddy Kelly | Renewable | 0 | 1 | 1 | 0 | 0
13 | Wilson Craig | Renewable | 0 | 0 | 1 | 0 | 0
14 | Sydney Stevens | Renewable | 0 | 0 | 1 | 0 | 0
15 | Adrianna Fowler | Renewable | 1 | 1 | 1 | 0 | 0
16 | Daryl Brown | Renewable | 0 | 0 | 1 | 0 | 0
17 | Victor Armstrong | Renewable | 0 | 1 | 1 | 0 | 1
18 | Martin Harrison | Renewable | 0 | 0 | 1 | 0 | 1
19 | Catherine Craig | Renewable | 0 | 0 | 1 | 0 | 0
20 | Kimberly Harrison | Renewable | 0 | 0 | 1 | 0 | 1
21 | Elise Tucker | Renewable | 0 | 0 | 1 | 0 | 0
22 | Alford Bailey | Renewable | 0 | 1 | 1 | 0 | 0
23 | Tony Payne | Renewable | 0 | 1 | 1 | 0 | 0
24 | Eric Parker | Renewable | 0 | 1 | 1 | 0 | 0
25 | Jasmine Ross | Renewable | 0 | 0 | 0 | 1 | 0
|  |  | 7 | 11 | 18 | 1 | 3