## Baseline Schedule
General |  | Relations |  | Baseline (not available) |  |  | Demand
ID | Name (not available) | Predecessors | Successors | Baseline Start | Baseline End | Duration | Skill Demand | Baseline duration (in calendar days)
1 | ETCS1-FS_L12 |  | FS2 | / | / | /
2 | Activiteit 1 | 1FS | FS3 | / | / | 1d | Project Manager [1]
3 | Activiteit 2 | 2FS | FS4,FS5,FS6 | / | / | 1d | Project Manager [1]
4 | Activiteit 3 | 3FS | FS7 | / | / | 1d | Quality Manager [1]
5 | Activiteit 4 | 3FS | FS7 | / | / | 1d | Quality Manager [1]
6 | Activiteit 5 | 3FS | FS17,FS18,FS19 | / | / | 27d | Project Engineer ETCS [1]; Technical Sector Chef [1]
7 | Activiteit 6 | 4FS,5FS | FS14,FS15 | / | / | 62d | Project Engineer ETCS [1]
8 | Activiteit 7 | 39FS | FS95 | / | / | 13d | Safety Manager [1]
9 | Activiteit 8 | 23FS | FS13 | / | / | 56d | Project Engineer ETCS [1]; Technical Sector Chef [1]
10 | Activiteit 9 | 23FS | FS95 | / | / | 47d | Project Engineer ETCS [1]
11 | Activiteit 10 | 12FS | FS95 | / | / | 30d | Safety Manager [1]; Quality Manager [1]; Project Engineer ETCS [1]; System Engineer [1]
12 | Activiteit 11 | 23FS | FS11 | / | / | 1d | Project Engineer ETCS [1]
13 | Activiteit 12 | 9FS | FS95 | / | / | 1d | Project Engineer ETCS [1]; System Engineer [1]
14 | Activiteit 13 | 7FS | FS23 | / | / | 34d | Project Engineer ETCS [1]
15 | Activiteit 14 | 7FS | FS16 | / | / | 4d | Project Engineer ETCS [1]
16 | Activiteit 15 | 15FS | FS95 | / | / | 2d | Project Engineer ETCS [1]; System Engineer [1]
17 | Activiteit 16 | 6FS | FS24 | / | / | 72d | Project Engineer ETCS [1]
18 | Activiteit 17 | 6FS | FS24 | / | / | 71d | Project Engineer ETCS [1]
19 | Activiteit 18 | 6FS | FS20,FS27 | / | / | 4d | Project Engineer ETCS [1]; System Engineer [1]
20 | Activiteit 19 | 19FS | FS21 | / | / | 2d | Project Engineer ETCS [1]
21 | Activiteit 20 | 20FS | FS22 | / | / | 6d | Project Engineer ETCS [1]
22 | Activiteit 21 | 21FS | FS95 | / | / | 3d | Project Engineer ETCS [1]; System Engineer [1]
23 | Activiteit 22 | 14FS | FS9,FS10,FS12 | / | / | 2d | Project Engineer ETCS [1]; System Engineer [1]
24 | Activiteit 23 | 17FS,18FS | FS25 | / | / | 2d | Project Engineer ETCS [1]
25 | Activiteit 24 | FS24 | FS26 | / | / | 3d | Project Engineer ETCS [1]; System Engineer [1]
26 | Activiteit 25 | FS25 | FS30 | / | / | 1d | Project Engineer ETCS [1]; System Engineer [1]
27 | Activiteit 26 | 19FS | FS28 | / | / | 2d | Project Engineer ETCS [1]
28 | Activiteit 27 | 27FS | FS29 | / | / | 5d | Project Engineer ETCS [1]; System Engineer [1]
29 | Activiteit 28 | 28FS | FS95 | / | / | 84d | Project Engineer ETCS [1]; System Engineer [1]
30 | Activiteit 29 | 26FS | FS31 | / | / | 20d | Project Engineer ETCS [1]; System Engineer [1]
31 | Activiteit 30 | 30FS | FS32,FS33 | / | / | 99d | Project Engineer ETCS [1]; Technical Sector Chef [1]
32 | Activiteit 31 | 31FS | FS34,FS35,FS38 | / | / | 19d | Project Engineer ETCS [1]; Technical Sector Chef [1]
33 | Activiteit 32 | 31FS | FS95 | / | / | 7d | Project Engineer ETCS [1]
34 | Activiteit 33 | 32FS | FS37 | / | / | 11d | Project Engineer ETCS [1]
35 | Activiteit 34 | 32FS | FS36 | / | / | 6d | Project Engineer ETCS [1]
36 | Activiteit 35 | 35FS | FS37 | / | / | 1d | Project Engineer ETCS [1]
37 | Activiteit 36 | 34FS | FS41 | / | / | 1d | Project Engineer ETCS [1]; System Engineer [1]
38 | Activiteit 37 | 32FS | FS39 | / | / | 4d | Project Engineer ETCS [1]
39 | Activiteit 38 | 38FS | FS40 | / | / | 2d | Project Engineer ETCS [1]; System Engineer [1]
40 | Activiteit 39 | 40FS | FS8 | / | / | 1d | Safety Manager [1]; Project Engineer ETCS [2]; System Engineer [1]
41 | Activiteit 40 | 37FS | FS42,FS43 | / | / | 9d | Project Engineer ETCS [1]; Technical Sector Chef [1]
42 | Activiteit 41 | 41FS | FS44 | / | / | 25d | Field Worker [1]
43 | Activiteit 42 | 41FS | FS44 | / | / | 25d | Software Engineer [1]; Technical Sector Chef [1]; Field Worker [1]
44 | Activiteit 43 | 42FS,43FS | FS45 | / | / | 6d | Technical Sector Chef [1];
45 | Activiteit 44 | 44FS | FS46 | / | / | 1d | Technical Sector Chef [1];
46 | Activiteit 45 | 45FS | FS47 | / | / | 4d | Technical Sector Chef [1];
47 | Activiteit 46 | 46FS | FS48 | / | / | 2d | Technical Sector Chef [1];
48 | Activiteit 47 | 47FS | FS49,FS50 | / | / | 1d | Technical Sector Chef [1];
49 | Activiteit 48 | 48FS | FS51 | / | / | 8d | Technical Sector Chef [1];
50 | Activiteit 49 | 48SF | FS51 | / | / | 32d | Project Engineer ETCS [2]
51 | Activiteit 50 | 49FS,50FS | FS52,FS67 | / | / | 31d | Project Engineer ETCS [2]
52 | Activiteit 51 | 51FS | FS53 | / | / | 32d | Project Engineer ETCS [2]
53 | Activiteit 52 | 52FS | FS54,FS55 | / | / | 1d | Project Manager [1]; Project Engineer ETCS [2]
54 | Activiteit 53 | 53FS | FS60,FS61,FS66,FS76 | / | / | 14d | Project Engineer ETCS [1]
55 | Activiteit 54 | 53FS | FS56 | / | / | 5d | Project Engineer ETCS [2]
56 | Activiteit 55 | 55FS | FS57 | / | / | 2d | Project Engineer ETCS [2]
57 | Activiteit 56 | 56FS | FS58 | / | / | 18d | Project Engineer ETCS [2]
58 | Activiteit 57 | 57FS | FS59 | / | / | 2d | Project Engineer ETCS [2]
59 | Activiteit 58 | 58FS | FS95 | / | / | 1d | Project Manager [1]
60 | Activiteit 59 | 54FS | FS62 | / | / | 14d | Project Engineer ETCS [1]
61 | Activiteit 60 | 54FS | FS62 | / | / | 16d | Project Engineer ETCS [2]
62 | Activiteit 61 | 60FS,61FS | FS63 | / | / | 2d | Project Engineer ETCS [1]
63 | Activiteit 62 | 62FS | FS64 | / | / | 2d | Project Engineer ETCS [2]
64 | Activiteit 63 | 63FS | FS65 | / | / | 3d | Project Engineer ETCS [2]
65 | Activiteit 64 | 64FS | FS75 | / | / | 1d | Project Manager [1]; Project Engineer ETCS [2]
66 | Activiteit 65 | 54FS | FS95 | / | / | 19d | Safety Manager [1]; Project Engineer ETCS [1]
67 | Activiteit 66 | 51FS | FS95 | / | / | 1d | Team Signaling [6]
68 | Activiteit 67 | 75FS | FS95 | / | / | 1d | Safety Manager [1]; Quality Manager [1]; Team Signaling [6]
69 | Activiteit 68 | 71FS | FS81 | / | / | 1d | Project Engineer ETCS [1];Team Signaling [6]
70 | Activiteit 69 | 75FS | FS95 | / | / | 1d | Team Signaling [6]
71 | Activiteit 70 | 75FS | FS69,FS74,FS80 | / | / | 2d | Project Engineer ETCS [3];Team Signaling [6]
72 | Activiteit 71 | 75FS | FS95 | / | / | 1d | Project Engineer ETCS [1];Team Signaling [6]
73 | Activiteit 72 | 75FS | FS95 | / | / | 1d | Project Engineer ETCS [2]; Technical Sector Chef [1]
74 | Activiteit 73 | 71FS | FS81 | / | / | 1d | Project Engineer ETCS [2];Team Signaling [6]
75 | Activiteit 74 | 65FS | FS68,FS70,FS71,FS72,FS73,FS78,FS79 | / | / | 1d | Project Engineer ETCS [1]
76 | Activiteit 75 | 54FS | FS77 | / | / | 4d | Project Engineer ETCS [1]
77 | Activiteit 76 | 76FS | FS95 | / | / | 2d | Project Engineer ETCS [2]
78 | Activiteit 77 | 75FS | FS95 | / | / | 3d | Project Engineer ETCS [2]
79 | Activiteit 78 | 75FS | FS95 | / | / | 6d | Project Engineer ETCS [2]
80 | Activiteit 79 | 71FS | FS81 | / | / | 1d | Project Manager [1]; Project Engineer ETCS [2]
81 | Activiteit 80 | 69FS,74FS,80FS | FS82 | / | / | 2d | Project Engineer ETCS [1]; System Engineer [1]
82 | Activiteit 81 | 81FS | FS83 | / | / | 8d | Project Engineer ETCS [2]
83 | Activiteit 82 | 82FS | FS84,FS85 | / | / | 3d | Project Engineer ETCS [1]; System Engineer [1]
84 | Activiteit 83 | 83FS | FS86 | / | / | 1d | Project Engineer ETCS [1]
85 | Activiteit 84 | 83FS | FS87,FS88 | / | / | 3d | Project Engineer ETCS [1]
86 | Activiteit 85 | 84FS | FS95 | / | / | 1d | Project Engineer ETCS [2]
87 | Activiteit 86 | 85FS | FS95 | / | / | 10d | Project Engineer ETCS [1]
88 | Activiteit 87 | 85FS | FS89 | / | / | 3d | Project Engineer ETCS [1]
89 | Activiteit 88 | 88FS | FS90,FS91 | / | / | 14d | Project Engineer ETCS [1]
90 | Activiteit 89 | 89FS | FS92 | / | / | 23d | Project Engineer ETCS [1]
91 | Activiteit 90 | 89FS | FS92 | / | / | 23d | Safety Manager [1]; Project Engineer ETCS [1]
92 | Activiteit 91 | 90FS,91FS | FS93 | / | / | 2d | Project Engineer ETCS [1]
93 | Activiteit 92 | 92FS | FS94 | / | / | 13d | Safety Manager [1]; Quality Manager [1]; Project Engineer ETCS [1]
94 | Activiteit 93 | 93FS | FS95 | / | / | 1d | Safety Manager [1]
95 | ETCS1-FS_L12 | FS8,FS10,FS11,FS13,FS16,FS22,FS29,FS33,FS59,FS66,FS67,FS68,FS70,FS72,FS73,FS77,FS78,FS79,FS86,FS87,FS94 |  | / | / | /

## Resources
General |  |  | Skill Distribution | [8 empty] | Skill Demand
ID | Name(generated) | Type | Safety Manager | Quality Manager | Project Manager | Project Engineer ETCS | System Engineer | Software Engineer | Team Signaling | Technical Sector Chef | Field Worker | Assigned to
1 | Richard Holmes | Renewable | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Alisa Montgomery | Renewable | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Alissa Harrison | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Thomas Miller | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
5 | Charlotte Clark | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
6 | Haris Harper | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
7 | Jessica Cameron | Renewable | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0
8 | Julia Turner | Renewable | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0
9 | Alissa Wright | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
10 | Sarah Jones | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
11 | Belinda Richards | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
12 | Byron Brown | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
13 | Honey Ferguson | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
14 | James Hill | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
15 | Steven Roberts | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
16 | Justin Tucker | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
17 | Elian Morgan | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
18 | Natalie Murphy | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
19 | Abigail Ross | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
20 | Samantha Walker | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
21 | Vincent Murray | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
22 | Preston Dixon | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
23 | Agata Hawkins | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
24 | Dominik Murray | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
25 | Sydney Barnes | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
26 | Adele Miller | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
27 | Patrick Johnston | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
28 | Kimberly Adams | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
29 | Kevin Rogers | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
30 | Haris Taylor | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  |  | 3 | 1 | 2 | 9 | 3 | 2 | 24 | 2 | 2