## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Demand
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Skill Demand | Baseline duration (in calendar days)
1 | ETCS1-FS_L28 |  | FS2,FS4 | 2017-08-01 | 2017-08-01 | / |  | 0
2 | Project Charter | 1FS | FS3 | 2017-08-01 | 2017-08-07 | 5d | Project Manager [1] | 7
3 | Project Scoping Document | 2FS | FS6 | 2017-08-31 | 2017-09-05 | 4d | Project Manager [1] | 6
4 | Specific Project Quality Plan | 1FS | FS5 | 2017-08-01 | 2017-08-07 | 5d | Quality Manager [1] | 7
5 | Project Quality Charter | 4FS | FS6 | 2017-08-07 | 2017-08-16 | 5d | Quality Manager [1]; Project Manager [1] | 10
6 | Create Specific Safety Plan | 3FS,5FS | FS7,FS8 | 2017-09-06 | 2017-09-19 | 10d | Safety Manager [1] | 14
7 | Produce, evaluate & send concept dossier | 6FS | FS9 | 2018-04-05 | 2018-05-08 | 23d | Project Manager [1] | 34
8 | Create basic layer | 6FS | FS17 | 2018-04-05 | 2017-07-10 | 65d | Project Engineer ETCS [2] | 95
9 | Execute Element SI positioning analysis | 7FS | FS10 | 2018-05-25 | 2018-06-12 | 15d | Project Engineer ETCS [1] | 19
10 | ETCS Form 3 & INST PLN Draft 1 | 9FS | FS11,FS16 | 2018-07-11 | 2018-07-17 | 5d | Project Engineer ETCS [1]; Signaling System Engineer [1] | 7
11 | DSG RPT Part 1 | 10FS | FS12 | 2018-07-18 | 2018-07-24 | 5d | Project Engineer ETCS [1] | 7
12 | 2.3.3. ETCS PART of Route Tables | 11FS | FS13 | 2018-08-22 | 2018-10-31 | 51d | Project Engineer ETCS [1] | 10
13 | 3.1.1. Finalize & verify ETCS part of Route table | 12FS | FS14,FS15,FS16 | 2018-11-15 | 2018-12-12 | 20d | Project Engineer ETCS [1] | 28
14 | DSG RPT Part 2 | 13FS | FS18 | 2018-12-13 | 2019-01-09 | 16d | Project Engineer ETCS [1] | 27
15 | Update FORM 3 & INST PLN | 13FS | FS17 | 2018-12-13 | 2018-12-17 | 3d | Project Engineer ETCS [1] | 5
16 | Create IL Part Route Table | 10FS,13FS | FS17 | 2018-12-13 | 2018-12-19 | 5d | System Engineer [1] | 7
17 | 3.1.2. Finalize & verify IL part of Route table | 8FS,15FS,16FS | FS18,FS22 | 2018-12-20 | 2019-01-15 | 15d | System Engineer [1] | 26
18 | 3.1.3. Approve route table (C4) | 14FS,17FS | FS19,FS20 | 2019-01-16 | 2019-01-22 | 5d | Project Engineer ETCS [1] | 7
19 | 3.2.1. Finalize ETCS INST PLN/ETCS FORM3 | 18FS,22FS | FS21 | 2019-01-23 | 2019-01-31 | 7d | Project Engineer ETCS [1] | 9
20 | 3.3.1. Finalize DSG RPT | 18FS | FS21 | 2019-01-23 | 2019-01-31 | 7d | Project Engineer ETCS [2] | 9
21 | Create/verify(SPR) Specific Programming rules | 19FS,20FS | FS23,FS26,FS33 | 2019-02-01 | 2019-02-26 | 18d | Project Engineer ETCS [2] | 26
22 | 6. Create SRS IL | 17FS | FS19 | 2019-01-16 | 2019-01-22 | 5d | Project Engineer ETCS [1]; Signaling System Engineer [1] | 7
23 | S.4. SPRLS VRF | 21FS | FS24,FS25 | 2019-02-27 | 2019-03-12 | 10d | Safety Manager [1] | 14
24 | S.3. SRS VRF Update (Design) | 23FS | FS27 | 2019-03-13 | 2019-03-26 | 10d | Safety Manager [1] | 14
25 | S.9. SASC Update (Design) | 23FS | FS27 | 2019-03-13 | 2019-03-19 | 5d | Safety Manager [1] | 7
26 | Engineering ETCS (DataPrep) | 21FS | FS38 | 2019-02-27 | 2019-07-09 | 90d | Software Engineer [1]; Technical Sector Chef [1]; Field Worker [1] | 133
27 | 18. Mounting (LEU) (installation sheets) | 24FS,25FS | FS28,FS34 | 2019-04-03 | 2019-04-25 | 16d | Team Signaling [6] | 23
28 | 19. Mounting (balises) (installation sheets) | 27FS | FS29 | 2019-04-26 | 2019-06-28 | 42d | Team Signaling [6] | 63
29 | 19.1 Mounting lateral signages | 28FS | FS30 | 2019-07-01 | 2019-09-27 | 25d | Team Signaling [6] | 88
30 | 20. Mounting (cablages loges) & 21. Mounting (Modify IL) | 29FS | FS31,FS41 | 2019-07-29 | 2019-08-26 | 19d | Team Signaling [6]; Signaling System Engineer [1] | 29
31 | 7. Modification 019-plans & Create S-interface plans (19b) | 30FS | FS42 | 2019-08-27 | 2019-09-20 | 19d | Field Worker [1] | 25
32 | 11. Update elements SI position (incl 30i adaptation) + SI NLS RPT | 41FS | FS42 | 2019-09-06 | 2019-09-20 | 11d | Team Signaling [6]; Technical Sector Chef [1] | 15
33 | 17. Modify data prep PLP- SUD | 21FS | FS27 | 2019-02-27 | 2019-04-02 | 25d | Software Engineer [1] | 35
34 | Relecture Dataprep IL - SUD | 27FS | FS35 | 2019-05-10 | 2019-06-04 | 16d | System Engineer [1] | 26
35 | Data prep "Safety test" Validation (IL) Modification | 34FS | FS36 | 2019-06-05 | 2019-06-17 | 8d | Software Engineer [1] | 13
36 | Download PLP - SUD | 35FS | FS37 | 2019-06-18 | 2019-06-18 | 1d | System Engineer [1] | 1
37 | Data prep "Safety test" Validation (IL) Modification | 36FS | FS55 | 2019-07-01 | 2019-08-02 | 25d | System Engineer [2] | 33
38 | 14. ETCS Validation (labo - F1) | 26FS | FS39,FS40 | 2019-07-10 | 2019-07-23 | 10d | Project Engineer ETCS [1] | 14
39 | 15. ETCS Validation (labo - F2) | 38FS | FS42 | 2019-07-24 | 2019-09-04 | 29d | Project Engineer ETCS [1] | 43
40 | 16. ETCS Validation (labo - F3) | 38FS | FS47 | 2019-07-24 | 2019-10-04 | 51d | Project Engineer ETCS [1] | 73
41 | Creation of commissioning plan part 1/3 | 30FS | FS32 | 2019-08-27 | 2019-09-02 | 5d | Project Engineer ETCS [1]; Safety Manager [1] | 7
42 | 22. Download LEU & Balise Files | 31FS,32FS,39FS | FS43,FS44 | 2019-09-24 | 2019-10-02 | 7d | Team Signaling [6]; Technical Sector Chef Signaling [1]; Project Engineer ETCS [1] | 9
43 | 23. ETCS integration tests (SRI - SIG_MD4) | 42FS | FS46 | 2019-10-03 | 2019-10-16 | 10d | Team Signaling [6]; Technical Sector Chef Signaling [1]; Project Engineer ETCS [1] | 14
44 | Commissioning part 2/3 ETCS validation (on site) | 42FS | FS45 | 2019-10-03 | 2019-10-11 | 7d | Project Engineer ETCS [1] | 9
45 | 25. ETCS Validation On site | 44FS | FS46,FS50 | 2019-10-14 | 2019-10-22 | 7d | Project Engineer ETCS [1] | 9
46 | Documents on site test | 43FS,45FS | FS55 | 2019-10-23 | 2019-11-04 | 8d | Project Engineer ETCS [2] | 13
47 | S.7. HZRD LOG RPT (final) | 40FS | FS48,FS49 | 2019-10-07 | 2019-10-08 | 2d | Safety Manager [1] | 2
48 | S.3. SRS VRF (final) | 47FS | FS55 | 2019-10-09 | 2019-10-17 | 7d | Safety Manager [1] | 9
49 | S.9. SASC (final) | 47FS | FS55 | 2019-10-11 | 2019-11-08 | 20d | Safety Manager [1]; Quality Manager [1] | 29
50 | S.2. ProcProd (final) | 45FS | FS51 | 2019-10-23 | 2019-11-12 | 13d | Safety Manager [1] | 21
51 | GR7 Docs sent to ISA/NoBo | 50FS | FS52 | 2019-11-13 | 2019-11-13 | 1d | Project Manager [1] | 1
52 | EC Certificate, Design Exam Certificate, QMS Certificate Received | 51FS | FS53 | 2019-12-11 | 2019-12-12 | 2d | Quality Manager [1]; Project Manager [1] | 2
53 | Commissioning part 3/3 | 52FS | FS54 | 2019-12-16 | 2019-12-16 | 1d | Team Signaling [6]; Technical Sector Chef Signaling [1]; Project Engineer ETCS [1] | 1
54 | Closing phase with lessons learned | 53FS | FS55 | 2020-01-24 | 2020-04-24 | 66d | Project Manager [1] | 91
55 | ETCS1-FS_L28 | 37FS,48FS,49FS,54FS |  | 2020-04-24 | 2020-04-24 | / |  | 0

## Resources
General |  |  | Skill Distribution | [8 empty] | Skill Demand
ID | Name(generated) | Type | Safety Manager | Quality Manager | Project Manager | Project Engineer ETCS | System Engineer | Software Engineer | Team Signaling | Technical Sector Chef | Field Worker | Assigned to
1 | Richard Holmes | Renewable | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Alisa Montgomery | Renewable | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Alissa Harrison | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Thomas Miller | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
5 | Charlotte Clark | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
6 | Haris Harper | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
7 | Jessica Cameron | Renewable | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0
8 | Julia Turner | Renewable | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
9 | Alissa Wright | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
10 | Sarah Jones | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
11 | Belinda Richards | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
12 | Byron Brown | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
13 | Honey Ferguson | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
14 | James Hill | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
15 | Steven Roberts | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
16 | Justin Tucker | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
17 | Elian Morgan | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
18 | Natalie Murphy | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
19 | Abigail Ross | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
20 | Samantha Walker | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
21 | Vincent Murray | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
22 | Preston Dixon | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
23 | Agata Hawkins | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
24 | Dominik Murray | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
25 | Sydney Barnes | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
26 | Adele Miller | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
27 | Patrick Johnston | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
28 | Kimberly Adams | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
29 | Kevin Rogers | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
30 | Haris Taylor | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
31 | Olivia Harper | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
32 | Adelaide Cole | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
33 | Olivia Owens | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
34 | Eddy Ellis | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
35 | Maya Brown | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  | 3 | 1 | 2 | 9 | 3 | 2 | 24 | 2 | 2