## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Demand
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Skill Demand | Baseline duration (in calendar days)
1 | Software Project for pay/calculation-motor |  | FS2 | 2018-07-30 | 2018-07-30 | / |  | 0
2 | Project leader setup | 1FS | FS3,FS5,FS6 | 2018-07-30 | 2018-08-08 | 8d | Main Project Worker [5] | 10
3 | Voorbereidingen project | 2FS | FS4,FS7,FS9 | 2018-08-09 | 2018-09-04 | 19d | Main Project Worker [2] | 27
4 | Databepaling en inzichten | 3FS | FS10,FS15 | 2018-09-05 | 2018-09-17 | 8d | Main Project Worker [3] | 13
| Minimum Viable Product |  |  |  |  | /
5 | IT Architectuur | 2FS | FS12,FS18,FS21 | 2018-08-09 | 2018-09-26 | 35d | Main Project Worker [3]; IT Architecture [2]; Front Office [1]; Billing [2]; Team Helpdesk [2]; Team PAY [1] | 49
6 | Loonbepaling | 2FS | FS12,FS19,FS30 | 2018-08-09 | 2018-10-24 | 55d | Main Project Worker [2]; IT Architecture [2]; Front Office [2]; Billing [2]; Team Helpdesk [2]; Team PAY [6] | 77
7 | Bruto bepalingen | 3FS | FS8,FS16,FS17 | 2018-09-05 | 2018-10-11 | 26d | Main Project Worker [2]; Team PAY [4] | 37
8 | Netto bepalingen | 7FS | FS18,FS26 | 2018-10-12 | 2018-10-31 | 13d | Main Project Worker [2]; Team PAY [4] | 20
9 | User Interface | 3FS | FS13,FS35 | 2018-09-05 | 2018-10-22 | 33d | Main Project Worker [1]; Front Office [2]; Software Engineer [4]; Team PAY [1] | 48
10 | Algemene presales | 4FS | FS11 | 2018-09-18 | 2018-09-20 | 3d | Main Project Worker [3]; Team Helpdesk [1]; Marketing [1] | 3
11 | Uitzetten van sociale wetgeving | 10FS | FS12 | 2018-09-21 | 2018-09-21 | 1d | Main Project Worker [2]; Front Office [1] | 1
12 | Marketing overleg en uitwerking | 5FS,6FS,11FS | FS13 | 2018-10-25 | 2018-10-07 | 9d | Main Project Worker [2]; Marketing [1] | 14
13 | Marktdistributie en voorspelling | 8FS,12FS | FS14 | 2018-10-23 | 2018-10-23 | 1d | Main Project Worker [1]; Front Office [1] | 1
14 | Opzetten klantenbehoudsysteem | 13FS,15FS | FS36 | 2018-12-21 | 2018-12-28 | 4d | Main Project Worker [2] | 8
Minimum Viable Product
15 | Multifunctionele aangifte | 4FS | FS14,FS19,FS22,FS29 | 2018-09-18 | 2018-12-20 | 68d | Main Project Worker [2]; Billing [6]; Team PAY [1] | 93
16 | Loonbetalingen en loonbrieven | 7FS | FS18,FS26,FS32 | 2018-10-12 | 2018-11-21 | 29d | Main Project Worker [2]; IT Architecture [1]; Front Office [2]; Billing (2]; Team Helpdesk [1]; Team PAY [7] | 41
17 | Indicatie bedrijfsvoorheffing | 7FS | FS18,FS25,FS28 | 2018-10-12 | 2018-11-15 | 25d | Main Project Worker [3]; IT Architecture [6]; Front Office [1]; Team PAY [2] | 35
18 | Initiele boekhouding | 5FS,8FS,16FS,17FS | FS19,FS23 | 2018-11-22 | 2018-11-22 | 1d | Main Project Worker [2] | 1
19 | Volledige boekhouding | 6FS,15FS,18FS | FS20 | 2018-12-21 | 2018-12-28 | 3d | Main Project Worker [1]; Team PAY [1] | 8
20 | Pay motor rapportering | 19FS | FS33 | 2018-12-28 | 2018-12-28 | 1d | Team PAY [3] | 1
Full Service
21 | IT Architectuur | 5FS | FS36 | 2018-09-27 | 2018-10-23 | 19d | Main Project Worker [3]; IT Architecture [1]; Front Office [2]; Billing [1]; Team Helpdesk [1]; Team PAY [2] | 27
22 | Aangifte van social risico's | 15FS | FS24 | 2018-12-21 | 2019-01-17 | 14d | Billing [4] | 28
23 | Boekhouding | 18FS | FS34 | 2018-11-23 | 2018-12-06 | 10d | Main Project Worker [2]; IT Architecture [3]; Team PAY [2] | 14
24 | Non-functionals | 22FS,28FS | FS36 | 2019-01-18 | 2019-01-21 | 2d | Main Project Worker [2]; IT Architecture [3]; Team PAY [2] | 4
25 | Belcotax | 17FS | FS36 | 2018-11-16 | 2018-12-06 | 15d | Main Project Worker [2]; IT Architecture [7] | 21
26 | Bruto bepalingen | 8FS,16FS | FS27 | 2018-11-22 | 2018-11-27 | 4d | Main Project Worker [2]; Team PAY [4] | 6
27 | Netto bepalingen | 26FS | FS36 | 2018-11-28 | 2018-12-20 | 17d | Main Project Worker [2]; Team PAY [4] | 23
28 | Bedrijfsvoorheffing | 17FS | FS24 | 2018-11-16 | 2018-12-05 | 14d | Main Project Worker [2]; IT Architecture [4]; Front Office [1]; Team PAY [2] | 20
29 | Multifunctionele aangifte | 15FS | FS36 | 2018-12-21 | 2019-01-22 | 23d | Main Project Worker [3]; Billing [7]; Team PAY [3] | 34
30 | Loonbepaling 1.1 | 6FS | FS31 | 2018-10-25 | 2018-10-31 | 5d | Team PAY [3] | 7
31 | Loonbepaling 1.2 | 30FS | FS36 | 2018-11-01 | 2019-01-18 | 57d | Main Project Worker [2]; IT Architecture [2]; Front Office [2]; Billing [2]; Team Helpdesk [2]; Team PAY [7] | 79
32 | Loonbetalingen en loonbrieven | 16FS | FS36 | 2018-11-22 | 2018-12-11 | 14d | Main Project Worker [2]; IT Architecture [1]; Front Office [2]; Billing [2]; Team Helpdesk [1]; Team PAY [7] | 20
33 | Pay motor rapportering | 20FS | FS34 | 2019-01-02 | 2019-01-02 | 1d | Team PAY [2] | 1
34 | Calculation motor rapportering | 23FS,33FS | FS36 | 2019-01-03 | 2019-01-15 | 9d | Team PAY [4] | 13
35 | User Interface | 9FS | FS36 | 2018-10-23 | 2018-11-16 | 19d | Main Project Worker [1]; Front Office [2]; Software Engineer [4]; Team PAY [1] | 24
36 | Software Project for pay/calculation-motor | 14FS,21FS,24FS,25FS,27FS,39FS,31FS,32SF,34FS,35FS |  | 2019-01-22 | 2019-01-22 | / |  | 0

## Resources
General |  |  | Skill Distribution | [7 empty] | Skill Demand
ID | Name(generated) | Type | Main Project Worker | IT Architecture | Front office | Billing | Software Engineer | Team helpdesk | Marketing | Team PAY | Assigned to
1 | John Baker | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Luke Morgan | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Nicholas Barnes | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Derek Roberts | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Sofia Ferguson | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Michelle Cooper | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Sawyer Barrett | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Alfred Brooks | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Melanie Scott | Renewable | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
10 | Maddie Stevens | Renewable | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
11 | Alexia Payne | Renewable | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
12 | Brooke Thompson | Renewable | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
13 | Mike Parker | Renewable | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
14 | Adam Richardson | Renewable | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
15 | Lilianna Riley | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
16 | Stuart Perkins | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
17 | Aston Thomas | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
18 | Annabella Baker | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
19 | Olivia Clark | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
20 | Chester Holmes | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
21 | Alford Jones | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
22 | Carl Craig | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
23 | Carina Clark | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
24 | Edgar Stevens | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
25 | Kristian Kelley | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
26 | Martin Fowler | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
27 | James Kelley | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
28 | Sophia Harris | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
29 | Kelvin Jones | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
30 | Myra Mitchell | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
31 | Samantha Crawford | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
32 | Aston Sullivan | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
33 | Deanna Anderson | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
34 | Dominik Harris | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
35 | Daisy Elliott | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
36 | Maya Rogers | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
37 | Charlotte Roberts | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
38 | Alissa Campbell | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
39 | Victor Jones | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
40 | David Harper | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
41 | Kevin Carter | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
42 | Ned Carroll | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
43 | Kristian Murray | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
44 | Alina Robinson | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
45 | Leonardo Hall | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
46 | Isabella Riley | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
47 | Honey Montgomery | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
48 | Miley Richardson | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
49 | Frederick Lloyd | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
50 | Valeria Hunt | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
51 | Adam Howard | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
52 | Amber Gibson | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
53 | Blake Dixon | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
54 | Miranda Wright | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
55 | Carlos Stevens | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
56 | Melanie Crawford | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
57 | Tiana Ellis | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
58 | Kirsten Thompson | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
59 | Penelope Cameron | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
60 | Maria Miller | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
61 | Brooke Murray | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
62 | Myra Ross | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
63 | Freddie Walker | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
64 | Justin Baker | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
65 | Cadie Chapman | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
66 | Kevin Ellis | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
67 | Nicholas Hawkins | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
68 | Fiona Gibson | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
69 | Charlie Owens | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
70 | Victoria Chapman | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
71 | Connie Hamilton | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
72 | Nicholas Jones | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
73 | Melissa Elliott | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  | 8 | 6 | 13 | 8 | 9 | 6 | 15 | 8