## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Demand
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Skill Demand | Baseline duration (in calendar days)
1 | ETCS1-FS_L10 |  | FS8 | 2016-02-01 | 2016-02-01 | / |  | 0
2 | Project Charter | 8FS | FS3,FS5 | 2016-02-02 | 2016-02-03 | 2d | Project Manager [1] | 2
3 | Preparation SRS, study & order & measurements | 2FS | FS4,FS7,FS14 | 2016-02-04 | 2016-02-05 | 2d | Project Manager [1] | 2
4 | Verify Signaling Plans | 3FS | FS63 | 2016-02-08 | 2016-02-08 | 1d | Safety Manager [1] | 1
5 | Complete Scoping Document | 2FS | FS6,FS9,FS10,FS15 | 2016-02-04 | 2016-02-24 | 15d | Project Engineer ETCS [1]; System Engineer [1] | 21
6 | Create RSR (system requirement specification - draft) | 5FS | FS63 | 2016-02-25 | 2016-03-17 | 15d | Project Engineer ETCS [1] | 21
7 | Design Signals to equip (+mounting template) | 3FS | FS13 | 2016-02-08 | 2016-03-28 | 33d | Project Engineer ETCS [1] | 49
8 | Hardware study | 1FS | FS2 | 2016-02-01 | 2016-02-01 | 1d | Project Manager [1] | 1
9 | Fill out mounting template (supply part) | 5FS | FS13 | 2016-02-25 | 2016-03-25 | 21d | Project Engineer ETCS [1]; System Engineer [1] | 29
10 | Create Basic Data | 5FS | FS63 | 2016-02-25 | 2016-02-25 | 1d | Project Engineer ETCS [1] | 1
11 | Prepare Measurement Campaign | 20FS | FS12 | 2016-06-13 | 2016-07-25 | 30d | Safety Manager [1] | 43
12 | Measurement Campaign | 11FS | FS29 | 2016-07-25 | 2016-07-25 | 1d | Project Manager [1] | 1
13 | Produce Census Elements List | 7FS,9FS | FS63 | 2016-03-28 | 2016-05-02 | 23d | Project Manager [1] | 35
14 | Create Safety Plan | 3FS | FS16,FS17,FS18 | 2016-02-06 | 2016-04-29 | 64d | Project Engineer ETCS [1] | 83
15 | Create SRS (System requirements specification - final) | 5FS | FS36 | 2016-02-25 | 2016-03-10 | 10d | Project Engineer ETCS [1] | 14
16 | Verify & Finalize SRS | 14FS | FS63 | 2016-04-29 | 2016-05-13 | 10d | Project Engineer ETCS [1]; System Engineer [1] | 15
17 | SRS/ETCS Design Verification | 14FS | FS63 | 2016-04-29 | 2016-05-09 | 5d | Project Engineer ETCS [1] | 11
18 | Produce Layout Plan | 14FS | FS19,FS20 | 2016-04-29 | 2016-05-30 | 21d | Project Engineer ETCS [1] | 32
19 | Verify Layout Plan | 18FS | FS22,FS25,FS26,FS27 | 2016-05-30 | 2016-06-20 | 13d | Project Engineer ETCS [1] | 22
20 | Produce Measuring Plan | 18FS | FS11,FS21 | 2016-05-30 | 2016-06-13 | 10d | Project Engineer ETCS [1] | 15
21 | Carry out/Correct Measurements | 20FS | FS63 | 2016-06-13 | 2016-06-20 | 5d | Project Engineer ETCS [1] | 8
22 | Verify Measuring Results | 19FS | FS23 | 2016-06-20 | 2016-06-28 | 6d | System Engineer [1] | 9
23 | Execute Elements SI position analysis | 22FS | FS24 | 2016-06-28 | 2016-07-26 | 20d | System Engineer [1] | 29
24 | Produce TOPO plan | 23FS | FS29 | 2016-07-26 | 2016-08-02 | 5d | Project Engineer ETCS [1] | 8
25 | Verify TOPO PLN | 19FS | FS28 | 2016-06-20 | 2016-06-29 | 7d | Project Engineer ETCS [1] | 10
26 | Produce/correct Speed Plan | 19FS | FS28 | 2016-06-20 | 2016-07-04 | 10d | Project Engineer ETCS [2] | 15
27 | Verify Speed Plan | 19FS | FS28,FS29 | 2016-06-20 | 2016-07-01 | 9d | Project Engineer ETCS [2] | 12
28 | Import/correct Gradient LST | 25FS,26FS,27FS | FS63 | 2016-07-05 | 2016-07-08 | 4d | Project Engineer ETCS [1]; System Engineer [1] | 4
29 | Verify Gradient LST | 27FS | FS30,FS37 | 2016-07-05 | 2016-07-06 | 2d | Project Engineer ETCS [1] | 2
30 | Approve & store documents (layout plan, topo plan, speed plan, gradient plan) | 29FS | FS31,FS32,FS33 | 2016-07-07 | 2016-07-21 | 10d | Safety Manager [1] | 15
31 | Prepare ETCS FORM 3 | 30FS | FS63 | 2016-07-22 | 2016-08-31 | 28d | Safety Manager [1] | 41
32 | Realize preliminary analysis (design report part 1) | 30FS | FS35,FS36 | 2016-07-22 | 2016-09-07 | 33d | Safety Manager [1] | 48
33 | Prepare ETCS part of route table | 30FS | FS34 | 2016-07-22 | 2016-07-22 | 1d | Project Manager [1] | 1
34 | Review ETCS Part Route Tables | 33FS | FS40 | 2016-07-25 | 2016-09-12 | 35d | System Engineer [1]; Team Signaling [6] | 50
35 | Create ETCS INST PLN/ETCS FORM3 | 32SF | FS63 | 2016-09-08 | 2016-09-16 | 6d | Field Worker [1] | 9
36 | Route table size analysis | 32FS | FS63 | 2016-09-08 | 2016-09-15 | 5d | Team Signaling [6]; Field Worker [1] | 8
37 | Piquetage | 29FS | FS38,FS41,FS42,FS44 | 2016-07-07 | 2016-09-16 | 51d | Software Engineer [1] | 72
38 | 5.7.1.1. Finalize/correct ETCS-part of route table | 37FS | FS39 | 2016-09-19 | 2016-10-04 | 11d | System Engineer [1] | 16
39 | 5.7.1.2. Verify ETCS part of route table | 38FS | FS40 | 2016-10-05 | 2016-10-14 | 7d | Technical Sector Chef [1]; Field Worker [1] | 10
40 | 5.7.1.3. Lock ETCS part of route table | 39FS | FS45 | 2016-10-17 | 2016-10-17 | 1d | System Engineer [1] | 1
41 | 5.7.2.1. Export route table | 37FS | FS43 | 2016-09-19 | 2016-09-21 | 3d | Project Engineer ETCS [1] | 3
42 | 5.7.2.3. Verify IL-part of route table | 37FS | FS45 | 2016-09-19 | 2016-10-03 | 10d | Project Engineer ETCS [1] | 15
43 | 5.7.2.4. Lock IL-part of route table | 41FS | FS63 | 2016-09-22 | 2016-10-13 | 15d | Project Engineer ETCS [1] | 22
44 | 6 Create SRS IL | 37FS | FS48 | 2016-09-19 | 2016-10-03 | 10d | Safety Manager [1]; Project Engineer ETCS [1] | 15
45 | S.2. VRF SRS & VRF SPRL | 42FS | FS46 | 2016-10-04 | 2016-10-05 | 2d | Team Signaling [6]; Technical Sector Chef [1] | 2
46 | 9. Engineering ETCS | 45FS | FS47,FS48 | 2016-10-06 | 2016-10-07 | 2d | System Engineer [1]; Team Signaling [6]; Technical Sector Chef [1] | 2
47 | 11. Update elements SI position (incl 30i adaptation) + SI NLS RPT | 46FS | FS63 | 2016-10-10 | 2016-10-11 | 2d | Project Engineer ETCS [1] | 2
48 | Data Prep - Safety test validation modification | 46FS | FS49 | 2016-10-10 | 2016-10-18 | 7d | Project Engineer ETCS [1] | 9
49 | S.7. HZRD LOG RPT | 48FS | FS50 | 2016-10-19 | 2016-10-20 | 2d | Project Engineer ETCS [1] | 2
50 | S.3. SRS VRF Update | 49FS | FS51,FS54 | 2016-10-21 | 2016-10-25 | 3d | Project Engineer ETCS [1] | 5
51 | S.9. SASC Update (installation) | 50FS | FS52,FS53,FS56 | 2016-10-26 | 2016-10-26 | 1d | Safety Manager [1] | 1
52 | S.2. ProcProd Update Draft | 51FS | FS63 | 2016-10-27 | 2016-11-04 | 7d | Safety Manager [1] | 9
53 | Creation of commissioning plan | 51FS | FS55 | 2016-10-27 | 2016-11-04 | 7d | Safety Manager [1]; Quality Manager [1] | 9
54 | 22. Download LEU & Balise Files | 50FS | FS55 | 2016-10-26 | 2016-10-26 | 1d | Safety Manager [1] | 1
55 | 23. ETCS integration tests | 53FS,54FS | FS63 | 2016-11-07 | 2016-11-07 | 1d | Project Manager [1] | 1
56 | Mounting (LEU) + (balies) | 51FS | FS57,FS59 | 2016-10-27 | 2016-12-08 | 30d | Safety Manager [1]; Team Signaling [6]; Technical Sector Chef [1] | 43
57 | Mounting (Modify IL) | 56FS | FS58 | 2016-12-09 | 2016-12-30 | 15d | Project Engineer ETCS [1]; Field Worker [1] | 22
58 | Modification 019-plans & Create draft S-interface plans | 57FS | FS60 | 2017-01-02 | 2017-01-23 | 15d | Team Signaling [3]; Technical Sector Chef [1] | 22
59 | Commissioning for ETCS validation | 56FS | FS60 | 2016-12-09 | 2017-03-06 | 60d | Safety Manager [1] | 90
60 | On Site | 58FS,59FS | FS61 | 2017-03-07 | 2017-03-20 | 10d | Project Manager [1] | 14
61 | SASC final | 60FS | FS62 | 2017-03-21 | 2017-04-06 | 10d | Project Manager [1] | 17
62 | Commissioning | 61FS | FS63 | 2017-04-06 | 2017-07-06 | 45d | Project Manager [1] | 92
63 | ETCS1-FS_L10 | 62FS |  | 2017-07-06 | 2017-07-06 | /

## Resources
General |  |  | Skill Distribution | [8 empty] | Skill Demand
ID | Name(generated) | Type | Safety Manager | Quality Manager | Project Manager | Project Engineer ETCS | System Engineer | Software Engineer | Team Signaling | Technical Sector Chef | Field Worker | Assigned to
1 | Richard Holmes | Renewable | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Alisa Montgomery | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Alissa Harrison | Renewable | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Andrew Stewart | Renewable | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Thomas Miller | Renewable | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
6 | Charlotte Clark | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
7 | Haris Harper | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
8 | Jessica Cameron | Renewable | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
9 | Julia Turner | Renewable | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
10 | Alissa Wright | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
11 | Sarah Jones | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
12 | Belinda Richards | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
13 | Byron Brown | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
14 | Honey Ferguson | Renewable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
15 | James Hill | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
16 | Steven Roberts | Renewable | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
17 | Justin Tucker | Renewable | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
18 | Elian Morgan | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
19 | Natalie Murphy | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
20 | Abigail Ross | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
21 | Samantha Walker | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
22 | Vincent Murray | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
23 | Preston Dixon | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
24 | Agata Hawkins | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
25 | Dominik Murray | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
26 | Sydney Barnes | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
27 | Adele Miller | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
28 | Patrick Johnston | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
29 | Kimberly Adams | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
30 | Kevin Rogers | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
31 | Haris Taylor | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
32 | Olivia Harper | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
33 | Adelaide Cole | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
34 | Olivia Owens | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
35 | Sophia Harper | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
36 | Isabella Crawford | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
37 | Amy Gibson | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
38 | Brooke Hall | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
39 | Eddy Ellis | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
40 | Maya Brown | Renewable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  | 3 | 1 | 2 | 9 | 3 | 2 | 24 | 2 | 2