## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Demand
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Skill Demand | Baseline duration (in calendar days)
1 | Merelbeke-Melle |  | FS2 | 2019-11-19 08:00 | 2019-11-19 08:00 | /
2 | Voorbereiden | 1FS | FS3,FS4 | 2019-11-19 08:00 | 2019-11-20 17:00 | 2d | Kraanbestuurder [1]; Chauffeur [1]; Spoorwegarbeider [1] | 2
3 | Spoor losmaken (met de hand) | FS2 | FS5 | 2019-11-21 08:00 | 2019-11-21 17:00 | 1d | Spoorwegarbeider [3] | 1
4 | Rails plaatsen | FS2 | FS6 | 2019-11-22 08:00 | 2019-11-25 17:00 | 2d | Kraanbestuurder [2]; Spoorwegarbeider [5] | 4
5 | Laswerk | FS3 | FS7,FS8 | 2019-11-26 08:00 | 2019-11-27 17:00 | 2d | Lasser [2] | 2
6 | Rails verplaatsen | FS4 | FS9 | 2019-11-28 08:00 | 2019-11-29 17:00 | 2d | Kraanbestuurder [2]; Spoorwegarbeider [5] | 2
7 | Laswerk | FS5 | FS9 | 2019-12-02 08:00 | 2019-12-03 17:00 | 2d | Lasser [2] | 2
8 | Ballast lossen | FS5 | FS9 | 2019-12-04 08:00 | 2019-12-04 17:00 | 1d | Kraanbestuurder [2] | 1
9 | Dwarsliggers plaatsen | FS6,FS7,FS8 | FS10,FS11 | 2019-12-04 23:00 | 2019-12-06 04:00 | 2d (2 nachten) | Kraanbestuurder [2]; Chauffeur [1]; Spoorwegarbeider [4] | 2
10 | Afvoer Materiaal | FS9 | FS12 | 2019-12-06 08:00 | 2019-12-10 17:00 | 3d | Chauffeur [1] | 5
11 | Onderstoppen | FS9 | FS12 | 2019-12-10 23:00 | 2019-12-12 04:00 | 2d (2 nachten) | Machinewerker [1] | 2
12 | Spanningsregelen en Opruimwerk | FS10,FS11 | FS13 | 2019-12-12 08:00 | 2019-12-16 17:00 | 3d | Spoorwegarbeider [6] | 5
13 | Merelbeke-Melle | FS12 |  | 2019-12-16 17:00 | 2019-12-16 17:00 | /

## Resources
General |  |  | Skill Distribution |  |  |  |  | Skill Demand
ID | Name(generated) | Type | Kraanbestuurder | Chauffeur | Spoorwegarbeider | Machinewerker | Lasser | Assigned to
1 | Albert Cooper | Renewable | 0 | 0 | 1 | 0 | 0
2 | Oliver Foster | Renewable | 0 | 1 | 1 | 0 | 0
3 | Kate Harrison | Renewable | 1 | 1 | 0 | 0 | 0
4 | Dominik Andrews | Renewable | 0 | 0 | 1 | 0 | 0
5 | Grace Murray | Renewable | 1 | 1 | 0 | 0 | 0
6 | Maddie Thompson | Renewable | 1 | 1 | 0 | 0 | 0
7 | Valeria Williams | Renewable | 1 | 1 | 0 | 0 | 0
8 | George Farrell | Renewable | 0 | 0 | 1 | 0 | 0
9 | Jared Perry | Renewable | 1 | 0 | 0 | 0 | 0
10 | Aldus Spencer | Renewable | 0 | 0 | 1 | 0 | 0
11 | Elise Spencer | Renewable | 1 | 0 | 0 | 0 | 0
12 | Eddy Kelly | Renewable | 0 | 1 | 1 | 0 | 0
13 | Wilson Craig | Renewable | 0 | 0 | 1 | 0 | 0
14 | Sydney Stevens | Renewable | 0 | 0 | 1 | 0 | 0
15 | Adrianna Fowler | Renewable | 1 | 1 | 1 | 0 | 0
16 | Daryl Brown | Renewable | 0 | 0 | 1 | 0 | 0
17 | Victor Armstrong | Renewable | 0 | 1 | 1 | 0 | 1
18 | Martin Harrison | Renewable | 0 | 0 | 1 | 0 | 1
19 | Catherine Craig | Renewable | 0 | 0 | 1 | 0 | 0
20 | Kimberly Harrison | Renewable | 0 | 0 | 1 | 0 | 1
21 | Elise Tucker | Renewable | 0 | 0 | 1 | 0 | 0
22 | Alford Bailey | Renewable | 0 | 1 | 1 | 0 | 0
23 | Tony Payne | Renewable | 0 | 1 | 1 | 0 | 0
24 | Eric Parker | Renewable | 0 | 1 | 1 | 0 | 0
25 | Jasmine Ross | Renewable | 0 | 0 | 0 | 1 | 0
|  |  | 7 | 11 | 18 | 1 | 3