## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Social Housing Kortrijk | 1 |  |  | 2011-01-03 08:00 | 2012-01-23 17:00 | 276d |  |  | 0 |  |  | 366456.5 | 385.375
1 | Goedkope Woning Kortrijk | 1.1 |  |  | 2011-01-03 08:00 | 2012-01-23 17:00 | 276d |  |  | 0 |  |  | 366456.5 | 385.375
2 | Afbraakwerken | 1.1.1 |  | FS3 | 2011-01-03 08:00 | 2011-02-04 17:00 | 25d |  | 0 | 0 | 0 | 0 | 0 | 32.375
3 | Bronbemaling | 1.1.2 | 2FS | FF11 | 2011-02-07 08:00 | 2011-06-24 17:00 | 100d |  | 0 | 0 | 0 | 0 | 0 | 137.375
5 | BlokA | 1.1.3 |  |  | 2011-01-03 08:00 | 2012-01-23 17:00 | 276d |  |  | 0 |  |  | 215034.5 | 385.375
6 | Ruwbouw | 1.1.3.1 |  |  | 2011-01-03 08:00 | 2012-01-23 17:00 | 276d |  |  | 0 |  |  | 215034.5 | 385.375
7 | Grondwerken | 1.1.3.1.1 |  | FS9;FS10;FS12;FS77 | 2011-01-03 08:00 | 2011-01-14 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
8 | Funderingswerken | 1.1.3.1.2 |  |  | 2011-01-17 08:00 | 2011-06-24 17:00 | 115d |  |  | 0 |  |  | 5845 | 158.375
9 | Funderingsbalken | 1.1.3.1.2.1 | 7FS | FS11 | 2011-02-18 08:00 | 2011-03-09 17:00 | 14d | KRAAN | 2450 | 0 | 0 | 0 | 2450 | 19.375
10 | paalkoppen | 1.1.3.1.2.2 | 7FS | FS11 | 2011-01-17 08:00 | 2011-02-03 17:00 | 14d | KRAAN[0.10 #2] | 245 | 0 | 0 | 0 | 245 | 17.375
11 | plaatfundering | 1.1.3.1.2.3 | 9FS;10FS;3FF | FS15 | 2011-06-14 08:00 | 2011-06-24 17:00 | 9d | KRAAN | 1575 | 0 | 0 | 0 | 1575 | 10.375
12 | liftput | 1.1.3.1.2.4 | 7FS |  | 2011-01-17 08:00 | 2011-01-27 17:00 | 9d | KRAAN | 1575 | 0 | 0 | 0 | 1575 | 10.375
13 | Niveau gelijkvloers | 1.1.3.1.3 |  |  | 2011-06-27 08:00 | 2011-08-02 17:00 | 27d |  |  | 0 |  |  | 39638 | 36.375
14 | Beton en opgaand metselwerk | 1.1.3.1.3.1 |  |  | 2011-06-27 08:00 | 2011-08-02 17:00 | 27d |  |  | 0 |  |  | 39638 | 36.375
15 | Landmeter | 1.1.3.1.3.1.1 | 11FS | FS16 | 2011-06-27 08:00 | 2011-06-27 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
16 | aftekenen muren | 1.1.3.1.3.1.2 | 15FS | FS17 | 2011-06-28 08:00 | 2011-06-28 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
17 | Kimmen | 1.1.3.1.3.1.3 | 16FS | SS18+2d | 2011-06-29 08:00 | 2011-07-08 17:00 | 8d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 8332 | 0 | 0 | 0 | 8332 | 9.375
18 | Lijmen | 1.1.3.1.3.1.4 | 17SS+2d | FS19;FS20;FS21 | 2011-07-01 08:00 | 2011-07-14 17:00 | 10d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 10415 | 0 | 0 | 0 | 10415 | 13.375
19 | Bekisten betonbalken | 1.1.3.1.3.1.5 | 18FS | FS22 | 2011-07-15 08:00 | 2011-07-21 17:00 | 5d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 5557.5 | 0 | 0 | 0 | 5557.5 | 6.375
20 | Schoren en doka's | 1.1.3.1.3.1.6 | 18FS | FS22 | 2011-07-15 08:00 | 2011-07-21 17:00 | 5d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 5207.5 | 0 | 0 | 0 | 5207.5 | 6.375
21 | Plaatsen betonwanden | 1.1.3.1.3.1.7 | 18FS | FS22 | 2011-07-22 08:00 | 2011-07-25 17:00 | 2d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 2223 | 0 | 0 | 0 | 2223 | 3.375
22 | Predallen | 1.1.3.1.3.1.8 | 21FS;20FS;19FS | FS23 | 2011-07-26 08:00 | 2011-07-27 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
23 | Terrassen en luifels | 1.1.3.1.3.1.9 | 22FS | FS24 | 2011-07-28 08:00 | 2011-07-29 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
24 | Vlechten wapening | 1.1.3.1.3.1.10 | 23FS | FS26 | 2011-08-01 08:00 | 2011-08-02 17:00 | 2d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 2595 | 0 | 0 | 0 | 2595 | 1.375
25 | Niveau +1 | 1.1.3.1.4 |  |  | 2011-08-03 08:00 | 2011-09-09 17:00 | 28d |  |  | 0 |  |  | 41942 | 37.375
26 | storten vloerplaat | 1.1.3.1.4.1 | 24FS | FS27 | 2011-08-03 08:00 | 2011-08-03 17:00 | 1d | Arbeiders[5.00 #8] | 1280 | 0 | 0 | 0 | 1280 | 0.375
27 | Landmeter | 1.1.3.1.4.2 | 26FS | FS28 | 2011-08-04 08:00 | 2011-08-04 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
28 | aftekenen muren | 1.1.3.1.4.3 | 27FS | FS29 | 2011-08-05 08:00 | 2011-08-05 17:00 | 1d | Arbeiders[4.00 #8] | 1024 | 0 | 0 | 0 | 1024 | 0.375
29 | Kimmen | 1.1.3.1.4.4 | 28FS | SS30+2d | 2011-08-08 08:00 | 2011-08-17 17:00 | 8d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 8332 | 0 | 0 | 0 | 8332 | 9.375
30 | Lijmen | 1.1.3.1.4.5 | 29SS+2d | FS31;FS32;FS33 | 2011-08-10 08:00 | 2011-08-23 17:00 | 10d | Arbeiders[4.00 #8];KRAAN[0.10 #2] | 10415 | 0 | 0 | 0 | 10415 | 13.375
31 | Bekisten betonbalken | 1.1.3.1.4.6 | 30FS | FS34 | 2011-08-24 08:00 | 2011-08-30 17:00 | 5d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 5557.5 | 0 | 0 | 0 | 5557.5 | 6.375
32 | Schoren en doka's | 1.1.3.1.4.7 | 30FS | FS34 | 2011-08-24 08:00 | 2011-08-30 17:00 | 5d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 5207.5 | 0 | 0 | 0 | 5207.5 | 6.375
33 | Plaatsen betonwanden | 1.1.3.1.4.8 | 30FS | FS34 | 2011-08-31 08:00 | 2011-09-01 17:00 | 2d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 2223 | 0 | 0 | 0 | 2223 | 1.375
34 | Predallen | 1.1.3.1.4.9 | 33FS;32FS;31FS | FS35 | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 3.375
35 | Terrassen en luifels | 1.1.3.1.4.10 | 34FS | FS36 | 2011-09-06 08:00 | 2011-09-07 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
36 | Vlechten wapening | 1.1.3.1.4.11 | 35FS | FS38 | 2011-09-08 08:00 | 2011-09-09 17:00 | 2d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 2595 | 0 | 0 | 0 | 2595 | 1.375
37 | Niveau +2 | 1.1.3.1.5 |  |  | 2011-09-12 08:00 | 2011-10-19 17:00 | 28d |  |  | 0 |  |  | 41942 | 37.375
38 | storten vloerplaat | 1.1.3.1.5.1 | 36FS | FS39 | 2011-09-12 08:00 | 2011-09-12 17:00 | 1d | Arbeiders[5.00 #8] | 1280 | 0 | 0 | 0 | 1280 | 0.375
39 | Landmeter | 1.1.3.1.5.2 | 38FS | FS40 | 2011-09-13 08:00 | 2011-09-13 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
40 | aftekenen muren | 1.1.3.1.5.3 | 39FS | FS41 | 2011-09-14 08:00 | 2011-09-14 17:00 | 1d | Arbeiders[4.00 #8] | 1024 | 0 | 0 | 0 | 1024 | 0.375
41 | Kimmen | 1.1.3.1.5.4 | 40FS | SS42+2d | 2011-09-15 08:00 | 2011-09-26 17:00 | 8d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 8332 | 0 | 0 | 0 | 8332 | 11.375
42 | Lijmen | 1.1.3.1.5.5 | 41SS+2d | FS43;FS44;FS45 | 2011-09-19 08:00 | 2011-09-30 17:00 | 10d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 10415 | 0 | 0 | 0 | 10415 | 11.375
43 | Bekisten betonbalken | 1.1.3.1.5.6 | 42FS | FS46 | 2011-10-03 08:00 | 2011-10-07 17:00 | 5d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 5557.5 | 0 | 0 | 0 | 5557.5 | 4.375
44 | Schoren en doka's | 1.1.3.1.5.7 | 42FS | FS46 | 2011-10-03 08:00 | 2011-10-07 17:00 | 5d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 5207.5 | 0 | 0 | 0 | 5207.5 | 4.375
45 | Plaatsen betonwanden | 1.1.3.1.5.8 | 42FS | FS46 | 2011-10-10 08:00 | 2011-10-11 17:00 | 2d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 2223 | 0 | 0 | 0 | 2223 | 1.375
46 | Predallen | 1.1.3.1.5.9 | 45FS;43FS;44FS | FS47 | 2011-10-12 08:00 | 2011-10-13 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
47 | Terrassen en luifels | 1.1.3.1.5.10 | 46FS | FS48 | 2011-10-14 08:00 | 2011-10-17 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 3.375
48 | Vlechten wapening | 1.1.3.1.5.11 | 47FS | FS50 | 2011-10-18 08:00 | 2011-10-19 17:00 | 2d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 2595 | 0 | 0 | 0 | 2595 | 1.375
49 | Niveau +3 | 1.1.3.1.6 |  |  | 2011-10-20 08:00 | 2011-11-10 17:00 | 16d |  |  | 0 |  |  | 21372.5 | 21.375
50 | storten vloerplaat | 1.1.3.1.6.1 | 48FS | FS51 | 2011-10-20 08:00 | 2011-10-20 17:00 | 1d | Arbeiders[5.00 #8] | 1280 | 0 | 0 | 0 | 1280 | 0.375
51 | Landmeter | 1.1.3.1.6.2 | 50FS | FS52 | 2011-10-21 08:00 | 2011-10-21 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
52 | aftekenen muren | 1.1.3.1.6.3 | 51FS | FS53 | 2011-10-24 08:00 | 2011-10-24 17:00 | 1d | Arbeiders[4.00 #8] | 1024 | 0 | 0 | 0 | 1024 | 0.375
53 | Kimmen | 1.1.3.1.6.4 | 52FS | SS54+2d | 2011-10-25 08:00 | 2011-10-27 17:00 | 3d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 3124.5 | 0 | 0 | 0 | 3124.5 | 2.375
54 | Lijmen | 1.1.3.1.6.5 | 53SS+2d | FS55;FS56;FS57 | 2011-10-27 08:00 | 2011-11-01 17:00 | 4d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 4166 | 0 | 0 | 0 | 4166 | 5.375
55 | Bekisten betonbalken | 1.1.3.1.6.6 | 54FS | FS58 | 2011-11-02 08:00 | 2011-11-04 17:00 | 3d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 3334.5 | 0 | 0 | 0 | 3334.5 | 2.375
56 | Schoren en doka's | 1.1.3.1.6.7 | 54FS | FS58 | 2011-11-02 08:00 | 2011-11-04 17:00 | 3d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 3124.5 | 0 | 0 | 0 | 3124.5 | 2.375
57 | Plaatsen betonwanden | 1.1.3.1.6.8 | 54FS | FS58 | 2011-11-07 08:00 | 2011-11-07 17:00 | 1d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 1111.5 | 0 | 0 | 0 | 1111.5 | 0.375
58 | Predallen | 1.1.3.1.6.9 | 57FS;55FS;56FS | FS59 | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d | KRAAN;Arbeiders[4.00 #8] | 1199 | 0 | 0 | 0 | 1199 | 0.375
59 | Terrassen en luifels | 1.1.3.1.6.10 | 58FS | FS60 | 2011-11-09 08:00 | 2011-11-09 17:00 | 1d | KRAAN;Arbeiders[4.00 #8] | 1199 | 0 | 0 | 0 | 1199 | 0.375
60 | Vlechten wapening | 1.1.3.1.6.11 | 59FS | FS62 | 2011-11-10 08:00 | 2011-11-10 17:00 | 1d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 1297.5 | 0 | 0 | 0 | 1297.5 | 0.375
61 | Niveau +4 | 1.1.3.1.7 |  |  | 2011-11-11 08:00 | 2011-12-02 17:00 | 16d |  |  | 0 |  |  | 21116.5 | 21.375
62 | storten vloerplaat | 1.1.3.1.7.1 | 60FS | FS63 | 2011-11-11 08:00 | 2011-11-11 17:00 | 1d | Arbeiders[5.00 #8] | 1280 | 0 | 0 | 0 | 1280 | 0.375
63 | Landmeter | 1.1.3.1.7.2 | 62FS | FS64 | 2011-11-14 08:00 | 2011-11-14 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
64 | aftekenen muren | 1.1.3.1.7.3 | 63FS | FS65 | 2011-11-15 08:00 | 2011-11-15 17:00 | 1d | Arbeiders[4.00 #8] | 1024 | 0 | 0 | 0 | 1024 | 0.375
65 | Kimmen | 1.1.3.1.7.4 | 64FS | SS66+2d | 2011-11-16 08:00 | 2011-11-18 17:00 | 3d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 3124.5 | 0 | 0 | 0 | 3124.5 | 2.375
66 | Lijmen | 1.1.3.1.7.5 | 65SS+2d | FS67;FS68;FS69 | 2011-11-18 08:00 | 2011-11-23 17:00 | 4d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 4166 | 0 | 0 | 0 | 4166 | 5.375
67 | Bekisten betonbalken | 1.1.3.1.7.6 | 66FS | FS70 | 2011-11-24 08:00 | 2011-11-28 17:00 | 3d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 3334.5 | 0 | 0 | 0 | 3334.5 | 4.375
68 | Schoren en doka's | 1.1.3.1.7.7 | 66FS | FS70 | 2011-11-24 08:00 | 2011-11-28 17:00 | 3d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 3124.5 | 0 | 0 | 0 | 3124.5 | 4.375
69 | Plaatsen betonwanden | 1.1.3.1.7.8 | 66FS | FS70 | 2011-11-29 08:00 | 2011-11-29 17:00 | 1d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 1111.5 | 0 | 0 | 0 | 1111.5 | 0.375
70 | Predallen | 1.1.3.1.7.9 | 67FS;68FS;69FS | FS71 | 2011-11-30 08:00 | 2011-11-30 17:00 | 1d | KRAAN;Arbeiders[4.00 #8] | 1199 | 0 | 0 | 0 | 1199 | 0.375
71 | Terrassen en luifels | 1.1.3.1.7.10 | 70FS | FS72 | 2011-12-01 08:00 | 2011-12-01 17:00 | 1d | KRAAN;Arbeiders[4.00 #8] | 1199 | 0 | 0 | 0 | 1199 | 0.375
72 | Vlechten wapening | 1.1.3.1.7.11 | 71FS | FS73 | 2011-12-02 08:00 | 2011-12-02 17:00 | 1d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 1041.5 | 0 | 0 | 0 | 1041.5 | 0.375
73 | Dakwerken | 1.1.3.1.8 | 131FS;72FS | FS74 | 2011-12-05 08:00 | 2011-12-22 17:00 | 14d | KRAAN[0.20 #2];Arbeiders[4.00 #8] | 14826 | 0 | 0 | 0 | 14826 | 17.375
74 | Gevelbekleding | 1.1.3.1.9 | 73FS;132FS |  | 2011-12-23 08:00 | 2012-01-23 17:00 | 22d | KRAAN[0.05 #2];Arbeiders[5.00 #8] | 28352.5 | 0 | 0 | 0 | 28352.5 | 31.375
75 | Blok B | 1.1.4 |  |  | 2011-01-17 08:00 | 2011-11-02 17:00 | 208d |  |  | 0 |  |  | 151422 | 289.375
76 | Ruwbouw | 1.1.4.1 |  |  | 2011-01-17 08:00 | 2011-09-13 17:00 | 172d |  |  | 0 |  |  | 150739.5 | 239.375
77 | Grondwerken | 1.1.4.1.1 | 7FS | FS79;FS80;FS82 | 2011-01-17 08:00 | 2011-01-28 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
78 | Funderingswerken | 1.1.4.1.2 |  |  | 2011-01-31 08:00 | 2011-03-22 17:00 | 37d |  |  | 0 |  |  | 5845 | 50.375
79 | Funderingsbalken | 1.1.4.1.2.1 | 77FS | FS81 | 2011-01-31 08:00 | 2011-02-17 17:00 | 14d | KRAAN | 2450 | 0 | 0 | 0 | 2450 | 17.375
80 | paalkoppen | 1.1.4.1.2.2 | 77FS | FS81 | 2011-01-31 08:00 | 2011-02-17 17:00 | 14d | KRAAN[0.10 #2] | 245 | 0 | 0 | 0 | 245 | 17.375
81 | plaatfundering | 1.1.4.1.2.3 | 79FS;80FS | FS85 | 2011-02-18 08:00 | 2011-03-02 17:00 | 9d | KRAAN | 1575 | 0 | 0 | 0 | 1575 | 12.375
82 | liftput | 1.1.4.1.2.4 | 77FS |  | 2011-03-10 08:00 | 2011-03-22 17:00 | 9d | KRAAN | 1575 | 0 | 0 | 0 | 1575 | 12.375
83 | Niveau gelijkvloers | 1.1.4.1.3 |  |  | 2011-03-03 08:00 | 2011-04-08 17:00 | 27d |  |  | 0 |  |  | 39638 | 36.375
84 | Beton en opgaand metselwerk | 1.1.4.1.3.1 |  |  | 2011-03-03 08:00 | 2011-04-08 17:00 | 27d |  |  | 0 |  |  | 39638 | 36.375
85 | Landmeter | 1.1.4.1.3.1.1 | 81FS | FS86 | 2011-03-03 08:00 | 2011-03-03 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
86 | aftekenen muren | 1.1.4.1.3.1.2 | 85FS | FS87 | 2011-03-04 08:00 | 2011-03-04 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
87 | Kimmen | 1.1.4.1.3.1.3 | 86FS | SS88+2d | 2011-03-07 08:00 | 2011-03-16 17:00 | 8d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 8332 | 0 | 0 | 0 | 8332 | 9.375
88 | Lijmen | 1.1.4.1.3.1.4 | 87SS+2d | FS89;FS90;FS91 | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 10415 | 0 | 0 | 0 | 10415 | 13.375
89 | Bekisten betonbalken | 1.1.4.1.3.1.5 | 88FS | FS92 | 2011-03-23 08:00 | 2011-03-29 17:00 | 5d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 5557.5 | 0 | 0 | 0 | 5557.5 | 6.375
90 | Schoren en doka's | 1.1.4.1.3.1.6 | 88FS | FS92 | 2011-03-23 08:00 | 2011-03-29 17:00 | 5d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 5207.5 | 0 | 0 | 0 | 5207.5 | 6.375
91 | Plaatsen betonwanden | 1.1.4.1.3.1.7 | 88FS | FS92 | 2011-03-30 08:00 | 2011-03-31 17:00 | 2d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 2223 | 0 | 0 | 0 | 2223 | 1.375
92 | Predallen | 1.1.4.1.3.1.8 | 89FS;90FS;91FS | FS93 | 2011-04-01 08:00 | 2011-04-04 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 3.375
93 | Terrassen en luifels | 1.1.4.1.3.1.9 | 92FS | FS94 | 2011-04-05 08:00 | 2011-04-06 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
94 | Vlechten wapening | 1.1.4.1.3.1.10 | 93FS | FS96 | 2011-04-07 08:00 | 2011-04-08 17:00 | 2d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 2595 | 0 | 0 | 0 | 2595 | 1.375
95 | Niveau +1 | 1.1.4.1.4 |  |  | 2011-04-11 08:00 | 2011-05-18 17:00 | 28d |  |  | 0 |  |  | 41942 | 37.375
96 | storten vloerplaat | 1.1.4.1.4.1 | 94FS | FS97 | 2011-04-11 08:00 | 2011-04-11 17:00 | 1d | Arbeiders[5.00 #8] | 1280 | 0 | 0 | 0 | 1280 | 0.375
97 | Landmeter | 1.1.4.1.4.2 | 96FS | FS98 | 2011-04-12 08:00 | 2011-04-12 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
98 | aftekenen muren | 1.1.4.1.4.3 | 97FS | FS99 | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d | Arbeiders[4.00 #8] | 1024 | 0 | 0 | 0 | 1024 | 0.375
99 | Kimmen | 1.1.4.1.4.4 | 98FS | SS100+2d | 2011-04-14 08:00 | 2011-04-25 17:00 | 8d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 8332 | 0 | 0 | 0 | 8332 | 11.375
100 | Lijmen | 1.1.4.1.4.5 | 99SS+2d | FS101;FS102;FS103 | 2011-04-18 08:00 | 2011-04-29 17:00 | 10d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 10415 | 0 | 0 | 0 | 10415 | 11.375
101 | Bekisten betonbalken | 1.1.4.1.4.6 | 100FS | FS104 | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 5557.5 | 0 | 0 | 0 | 5557.5 | 4.375
102 | Schoren en doka's | 1.1.4.1.4.7 | 100FS | FS104 | 2011-05-02 08:00 | 2011-05-06 17:00 | 5d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 5207.5 | 0 | 0 | 0 | 5207.5 | 4.375
103 | Plaatsen betonwanden | 1.1.4.1.4.8 | 100FS | FS104 | 2011-05-09 08:00 | 2011-05-10 17:00 | 2d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 2223 | 0 | 0 | 0 | 2223 | 1.375
104 | Predallen | 1.1.4.1.4.9 | 101FS;102FS;103FS | FS105 | 2011-05-11 08:00 | 2011-05-12 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
105 | Terrassen en luifels | 1.1.4.1.4.10 | 104FS | FS106 | 2011-05-13 08:00 | 2011-05-16 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 3.375
106 | Vlechten wapening | 1.1.4.1.4.11 | 105FS | FS108 | 2011-05-17 08:00 | 2011-05-18 17:00 | 2d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 2595 | 0 | 0 | 0 | 2595 | 1.375
107 | Niveau +2 | 1.1.4.1.5 |  |  | 2011-05-19 08:00 | 2011-06-27 17:00 | 28d |  |  | 0 |  |  | 41942 | 39.375
108 | storten vloerplaat | 1.1.4.1.5.1 | 106FS | FS109 | 2011-05-19 08:00 | 2011-05-19 17:00 | 1d | Arbeiders[5.00 #8] | 1280 | 0 | 0 | 0 | 1280 | 0.375
109 | Landmeter | 1.1.4.1.5.2 | 108FS | FS110 | 2011-05-20 08:00 | 2011-05-20 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
110 | aftekenen muren | 1.1.4.1.5.3 | 109FS | FS111 | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | Arbeiders[4.00 #8] | 1024 | 0 | 0 | 0 | 1024 | 0.375
111 | Kimmen | 1.1.4.1.5.4 | 110FS | SS112+2d | 2011-05-24 08:00 | 2011-06-02 17:00 | 8d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 8332 | 0 | 0 | 0 | 8332 | 9.375
112 | Lijmen | 1.1.4.1.5.5 | 111SS+2d | FS113;FS114;FS115 | 2011-05-26 08:00 | 2011-06-08 17:00 | 10d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 10415 | 0 | 0 | 0 | 10415 | 13.375
113 | Bekisten betonbalken | 1.1.4.1.5.6 | 112FS | FS116 | 2011-06-09 08:00 | 2011-06-15 17:00 | 5d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 5557.5 | 0 | 0 | 0 | 5557.5 | 6.375
114 | Schoren en doka's | 1.1.4.1.5.7 | 112FS | FS116 | 2011-06-09 08:00 | 2011-06-15 17:00 | 5d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 5207.5 | 0 | 0 | 0 | 5207.5 | 6.375
115 | Plaatsen betonwanden | 1.1.4.1.5.8 | 112FS | FS116 | 2011-06-16 08:00 | 2011-06-17 17:00 | 2d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 2223 | 0 | 0 | 0 | 2223 | 1.375
116 | Predallen | 1.1.4.1.5.9 | 113FS;114FS;115FS | FS117 | 2011-06-20 08:00 | 2011-06-21 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
117 | Terrassen en luifels | 1.1.4.1.5.10 | 116FS | FS118 | 2011-06-22 08:00 | 2011-06-23 17:00 | 2d | KRAAN;Arbeiders[4.00 #8] | 2398 | 0 | 0 | 0 | 2398 | 1.375
118 | Vlechten wapening | 1.1.4.1.5.11 | 117FS | FS120 | 2011-06-24 08:00 | 2011-06-27 17:00 | 2d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 2595 | 0 | 0 | 0 | 2595 | 3.375
119 | Niveau +3 | 1.1.4.1.6 |  |  | 2011-06-28 08:00 | 2011-09-13 17:00 | 56d |  |  | 0 |  |  | 21372.5 | 77.375
120 | storten vloerplaat | 1.1.4.1.6.1 | 118FS | FS121 | 2011-06-28 08:00 | 2011-06-28 17:00 | 1d | Arbeiders[5.00 #8] | 1280 | 0 | 0 | 0 | 1280 | 0.375
121 | Landmeter | 1.1.4.1.6.2 | 120FS | FS122 | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Arbeiders[2.00 #8] | 512 | 0 | 0 | 0 | 512 | 0.375
122 | aftekenen muren | 1.1.4.1.6.3 | 121FS | FS123 | 2011-06-30 08:00 | 2011-06-30 17:00 | 1d | Arbeiders[4.00 #8] | 1024 | 0 | 0 | 0 | 1024 | 0.375
123 | Kimmen | 1.1.4.1.6.4 | 122FS | SS124+2d | 2011-07-11 08:00 | 2011-07-13 17:00 | 3d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 3124.5 | 0 | 0 | 0 | 3124.5 | 2.375
124 | Lijmen | 1.1.4.1.6.5 | 123SS+2d | FS125;FS126;FS127 | 2011-07-22 08:00 | 2011-07-27 17:00 | 4d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 4166 | 0 | 0 | 0 | 4166 | 5.375
125 | Bekisten betonbalken | 1.1.4.1.6.6 | 124FS | FS128 | 2011-08-18 08:00 | 2011-08-22 17:00 | 3d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 3334.5 | 0 | 0 | 0 | 3334.5 | 4.375
126 | Schoren en doka's | 1.1.4.1.6.7 | 124FS | FS128 | 2011-08-04 08:00 | 2011-08-08 17:00 | 3d | KRAAN[0.10 #2];Arbeiders[4.00 #8] | 3124.5 | 0 | 0 | 0 | 3124.5 | 4.375
127 | Plaatsen betonwanden | 1.1.4.1.6.8 | 124FS | FS128 | 2011-07-28 08:00 | 2011-07-28 17:00 | 1d | KRAAN[0.50 #2];Arbeiders[4.00 #8] | 1111.5 | 0 | 0 | 0 | 1111.5 | 0.375
128 | Predallen | 1.1.4.1.6.9 | 125FS;126FS;127FS | FS129 | 2011-08-23 08:00 | 2011-08-23 17:00 | 1d | KRAAN;Arbeiders[4.00 #8] | 1199 | 0 | 0 | 0 | 1199 | 0.375
129 | Terrassen en luifels | 1.1.4.1.6.10 | 128FS | FS130 | 2011-08-31 08:00 | 2011-08-31 17:00 | 1d | KRAAN;Arbeiders[4.00 #8] | 1199 | 0 | 0 | 0 | 1199 | 0.375
130 | Vlechten wapening | 1.1.4.1.6.11 | 129FS | FS131 | 2011-09-13 08:00 | 2011-09-13 17:00 | 1d | KRAAN[0.10 #2];Arbeiders[5.00 #8] | 1297.5 | 0 | 0 | 0 | 1297.5 | 0.375
131 | Dakwerken | 1.1.4.2 | 130FS | FS73;FS132 | 2011-09-14 08:00 | 2011-10-03 17:00 | 14d | KRAAN[0.20 #2] | 490 | 0 | 0 | 0 | 490 | 19.375
132 | Gevelbekleding | 1.1.4.3 | 131FS | FS74 | 2011-10-04 08:00 | 2011-11-02 17:00 | 22d | KRAAN[0.05 #2] | 192.5 | 0 | 0 | 0 | 192.5 | 29.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | KRAAN | Renewable | 2 kranen | 0 | 21.875 | 9;10[0.10 KRAAN];11;12;17[0.10 KRAAN];18[0.10 KRAAN];19[0.50 KRAAN];20[0.10 KRAAN];21[0.50 KRAAN];22;23;24[0.10 KRAAN];29[0.10 KRAAN];30[0.10 KRAAN];31[0.50 KRAAN];32[0.10 KRAAN];33[0.50 KRAAN];34;35;36[0.10 KRAAN];41[0.10 KRAAN];42[0.10 KRAAN];43[0.50 KRAAN];44[0.10 KRAAN];45[0.50 KRAAN];46;47;48[0.10 KRAAN];53[0.10 KRAAN];54[0.10 KRAAN];55[0.50 KRAAN];56[0.10 KRAAN];57[0.50 KRAAN];58;59;60[0.10 KRAAN];65[0.10 KRAAN];66[0.10 KRAAN];67[0.50 KRAAN];68[0.10 KRAAN];69[0.50 KRAAN];70;71;72[0.10 KRAAN];73[0.20 KRAAN];74[0.05 KRAAN];79;80[0.10 KRAAN];81;82;87[0.10 KRAAN];88[0.10 KRAAN];89[0.50 KRAAN];90[0.10 KRAAN];91[0.50 KRAAN];92;93;94[0.10 KRAAN];99[0.10 KRAAN];100[0.10 KRAAN];101[0.50 KRAAN];102[0.10 KRAAN];103[0.50 KRAAN];104;105;106[0.10 KRAAN];111[0.10 KRAAN];112[0.10 KRAAN];113[0.50 KRAAN];114[0.10 KRAAN];115[0.50 KRAAN];116;117;118[0.10 KRAAN];123[0.10 KRAAN];124[0.10 KRAAN];125[0.50 KRAAN];126[0.10 KRAAN];127[0.50 KRAAN];128;129;130[0.10 KRAAN];131[0.20 KRAAN];132[0.05 KRAAN]; | 26232.5
2 | Arbeiders | Renewable | 8 arbeiders | 0 | 32 | 16[2.00 Arbeiders];17[4.00 Arbeiders];18[4.00 Arbeiders];19[4.00 Arbeiders];20[4.00 Arbeiders];21[4.00 Arbeiders];22[4.00 Arbeiders];23[4.00 Arbeiders];24[5.00 Arbeiders];26[5.00 Arbeiders];27[2.00 Arbeiders];28[4.00 Arbeiders];29[4.00 Arbeiders];30[4.00 Arbeiders];31[4.00 Arbeiders];32[4.00 Arbeiders];33[4.00 Arbeiders];34[4.00 Arbeiders];35[4.00 Arbeiders];36[5.00 Arbeiders];38[5.00 Arbeiders];39[2.00 Arbeiders];40[4.00 Arbeiders];41[4.00 Arbeiders];42[4.00 Arbeiders];43[4.00 Arbeiders];44[4.00 Arbeiders];45[4.00 Arbeiders];46[4.00 Arbeiders];47[4.00 Arbeiders];48[5.00 Arbeiders];50[5.00 Arbeiders];51[2.00 Arbeiders];52[4.00 Arbeiders];53[4.00 Arbeiders];54[4.00 Arbeiders];55[4.00 Arbeiders];56[4.00 Arbeiders];57[4.00 Arbeiders];58[4.00 Arbeiders];59[4.00 Arbeiders];60[5.00 Arbeiders];62[5.00 Arbeiders];63[2.00 Arbeiders];64[4.00 Arbeiders];65[4.00 Arbeiders];66[4.00 Arbeiders];67[4.00 Arbeiders];68[4.00 Arbeiders];69[4.00 Arbeiders];70[4.00 Arbeiders];71[4.00 Arbeiders];72[4.00 Arbeiders];73[4.00 Arbeiders];74[5.00 Arbeiders];86[2.00 Arbeiders];87[4.00 Arbeiders];88[4.00 Arbeiders];89[4.00 Arbeiders];90[4.00 Arbeiders];91[4.00 Arbeiders];92[4.00 Arbeiders];93[4.00 Arbeiders];94[5.00 Arbeiders];96[5.00 Arbeiders];97[2.00 Arbeiders];98[4.00 Arbeiders];99[4.00 Arbeiders];100[4.00 Arbeiders];101[4.00 Arbeiders];102[4.00 Arbeiders];103[4.00 Arbeiders];104[4.00 Arbeiders];105[4.00 Arbeiders];106[5.00 Arbeiders];108[5.00 Arbeiders];109[2.00 Arbeiders];110[4.00 Arbeiders];111[4.00 Arbeiders];112[4.00 Arbeiders];113[4.00 Arbeiders];114[4.00 Arbeiders];115[4.00 Arbeiders];116[4.00 Arbeiders];117[4.00 Arbeiders];118[5.00 Arbeiders];120[5.00 Arbeiders];121[2.00 Arbeiders];122[4.00 Arbeiders];123[4.00 Arbeiders];124[4.00 Arbeiders];125[4.00 Arbeiders];126[4.00 Arbeiders];127[4.00 Arbeiders];128[4.00 Arbeiders];129[4.00 Arbeiders];130[5.00 Arbeiders]; | 340224

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Social Housing Kortrijk | 2208h |  |  |  |  | 99 | 100 | 101
1 | Goedkope Woning Kortrijk | 2208h |  |  |  |  | 99 | 100 | 101
2 | Afbraakwerken | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Bronbemaling | 800h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | BlokA | 2208h |  |  |  |  | 99 | 100 | 101
6 | Ruwbouw | 2208h |  |  |  |  | 99 | 100 | 101
7 | Grondwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Funderingswerken | 920h |  |  |  |  | 99 | 100 | 101
9 | Funderingsbalken | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | paalkoppen | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | plaatfundering | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | liftput | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Niveau gelijkvloers | 216h |  |  |  |  | 99 | 100 | 101
14 | Beton en opgaand metselwerk | 216h |  |  |  |  | 99 | 100 | 101
15 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Kimmen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Lijmen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Bekisten betonbalken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Schoren en doka's | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Plaatsen betonwanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Predallen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Terrassen en luifels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Vlechten wapening | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Niveau +1 | 224h |  |  |  |  | 99 | 100 | 101
26 | storten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Kimmen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Lijmen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Bekisten betonbalken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Schoren en doka's | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Plaatsen betonwanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Predallen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Terrassen en luifels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Vlechten wapening | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Niveau +2 | 224h |  |  |  |  | 99 | 100 | 101
38 | storten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Kimmen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Lijmen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Bekisten betonbalken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Schoren en doka's | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Plaatsen betonwanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Predallen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Terrassen en luifels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Vlechten wapening | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Niveau +3 | 128h |  |  |  |  | 99 | 100 | 101
50 | storten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Kimmen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Lijmen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Bekisten betonbalken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Schoren en doka's | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Plaatsen betonwanden | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Predallen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Terrassen en luifels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Vlechten wapening | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Niveau +4 | 128h |  |  |  |  | 99 | 100 | 101
62 | storten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Kimmen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Lijmen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Bekisten betonbalken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Schoren en doka's | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Plaatsen betonwanden | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Predallen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Terrassen en luifels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | Vlechten wapening | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Dakwerken | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Gevelbekleding | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | Blok B | 1664h |  |  |  |  | 99 | 100 | 101
76 | Ruwbouw | 1376h |  |  |  |  | 99 | 100 | 101
77 | Grondwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Funderingswerken | 296h |  |  |  |  | 99 | 100 | 101
79 | Funderingsbalken | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | paalkoppen | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | plaatfundering | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | liftput | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Niveau gelijkvloers | 216h |  |  |  |  | 99 | 100 | 101
84 | Beton en opgaand metselwerk | 216h |  |  |  |  | 99 | 100 | 101
85 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | Kimmen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | Lijmen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | Bekisten betonbalken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | Schoren en doka's | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Plaatsen betonwanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Predallen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Terrassen en luifels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | Vlechten wapening | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Niveau +1 | 224h |  |  |  |  | 99 | 100 | 101
96 | storten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | Kimmen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | Lijmen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | Bekisten betonbalken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | Schoren en doka's | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | Plaatsen betonwanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | Predallen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | Terrassen en luifels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | Vlechten wapening | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | Niveau +2 | 224h |  |  |  |  | 99 | 100 | 101
108 | storten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | Kimmen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | Lijmen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | Bekisten betonbalken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | Schoren en doka's | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | Plaatsen betonwanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | Predallen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | Terrassen en luifels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | Vlechten wapening | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | Niveau +3 | 448h |  |  |  |  | 99 | 100 | 101
120 | storten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | Landmeter | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | aftekenen muren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | Kimmen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | Lijmen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | Bekisten betonbalken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Schoren en doka's | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | Plaatsen betonwanden | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | Predallen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | Terrassen en luifels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | Vlechten wapening | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | Dakwerken | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Gevelbekleding | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold