## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Patient Transport System | 1 |  |  | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 | 544.375
50 | Description of staff's needs & Set-up | 1.1 |  |  | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 | 60.375
1 | Compose survey for the staff | 1.1.1 |  | FS2+1w 1d | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 0.16667
2 | Brainstorming and filling in the survey | 1.1.2 | 1FS+1w 1d | FS3+7w 2h | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 0.083333
3 | Collecting and analyzing the surveys | 1.1.3 | 2FS+7w 2h | FS4 | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 0.375
51 | Meeting ICT Committee | 1.2 |  |  | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 | 0.375
4 | Get-together PC, ICT committee & board | 1.2.1 | 3FS | FS5+2h | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 0.16667
5 | Enrollment of the meeting | 1.2.2 | 4FS+2h | FS6 | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 0.083333
52 | Set-up format specifications | 1.3 |  |  | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 | 43.375
6 | Registering the technical requirements | 1.3.1 | 5FS | FS7+2w | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 1.375
7 | Set-up a detailed budget study | 1.3.2 | 6FS+2w | FS8+3w | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 1.375
8 | Putting together the formal document | 1.3.3 | 7FS+3w | FS9;FS20+1w | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2.375
53 | Request proposal suppliers transport system | 1.4 |  |  | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 | 29.375
9 | Research suppliers transport systems | 1.4.1 | 8FS | FS10+1w 1d 4h | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2.375
10 | Meeting with board for final proposal | 1.4.2 | 9FS+1w 1d 4h | FS11+2w | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 0.16667
11 | Contacting suppliers and sending proposal | 1.4.3 | 10FS+2w | FS12+3w | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 1.375
54 | Decision supplier | 1.5 |  |  | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 | 99.375
12 | Analyzing the received offers | 1.5.1 | 11FS+3w | FS13+4w | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2.375
13 | Presentation to board & ICT staff | 1.5.2 | 12FS+4w | FS14+3w | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 0.375
14 | Collecting and registering comments on offers | 1.5.3 | 13FS+3w | FS15+6w | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 0.375
15 | Taking final decision and contacting supplier | 1.5.4 | 14FS+6w | FS16 | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 1.375
55 | Negociation conditions final supplier transport system | 1.6 |  |  | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 | 103.375
16 | Discussing project development with supplier | 1.6.1 | 15FS | FS17+7w 3d 4h | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 4.375
17 | Discussing project development with board | 1.6.2 | 16FS+7w 3d 4h | FS18+6w | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 0.16667
18 | Final agreement with supplier | 1.6.3 | 17FS+6w | FS19 | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 1.375
56 | Draw up & Sign contract with supplier transport system | 1.7 |  |  | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 | 0.16667
19 | Signing contract | 1.7.1 | 18FS | FS27+4d 4h | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 0.16667
57 | Request proposal supplier DACS | 1.8 |  |  | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 | 15.375
20 | Meeting with ICT committee | 1.8.1 | 8FS+1w | FS21+1w 2d | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 1.375
21 | Contacting Siemens and sending proposal | 1.8.2 | 20FS+1w 2d | FS22+2w | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 4.375
58 | Negociation conditions DACS | 1.9 |  |  | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 | 19.1667
22 | Discussing project development with supplier | 1.9.1 | 21FS+2w | FS23+1w | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 1.375
23 | Discussing progress with board | 1.9.2 | 22FS+1w | FS24+2d | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 0.083333
24 | Discussing progress with ICT committee | 1.9.3 | 23FS+2d | FS25+1d 6h | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 0.20833
25 | Final agreement with supplier | 1.9.4 | 24FS+1d 6h | FS26 | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 0.16667
59 | Draw up & Sign contract with supplier DACS | 1.10 |  |  | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 | 0.16667
26 | Signing contract | 1.10.1 | 25FS | FS27+8w | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 0.16667
60 | Kick-off Meeting | 1.11 |  |  | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 | 0.375
27 | Information session | 1.11.1 | 26FS+8w;19FS+4d 4h | FS28+4h | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 0.083333
28 | Explanation project implementation to staff | 1.11.2 | 27FS+4h | FS29;FS30;FS31;FS34 | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 0.083333
61 | Installation | 1.12 |  |  | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 | 7.375
29 | Installation transport system | 1.12.1 | 28FS | FS36 | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 7.375
30 | Installation DACS | 1.12.2 | 28FS | FS38;FS44 | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 7.375
62 | Training PC | 1.13 |  |  | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 | 162.375
31 | Training coordinator | 1.13.1 | 28FS | FS32;FS36 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 0.375
32 | Train de trainer | 1.13.2 | 31FS | FS38;FS44 | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 0.375
33 | Training rapportage | 1.13.3 | 46FS | FS47 | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 | 0.375
63 | Creation code list | 1.14 |  |  | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 | 38.375
34 | Surveying the required functionalities | 1.14.1 | 28FS | FS35+4w 4d | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 0.375
35 | Creating codes | 1.14.2 | 34FS+4w 4d | FF37+1w | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 3.375
64 | Fill the database | 1.15 |  |  | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 | 36.375
36 | Registration data about employees | 1.15.1 | 29FS;31FS | FS37+3w 2d | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 3.375
37 | Registration hospital data | 1.15.2 | 36FS+3w 2d;35FF+1w | FS38;FS44 | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 7.375
65 | Training staff | 1.16 |  |  | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 | 15.375
38 | Training team 1 | 1.16.1 | 30FS;32FS;37FS | FS39 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 1.375
39 | Training team 2 | 1.16.2 | 38FS | FS40 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 1.375
40 | Training team 3 | 1.16.3 | 39FS | FS41 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 1.375
41 | Training team 4 | 1.16.4 | 40FS | FS42 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 3.375
42 | Training team 5 | 1.16.5 | 41FS | FS43 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 1.375
43 | Training team 6 | 1.16.6 | 42FS | FS46 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 1.375
66 | Final check program | 1.17 |  |  | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 | 15.375
44 | Check-up by PC | 1.17.1 | 30FS;32FS;37FS | FS45+2w | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 0.375
45 | Check-up by ICT committee | 1.17.2 | 44FS+2w | FS46 | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 | 0.375
67 | Live | 1.18 |  |  | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 | 98.375
46 | Live pilot period | 1.18.1 | 43FS;45FS | FS33 | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 | 98.375
68 | Evaluation | 1.19 |  |  | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 | 7.375
47 | Discussing project with board | 1.19.1 | 33FS | FS48+4d 2h | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 0.083333
48 | Discussing project with head nurses | 1.19.2 | 47FS+4d 2h | FS49 | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 | 0.16667
49 | Enrollment of the entire project | 1.19.3 | 48FS |  | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Project Coordinator | Renewable | 1 #persons | 0 | 31.28 | 1;3;4;5;6;7;8;9;10;11;12;13;14;15;16;17;18;19;20;21;22;23;24;25;26;27;28;31;32;33;34;35;36;37;38;39;40;41;42;43;44;47;48;49; | 16953.7656
2 | Headnurses | Renewable | 65 #persons | 0 | 31.28 | 2[65.00 Headnurses];28[65.00 Headnurses];40[17.00 Headnurses];41[16.00 Headnurses];42[16.00 Headnurses];43[16.00 Headnurses];48[65.00 Headnurses]; | 48796.8008
3 | ICT committee | Renewable | 5 #persons | 0 | 27.62 | 4[5.00 ICT committee];6;10;13[5.00 ICT committee];20[5.00 ICT committee];24[5.00 ICT committee];27[5.00 ICT committee];29[2.00 ICT committee];30[2.00 ICT committee];35;45[5.00 ICT committee]; | 12097.5596
4 | Board of directors | Renewable | 7 #persons | 0 | 62.1 | 4[7.00 Board of directors];10[7.00 Board of directors];13[7.00 Board of directors];17[7.00 Board of directors];19;23[7.00 Board of directors];26;27[7.00 Board of directors];47[7.00 Board of directors]; | 11799.002
5 | Stretcher-bearer/logisticians | Renewable | 24 #persons | 0 | 22.31 | 2[24.00 Stretcher-bearer/logisticians];28[24.00 Stretcher-bearer/logisticians];34[24.00 Stretcher-bearer/logisticians];38[12.00 Stretcher-bearer/logisticians];39[12.00 Stretcher-bearer/logisticians]; | 14992.3203

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Patient Transport System | 3112h |  |  |  |  | 99 | 100 | 101
50 | Description of staff's needs & Set-up | 344h |  |  |  |  | 99 | 100 | 101
1 | Compose survey for the staff | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Brainstorming and filling in the survey | 2h | manual - absolute | 2 | 3 | 4 | 100 | 150 | 200
3 | Collecting and analyzing the surveys | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Meeting ICT Committee | 8h |  |  |  |  | 99 | 100 | 101
4 | Get-together PC, ICT committee & board | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Enrollment of the meeting | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Set-up format specifications | 256h |  |  |  |  | 99 | 100 | 101
6 | Registering the technical requirements | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Set-up a detailed budget study | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Putting together the formal document | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Request proposal suppliers transport system | 176h |  |  |  |  | 99 | 100 | 101
9 | Research suppliers transport systems | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Meeting with board for final proposal | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Contacting suppliers and sending proposal | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Decision supplier | 576h |  |  |  |  | 99 | 100 | 101
12 | Analyzing the received offers | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Presentation to board & ICT staff | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Collecting and registering comments on offers | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Taking final decision and contacting supplier | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Negociation conditions final supplier transport system | 592h |  |  |  |  | 99 | 100 | 101
16 | Discussing project development with supplier | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Discussing project development with board | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Final agreement with supplier | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Draw up & Sign contract with supplier transport system | 4h |  |  |  |  | 99 | 100 | 101
19 | Signing contract | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Request proposal supplier DACS | 96h |  |  |  |  | 99 | 100 | 101
20 | Meeting with ICT committee | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Contacting Siemens and sending proposal | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Negociation conditions DACS | 108h |  |  |  |  | 99 | 100 | 101
22 | Discussing project development with supplier | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Discussing progress with board | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Discussing progress with ICT committee | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Final agreement with supplier | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Draw up & Sign contract with supplier DACS | 4h |  |  |  |  | 99 | 100 | 101
26 | Signing contract | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Kick-off Meeting | 8h |  |  |  |  | 99 | 100 | 101
27 | Information session | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Explanation project implementation to staff | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Installation | 48h |  |  |  |  | 99 | 100 | 101
29 | Installation transport system | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Installation DACS | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Training PC | 936h |  |  |  |  | 99 | 100 | 101
31 | Training coordinator | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Train de trainer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Training rapportage | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Creation code list | 216h |  |  |  |  | 99 | 100 | 101
34 | Surveying the required functionalities | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Creating codes | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Fill the database | 216h |  |  |  |  | 99 | 100 | 101
36 | Registration data about employees | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Registration hospital data | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Training staff | 96h |  |  |  |  | 99 | 100 | 101
38 | Training team 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Training team 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Training team 3 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Training team 4 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Training team 5 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Training team 6 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Final check program | 96h |  |  |  |  | 99 | 100 | 101
44 | Check-up by PC | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Check-up by ICT committee | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Live | 568h |  |  |  |  | 99 | 100 | 101
46 | Live pilot period | 568h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Evaluation | 48h |  |  |  |  | 99 | 100 | 101
47 | Discussing project with board | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Discussing project with head nurses | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Enrollment of the entire project | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2010-01-28 17:00 |  | TP Name | 28/01, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 20d | [5 empty] | 5262.4 |  | 2.911% |  | 5262.4 | 5262.4
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 20d | [5 empty] | 5262.4 |  | 95.46% |  | 5262.4 | 5262.4
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 |  | 0 | 0 | 2416.32 | 4h | 0 | 0 | 0 | 2416.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 |  | 0 | 0 | 62.56 | 2h | 0 | 0 | 0 | 62.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 |  | 0 | 0 | 1974.4 | 4h | 0 | 0 | 0 | 1974.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 |  | 0 | 0 | 4832.64 | 1d | 0 | 0 | 0 | 4832.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 |  | 0 | 0 | 2710.08 | 2d | 0 | 0 | 0 | 2710.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2010-02-25 17:00 |  | TP Name | 25/02, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 40d | [5 empty] | 5262.4 |  | 2.911% |  | 5262.4 | 5262.4
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 40d | [5 empty] | 5262.4 |  | 95.46% |  | 5262.4 | 5262.4
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 |  | 0 | 0 | 2416.32 | 4h | 0 | 0 | 0 | 2416.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 |  | 0 | 0 | 62.56 | 2h | 0 | 0 | 0 | 62.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 |  | 0 | 0 | 1974.4 | 4h | 0 | 0 | 0 | 1974.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 |  | 0 | 0 | 4832.64 | 1d | 0 | 0 | 0 | 4832.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 |  | 0 | 0 | 2710.08 | 2d | 0 | 0 | 0 | 2710.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2010-03-25 17:00 |  | TP Name | 25/03, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 60d | [5 empty] | 10155.84 |  | 5.219% |  | 9434.4 | 9434.4
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 16d | [5 empty] | 2164.32 |  | 65.78% |  | 1442.88 | 1442.88
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 |  | 0 | 0 | 1974.4 | 4h | 0 | 0 | 0 | 1974.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 |  | 0 | 0 | 4832.64 | 1d | 0 | 0 | 0 | 4832.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 |  | 0 | 0 | 2710.08 | 2d | 0 | 0 | 0 | 2710.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2010-04-22 17:00 |  | TP Name | 22/04, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 80d | [5 empty] | 11657.28 |  | 6.05% |  | 10935.84 | 10935.84
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 4d | [5 empty] | 750.72 |  | 23.27% |  | 750.72 | 750.72
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 |  | 0 | 0 | 1974.4 | 4h | 0 | 0 | 0 | 1974.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 |  | 0 | 0 | 4832.64 | 1d | 0 | 0 | 0 | 4832.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 |  | 0 | 0 | 2710.08 | 2d | 0 | 0 | 0 | 2710.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2010-05-20 17:00 |  | TP Name | 20/05, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 100d | [5 empty] | 17592.96 |  | 9.334% |  | 16871.52 | 16871.52
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 |  | 0 | 0 | 4832.64 | 1d | 0 | 0 | 0 | 4832.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2010-06-17 17:00 |  | TP Name | 17/06, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 120d | [5 empty] | 18593.92 |  | 9.749% |  | 17622.24 | 38350.84
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 7d | [5 empty] | 1000.96 |  | 11.85% |  | 750.72 | 750.72
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 |  | 0 | 0 | 4832.64 | 1d | 0 | 0 | 0 | 4832.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 500.48 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 677.52 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2010-07-15 17:00 |  | TP Name | 15/07, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 140d | [5 empty] | 23426.56 |  | 12.42% |  | 22454.88 | 43183.48
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 27d | [5 empty] | 5833.6 |  | 88.15% |  | 5583.36 | 5583.36
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 500.48 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 677.52 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2010-08-12 17:00 |  | TP Name | 12/08, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 160d | [5 empty] | 23927.04 |  | 12.56% |  | 22705.12 | 43433.72
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 47d | [5 empty] | 6334.08 |  | 92.1% |  | 5833.6 | 5833.6
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 500.48 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 677.52 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2010-09-09 17:00 |  | TP Name | 09/09, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 180d | [5 empty] | 23927.04 |  | 12.56% |  | 22705.12 | 43433.72
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 67d | [5 empty] | 6334.08 |  | 92.1% |  | 5833.6 | 5833.6
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 |  | 0 | 0 | 750.72 | 3d | 0 | 0 | 0 | 750.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 500.48 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 677.52 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2010-10-07 17:00 |  | TP Name | 07/10, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 200d | [5 empty] | 25178.24 |  | 13.25% |  | 23956.32 | 44684.92
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 15d | [5 empty] | 750.72 |  | 24.1% |  | 750.72 | 750.72
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 500.48 | 100 |  | 0 | 100 |  | 0
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 677.52 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2010-11-04 17:00 |  | TP Name | 04/11, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 220d | [5 empty] | 25678.72 |  | 13.53% |  | 24456.8 | 44684.92
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 35d | [5 empty] | 750.72 |  | 24.1% |  | 750.72 | 750.72
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 |  | 0 | 0 | 1863.92 | 4h | 0 | 0 | 0 | 1863.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 2d | [5 empty] | 500.48 |  | 22.39% |  | 500.48 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 |  | 0 | 0 | 677.52 | 4h | 0 | 0 | 0 | 677.52 | 0% | Not Started | 0 | 677.52 | 100 |  | 0 | 100 |  | 0
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2010-12-02 17:00 |  | TP Name | 02/12, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 240d | [5 empty] | 29152.12 |  | 15.45% |  | 27930.2 | 46548.84
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 55d | [5 empty] | 2614.64 |  | 83.93% |  | 2614.64 | 2614.64
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 |  | 0 | 0 | 500.48 | 2d | 0 | 0 | 0 | 500.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 22d | [5 empty] | 2109.96 |  | 94.4% |  | 2109.96 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2010-12-30 17:00 |  | TP Name | 30/12, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 260d | [5 empty] | 29652.6 |  | 15.73% |  | 28430.68 | 102422.84
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 |  | 0 | 0 | 55373.52 | 4h | 0 | 0 | 0 | 55373.52 | 0% | Not Started | 0 | 55373.52 | 100 |  | 0 | 100 |  | 0
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 42d | [5 empty] | 2109.96 |  | 94.4% |  | 2109.96 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 |  | 0 | 0 | 125.12 | 4h | 0 | 0 | 0 | 125.12 | 0% | Not Started | 0 | 125.12 | 100 |  | 0 | 100 |  | 0
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 |  | 0 | 0 | 18493.52 | 4h | 0 | 0 | 0 | 18493.52 | 0% | Not Started | 0 | 18493.52 | 100 |  | 0 | 100 |  | 0
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 |  | 0 | 0 | 1208.16 | 2h | 0 | 0 | 0 | 1208.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 |  | 0 | 0 | 5199.84 | 2h | 0 | 0 | 0 | 5199.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 |  | 0 | 0 | 1250.24 | 1d | 0 | 0 | 0 | 1250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 |  | 0 | 0 | 4533.76 | 1d | 0 | 0 | 0 | 4533.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2011-01-27 17:00 |  | TP Name | 27/01, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 281d | [5 empty] | 124272.28 |  | 65.57% |  | 118516.6 | 122169.08
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 6d | [5 empty] | 2651.52 |  | 50% |  | 2651.52 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 2651.52 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 4d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 2500.48
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 4d | [5 empty] | 9067.52 |  | 82.79% |  | 4533.76 | 4533.76
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1000.96
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 1000.96 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2011-02-24 17:00 |  | TP Name | 24/02, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 300d | [5 empty] | 124272.28 |  | 65.57% |  | 118516.6 | 127255.16
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 25d | [5 empty] | 2651.52 |  | 50% |  | 2651.52 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 |  | 0 | 0 | 2651.52 | 6d | 0 | 0 | 0 | 2651.52 | 0% | Not Started | 0 | 2651.52 | 100 |  | 0 | 100 |  | 0
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 24d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 2500.48
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 24d | [5 empty] | 9067.52 |  | 82.79% |  | 4533.76 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 |  | 0 | 0 | 942.4 | 2d | 0 | 0 | 0 | 942.4 | 0% | Not Started | 0 | 942.4 | 100 |  | 0 | 100 |  | 0
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 |  | 0 | 0 | 1000.96 | 4d | 0 | 0 | 0 | 1000.96 | 0% | Not Started | 0 | 1000.96 | 100 |  | 0 | 100 |  | 0
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 1501.44 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2392
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 2392 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 250.24
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 250.24 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2011-03-24 17:00 |  | TP Name | 24/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 320d | [5 empty] | 128867.16 |  | 67.41% |  | 121850.6801 | 170569.08
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 45d | [5 empty] | 5303.04 |  | 80% |  | 4242.4321 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 6d | 2651.52 | 1767.68 | 4d | 0 | 0 | 2651.52 | 1767.68 | 60% | Started | 1590.9121 | 2651.52 | 100 | 100 | 60 | 100 | 100 | 60
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 44d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 2500.48
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 4d | [5 empty] | 1000.96 |  | 32% |  | 800.768 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 4d | 1000.96 | 250.24 | 1d | 0 | 0 | 1000.96 | 250.24 | 80% | Started | 800.768 | 1000.96 | 100 | 100 | 80 | 100 | 100 | 80
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 |  | 0 | 0 | 1501.44 | 6d | 0 | 0 | 0 | 1501.44 | 0% | Not Started | 0 | 1501.44 | 100 |  | 0 | 100 |  | 0
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 4784 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 4784 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 9008.64 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 8508.16 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 8508.16 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 8508.16 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 250.24 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 1104.8 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2011-04-21 17:00 |  | TP Name | 21/04, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 340d | [5 empty] | 131385.56 |  | 68.35% |  | 123540.4629 | 170569.08
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 100% |  | 5303.04 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 64d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 2500.48
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 24d | [5 empty] | 1751.68 |  | 57.14% |  | 1429.9429 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 100% | Finished | 1000.96 | 1000.96 | 100 | 125 | 100 | 100 | 125 | 100
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 2d | 500.48 | 1251.2 | 5d | 0 | 0 | 500.48 | 1251.2 | 28.57% | Started | 428.9829 | 1501.44 | 100 | 33.3333 | 28.5714 | 100 | 33.3333 | 28.5714
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 4784 | 100 |  | 0 | 100 |  | 0
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 |  | 0 | 0 | 4784 | 2d | 0 | 0 | 0 | 4784 | 0% | Not Started | 0 | 4784 | 100 |  | 0 | 100 |  | 0
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 |  | 0 | 0 | 9008.64 | 2d | 0 | 0 | 0 | 9008.64 | 0% | Not Started | 0 | 9008.64 | 100 |  | 0 | 100 |  | 0
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 8508.16 | 100 |  | 0 | 100 |  | 0
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 8508.16 | 100 |  | 0 | 100 |  | 0
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 |  | 0 | 0 | 8508.16 | 2d | 0 | 0 | 0 | 8508.16 | 0% | Not Started | 0 | 8508.16 | 100 |  | 0 | 100 |  | 0
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 250.24 | 100 |  | 0 | 100 |  | 0
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 1104.8 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2011-05-19 17:00 |  | TP Name | 19/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 360d | [5 empty] | 176988.12 |  | 93.47% |  | 168964.28 | 170569.08
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 100% |  | 5303.04 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 84d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 2500.48
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 29d | [5 empty] | 3002.88 |  | 100% |  | 2502.4 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 100% | Finished | 1000.96 | 1000.96 | 100 | 125 | 100 | 100 | 125 | 100
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 7d | 1751.68 | 0 | 0 | 0 | 0 | 1751.68 | 0 | 100% | Finished | 1501.44 | 1501.44 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 12d | [5 empty] | 44101.12 |  | 100% |  | 44101.12 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-02 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-04 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 2011-05-06 08:00 | 2d | 9008.64 | 0 | 0 | 0 | 0 | 9008.64 | 0 | 100% | Finished | 9008.64 | 9008.64 | 100 | 100 | 100 | 100 | 100 | 100
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-10 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-12 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-16 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 14d | [5 empty] | 250.24 |  | 18.47% |  | 250.24 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-05-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 |  | 0 | 0 | 1104.8 | 1d | 0 | 0 | 0 | 1104.8 | 0% | Not Started | 0 | 1104.8 | 100 |  | 0 | 100 |  | 0
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 71d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500 | 100 |  | 0 | 100 |  | 0
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2011-06-16 17:00 |  | TP Name | 16/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 380d | [5 empty] | 178592.92 |  | 94.36% |  | 170569.08 | 170569.08
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 100% |  | 5303.04 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 104d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 2500.48
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 29d | [5 empty] | 3002.88 |  | 100% |  | 2502.4 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 100% | Finished | 1000.96 | 1000.96 | 100 | 125 | 100 | 100 | 125 | 100
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 7d | 1751.68 | 0 | 0 | 0 | 0 | 1751.68 | 0 | 100% | Finished | 1501.44 | 1501.44 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 12d | [5 empty] | 44101.12 |  | 100% |  | 44101.12 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-02 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-04 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 2011-05-06 08:00 | 2d | 9008.64 | 0 | 0 | 0 | 0 | 9008.64 | 0 | 100% | Finished | 9008.64 | 9008.64 | 100 | 100 | 100 | 100 | 100 | 100
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-10 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-12 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-16 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 16d | [5 empty] | 1355.04 |  | 100% |  | 1355.04 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-05-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 | 2011-05-23 08:00 | 1d | 1104.8 | 0 | 0 | 0 | 0 | 1104.8 | 0 | 100% | Finished | 1104.8 | 1104.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 18d | [5 empty] | 500 |  | 100% |  | 500 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 | 2011-05-24 08:00 | 16d | 500 | 0 | 55d | 0 | 0 | 500 | 0 | 22.54% | Started | 500 | 500 | 100 | 22.5352 | 22.5352 | 100 | 100 | 22.5352
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2011-07-14 17:00 |  | TP Name | 14/07, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 400d | [5 empty] | 178592.92 |  | 94.36% |  | 170569.08 | 180759.44
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 100% |  | 5303.04 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 124d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 3250.72
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 750.24 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 29d | [5 empty] | 3002.88 |  | 100% |  | 2502.4 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 100% | Finished | 1000.96 | 1000.96 | 100 | 125 | 100 | 100 | 125 | 100
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 7d | 1751.68 | 0 | 0 | 0 | 0 | 1751.68 | 0 | 100% | Finished | 1501.44 | 1501.44 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 12d | [5 empty] | 44101.12 |  | 100% |  | 44101.12 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-02 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-04 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 2011-05-06 08:00 | 2d | 9008.64 | 0 | 0 | 0 | 0 | 9008.64 | 0 | 100% | Finished | 9008.64 | 9008.64 | 100 | 100 | 100 | 100 | 100 | 100
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-10 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-12 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-16 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 16d | [5 empty] | 1355.04 |  | 100% |  | 1355.04 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-05-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 | 2011-05-23 08:00 | 1d | 1104.8 | 0 | 0 | 0 | 0 | 1104.8 | 0 | 100% | Finished | 1104.8 | 1104.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 38d | [5 empty] | 500 |  | 100% |  | 500 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 | 2011-05-24 08:00 | 36d | 500 | 0 | 35d | 0 | 0 | 500 | 0 | 50.7% | Started | 500 | 500 | 100 | 50.7042 | 50.7042 | 100 | 100 | 50.7042
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 9440.12
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 8257.92 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 250.24 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2011-08-11 17:00 |  | TP Name | 11/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 420d | [5 empty] | 178592.92 |  | 94.36% |  | 170569.08 | 180759.44
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 100% |  | 5303.04 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 144d | [5 empty] | 2500.48 |  | 76.92% |  | 2500.48 | 3250.72
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 |  | 0 | 0 | 750.24 | 1d | 0 | 0 | 0 | 750.24 | 0% | Not Started | 0 | 750.24 | 100 |  | 0 | 100 |  | 0
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 29d | [5 empty] | 3002.88 |  | 100% |  | 2502.4 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 100% | Finished | 1000.96 | 1000.96 | 100 | 125 | 100 | 100 | 125 | 100
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 7d | 1751.68 | 0 | 0 | 0 | 0 | 1751.68 | 0 | 100% | Finished | 1501.44 | 1501.44 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 12d | [5 empty] | 44101.12 |  | 100% |  | 44101.12 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-02 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-04 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 2011-05-06 08:00 | 2d | 9008.64 | 0 | 0 | 0 | 0 | 9008.64 | 0 | 100% | Finished | 9008.64 | 9008.64 | 100 | 100 | 100 | 100 | 100 | 100
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-10 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-12 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-16 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 16d | [5 empty] | 1355.04 |  | 100% |  | 1355.04 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-05-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 | 2011-05-23 08:00 | 1d | 1104.8 | 0 | 0 | 0 | 0 | 1104.8 | 0 | 100% | Finished | 1104.8 | 1104.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 58d | [5 empty] | 500 |  | 100% |  | 500 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 | 2011-05-24 08:00 | 56d | 500 | 0 | 15d | 0 | 0 | 500 | 0 | 78.87% | Started | 500 | 500 | 100 | 78.8732 | 78.8732 | 100 | 100 | 78.8732
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 9440.12
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 |  | 0 | 0 | 931.96 | 2h | 0 | 0 | 0 | 931.96 | 0% | Not Started | 0 | 931.96 | 100 |  | 0 | 100 |  | 0
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 8257.92 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 250.24 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2011-09-08 17:00 |  | TP Name | 08/09, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 440d | [5 empty] | 181673.06 |  | 95.29% |  | 172251.28 | 180759.44
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 100% |  | 5303.04 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 161d | [5 empty] | 3250.72 |  | 100% |  | 3250.72 | 3250.72
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 | 2011-09-05 08:00 | 1d | 750.24 | 0 | 0 | 0 | 0 | 750.24 | 0 | 100% | Finished | 750.24 | 750.24 | 100 | 100 | 100 | 100 | 100 | 100
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 29d | [5 empty] | 3002.88 |  | 100% |  | 2502.4 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 100% | Finished | 1000.96 | 1000.96 | 100 | 125 | 100 | 100 | 125 | 100
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 7d | 1751.68 | 0 | 0 | 0 | 0 | 1751.68 | 0 | 100% | Finished | 1501.44 | 1501.44 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 12d | [5 empty] | 44101.12 |  | 100% |  | 44101.12 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-02 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-04 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 2011-05-06 08:00 | 2d | 9008.64 | 0 | 0 | 0 | 0 | 9008.64 | 0 | 100% | Finished | 9008.64 | 9008.64 | 100 | 100 | 100 | 100 | 100 | 100
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-10 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-12 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-16 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 16d | [5 empty] | 1355.04 |  | 100% |  | 1355.04 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-05-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 | 2011-05-23 08:00 | 1d | 1104.8 | 0 | 0 | 0 | 0 | 1104.8 | 0 | 100% | Finished | 1104.8 | 1104.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 71d | [5 empty] | 500 |  | 100% |  | 500 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 | 2011-05-24 08:00 | 71d | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500 | 100 | 100 | 100 | 100 | 100 | 100
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 3d | [5 empty] | 2329.9 |  | 9.872% |  | 931.96 | 9440.12
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2011-09-06 08:00 | 5h | 2329.9 | 0 | 0 | 0 | 0 | 2329.9 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 250 | 100 | 100 | 250 | 100
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 |  | 0 | 0 | 8257.92 | 4h | 0 | 0 | 0 | 8257.92 | 0% | Not Started | 0 | 8257.92 | 100 |  | 0 | 100 |  | 0
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 |  | 0 | 0 | 250.24 | 1d | 0 | 0 | 0 | 250.24 | 0% | Not Started | 0 | 250.24 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2011-09-15 20:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Patient Transport System | 2010-01-01 08:00 | 2011-06-29 17:00 | 389d |  |  | 76120 |  |  | 180759.44 |  | 444d | [5 empty] | 191065.06 |  | 100% |  | 180759.44 | 180759.44
50 | Description of staff's needs & Set-up | 2010-01-01 08:00 | 2010-03-02 17:00 | 43d |  |  | 0 |  |  | 5512.64 |  | 43d | [5 empty] | 5512.64 |  | 100% |  | 5512.64 | 5512.64
1 | Compose survey for the staff | 2010-01-01 08:00 | 2010-01-01 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2010-01-01 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
2 | Brainstorming and filling in the survey | 2010-01-11 13:00 | 2010-01-11 15:00 | 2h | Headnurses[65.00 #65];Stretcher-bearer/logisticians[24.00 #24] | 5137.28 | 0 | 0 | 0 | 5137.28 | 2010-01-11 13:00 | 2h | 5137.28 | 0 | 0 | 0 | 0 | 5137.28 | 0 | 100% | Finished | 5137.28 | 5137.28 | 100 | 100 | 100 | 100 | 100 | 100
3 | Collecting and analyzing the surveys | 2010-03-02 08:00 | 2010-03-02 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-03-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | Meeting ICT Committee | 2010-03-03 08:00 | 2010-03-03 17:00 | 1d |  |  | 0 |  |  | 2478.88 |  | 1d | [5 empty] | 2478.88 |  | 100% |  | 2478.88 | 2478.88
4 | Get-together PC, ICT committee & board | 2010-03-03 08:00 | 2010-03-03 12:00 | 4h | Project Coordinator;ICT committee[5.00 #5];Board of directors[7.00 #7] | 2416.32 | 0 | 0 | 0 | 2416.32 | 2010-03-03 08:00 | 4h | 2416.32 | 0 | 0 | 0 | 0 | 2416.32 | 0 | 100% | Finished | 2416.32 | 2416.32 | 100 | 100 | 100 | 100 | 100 | 100
5 | Enrollment of the meeting | 2010-03-03 15:00 | 2010-03-03 17:00 | 2h | Project Coordinator | 62.56 | 0 | 0 | 0 | 62.56 | 2010-03-03 15:00 | 2h | 62.56 | 0 | 0 | 0 | 0 | 62.56 | 0 | 100% | Finished | 62.56 | 62.56 | 100 | 100 | 100 | 100 | 100 | 100
52 | Set-up format specifications | 2010-03-04 08:00 | 2010-04-16 17:00 | 32d |  |  | 0 |  |  | 2193.6 |  | 32d | [5 empty] | 2915.04 |  | 100% |  | 2193.6 | 2193.6
6 | Registering the technical requirements | 2010-03-04 08:00 | 2010-03-05 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2010-03-04 08:00 | 3d | 1413.6 | 0 | 0 | 0 | 0 | 1413.6 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 150 | 100 | 100 | 150 | 100
7 | Set-up a detailed budget study | 2010-03-22 08:00 | 2010-03-23 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-03-22 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 150 | 100 | 100 | 150 | 100
8 | Putting together the formal document | 2010-04-14 08:00 | 2010-04-16 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-14 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
53 | Request proposal suppliers transport system | 2010-04-19 08:00 | 2010-05-18 17:00 | 22d |  |  | 0 |  |  | 3225.6 |  | 22d | [5 empty] | 3225.6 |  | 100% |  | 3225.6 | 3225.6
9 | Research suppliers transport systems | 2010-04-19 08:00 | 2010-04-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-04-19 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
10 | Meeting with board for final proposal | 2010-04-30 13:00 | 2010-04-30 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7];ICT committee | 1974.4 | 0 | 0 | 0 | 1974.4 | 2010-04-30 13:00 | 4h | 1974.4 | 0 | 0 | 0 | 0 | 1974.4 | 0 | 100% | Finished | 1974.4 | 1974.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | Contacting suppliers and sending proposal | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-05-17 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
54 | Decision supplier | 2010-06-09 08:00 | 2010-09-16 17:00 | 72d |  |  | 0 |  |  | 6334.08 |  | 72d | [5 empty] | 6834.56 |  | 100% |  | 6334.08 | 6334.08
12 | Analyzing the received offers | 2010-06-09 08:00 | 2010-06-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-06-09 08:00 | 4d | 1000.96 | 0 | 0 | 0 | 0 | 1000.96 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
13 | Presentation to board & ICT staff | 2010-07-12 08:00 | 2010-07-12 17:00 | 1d | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 4832.64 | 0 | 0 | 0 | 4832.64 | 2010-07-12 08:00 | 1d | 4832.64 | 0 | 0 | 0 | 0 | 4832.64 | 0 | 100% | Finished | 4832.64 | 4832.64 | 100 | 100 | 100 | 100 | 100 | 100
14 | Collecting and registering comments on offers | 2010-08-03 08:00 | 2010-08-03 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2010-08-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 200 | 100 | 100 | 200 | 100
15 | Taking final decision and contacting supplier | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-09-15 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
55 | Negociation conditions final supplier transport system | 2010-09-17 08:00 | 2010-12-29 17:00 | 74d |  |  | 0 |  |  | 3115.12 |  | 74d | [5 empty] | 3115.12 |  | 100% |  | 3115.12 | 3115.12
16 | Discussing project development with supplier | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-09-17 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
17 | Discussing project development with board | 2010-11-15 13:00 | 2010-11-15 17:00 | 4h | Project Coordinator;Board of directors[7.00 #7] | 1863.92 | 0 | 0 | 0 | 1863.92 | 2010-11-15 13:00 | 4h | 1863.92 | 0 | 0 | 0 | 0 | 1863.92 | 0 | 100% | Finished | 1863.92 | 1863.92 | 100 | 100 | 100 | 100 | 100 | 100
18 | Final agreement with supplier | 2010-12-28 08:00 | 2010-12-29 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-12-28 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | Draw up & Sign contract with supplier transport system | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h |  |  | 55000 |  |  | 55373.52 |  | 4h | [5 empty] | 55373.52 |  | 100% |  | 55373.52 | 55373.52
19 | Signing contract | 2010-12-30 08:00 | 2010-12-30 12:00 | 4h | Project Coordinator;Board of directors | 373.52 | 55000 | 0 | 0 | 55373.52 | 2011-01-05 08:00 | 4h | 55373.52 | 0 | 0 | 0 | 0 | 55373.52 | 0 | 100% | Finished | 55373.52 | 55373.52 | 100 | 100 | 100 | 100 | 100 | 100
57 | Request proposal supplier DACS | 2010-04-26 08:00 | 2010-05-11 17:00 | 12d |  |  | 0 |  |  | 3460.8 |  | 12d | [5 empty] | 3460.8 |  | 100% |  | 3460.8 | 3460.8
20 | Meeting with ICT committee | 2010-04-26 08:00 | 2010-04-27 17:00 | 2d | Project Coordinator;ICT committee[5.00 #5] | 2710.08 | 0 | 0 | 0 | 2710.08 | 2010-04-26 08:00 | 2d | 2710.08 | 0 | 0 | 0 | 0 | 2710.08 | 0 | 100% | Finished | 2710.08 | 2710.08 | 100 | 100 | 100 | 100 | 100 | 100
21 | Contacting Siemens and sending proposal | 2010-05-07 08:00 | 2010-05-11 17:00 | 3d | Project Coordinator | 750.72 | 0 | 0 | 0 | 750.72 | 2010-05-07 08:00 | 3d | 750.72 | 0 | 0 | 0 | 0 | 750.72 | 0 | 100% | Finished | 750.72 | 750.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | Negociation conditions DACS | 2010-05-26 08:00 | 2010-06-14 12:00 | 13d 4h |  |  | 0 |  |  | 2235.08 |  | 48d 4h | [5 empty] | 2235.08 |  | 100% |  | 2235.08 | 2235.08
22 | Discussing project development with supplier | 2010-05-26 08:00 | 2010-05-27 17:00 | 2d | Project Coordinator | 500.48 | 0 | 0 | 0 | 500.48 | 2010-11-03 08:00 | 2d | 500.48 | 0 | 0 | 0 | 0 | 500.48 | 0 | 100% | Finished | 500.48 | 500.48 | 100 | 100 | 100 | 100 | 100 | 100
23 | Discussing progress with board | 2010-06-04 08:00 | 2010-06-04 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2010-11-17 08:00 | 2h | 931.96 | 0 | 0 | 0 | 0 | 931.96 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | Discussing progress with ICT committee | 2010-06-08 10:00 | 2010-06-08 15:00 | 4h | Project Coordinator;ICT committee[5.00 #5] | 677.52 | 0 | 0 | 0 | 677.52 | 2010-11-22 08:00 | 4h | 677.52 | 0 | 0 | 0 | 0 | 677.52 | 0 | 100% | Finished | 677.52 | 677.52 | 100 | 100 | 100 | 100 | 100 | 100
25 | Final agreement with supplier | 2010-06-14 08:00 | 2010-06-14 12:00 | 4h | Project Coordinator | 125.12 | 0 | 0 | 0 | 125.12 | 2011-01-10 08:00 | 4h | 125.12 | 0 | 0 | 0 | 0 | 125.12 | 0 | 100% | Finished | 125.12 | 125.12 | 100 | 100 | 100 | 100 | 100 | 100
59 | Draw up & Sign contract with supplier DACS | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h |  |  | 18120 |  |  | 18493.52 |  | 4h | [5 empty] | 18493.52 |  | 100% |  | 18493.52 | 18493.52
26 | Signing contract | 2010-06-14 13:00 | 2010-06-14 17:00 | 4h | Project Coordinator;Board of directors | 373.52 | 18120 | 0 | 0 | 18493.52 | 2011-01-17 08:00 | 4h | 18493.52 | 0 | 0 | 0 | 0 | 18493.52 | 0 | 100% | Finished | 18493.52 | 18493.52 | 100 | 100 | 100 | 100 | 100 | 100
60 | Kick-off Meeting | 2011-01-06 08:00 | 2011-01-06 17:00 | 1d |  |  | 0 |  |  | 6408 |  | 1d | [5 empty] | 6408 |  | 100% |  | 6408 | 6408
27 | Information session | 2011-01-06 08:00 | 2011-01-06 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7];ICT committee[5.00 #5] | 1208.16 | 0 | 0 | 0 | 1208.16 | 2011-01-20 08:00 | 2h | 1208.16 | 0 | 0 | 0 | 0 | 1208.16 | 0 | 100% | Finished | 1208.16 | 1208.16 | 100 | 100 | 100 | 100 | 100 | 100
28 | Explanation project implementation to staff | 2011-01-06 15:00 | 2011-01-06 17:00 | 2h | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24];Headnurses[65.00 #65] | 5199.84 | 0 | 0 | 0 | 5199.84 | 2011-01-20 15:00 | 2h | 5199.84 | 0 | 0 | 0 | 0 | 5199.84 | 0 | 100% | Finished | 5199.84 | 5199.84 | 100 | 100 | 100 | 100 | 100 | 100
61 | Installation | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d |  |  | 0 |  |  | 5303.04 |  | 51d | [5 empty] | 7070.72 |  | 100% |  | 5303.04 | 5303.04
29 | Installation transport system | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-01-21 08:00 | 6d | 2651.52 | 0 | 0 | 0 | 0 | 2651.52 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 100 | 100 | 100 | 100 | 100
30 | Installation DACS | 2011-01-07 08:00 | 2011-01-14 17:00 | 6d | ICT committee[2.00 #5] | 2651.52 | 0 | 0 | 0 | 2651.52 | 2011-03-21 08:00 | 10d | 4419.2 | 0 | 0 | 0 | 0 | 4419.2 | 0 | 100% | Finished | 2651.52 | 2651.52 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
62 | Training PC | 2011-01-10 08:00 | 2011-06-21 17:00 | 117d |  |  | 2500 |  |  | 3250.72 |  | 161d | [5 empty] | 3250.72 |  | 100% |  | 3250.72 | 3250.72
31 | Training coordinator | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-24 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
32 | Train de trainer | 2011-01-11 08:00 | 2011-01-11 17:00 | 1d | Project Coordinator | 250.24 | 1000 | 0 | 0 | 1250.24 | 2011-01-27 08:00 | 1d | 1250.24 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 100% | Finished | 1250.24 | 1250.24 | 100 | 100 | 100 | 100 | 100 | 100
33 | Training rapportage | 2011-06-21 08:00 | 2011-06-21 17:00 | 1d | Project Coordinator | 250.24 | 500 | 0 | 0 | 750.24 | 2011-09-05 08:00 | 1d | 750.24 | 0 | 0 | 0 | 0 | 750.24 | 0 | 100% | Finished | 750.24 | 750.24 | 100 | 100 | 100 | 100 | 100 | 100
63 | Creation code list | 2011-01-07 08:00 | 2011-02-14 17:00 | 27d |  |  | 0 |  |  | 5476.16 |  | 37d | [5 empty] | 10009.92 |  | 100% |  | 5476.16 | 5476.16
34 | Surveying the required functionalities | 2011-01-07 08:00 | 2011-01-07 17:00 | 1d | Project Coordinator;Stretcher-bearer/logisticians[24.00 #24] | 4533.76 | 0 | 0 | 0 | 4533.76 | 2011-01-24 08:00 | 2d | 9067.52 | 0 | 0 | 0 | 0 | 9067.52 | 0 | 100% | Finished | 4533.76 | 4533.76 | 100 | 200 | 100 | 100 | 200 | 100
35 | Creating codes | 2011-02-11 08:00 | 2011-02-14 17:00 | 2d | Project Coordinator;ICT committee | 942.4 | 0 | 0 | 0 | 942.4 | 2011-03-14 08:00 | 2d | 942.4 | 0 | 0 | 0 | 0 | 942.4 | 0 | 100% | Finished | 942.4 | 942.4 | 100 | 100 | 100 | 100 | 100 | 100
64 | Fill the database | 2011-01-17 08:00 | 2011-02-22 17:00 | 27d |  |  | 0 |  |  | 2502.4 |  | 29d | [5 empty] | 3002.88 |  | 100% |  | 2502.4 | 2502.4
36 | Registration data about employees | 2011-01-17 08:00 | 2011-01-20 17:00 | 4d | Project Coordinator | 1000.96 | 0 | 0 | 0 | 1000.96 | 2011-03-21 08:00 | 5d | 1251.2 | 0 | 0 | 0 | 0 | 1251.2 | 0 | 100% | Finished | 1000.96 | 1000.96 | 100 | 125 | 100 | 100 | 125 | 100
37 | Registration hospital data | 2011-02-15 08:00 | 2011-02-22 17:00 | 6d | Project Coordinator | 1501.44 | 0 | 0 | 0 | 1501.44 | 2011-04-20 08:00 | 7d | 1751.68 | 0 | 0 | 0 | 0 | 1751.68 | 0 | 100% | Finished | 1501.44 | 1501.44 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
65 | Training staff | 2011-02-24 08:00 | 2011-03-11 17:00 | 12d |  |  | 0 |  |  | 44101.12 |  | 12d | [5 empty] | 44101.12 |  | 100% |  | 44101.12 | 44101.12
38 | Training team 1 | 2011-02-24 08:00 | 2011-02-25 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-02 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
39 | Training team 2 | 2011-02-28 08:00 | 2011-03-01 17:00 | 2d | Project Coordinator;Stretcher-bearer/logisticians[12.00 #24] | 4784 | 0 | 0 | 0 | 4784 | 2011-05-04 08:00 | 2d | 4784 | 0 | 0 | 0 | 0 | 4784 | 0 | 100% | Finished | 4784 | 4784 | 100 | 100 | 100 | 100 | 100 | 100
40 | Training team 3 | 2011-03-02 08:00 | 2011-03-03 17:00 | 2d | Project Coordinator;Headnurses[17.00 #65] | 9008.64 | 0 | 0 | 0 | 9008.64 | 2011-05-06 08:00 | 2d | 9008.64 | 0 | 0 | 0 | 0 | 9008.64 | 0 | 100% | Finished | 9008.64 | 9008.64 | 100 | 100 | 100 | 100 | 100 | 100
41 | Training team 4 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-10 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
42 | Training team 5 | 2011-03-08 08:00 | 2011-03-09 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-12 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
43 | Training team 6 | 2011-03-10 08:00 | 2011-03-11 17:00 | 2d | Project Coordinator;Headnurses[16.00 #65] | 8508.16 | 0 | 0 | 0 | 8508.16 | 2011-05-16 08:00 | 2d | 8508.16 | 0 | 0 | 0 | 0 | 8508.16 | 0 | 100% | Finished | 8508.16 | 8508.16 | 100 | 100 | 100 | 100 | 100 | 100
66 | Final check program | 2011-02-23 08:00 | 2011-03-10 17:00 | 12d |  |  | 0 |  |  | 1355.04 |  | 16d | [5 empty] | 1355.04 |  | 100% |  | 1355.04 | 1355.04
44 | Check-up by PC | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-05-02 08:00 | 1d | 250.24 | 0 | 0 | 0 | 0 | 250.24 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | Check-up by ICT committee | 2011-03-10 08:00 | 2011-03-10 17:00 | 1d | ICT committee[5.00 #5] | 1104.8 | 0 | 0 | 0 | 1104.8 | 2011-05-23 08:00 | 1d | 1104.8 | 0 | 0 | 0 | 0 | 1104.8 | 0 | 100% | Finished | 1104.8 | 1104.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Live | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  |  | 500 |  |  | 500 |  | 71d | [5 empty] | 500 |  | 100% |  | 500 | 500
46 | Live pilot period | 2011-03-14 08:00 | 2011-06-20 17:00 | 71d |  | 0 | 500 | 0 | 0 | 500 | 2011-05-24 08:00 | 71d | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500 | 100 | 100 | 100 | 100 | 100 | 100
68 | Evaluation | 2011-06-22 08:00 | 2011-06-29 17:00 | 6d |  |  | 0 |  |  | 9440.12 |  | 7d | [5 empty] | 11721.9 |  | 100% |  | 9440.12 | 9440.12
47 | Discussing project with board | 2011-06-22 08:00 | 2011-06-22 10:00 | 2h | Project Coordinator;Board of directors[7.00 #7] | 931.96 | 0 | 0 | 0 | 931.96 | 2011-09-06 08:00 | 5h | 2329.9 | 0 | 0 | 0 | 0 | 2329.9 | 0 | 100% | Finished | 931.96 | 931.96 | 100 | 250 | 100 | 100 | 250 | 100
48 | Discussing project with head nurses | 2011-06-28 13:00 | 2011-06-28 17:00 | 4h | Project Coordinator;Headnurses[65.00 #65] | 8257.92 | 0 | 0 | 0 | 8257.92 | 2011-09-13 08:00 | 4h | 8257.92 | 0 | 0 | 500 | 0 | 8757.92 | 0 | 100% | Finished | 8257.92 | 8257.92 | 100 | 100 | 100 | 100 | 106.0548 | 100
49 | Enrollment of the entire project | 2011-06-29 08:00 | 2011-06-29 17:00 | 1d | Project Coordinator | 250.24 | 0 | 0 | 0 | 250.24 | 2011-09-14 08:00 | 1d | 250.24 | 0 | 0 | 383.84 | 0 | 634.08 | 0 | 100% | Finished | 250.24 | 250.24 | 100 | 100 | 100 | 100 | 253.3887 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
28/01, 2010 | 2010-01-01 08:00 | 2010-01-28 17:00 | 5262.4 | 5262.4 | 5262.4 | 2010-01-28 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
25/02, 2010 | 2010-01-28 17:00 | 2010-02-25 17:00 | 5262.4 | 5262.4 | 5262.4 | 2010-02-25 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 180759.44 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
25/03, 2010 | 2010-02-25 17:00 | 2010-03-25 17:00 | 9434.4 | 9434.4 | 10155.84 | 2010-03-25 17:00 | 0 | 100% | -721.44 | 92.9% | 0 | 100% | 100% | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-08-10 15:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-08-04 09:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-08-04 09:00 | 181480.88 | 194581.9502 | 181480.88 | 181480.88 | 194581.9502 | 194581.9502 | 191803.8584 | 191803.8584 | 1 | 0.92896 | 1 | 1 | 0 | 0.92896 | 1 | 1 | 1
22/04, 2010 | 2010-03-25 17:00 | 2010-04-22 17:00 | 10935.84 | 10935.84 | 11657.28 | 2010-04-22 17:00 | 0 | 100% | -721.44 | 93.81% | 0 | 100% | 100% | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-08-04 14:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-07-28 11:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-07-28 11:00 | 181480.88 | 192684.1838 | 181480.88 | 181480.88 | 192684.1838 | 192684.1838 | 190326.8094 | 190326.8094 | 1 | 0.93811 | 1 | 1 | 0 | 0.93811 | 1 | 1 | 1
20/05, 2010 | 2010-04-22 17:00 | 2010-05-20 17:00 | 16871.52 | 16871.52 | 17592.96 | 2010-05-20 17:00 | 0 | 100% | -721.44 | 95.9% | 0 | 100% | 100% | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-07-22 14:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-07-18 11:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-07-18 11:00 | 181480.88 | 188488.8616 | 181480.88 | 181480.88 | 188488.8616 | 188488.8616 | 187039.7251 | 187039.7251 | 1 | 0.95899 | 1 | 1 | 0 | 0.95899 | 1 | 1 | 1
17/06, 2010 | 2010-05-20 17:00 | 2010-06-17 17:00 | 38350.84 | 17622.24 | 18593.92 | 2010-06-03 17:00 | -20728.6 | 45.95% | -971.68 | 94.77% | -10d | 91.67% | 97.12% | 2011-08-31 14:00 | 2013-04-01 14:00 | 2013-06-05 10:00 | 2011-09-28 16:00 | 2013-04-01 14:00 | 2013-05-27 14:00 | 2011-07-13 17:00 | 2011-08-18 11:00 | 2011-09-12 09:00 | 181731.12 | 190726.4097 | 373625.3266 | 196561.7745 | 393201.5506 | 206374.8179 | 210498.861 | 191862.667 | 0.91667 | 0.94774 | 0.4595 | 0.97119 | -10 | 0.94774 | 1 | 0.91667 | 1
15/07, 2010 | 2010-06-17 17:00 | 2010-07-15 17:00 | 43183.48 | 22454.88 | 23426.56 | 2010-06-14 12:00 | -20728.6 | 52% | -971.68 | 95.85% | -23d 4h | 83.21% | 88.74% | 2011-08-31 14:00 | 2012-11-14 09:00 | 2012-12-28 12:00 | 2011-10-03 10:00 | 2012-11-14 09:00 | 2012-12-20 11:00 | 2011-08-02 12:00 | 2011-10-18 12:00 | 2011-11-07 14:00 | 181731.12 | 188581.3626 | 327865.5862 | 213663.7995 | 341039.4403 | 221895.8506 | 205215.4482 | 193054.3872 | 0.83214 | 0.95852 | 0.51999 | 0.88744 | -23.5 | 0.95852 | 1 | 0.83214 | 1
12/08, 2010 | 2010-07-15 17:00 | 2010-08-12 17:00 | 43433.72 | 22705.12 | 23927.04 | 2010-06-14 12:00 | -20728.6 | 52.28% | -1221.92 | 94.89% | -43d 4h | 72.81% | 88.74% | 2011-08-31 14:00 | 2012-11-08 09:00 | 2013-01-03 09:00 | 2011-10-14 11:00 | 2012-11-08 09:00 | 2012-12-21 14:00 | 2011-08-30 12:00 | 2012-01-19 10:00 | 2012-02-16 11:00 | 181981.36 | 190487.3593 | 326276.7778 | 240997.3507 | 342548.3145 | 252679.4098 | 206924.7128 | 198617.0678 | 0.72813 | 0.94893 | 0.52275 | 0.88744 | -43.5 | 0.94893 | 1 | 0.72813 | 1
09/09, 2010 | 2010-08-12 17:00 | 2010-09-09 17:00 | 43433.72 | 22705.12 | 23927.04 | 2010-06-14 12:00 | -20728.6 | 52.28% | -1221.92 | 94.89% | -63d 4h | 64.72% | 88.74% | 2011-08-31 14:00 | 2012-11-08 09:00 | 2013-01-03 09:00 | 2011-10-27 16:00 | 2012-11-08 09:00 | 2012-12-20 12:00 | 2011-09-27 12:00 | 2012-04-20 17:00 | 2012-05-23 15:00 | 181981.36 | 190487.3593 | 326276.7778 | 268131.1396 | 342548.3145 | 281273.4561 | 206924.7128 | 201798.0434 | 0.64722 | 0.94893 | 0.52275 | 0.88744 | -63.5 | 0.94893 | 1 | 0.64722 | 1
07/10, 2010 | 2010-09-09 17:00 | 2010-10-07 17:00 | 44684.92 | 23956.32 | 25178.24 | 2010-06-14 12:00 | -20728.6 | 53.61% | -1221.92 | 95.15% | -83d 4h | 58.25% | 88.74% | 2011-08-31 14:00 | 2012-10-12 14:00 | 2012-12-04 14:00 | 2011-11-07 15:00 | 2012-10-12 14:00 | 2012-11-20 11:00 | 2011-10-25 12:00 | 2012-07-24 15:00 | 2012-08-27 14:00 | 181981.36 | 189979.2857 | 317657.8392 | 294368.1456 | 332576.1018 | 308098.4902 | 205744.0663 | 203835.5504 | 0.5825 | 0.95147 | 0.53612 | 0.88744 | -83.5 | 0.95147 | 1 | 0.5825 | 1
04/11, 2010 | 2010-10-07 17:00 | 2010-11-04 17:00 | 44684.92 | 24456.8 | 25678.72 | 2010-06-14 12:00 | -20228.12 | 54.73% | -1221.92 | 95.24% | -103d 4h | 52.95% | 91.26% | 2011-08-30 12:00 | 2012-09-21 15:00 | 2012-11-12 10:00 | 2011-11-16 14:00 | 2012-09-21 15:00 | 2012-10-26 10:00 | 2011-11-22 12:00 | 2012-10-25 14:00 | 2012-11-30 10:00 | 181981.36 | 189790.6123 | 311258.639 | 320842.5037 | 325526.8922 | 335589.5896 | 205049.236 | 205783.8464 | 0.52955 | 0.95242 | 0.54732 | 0.91265 | -103.5 | 0.95242 | 1 | 0.52955 | 1
02/12, 2010 | 2010-11-04 17:00 | 2010-12-02 17:00 | 46548.84 | 27930.2 | 29152.12 | 2010-06-14 12:00 | -18618.64 | 60% | -1221.92 | 95.81% | -123d 4h | 48.54% | 99.37% | 2011-08-25 09:00 | 2012-06-27 11:00 | 2012-08-06 14:00 | 2011-11-10 17:00 | 2012-06-27 11:00 | 2012-07-23 09:00 | 2011-12-20 12:00 | 2013-01-28 11:00 | 2013-03-01 16:00 | 181981.36 | 188667.4956 | 283859.3487 | 343993.4728 | 295002.5506 | 357767.4861 | 201553.8518 | 206129.7672 | 0.48542 | 0.95808 | 0.60002 | 0.9937 | -123.5 | 0.95808 | 1 | 0.48542 | 1
30/12, 2010 | 2010-12-02 17:00 | 2010-12-30 17:00 | 102422.84 | 28430.68 | 29652.6 | 2010-06-14 12:00 | -73992.16 | 27.76% | -1221.92 | 95.88% | -143d 4h | 44.81% | 99.37% | 2012-02-08 10:00 | 2015-05-18 11:00 | 2015-08-10 14:00 | 2012-03-19 16:00 | 2015-05-18 11:00 | 2015-07-24 12:00 | 2012-01-17 12:00 | 2013-05-01 09:00 | 2013-06-06 10:00 | 181981.36 | 188528.286 | 578424.0051 | 369613.7811 | 602009.609 | 384224.9465 | 214843.4806 | 207471.9191 | 0.44808 | 0.95879 | 0.27758 | 0.9937 | -143.5 | 0.95879 | 1 | 0.44808 | 1
27/01, 2011 | 2010-12-30 17:00 | 2011-01-27 17:00 | 122169.08 | 118516.6 | 124272.28 | 2011-01-11 17:00 | -3652.48 | 97.01% | -5755.68 | 95.37% | -12d | 95.71% | 98.88% | 2011-07-11 16:00 | 2011-07-15 17:00 | 2011-08-12 12:00 | 2011-07-12 11:00 | 2011-07-15 17:00 | 2011-07-25 16:00 | 2011-07-15 17:00 | 2011-07-25 11:00 | 2011-08-02 12:00 | 186515.12 | 189537.9022 | 188433.3384 | 189302.1128 | 191549.2777 | 192460.2435 | 189313.9574 | 189490.6076 | 0.95714 | 0.95368 | 0.9701 | 0.98881 | -12 | 0.95368 | 1 | 0.95714 | 1
24/02, 2011 | 2011-01-27 17:00 | 2011-02-24 17:00 | 127255.16 | 118516.6 | 124272.28 | 2011-01-11 17:00 | -8738.56 | 93.13% | -5755.68 | 95.37% | -32d | 89.33% | 98.88% | 2011-07-26 15:00 | 2011-08-09 14:00 | 2011-09-06 17:00 | 2011-07-28 14:00 | 2011-08-09 14:00 | 2011-08-17 11:00 | 2011-08-12 17:00 | 2011-09-02 12:00 | 2011-09-12 17:00 | 186515.12 | 189537.9022 | 191104.4585 | 193947.1009 | 194350.1189 | 197330.8123 | 189845.3105 | 190374.5256 | 0.89333 | 0.95368 | 0.93133 | 0.98881 | -32 | 0.95368 | 1 | 0.89333 | 1
24/03, 2011 | 2011-02-24 17:00 | 2011-03-24 17:00 | 170569.08 | 121850.6801 | 128867.16 | 2011-01-19 14:00 | -48718.3999 | 71.44% | -7016.4799 | 94.56% | -46d 3h | 85.51% | 99.13% | 2011-11-23 16:00 | 2012-02-02 12:00 | 2012-03-16 16:00 | 2011-11-04 11:00 | 2012-02-02 12:00 | 2012-02-21 12:00 | 2011-09-02 11:00 | 2011-09-29 16:00 | 2011-10-11 15:00 | 187775.9199 | 191168.0399 | 211328.8498 | 197759.9994 | 216077.209 | 201727.0287 | 194371.0076 | 192383.5434 | 0.85508 | 0.94555 | 0.71438 | 0.99129 | -46.375 | 0.94555 | 1 | 0.85508 | 1
21/04, 2011 | 2011-03-24 17:00 | 2011-04-21 17:00 | 170569.08 | 123540.4629 | 131385.56 | 2011-02-16 14:00 | -47028.6171 | 72.43% | -7845.0971 | 94.03% | -46d 3h | 86.36% | 100% | 2011-11-18 10:00 | 2012-01-24 09:00 | 2012-03-12 10:00 | 2011-11-08 15:00 | 2012-01-24 09:00 | 2012-02-09 14:00 | 2011-09-02 11:00 | 2011-09-23 12:00 | 2011-10-04 12:00 | 188604.5371 | 192238.0708 | 210386.3024 | 197641.6766 | 215403.0272 | 201849.0889 | 195168.5455 | 193247.111 | 0.8636 | 0.94029 | 0.72428 | 1 | -46.375 | 0.94029 | 1 | 0.8636 | 1
19/05, 2011 | 2011-04-21 17:00 | 2011-05-19 17:00 | 170569.08 | 168964.28 | 176988.12 | 2011-03-11 14:00 | -1604.8 | 99.06% | -8023.84 | 95.47% | -49d 3h | 86.28% | 99.34% | 2011-07-05 12:00 | 2011-07-05 15:00 | 2011-08-01 11:00 | 2011-07-05 11:00 | 2011-07-05 15:00 | 2011-07-07 10:00 | 2011-09-07 11:00 | 2011-09-23 16:00 | 2011-09-30 09:00 | 188783.28 | 189343.413 | 188895.3088 | 190658.1646 | 189460.762 | 191307.3329 | 189251.1142 | 189585.7346 | 0.86285 | 0.95466 | 0.99059 | 0.99344 | -49.375 | 0.95466 | 1 | 0.86285 | 1
16/06, 2011 | 2011-05-19 17:00 | 2011-06-16 17:00 | 170569.08 | 170569.08 | 178592.92 | 2011-06-16 17:00 | 0 | 100% | -8023.84 | 95.51% | 0 | 100% | 100% | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-07-26 10:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-30 11:00 | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-06-30 11:00 | 188783.28 | 189262.6507 | 188783.28 | 188783.28 | 189262.6507 | 189262.6507 | 189163.2021 | 189163.2021 | 1 | 0.95507 | 1 | 1 | 0 | 0.95507 | 1 | 1 | 1
14/07, 2011 | 2011-06-16 17:00 | 2011-07-14 17:00 | 180759.44 | 170569.08 | 178592.92 | 2011-06-20 17:00 | -10190.36 | 94.36% | -8023.84 | 95.51% | -18d | 95.5% | 100% | 2011-07-29 16:00 | 2011-08-02 10:00 | 2011-08-29 14:00 | 2011-08-16 12:00 | 2011-08-17 16:00 | 2011-08-18 17:00 | 2011-07-25 17:00 | 2011-07-26 11:00 | 2011-07-26 14:00 | 188783.28 | 189262.6507 | 189392.0858 | 189263.454 | 189900.0956 | 189765.4129 | 189288.2889 | 189262.8114 | 0.955 | 0.95507 | 0.94362 | 1 | -18 | 0.95507 | 1 | 0.955 | 1
11/08, 2011 | 2011-07-14 17:00 | 2011-08-11 17:00 | 180759.44 | 170569.08 | 178592.92 | 2011-06-20 17:00 | -10190.36 | 94.36% | -8023.84 | 95.51% | -38d | 90.95% | 100% | 2011-07-29 16:00 | 2011-08-02 10:00 | 2011-08-29 14:00 | 2011-09-14 14:00 | 2011-09-16 09:00 | 2011-09-19 10:00 | 2011-08-22 17:00 | 2011-08-23 15:00 | 2011-08-23 17:00 | 188783.28 | 189262.6507 | 189392.0858 | 189796.9807 | 189900.0956 | 190324.0375 | 189288.2889 | 189365.4002 | 0.90952 | 0.95507 | 0.94362 | 1 | -38 | 0.95507 | 1 | 0.90952 | 1
08/09, 2011 | 2011-08-11 17:00 | 2011-09-08 17:00 | 180759.44 | 172251.28 | 181673.06 | 2011-06-28 12:00 | -8508.16 | 95.29% | -9421.78 | 94.81% | -52d 4h | 88.07% | 100% | 2011-07-26 10:00 | 2011-07-27 10:00 | 2011-08-26 12:00 | 2011-10-07 15:00 | 2011-10-10 15:00 | 2011-10-11 16:00 | 2011-09-12 12:00 | 2011-09-12 15:00 | 2011-09-12 15:00 | 190181.22 | 190646.5983 | 190601.4711 | 191333.9385 | 191089.8362 | 191862.368 | 190637.5364 | 190776.1291 | 0.88068 | 0.94814 | 0.95293 | 1 | -52.5 | 0.94814 | 1 | 0.88068 | 1
Actual Schedule | 2011-09-08 17:00 | 2011-09-15 20:00 | 180759.44 | 180759.44 | 191065.06 | 2011-06-29 17:00 | 0 | 100% | -10305.62 | 94.61% | -56d | 87.42% | 100% | 2011-06-29 17:00 | 2011-06-29 17:00 | 2011-08-01 09:00 | 2011-09-15 17:00 | 2011-09-15 17:00 | 2011-09-15 17:00 | 2011-09-15 17:00 | 2011-09-15 17:00 | 2011-09-15 17:00 | 191065.06 | 191065.06 | 191065.06 | 191065.06 | 191065.06 | 191065.06 | 191065.06 | 191065.06 | 0.87416 | 0.94606 | 1 | 1 | -56 | 0.94606 | 1 | 0.87416 | 1