## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Commercial IT Project | 1 |  |  | 2010-10-19 08:00 | 2011-01-05 14:00 | 56d 5h |  |  | 20300 |  |  | 33622.8 | 78.25
22 | Explore the market | 1.1 |  | FS23 | 2010-10-19 08:00 | 2010-11-01 17:00 | 10d |  | 0 | 4000 | 0 | 0 | 4000 | 13.375
23 | Set up a survey | 1.2 | 22FS | FS24 | 2010-11-02 08:00 | 2010-11-04 17:00 | 3d |  | 0 | 2000 | 0 | 0 | 2000 | 2.375
24 | Analysis of the market | 1.3 | 23FS | FS1 | 2010-11-05 08:00 | 2010-11-25 17:00 | 15d |  | 0 | 1000 | 0 | 0 | 1000 | 20.375
1 | Problem study/analysis | 1.4 | 24FS | FS2;FS3;FS39;FS40 | 2010-11-26 08:00 | 2010-11-30 17:00 | 3d | Analyst programmer;IT Manager[0.20 #1] | 595.2 | 0 | 0 | 0 | 595.2 | 4.375
39 | Negotiate and buy server | 1.5 | 1FS | FS41 | 2010-12-01 08:00 | 2010-12-02 17:00 | 2d | Marketing manager[0.50 #1];IT Manager[0.10 #1] | 286.4 | 10000 | 0 | 0 | 10286.4 | 1.375
40 | Negotiate and buy computer | 1.6 | 1FS | FS42 | 2010-12-01 08:00 | 2010-12-02 17:00 | 2d | IT Manager[0.10 #1];Marketing manager[0.50 #1] | 286.4 | 3000 | 0 | 0 | 3286.4 | 1.375
2 | Processmodels (BPMN) | 1.7 | 1FS | FS4;FS7 | 2010-12-01 08:00 | 2010-12-01 16:00 | 7h | Analyst programmer | 133 | 0 | 0 | 0 | 133 | 0.33333
3 | Conceptual datamodel (ER) | 1.8 | 1FS | FS4;FS7 | 2010-12-01 08:00 | 2010-12-01 17:00 | 1d | Analyst programmer | 152 | 0 | 0 | 0 | 152 | 0.375
4 | Normalisation DB | 1.9 | 2FS;3FS | FS5 | 2010-12-02 08:00 | 2010-12-02 12:00 | 4h | Database administrator | 76 | 0 | 0 | 0 | 76 | 0.16667
5 | Datamap | 1.10 | 4FS | FS6 | 2010-12-02 13:00 | 2010-12-02 14:00 | 1h | Analyst programmer[0.50 #1];Database administrator[0.50 #1] | 19 | 0 | 0 | 0 | 19 | 0.041667
6 | Logic Databasemodel | 1.11 | 5FS | FS8;FS9 | 2010-12-02 14:00 | 2010-12-02 16:00 | 2h | Database administrator | 38 | 0 | 0 | 0 | 38 | 0.083333
7 | Software design (UML-class diagram) | 1.12 | 2FS;3FS | FS10;FS11 | 2010-12-02 08:00 | 2010-12-03 17:00 | 2d | Analyst programmer[0.30 #1] | 91.2 | 0 | 0 | 0 | 91.2 | 1.375
8 | Develop Database Tables 1 | 1.13 | 6FS | FS12 | 2010-12-02 16:00 | 2010-12-03 14:00 | 6h | Database administrator | 114 | 0 | 0 | 0 | 114 | 0.91667
9 | Develop Database Tables 2 | 1.14 | 6FS | FS13 | 2010-12-02 16:00 | 2010-12-03 16:00 | 1d | Database administrator | 152 | 0 | 0 | 0 | 152 | 1
10 | Design & Develop GUI 1 | 1.15 | 7FS | FS18;FS25;FS26 | 2010-12-06 08:00 | 2010-12-07 17:00 | 2d | Programmers | 272 | 0 | 0 | 0 | 272 | 1.375
11 | Design & Develop GUI 2 | 1.16 | 7FS | FS19;FS25;FS26 | 2010-12-06 08:00 | 2010-12-08 14:00 | 2d 5h | Programmers[1.50 #3] | 535.5 | 0 | 0 | 0 | 535.5 | 2.25
25 | Design CD-box | 1.17 | 10FS;11FS |  | 2010-12-08 14:00 | 2010-12-22 14:00 | 10d |  | 0 | 250 | 0 | 0 | 250 | 14
26 | Design CD-labels | 1.18 | 10FS;11FS |  | 2010-12-08 14:00 | 2010-12-22 14:00 | 10d |  | 0 | 50 | 0 | 0 | 50 | 14
12 | Develop SQL's 1 | 1.19 | 8FS | FS14 | 2010-12-03 14:00 | 2010-12-07 16:00 | 2d 2h | Database administrator[0.40 #1] | 136.8 | 0 | 0 | 0 | 136.8 | 4.0833
13 | Develop SQL's 2 | 1.20 | 9FS | FS15 | 2010-12-03 16:00 | 2010-12-08 11:00 | 2d 4h | Database administrator[0.60 #1] | 228 | 0 | 0 | 0 | 228 | 4.7917
14 | Debug SQL’s 1 | 1.21 | 12FS | FS16 | 2010-12-07 16:00 | 2010-12-09 09:00 | 1d 2h | Database administrator[0.40 #1] | 76 | 0 | 0 | 0 | 76 | 1.7083
15 | Debug SQL’s 2 | 1.22 | 13FS | FS17 | 2010-12-08 11:00 | 2010-12-09 16:00 | 1d 4h | Database administrator[0.60 #1] | 136.8 | 0 | 0 | 0 | 136.8 | 1.2083
16 | Implement SQL’s in JAVA 1 | 1.23 | 14FS | FS18 | 2010-12-09 09:00 | 2010-12-09 10:00 | 1h | Programmers[2.00 #3] | 34 | 0 | 0 | 0 | 34 | 0.041667
17 | Implement SQL’s in JAVA 2 | 1.24 | 15FS | FS19 | 2010-12-09 16:00 | 2010-12-09 17:00 | 1h | Programmers[2.50 #3] | 42.5 | 0 | 0 | 0 | 42.5 | 0.041667
18 | Develop program 1 | 1.25 | 16FS;10FS | FS20 | 2010-12-09 10:00 | 2010-12-14 10:00 | 3d | Programmers[2.00 #3] | 816 | 0 | 0 | 0 | 816 | 5
19 | Develop program 2 | 1.26 | 17FS;11FS | FS21 | 2010-12-10 08:00 | 2010-12-15 14:00 | 3d 5h | Programmers[3.00 #3] | 1479 | 0 | 0 | 0 | 1479 | 5.25
20 | Testing & Debugging 1 | 1.27 | 18FS | FS27;FS37;FS38 | 2010-12-14 10:00 | 2010-12-15 10:00 | 1d | Programmers[2.00 #3] | 272 | 0 | 0 | 0 | 272 | 1
21 | Testing & Debugging 2 | 1.28 | 19FS | FS27;FS37;FS38 | 2010-12-15 14:00 | 2010-12-16 14:00 | 1d | Programmers[3.00 #3] | 408 | 0 | 0 | 0 | 408 | 1
38 | Visitations by sales representatives | 1.29 | 20FS;21FS |  | 2010-12-16 14:00 | 2010-12-30 14:00 | 10d | Sales representatives[2.00 #2] | 2400 | 0 | 0 | 0 | 2400 | 14
37 | Direct mailings | 1.30 | 20FS;21FS |  | 2010-12-16 14:00 | 2010-12-16 16:00 | 2h | Secretary;Marketing manager[0.50 #1] | 52 | 0 | 0 | 0 | 52 | 0.083333
27 | Make up report + presentation Alpha version | 1.31 | 20FS;21FS | FS28 | 2010-12-16 14:00 | 2010-12-20 14:00 | 2d | Secretary;Analyst programmer[0.30 #1] | 267.2 | 0 | 0 | 0 | 267.2 | 4
28 | Presentation Alpha version | 1.32 | 27FS | FS29 | 2010-12-20 14:00 | 2010-12-20 16:00 | 2h | IT Manager;Analyst programmer | 96 | 0 | 0 | 0 | 96 | 0.083333
29 | Reading of management report + Approval Alpha | 1.33 | 28FS | FS31 | 2010-12-20 16:00 | 2010-12-21 12:00 | 5h | IT Manager[0.50 #1] | 72.5 | 0 | 0 | 0 | 72.5 | 0.83333
31 | Testing phase Alpha version | 1.34 | 29FS | FS32 | 2010-12-21 13:00 | 2010-12-24 12:00 | 3d | Programmers[2.00 #3];Database administrator[0.30 #1];Analyst programmer[0.10 #1] | 998.4 | 0 | 0 | 0 | 998.4 | 2.9583
32 | Fix outstanding problems from Alpha | 1.35 | 31FS | FS33 | 2010-12-24 13:00 | 2010-12-27 15:00 | 1d 2h | Programmers | 170 | 0 | 0 | 0 | 170 | 3.0833
33 | Make up Report+ presentation Beta version | 1.36 | 32FS | FS34 | 2010-12-27 15:00 | 2010-12-28 15:00 | 1d | Secretary;Analyst programmer[0.20 #1] | 118.4 | 0 | 0 | 0 | 118.4 | 1
34 | Presentation Beta version | 1.37 | 33FS | FS35 | 2010-12-28 15:00 | 2010-12-28 17:00 | 2h | IT Manager;Analyst programmer | 96 | 0 | 0 | 0 | 96 | 0.083333
35 | Reading of management report + Approval Beta | 1.38 | 34FS | FS36;FS41;FS42 | 2010-12-29 08:00 | 2010-12-29 14:00 | 5h | IT Manager[0.50 #1] | 72.5 | 0 | 0 | 0 | 72.5 | 0.25
36 | Launch and installation Beta version | 1.39 | 35FS |  | 2010-12-29 14:00 | 2011-01-05 14:00 | 5d | Technicians[3.00 #3] | 1560 | 0 | 0 | 0 | 1560 | 7
41 | Installation server | 1.40 | 35FS;39FS |  | 2010-12-29 14:00 | 2011-01-05 14:00 | 5d | Technicians | 520 | 0 | 0 | 0 | 520 | 7
42 | Installation computer | 1.41 | 35FS;40FS |  | 2010-12-29 14:00 | 2011-01-05 14:00 | 5d | Technicians | 520 | 0 | 0 | 0 | 520 | 7

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Programmers | Renewable | 3 Programmers | 0 | 17 | 10;11[1.50 Programmers];16[2.00 Programmers];17[2.50 Programmers];18[2.00 Programmers];19[3.00 Programmers];20[2.00 Programmers];21[3.00 Programmers];31[2.00 Programmers];32; | 4845
2 | IT Manager | Renewable | 1 IT Manager | 0 | 29 | 1[0.20 IT Manager];39[0.10 IT Manager];40[0.10 IT Manager];28;29[0.50 IT Manager];34;35[0.50 IT Manager]; | 493
3 | Database administrator | Renewable | 1 Database administrator | 0 | 19 | 4;5[0.50 Database administrator];6;8;9;12[0.40 Database administrator];13[0.60 Database administrator];14[0.40 Database administrator];15[0.60 Database administrator];31[0.30 Database administrator]; | 1103.9
4 | Analyst programmer | Renewable | 1 Analyst programmer | 0 | 19 | 1;2;3;5[0.50 Analyst programmer];7[0.30 Analyst programmer];27[0.30 Analyst programmer];28;31[0.10 Analyst programmer];33[0.20 Analyst programmer];34; | 1084.9
5 | Secretary | Renewable | 1 Secretary | 0 | 11 | 37;27;33; | 286
6 | Marketing manager | Renewable | 1 Marketing manager | 0 | 30 | 39[0.50 Marketing manager];40[0.50 Marketing manager];37[0.50 Marketing manager]; | 510
7 | Sales representatives | Renewable | 2 Sales representatives | 0 | 15 | 38[2.00 Sales representatives]; | 2400
8 | Technicians | Renewable | 3 Technicians | 0 | 13 | 36[3.00 Technicians];41;42; | 2600

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Commercial IT Project | 453h |  |  |  |  | 99 | 100 | 101
22 | Explore the market | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Set up a survey | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Analysis of the market | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Problem study/analysis | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Negotiate and buy server | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Negotiate and buy computer | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Processmodels (BPMN) | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Conceptual datamodel (ER) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Normalisation DB | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Datamap | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Logic Databasemodel | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Software design (UML-class diagram) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Develop Database Tables 1 | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Develop Database Tables 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Design & Develop GUI 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Design & Develop GUI 2 | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Design CD-box | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Design CD-labels | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Develop SQL's 1 | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Develop SQL's 2 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Debug SQL’s 1 | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Debug SQL’s 2 | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Implement SQL’s in JAVA 1 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Implement SQL’s in JAVA 2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Develop program 1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Develop program 2 | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Testing & Debugging 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Testing & Debugging 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Visitations by sales representatives | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Direct mailings | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Make up report + presentation Alpha version | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Presentation Alpha version | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Reading of management report + Approval Alpha | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Testing phase Alpha version | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Fix outstanding problems from Alpha | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Make up Report+ presentation Beta version | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Presentation Beta version | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Reading of management report + Approval Beta | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Launch and installation Beta version | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Installation server | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Installation computer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold