## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Building a House | 1 |  |  | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 | 312.2917
33 | Dummy | 1.1 |  | FS1;FS2 | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
1 | Moving tanks | 1.2 | 33FS | FS32 | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 33.1667
2 | Masonry draining (foundations) | 1.3 | 33FS | FS12 | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 32.375
3 | Masonry draining (interior walls) | 1.4 | 12FS | FS6;FS4 | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 76.375
4 | Masonry draining (exterior walls) | 1.5 | 3FS | FS5;FS7 | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 13.375
5 | Masonry draining (clean up) | 1.6 | 4FS | FS8 | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 1.1667
6 | Roofing + Frame | 1.7 | 3FS | FS9 | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 36.1667
7 | Sanitary (foundations) | 1.8 | 4FS | FS8 | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 37.1667
8 | Carpentry outside (part 1) | 1.9 | 5FS;7FS | FS14;FS9 | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 7.375
9 | Carpentry outside (part 2) | 1.10 | 6FS;8FS | FS10;FS13 | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 1.1667
10 | Carpentry outside (part 3) | 1.11 | 9FS | FS11;FS15 | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 6.375
11 | Carpentry outside (part 4) | 1.12 | 10FS | FS16 | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 5.375
12 | Heating under title floor | 1.13 | 2FS | FS3 | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 6.375
13 | Sanitary + heating phase 1 | 1.14 | 9FS | FS16 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 13.1667
14 | Ventilation phase 1 | 1.15 | 8FS | FS22 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 13.375
15 | Electricity phase 1 | 1.16 | 10FS | FS21 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 26.375
16 | Ceiling - False ceiling | 1.17 | 11FS;13FS | FS17 | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 23.375
17 | Isolated screen | 1.18 | 16FS | FS18 | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 6.375
18 | Screed | 1.19 | 17FS | FS19;FS21;FS22;FS20 | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 4.375
19 | Screed (clean up) | 1.20 | 18FS | FS23 | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 1.0833
20 | Sanitary phase 2 (part 1) | 1.21 | 18FS | FS25;FS23 | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 20.2917
21 | Electricity phase 2 (part 1) | 1.22 | 15FS;18FS | FS26;FS23 | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 20.2917
22 | Ventilation phase 2 (part 1) | 1.23 | 14FS;18FS | FS27;FS23 | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 20.2917
23 | Carpentry inside | 1.24 | 19FS;20FS;21FS;22FS | FS24;FS30 | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 | 13.375
24 | Carpentry inside (clean up) | 1.25 | 23FS | FS31 | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 | 4.1667
25 | Sanitary phase 2 (part 2) | 1.26 | 20FS | FS28;FS30 | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 26
26 | Electricity phase 2 (part 2) | 1.27 | 21FS | FS29;FS30 | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 | 4
27 | Ventilation phase 2 (part 2) | 1.28 | 22FS | FS30 | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 14.875
28 | Sanitary phase 2 (clean up) | 1.29 | 25FS | FS31 | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 | 3
29 | Electricity phase 2 (clean up) | 1.30 | 26FS | FS31 | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 | 0.29167
30 | Painting part 1 | 1.31 | 23FS;25FS;26FS;27FS | FS31;FS32 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 | 6.7917
31 | Painting (clean up) | 1.32 | 24FS;28FS;29FS;30FS | FS34 | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 | 0.375
32 | Total clean up | 1.33 | 1FS;30FS | FS34 | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 | 11.2083
34 | Dummy | 1.34 | 31FS;32FS |  | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Workforce | Renewable | 6 | 0 | 15.5 | 1[2.00 Workforce];2[4.00 Workforce];3[5.00 Workforce];4[5.00 Workforce];5[3.33 Workforce];6[4.00 Workforce];7[1.71 Workforce];8[6.00 Workforce];9[6.00 Workforce];10[3.00 Workforce];11[3.00 Workforce];12[3.00 Workforce];13[6.00 Workforce];14[2.00 Workforce];15[3.00 Workforce];16[3.00 Workforce];17[3.00 Workforce];18[4.00 Workforce];19[2.40 Workforce];20[1.71 Workforce];21[1.71 Workforce];22[1.14 Workforce];23[3.00 Workforce];24[2.40 Workforce];25[1.71 Workforce];26[6.00 Workforce];27[1.14 Workforce];28[3.00 Workforce];29[4.00 Workforce];30[4.00 Workforce];31[4.00 Workforce];32[2.00 Workforce]; | 124124

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Building a House | 1558h |  |  |  |  | 99 | 100 | 101
33 | Dummy | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Moving tanks | 180h | manual - absolute | 110 | 120 | 130 | 61 | 66 | 72
2 | Masonry draining (foundations) | 176h | manual - absolute | 162 | 176 | 190 | 92 | 100 | 107
3 | Masonry draining (interior walls) | 392h | manual - absolute | 360 | 392 | 424 | 91 | 100 | 108
4 | Masonry draining (exterior walls) | 80h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
5 | Masonry draining (clean up) | 12h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
6 | Roofing + Frame | 132h | manual - absolute | 141 | 314 | 386 | 106 | 237 | 292
7 | Sanitary (foundations) | 140h | manual - absolute | 64 | 253 | 316 | 45 | 180 | 225
8 | Carpentry outside (part 1) | 48h | manual - absolute | 77 | 245 | 311 | 160 | 510 | 647
9 | Carpentry outside (part 2) | 12h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
10 | Carpentry outside (part 3) | 40h | manual - absolute | 32 | 40 | 48 | 80 | 100 | 120
11 | Carpentry outside (part 4) | 32h | manual - absolute | 24 | 32 | 40 | 75 | 100 | 125
12 | Heating under title floor | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Sanitary + heating phase 1 | 76h | manual - absolute | 133 | 152 | 171 | 175 | 200 | 225
14 | Ventilation phase 1 | 80h | manual - absolute | 70 | 80 | 90 | 87 | 100 | 112
15 | Electricity phase 1 | 152h | manual - absolute | 133 | 152 | 171 | 87 | 100 | 112
16 | Ceiling - False ceiling | 144h | manual - absolute | 120 | 144 | 168 | 83 | 100 | 116
17 | Isolated screen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Screed | 24h | manual - absolute | 24 | 32 | 40 | 100 | 133 | 166
19 | Screed (clean up) | 10h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
20 | Sanitary phase 2 (part 1) | 70h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Electricity phase 2 (part 1) | 70h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Ventilation phase 2 (part 1) | 70h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Carpentry inside | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Carpentry inside (clean up) | 20h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
25 | Sanitary phase 2 (part 2) | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Electricity phase 2 (part 2) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Ventilation phase 2 (part 2) | 70h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Sanitary phase 2 (clean up) | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
29 | Electricity phase 2 (clean up) | 6h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
30 | Painting part 1 | 28h | manual - absolute | 49 | 56 | 61 | 175 | 200 | 217
31 | Painting (clean up) | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
32 | Total clean up | 60h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
34 | Dummy | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-08-11 17:00 |  | TP Name | 11/08/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 5d | [5 empty] | 39004.6699 |  | 8.045% |  | 38967.7192 | 39004.6699
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 5d | 32692.6699 | 2790 | 11d 2h | 0 | 0 | 32692.6699 | 2790 | 30.77% | Started | 33169.5931 | 32692.6699 | 100 | 22.2222 | 30.7692 | 100 | 88.2806 | 30.7692
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 5d | 6312 | 11284 | 22d 6h | 0 | 0 | 6312 | 11284 | 18.02% | Started | 5798.1261 | 6312 | 100 | 22.7273 | 18.018 | 100 | 42.8106 | 18.018
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 |  | 0 | 0 | 118606.9531 | 49d | 0 | 0 | 0 | 118606.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 |  | 0 | 0 | 7039.1001 | 5d | 0 | 0 | 0 | 7039.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-08-19 17:00 |  | TP Name | 19/08/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 10d | [5 empty] | 42724.6699 |  | 8.805% |  | 42650.7684 | 42724.6699
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 10d | 33932.6699 | 1550 | 6d 2h | 0 | 0 | 33932.6699 | 1550 | 61.54% | Started | 34886.5162 | 33932.6699 | 100 | 44.4444 | 61.5385 | 100 | 91.629 | 61.5385
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 10d | 8792 | 8804 | 17d 6h | 0 | 0 | 8792 | 8804 | 36.04% | Started | 7764.2522 | 8792 | 100 | 45.4545 | 36.036 | 100 | 59.631 | 36.036
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 |  | 0 | 0 | 118606.9531 | 49d | 0 | 0 | 0 | 118606.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 |  | 0 | 0 | 7039.1001 | 5d | 0 | 0 | 0 | 7039.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-08-26 17:00 |  | TP Name | 26/08/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 15d | [5 empty] | 46444.6699 |  | 9.565% |  | 46333.8173 | 46444.6699
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 15d | 35172.6699 | 310 | 1d 2h | 0 | 0 | 35172.6699 | 310 | 92.31% | Started | 36603.4392 | 35172.6699 | 100 | 66.6667 | 92.3077 | 100 | 94.9774 | 92.3077
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 15d | 11272 | 6324 | 12d 6h | 0 | 0 | 11272 | 6324 | 54.05% | Started | 9730.3781 | 11272 | 100 | 68.1818 | 54.0541 | 100 | 76.4514 | 54.0541
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 |  | 0 | 0 | 118606.9531 | 49d | 0 | 0 | 0 | 118606.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 |  | 0 | 0 | 7039.1001 | 5d | 0 | 0 | 0 | 7039.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-09-02 17:00 |  | TP Name | 2/09/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 20d | [5 empty] | 49234.6699 |  | 10.06% |  | 48729.1743 | 50164.6699
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 36412.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 20d | 13752 | 3844 | 7d 6h | 0 | 0 | 13752 | 3844 | 72.07% | Started | 11696.5044 | 13752 | 100 | 90.9091 | 72.0721 | 100 | 93.2718 | 72.0721
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 |  | 0 | 0 | 118606.9531 | 49d | 0 | 0 | 0 | 118606.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 |  | 0 | 0 | 7039.1001 | 5d | 0 | 0 | 0 | 7039.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-09-09 17:00 |  | TP Name | 9/09/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 25d | [5 empty] | 51714.6699 |  | 10.47% |  | 50695.3005 | 58071.77
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 25d | 16232 | 1364 | 2d 6h | 0 | 0 | 16232 | 1364 | 90.09% | Started | 13662.6306 | 14744 | 100 | 113.6364 | 90.0901 | 100 | 110.0922 | 90.0901
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 |  | 0 | 0 | 118606.9531 | 49d | 0 | 0 | 0 | 118606.9531 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 |  | 0 | 0 | 7039.1001 | 5d | 0 | 0 | 0 | 7039.1001 | 0% | Not Started | 0 | 6295.1001 | 100 |  | 0 | 100 |  | 0
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2011-09-16 17:00 |  | TP Name | 16/09/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 30d | [5 empty] | 59094.77 |  | 11.9% |  | 57653.27 | 148902.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 |  | 0 | 0 | 118606.9531 | 49d | 0 | 0 | 0 | 118606.9531 | 0% | Not Started | 0 | 90086.9531 | 100 |  | 0 | 100 |  | 0
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 2d 2h | 6016.1001 | 1395 | 3d 6h | 0 | 0 | 6016.1001 | 1395 | 37.5% | Started | 5876.6001 | 7039.1001 | 100 | 45 | 37.5 | 100 | 85.4669 | 37.5
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2011-09-23 17:00 |  | TP Name | 23/09/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 35d | [5 empty] | 149491.7231 |  | 30.47% |  | 147599.1334 | 152002.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 1d 2h | 89001.9531 | 41540 | 67d | 0 | 0 | 89001.9531 | 41540 | 1.832% | Started | 88783.3634 | 93186.9531 | 100 | 2.551 | 1.8315 | 100 | 75.0394 | 1.8315
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2011-09-30 17:00 |  | TP Name | 30/09/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 40d | [5 empty] | 152591.7231 |  | 30.93% |  | 149824.7745 | 155102.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 6d 2h | 92101.9531 | 38440 | 62d | 0 | 0 | 92101.9531 | 38440 | 9.158% | Started | 91009.0045 | 96286.9531 | 100 | 12.7551 | 9.1575 | 100 | 77.6531 | 9.1575
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2011-10-07 17:00 |  | TP Name | 7/10/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 45d | [5 empty] | 155691.7231 |  | 31.39% |  | 152050.4156 | 158202.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 11d 2h | 95201.9531 | 35340 | 57d | 0 | 0 | 95201.9531 | 35340 | 16.48% | Started | 93234.6456 | 99386.9531 | 100 | 22.9592 | 16.4835 | 100 | 80.2668 | 16.4835
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2011-10-14 17:00 |  | TP Name | 14/10/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 50d | [5 empty] | 158791.7231 |  | 31.85% |  | 154276.0565 | 161302.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 16d 2h | 98301.9531 | 32240 | 52d | 0 | 0 | 98301.9531 | 32240 | 23.81% | Started | 95460.2865 | 102486.9531 | 100 | 33.1633 | 23.8095 | 100 | 82.8804 | 23.8095
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2011-10-21 17:00 |  | TP Name | 21/10/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 55d | [5 empty] | 161891.7231 |  | 32.31% |  | 156501.6978 | 164402.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 21d 2h | 101401.9531 | 29140 | 47d | 0 | 0 | 101401.9531 | 29140 | 31.14% | Started | 97685.9278 | 105586.9531 | 100 | 43.3673 | 31.1355 | 100 | 85.4941 | 31.1355
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2011-10-28 17:00 |  | TP Name | 28/10/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 60d | [5 empty] | 164991.7231 |  | 32.77% |  | 158727.3387 | 167502.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 26d 2h | 104501.9531 | 26040 | 42d | 0 | 0 | 104501.9531 | 26040 | 38.46% | Started | 99911.5687 | 108686.9531 | 100 | 53.5714 | 38.4615 | 100 | 88.1078 | 38.4615
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2011-11-14 17:00 |  | TP Name | 14/11/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 65d | [5 empty] | 168091.7231 |  | 33.23% |  | 160952.9796 | 170602.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 31d 2h | 107601.9531 | 22940 | 37d | 0 | 0 | 107601.9531 | 22940 | 45.79% | Started | 102137.2096 | 111786.9531 | 100 | 63.7755 | 45.7875 | 100 | 90.7215 | 45.7875
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2011-11-21 17:00 |  | TP Name | 21/11/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 70d | [5 empty] | 171191.7231 |  | 33.69% |  | 163178.6214 | 173702.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 36d 2h | 110701.9531 | 19840 | 32d | 0 | 0 | 110701.9531 | 19840 | 53.11% | Started | 104362.8514 | 114886.9531 | 100 | 73.9796 | 53.1136 | 100 | 93.3351 | 53.1136
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2011-11-28 17:00 |  | TP Name | 28/11/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 75d | [5 empty] | 174291.7231 |  | 34.15% |  | 165404.2623 | 176802.7231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 41d 2h | 113801.9531 | 16740 | 27d | 0 | 0 | 113801.9531 | 16740 | 60.44% | Started | 106588.4923 | 117986.9531 | 100 | 84.1837 | 60.4396 | 100 | 95.9488 | 60.4396
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2011-12-05 17:00 |  | TP Name | 5/12/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 80d | [5 empty] | 177391.7231 |  | 34.61% |  | 167629.9032 | 197908.2231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 46d 2h | 116901.9531 | 13640 | 22d | 0 | 0 | 116901.9531 | 13640 | 67.77% | Started | 108814.1332 | 118606.9531 | 100 | 94.3878 | 67.7656 | 100 | 98.5625 | 67.7656
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 20485.5 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2011-12-12 17:00 |  | TP Name | 12/12/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 85d | [5 empty] | 180491.7231 |  | 35.07% |  | 169855.5441 | 201008.2231
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 51d 2h | 120001.9531 | 10540 | 17d | 0 | 0 | 120001.9531 | 10540 | 75.09% | Started | 111039.7741 | 118606.9531 | 100 | 104.5918 | 75.0916 | 100 | 101.1762 | 75.0916
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 23585.5 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2011-12-19 17:00 |  | TP Name | 19/12/2011 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 90d | [5 empty] | 183591.7231 |  | 35.52% |  | 172081.185 | 257849.3682
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 56d 2h | 123101.9531 | 7440 | 12d | 0 | 0 | 123101.9531 | 7440 | 82.42% | Started | 113265.415 | 118606.9531 | 100 | 114.7959 | 82.4176 | 100 | 103.7898 | 82.4176
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 24205.5 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 27375.2793 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 28845.8658 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2012-01-09 17:00 |  | TP Name | 9/01/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 95d | [5 empty] | 186691.7231 |  | 35.98% |  | 174306.8259 | 261392.2254
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 61d 2h | 126201.9531 | 4340 | 7d | 0 | 0 | 126201.9531 | 4340 | 89.74% | Started | 115491.0559 | 118606.9531 | 100 | 125 | 89.7436 | 100 | 106.4035 | 89.7436
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 24205.5 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 29855.2793 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 29908.723 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2012-01-16 17:00 |  | TP Name | 16/01/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 100d | [5 empty] | 189791.7231 |  | 36.44% |  | 176532.4668 | 264935.0825
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 66d 2h | 129301.9531 | 1240 | 2d | 0 | 0 | 129301.9531 | 1240 | 97.07% | Started | 117716.6968 | 118606.9531 | 100 | 135.2041 | 97.0696 | 100 | 109.0172 | 97.0696
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 |  | 0 | 0 | 24205.5 | 10d | 0 | 0 | 0 | 24205.5 | 0% | Not Started | 0 | 24205.5 | 100 |  | 0 | 100 |  | 0
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 |  | 0 | 0 | 33575.2793 | 16d 4h | 0 | 0 | 0 | 33575.2793 | 0% | Not Started | 0 | 32335.2793 | 100 |  | 0 | 100 |  | 0
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 30971.5801 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2012-01-23 17:00 |  | TP Name | 23/01/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 105d | [5 empty] | 237776.5024 |  | 46.27% |  | 224148.5413 | 296140.2322
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 3d | 19865.5 | 3875 | 6d 2h | 0 | 0 | 19865.5 | 3875 | 32.43% | Started | 20016.3107 | 24205.5 | 100 | 30 | 32.4324 | 100 | 82.0702 | 32.4324
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 2420.55 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 3d | 26879.2793 | 7750 | 15d 5h | 0 | 0 | 26879.2793 | 7750 | 16.11% | Started | 26709.5074 | 33575.2793 | 100 | 18.1818 | 16.1074 | 100 | 80.0568 | 16.1074
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 31715.5801 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 26800.5996 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2012-01-30 17:00 |  | TP Name | 30/01/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 110d | [5 empty] | 243356.5024 |  | 47.42% |  | 229696.9399 | 299860.2322
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 8d | 22965.5 | 775 | 1d 2h | 0 | 0 | 22965.5 | 775 | 86.49% | Started | 23367.6623 | 24205.5 | 100 | 80 | 86.4865 | 100 | 94.8772 | 86.4865
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 |  | 0 | 0 | 2420.55 | 1d 4h | 0 | 0 | 0 | 2420.55 | 0% | Not Started | 0 | 2420.55 | 100 |  | 0 | 100 |  | 0
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 8d | 29359.2793 | 5270 | 10d 5h | 0 | 0 | 29359.2793 | 5270 | 42.95% | Started | 28906.5545 | 33575.2793 | 100 | 48.4848 | 42.953 | 100 | 87.4431 | 42.953
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 |  | 0 | 0 | 31715.5801 | 17d 4h | 0 | 0 | 0 | 31715.5801 | 0% | Not Started | 0 | 31715.5801 | 100 |  | 0 | 100 |  | 0
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 30520.5996 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2012-02-06 17:00 |  | TP Name | 6/02/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 115d | [5 empty] | 277824.7754 |  | 54.51% |  | 264040.7549 | 329774.9719
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 13d | 31839.2793 | 2790 | 5d 5h | 0 | 0 | 31839.2793 | 2790 | 69.8% | Started | 31103.6017 | 33575.2793 | 100 | 78.7879 | 69.7987 | 100 | 94.8295 | 69.7987
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 3d 6h | 28792.7229 | 2524.2857 | 11d 7h | 0 | 0 | 28792.7229 | 2524.2857 | 24% | Started | 28888.3801 | 31715.5801 | 100 | 21.4286 | 24 | 100 | 90.7842 | 24
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 30520.5996 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 7630.1499 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 22284.5898 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2012-02-13 17:00 |  | TP Name | 13/02/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 120d | [5 empty] | 281367.6326 |  | 55.21% |  | 267428.2016 | 333494.9719
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d | 34319.2793 | 310 | 5h | 0 | 0 | 34319.2793 | 310 | 96.64% | Started | 33300.6483 | 33575.2793 | 100 | 109.0909 | 96.6443 | 100 | 102.2159 | 96.6443
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 8d 6h | 29855.5801 | 1461.4286 | 6d 7h | 0 | 0 | 29855.5801 | 1461.4286 | 56% | Started | 30078.7801 | 31715.5801 | 100 | 50 | 56 | 100 | 94.1354 | 56
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 30520.5996 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 7630.1499 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 26004.5898 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2012-02-20 17:00 |  | TP Name | 20/02/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 125d | [5 empty] | 282740.4897 |  | 55.51% |  | 268893.2326 | 346583.8821
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 13d 6h | 30918.4373 | 398.5714 | 1d 7h | 0 | 0 | 30918.4373 | 398.5714 | 88% | Started | 31269.1801 | 31715.5801 | 100 | 78.5714 | 88 | 100 | 97.4866 | 88
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 |  | 0 | 0 | 30520.5996 | 6d | 0 | 0 | 0 | 30520.5996 | 0% | Not Started | 0 | 30520.5996 | 100 |  | 0 | 100 |  | 0
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 |  | 0 | 0 | 7630.1499 | 1d 4h | 0 | 0 | 0 | 7630.1499 | 0% | Not Started | 0 | 7630.1499 | 100 |  | 0 | 100 |  | 0
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 12344.9102 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 26748.5898 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 |  | 0 | 0 | 3762 | 10d | 0 | 0 | 0 | 3762 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2012-02-27 17:00 |  | TP Name | 27/02/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 130d | [5 empty] | 319347.8107 |  | 63.54% |  | 307773.6958 | 367532.6526
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1h | 6607.1499 | 1023 | 1d 3h | 0 | 0 | 6607.1499 | 1023 | 8.333% | Started | 6607.1499 | 7630.1499 | 100 | 8.3333 | 8.3333 | 100 | 86.5927 | 8.3333
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 |  | 0 | 0 | 12716.9102 | 5d | 0 | 0 | 0 | 12716.9102 | 0% | Not Started | 0 | 12716.9102 | 100 |  | 0 | 100 |  | 0
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 10173.5303 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 |  | 0 | 0 | 26748.5898 | 9d 4h | 0 | 0 | 0 | 26748.5898 | 0% | Not Started | 0 | 26748.5898 | 100 |  | 0 | 100 |  | 0
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 1h | 1313 | 3131 | 12d 5h | 0 | 0 | 1313 | 3131 | 0.9804% | Started | 1306.3137 | 0 | 100 | 1.25 | 0.98039 | 100 | 34.9016 | 0.98039
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 10403.2402 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2012-03-05 17:00 |  | TP Name | 5/03/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 135d | [5 empty] | 356193.8107 |  | 71.11% |  | 344471.8088 | 394226.1624
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 3d 5h | 12205.4102 | 186 | 4h | 0 | 0 | 12205.4102 | 186 | 87.88% | Started | 12491.4556 | 12716.9102 | 100 | 72.5 | 87.8788 | 100 | 95.9778 | 87.8788
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 |  | 0 | 0 | 10173.5303 | 4d | 0 | 0 | 0 | 10173.5303 | 0% | Not Started | 0 | 10173.5303 | 100 |  | 0 | 100 |  | 0
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 3d 5h | 22377.5898 | 4836 | 6d 4h | 0 | 0 | 22377.5898 | 4836 | 35.8% | Started | 22211.1083 | 26748.5898 | 100 | 38.1579 | 35.8025 | 100 | 83.659 | 35.8025
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 5d 1h | 2553 | 1891 | 7d 5h | 0 | 0 | 2553 | 1891 | 40.2% | Started | 2278.8628 | 0 | 100 | 51.25 | 40.1961 | 100 | 67.8628 | 40.1961
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 |  | 0 | 0 | 15983.2402 | 19d | 0 | 0 | 0 | 15983.2402 | 0% | Not Started | 0 | 12263.2402 | 100 |  | 0 | 100 |  | 0
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 24833.5098 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2012-03-12 17:00 |  | TP Name | 12/03/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 140d | [5 empty] | 381963.0812 |  | 76.49% |  | 370520.8105 | 397946.1624
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 8d 5h | 26097.5898 | 1116 | 1d 4h | 0 | 0 | 26097.5898 | 1116 | 85.19% | Started | 25701.4789 | 26748.5898 | 100 | 90.7895 | 85.1852 | 100 | 97.5662 | 85.1852
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 10d 1h | 3793 | 651 | 2d 5h | 0 | 0 | 3793 | 651 | 79.41% | Started | 3251.4117 | 0 | 100 | 101.25 | 79.4118 | 100 | 100.824 | 79.4118
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 4d 4h | 10589.2402 | 3534 | 9d 4h | 0 | 0 | 10589.2402 | 3534 | 32.14% | Started | 11187.0973 | 14123.2402 | 100 | 23.6842 | 32.1429 | 100 | 66.2521 | 32.1429
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 |  | 0 | 0 | 29669.5098 | 18d | 0 | 0 | 0 | 29669.5098 | 0% | Not Started | 0 | 26693.5098 | 100 |  | 0 | 100 |  | 0
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2012-03-19 17:00 |  | TP Name | 19/03/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 145d | [5 empty] | 409865.5909 |  | 82.31% |  | 398705.7508 | 401666.1624
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 0 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 9d 4h | 12449.2402 | 1674 | 4d 4h | 0 | 0 | 12449.2402 | 1674 | 67.86% | Started | 13711.3829 | 15983.2402 | 100 | 50 | 67.8571 | 100 | 77.8893 | 67.8571
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 3d 4h | 24275.5098 | 6417 | 17d 2h | 0 | 0 | 24275.5098 | 6417 | 16.87% | Started | 24102.9555 | 28553.5098 | 100 | 19.4444 | 16.8675 | 100 | 81.8197 | 16.8675
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP30
| TP Status Date | 2012-03-26 17:00 |  | TP Name | 26/03/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 150d | [5 empty] | 413399.5909 |  | 83.11% |  | 402591.1021 | 416810.2219
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 2522 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 8d 4h | 26135.5098 | 4557 | 12d 2h | 0 | 0 | 26135.5098 | 4557 | 40.96% | Started | 25716.4495 | 29669.5098 | 100 | 47.2222 | 40.9639 | 100 | 88.0888 | 40.9639
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 11506.0596 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP31
| TP Status Date | 2012-04-02 17:00 |  | TP Name | 2/04/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 155d | [5 empty] | 415259.5909 |  | 83.44% |  | 404204.596 | 429042.2122
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 13d 4h | 27995.5098 | 2697 | 7d 2h | 0 | 0 | 27995.5098 | 2697 | 65.06% | Started | 27329.9434 | 29669.5098 | 100 | 75 | 65.0602 | 100 | 94.3578 | 65.0602
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 12622.0596 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 9875.9902 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP32
| TP Status Date | 2012-04-17 17:00 |  | TP Name | 17/04/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 160d | [5 empty] | 417119.5909 |  | 83.78% |  | 405818.0902 | 440557.5439
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 18d 4h | 29855.5098 | 837 | 2d 2h | 0 | 0 | 29855.5098 | 837 | 89.16% | Started | 28943.4376 | 29669.5098 | 100 | 102.7778 | 89.1566 | 100 | 100.6269 | 89.1566
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 |  | 0 | 0 | 12622.0596 | 5d | 0 | 0 | 0 | 12622.0596 | 0% | Not Started | 0 | 12622.0596 | 100 |  | 0 | 100 |  | 0
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 10371.9902 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 6969.3544 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 2983.8344 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 1066.1429 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP33
| TP Status Date | 2012-04-24 17:00 |  | TP Name | 24/04/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 165d | [5 empty] | 429741.6505 |  | 86.35% |  | 418280.5077 | 443391.8297
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 2d 6h | 11785.0596 | 930 | 2d 4h | 0 | 0 | 11785.0596 | 930 | 52.38% | Started | 11736.3453 | 12622.0596 | 100 | 55 | 52.381 | 100 | 93.3688 | 52.381
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 |  | 0 | 0 | 10371.9902 | 3d | 0 | 0 | 0 | 10371.9902 | 0% | Not Started | 0 | 10371.9902 | 100 |  | 0 | 100 |  | 0
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 8032.2116 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 4046.6916 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 1774.7143 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP34
| TP Status Date | 2012-05-03 17:00 |  | TP Name | 3/05/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 170d | [5 empty] | 440795.6407 |  | 88.66% |  | 429467.355 | 460703.6167
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 4h | 10123.9902 | 62 | 1h | 0 | 0 | 10123.9902 | 62 | 95.24% | Started | 10301.1331 | 10371.9902 | 100 | 83.3333 | 95.2381 | 100 | 97.6089 | 95.2381
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 |  | 0 | 0 | 2593 | 1d 2h | 0 | 0 | 0 | 2593 | 0% | Not Started | 0 | 2593 | 100 |  | 0 | 100 |  | 0
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 |  | 0 | 0 | 8191.6402 | 8d 6h | 0 | 0 | 0 | 8191.6402 | 0% | Not Started | 0 | 8191.6402 | 100 |  | 0 | 100 |  | 0
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 |  | 0 | 0 | 4206.1201 | 8d 6h | 0 | 0 | 0 | 4206.1201 | 0% | Not Started | 0 | 4206.1201 | 100 |  | 0 | 100 |  | 0
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 1881.0001 | 100 |  | 0 | 100 |  | 0
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 2016.3 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 11034.0585 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 |  | 0 | 0 | 1881.0001 | 8d 6h | 0 | 0 | 0 | 1881.0001 | 0% | Not Started | 0 | 1243.2857 | 100 |  | 0 | 100 |  | 0
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP35
| TP Status Date | 2012-05-10 17:00 |  | TP Name | 10/05/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 175d | [5 empty] | 456062.2296 |  | 91.89% |  | 445093.1677 | 464264.1882
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 100% | Finished | 10371.9902 | 10371.9902 | 100 | 87.5 | 100 | 100 | 98.2067 | 100
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 100% | Finished | 2593 | 2593 | 100 | 70 | 100 | 100 | 95.6961 | 100
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 4d 7h | 7367.9259 | 903.4286 | 4d 2h | 0 | 0 | 7367.9259 | 903.4286 | 53.42% | Started | 7325.3388 | 8191.6402 | 100 | 55.7143 | 53.4247 | 100 | 89.9445 | 53.4247
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 4d 7h | 3382.4058 | 1594.2857 | 7d 4h | 0 | 0 | 3382.4058 | 1594.2857 | 39.39% | Started | 3078.8474 | 4206.1201 | 100 | 55.7143 | 39.3939 | 100 | 80.4163 | 39.3939
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 51.4286 | 100 | 100 | 67.9806 | 100
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 3876.3 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 |  | 0 | 0 | 13106.6299 | 14d | 0 | 0 | 0 | 13106.6299 | 0% | Not Started | 0 | 12096.9156 | 100 |  | 0 | 100 |  | 0
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 3h | 694.1429 | 1789.1429 | 12d 5h | 0 | 0 | 694.1429 | 1789.1429 | 2.885% | Started | 676.7692 | 1881.0001 | 100 | 4.2857 | 2.8846 | 100 | 36.9029 | 2.8846
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP36
| TP Status Date | 2012-05-21 17:00 |  | TP Name | 21/05/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 180d | [5 empty] | 469027.1453 |  | 94.44% |  | 457448.8729 | 470182.7726
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 100% | Finished | 10371.9902 | 10371.9902 | 100 | 87.5 | 100 | 100 | 98.2067 | 100
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 100% | Finished | 2593 | 2593 | 100 | 70 | 100 | 100 | 95.6961 | 100
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 9d 1h | 8271.3544 | 0 | 0 | 0 | 0 | 8271.3544 | 0 | 100% | Finished | 8191.6402 | 8191.6402 | 100 | 104.2857 | 100 | 100 | 100.9731 | 100
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 9d 7h | 4445.263 | 531.4286 | 2d 4h | 0 | 0 | 4445.263 | 531.4286 | 79.8% | Started | 3830.3625 | 4206.1201 | 100 | 112.8571 | 79.798 | 100 | 105.6856 | 79.798
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 51.4286 | 100 | 100 | 67.9806 | 100
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 |  | 0 | 0 | 3876.3 | 8d | 0 | 0 | 0 | 3876.3 | 0% | Not Started | 0 | 3876.3 | 100 |  | 0 | 100 |  | 0
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 969.08 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 2012-05-21 10:00 | 6h | 10290.0585 | 3480.8572 | 16d 3h | 0 | 0 | 10290.0585 | 3480.8572 | 4.38% | Started | 10260.9656 | 13106.6299 | 100 | 5.3571 | 4.3796 | 100 | 78.5103 | 4.3796
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 |  | 0 | 0 | 6729.79 | 4d | 0 | 0 | 0 | 6729.79 | 0% | Not Started | 0 | 3939.79 | 100 |  | 0 | 100 |  | 0
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 5d 3h | 1402.7143 | 1080.5715 | 7d 5h | 0 | 0 | 1402.7143 | 1080.5715 | 41.35% | Started | 1153.6923 | 1881.0001 | 100 | 61.4286 | 41.3462 | 100 | 74.5728 | 41.3462
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP37
| TP Status Date | 2012-05-29 17:00 |  | TP Name | 29/05/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 185d | [5 empty] | 478774.0925 |  | 96.37% |  | 466807.5677 | 474693.4526
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 100% | Finished | 10371.9902 | 10371.9902 | 100 | 87.5 | 100 | 100 | 98.2067 | 100
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 100% | Finished | 2593 | 2593 | 100 | 70 | 100 | 100 | 95.6961 | 100
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 9d 1h | 8271.3544 | 0 | 0 | 0 | 0 | 8271.3544 | 0 | 100% | Finished | 8191.6402 | 8191.6402 | 100 | 104.2857 | 100 | 100 | 100.9731 | 100
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 12d 3h | 4976.6916 | 0 | 0 | 0 | 0 | 4976.6916 | 0 | 100% | Finished | 4206.1201 | 4206.1201 | 100 | 141.4286 | 100 | 100 | 118.3202 | 100
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 51.4286 | 100 | 100 | 67.9806 | 100
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 | 2012-05-24 13:00 | 2d 4h | 1830.3 | 1534.5 | 4d 1h | 0 | 0 | 1830.3 | 1534.5 | 37.74% | Started | 2023.3189 | 3876.3 | 100 | 31.25 | 37.7358 | 100 | 47.2177 | 37.7358
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 |  | 0 | 0 | 969.08 | 2d 4h | 0 | 0 | 0 | 969.08 | 0% | Not Started | 0 | 969.08 | 100 |  | 0 | 100 |  | 0
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 2012-05-21 10:00 | 5d 6h | 11352.9156 | 2418 | 11d 3h | 0 | 0 | 11352.9156 | 2418 | 33.58% | Started | 11129.8708 | 13106.6299 | 100 | 41.0714 | 33.5766 | 100 | 86.6196 | 33.5766
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 | 2012-05-24 13:00 | 2d 4h | 5613.79 | 1116 | 1d 4h | 0 | 0 | 5613.79 | 1116 | 62.5% | Started | 5613.79 | 6729.79 | 100 | 62.5 | 62.5 | 100 | 83.417 | 62.5
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 10d 3h | 2111.2858 | 372 | 2d 5h | 0 | 0 | 2111.2858 | 372 | 79.81% | Started | 1630.6154 | 1881.0001 | 100 | 118.5714 | 79.8077 | 100 | 112.2427 | 79.8077
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 |  | 0 | 0 | 841.22 | 6h | 0 | 0 | 0 | 841.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 1720.6801 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP38
| TP Status Date | 2012-06-05 17:00 |  | TP Name | 5/06/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 190d | [5 empty] | 484186.1497 |  | 97.52% |  | 472396.1385 | 483220.4125
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 100% | Finished | 10371.9902 | 10371.9902 | 100 | 87.5 | 100 | 100 | 98.2067 | 100
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 100% | Finished | 2593 | 2593 | 100 | 70 | 100 | 100 | 95.6961 | 100
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 9d 1h | 8271.3544 | 0 | 0 | 0 | 0 | 8271.3544 | 0 | 100% | Finished | 8191.6402 | 8191.6402 | 100 | 104.2857 | 100 | 100 | 100.9731 | 100
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 12d 3h | 4976.6916 | 0 | 0 | 0 | 0 | 4976.6916 | 0 | 100% | Finished | 4206.1201 | 4206.1201 | 100 | 141.4286 | 100 | 100 | 118.3202 | 100
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 51.4286 | 100 | 100 | 67.9806 | 100
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 | 2012-05-24 13:00 | 6d 5h | 3364.8 | 0 | 0 | 0 | 0 | 3364.8 | 0 | 100% | Finished | 3876.3 | 3876.3 | 100 | 82.8125 | 100 | 100 | 86.8044 | 100
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 | 2012-06-05 09:00 | 7h | 485.48 | 186 | 5h | 0 | 0 | 485.48 | 186 | 58.33% | Started | 659.08 | 969.08 | 100 | 35 | 58.3333 | 100 | 50.097 | 58.3333
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 2012-05-21 10:00 | 10d 6h | 12415.7728 | 1355.1429 | 6d 3h | 0 | 0 | 12415.7728 | 1355.1429 | 62.77% | Started | 11998.7759 | 13106.6299 | 100 | 76.7857 | 62.7737 | 100 | 94.7289 | 62.7737
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 | 2012-05-24 13:00 | 4d | 6729.79 | 0 | 0 | 0 | 0 | 6729.79 | 0 | 100% | Finished | 6729.79 | 6729.79 | 100 | 100 | 100 | 100 | 100 | 100
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 13d | 2483.2858 | 0 | 0 | 0 | 0 | 2483.2858 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 148.5714 | 100 | 100 | 132.0194 | 100
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 1638.33 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 | 2012-05-31 13:00 | 6h | 841.22 | 0 | 0 | 0 | 0 | 841.22 | 0 | 100% | Finished | 841.22 | 841.22 | 100 | 100 | 100 | 100 | 100 | 100
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 2836.6801 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 810.48 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 4120.9299 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP39
| TP Status Date | 2012-06-12 17:00 |  | TP Name | 12/06/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 195d | [5 empty] | 485435.0068 |  | 97.77% |  | 473575.0436 | 484398.4125
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 100% | Finished | 10371.9902 | 10371.9902 | 100 | 87.5 | 100 | 100 | 98.2067 | 100
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 100% | Finished | 2593 | 2593 | 100 | 70 | 100 | 100 | 95.6961 | 100
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 9d 1h | 8271.3544 | 0 | 0 | 0 | 0 | 8271.3544 | 0 | 100% | Finished | 8191.6402 | 8191.6402 | 100 | 104.2857 | 100 | 100 | 100.9731 | 100
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 12d 3h | 4976.6916 | 0 | 0 | 0 | 0 | 4976.6916 | 0 | 100% | Finished | 4206.1201 | 4206.1201 | 100 | 141.4286 | 100 | 100 | 118.3202 | 100
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 51.4286 | 100 | 100 | 67.9806 | 100
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 | 2012-05-24 13:00 | 6d 5h | 3364.8 | 0 | 0 | 0 | 0 | 3364.8 | 0 | 100% | Finished | 3876.3 | 3876.3 | 100 | 82.8125 | 100 | 100 | 86.8044 | 100
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 | 2012-06-05 09:00 | 1d 4h | 671.48 | 0 | 0 | 0 | 0 | 671.48 | 0 | 100% | Finished | 969.08 | 969.08 | 100 | 60 | 100 | 100 | 69.2905 | 100
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 2012-05-21 10:00 | 15d 6h | 13478.6299 | 292.2857 | 1d 3h | 0 | 0 | 13478.6299 | 292.2857 | 91.97% | Started | 12867.681 | 13106.6299 | 100 | 112.5 | 91.9708 | 100 | 102.8383 | 91.9708
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 | 2012-05-24 13:00 | 4d | 6729.79 | 0 | 0 | 0 | 0 | 6729.79 | 0 | 100% | Finished | 6729.79 | 6729.79 | 100 | 100 | 100 | 100 | 100 | 100
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 13d | 2483.2858 | 0 | 0 | 0 | 0 | 2483.2858 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 148.5714 | 100 | 100 | 132.0194 | 100
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 |  | 0 | 0 | 1638.33 | 1d | 0 | 0 | 0 | 1638.33 | 0% | Not Started | 0 | 1638.33 | 100 |  | 0 | 100 |  | 0
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 | 2012-05-31 13:00 | 6h | 841.22 | 0 | 0 | 0 | 0 | 841.22 | 0 | 100% | Finished | 841.22 | 841.22 | 100 | 100 | 100 | 100 | 100 | 100
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 |  | 0 | 0 | 2836.6801 | 3d 4h | 0 | 0 | 0 | 2836.6801 | 0% | Not Started | 0 | 2836.6801 | 100 |  | 0 | 100 |  | 0
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 |  | 0 | 0 | 810.48 | 1d | 0 | 0 | 0 | 810.48 | 0% | Not Started | 0 | 810.48 | 100 |  | 0 | 100 |  | 0
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 |  | 0 | 0 | 5298.9299 | 7d 4h | 0 | 0 | 0 | 5298.9299 | 0% | Not Started | 0 | 5298.9299 | 100 |  | 0 | 100 |  | 0
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP40
| TP Status Date | 2012-06-19 17:00 |  | TP Name | 19/06/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 200d | [5 empty] | 494234.7125 |  | 99.72% |  | 483061.5375 | 484398.4125
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 100% | Finished | 10371.9902 | 10371.9902 | 100 | 87.5 | 100 | 100 | 98.2067 | 100
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 100% | Finished | 2593 | 2593 | 100 | 70 | 100 | 100 | 95.6961 | 100
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 9d 1h | 8271.3544 | 0 | 0 | 0 | 0 | 8271.3544 | 0 | 100% | Finished | 8191.6402 | 8191.6402 | 100 | 104.2857 | 100 | 100 | 100.9731 | 100
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 12d 3h | 4976.6916 | 0 | 0 | 0 | 0 | 4976.6916 | 0 | 100% | Finished | 4206.1201 | 4206.1201 | 100 | 141.4286 | 100 | 100 | 118.3202 | 100
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 51.4286 | 100 | 100 | 67.9806 | 100
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 | 2012-05-24 13:00 | 6d 5h | 3364.8 | 0 | 0 | 0 | 0 | 3364.8 | 0 | 100% | Finished | 3876.3 | 3876.3 | 100 | 82.8125 | 100 | 100 | 86.8044 | 100
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 | 2012-06-05 09:00 | 1d 4h | 671.48 | 0 | 0 | 0 | 0 | 671.48 | 0 | 100% | Finished | 969.08 | 969.08 | 100 | 60 | 100 | 100 | 69.2905 | 100
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 2012-05-21 10:00 | 17d 1h | 13770.9156 | 0 | 0 | 0 | 0 | 13770.9156 | 0 | 100% | Finished | 13106.6299 | 13106.6299 | 100 | 122.3214 | 100 | 100 | 105.0683 | 100
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 | 2012-05-24 13:00 | 4d | 6729.79 | 0 | 0 | 0 | 0 | 6729.79 | 0 | 100% | Finished | 6729.79 | 6729.79 | 100 | 100 | 100 | 100 | 100 | 100
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 13d | 2483.2858 | 0 | 0 | 0 | 0 | 2483.2858 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 148.5714 | 100 | 100 | 132.0194 | 100
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 | 2012-06-14 11:00 | 1d | 1638.33 | 0 | 0 | 0 | 0 | 1638.33 | 0 | 100% | Finished | 1638.33 | 1638.33 | 100 | 100 | 100 | 100 | 100 | 100
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 | 2012-05-31 13:00 | 6h | 841.22 | 0 | 0 | 0 | 0 | 841.22 | 0 | 100% | Finished | 841.22 | 841.22 | 100 | 100 | 100 | 100 | 100 | 100
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 | 2012-06-14 11:00 | 2d 4h | 2340.6801 | 0 | 0 | 0 | 0 | 2340.6801 | 0 | 100% | Finished | 2836.6801 | 2836.6801 | 100 | 71.4286 | 100 | 100 | 82.5148 | 100
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 | 2012-06-18 16:00 | 1d | 810.48 | 0 | 0 | 0 | 0 | 810.48 | 0 | 100% | Finished | 810.48 | 810.48 | 100 | 100 | 100 | 100 | 100 | 100
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 | 2012-06-18 16:00 | 1d 1h | 3717.9299 | 713 | 2d 7h | 0 | 0 | 3717.9299 | 713 | 28.12% | Started | 3962.0549 | 5298.9299 | 100 | 15 | 28.125 | 100 | 70.1638 | 28.125
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP41
| TP Status Date | 2012-06-26 17:00 |  | TP Name | 26/06/2012 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Building a House | 2011-08-05 08:00 | 2012-06-12 15:00 | 194d 6h |  |  | 360274.4123 |  |  | 484398.4125 |  | 202d 7h | [5 empty] | 494947.7125 |  | 100% |  | 484398.4125 | 484398.4125
33 | Dummy | 2011-08-05 08:00 | 2011-08-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
1 | Moving tanks | 2011-08-05 08:00 | 2011-09-07 12:00 | 22d 4h | Workforce[2.00 #6] | 5580 | 31452.6699 | 0 | 0 | 37032.6699 | 2011-08-05 08:00 | 16d 2h | 35482.6699 | 0 | 0 | 0 | 0 | 35482.6699 | 0 | 100% | Finished | 37032.6699 | 37032.6699 | 100 | 72.2222 | 100 | 100 | 95.8145 | 100
2 | Masonry draining (foundations) | 2011-08-05 08:00 | 2011-09-06 17:00 | 22d | Workforce[4.00 #6] | 10912 | 3832 | 0 | 0 | 14744 | 2011-08-05 08:00 | 27d 6h | 17596 | 0 | 0 | 0 | 0 | 17596 | 0 | 100% | Finished | 14744 | 14744 | 100 | 126.1364 | 100 | 100 | 119.3435 | 100
3 | Masonry draining (interior walls) | 2011-09-14 08:00 | 2011-11-29 17:00 | 49d | Workforce[5.00 #6] | 30380 | 88226.9531 | 0 | 0 | 118606.9531 | 2011-09-22 15:00 | 68d 2h | 130541.9531 | 0 | 0 | 0 | 0 | 130541.9531 | 0 | 100% | Finished | 118606.9531 | 118606.9531 | 100 | 139.2857 | 100 | 100 | 110.0626 | 100
4 | Masonry draining (exterior walls) | 2011-11-30 08:00 | 2011-12-13 17:00 | 10d | Workforce[5.00 #6] | 6200 | 18005.5 | 0 | 0 | 24205.5 | 2012-01-19 08:00 | 9d 2h | 23740.5 | 0 | 0 | 0 | 0 | 23740.5 | 0 | 100% | Finished | 24205.5 | 24205.5 | 100 | 92.5 | 100 | 100 | 98.0789 | 100
5 | Masonry draining (clean up) | 2012-01-19 13:00 | 2012-01-20 17:00 | 1d 4h | Workforce[3.33 #6] | 620 | 1800.55 | 0 | 0 | 2420.55 | 2012-02-01 10:00 | 1d 4h | 2420.55 | 0 | 0 | 0 | 0 | 2420.55 | 0 | 100% | Finished | 2420.55 | 2420.55 | 100 | 100 | 100 | 100 | 100 | 100
6 | Roofing + Frame | 2011-12-14 08:00 | 2012-01-19 12:00 | 16d 4h | Workforce[4.00 #6] | 8184 | 25391.2793 | 0 | 0 | 33575.2793 | 2012-01-19 08:00 | 18d 5h | 34629.2793 | 0 | 0 | 0 | 0 | 34629.2793 | 0 | 100% | Finished | 33575.2793 | 33575.2793 | 100 | 112.8788 | 100 | 100 | 103.1392 | 100
7 | Sanitary (foundations) | 2011-12-14 08:00 | 2012-01-20 12:00 | 17d 4h | Workforce[1.71 #6] | 3720 | 27995.5801 | 0 | 0 | 31715.5801 | 2012-02-01 10:00 | 15d 5h | 31317.0087 | 0 | 0 | 0 | 0 | 31317.0087 | 0 | 100% | Finished | 31715.5801 | 31715.5801 | 100 | 89.2857 | 100 | 100 | 98.7433 | 100
8 | Carpentry outside (part 1) | 2012-01-23 08:00 | 2012-01-30 17:00 | 6d | Workforce[6.00 #6] | 4464 | 26056.5996 | 0 | 0 | 30520.5996 | 2012-02-22 16:00 | 3d | 28288.5996 | 0 | 0 | 0 | 0 | 28288.5996 | 0 | 100% | Finished | 30520.5996 | 30520.5996 | 100 | 50 | 100 | 100 | 92.6869 | 100
9 | Carpentry outside (part 2) | 2012-01-31 08:00 | 2012-02-01 12:00 | 1d 4h | Workforce[6.00 #6] | 1116 | 6514.1499 | 0 | 0 | 7630.1499 | 2012-02-27 16:00 | 1d 4h | 7630.1499 | 0 | 0 | 0 | 0 | 7630.1499 | 0 | 100% | Finished | 7630.1499 | 7630.1499 | 100 | 100 | 100 | 100 | 100 | 100
10 | Carpentry outside (part 3) | 2012-02-15 08:00 | 2012-02-21 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10856.9102 | 0 | 0 | 12716.9102 | 2012-02-29 11:00 | 4d 1h | 12391.4102 | 0 | 0 | 0 | 0 | 12391.4102 | 0 | 100% | Finished | 12716.9102 | 12716.9102 | 100 | 82.5 | 100 | 100 | 97.4404 | 100
11 | Carpentry outside (part 4) | 2012-02-22 08:00 | 2012-02-27 17:00 | 4d | Workforce[3.00 #6] | 1488 | 8685.5303 | 0 | 0 | 10173.5303 | 2012-03-06 13:00 | 3d 5h | 10034.0303 | 0 | 0 | 0 | 0 | 10034.0303 | 0 | 100% | Finished | 10173.5303 | 10173.5303 | 100 | 90.625 | 100 | 100 | 98.6288 | 100
12 | Heating under title floor | 2011-09-07 08:00 | 2011-09-13 17:00 | 5d | Workforce[3.00 #6] | 1860 | 5179.1001 | 0 | 0 | 7039.1001 | 2011-09-14 15:00 | 6d | 7411.1001 | 0 | 0 | 0 | 0 | 7411.1001 | 0 | 100% | Finished | 7039.1001 | 7039.1001 | 100 | 120 | 100 | 100 | 105.2848 | 100
13 | Sanitary + heating phase 1 | 2012-02-01 13:00 | 2012-02-14 17:00 | 9d 4h | Workforce[6.00 #6] | 7068 | 19680.5898 | 0 | 0 | 26748.5898 | 2012-02-29 11:00 | 10d 1h | 27213.5898 | 0 | 0 | 0 | 0 | 27213.5898 | 0 | 100% | Finished | 26748.5898 | 26748.5898 | 100 | 106.5789 | 100 | 100 | 101.7384 | 100
14 | Ventilation phase 1 | 2012-03-20 08:00 | 2012-04-02 17:00 | 10d | Workforce[2.00 #6] | 2480 | 1282 | 0 | 0 | 3762 | 2012-02-27 16:00 | 12d 6h | 4444 | 0 | 0 | 0 | 0 | 4444 | 0 | 100% | Finished | 3762 | 3762 | 100 | 127.5 | 100 | 100 | 118.1287 | 100
15 | Electricity phase 1 | 2012-02-22 08:00 | 2012-03-19 17:00 | 19d | Workforce[3.00 #6] | 7068 | 8915.2402 | 0 | 0 | 15983.2402 | 2012-03-06 13:00 | 14d | 14123.2402 | 0 | 0 | 0 | 0 | 14123.2402 | 0 | 100% | Finished | 15983.2402 | 15983.2402 | 100 | 73.6842 | 100 | 100 | 88.3628 | 100
16 | Ceiling - False ceiling | 2012-02-28 08:00 | 2012-03-22 17:00 | 18d | Workforce[3.00 #6] | 6696 | 22973.5098 | 0 | 0 | 29669.5098 | 2012-03-14 13:00 | 20d 6h | 30692.5098 | 0 | 0 | 0 | 0 | 30692.5098 | 0 | 100% | Finished | 29669.5098 | 29669.5098 | 100 | 115.2778 | 100 | 100 | 103.448 | 100
17 | Isolated screen | 2012-03-23 08:00 | 2012-03-29 17:00 | 5d | Workforce[3.00 #6] | 1860 | 10762.0596 | 0 | 0 | 12622.0596 | 2012-04-20 10:00 | 5d 2h | 12715.0596 | 0 | 0 | 0 | 0 | 12715.0596 | 0 | 100% | Finished | 12622.0596 | 12622.0596 | 100 | 105 | 100 | 100 | 100.7368 | 100
18 | Screed | 2012-03-30 08:00 | 2012-04-03 17:00 | 3d | Workforce[4.00 #6] | 1488 | 8883.9902 | 0 | 0 | 10371.9902 | 2012-04-27 13:00 | 2d 5h | 10185.9902 | 0 | 0 | 0 | 0 | 10185.9902 | 0 | 100% | Finished | 10371.9902 | 10371.9902 | 100 | 87.5 | 100 | 100 | 98.2067 | 100
19 | Screed (clean up) | 2012-04-25 15:00 | 2012-04-26 17:00 | 1d 2h | Workforce[2.40 #6] | 372 | 2221 | 0 | 0 | 2593 | 2012-05-04 09:00 | 7h | 2481.4 | 0 | 0 | 0 | 0 | 2481.4 | 0 | 100% | Finished | 2593 | 2593 | 100 | 70 | 100 | 100 | 95.6961 | 100
20 | Sanitary phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 6331.6401 | 0 | 0 | 8191.6402 | 2012-05-04 09:00 | 9d 1h | 8271.3544 | 0 | 0 | 0 | 0 | 8271.3544 | 0 | 100% | Finished | 8191.6402 | 8191.6402 | 100 | 104.2857 | 100 | 100 | 100.9731 | 100
21 | Electricity phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.71 #6] | 1860 | 2346.1201 | 0 | 0 | 4206.1201 | 2012-05-04 09:00 | 12d 3h | 4976.6916 | 0 | 0 | 0 | 0 | 4976.6916 | 0 | 100% | Finished | 4206.1201 | 4206.1201 | 100 | 141.4286 | 100 | 100 | 118.3202 | 100
22 | Ventilation phase 2 (part 1) | 2012-04-05 08:00 | 2012-04-25 15:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-04 09:00 | 4d 4h | 1278.7143 | 0 | 0 | 0 | 0 | 1278.7143 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 51.4286 | 100 | 100 | 67.9806 | 100
23 | Carpentry inside | 2012-04-27 08:00 | 2012-05-10 17:00 | 8d | Workforce[3.00 #6] | 2976 | 900.3 | 0 | 0 | 3876.3 | 2012-05-24 13:00 | 6d 5h | 3364.8 | 0 | 0 | 0 | 0 | 3364.8 | 0 | 100% | Finished | 3876.3 | 3876.3 | 100 | 82.8125 | 100 | 100 | 86.8044 | 100
24 | Carpentry inside (clean up) | 2012-05-11 08:00 | 2012-05-15 12:00 | 2d 4h | Workforce[2.40 #6] | 744 | 225.08 | 0 | 0 | 969.08 | 2012-06-05 09:00 | 1d 4h | 671.48 | 0 | 0 | 0 | 0 | 671.48 | 0 | 100% | Finished | 969.08 | 969.08 | 100 | 60 | 100 | 100 | 69.2905 | 100
25 | Sanitary phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-21 15:00 | 14d | Workforce[1.71 #6] | 2976 | 10130.6299 | 0 | 0 | 13106.6299 | 2012-05-21 10:00 | 17d 1h | 13770.9156 | 0 | 0 | 0 | 0 | 13770.9156 | 0 | 100% | Finished | 13106.6299 | 13106.6299 | 100 | 122.3214 | 100 | 100 | 105.0683 | 100
26 | Electricity phase 2 (part 2) | 2012-05-21 15:00 | 2012-05-25 15:00 | 4d | Workforce[6.00 #6] | 2976 | 3753.79 | 0 | 0 | 6729.79 | 2012-05-24 13:00 | 4d | 6729.79 | 0 | 0 | 0 | 0 | 6729.79 | 0 | 100% | Finished | 6729.79 | 6729.79 | 100 | 100 | 100 | 100 | 100 | 100
27 | Ventilation phase 2 (part 2) | 2012-04-25 15:00 | 2012-05-10 12:00 | 8d 6h | Workforce[1.14 #6] | 1240.0001 | 641 | 0 | 0 | 1881.0001 | 2012-05-10 14:00 | 13d | 2483.2858 | 0 | 0 | 0 | 0 | 2483.2858 | 0 | 100% | Finished | 1881.0001 | 1881.0001 | 100 | 148.5714 | 100 | 100 | 132.0194 | 100
28 | Sanitary phase 2 (clean up) | 2012-06-01 10:00 | 2012-06-04 10:00 | 1d | Workforce[3.00 #6] | 372 | 1266.33 | 0 | 0 | 1638.33 | 2012-06-14 11:00 | 1d | 1638.33 | 0 | 0 | 0 | 0 | 1638.33 | 0 | 100% | Finished | 1638.33 | 1638.33 | 100 | 100 | 100 | 100 | 100 | 100
29 | Electricity phase 2 (clean up) | 2012-06-04 10:00 | 2012-06-04 17:00 | 6h | Workforce[4.00 #6] | 372 | 469.22 | 0 | 0 | 841.22 | 2012-05-31 13:00 | 6h | 841.22 | 0 | 0 | 0 | 0 | 841.22 | 0 | 100% | Finished | 841.22 | 841.22 | 100 | 100 | 100 | 100 | 100 | 100
30 | Painting part 1 | 2012-05-25 15:00 | 2012-06-01 10:00 | 3d 4h | Workforce[4.00 #6] | 1736 | 1100.6801 | 0 | 0 | 2836.6801 | 2012-06-14 11:00 | 2d 4h | 2340.6801 | 0 | 0 | 0 | 0 | 2340.6801 | 0 | 100% | Finished | 2836.6801 | 2836.6801 | 100 | 71.4286 | 100 | 100 | 82.5148 | 100
31 | Painting (clean up) | 2012-06-05 08:00 | 2012-06-05 17:00 | 1d | Workforce[4.00 #6] | 496 | 314.48 | 0 | 0 | 810.48 | 2012-06-18 16:00 | 1d | 810.48 | 0 | 0 | 0 | 0 | 810.48 | 0 | 100% | Finished | 810.48 | 810.48 | 100 | 100 | 100 | 100 | 100 | 100
32 | Total clean up | 2012-06-01 10:00 | 2012-06-12 15:00 | 7d 4h | Workforce[2.00 #6] | 1860 | 3438.9299 | 0 | 0 | 5298.9299 | 2012-06-18 16:00 | 4d | 4430.9299 | 0 | 0 | 0 | 0 | 4430.9299 | 0 | 100% | Finished | 5298.9299 | 5298.9299 | 100 | 53.3333 | 100 | 100 | 83.6193 | 100
34 | Dummy | 2012-06-12 15:00 | 2012-06-12 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2011-08-15
1:00 - 2:00 | No | Tuesday | Yes | 2011-10-31
2:00 - 3:00 | No | Wednesday | Yes | 2011-11-01
3:00 - 4:00 | No | Thursday | Yes | 2011-11-02
4:00 - 5:00 | No | Friday | Yes | 2011-11-03
5:00 - 6:00 | No | Saturday | No | 2011-11-04
6:00 - 7:00 | No | Sunday | No | 2011-11-11
7:00 - 8:00 | No |  |  | 2011-12-26
8:00 - 9:00 | Yes |  |  | 2011-12-27
9:00 - 10:00 | Yes |  |  | 2011-12-28
10:00 - 11:00 | Yes |  |  | 2011-12-29
11:00 - 12:00 | Yes |  |  | 2011-12-30
12:00 - 13:00 | No |  |  | 2012-01-02
13:00 - 14:00 | Yes |  |  | 2012-01-03
14:00 - 15:00 | Yes |  |  | 2012-01-04
15:00 - 16:00 | Yes |  |  | 2012-01-05
16:00 - 17:00 | Yes |  |  | 2012-01-06
17:00 - 18:00 | No |  |  | 2012-04-06
18:00 - 19:00 | No |  |  | 2012-04-09
19:00 - 20:00 | No |  |  | 2012-04-10
20:00 - 21:00 | No |  |  | 2012-04-11
21:00 - 22:00 | No |  |  | 2012-04-12
22:00 - 23:00 | No |  |  | 2012-04-13
23:00 - 0:00 | No |  |  | 2012-04-30
2012-05-01
2012-05-17
Generated by PMConverter v1.1.3 |  |  |  | 2012-05-18
2012-05-28

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
11/08/2011 17:00 | 2011-08-05 08:00 | 2011-08-11 17:00 | 39004.6699 | 38967.7192 | 39004.6699 | 2011-08-11 16:00 | -36.9508 | 99.91% | -36.9508 | 99.91% | -1h | 97.5% | 98.84% | 2012-06-12 15:00 | 2012-06-12 16:00 | 2012-06-13 09:00 | 2012-06-12 15:00 | 2012-06-12 16:00 | 2012-06-13 09:00 | 2012-06-12 16:00 | 2012-06-19 15:00 | 2012-06-19 16:00 | 484435.3633 | 484857.7387 | 484857.7387 | 495856.6631 | 485280.5146 | 496289.8686 | 484857.7387 | 487014.9499 | 0.975 | 0.99905 | 0.99905 | 0.98839 | -0.125 | 0.99905 | 1 | 0.975 | 1
19/08/2011 17:00 | 2011-08-11 17:00 | 2011-08-19 17:00 | 42724.6699 | 42650.7684 | 42724.6699 | 2011-08-19 16:00 | -73.9015 | 99.83% | -73.9015 | 99.83% | -1h | 98.75% | 97.73% | 2012-06-12 15:00 | 2012-06-13 09:00 | 2012-06-13 11:00 | 2012-06-12 15:00 | 2012-06-13 09:00 | 2012-06-13 11:00 | 2012-06-12 16:00 | 2012-06-15 10:00 | 2012-06-15 12:00 | 484472.3141 | 485237.7359 | 485237.7359 | 490064.0564 | 486004.4839 | 490839.1671 | 485237.7359 | 486194.6506 | 0.9875 | 0.99827 | 0.99827 | 0.97735 | -0.125 | 0.99827 | 1 | 0.9875 | 1
26/08/2011 17:00 | 2011-08-19 17:00 | 2011-08-26 17:00 | 46444.6699 | 46333.8173 | 46444.6699 | 2011-08-26 15:00 | -110.8526 | 99.76% | -110.8526 | 99.76% | -2h | 98.33% | 96.94% | 2012-06-12 15:00 | 2012-06-13 10:00 | 2012-06-13 14:00 | 2012-06-12 15:00 | 2012-06-13 10:00 | 2012-06-13 14:00 | 2012-06-12 17:00 | 2012-06-15 17:00 | 2012-06-18 12:00 | 484509.2652 | 485557.325 | 485557.325 | 491934.0888 | 486607.8922 | 492999.9123 | 485557.325 | 486818.0314 | 0.98333 | 0.99761 | 0.99761 | 0.96935 | -0.25 | 0.99761 | 1 | 0.98333 | 1
2/09/2011 17:00 | 2011-08-26 17:00 | 2011-09-02 17:00 | 50164.6699 | 48729.1743 | 49234.6699 | 2011-08-31 17:00 | -1435.4956 | 97.14% | -505.4956 | 98.97% | -2d | 90% | 97.82% | 2012-06-13 11:00 | 2012-06-20 12:00 | 2012-06-22 14:00 | 2012-06-13 11:00 | 2012-06-20 12:00 | 2012-06-22 11:00 | 2012-06-14 15:00 | 2012-07-12 11:00 | 2012-07-16 11:00 | 484903.9082 | 489423.3547 | 497738.1352 | 533311.6013 | 502390.7185 | 538333.2085 | 491061.5554 | 497552.5946 | 0.9 | 0.98973 | 0.97138 | 0.97815 | -2 | 0.98973 | 1 | 0.9 | 1
9/09/2011 17:00 | 2011-09-02 17:00 | 2011-09-09 17:00 | 58071.77 | 50695.3005 | 51714.6699 | 2011-09-05 14:00 | -7376.4695 | 87.3% | -1019.3694 | 98.03% | -4d 3h | 82.5% | 99.21% | 2012-06-15 15:00 | 2012-07-23 09:00 | 2012-07-27 14:00 | 2012-06-15 16:00 | 2012-07-23 09:00 | 2012-07-27 09:00 | 2012-06-19 09:00 | 2012-08-08 17:00 | 2012-08-15 10:00 | 485417.7819 | 494138.5837 | 548524.179 | 577415.4117 | 558513.9096 | 587986.0806 | 504041.8083 | 508614.1735 | 0.825 | 0.98029 | 0.87298 | 0.99211 | -4.375 | 0.98029 | 1 | 0.825 | 1
16/09/2011 17:00 | 2011-09-09 17:00 | 2011-09-16 17:00 | 148902.7231 | 57653.27 | 59094.77 | 2011-09-08 16:00 | -91249.4531 | 38.72% | -1441.5 | 97.56% | -6d 1h | 79.58% | 100% | 2012-08-02 11:00 | 2013-08-16 17:00 | 2013-09-04 12:00 | 2012-07-09 09:00 | 2013-08-16 17:00 | 2013-09-03 15:00 | 2012-06-20 16:00 | 2012-08-21 15:00 | 2012-08-29 09:00 | 485839.9125 | 496509.7865 | 1161261.4604 | 595319.0328 | 1188818.8441 | 608726.2043 | 556511.3254 | 513246.9766 | 0.79583 | 0.97561 | 0.38719 | 1 | -6.125 | 0.97561 | 1 | 0.79583 | 1
23/09/2011 17:00 | 2011-09-16 17:00 | 2011-09-23 17:00 | 152002.7231 | 147599.1334 | 149491.7231 | 2011-09-14 16:00 | -4403.5897 | 97.1% | -1892.5897 | 98.73% | -7d 1h | 79.64% | 100% | 2012-06-14 12:00 | 2012-06-20 12:00 | 2012-06-25 09:00 | 2012-06-13 15:00 | 2012-06-20 12:00 | 2012-06-22 14:00 | 2012-06-21 16:00 | 2012-08-21 12:00 | 2012-08-24 10:00 | 486291.0022 | 490609.6106 | 496339.3393 | 572378.7104 | 500786.7925 | 577801.1783 | 491740.3618 | 504331.9363 | 0.79643 | 0.98734 | 0.97103 | 1 | -7.125 | 0.98734 | 1 | 0.79643 | 1
30/09/2011 17:00 | 2011-09-23 17:00 | 2011-09-30 17:00 | 155102.7231 | 149824.7745 | 152591.7231 | 2011-09-20 11:00 | -5277.9487 | 96.6% | -2766.9487 | 98.19% | -8d 5h | 78.44% | 100% | 2012-06-14 16:00 | 2012-06-21 14:00 | 2012-06-27 11:00 | 2012-06-14 09:00 | 2012-06-21 14:00 | 2012-06-26 14:00 | 2012-06-25 11:00 | 2012-08-27 10:00 | 2012-08-31 09:00 | 487165.3612 | 493344.233 | 498951.546 | 579139.7876 | 505348.0839 | 587017.2337 | 494451.1239 | 507626.519 | 0.78438 | 0.98187 | 0.96597 | 1 | -8.625 | 0.98187 | 1 | 0.78438 | 1
7/10/2011 17:00 | 2011-09-30 17:00 | 2011-10-07 17:00 | 158202.7231 | 152050.4156 | 155691.7231 | 2011-09-23 17:00 | -6152.3075 | 96.11% | -3641.3075 | 97.66% | -10d | 77.78% | 100% | 2012-06-15 10:00 | 2012-06-22 14:00 | 2012-06-29 12:00 | 2012-06-14 12:00 | 2012-06-22 14:00 | 2012-06-28 11:00 | 2012-06-26 15:00 | 2012-08-29 11:00 | 2012-09-05 10:00 | 488039.7201 | 495998.799 | 501487.2801 | 582996.2906 | 509768.4016 | 593229.3921 | 497082.5127 | 510444.0276 | 0.77778 | 0.97661 | 0.96111 | 1 | -10 | 0.97661 | 1 | 0.77778 | 1
14/10/2011 17:00 | 2011-10-07 17:00 | 2011-10-14 17:00 | 161302.7231 | 154276.0565 | 158791.7231 | 2011-09-29 14:00 | -7026.6666 | 95.64% | -4515.6666 | 97.16% | -11d 3h | 77.25% | 100% | 2012-06-15 14:00 | 2012-06-25 14:00 | 2012-07-03 14:00 | 2012-06-14 16:00 | 2012-06-25 14:00 | 2012-07-02 09:00 | 2012-06-28 09:00 | 2012-08-31 09:00 | 2012-09-07 17:00 | 488914.0792 | 498576.7744 | 503949.8521 | 586134.5788 | 514052.645 | 598642.9221 | 499637.9653 | 513095.3499 | 0.7725 | 0.97156 | 0.95644 | 1 | -11.375 | 0.97156 | 1 | 0.7725 | 1
21/10/2011 17:00 | 2011-10-14 17:00 | 2011-10-21 17:00 | 164402.7231 | 156501.6978 | 161891.7231 | 2011-10-05 10:00 | -7901.0253 | 95.19% | -5390.0253 | 96.67% | -12d 6h | 76.82% | 100% | 2012-06-15 16:00 | 2012-06-26 14:00 | 2012-07-05 14:00 | 2012-06-15 11:00 | 2012-06-26 14:00 | 2012-07-03 15:00 | 2012-06-29 12:00 | 2012-09-03 12:00 | 2012-09-12 11:00 | 489788.4378 | 501081.4245 | 506342.3812 | 588739.5174 | 518205.4969 | 603440.4468 | 502120.7199 | 515609.4222 | 0.76818 | 0.96671 | 0.95194 | 1 | -12.75 | 0.96671 | 1 | 0.76818 | 1
28/10/2011 17:00 | 2011-10-21 17:00 | 2011-10-28 17:00 | 167502.7231 | 158727.3387 | 164991.7231 | 2011-10-10 15:00 | -8775.3844 | 94.76% | -6264.3844 | 96.2% | -14d 2h | 76.25% | 100% | 2012-06-18 10:00 | 2012-06-27 12:00 | 2012-07-09 14:00 | 2012-06-15 16:00 | 2012-06-27 12:00 | 2012-07-05 10:00 | 2012-07-02 17:00 | 2012-09-05 11:00 | 2012-09-17 09:00 | 490662.7969 | 503515.8367 | 508667.8166 | 592101.3281 | 522231.4483 | 608957.7737 | 504533.8384 | 518165.9949 | 0.7625 | 0.96203 | 0.94761 | 1 | -14.25 | 0.96203 | 1 | 0.7625 | 1
14/11/2011 17:00 | 2011-10-28 17:00 | 2011-11-14 17:00 | 170602.7231 | 160952.9796 | 168091.7231 | 2011-10-14 11:00 | -9649.7435 | 94.34% | -7138.7435 | 95.75% | -15d 5h | 75.96% | 100% | 2012-06-18 14:00 | 2012-06-28 11:00 | 2012-07-11 14:00 | 2012-06-18 11:00 | 2012-06-28 11:00 | 2012-07-06 15:00 | 2012-07-04 11:00 | 2012-09-06 11:00 | 2012-09-18 16:00 | 491537.156 | 505882.9233 | 510928.9404 | 593893.3057 | 526134.791 | 612778.8727 | 506880.2085 | 520448.905 | 0.75962 | 0.95753 | 0.94344 | 1 | -15.625 | 0.95753 | 1 | 0.75962 | 1
21/11/2011 17:00 | 2011-11-14 17:00 | 2011-11-21 17:00 | 173702.7231 | 163178.6214 | 171191.7231 | 2011-10-19 17:00 | -10524.1017 | 93.94% | -8013.1017 | 95.32% | -17d | 75.71% | 100% | 2012-06-18 17:00 | 2012-06-29 10:00 | 2012-07-13 12:00 | 2012-06-18 17:00 | 2012-06-29 10:00 | 2012-07-09 17:00 | 2012-07-05 15:00 | 2012-09-07 10:00 | 2012-09-20 11:00 | 492411.5142 | 508185.4363 | 513128.381 | 595444.2774 | 529919.6322 | 616277.7594 | 509162.5595 | 522642.4786 | 0.75714 | 0.95319 | 0.93941 | 1 | -17 | 0.95319 | 1 | 0.75714 | 1
28/11/2011 17:00 | 2011-11-21 17:00 | 2011-11-28 17:00 | 176802.7231 | 165404.2623 | 174291.7231 | 2011-10-25 12:00 | -11398.4608 | 93.55% | -8887.4608 | 94.9% | -18d 4h | 75.33% | 100% | 2012-06-19 11:00 | 2012-07-02 09:00 | 2012-07-17 11:00 | 2012-06-19 14:00 | 2012-07-02 09:00 | 2012-07-11 11:00 | 2012-07-09 10:00 | 2012-09-10 12:00 | 2012-09-24 11:00 | 493285.8733 | 510425.9879 | 515268.6341 | 597735.2854 | 533589.9209 | 620487.6499 | 511383.4816 | 524883.6082 | 0.75333 | 0.94901 | 0.93553 | 1 | -18.5 | 0.94901 | 1 | 0.75333 | 1
5/12/2011 17:00 | 2011-11-28 17:00 | 2011-12-05 17:00 | 197908.2231 | 167629.9032 | 177391.7231 | 2011-11-07 09:00 | -30278.3199 | 84.7% | -9761.8199 | 94.5% | -19d 7h | 75.16% | 100% | 2012-06-28 16:00 | 2012-07-31 16:00 | 2012-08-20 11:00 | 2012-06-28 17:00 | 2012-07-31 16:00 | 2012-08-13 14:00 | 2012-07-10 14:00 | 2012-09-11 09:00 | 2012-09-25 12:00 | 494160.2325 | 512607.0435 | 551376.8632 | 598871.6524 | 573155.648 | 623416.2658 | 519704.3298 | 526914.4588 | 0.75156 | 0.94497 | 0.84701 | 1 | -19.875 | 0.94497 | 1 | 0.75156 | 1
12/12/2011 17:00 | 2011-12-05 17:00 | 2011-12-12 17:00 | 201008.2231 | 169855.5441 | 180491.7231 | 2011-11-10 15:00 | -31152.679 | 84.5% | -10636.179 | 94.11% | -21d 2h | 75% | 100% | 2012-06-29 10:00 | 2012-08-01 12:00 | 2012-08-21 16:00 | 2012-06-29 16:00 | 2012-08-01 12:00 | 2012-08-14 14:00 | 2012-07-11 17:00 | 2012-09-11 14:00 | 2012-09-26 14:00 | 495034.5916 | 514730.9417 | 552723.9244 | 599882.2144 | 576032.7211 | 626144.0145 | 521696.1499 | 528877.9136 | 0.75 | 0.94107 | 0.84502 | 1 | -21.25 | 0.94107 | 1 | 0.75 | 1
19/12/2011 17:00 | 2011-12-12 17:00 | 2011-12-19 17:00 | 257849.3682 | 172081.185 | 183591.7231 | 2011-11-17 11:00 | -85768.1832 | 66.74% | -11510.5381 | 93.73% | -22d 5h | 74.86% | 100% | 2012-07-31 10:00 | 2012-10-25 16:00 | 2012-11-22 11:00 | 2012-07-24 14:00 | 2012-10-25 16:00 | 2012-11-14 11:00 | 2012-07-13 11:00 | 2012-09-12 09:00 | 2012-09-27 12:00 | 495908.9507 | 516799.9002 | 651573.1576 | 600787.2775 | 682876.5111 | 628693.5553 | 537164.8999 | 530778.6291 | 0.74861 | 0.9373 | 0.66737 | 1 | -22.625 | 0.9373 | 1 | 0.74861 | 1
9/01/2012 17:00 | 2011-12-19 17:00 | 2012-01-09 17:00 | 261392.2254 | 174306.8259 | 186691.7231 | 2011-11-22 16:00 | -87085.3995 | 66.68% | -12384.8973 | 93.37% | -24d 1h | 74.61% | 100% | 2012-07-31 15:00 | 2012-10-25 17:00 | 2012-11-23 15:00 | 2012-07-26 11:00 | 2012-10-25 17:00 | 2012-11-14 17:00 | 2012-07-16 16:00 | 2012-09-12 17:00 | 2012-09-28 16:00 | 496783.3098 | 518816.0237 | 651708.1073 | 602334.7669 | 684748.5812 | 631867.1525 | 538949.6315 | 532722.2017 | 0.74605 | 0.93366 | 0.66684 | 1 | -24.125 | 0.93366 | 1 | 0.74605 | 1
16/01/2012 17:00 | 2012-01-09 17:00 | 2012-01-16 17:00 | 264935.0825 | 176532.4668 | 189791.7231 | 2011-11-28 12:00 | -88402.6158 | 66.63% | -13259.2564 | 93.01% | -25d 4h | 74.5% | 100% | 2012-08-01 10:00 | 2012-10-26 10:00 | 2012-11-27 10:00 | 2012-07-30 09:00 | 2012-10-26 10:00 | 2012-11-15 15:00 | 2012-07-18 10:00 | 2012-09-13 11:00 | 2012-10-01 12:00 | 497657.6689 | 520781.3105 | 651828.4874 | 603034.6033 | 686531.8143 | 634073.0485 | 540686.0976 | 534503.8494 | 0.745 | 0.93014 | 0.66632 | 1 | -25.5 | 0.93014 | 1 | 0.745 | 1
23/01/2012 17:00 | 2012-01-16 17:00 | 2012-01-23 17:00 | 296140.2322 | 224148.5413 | 237776.5024 | 2011-12-13 17:00 | -71991.6909 | 75.69% | -13627.9611 | 94.27% | -19d | 81.9% | 97.92% | 2012-07-23 15:00 | 2012-09-07 10:00 | 2012-09-28 17:00 | 2012-07-18 10:00 | 2012-09-07 10:00 | 2012-09-20 12:00 | 2012-07-09 15:00 | 2012-08-10 15:00 | 2012-08-22 16:00 | 498026.3737 | 513849.2522 | 581613.0353 | 555523.4382 | 602517.8821 | 574842.069 | 525177.5312 | 521286.0054 | 0.81905 | 0.94269 | 0.7569 | 0.97922 | -19 | 0.94269 | 1 | 0.81905 | 1
30/01/2012 17:00 | 2012-01-23 17:00 | 2012-01-30 17:00 | 299860.2322 | 229696.9399 | 243356.5024 | 2011-12-13 17:00 | -70163.2923 | 76.6% | -13659.5625 | 94.39% | -24d | 78.18% | 99.58% | 2012-07-20 17:00 | 2012-09-04 10:00 | 2012-09-25 11:00 | 2012-07-18 12:00 | 2012-09-04 10:00 | 2012-09-14 16:00 | 2012-07-16 15:00 | 2012-08-28 09:00 | 2012-09-07 11:00 | 498057.975 | 513204.5011 | 575859.159 | 569137.4558 | 595632.3472 | 588510.9194 | 523772.4562 | 522799.9661 | 0.78182 | 0.94387 | 0.76601 | 0.99584 | -24 | 0.94387 | 1 | 0.78182 | 1
6/02/2012 17:00 | 2012-01-30 17:00 | 2012-02-06 17:00 | 329774.9719 | 264040.7549 | 277824.7754 | 2012-01-13 14:00 | -65734.217 | 80.07% | -13784.0205 | 95.04% | -16d 3h | 85.76% | 99.11% | 2012-07-19 09:00 | 2012-08-20 10:00 | 2012-09-05 16:00 | 2012-07-13 14:00 | 2012-08-20 10:00 | 2012-08-28 16:00 | 2012-07-05 09:00 | 2012-07-27 09:00 | 2012-08-03 16:00 | 498182.433 | 509686.015 | 553041.5327 | 534769.0657 | 567408.9868 | 548182.6214 | 517228.786 | 514303.0442 | 0.85761 | 0.95039 | 0.80067 | 0.99113 | -16.375 | 0.95039 | 1 | 0.85761 | 1
13/02/2012 17:00 | 2012-02-06 17:00 | 2012-02-13 17:00 | 333494.9719 | 267428.2016 | 281367.6326 | 2012-01-19 12:00 | -66066.7703 | 80.19% | -13939.4309 | 95.05% | -17d 4h | 85.42% | 99.36% | 2012-07-19 10:00 | 2012-08-17 16:00 | 2012-09-05 12:00 | 2012-07-16 12:00 | 2012-08-17 16:00 | 2012-08-28 10:00 | 2012-07-06 10:00 | 2012-07-27 17:00 | 2012-08-06 14:00 | 498337.8435 | 509647.2015 | 551939.2251 | 535381.538 | 566042.5022 | 548621.762 | 517013.7937 | 514368.2953 | 0.85417 | 0.95046 | 0.8019 | 0.99363 | -17.5 | 0.95046 | 1 | 0.85417 | 1
20/02/2012 17:00 | 2012-02-13 17:00 | 2012-02-20 17:00 | 346583.8821 | 268893.2326 | 282740.4897 | 2012-01-19 17:00 | -77690.6495 | 77.58% | -13847.2572 | 95.1% | -22d | 82.4% | 99.87% | 2012-07-25 17:00 | 2012-08-29 17:00 | 2012-09-17 17:00 | 2012-07-20 15:00 | 2012-08-29 17:00 | 2012-09-07 12:00 | 2012-07-12 15:00 | 2012-08-09 11:00 | 2012-08-17 09:00 | 498245.6697 | 509343.5899 | 560511.0426 | 544275.9023 | 574815.4572 | 557744.2521 | 518011.3261 | 515563.0383 | 0.824 | 0.95102 | 0.77584 | 0.99873 | -22 | 0.95102 | 1 | 0.824 | 1
27/02/2012 17:00 | 2012-02-20 17:00 | 2012-02-27 17:00 | 367532.6526 | 307773.6958 | 319347.8107 | 2012-02-01 12:00 | -59758.9568 | 83.74% | -11574.1148 | 96.38% | -18d 4h | 85.77% | 99.67% | 2012-07-16 15:00 | 2012-08-03 14:00 | 2012-08-16 10:00 | 2012-07-11 16:00 | 2012-08-03 14:00 | 2012-08-09 11:00 | 2012-07-09 10:00 | 2012-07-27 09:00 | 2012-08-01 15:00 | 495972.5274 | 502614.6634 | 530266.9097 | 525277.9736 | 538198.7178 | 533022.1681 | 507549.4445 | 506739.2762 | 0.85769 | 0.96376 | 0.83741 | 0.99667 | -18.5 | 0.96376 | 1 | 0.85769 | 1
5/03/2012 17:00 | 2012-02-27 17:00 | 2012-03-05 17:00 | 394226.1624 | 344471.8088 | 356193.8107 | 2012-02-14 17:00 | -49754.3536 | 87.38% | -11722.0019 | 96.71% | -14d | 89.63% | 98.64% | 2012-07-10 15:00 | 2012-07-20 16:00 | 2012-08-01 12:00 | 2012-07-05 15:00 | 2012-07-20 16:00 | 2012-07-25 16:00 | 2012-07-02 15:00 | 2012-07-13 10:00 | 2012-07-18 09:00 | 496120.4144 | 500881.9649 | 516330.9441 | 512310.2694 | 521780.237 | 517622.7431 | 503728.6025 | 503031.7818 | 0.8963 | 0.96709 | 0.87379 | 0.98642 | -14 | 0.96709 | 1 | 0.8963 | 1
12/03/2012 17:00 | 2012-03-05 17:00 | 2012-03-12 17:00 | 397946.1624 | 370520.8105 | 381963.0812 | 2012-02-27 17:00 | -27425.3518 | 93.11% | -11442.2706 | 97% | -10d | 92.86% | 99.72% | 2012-06-27 15:00 | 2012-07-03 09:00 | 2012-07-11 14:00 | 2012-06-26 11:00 | 2012-07-03 09:00 | 2012-07-05 10:00 | 2012-06-26 15:00 | 2012-07-03 15:00 | 2012-07-05 16:00 | 495840.6832 | 499357.4042 | 504269.7193 | 504600.4987 | 508046.7424 | 508387.7368 | 500308.044 | 500369.8487 | 0.92857 | 0.97004 | 0.93108 | 0.99715 | -10 | 0.97004 | 1 | 0.92857 | 1
19/03/2012 17:00 | 2012-03-12 17:00 | 2012-03-19 17:00 | 401666.1624 | 398705.7508 | 409865.5909 | 2012-03-13 17:00 | -2960.4116 | 99.26% | -11159.8401 | 97.28% | -4d | 97.24% | 99.06% | 2012-06-13 17:00 | 2012-06-14 10:00 | 2012-06-21 15:00 | 2012-06-13 16:00 | 2012-06-14 10:00 | 2012-06-15 14:00 | 2012-06-18 15:00 | 2012-06-20 10:00 | 2012-06-21 16:00 | 495558.2527 | 497956.8045 | 496194.5253 | 497989.2502 | 498610.8865 | 500455.846 | 497598.6162 | 497963.2917 | 0.97241 | 0.97277 | 0.99263 | 0.9906 | -4 | 0.97277 | 1 | 0.97241 | 1
26/03/2012 17:00 | 2012-03-19 17:00 | 2012-03-26 17:00 | 416810.2219 | 402591.1021 | 413399.5909 | 2012-03-19 17:00 | -14219.1198 | 96.59% | -10808.4888 | 97.39% | -5d | 96.67% | 99.29% | 2012-06-20 12:00 | 2012-06-21 14:00 | 2012-06-28 17:00 | 2012-06-19 16:00 | 2012-06-21 14:00 | 2012-06-22 17:00 | 2012-06-19 15:00 | 2012-06-21 12:00 | 2012-06-22 16:00 | 495206.9013 | 497403.2077 | 498096.2547 | 498027.8431 | 500370.1324 | 500299.8841 | 497540.9082 | 497527.396 | 0.96667 | 0.97385 | 0.96589 | 0.99294 | -5 | 0.97385 | 1 | 0.96667 | 1
2/04/2012 17:00 | 2012-03-26 17:00 | 2012-04-02 17:00 | 429042.2122 | 404204.596 | 415259.5909 | 2012-03-21 17:00 | -24837.6161 | 94.21% | -11054.9949 | 97.34% | -8d | 94.84% | 99.51% | 2012-06-26 15:00 | 2012-06-28 15:00 | 2012-07-06 11:00 | 2012-06-25 15:00 | 2012-06-28 15:00 | 2012-07-02 09:00 | 2012-06-22 15:00 | 2012-06-27 11:00 | 2012-06-28 15:00 | 495453.4074 | 497646.7081 | 500381.1674 | 499817.6967 | 502709.2423 | 502130.3608 | 498179.4544 | 498071.9416 | 0.94839 | 0.97338 | 0.94211 | 0.99513 | -8 | 0.97338 | 1 | 0.94839 | 1
17/04/2012 17:00 | 2012-04-02 17:00 | 2012-04-17 17:00 | 440557.5439 | 405818.0902 | 417119.5909 | 2012-03-22 17:00 | -34739.4537 | 92.11% | -11301.5008 | 97.29% | -12d | 92.5% | 99.82% | 2012-07-02 15:00 | 2012-07-05 11:00 | 2012-07-13 10:00 | 2012-06-29 11:00 | 2012-07-05 11:00 | 2012-07-06 16:00 | 2012-06-28 15:00 | 2012-07-04 12:00 | 2012-07-05 17:00 | 495699.9133 | 497888.2721 | 502426.6649 | 502071.2908 | 504802.3548 | 504437.084 | 498756.9039 | 498691.5926 | 0.925 | 0.97291 | 0.92115 | 0.99821 | -12 | 0.97291 | 1 | 0.925 | 1
24/04/2012 17:00 | 2012-04-17 17:00 | 2012-04-24 17:00 | 443391.8297 | 418280.5077 | 429741.6505 | 2012-03-29 10:00 | -25111.3219 | 94.34% | -11461.1428 | 97.33% | -12d 6h | 92.27% | 99.85% | 2012-06-26 16:00 | 2012-06-28 12:00 | 2012-07-06 09:00 | 2012-06-26 09:00 | 2012-06-28 12:00 | 2012-06-29 14:00 | 2012-06-29 12:00 | 2012-07-04 17:00 | 2012-07-06 11:00 | 495859.5553 | 497671.2265 | 499828.9203 | 501396.5227 | 501749.3545 | 503359.9102 | 498092.0712 | 498384.972 | 0.92273 | 0.97333 | 0.94337 | 0.99855 | -12.75 | 0.97333 | 1 | 0.92273 | 1
3/05/2012 17:00 | 2012-04-24 17:00 | 2012-05-03 17:00 | 460703.6167 | 429467.355 | 440795.6407 | 2012-04-03 15:00 | -31236.2617 | 93.22% | -11328.2857 | 97.43% | -14d 2h | 91.62% | 100% | 2012-06-29 10:00 | 2012-07-02 16:00 | 2012-07-10 11:00 | 2012-06-28 10:00 | 2012-07-02 16:00 | 2012-07-03 17:00 | 2012-07-02 17:00 | 2012-07-06 14:00 | 2012-07-09 15:00 | 495726.6982 | 497175.6435 | 499721.9749 | 500752.4932 | 501276.3057 | 502334.0066 | 497667.1512 | 497856.4597 | 0.91618 | 0.9743 | 0.9322 | 1 | -14.25 | 0.9743 | 1 | 0.91618 | 1
10/05/2012 17:00 | 2012-05-03 17:00 | 2012-05-10 17:00 | 464264.1882 | 445093.1677 | 456062.2296 | 2012-04-25 15:00 | -19171.0205 | 95.87% | -10969.062 | 97.59% | -9d 2h | 94.71% | 99.55% | 2012-06-22 12:00 | 2012-06-25 09:00 | 2012-07-02 09:00 | 2012-06-21 17:00 | 2012-06-25 09:00 | 2012-06-25 16:00 | 2012-06-25 17:00 | 2012-06-27 14:00 | 2012-06-28 11:00 | 495367.4745 | 496336.1294 | 497060.4271 | 497560.9799 | 498070.8039 | 498583.6924 | 496478.9343 | 496575.2808 | 0.94714 | 0.97595 | 0.95871 | 0.99551 | -9.25 | 0.97595 | 1 | 0.94714 | 1
21/05/2012 17:00 | 2012-05-10 17:00 | 2012-05-21 17:00 | 470182.7726 | 457448.8729 | 469027.1453 | 2012-04-26 14:00 | -12733.8997 | 97.29% | -11578.2724 | 97.53% | -13d 3h | 92.57% | 99.91% | 2012-06-19 16:00 | 2012-06-20 09:00 | 2012-06-27 10:00 | 2012-06-19 14:00 | 2012-06-20 09:00 | 2012-06-20 14:00 | 2012-07-02 09:00 | 2012-07-04 11:00 | 2012-07-05 09:00 | 495976.6849 | 496658.792 | 496726.8731 | 498139.9263 | 497427.9678 | 498876.7861 | 496672.3814 | 496942.8383 | 0.92569 | 0.97531 | 0.97292 | 0.99906 | -13.375 | 0.97531 | 1 | 0.92569 | 1
29/05/2012 17:00 | 2012-05-21 17:00 | 2012-05-29 17:00 | 474693.4526 | 466807.5677 | 478774.0925 | 2012-05-21 15:00 | -7885.8849 | 98.34% | -11966.5248 | 97.5% | -5d 2h | 97.16% | 98.92% | 2012-06-15 16:00 | 2012-06-15 17:00 | 2012-06-25 09:00 | 2012-06-15 16:00 | 2012-06-15 17:00 | 2012-06-18 11:00 | 2012-06-19 17:00 | 2012-06-20 12:00 | 2012-06-20 16:00 | 496364.9373 | 496815.8754 | 496662.1034 | 496878.7172 | 497120.6592 | 497342.8259 | 496784.9098 | 496828.4088 | 0.97162 | 0.97501 | 0.98339 | 0.98917 | -5.25 | 0.97501 | 1 | 0.97162 | 1
5/06/2012 17:00 | 2012-05-29 17:00 | 2012-06-05 17:00 | 483220.4125 | 472396.1385 | 484186.1497 | 2012-05-24 16:00 | -10824.274 | 97.76% | -11790.0112 | 97.56% | -7d 1h | 96.25% | 99.7% | 2012-06-19 09:00 | 2012-06-19 10:00 | 2012-06-26 09:00 | 2012-06-18 17:00 | 2012-06-19 10:00 | 2012-06-19 12:00 | 2012-06-21 16:00 | 2012-06-22 11:00 | 2012-06-22 14:00 | 496188.4237 | 496487.9751 | 496463.4384 | 496656.0448 | 496769.8537 | 496967.267 | 496483.06 | 496521.2256 | 0.9625 | 0.97565 | 0.9776 | 0.997 | -7.125 | 0.97565 | 1 | 0.9625 | 1
12/06/2012 17:00 | 2012-06-05 17:00 | 2012-06-12 17:00 | 484398.4125 | 473575.0436 | 485435.0068 | 2012-05-25 15:00 | -10823.3689 | 97.77% | -11859.9632 | 97.56% | -11d 2h | 94.23% | 99.95% | 2012-06-19 09:00 | 2012-06-19 10:00 | 2012-06-26 10:00 | 2012-06-19 11:00 | 2012-06-19 12:00 | 2012-06-19 14:00 | 2012-06-27 17:00 | 2012-06-28 14:00 | 2012-06-28 17:00 | 496258.3758 | 496529.4305 | 496505.7395 | 496921.031 | 496782.9891 | 497208.6809 | 496524.6842 | 496605.5997 | 0.94231 | 0.97557 | 0.97766 | 0.99949 | -11.25 | 0.97557 | 1 | 0.94231 | 1
19/06/2012 17:00 | 2012-06-12 17:00 | 2012-06-19 17:00 | 484398.4125 | 483061.5375 | 494234.7125 | 2012-06-05 15:00 | -1336.875 | 99.72% | -11173.175 | 97.74% | -10d 2h | 94.88% | 99.98% | 2012-06-13 10:00 | 2012-06-13 10:00 | 2012-06-19 15:00 | 2012-06-20 12:00 | 2012-06-20 12:00 | 2012-06-20 14:00 | 2012-06-26 17:00 | 2012-06-27 10:00 | 2012-06-27 11:00 | 495571.5875 | 495602.5093 | 495575.2873 | 495643.8034 | 495606.2947 | 495676.3956 | 495596.9768 | 495610.5734 | 0.94875 | 0.97739 | 0.99724 | 0.9998 | -10.25 | 0.97739 | 1 | 0.94875 | 1
26/06/2012 17:00 | 2012-06-19 17:00 | 2012-06-26 17:00 | 484398.4125 | 484398.4125 | 494947.7125 | 2012-06-12 15:00 | 0 | 100% | -10549.3 | 97.87% | -10d 2h | 95% | 100% | 2012-06-12 15:00 | 2012-06-12 15:00 | 2012-06-18 17:00 | 2012-06-26 17:00 | 2012-06-26 17:00 | 2012-06-26 17:00 | 2012-06-26 17:00 | 2012-06-26 17:00 | 2012-06-26 17:00 | 494947.7125 | 494947.7125 | 494947.7125 | 494947.7125 | 494947.7125 | 494947.7125 | 494947.7125 | 494947.7125 | 0.95 | 0.97869 | 1 | 1 | -10.25 | 0.97869 | 1 | 0.95 | 1