39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 120d | [5 empty] | 18717005.5251 |  | 97.57% |  | 16376461.806 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 10d | [5 empty] | 93845.8724 |  | 52.01% |  | 90705.4025 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 1d | 15962.1104 | 8952.3203 | 2d | 314.05 | 0 | 16276.1603 | 8952.3203 | 33.33% | Started | 15962.1105 | 24914.4307 | 100 | 33.3333 | 33.3333 | 100 | 65.3282 | 33.3333
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 7d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 7d | [5 empty] | 81246.3682 |  | 29.53% |  | 49590.6892 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 4d | 31450.8693 | 7460.3198 | 1d | 725.76 | 0 | 32176.6293 | 7460.3198 | 80% | Started | 19514.3578 | 23990.5494 | 100 | 133.3333 | 80 | 100 | 134.1221 | 80
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 1d | 9069.9098 | 29841.2793 | 4d | 181.44 | 0 | 9251.3498 | 29841.2793 | 20% | Started | 6085.7819 | 23990.5494 | 100 | 33.3333 | 20 | 100 | 38.5625 | 20
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 2d | [5 empty] | 7015.4701 |  | 14.29% |  | 6974.8901 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 2d | 6974.8901 | 0 | 11d | 40.58 | 0 | 7015.4701 | 0 | 15.38% | Started | 6974.8901 | 6974.8901 | 100 | 15.3846 | 15.3846 | 100 | 100.5818 | 15.3846
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 47d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 47d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 221d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 221d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP112
| TP Status Date | 2010-12-12 17:00 |  | TP Name | 112
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 560d | [5 empty] | 25691423.9846 |  | 98.49% |  | 21047004.9098 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 560d | [5 empty] | 25691423.9846 |  | 98.49% |  | 21047004.9098 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 125d | [5 empty] | 18829338.845 |  | 98.08% |  | 16461697.4624 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 15d | [5 empty] | 129282.8534 |  | 71.43% |  | 124572.1533 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 12d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 12d | [5 empty] | 143990.0367 |  | 51.81% |  | 87009.8145 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 3d | 23990.5494 | 14920.6396 | 2d | 544.32 | 0 | 24534.8694 | 14920.6396 | 60% | Started | 15038.1662 | 23990.5494 | 100 | 100 | 60 | 100 | 102.2689 | 60
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 7d | [5 empty] | 21168.1404 |  | 42.86% |  | 20924.6704 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 7d | 6974.8901 | 0 | 6d | 142.02 | 0 | 7116.9101 | 0 | 53.85% | Started | 6974.8901 | 6974.8901 | 100 | 53.8462 | 53.8462 | 100 | 102.0362 | 53.8462
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 4d | 6974.8901 | 0 | 9d | 81.16 | 0 | 7056.0501 | 0 | 30.77% | Started | 6974.8901 | 6974.8901 | 100 | 30.7692 | 30.7692 | 100 | 101.1636 | 30.7692
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 1d | 6974.8901 | 0 | 12d | 20.29 | 0 | 6995.1801 | 0 | 7.692% | Started | 6974.8901 | 6974.8901 | 100 | 7.6923 | 7.6923 | 100 | 100.2909 | 7.6923
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP113
| TP Status Date | 2010-12-19 17:00 |  | TP Name | 113
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 565d | [5 empty] | 25817682.0243 |  | 98.94% |  | 21142837.4079 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 565d | [5 empty] | 25817682.0243 |  | 98.94% |  | 21142837.4079 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 130d | [5 empty] | 18955596.8847 |  | 98.65% |  | 16557529.9606 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 20d | [5 empty] | 176205.7846 |  | 97.43% |  | 169924.8548 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 2d | 20438.2705 | 4476.1602 | 1d | 628.09 | 0 | 21066.3605 | 4476.1602 | 66.67% | Started | 20438.2708 | 24914.4307 | 100 | 66.6667 | 66.6667 | 100 | 84.5549 | 66.6667
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 17d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 17d | [5 empty] | 215985.0551 |  | 77.72% |  | 130514.7211 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 2d | 16530.2296 | 22380.9595 | 3d | 362.88 | 0 | 16893.1096 | 22380.9595 | 40% | Started | 10561.9739 | 23990.5494 | 100 | 66.6667 | 40 | 100 | 70.4157 | 40
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 12d | [5 empty] | 28508.2306 |  | 57.14% |  | 27899.5605 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 12d | 6974.8901 | 0 | 1d | 243.47 | 0 | 7218.3601 | 0 | 92.31% | Started | 6974.8901 | 6974.8901 | 100 | 92.3077 | 92.3077 | 100 | 103.4907 | 92.3077
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 9d | 6974.8901 | 0 | 4d | 182.6 | 0 | 7157.4901 | 0 | 69.23% | Started | 6974.8901 | 6974.8901 | 100 | 69.2308 | 69.2308 | 100 | 102.618 | 69.2308
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 6d | 6974.8901 | 0 | 7d | 121.73 | 0 | 7096.6201 | 0 | 46.15% | Started | 6974.8901 | 6974.8901 | 100 | 46.1538 | 46.1538 | 100 | 101.7453 | 46.1538
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 3d | 6974.8901 | 0 | 10d | 60.87 | 0 | 7035.7601 | 0 | 23.08% | Started | 6974.8901 | 6974.8901 | 100 | 23.0769 | 23.0769 | 100 | 100.8727 | 23.0769
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP114
| TP Status Date | 2010-12-26 17:00 |  | TP Name | 114
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 570d | [5 empty] | 25817682.0243 |  | 98.94% |  | 21142837.4079 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 570d | [5 empty] | 25817682.0243 |  | 98.94% |  | 21142837.4079 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 135d | [5 empty] | 18955596.8847 |  | 98.65% |  | 16557529.9606 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 25d | [5 empty] | 176205.7846 |  | 97.43% |  | 169924.8548 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 2d | 20438.2705 | 4476.1602 | 1d | 628.09 | 0 | 21066.3605 | 4476.1602 | 66.67% | Started | 20438.2708 | 24914.4307 | 100 | 66.6667 | 66.6667 | 100 | 84.5549 | 66.6667
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 22d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 22d | [5 empty] | 215985.0551 |  | 77.72% |  | 130514.7211 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 2d | 16530.2296 | 22380.9595 | 3d | 362.88 | 0 | 16893.1096 | 22380.9595 | 40% | Started | 10561.9739 | 23990.5494 | 100 | 66.6667 | 40 | 100 | 70.4157 | 40
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 17d | [5 empty] | 28508.2306 |  | 57.14% |  | 27899.5605 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 12d | 6974.8901 | 0 | 1d | 243.47 | 0 | 7218.3601 | 0 | 92.31% | Started | 6974.8901 | 6974.8901 | 100 | 92.3077 | 92.3077 | 100 | 103.4907 | 92.3077
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 9d | 6974.8901 | 0 | 4d | 182.6 | 0 | 7157.4901 | 0 | 69.23% | Started | 6974.8901 | 6974.8901 | 100 | 69.2308 | 69.2308 | 100 | 102.618 | 69.2308
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 6d | 6974.8901 | 0 | 7d | 121.73 | 0 | 7096.6201 | 0 | 46.15% | Started | 6974.8901 | 6974.8901 | 100 | 46.1538 | 46.1538 | 100 | 101.7453 | 46.1538
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 3d | 6974.8901 | 0 | 10d | 60.87 | 0 | 7035.7601 | 0 | 23.08% | Started | 6974.8901 | 6974.8901 | 100 | 23.0769 | 23.0769 | 100 | 100.8727 | 23.0769
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP115
| TP Status Date | 2011-01-02 17:00 |  | TP Name | 115
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 575d | [5 empty] | 25817682.0243 |  | 98.94% |  | 21142837.4079 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 575d | [5 empty] | 25817682.0243 |  | 98.94% |  | 21142837.4079 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 140d | [5 empty] | 18955596.8847 |  | 98.65% |  | 16557529.9606 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 30d | [5 empty] | 176205.7846 |  | 97.43% |  | 169924.8548 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 2d | 20438.2705 | 4476.1602 | 1d | 628.09 | 0 | 21066.3605 | 4476.1602 | 66.67% | Started | 20438.2708 | 24914.4307 | 100 | 66.6667 | 66.6667 | 100 | 84.5549 | 66.6667
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 27d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 27d | [5 empty] | 215985.0551 |  | 77.72% |  | 130514.7211 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 2d | 16530.2296 | 22380.9595 | 3d | 362.88 | 0 | 16893.1096 | 22380.9595 | 40% | Started | 10561.9739 | 23990.5494 | 100 | 66.6667 | 40 | 100 | 70.4157 | 40
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 22d | [5 empty] | 28508.2306 |  | 57.14% |  | 27899.5605 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 12d | 6974.8901 | 0 | 1d | 243.47 | 0 | 7218.3601 | 0 | 92.31% | Started | 6974.8901 | 6974.8901 | 100 | 92.3077 | 92.3077 | 100 | 103.4907 | 92.3077
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 9d | 6974.8901 | 0 | 4d | 182.6 | 0 | 7157.4901 | 0 | 69.23% | Started | 6974.8901 | 6974.8901 | 100 | 69.2308 | 69.2308 | 100 | 102.618 | 69.2308
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 6d | 6974.8901 | 0 | 7d | 121.73 | 0 | 7096.6201 | 0 | 46.15% | Started | 6974.8901 | 6974.8901 | 100 | 46.1538 | 46.1538 | 100 | 101.7453 | 46.1538
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 3d | 6974.8901 | 0 | 10d | 60.87 | 0 | 7035.7601 | 0 | 23.08% | Started | 6974.8901 | 6974.8901 | 100 | 23.0769 | 23.0769 | 100 | 100.8727 | 23.0769
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP116
| TP Status Date | 2011-01-09 17:00 |  | TP Name | 116
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 580d | [5 empty] | 25929018.215 |  | 99.35% |  | 21229923.843 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 580d | [5 empty] | 25929018.215 |  | 99.35% |  | 21229923.843 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 145d | [5 empty] | 19066933.0754 |  | 99.17% |  | 16644616.3957 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 21d | [5 empty] | 180995.9948 |  | 100% |  | 174401.0146 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 28d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 32d | [5 empty] | 271086.9639 |  | 97.33% |  | 163457.6544 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2011-01-04 08:00 | 4d | 31450.8693 | 7460.3198 | 1d | 725.76 | 0 | 32176.6293 | 7460.3198 | 80% | Started | 19514.3578 | 23990.5494 | 100 | 133.3333 | 80 | 100 | 134.1221 | 80
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 27d | [5 empty] | 42904.3708 |  | 85.71% |  | 41849.3408 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 11d | 6974.8901 | 0 | 2d | 223.18 | 0 | 7198.0701 | 0 | 84.62% | Started | 6974.8901 | 6974.8901 | 100 | 84.6154 | 84.6154 | 100 | 103.1998 | 84.6154
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 8d | 6974.8901 | 0 | 5d | 162.31 | 0 | 7137.2001 | 0 | 61.54% | Started | 6974.8901 | 6974.8901 | 100 | 61.5385 | 61.5385 | 100 | 102.3271 | 61.5385
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-03 08:00 | 5d | 6974.8901 | 0 | 8d | 101.44 | 0 | 7076.3301 | 0 | 38.46% | Started | 6974.8901 | 6974.8901 | 100 | 38.4615 | 38.4615 | 100 | 101.4544 | 38.4615
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-06 08:00 | 2d | 6974.8901 | 0 | 11d | 40.58 | 0 | 7015.4701 | 0 | 15.38% | Started | 6974.8901 | 6974.8901 | 100 | 15.3846 | 15.3846 | 100 | 100.5818 | 15.3846
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 4d | [5 empty] | 37047.9315 |  | 21.76% |  | 35717.5615 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-04 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-07 08:00 | 1d | 12263.5405 | 11190.4805 | 1d | 443.46 | 0 | 12707.0005 | 11190.4805 | 50% | Started | 12263.5405 | 23454.021 | 100 | 50 | 50 | 100 | 54.1783 | 50
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP117
| TP Status Date | 2011-01-16 17:00 |  | TP Name | 117
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 585d | [5 empty] | 25980035.8064 |  | 99.56% |  | 21276019.4262 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 585d | [5 empty] | 25980035.8064 |  | 99.56% |  | 21276019.4262 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 150d | [5 empty] | 19117950.6668 |  | 99.44% |  | 16690711.9789 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 21d | [5 empty] | 180995.9948 |  | 100% |  | 174401.0146 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 28d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 33d | [5 empty] | 278728.7237 |  | 100% |  | 167933.8461 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2011-01-04 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 32d | [5 empty] | 50305.341 |  | 100% |  | 48824.231 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-03 08:00 | 10d | 6974.8901 | 0 | 3d | 202.89 | 0 | 7177.7801 | 0 | 76.92% | Started | 6974.8901 | 6974.8901 | 100 | 76.9231 | 76.9231 | 100 | 102.9089 | 76.9231
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-06 08:00 | 7d | 6974.8901 | 0 | 6d | 142.02 | 0 | 7116.9101 | 0 | 53.85% | Started | 6974.8901 | 6974.8901 | 100 | 53.8462 | 53.8462 | 100 | 102.0362 | 53.8462
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-11 08:00 | 4d | 6974.8901 | 0 | 9d | 81.16 | 0 | 7056.0501 | 0 | 30.77% | Started | 6974.8901 | 6974.8901 | 100 | 30.7692 | 30.7692 | 100 | 101.1636 | 30.7692
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 9d | [5 empty] | 73022.7929 |  | 42.86% |  | 70362.063 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-04 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-07 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-12 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP118
| TP Status Date | 2011-01-23 17:00 |  | TP Name | 118
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 590d | [5 empty] | 26028981.4284 |  | 99.78% |  | 21322927.4682 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 590d | [5 empty] | 26028981.4284 |  | 99.78% |  | 21322927.4682 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 155d | [5 empty] | 19166896.2888 |  | 99.72% |  | 16737620.0209 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 21d | [5 empty] | 180995.9948 |  | 100% |  | 174401.0146 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 28d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 33d | [5 empty] | 278728.7237 |  | 100% |  | 167933.8461 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2011-01-04 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 37d | [5 empty] | 50569.101 |  | 100% |  | 48824.231 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-03 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-06 08:00 | 12d | 6974.8901 | 0 | 1d | 243.47 | 0 | 7218.3601 | 0 | 92.31% | Started | 6974.8901 | 6974.8901 | 100 | 92.3077 | 92.3077 | 100 | 103.4907 | 92.3077
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-11 08:00 | 9d | 6974.8901 | 0 | 4d | 182.6 | 0 | 7157.4901 | 0 | 69.23% | Started | 6974.8901 | 6974.8901 | 100 | 69.2308 | 69.2308 | 100 | 102.618 | 69.2308
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 14d | [5 empty] | 121704.6548 |  | 71.43% |  | 117270.105 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-04 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-07 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-12 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-17 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-20 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP119
| TP Status Date | 2011-01-30 17:00 |  | TP Name | 119
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 595d | [5 empty] | 26066130.8099 |  | 99.95% |  | 21358645.0297 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 595d | [5 empty] | 26066130.8099 |  | 99.95% |  | 21358645.0297 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 160d | [5 empty] | 19204045.6703 |  | 99.93% |  | 16773337.5824 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 21d | [5 empty] | 180995.9948 |  | 100% |  | 174401.0146 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 28d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 33d | [5 empty] | 278728.7237 |  | 100% |  | 167933.8461 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2011-01-04 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 41d | [5 empty] | 50670.551 |  | 100% |  | 48824.231 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-03 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-06 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-11 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 19d | [5 empty] | 158752.5863 |  | 93.18% |  | 152987.6665 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-04 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-07 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-12 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-17 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-20 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-25 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-28 08:00 | 1d | 12263.5405 | 11190.4805 | 1d | 443.46 | 0 | 12707.0005 | 11190.4805 | 50% | Started | 12263.5405 | 23454.021 | 100 | 50 | 50 | 100 | 54.1783 | 50
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP120
| TP Status Date | 2011-02-06 17:00 |  | TP Name | 120
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 600d | [5 empty] | 26077764.7403 |  | 100% |  | 21369835.5102 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 600d | [5 empty] | 26077764.7403 |  | 100% |  | 21369835.5102 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 161d | [5 empty] | 19215679.6007 |  | 100% |  | 16784528.0629 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 21d | [5 empty] | 180995.9948 |  | 100% |  | 174401.0146 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-30 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-03 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-08 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-13 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-12-16 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 28d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-01-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 33d | [5 empty] | 278728.7237 |  | 100% |  | 167933.8461 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-30 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-03 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-08 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-13 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-12-16 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2011-01-04 08:00 | 5d | 38911.1891 | 0 | 0 | 907.2 | 0 | 39818.3891 | 0 | 100% | Finished | 23990.5494 | 23990.5494 | 100 | 166.6667 | 100 | 100 | 165.9753 | 100
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 41d | [5 empty] | 50670.551 |  | 100% |  | 48824.231 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-02 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-07 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-10 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2010-12-15 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-03 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-06 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 2011-01-11 08:00 | 13d | 6974.8901 | 0 | 0 | 263.76 | 0 | 7238.6501 | 0 | 100% | Finished | 6974.8901 | 6974.8901 | 100 | 100 | 100 | 100 | 103.7816 | 100
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 20d | [5 empty] | 170386.5168 |  | 100% |  | 164178.147 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-04 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-07 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-12 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-17 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-20 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-25 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 2011-01-28 08:00 | 2d | 23454.021 | 0 | 0 | 886.91 | 0 | 24340.931 | 0 | 100% | Finished | 23454.021 | 23454.021 | 100 | 100 | 100 | 100 | 103.7815 | 100
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 51d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 225d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-02-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
1 | 2008-10-20 08:00 | 2008-10-26 17:00 | 56573.6211 | 56573.6211 | 56573.6211 | 2008-10-24 17:00 | 4.4331e-06 | 100% | 4.4331e-06 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.5085 | 21369835.5085 | 21369835.5102 | 21369835.5069 | 21369835.5085 | 21369835.5085 | 21369835.5089 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2 | 2008-10-26 17:00 | 2008-11-02 17:00 | 56811.6211 | 56811.6211 | 56811.6211 | 2008-10-31 17:00 | 8.8662e-06 | 100% | 8.8662e-06 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.5069 | 21369835.5069 | 21369835.5102 | 21369835.5035 | 21369835.5069 | 21369835.5069 | 21369835.5075 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
3 | 2008-11-02 17:00 | 2008-11-09 17:00 | 57049.6211 | 57049.6211 | 57049.6211 | 2008-11-07 17:00 | 3.1918e-05 | 100% | 3.1918e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.4982 | 21369835.4982 | 21369835.5102 | 21369835.4863 | 21369835.4982 | 21369835.4982 | 21369835.5006 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
4 | 2008-11-09 17:00 | 2008-11-16 17:00 | 57287.6211 | 57287.6211 | 57287.6211 | 2008-11-14 17:00 | 1.7732e-05 | 100% | 1.7732e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.5036 | 21369835.5036 | 21369835.5102 | 21369835.497 | 21369835.5036 | 21369835.5036 | 21369835.5049 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
5 | 2008-11-16 17:00 | 2008-11-23 17:00 | 57525.6211 | 57525.6211 | 57525.6211 | 2008-11-21 17:00 | 3.5465e-06 | 100% | 3.5465e-06 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.5089 | 21369835.5089 | 21369835.5102 | 21369835.5076 | 21369835.5089 | 21369835.5089 | 21369835.5091 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
6 | 2008-11-23 17:00 | 2008-11-30 17:00 | 57763.621 | 57763.6211 | 57763.621 | 2008-11-28 17:00 | 6.3837e-05 | 100% | 6.3837e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5101 | 21369835.4866 | 21369835.4866 | 21369835.5101 | 21369835.463 | 21369835.4866 | 21369835.4866 | 21369835.4913 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
7 | 2008-11-30 17:00 | 2008-12-07 17:00 | 58001.621 | 58001.6211 | 58001.621 | 2008-12-05 17:00 | 4.9651e-05 | 100% | 4.9651e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.4919 | 21369835.4919 | 21369835.5102 | 21369835.4737 | 21369835.4919 | 21369835.4919 | 21369835.4956 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
8 | 2008-12-07 17:00 | 2008-12-14 17:00 | 58239.621 | 58239.6211 | 58239.621 | 2008-12-12 17:00 | 3.5465e-05 | 100% | 3.5465e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.4972 | 21369835.4972 | 21369835.5102 | 21369835.4842 | 21369835.4972 | 21369835.4972 | 21369835.4998 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
9 | 2008-12-14 17:00 | 2008-12-21 17:00 | 58477.621 | 58477.621 | 58477.621 | 2008-12-19 17:00 | 2.1279e-05 | 100% | 2.1279e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.5024 | 21369835.5024 | 21369835.5102 | 21369835.4947 | 21369835.5024 | 21369835.5024 | 21369835.504 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
10 | 2008-12-21 17:00 | 2008-12-28 17:00 | 58715.621 | 58715.621 | 58715.621 | 2008-12-26 17:00 | 7.093e-06 | 100% | 7.093e-06 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5102 | 21369835.5076 | 21369835.5076 | 21369835.5102 | 21369835.505 | 21369835.5076 | 21369835.5076 | 21369835.5081 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
11 | 2008-12-28 17:00 | 2009-01-04 17:00 | 58953.621 | 58953.6212 | 58953.621 | 2009-01-02 17:00 | 0.00014186 | 100% | 0.00014186 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5101 | 21369835.4588 | 21369835.4588 | 21369835.5101 | 21369835.4075 | 21369835.4588 | 21369835.4588 | 21369835.469 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
12 | 2009-01-04 17:00 | 2009-01-11 17:00 | 59191.621 | 59191.6211 | 59191.621 | 2009-01-09 17:00 | 0.00012767 | 100% | 0.00012767 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5101 | 21369835.4641 | 21369835.4641 | 21369835.5101 | 21369835.4181 | 21369835.4641 | 21369835.4641 | 21369835.4733 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
13 | 2009-01-11 17:00 | 2009-01-18 17:00 | 59429.621 | 59429.6211 | 59429.621 | 2009-01-16 17:00 | 0.00011349 | 100% | 0.00011349 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5101 | 21369835.4694 | 21369835.4694 | 21369835.5101 | 21369835.4287 | 21369835.4694 | 21369835.4694 | 21369835.4775 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
14 | 2009-01-18 17:00 | 2009-01-25 17:00 | 59667.621 | 59667.6211 | 59667.621 | 2009-01-23 17:00 | 9.9301e-05 | 100% | 9.9301e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5101 | 21369835.4746 | 21369835.4746 | 21369835.5101 | 21369835.4392 | 21369835.4746 | 21369835.4746 | 21369835.4817 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
15 | 2009-01-25 17:00 | 2009-02-01 17:00 | 59905.621 | 59905.6211 | 59905.621 | 2009-01-30 17:00 | 8.5115e-05 | 100% | 8.5115e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5101 | 21369835.4798 | 21369835.4798 | 21369835.5101 | 21369835.4496 | 21369835.4798 | 21369835.4798 | 21369835.4859 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
16 | 2009-02-01 17:00 | 2009-02-08 17:00 | 65708.9208 | 65708.9209 | 65708.9208 | 2009-02-06 17:00 | 7.391e-05 | 100% | 7.391e-05 | 100% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 21369835.5101 | 21369835.4862 | 21369835.4862 | 21369835.5101 | 21369835.4622 | 21369835.4862 | 21369835.4862 | 21369835.491 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
17 | 2009-02-08 17:00 | 2009-02-15 17:00 | 104129.5712 | 104129.5714 | 106926.451 | 2009-02-13 17:00 | 0.00019383 | 100% | -2796.8797 | 97.38% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-12 09:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-09 16:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-09 16:00 | 21372632.3899 | 21943820.9604 | 21372632.3503 | 21372632.3899 | 21943820.9198 | 21943820.9604 | 21827141.6497 | 21827141.658 | 1 | 0.97384 | 1 | 1 | 0 | 0.97384 | 1 | 1 | 1
18 | 2009-02-15 17:00 | 2009-02-22 17:00 | 129693.2311 | 129693.2311 | 136685.421 | 2009-02-20 17:00 | 8.3427e-05 | 100% | -6992.1899 | 94.88% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-12-02 10:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-25 12:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-25 12:00 | 21376827.7001 | 22521953.8266 | 21376827.6864 | 21376827.7001 | 22521953.8122 | 22521953.8266 | 22283155.969 | 22283155.972 | 1 | 0.94884 | 1 | 1 | 0 | 0.94884 | 1 | 1 | 1
19 | 2009-02-22 17:00 | 2009-03-01 17:00 | 132216.831 | 132216.8311 | 139209.021 | 2009-02-27 17:00 | 2.8372e-05 | 100% | -6992.1899 | 94.98% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-12-01 15:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-24 15:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-24 15:00 | 21376827.7001 | 22499963.5514 | 21376827.6956 | 21376827.7001 | 22499963.5466 | 22499963.5514 | 22265932.4499 | 22265932.4509 | 1 | 0.94977 | 1 | 1 | 0 | 0.94977 | 1 | 1 | 1
20 | 2009-03-01 17:00 | 2009-03-08 17:00 | 144823.3709 | 144823.3711 | 151815.5609 | 2009-03-06 17:00 | 0.00018363 | 100% | -6992.1898 | 95.39% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-29 11:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-22 12:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-22 12:00 | 21376827.7 | 22401588.4919 | 21376827.673 | 21376827.7 | 22401588.4637 | 22401588.4919 | 22188795.8317 | 22188795.8375 | 1 | 0.95394 | 1 | 1 | 0 | 0.95394 | 1 | 1 | 1
21 | 2009-03-08 17:00 | 2009-03-15 17:00 | 156915.7509 | 156915.7508 | 163907.9408 | 2009-03-13 17:00 | -7.4508e-05 | 100% | -6992.19 | 95.73% | 0 | 100% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-25 11:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-18 15:00 | 2010-10-22 17:00 | 2010-10-22 17:00 | 2010-11-18 15:00 | 21376827.7002 | 22322078.6708 | 21376827.7103 | 21376827.7002 | 22322078.6813 | 22322078.6708 | 22126348.7244 | 22126348.7223 | 1 | 0.95734 | 1 | 1 | 0 | 0.95734 | 1 | 1 | 1
22 | 2009-03-15 17:00 | 2009-03-22 17:00 | 219778.4427 | 219838.4644 | 226770.6327 | 2009-03-23 09:00 | 60.0217 | 100% | -6932.1682 | 96.94% | 1h | 100.1% | 69.02% | 2010-10-22 17:00 | 2010-10-22 16:00 | 2010-11-16 11:00 | 2010-10-22 17:00 | 2010-10-22 16:00 | 2010-11-10 17:00 | 2010-10-22 16:00 | 2010-10-22 11:00 | 2010-11-10 12:00 | 21376767.6784 | 22043690.7212 | 21370993.1704 | 21352760.8713 | 22037734.1256 | 22018926.9073 | 21905748.5921 | 21901912.7264 | 1.0011 | 0.96943 | 1.0003 | 0.69017 | 0.125 | 0.96943 | 1 | 1.0011 | 1
23 | 2009-03-22 17:00 | 2009-03-29 17:00 | 322202.9865 | 223747.6861 | 230619.8327 | 2009-03-20 17:00 | -98455.3004 | 69.44% | -6872.1466 | 97.02% | -5d | 95.65% | 100% | 2010-10-27 11:00 | 2011-09-12 17:00 | 2011-10-14 10:00 | 2010-12-13 09:00 | 2011-09-12 17:00 | 2011-10-10 15:00 | 2010-10-29 17:00 | 2010-11-25 16:00 | 2010-12-15 10:00 | 21376707.6568 | 22026184.8338 | 30681583.4537 | 22337893.467 | 31616848.9295 | 23016892.3338 | 23339903.9554 | 22087821.366 | 0.95652 | 0.9702 | 0.69443 | 1 | -5 | 0.9702 | 1 | 0.95652 | 1
24 | 2009-03-29 17:00 | 2009-04-05 17:00 | 325123.5466 | 226728.2677 | 233540.3927 | 2009-03-20 17:00 | -98395.2789 | 69.74% | -6812.1251 | 97.08% | -10d | 91.67% | 100% | 2010-10-27 11:00 | 2011-09-07 16:00 | 2011-10-10 12:00 | 2010-12-14 11:00 | 2011-09-07 16:00 | 2011-10-04 16:00 | 2010-11-05 17:00 | 2010-12-29 15:00 | 2011-01-18 11:00 | 21376647.6353 | 22011899.2193 | 30552309.5642 | 23298748.2937 | 31463246.9171 | 23991750.0218 | 23312085.5473 | 22257652.1118 | 0.91667 | 0.97083 | 0.69736 | 1 | -10 | 0.97083 | 1 | 0.91667 | 1
25 | 2009-04-05 17:00 | 2009-04-12 17:00 | 325401.1466 | 227065.8892 | 233817.9927 | 2009-03-20 17:00 | -98335.2573 | 69.78% | -6752.1035 | 97.11% | -15d | 88% | 100% | 2010-10-27 11:00 | 2011-09-07 11:00 | 2011-10-07 15:00 | 2010-12-15 15:00 | 2011-09-07 11:00 | 2011-10-03 17:00 | 2010-11-12 17:00 | 2011-02-01 14:00 | 2011-02-21 14:00 | 21376587.6137 | 22005295.7368 | 30532871.2731 | 24259692.562 | 31433853.5598 | 24974133.611 | 23303896.2799 | 22421682.2504 | 0.88 | 0.97112 | 0.6978 | 1 | -15 | 0.97112 | 1 | 0.88 | 1
26 | 2009-04-12 17:00 | 2009-04-19 17:00 | 325678.7466 | 227403.511 | 234095.5927 | 2009-03-20 17:00 | -98275.2356 | 69.82% | -6692.0818 | 97.14% | -20d | 84.62% | 100% | 2010-10-27 11:00 | 2011-09-06 16:00 | 2011-10-06 17:00 | 2010-12-17 10:00 | 2011-09-06 16:00 | 2011-10-03 09:00 | 2010-11-19 17:00 | 2011-03-07 12:00 | 2011-03-25 16:00 | 21376527.592 | 21998711.848 | 30513490.6813 | 25220606.1373 | 31404559.5473 | 25955914.8035 | 23295730.6383 | 22574859.3582 | 0.84615 | 0.97141 | 0.69824 | 1 | -20 | 0.97141 | 1 | 0.84615 | 1
27 | 2009-04-19 17:00 | 2009-04-26 17:00 | 325956.3466 | 227741.1325 | 234373.1927 | 2009-03-20 17:00 | -98215.214 | 69.87% | -6632.0602 | 97.17% | -25d | 81.48% | 100% | 2010-10-27 11:00 | 2011-09-06 11:00 | 2011-10-06 10:00 | 2010-12-20 14:00 | 2011-09-06 11:00 | 2011-09-30 11:00 | 2010-11-26 17:00 | 2011-04-08 11:00 | 2011-04-29 09:00 | 21376467.5704 | 21992147.4945 | 30494167.5722 | 26181489.0199 | 31375364.4666 | 26937096.1995 | 23287588.5498 | 22718180.7801 | 0.81481 | 0.9717 | 0.69869 | 1 | -25 | 0.9717 | 1 | 0.81481 | 1
28 | 2009-04-26 17:00 | 2009-05-03 17:00 | 326233.9466 | 228078.7541 | 234650.7928 | 2009-03-20 17:00 | -98155.1925 | 69.91% | -6572.0387 | 97.2% | -30d | 78.57% | 100% | 2010-10-27 11:00 | 2011-09-05 16:00 | 2011-10-05 14:00 | 2010-12-22 09:00 | 2011-09-05 16:00 | 2011-09-29 12:00 | 2010-12-03 17:00 | 2011-05-12 09:00 | 2011-06-02 11:00 | 21376407.5489 | 21985602.5753 | 30474901.6705 | 27142341.2096 | 31346267.7848 | 27917680.3342 | 23279469.8964 | 22852525.4997 | 0.78571 | 0.97199 | 0.69913 | 1 | -30 | 0.97199 | 1 | 0.78571 | 1
29 | 2009-05-03 17:00 | 2009-05-10 17:00 | 326511.5466 | 228416.3757 | 234928.3928 | 2009-03-20 17:00 | -98095.1709 | 69.96% | -6512.0171 | 97.23% | -35d | 75.86% | 100% | 2010-10-27 11:00 | 2011-09-05 12:00 | 2011-10-04 16:00 | 2010-12-23 14:00 | 2011-09-05 12:00 | 2011-09-28 15:00 | 2010-12-10 17:00 | 2011-06-14 17:00 | 2011-07-06 14:00 | 21376347.5273 | 21979077.0041 | 30455692.7225 | 28103162.7065 | 31317269.0131 | 28897669.7441 | 23271374.576 | 22978671.2285 | 0.75862 | 0.97228 | 0.69957 | 1 | -35 | 0.97228 | 1 | 0.75862 | 1
30 | 2009-05-10 17:00 | 2009-05-17 17:00 | 326789.1466 | 228753.9974 | 235205.9928 | 2009-03-20 17:00 | -98035.1492 | 70% | -6451.9954 | 97.26% | -40d | 73.33% | 100% | 2010-10-27 11:00 | 2011-09-02 17:00 | 2011-10-04 09:00 | 2010-12-24 17:00 | 2011-09-02 17:00 | 2011-09-27 16:00 | 2010-12-17 17:00 | 2011-07-18 16:00 | 2011-08-09 16:00 | 21376287.5056 | 21972570.681 | 30436540.4563 | 29063953.5102 | 31288367.6254 | 29877066.9313 | 23263302.4718 | 23097308.5593 | 0.73333 | 0.97257 | 0.7 | 1 | -40 | 0.97257 | 1 | 0.73333 | 1
31 | 2009-05-17 17:00 | 2009-05-24 17:00 | 327066.7466 | 229091.6191 | 235483.5928 | 2009-03-20 17:00 | -97975.1275 | 70.04% | -6391.9736 | 97.29% | -45d | 70.97% | 100% | 2010-10-27 11:00 | 2011-09-02 12:00 | 2011-10-03 12:00 | 2010-12-28 11:00 | 2011-09-02 12:00 | 2011-09-27 09:00 | 2010-12-24 17:00 | 2011-08-19 15:00 | 2011-09-13 09:00 | 21376227.4838 | 21966083.5352 | 30417444.641 | 30024713.6211 | 31259563.1803 | 30855874.4207 | 23255253.4982 | 23209052.8657 | 0.70968 | 0.97286 | 0.70044 | 1 | -45 | 0.97286 | 1 | 0.70968 | 1
32 | 2009-05-24 17:00 | 2009-05-31 17:00 | 327344.3466 | 229429.2405 | 235761.1928 | 2009-03-20 17:00 | -97915.106 | 70.09% | -6331.9522 | 97.31% | -50d | 68.75% | 100% | 2010-10-27 11:00 | 2011-09-01 17:00 | 2011-09-30 15:00 | 2010-12-29 16:00 | 2011-09-01 17:00 | 2011-09-26 11:00 | 2010-12-31 17:00 | 2011-09-22 14:00 | 2011-10-17 10:00 | 21376167.4624 | 21959615.5105 | 30398405.067 | 30985443.0395 | 31230855.2795 | 31834094.7458 | 23247227.5851 | 23314454.2649 | 0.6875 | 0.97314 | 0.70088 | 1 | -50 | 0.97314 | 1 | 0.6875 | 1
33 | 2009-05-31 17:00 | 2009-06-07 17:00 | 327621.9466 | 229766.8623 | 236038.7928 | 2009-03-20 17:00 | -97855.0843 | 70.13% | -6271.9305 | 97.34% | -55d | 66.67% | 100% | 2010-10-27 11:00 | 2011-09-01 14:00 | 2011-09-29 17:00 | 2010-12-31 10:00 | 2011-09-01 14:00 | 2011-09-23 12:00 | 2011-01-07 17:00 | 2011-10-26 12:00 | 2011-11-18 12:00 | 21376107.4407 | 21953166.4657 | 30379421.4074 | 31946141.7647 | 31202243.2851 | 32811730.3021 | 23239224.5722 | 23414005.9562 | 0.66667 | 0.97343 | 0.70132 | 1 | -55 | 0.97343 | 1 | 0.66667 | 1
34 | 2009-06-07 17:00 | 2009-06-14 17:00 | 327899.5466 | 230104.484 | 236316.3928 | 2009-03-20 17:00 | -97795.0626 | 70.18% | -6211.9088 | 97.37% | -60d | 64.71% | 100% | 2010-10-27 11:00 | 2011-09-01 09:00 | 2011-09-29 11:00 | 2011-01-03 15:00 | 2011-09-01 09:00 | 2011-09-22 15:00 | 2011-01-14 17:00 | 2011-11-29 11:00 | 2011-12-22 14:00 | 21376047.419 | 21946736.3456 | 30360493.4554 | 32906809.7969 | 31173726.8051 | 33788783.5926 | 23231244.3906 | 23508151.5302 | 0.64706 | 0.97371 | 0.70175 | 1 | -60 | 0.97371 | 1 | 0.64706 | 1
35 | 2009-06-14 17:00 | 2009-06-21 17:00 | 328177.1466 | 230442.1054 | 236593.9928 | 2009-03-20 17:00 | -97735.0412 | 70.22% | -6151.8874 | 97.4% | -65d | 62.86% | 100% | 2010-10-27 11:00 | 2011-08-31 14:00 | 2011-09-28 14:00 | 2011-01-05 09:00 | 2011-08-31 14:00 | 2011-09-21 17:00 | 2011-01-21 17:00 | 2012-01-02 10:00 | 2012-01-25 16:00 | 21375987.3976 | 21940325.0955 | 30341621.0056 | 33867447.1368 | 31145305.4499 | 34765257.1108 | 23223286.9718 | 23597290.9948 | 0.62857 | 0.974 | 0.70219 | 1 | -65 | 0.974 | 1 | 0.62857 | 1
36 | 2009-06-21 17:00 | 2009-06-28 17:00 | 328454.7466 | 262920.6221 | 269024.4921 | 2009-03-20 17:00 | -65534.1244 | 80.05% | -6103.8699 | 97.73% | -70d | 61.11% | 100% | 2010-10-26 14:00 | 2011-04-25 16:00 | 2011-05-17 09:00 | 2010-12-13 16:00 | 2011-04-25 16:00 | 2011-05-10 16:00 | 2011-01-28 17:00 | 2012-02-03 09:00 | 2012-02-24 16:00 | 21375939.3801 | 21865949.8712 | 26636930.9894 | 34807612.4907 | 27249078.7562 | 35609447.8398 | 22676839.1281 | 23615545.4079 | 0.61111 | 0.97731 | 0.80048 | 1 | -70 | 0.97731 | 1 | 0.61111 | 1
37 | 2009-06-28 17:00 | 2009-07-05 17:00 | 328732.3466 | 263003.8221 | 269107.6921 | 2009-03-20 17:00 | -65728.5245 | 80.01% | -6103.8699 | 97.73% | -75d | 59.46% | 100% | 2010-10-26 14:00 | 2011-04-26 10:00 | 2011-05-17 11:00 | 2010-12-14 17:00 | 2011-04-26 10:00 | 2011-05-11 09:00 | 2011-02-04 17:00 | 2012-03-07 17:00 | 2012-03-30 09:00 | 21375939.3801 | 21865792.9278 | 26650847.1417 | 35766960.9856 | 27263122.2976 | 36590805.5885 | 22678712.5958 | 23701006.8209 | 0.59459 | 0.97732 | 0.80005 | 1 | -75 | 0.97732 | 1 | 0.59459 | 1
38 | 2009-07-05 17:00 | 2009-07-12 17:00 | 329009.9466 | 263087.0221 | 269190.8921 | 2009-03-20 17:00 | -65922.9245 | 79.96% | -6103.8699 | 97.73% | -80d | 57.89% | 100% | 2010-10-26 14:00 | 2011-04-26 12:00 | 2011-05-17 15:00 | 2010-12-16 09:00 | 2011-04-26 12:00 | 2011-05-11 11:00 | 2011-02-11 17:00 | 2012-04-10 16:00 | 2012-05-03 12:00 | 21375939.3801 | 21865636.0834 | 26664754.3691 | 36726301.9169 | 27277156.6263 | 37572141.6772 | 22680583.0498 | 23782540.7715 | 0.57895 | 0.97733 | 0.79963 | 1 | -80 | 0.97733 | 1 | 0.57895 | 1
39 | 2009-07-12 17:00 | 2009-07-19 17:00 | 329287.5466 | 263170.2221 | 269274.0921 | 2009-03-20 17:00 | -66117.3244 | 79.92% | -6103.8699 | 97.73% | -85d | 56.41% | 100% | 2010-10-26 14:00 | 2011-04-26 16:00 | 2011-05-18 09:00 | 2010-12-17 09:00 | 2011-04-26 16:00 | 2011-05-11 14:00 | 2011-02-18 17:00 | 2012-05-14 14:00 | 2012-06-06 15:00 | 21375939.3801 | 21865479.3377 | 26678652.6794 | 37685635.2845 | 27291181.75 | 38553456.1183 | 22682450.4967 | 23860411.2726 | 0.5641 | 0.97733 | 0.79921 | 1 | -85 | 0.97733 | 1 | 0.5641 | 1
40 | 2009-07-19 17:00 | 2009-07-26 17:00 | 361562.5259 | 263253.4221 | 269357.2921 | 2009-03-20 17:00 | -98309.1038 | 72.81% | -6103.8699 | 97.73% | -90d | 55% | 100% | 2010-10-27 11:00 | 2011-07-25 17:00 | 2011-08-17 15:00 | 2011-01-07 11:00 | 2011-07-25 17:00 | 2011-08-11 09:00 | 2011-02-25 17:00 | 2012-06-15 12:00 | 2012-07-10 17:00 | 21375939.3801 | 21865322.6934 | 29257961.0153 | 38644961.0886 | 29930099.1606 | 39534748.9309 | 23025996.7758 | 23934859.1963 | 0.55 | 0.97734 | 0.7281 | 1 | -90 | 0.97734 | 1 | 0.55 | 1
41 | 2009-07-26 17:00 | 2009-08-02 17:00 | 361645.7259 | 263336.6221 | 269440.4921 | 2009-03-20 17:00 | -98309.1038 | 72.82% | -6103.8699 | 97.73% | -95d | 53.66% | 100% | 2010-10-27 11:00 | 2011-07-25 17:00 | 2011-08-17 15:00 | 2011-01-10 15:00 | 2011-07-25 17:00 | 2011-08-10 17:00 | 2011-03-04 17:00 | 2012-07-19 11:00 | 2012-08-14 11:00 | 21375939.3801 | 21865166.1457 | 29255439.6654 | 39604279.3289 | 29927305.0798 | 40516020.1193 | 23025545.9742 | 24006104.7448 | 0.53659 | 0.97735 | 0.72816 | 1 | -95 | 0.97735 | 1 | 0.53659 | 1
42 | 2009-08-02 17:00 | 2009-08-09 17:00 | 361728.9259 | 263419.8221 | 269523.692 | 2009-03-20 17:00 | -98309.1038 | 72.82% | -6103.8699 | 97.74% | -100d | 52.38% | 100% | 2010-10-27 11:00 | 2011-07-25 16:00 | 2011-08-17 14:00 | 2011-01-12 09:00 | 2011-07-25 16:00 | 2011-08-10 15:00 | 2011-03-11 17:00 | 2012-08-22 10:00 | 2012-09-17 14:00 | 21375939.3802 | 21865009.6993 | 29252919.9114 | 40563590.0057 | 29924512.8076 | 41497269.7059 | 23025095.4222 | 24074349.636 | 0.52381 | 0.97735 | 0.72822 | 1 | -100 | 0.97735 | 1 | 0.52381 | 1
43 | 2009-08-09 17:00 | 2009-08-16 17:00 | 361812.1259 | 263503.0221 | 269606.892 | 2009-03-20 17:00 | -98309.1037 | 72.83% | -6103.8699 | 97.74% | -105d | 51.16% | 100% | 2010-10-27 11:00 | 2011-07-25 16:00 | 2011-08-17 14:00 | 2011-01-13 11:00 | 2011-07-25 16:00 | 2011-08-10 14:00 | 2011-03-18 17:00 | 2012-09-25 09:00 | 2012-10-19 16:00 | 21375939.3801 | 21864853.3468 | 29250401.7421 | 41522893.1187 | 29921722.3221 | 42478497.69 | 23024645.1115 | 24139778.9844 | 0.51163 | 0.97736 | 0.72829 | 1 | -105 | 0.97736 | 1 | 0.51163 | 1
44 | 2009-08-16 17:00 | 2009-08-23 17:00 | 361895.3259 | 263586.2221 | 269690.092 | 2009-03-20 17:00 | -98309.1038 | 72.83% | -6103.8699 | 97.74% | -110d | 50% | 100% | 2010-10-27 11:00 | 2011-07-25 15:00 | 2011-08-17 12:00 | 2011-01-14 15:00 | 2011-07-25 15:00 | 2011-08-10 11:00 | 2011-03-25 17:00 | 2012-10-26 17:00 | 2012-11-23 10:00 | 21375939.3801 | 21864697.0979 | 29247885.169 | 42482188.6682 | 29918933.6485 | 43459704.1039 | 23024195.0525 | 24202563.0007 | 0.5 | 0.97737 | 0.72835 | 1 | -110 | 0.97737 | 1 | 0.5 | 1
45 | 2009-08-23 17:00 | 2009-08-30 17:00 | 361978.5259 | 263669.4221 | 269773.292 | 2009-03-20 17:00 | -98309.1038 | 72.84% | -6103.8699 | 97.74% | -115d | 48.89% | 100% | 2010-10-27 11:00 | 2011-07-25 15:00 | 2011-08-17 11:00 | 2011-01-18 09:00 | 2011-07-25 15:00 | 2011-08-10 10:00 | 2011-04-01 17:00 | 2012-11-29 16:00 | 2012-12-27 12:00 | 21375939.3802 | 21864540.9477 | 29245370.1842 | 43441476.6541 | 29916146.7716 | 44440888.9513 | 23023745.2396 | 24262858.4344 | 0.48889 | 0.97737 | 0.72841 | 1 | -115 | 0.97737 | 1 | 0.48889 | 1
46 | 2009-08-30 17:00 | 2009-09-06 17:00 | 362061.7259 | 263752.6221 | 269856.492 | 2009-03-20 17:00 | -98309.1037 | 72.85% | -6103.8699 | 97.74% | -120d | 47.83% | 100% | 2010-10-27 11:00 | 2011-07-25 14:00 | 2011-08-17 11:00 | 2011-01-19 12:00 | 2011-07-25 14:00 | 2011-08-09 17:00 | 2011-04-08 17:00 | 2013-01-02 15:00 | 2013-01-30 15:00 | 21375939.3801 | 21864384.891 | 29242856.7794 | 44400757.0762 | 29913361.6762 | 45422052.2353 | 23023295.6676 | 24320809.8904 | 0.47826 | 0.97738 | 0.72847 | 1 | -120 | 0.97738 | 1 | 0.47826 | 1
47 | 2009-09-06 17:00 | 2009-09-13 17:00 | 362144.9259 | 263835.8221 | 269939.692 | 2009-03-20 17:00 | -98309.1038 | 72.85% | -6103.8699 | 97.74% | -125d | 46.81% | 100% | 2010-10-27 11:00 | 2011-07-25 14:00 | 2011-08-17 10:00 | 2011-01-20 15:00 | 2011-07-25 14:00 | 2011-08-09 16:00 | 2011-04-15 17:00 | 2013-02-05 14:00 | 2013-03-06 09:00 | 21375939.3801 | 21864228.9377 | 29240344.9664 | 45360029.9348 | 29910578.3874 | 46403193.9896 | 23022846.3466 | 24376550.9973 | 0.46809 | 0.97739 | 0.72854 | 1 | -125 | 0.97739 | 1 | 0.46809 | 1
48 | 2009-09-13 17:00 | 2009-09-20 17:00 | 362228.1259 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98325.7438 | 72.86% | -6103.8699 | 97.74% | -130d | 45.83% | 100% | 2010-10-27 11:00 | 2011-07-25 14:00 | 2011-08-17 10:00 | 2011-01-24 09:00 | 2011-07-25 14:00 | 2011-08-09 15:00 | 2011-04-22 17:00 | 2013-03-11 12:00 | 2013-04-09 11:00 | 21375939.3801 | 21864104.2448 | 29239667.4605 | 46319314.8952 | 29909714.6296 | 47384401.8727 | 23022651.2525 | 24430238.6327 | 0.45833 | 0.97739 | 0.72855 | 1 | -130 | 0.97739 | 1 | 0.45833 | 1
49 | 2009-09-20 17:00 | 2009-09-27 17:00 | 362311.3259 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98408.9438 | 72.84% | -6103.8699 | 97.74% | -135d | 44.9% | 100% | 2010-10-27 11:00 | 2011-07-25 15:00 | 2011-08-17 12:00 | 2011-01-25 12:00 | 2011-07-25 15:00 | 2011-08-09 15:00 | 2011-04-29 17:00 | 2013-04-12 11:00 | 2013-05-13 15:00 | 21375939.3801 | 21864104.2448 | 29246321.4875 | 47278675.4919 | 29916522.5594 | 48365951.7815 | 23023471.9959 | 24482088.0692 | 0.44898 | 0.97739 | 0.72839 | 1 | -135 | 0.97739 | 1 | 0.44898 | 1
50 | 2009-09-27 17:00 | 2009-10-04 17:00 | 362394.5258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98492.1438 | 72.82% | -6103.8699 | 97.74% | -140d | 44% | 100% | 2010-10-27 11:00 | 2011-07-25 17:00 | 2011-08-17 14:00 | 2011-01-26 17:00 | 2011-07-25 17:00 | 2011-08-09 16:00 | 2011-05-06 17:00 | 2013-05-16 09:00 | 2013-06-14 17:00 | 21375939.3801 | 21864104.2448 | 29252975.5144 | 48238036.0886 | 29923330.4892 | 49347501.6902 | 23024292.4217 | 24532073.3305 | 0.44 | 0.97739 | 0.72822 | 1 | -140 | 0.97739 | 1 | 0.44 | 1
51 | 2009-10-04 17:00 | 2009-10-11 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -145d | 43.14% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-01-28 11:00 | 2011-07-26 09:00 | 2011-08-09 16:00 | 2011-05-13 17:00 | 2013-06-18 17:00 | 2013-07-19 10:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 49197396.6854 | 29930138.419 | 50329051.599 | 23025112.5299 | 24580293.1768 | 0.43137 | 0.97739 | 0.72805 | 1 | -145 | 0.97739 | 1 | 0.43137 | 1
52 | 2009-10-11 17:00 | 2009-10-18 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -150d | 42.31% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-01-31 15:00 | 2011-07-26 09:00 | 2011-08-09 15:00 | 2011-05-20 17:00 | 2013-07-22 16:00 | 2013-08-22 14:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 50156757.2821 | 29930138.419 | 51310601.5078 | 23025112.5299 | 24626839.5135 | 0.42308 | 0.97739 | 0.72805 | 1 | -150 | 0.97739 | 1 | 0.42308 | 1
53 | 2009-10-18 17:00 | 2009-10-25 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -155d | 41.51% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-02 09:00 | 2011-07-26 09:00 | 2011-08-09 14:00 | 2011-05-27 17:00 | 2013-08-23 15:00 | 2013-09-25 16:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 51116117.8788 | 29930138.419 | 52292151.4165 | 23025112.5299 | 24671797.9754 | 0.41509 | 0.97739 | 0.72805 | 1 | -155 | 0.97739 | 1 | 0.41509 | 1
54 | 2009-10-25 17:00 | 2009-11-01 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -160d | 40.74% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-03 11:00 | 2011-07-26 09:00 | 2011-08-09 12:00 | 2011-06-03 17:00 | 2013-09-26 14:00 | 2013-10-30 10:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 52075478.4756 | 29930138.419 | 53273701.3253 | 23025112.5299 | 24715248.4525 | 0.40741 | 0.97739 | 0.72805 | 1 | -160 | 0.97739 | 1 | 0.40741 | 1
55 | 2009-11-01 17:00 | 2009-11-08 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -165d | 40% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-04 15:00 | 2011-07-26 09:00 | 2011-08-09 11:00 | 2011-06-10 17:00 | 2013-10-30 12:00 | 2013-12-03 12:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 53034839.0723 | 29930138.419 | 54255251.2341 | 23025112.5299 | 24757265.5641 | 0.4 | 0.97739 | 0.72805 | 1 | -165 | 0.97739 | 1 | 0.4 | 1
56 | 2009-11-08 17:00 | 2009-11-15 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -170d | 39.29% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-08 09:00 | 2011-07-26 09:00 | 2011-08-09 10:00 | 2011-06-17 17:00 | 2013-12-03 11:00 | 2014-01-06 15:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 53994199.669 | 29930138.419 | 55236801.1428 | 23025112.5299 | 24797919.0861 | 0.39286 | 0.97739 | 0.72805 | 1 | -170 | 0.97739 | 1 | 0.39286 | 1
57 | 2009-11-15 17:00 | 2009-11-22 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -175d | 38.6% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-09 12:00 | 2011-07-26 09:00 | 2011-08-09 10:00 | 2011-06-24 17:00 | 2014-01-06 10:00 | 2014-02-10 09:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 54953560.2658 | 29930138.419 | 56218351.0516 | 23025112.5299 | 24837274.3379 | 0.38596 | 0.97739 | 0.72805 | 1 | -175 | 0.97739 | 1 | 0.38596 | 1
58 | 2009-11-22 17:00 | 2009-11-29 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -180d | 37.93% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-10 16:00 | 2011-07-26 09:00 | 2011-08-09 09:00 | 2011-07-01 17:00 | 2014-02-07 09:00 | 2014-03-14 11:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 55912920.8625 | 29930138.419 | 57199900.9604 | 23025112.5299 | 24875392.5324 | 0.37931 | 0.97739 | 0.72805 | 1 | -180 | 0.97739 | 1 | 0.37931 | 1
59 | 2009-11-29 17:00 | 2009-12-06 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -185d | 37.29% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-14 10:00 | 2011-07-26 09:00 | 2011-08-08 17:00 | 2011-07-08 17:00 | 2014-03-12 17:00 | 2014-04-17 15:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 56872281.4592 | 29930138.419 | 58181450.8691 | 23025112.5299 | 24912331.094 | 0.37288 | 0.97739 | 0.72805 | 1 | -185 | 0.97739 | 1 | 0.37288 | 1
60 | 2009-12-06 17:00 | 2009-12-13 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -190d | 36.67% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-15 14:00 | 2011-07-26 09:00 | 2011-08-08 16:00 | 2011-07-15 17:00 | 2014-04-15 16:00 | 2014-05-21 17:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 57831642.056 | 29930138.419 | 59163000.7779 | 23025112.5299 | 24948143.9468 | 0.36667 | 0.97739 | 0.72805 | 1 | -190 | 0.97739 | 1 | 0.36667 | 1
61 | 2009-12-13 17:00 | 2009-12-20 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -195d | 36.07% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-16 17:00 | 2011-07-26 09:00 | 2011-08-08 15:00 | 2011-07-22 17:00 | 2014-05-19 14:00 | 2014-06-25 10:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 58791002.6527 | 29930138.419 | 60144550.6866 | 23025112.5299 | 24982881.7778 | 0.36066 | 0.97739 | 0.72805 | 1 | -195 | 0.97739 | 1 | 0.36066 | 1
62 | 2009-12-20 17:00 | 2009-12-27 17:00 | 362477.7258 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -98575.3438 | 72.81% | -6103.8699 | 97.74% | -200d | 35.48% | 100% | 2010-10-27 11:00 | 2011-07-26 09:00 | 2011-08-17 15:00 | 2011-02-18 10:00 | 2011-07-26 09:00 | 2011-08-08 14:00 | 2011-07-29 17:00 | 2014-06-20 12:00 | 2014-07-29 14:00 | 21375939.3801 | 21864104.2448 | 29259629.5414 | 59750363.2494 | 29930138.419 | 61126100.5954 | 23025112.5299 | 25016592.2759 | 0.35484 | 0.97739 | 0.72805 | 1 | -200 | 0.97739 | 1 | 0.35484 | 1
63 | 2009-12-27 17:00 | 2010-01-03 17:00 | 395160.3762 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -131257.9941 | 66.78% | -6103.8699 | 97.74% | -205d | 34.92% | 100% | 2010-10-28 10:00 | 2011-10-25 09:00 | 2011-11-18 10:00 | 2011-03-18 14:00 | 2011-10-25 09:00 | 2011-11-08 17:00 | 2011-08-05 17:00 | 2014-07-24 11:00 | 2014-09-01 16:00 | 21375939.3801 | 21864104.2448 | 31873466.6281 | 60709723.8461 | 32604431.6542 | 62107650.5042 | 23324452.6078 | 25049320.3503 | 0.34921 | 0.97739 | 0.66784 | 1 | -205 | 0.97739 | 1 | 0.34921 | 1
64 | 2010-01-03 17:00 | 2010-01-10 17:00 | 594374.6809 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -330472.2988 | 44.4% | -6103.8699 | 97.74% | -210d | 34.38% | 100% | 2010-11-04 09:00 | 2013-05-01 11:00 | 2013-06-07 15:00 | 2011-06-29 16:00 | 2013-05-01 11:00 | 2013-05-29 11:00 | 2011-08-12 17:00 | 2014-08-27 10:00 | 2014-10-06 10:00 | 21375939.3801 | 21864104.2448 | 47805887.3949 | 61669084.4429 | 48905357.7119 | 63089200.4129 | 24509781.4781 | 25081108.3303 | 0.34375 | 0.97739 | 0.444 | 1 | -210 | 0.97739 | 1 | 0.34375 | 1
65 | 2010-01-10 17:00 | 2010-01-17 17:00 | 952889.095 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -688986.7129 | 27.69% | -6103.8699 | 97.74% | -215d | 33.85% | 100% | 2010-11-16 16:00 | 2016-01-25 14:00 | 2016-03-25 12:00 | 2011-09-16 17:00 | 2016-01-25 14:00 | 2016-03-15 17:00 | 2011-08-19 17:00 | 2014-09-30 09:00 | 2014-11-07 12:00 | 21375939.3801 | 21864104.2448 | 76478539.7165 | 62628445.0396 | 78241187.6034 | 64070750.3217 | 25476994.7865 | 25111996.1479 | 0.33846 | 0.97739 | 0.27695 | 1 | -215 | 0.97739 | 1 | 0.33846 | 1
66 | 2010-01-17 17:00 | 2010-01-24 17:00 | 1311403.509 | 263902.3821 | 270006.252 | 2009-03-20 17:00 | -1047501.127 | 20.12% | -6103.8699 | 97.74% | -220d | 33.33% | 100% | 2010-11-29 15:00 | 2018-10-18 16:00 | 2019-01-11 10:00 | 2011-10-27 14:00 | 2018-10-18 16:00 | 2019-01-01 14:00 | 2011-08-26 17:00 | 2014-10-31 17:00 | 2014-12-11 15:00 | 21375939.3801 | 21864104.2448 | 105151192.0381 | 63587805.6363 | 107577017.4948 | 65052300.2305 | 25941258.4437 | 25142021.5051 | 0.33333 | 0.97739 | 0.20124 | 1 | -220 | 0.97739 | 1 | 0.33333 | 1
67 | 2010-01-24 17:00 | 2010-01-31 17:00 | 1557510.157 | 390793.0756 | 396896.9454 | 2010-01-01 09:00 | -1166717.0814 | 25.09% | -6103.8698 | 98.46% | -20d 7h | 93.77% | 92.76% | 2010-12-02 14:00 | 2016-10-26 11:00 | 2016-12-12 09:00 | 2011-10-10 17:00 | 2016-10-26 11:00 | 2016-12-02 16:00 | 2010-11-22 16:00 | 2010-12-10 16:00 | 2010-12-16 11:00 | 21375939.38 | 21703614.9511 | 84009104.3252 | 22770089.8323 | 85315058.9649 | 23119540.899 | 25435181.4764 | 21908697.8414 | 0.93769 | 0.98462 | 0.25091 | 0.92756 | -20.875 | 0.98462 | 1 | 0.93769 | 1
68 | 2010-01-31 17:00 | 2010-02-07 17:00 | 1634164.159 | 425063.8779 | 431167.7462 | 2010-01-07 17:00 | -1209100.2811 | 26.01% | -6103.8683 | 98.58% | -21d | 93.82% | 87.31% | 2010-12-03 15:00 | 2016-07-14 11:00 | 2016-08-24 11:00 | 2011-10-11 12:00 | 2016-07-14 11:00 | 2016-08-17 12:00 | 2010-11-22 17:00 | 2010-12-10 12:00 | 2010-12-15 15:00 | 21375939.3785 | 21676703.8854 | 80953641.8987 | 22754748.7963 | 82109935.3477 | 23075312.8475 | 25344750.3748 | 21883901.9228 | 0.93824 | 0.98584 | 0.26011 | 0.8731 | -21 | 0.98584 | 1 | 0.93824 | 1
69 | 2010-02-07 17:00 | 2010-02-14 17:00 | 1776698.3015 | 459334.6787 | 465438.547 | 2010-01-07 17:00 | -1317363.6229 | 25.85% | -6103.8683 | 98.69% | -26d | 92.46% | 87.31% | 2010-12-08 11:00 | 2016-08-01 15:00 | 2016-09-07 14:00 | 2011-10-17 15:00 | 2016-08-01 15:00 | 2016-09-01 09:00 | 2010-11-29 17:00 | 2010-12-22 15:00 | 2010-12-27 15:00 | 21375939.3785 | 21653808.5425 | 81346880.8552 | 23080243.5215 | 82421673.7997 | 23380760.329 | 25322932.4873 | 21924515.9724 | 0.92464 | 0.98689 | 0.25853 | 0.8731 | -26 | 0.98689 | 1 | 0.92464 | 1
70 | 2010-02-14 17:00 | 2010-02-21 17:00 | 1880209.5032 | 493605.4794 | 499709.3477 | 2010-01-07 17:00 | -1386604.0238 | 26.25% | -6103.8683 | 98.78% | -31d | 91.14% | 87.31% | 2010-12-10 09:00 | 2016-06-17 15:00 | 2016-07-22 12:00 | 2011-10-20 09:00 | 2016-06-17 15:00 | 2016-07-18 10:00 | 2010-12-06 17:00 | 2011-01-03 17:00 | 2011-01-06 16:00 | 21375939.3785 | 21634092.4259 | 80020070.7095 | 23404663.9269 | 81003410.3058 | 23687903.9476 | 25271751.7792 | 21965964.1957 | 0.91143 | 0.98779 | 0.26253 | 0.8731 | -31 | 0.98779 | 1 | 0.91143 | 1
71 | 2010-02-21 17:00 | 2010-02-28 17:00 | 2049600.8455 | 580558.9224 | 593654.9888 | 2010-01-08 15:00 | -1469041.923 | 28.33% | -13096.0664 | 97.79% | -35d 2h | 90.07% | 72.02% | 2010-12-14 09:00 | 2015-11-26 12:00 | 2016-01-25 10:00 | 2011-10-14 12:00 | 2015-11-26 12:00 | 2016-01-13 10:00 | 2010-12-13 10:00 | 2011-01-12 16:00 | 2011-01-19 17:00 | 21382931.5766 | 21851889.5692 | 73987960.4152 | 23674790.8408 | 75643566.1789 | 24195447.8771 | 25372207.2527 | 22193065.0849 | 0.9007 | 0.97794 | 0.28325 | 0.7202 | -35.25 | 0.97794 | 1 | 0.9007 | 1
72 | 2010-02-28 17:00 | 2010-03-07 17:00 | 2169226.377 | 836413.9166 | 1097116.0655 | 2010-01-14 11:00 | -1332812.4604 | 38.56% | -260702.1489 | 76.24% | -36d 5h | 89.83% | 76.13% | 2010-12-08 15:00 | 2014-01-07 14:00 | 2015-08-24 17:00 | 2011-08-30 10:00 | 2014-01-07 14:00 | 2015-03-19 15:00 | 2010-12-14 14:00 | 2011-01-14 12:00 | 2011-04-22 11:00 | 21630537.6591 | 28030607.0836 | 54350222.9855 | 23956124.2563 | 70948702.6788 | 31081056.5881 | 30984935.8854 | 27103509.9464 | 0.89826 | 0.76238 | 0.38558 | 0.76132 | -36.625 | 0.76238 | 1 | 0.89826 | 1
73 | 2010-03-07 17:00 | 2010-03-14 17:00 | 2338617.7192 | 987440.1388 | 1495849.8004 | 2010-01-18 11:00 | -1351177.5804 | 42.22% | -508409.6616 | 66.01% | -39d 5h | 89.14% | 76.63% | 2010-12-09 10:00 | 2013-07-25 11:00 | 2016-01-07 14:00 | 2011-08-15 16:00 | 2013-07-25 11:00 | 2015-04-20 14:00 | 2010-12-17 14:00 | 2011-01-20 16:00 | 2011-07-01 10:00 | 21878245.1718 | 32372660.3034 | 49768782.1064 | 24360465.4303 | 74623377.5554 | 36132917.2875 | 34770929.0828 | 30350422.4263 | 0.89144 | 0.66012 | 0.42223 | 0.76631 | -39.625 | 0.66012 | 1 | 0.89144 | 1
74 | 2010-03-14 17:00 | 2010-03-21 17:00 | 2458243.2507 | 1208381.2261 | 1967142.2472 | 2010-01-21 12:00 | -1249862.0247 | 49.16% | -758761.0211 | 61.43% | -41d 4h | 88.78% | 71.84% | 2010-12-06 15:00 | 2012-11-21 17:00 | 2015-06-18 14:00 | 2011-07-14 09:00 | 2012-11-21 17:00 | 2014-07-29 11:00 | 2010-12-21 12:00 | 2011-01-25 11:00 | 2011-08-08 10:00 | 22128596.5313 | 34788281.4969 | 42982144.6733 | 24675629.5688 | 68736090.9045 | 38934635.466 | 36154242.2592 | 32104131.8913 | 0.88784 | 0.61428 | 0.49156 | 0.71844 | -41.5 | 0.61428 | 1 | 0.88784 | 1
75 | 2010-03-21 17:00 | 2010-03-28 17:00 | 2645219.343 | 1422468.1747 | 2431580.525 | 2010-01-26 12:00 | -1222751.1683 | 53.78% | -1009112.3504 | 58.5% | -43d 4h | 88.4% | 68.99% | 2010-12-03 17:00 | 2012-07-17 10:00 | 2015-03-12 16:00 | 2011-06-23 11:00 | 2012-07-17 10:00 | 2014-03-05 16:00 | 2010-12-23 12:00 | 2011-01-27 16:00 | 2011-09-02 09:00 | 22378947.8606 | 36529798.5395 | 39525670.1204 | 24996475.701 | 65840567.4252 | 41004225.3378 | 37089623.8276 | 33367425.4464 | 0.884 | 0.585 | 0.53775 | 0.68992 | -43.5 | 0.585 | 1 | 0.884 | 1
76 | 2010-03-28 17:00 | 2010-04-04 17:00 | 3266477.689 | 1703301.7873 | 2964629.5014 | 2010-02-10 17:00 | -1563175.9016 | 52.14% | -1261327.714 | 57.45% | -37d | 90.26% | 74.27% | 2010-12-16 11:00 | 2012-08-28 15:00 | 2015-07-08 11:00 | 2011-07-05 16:00 | 2012-08-28 15:00 | 2014-06-09 17:00 | 2010-12-14 17:00 | 2011-01-11 14:00 | 2011-08-08 17:00 | 22631163.2242 | 37194609.4717 | 40679786.0884 | 24752626.0456 | 68608584.4933 | 40887056.2906 | 37839145.292 | 33685942.9293 | 0.90263 | 0.57454 | 0.52145 | 0.74273 | -37 | 0.57454 | 1 | 0.90263 | 1
77 | 2010-04-04 17:00 | 2010-04-11 17:00 | 3456296.0898 | 1916829.2893 | 3430372.3471 | 2010-02-23 14:00 | -1539466.8005 | 55.46% | -1513543.0578 | 55.88% | -33d 3h | 91.33% | 83.33% | 2010-12-15 16:00 | 2012-06-05 14:00 | 2015-04-17 09:00 | 2011-06-21 12:00 | 2012-06-05 14:00 | 2014-02-17 09:00 | 2010-12-09 11:00 | 2010-12-31 16:00 | 2011-07-29 15:00 | 22883378.568 | 38243620.9654 | 38506708.9368 | 24729789.0411 | 66203252.4074 | 41547971.2608 | 38295922.3612 | 34323474.2935 | 0.91331 | 0.55878 | 0.55459 | 0.83334 | -33.375 | 0.55878 | 1 | 0.91331 | 1
78 | 2010-04-11 17:00 | 2010-04-18 17:00 | 4239512.3044 | 2130356.7889 | 3896115.1749 | 2010-03-04 10:00 | -2109155.5156 | 50.25% | -1765758.3861 | 54.68% | -31d 6h | 91.86% | 85.88% | 2011-01-04 16:00 | 2012-10-19 15:00 | 2016-02-15 15:00 | 2011-07-21 17:00 | 2012-10-19 15:00 | 2014-11-19 12:00 | 2010-12-07 15:00 | 2010-12-28 12:00 | 2011-07-26 17:00 | 23135593.8963 | 39082345.6675 | 42183601.6637 | 24840697.7327 | 73918403.4129 | 42200734.5527 | 39661743.1595 | 34870083.5973 | 0.91859 | 0.54679 | 0.5025 | 0.85878 | -31.75 | 0.54679 | 1 | 0.91859 | 1
79 | 2010-04-18 17:00 | 2010-04-25 17:00 | 4697364.8611 | 2411190.4414 | 4429164.1613 | 2010-03-17 17:00 | -2286174.4196 | 51.33% | -2017973.7198 | 54.44% | -27d | 93.16% | 90% | 2011-01-11 09:00 | 2012-09-19 15:00 | 2015-12-31 15:00 | 2011-07-20 10:00 | 2012-09-19 15:00 | 2014-09-25 09:00 | 2010-11-30 17:00 | 2010-12-16 12:00 | 2011-07-01 12:00 | 23387809.23 | 39254680.1559 | 41363481.5957 | 24778796.7758 | 72274553.845 | 41809813.1229 | 39656953.2587 | 34917108.6845 | 0.93165 | 0.54439 | 0.51331 | 0.9 | -27 | 0.54439 | 1 | 0.93165 | 1
80 | 2010-04-25 17:00 | 2010-05-02 17:00 | 5685999.0759 | 2626342.2621 | 4847010.1437 | 2010-03-26 09:00 | -3059656.8138 | 46.19% | -2220667.8816 | 54.18% | -25d 7h | 93.53% | 91.34% | 2011-02-07 09:00 | 2013-02-26 14:00 | 2016-11-02 14:00 | 2011-08-22 10:00 | 2013-02-26 14:00 | 2015-07-17 12:00 | 2010-11-29 16:00 | 2010-12-14 10:00 | 2011-06-22 15:00 | 23590503.3918 | 39438808.4839 | 45426445.211 | 24886829.1861 | 79737833.1097 | 41831224.8743 | 40490677.9041 | 35052103.3008 | 0.93531 | 0.54185 | 0.4619 | 0.91338 | -25.875 | 0.54185 | 1 | 0.93531 | 1
81 | 2010-05-02 17:00 | 2010-05-09 17:00 | 6121888.4909 | 2721741.0648 | 4944272.9349 | 2010-03-31 17:00 | -3400147.4261 | 44.46% | -2222531.8701 | 55.05% | -27d | 93.33% | 91.1% | 2011-02-17 12:00 | 2013-04-29 16:00 | 2017-01-09 09:00 | 2011-09-02 17:00 | 2013-04-29 16:00 | 2015-10-02 11:00 | 2010-11-30 17:00 | 2010-12-15 12:00 | 2011-06-14 09:00 | 23592367.3803 | 38820114.3392 | 46888584.3317 | 24924374.1264 | 81139663.5606 | 41239817.2967 | 40175542.1877 | 34683511.3538 | 0.93333 | 0.55048 | 0.44459 | 0.91097 | -27 | 0.55048 | 1 | 0.93333 | 1
82 | 2010-05-09 17:00 | 2010-05-16 17:00 | 6897591.9724 | 2884446.0175 | 5108841.8768 | 2010-03-31 17:00 | -4013145.9549 | 41.82% | -2224395.8593 | 56.46% | -32d | 92.2% | 94.56% | 2011-03-10 14:00 | 2013-08-12 11:00 | 2017-04-27 14:00 | 2011-09-22 12:00 | 2013-08-12 11:00 | 2016-02-10 11:00 | 2010-12-07 17:00 | 2010-12-24 12:00 | 2011-06-15 11:00 | 23594231.3695 | 37849593.9578 | 49313057.6597 | 25159132.0673 | 83401986.3332 | 40621297.8377 | 39640616.5493 | 34170753.6045 | 0.92195 | 0.5646 | 0.41818 | 0.9456 | -32 | 0.5646 | 1 | 0.92195 | 1
83 | 2010-05-16 17:00 | 2010-05-23 17:00 | 7366912.2214 | 2979844.8196 | 5206104.6781 | 2010-03-31 17:00 | -4387067.4018 | 40.45% | -2226259.8585 | 57.24% | -37d | 91.08% | 95.55% | 2011-03-23 15:00 | 2013-10-09 16:00 | 2017-06-28 14:00 | 2011-10-05 09:00 | 2013-10-09 16:00 | 2016-04-20 14:00 | 2010-12-14 17:00 | 2011-01-04 11:00 | 2011-06-21 17:00 | 23596095.3687 | 37335367.2277 | 50670702.7945 | 25396173.8226 | 84637575.5344 | 40480295.0434 | 39337606.5512 | 33937377.6309 | 0.91084 | 0.57238 | 0.40449 | 0.95548 | -37 | 0.57238 | 1 | 0.91084 | 1
84 | 2010-05-23 17:00 | 2010-05-30 17:00 | 7742241.6903 | 3061535.2957 | 5289659.149 | 2010-03-31 17:00 | -4680706.3946 | 39.54% | -2228123.8534 | 57.88% | -42d | 90% | 96.54% | 2011-04-01 17:00 | 2013-11-20 14:00 | 2017-08-03 16:00 | 2011-10-13 16:00 | 2013-11-20 14:00 | 2016-06-02 10:00 | 2010-12-21 17:00 | 2011-01-13 11:00 | 2011-06-29 10:00 | 23597959.3636 | 36922372.2753 | 51589071.5389 | 25632214.943 | 85284853.2894 | 40437118.1783 | 39062051.8136 | 33761938.3987 | 0.9 | 0.57878 | 0.39543 | 0.96536 | -42 | 0.57878 | 1 | 0.9 | 1
85 | 2010-05-30 17:00 | 2010-06-06 17:00 | 8059139.9066 | 3155698.6468 | 5385686.4894 | 2010-03-31 17:00 | -4903441.2598 | 39.16% | -2229987.8426 | 58.59% | -47d | 88.94% | 100% | 2011-04-11 12:00 | 2013-12-09 15:00 | 2017-07-27 10:00 | 2011-10-20 14:00 | 2013-12-09 15:00 | 2016-06-01 16:00 | 2010-12-28 17:00 | 2011-01-24 10:00 | 2011-07-06 09:00 | 23599823.3528 | 36470920.4742 | 51901622.7971 | 25864544.0739 | 84772306.6181 | 40336015.7051 | 38679850.9236 | 33553223.5375 | 0.88941 | 0.58594 | 0.39157 | 1 | -47 | 0.58594 | 1 | 0.88941 | 1
86 | 2010-06-06 17:00 | 2010-06-13 17:00 | 8237888.4969 | 3281992.599 | 5513844.4381 | 2010-04-05 11:00 | -4955895.8979 | 39.84% | -2231851.8391 | 59.52% | -49d 5h | 88.46% | 84.25% | 2011-04-12 15:00 | 2013-11-06 15:00 | 2017-04-13 16:00 | 2011-10-20 14:00 | 2013-11-06 15:00 | 2016-03-01 12:00 | 2010-12-31 14:00 | 2011-01-27 12:00 | 2011-07-01 14:00 | 23601687.3493 | 35901954.4119 | 50914810.027 | 25961488.084 | 81788806.6882 | 39866489.2984 | 38053980.7478 | 33209179.1743 | 0.88459 | 0.59523 | 0.3984 | 0.84247 | -49.625 | 0.59523 | 1 | 0.88459 | 1
87 | 2010-06-13 17:00 | 2010-06-20 17:00 | 8438212.087 | 3400238.5987 | 5633954.4266 | 2010-04-08 12:00 | -5037973.4883 | 40.3% | -2233715.8279 | 60.35% | -51d 4h | 88.16% | 83.06% | 2011-04-14 15:00 | 2013-10-16 16:00 | 2017-01-26 15:00 | 2011-10-21 15:00 | 2013-10-16 16:00 | 2015-12-23 17:00 | 2011-01-04 12:00 | 2011-01-31 12:00 | 2011-06-27 17:00 | 23603551.3381 | 35408303.2335 | 50228257.2839 | 26016678.4332 | 79523554.4333 | 39406683.8425 | 37528174.3539 | 32896027.0772 | 0.88161 | 0.60353 | 0.40296 | 0.8306 | -51.5 | 0.60353 | 1 | 0.88161 | 1
88 | 2010-06-20 17:00 | 2010-06-27 17:00 | 8556458.0855 | 4152187.7178 | 6400261.9203 | 2010-04-15 10:00 | -4404270.3677 | 48.53% | -2248074.2024 | 64.88% | -51d 6h | 88.24% | 83.85% | 2011-03-24 10:00 | 2012-12-11 16:00 | 2015-03-11 14:00 | 2011-09-06 12:00 | 2012-12-11 16:00 | 2014-04-11 11:00 | 2011-01-04 15:00 | 2011-01-28 17:00 | 2011-05-26 16:00 | 23617909.7126 | 32939875.0137 | 41880854.7256 | 25912856.9715 | 61090729.3251 | 36477350.8091 | 34348442.9063 | 31156775.75 | 0.88239 | 0.64875 | 0.48527 | 0.83848 | -51.75 | 0.64875 | 1 | 0.88239 | 1
89 | 2010-06-27 17:00 | 2010-07-04 17:00 | 8625698.4864 | 4273464.5179 | 6535897.0995 | 2010-04-16 17:00 | -4352233.9685 | 49.54% | -2262432.5815 | 65.38% | -55d | 87.64% | 84.86% | 2011-03-22 16:00 | 2012-11-09 14:00 | 2015-01-05 14:00 | 2011-09-02 12:00 | 2012-11-09 14:00 | 2014-02-10 09:00 | 2011-01-07 17:00 | 2011-02-03 17:00 | 2011-05-30 14:00 | 23632268.0917 | 32683328.7935 | 41043763.2049 | 26043294.7701 | 59312715.7768 | 36370787.1094 | 34014826.8903 | 31016744.0504 | 0.8764 | 0.65385 | 0.49543 | 0.84859 | -55 | 0.65385 | 1 | 0.8764 | 1
90 | 2010-07-04 17:00 | 2010-07-11 17:00 | 8744704.7181 | 5244324.6965 | 7533610.0294 | 2010-04-28 17:00 | -3500380.0216 | 59.97% | -2289285.3329 | 69.61% | -52d | 88.44% | 91.69% | 2011-02-21 17:00 | 2012-02-27 11:00 | 2013-08-14 12:00 | 2011-07-04 09:00 | 2012-02-27 11:00 | 2012-11-13 09:00 | 2011-01-04 17:00 | 2011-01-27 14:00 | 2011-04-26 10:00 | 23659120.8431 | 30698329.4214 | 34422263.6988 | 25765971.5022 | 46159866.5416 | 33724875.6736 | 31358246.2821 | 29509321.8807 | 0.88444 | 0.69612 | 0.59971 | 0.91686 | -52 | 0.69612 | 1 | 0.88444 | 1
91 | 2010-07-11 17:00 | 2010-07-18 17:00 | 9319074.9725 | 5451791.5384 | 7757934.1392 | 2010-04-28 17:00 | -3867283.4341 | 58.5% | -2306142.6009 | 70.27% | -57d | 87.47% | 93.95% | 2011-03-04 17:00 | 2012-03-28 11:00 | 2013-09-10 17:00 | 2011-07-14 16:00 | 2012-03-28 11:00 | 2012-12-14 12:00 | 2011-01-11 17:00 | 2011-02-07 10:00 | 2011-05-03 14:00 | 23675978.1111 | 30409412.2617 | 34967603.5012 | 25955697.9764 | 46477467.2277 | 33653468.1737 | 31194640.393 | 29352407.5068 | 0.87473 | 0.70274 | 0.58501 | 0.93946 | -57 | 0.70274 | 1 | 0.87473 | 1
92 | 2010-07-18 17:00 | 2010-07-25 17:00 | 9440351.7718 | 6422651.7481 | 8755647.0792 | 2010-05-12 17:00 | -3017700.0237 | 68.03% | -2332995.331 | 73.35% | -52d | 88.7% | 90.83% | 2011-02-04 09:00 | 2011-10-04 14:00 | 2012-10-30 17:00 | 2011-05-17 17:00 | 2011-10-04 14:00 | 2012-03-09 16:00 | 2011-01-04 17:00 | 2011-01-25 16:00 | 2011-04-01 16:00 | 23702830.8412 | 29132318.7376 | 30725804.9275 | 25607864.0658 | 38706352.1675 | 31729345.5176 | 29432251.8042 | 28314226.647 | 0.88696 | 0.73354 | 0.68034 | 0.90826 | -52 | 0.73354 | 1 | 0.88696 | 1
93 | 2010-07-25 17:00 | 2010-08-01 17:00 | 9739676.6387 | 6562812.4658 | 8912665.0384 | 2010-05-12 17:00 | -3176864.173 | 67.38% | -2349852.5726 | 73.63% | -57d | 87.74% | 92.65% | 2011-02-09 17:00 | 2011-10-14 09:00 | 2012-11-08 09:00 | 2011-05-24 14:00 | 2011-10-14 09:00 | 2012-03-20 14:00 | 2011-01-11 17:00 | 2011-02-03 11:00 | 2011-04-12 09:00 | 23719688.0828 | 29021427.4477 | 30887331.7209 | 25788316.3023 | 38755486.9219 | 31830739.8431 | 29368820.4558 | 28279356.3472 | 0.87742 | 0.73635 | 0.67382 | 0.92646 | -57 | 0.73635 | 1 | 0.87742 | 1
94 | 2010-08-01 17:00 | 2010-08-08 17:00 | 11468246.8985 | 7600978.7974 | 9977684.119 | 2010-05-26 17:00 | -3867268.1011 | 66.28% | -2376705.3216 | 76.18% | -52d | 88.94% | 90.46% | 2011-03-04 17:00 | 2011-11-02 09:00 | 2012-10-12 15:00 | 2011-06-02 12:00 | 2011-11-02 09:00 | 2012-03-21 16:00 | 2011-01-04 17:00 | 2011-01-24 10:00 | 2011-03-16 16:00 | 23746540.8318 | 28051843.5953 | 30751936.0281 | 25459412.9587 | 37247714.5825 | 30300303.6258 | 28534213.2528 | 27466151.4049 | 0.88936 | 0.7618 | 0.66278 | 0.90461 | -52 | 0.7618 | 1 | 0.88936 | 1
95 | 2010-08-08 17:00 | 2010-08-15 17:00 | 12839777.9405 | 7741139.5174 | 10134702.0882 | 2010-05-28 16:00 | -5098638.4231 | 60.29% | -2393562.5708 | 76.38% | -55d 1h | 88.39% | 90.26% | 2011-04-18 10:00 | 2012-02-20 15:00 | 2013-03-01 17:00 | 2011-07-14 14:00 | 2012-02-20 15:00 | 2012-08-09 09:00 | 2011-01-10 09:00 | 2011-01-27 16:00 | 2011-03-21 15:00 | 23763398.081 | 27977394.8115 | 32739827.5703 | 25552696.9595 | 39729338.8871 | 30319945.4191 | 28762284.1232 | 27433304.8025 | 0.88395 | 0.76383 | 0.6029 | 0.90263 | -55.125 | 0.76383 | 1 | 0.88395 | 1
96 | 2010-08-15 17:00 | 2010-08-22 17:00 | 14433042.7897 | 8711999.696 | 11132415.0181 | 2010-07-07 17:00 | -5721043.0937 | 60.36% | -2420415.3221 | 78.26% | -32d | 93.33% | 92.28% | 2011-05-09 12:00 | 2012-02-17 15:00 | 2013-01-22 11:00 | 2011-07-18 10:00 | 2012-02-17 15:00 | 2012-07-18 17:00 | 2010-12-07 17:00 | 2010-12-15 12:00 | 2011-01-17 11:00 | 23790250.8323 | 27306919.8887 | 32102466.9358 | 24694381.9619 | 37928481.2539 | 28462241.6652 | 28082151.7304 | 26706876.0982 | 0.93333 | 0.78258 | 0.60361 | 0.92282 | -32 | 0.78258 | 1 | 0.93333 | 1
97 | 2010-08-22 17:00 | 2010-08-29 17:00 | 16410864.4354 | 9965595.3603 | 12545706.2899 | 2010-08-03 17:00 | -6445269.0751 | 60.73% | -2580110.9296 | 79.43% | -18d | 96.29% | 89.4% | 2011-06-02 11:00 | 2012-02-10 12:00 | 2012-12-20 11:00 | 2011-07-18 12:00 | 2012-02-10 12:00 | 2012-06-27 15:00 | 2010-11-17 17:00 | 2010-11-22 10:00 | 2010-12-13 16:00 | 23949946.4398 | 26902525.1458 | 31325661.9596 | 24389510.2999 | 36187826.951 | 27455892.8962 | 27612231.8684 | 26318081.4452 | 0.96289 | 0.79434 | 0.60726 | 0.89399 | -18 | 0.79434 | 1 | 0.96289 | 1
98 | 2010-08-29 17:00 | 2010-09-05 17:00 | 17822313.2373 | 10464058.5634 | 13201366.2186 | 2010-08-05 17:00 | -7358254.6738 | 58.71% | -2737307.6552 | 79.26% | -21d | 95.71% | 88.65% | 2011-07-04 15:00 | 2012-03-23 09:00 | 2013-02-14 09:00 | 2011-08-03 10:00 | 2012-03-23 09:00 | 2012-08-17 16:00 | 2010-11-22 17:00 | 2010-11-25 12:00 | 2010-12-16 16:00 | 24107143.1654 | 26960000.5477 | 31776011.1962 | 24595461.5361 | 36634978.4488 | 27576058.8012 | 27712485.5089 | 26411710.0098 | 0.95714 | 0.79265 | 0.58713 | 0.88646 | -21 | 0.79265 | 1 | 0.95714 | 1
99 | 2010-09-05 17:00 | 2010-09-12 17:00 | 19351611.5289 | 12170747.6739 | 15065252.0555 | 2010-08-12 17:00 | -7180863.855 | 62.89% | -2894504.3816 | 80.79% | -21d | 95.76% | 93.98% | 2011-06-28 11:00 | 2011-12-30 15:00 | 2012-10-04 10:00 | 2011-07-07 14:00 | 2011-12-30 15:00 | 2012-04-23 12:00 | 2010-11-22 17:00 | 2010-11-25 10:00 | 2010-12-13 16:00 | 24264339.8918 | 26452110.1719 | 29691894.4769 | 24671894.4162 | 33170471.2834 | 26956591.2277 | 26979927.5271 | 26045170.4125 | 0.95758 | 0.80787 | 0.62893 | 0.93979 | -21 | 0.80787 | 1 | 0.95758 | 1
100 | 2010-09-12 17:00 | 2010-09-19 17:00 | 20956421.3693 | 12386024.4652 | 15437725.5789 | 2010-08-12 17:00 | -8570396.9042 | 59.1% | -3051701.1138 | 80.23% | -26d | 94.8% | 94.46% | 2011-08-15 12:00 | 2012-03-15 10:00 | 2013-01-16 09:00 | 2011-08-05 12:00 | 2012-03-15 10:00 | 2012-07-26 16:00 | 2010-11-29 17:00 | 2010-12-02 15:00 | 2010-12-21 17:00 | 24421536.624 | 26634991.4939 | 30637802.9154 | 24914319.5083 | 34382837.7381 | 27249187.5146 | 27257520.0128 | 26242620.9663 | 0.948 | 0.80232 | 0.59104 | 0.94462 | -26 | 0.80232 | 1 | 0.948 | 1
101 | 2010-09-19 17:00 | 2010-09-26 17:00 | 21229126.7762 | 13809527.1415 | 17018424.9871 | 2010-08-19 17:00 | -7419599.6346 | 65.05% | -3208897.8456 | 81.14% | -26d | 94.85% | 94.77% | 2011-07-06 10:00 | 2011-11-23 09:00 | 2012-08-10 14:00 | 2011-06-28 12:00 | 2011-11-23 09:00 | 2012-02-29 10:00 | 2010-11-29 17:00 | 2010-12-02 12:00 | 2010-12-17 15:00 | 24578733.3558 | 26335510.18 | 28640745.084 | 24989105 | 31341405.1093 | 26841239.2302 | 26720377.9235 | 26031028.8435 | 0.94851 | 0.81145 | 0.6505 | 0.94773 | -26 | 0.81145 | 1 | 0.94851 | 1
102 | 2010-09-26 17:00 | 2010-10-03 17:00 | 21292498.5571 | 14640249.843 | 18006344.4119 | 2010-08-24 11:00 | -6652248.7141 | 68.76% | -3366094.5689 | 81.31% | -28d 5h | 94.39% | 95.36% | 2011-06-09 11:00 | 2011-09-22 12:00 | 2012-05-25 09:00 | 2011-06-03 11:00 | 2011-09-22 12:00 | 2011-12-13 16:00 | 2010-12-02 14:00 | 2010-12-07 10:00 | 2010-12-21 16:00 | 24735930.0791 | 26283200.2424 | 27793724.7261 | 25136105.3889 | 30044044.7734 | 26775384.0869 | 26546817.1187 | 26025173.158 | 0.94387 | 0.81306 | 0.68758 | 0.9536 | -28.625 | 0.81306 | 1 | 0.94387 | 1
103 | 2010-10-03 17:00 | 2010-10-10 17:00 | 21322927.4682 | 16164092.6699 | 19692669.744 | 2010-08-26 17:00 | -5158834.7983 | 75.81% | -3528577.0741 | 82.08% | -31d | 93.98% | 97.33% | 2011-04-19 15:00 | 2011-06-15 12:00 | 2012-01-12 15:00 | 2011-04-15 14:00 | 2011-06-15 12:00 | 2011-08-09 11:00 | 2010-12-06 17:00 | 2010-12-09 14:00 | 2010-12-23 09:00 | 24898412.5843 | 26034811.9613 | 26559846.2239 | 25231838.2621 | 28058932.0054 | 26441023.5496 | 26133296.3871 | 25856117.7536 | 0.93981 | 0.82082 | 0.75806 | 0.97326 | -31 | 0.82082 | 1 | 0.93981 | 1
104 | 2010-10-10 17:00 | 2010-10-17 17:00 | 21346381.4892 | 16633732.1214 | 20324791.6834 | 2010-09-01 16:00 | -4712649.3678 | 77.92% | -3691059.562 | 81.84% | -32d 1h | 93.82% | 97.65% | 2011-04-04 15:00 | 2011-05-19 15:00 | 2011-12-15 10:00 | 2011-04-01 15:00 | 2011-05-19 15:00 | 2011-07-06 16:00 | 2010-12-08 09:00 | 2010-12-10 14:00 | 2010-12-23 11:00 | 25060895.0722 | 26111846.2101 | 26402722.2988 | 25372752.2515 | 27751427.6736 | 26492905.1425 | 26167772.5949 | 25947205.7686 | 0.93822 | 0.8184 | 0.77923 | 0.97648 | -32.125 | 0.8184 | 1 | 0.93822 | 1
105 | 2010-10-17 17:00 | 2010-10-24 17:00 | 21369835.5102 | 17982928.8815 | 21835330.3323 | 2010-09-07 17:00 | -3386906.6287 | 84.15% | -3852401.4508 | 82.36% | -33d | 93.71% | 97.75% | 2011-02-17 10:00 | 2011-03-10 16:00 | 2011-09-14 12:00 | 2011-02-17 10:00 | 2011-03-10 16:00 | 2011-04-08 17:00 | 2010-12-08 17:00 | 2010-12-13 10:00 | 2010-12-22 15:00 | 25222236.961 | 25947798.6365 | 25860127.295 | 25449407.5276 | 26722341.3293 | 26223634.9252 | 25929960.1373 | 25837418.8506 | 0.93714 | 0.82357 | 0.84151 | 0.97746 | -33 | 0.82357 | 1 | 0.93714 | 1
106 | 2010-10-24 17:00 | 2010-10-31 17:00 | 21369835.5102 | 18130786.1982 | 22152461.4744 | 2010-09-08 17:00 | -3239049.312 | 84.84% | -4021675.2762 | 81.85% | -37d | 93.02% | 97.99% | 2011-02-11 14:00 | 2011-03-03 15:00 | 2011-09-12 17:00 | 2011-02-21 11:00 | 2011-03-11 14:00 | 2011-04-11 14:00 | 2010-12-14 17:00 | 2010-12-17 11:00 | 2010-12-28 17:00 | 25391510.7864 | 26109979.6049 | 25970164.1516 | 25634603.7368 | 26816986.8045 | 26406994.1501 | 26081203.1992 | 26004796.8112 | 0.93019 | 0.81845 | 0.84843 | 0.97989 | -37 | 0.81845 | 1 | 0.93019 | 1
107 | 2010-10-31 17:00 | 2010-11-07 17:00 | 21369835.5102 | 19319126.2831 | 23485503.9168 | 2010-09-10 14:00 | -2050709.2271 | 90.4% | -4166377.6337 | 82.26% | -40d 3h | 92.45% | 98.13% | 2011-01-03 11:00 | 2011-01-10 15:00 | 2011-07-04 17:00 | 2011-01-18 11:00 | 2011-01-25 15:00 | 2011-02-10 17:00 | 2010-12-20 11:00 | 2010-12-22 16:00 | 2010-12-31 17:00 | 25536213.1439 | 25978470.6731 | 25753894.227 | 25703607.4022 | 26243097.026 | 26181965.306 | 25930067.0714 | 25918180.1281 | 0.92453 | 0.8226 | 0.90404 | 0.98133 | -40.375 | 0.8226 | 1 | 0.92453 | 1
108 | 2010-11-07 17:00 | 2010-11-14 17:00 | 21369835.5102 | 19527634.5406 | 23833571.6596 | 2010-09-13 17:00 | -1842200.9696 | 91.38% | -4305937.119 | 81.93% | -44d | 91.85% | 98.5% | 2010-12-27 10:00 | 2010-12-31 12:00 | 2011-06-28 10:00 | 2011-01-18 12:00 | 2011-01-24 17:00 | 2011-02-09 09:00 | 2010-12-23 17:00 | 2010-12-28 14:00 | 2011-01-06 12:00 | 25675772.6292 | 26081986.7828 | 25849562.4657 | 25839193.683 | 26294098.1121 | 26281442.9631 | 26031311.145 | 26028836.6688 | 0.91852 | 0.81933 | 0.91379 | 0.98499 | -44 | 0.81933 | 1 | 0.91852 | 1
109 | 2010-11-14 17:00 | 2010-11-21 17:00 | 21369835.5102 | 20693641.0743 | 25131423.4111 | 2010-09-16 17:00 | -676194.4359 | 96.84% | -4437782.3368 | 82.34% | -46d | 91.56% | 98.49% | 2010-11-16 14:00 | 2010-11-17 09:00 | 2011-04-28 11:00 | 2010-12-15 10:00 | 2010-12-15 15:00 | 2010-12-21 14:00 | 2010-12-27 17:00 | 2010-12-30 11:00 | 2011-01-07 12:00 | 25807617.847 | 25952628.757 | 25829713.4711 | 25869952.4042 | 25979462.8209 | 26028331.0534 | 25924701.6734 | 25934645.0525 | 0.9156 | 0.82342 | 0.96836 | 0.98486 | -46 | 0.82342 | 1 | 0.9156 | 1
110 | 2010-11-21 17:00 | 2010-11-28 17:00 | 21369835.5102 | 20870412.9469 | 25460798.9949 | 2010-09-16 17:00 | -499422.5633 | 97.66% | -4590386.048 | 81.97% | -51d | 90.73% | 98.77% | 2010-11-10 10:00 | 2010-11-10 14:00 | 2011-04-25 15:00 | 2010-12-15 16:00 | 2010-12-16 09:00 | 2010-12-20 17:00 | 2011-01-03 17:00 | 2011-01-06 14:00 | 2011-01-14 17:00 | 25960221.5582 | 26070068.0846 | 25972172.5865 | 26011264.746 | 26084647.7065 | 26132338.0717 | 26047601.0355 | 26057323.377 | 0.90727 | 0.81971 | 0.97663 | 0.98767 | -51 | 0.81971 | 1 | 0.90727 | 1
111 | 2010-11-28 17:00 | 2010-12-05 17:00 | 21369835.5102 | 20961769.2533 | 25579090.6647 | 2010-09-17 17:00 | -408066.2569 | 98.09% | -4617321.4114 | 81.95% | -55d | 90.09% | 99.1% | 2010-11-05 17:00 | 2010-11-08 10:00 | 2011-04-21 09:00 | 2010-12-20 14:00 | 2010-12-20 15:00 | 2010-12-23 09:00 | 2011-01-07 17:00 | 2011-01-12 15:00 | 2011-01-20 16:00 | 25987156.9216 | 26077043.0873 | 25995100.8154 | 26032044.2098 | 26086736.8101 | 26131817.8538 | 26058170.0603 | 26067341.9772 | 0.9009 | 0.81949 | 0.9809 | 0.99103 | -55 | 0.81949 | 1 | 0.9009 | 1
112 | 2010-12-05 17:00 | 2010-12-12 17:00 | 21369835.5102 | 21047004.9098 | 25691423.9846 | 2010-09-21 12:00 | -322830.6004 | 98.49% | -4644419.0748 | 81.92% | -58d 4h | 89.55% | 99.45% | 2010-11-03 16:00 | 2010-11-03 17:00 | 2011-04-18 14:00 | 2010-12-23 12:00 | 2010-12-23 14:00 | 2010-12-27 12:00 | 2011-01-13 12:00 | 2011-01-18 10:00 | 2011-01-25 17:00 | 26014254.585 | 26085493.2532 | 26019206.3393 | 26051912.7907 | 26091537.7055 | 26131461.453 | 26070174.4309 | 26078285.8176 | 0.89554 | 0.81922 | 0.98489 | 0.99446 | -58.5 | 0.81922 | 1 | 0.89554 | 1
113 | 2010-12-12 17:00 | 2010-12-19 17:00 | 21369835.5102 | 21142837.4079 | 25817682.0243 | 2010-09-23 09:00 | -226998.1023 | 98.94% | -4674844.6164 | 81.89% | -61d 7h | 89.05% | 99.73% | 2010-11-01 14:00 | 2010-11-01 14:00 | 2011-04-13 17:00 | 2010-12-27 17:00 | 2010-12-28 09:00 | 2010-12-29 11:00 | 2011-01-18 16:00 | 2011-01-21 14:00 | 2011-01-28 17:00 | 26044680.1266 | 26094871.1599 | 26047117.2705 | 26072596.6634 | 26097847.1752 | 26128960.2585 | 26083793.6424 | 26090110.1934 | 0.89049 | 0.81893 | 0.98938 | 0.99733 | -61.875 | 0.81893 | 1 | 0.89049 | 1
114 | 2010-12-19 17:00 | 2010-12-26 17:00 | 21369835.5102 | 21142837.4079 | 25817682.0243 | 2010-09-23 09:00 | -226998.1023 | 98.94% | -4674844.6164 | 81.89% | -66d 7h | 88.27% | 99.73% | 2010-11-01 14:00 | 2010-11-01 14:00 | 2011-04-13 17:00 | 2011-01-03 17:00 | 2011-01-04 09:00 | 2011-01-05 12:00 | 2011-01-25 16:00 | 2011-01-28 15:00 | 2011-02-07 10:00 | 26044680.1266 | 26094871.1599 | 26047117.2705 | 26074852.5451 | 26097847.1752 | 26131714.9332 | 26083793.6424 | 26090621.9334 | 0.88268 | 0.81893 | 0.98938 | 0.99733 | -66.875 | 0.81893 | 1 | 0.88268 | 1
115 | 2010-12-26 17:00 | 2011-01-02 17:00 | 21369835.5102 | 21142837.4079 | 25817682.0243 | 2010-09-23 09:00 | -226998.1023 | 98.94% | -4674844.6164 | 81.89% | -71d 7h | 87.5% | 99.73% | 2010-11-01 14:00 | 2010-11-01 14:00 | 2011-04-13 17:00 | 2011-01-11 09:00 | 2011-01-11 09:00 | 2011-01-12 12:00 | 2011-02-01 16:00 | 2011-02-04 17:00 | 2011-02-14 12:00 | 26044680.1266 | 26094871.1599 | 26047117.2705 | 26077108.4269 | 26097847.1752 | 26134469.6078 | 26083793.6424 | 26091126.6498 | 0.875 | 0.81893 | 0.98938 | 0.99733 | -71.875 | 0.81893 | 1 | 0.875 | 1
116 | 2011-01-02 17:00 | 2011-01-09 17:00 | 21369835.5102 | 21229923.843 | 25929018.215 | 2010-09-24 17:00 | -139911.6672 | 99.35% | -4699094.372 | 81.88% | -75d | 87.07% | 99.84% | 2010-10-28 11:00 | 2010-10-28 12:00 | 2011-04-11 11:00 | 2011-01-13 15:00 | 2011-01-13 16:00 | 2011-01-14 14:00 | 2011-02-04 17:00 | 2011-02-09 17:00 | 2011-02-16 17:00 | 26068929.8822 | 26099898.346 | 26069851.9427 | 26089708.8427 | 26101024.4981 | 26125276.5833 | 26092905.3902 | 26097758.3602 | 0.87069 | 0.81877 | 0.99345 | 0.99837 | -75 | 0.81877 | 1 | 0.87069 | 1
117 | 2011-01-09 17:00 | 2011-01-16 17:00 | 21369835.5102 | 21276019.4262 | 25980035.8064 | 2010-09-30 17:00 | -93816.084 | 99.56% | -4704016.3802 | 81.89% | -76d | 87.01% | 99.94% | 2010-10-27 10:00 | 2010-10-27 11:00 | 2011-04-07 16:00 | 2011-01-19 14:00 | 2011-01-19 14:00 | 2011-01-20 09:00 | 2011-02-07 17:00 | 2011-02-10 11:00 | 2011-02-16 12:00 | 26073851.8904 | 26094594.1348 | 26074265.5701 | 26087859.7929 | 26095099.277 | 26111699.1112 | 26089855.7553 | 26093180.7998 | 0.87009 | 0.81894 | 0.99561 | 0.99942 | -76 | 0.81894 | 1 | 0.87009 | 1
118 | 2011-01-16 17:00 | 2011-01-23 17:00 | 21369835.5102 | 21322927.4682 | 26028981.4284 | 2010-10-13 17:00 | -46908.042 | 99.78% | -4706053.9601 | 81.92% | -72d | 87.8% | 100% | 2010-10-26 09:00 | 2010-10-26 09:00 | 2011-04-06 10:00 | 2011-01-25 10:00 | 2011-01-25 10:00 | 2011-01-25 14:00 | 2011-02-01 17:00 | 2011-02-02 17:00 | 2011-02-04 15:00 | 26075889.4703 | 26086242.2597 | 26075992.6628 | 26082409.5071 | 26086368.2271 | 26094201.2942 | 26083849.7337 | 26085432.3396 | 0.87797 | 0.8192 | 0.9978 | 1 | -72 | 0.8192 | 1 | 0.87797 | 1
119 | 2011-01-23 17:00 | 2011-01-30 17:00 | 21369835.5102 | 21358645.0297 | 26066130.8099 | 2010-10-21 17:00 | -11190.4805 | 99.95% | -4707485.7801 | 81.94% | -71d | 88.07% | 100% | 2010-10-25 10:00 | 2010-10-25 10:00 | 2011-04-04 17:00 | 2011-01-31 10:00 | 2011-01-31 10:00 | 2011-01-31 11:00 | 2011-01-31 17:00 | 2011-02-01 09:00 | 2011-02-01 11:00 | 26077321.2903 | 26079787.6934 | 26077327.1534 | 26078837.5577 | 26079794.8487 | 26081638.149 | 26079212.7103 | 26079586.4665 | 0.88067 | 0.8194 | 0.99948 | 1 | -71 | 0.8194 | 1 | 0.88067 | 1
120 | 2011-01-30 17:00 | 2011-02-06 17:00 | 21369835.5102 | 21369835.5102 | 26077764.7403 | 2010-10-22 17:00 | 0 | 100% | -4707929.2301 | 81.95% | -75d | 87.5% | 100% | 2010-10-22 17:00 | 2010-10-22 17:00 | 2011-04-04 14:00 | 2011-02-04 17:00 | 2011-02-04 17:00 | 2011-02-04 17:00 | 2011-02-04 17:00 | 2011-02-04 17:00 | 2011-02-04 17:00 | 26077764.7403 | 26077764.7403 | 26077764.7403 | 26077764.7403 | 26077764.7403 | 26077764.7403 | 26077764.7403 | 26077764.7403 | 0.875 | 0.81947 | 1 | 1 | -75 | 0.81947 | 1 | 0.875 | 1