## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Wind Farm | 1 |  |  | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 | 732.375
1 | Wind Farm | 1.1 |  |  | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 | 732.375
2 | Vergunningen | 1.1.1 |  |  | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 | 20
3 | Milieuvergunning | 1.1.1.1 |  |  | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
4 | Bouwvergunning | 1.1.1.2 |  |  | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
5 | RUP | 1.1.1.3 |  | FS16;FS17 | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
6 | studies | 1.1.2 |  |  | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 | 403.375
7 | sonderingen | 1.1.2.1 |  |  | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 | 53.375
8 | offerte | 1.1.2.1.1 |  | FS9 | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 13.375
9 | sondering | 1.1.2.1.2 | 8FS | FS10;SF21 | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 19.375
10 | sonderingsverslag | 1.1.2.1.3 | 9FS | FS14 | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 19.375
11 | Aansluitingen | 1.1.2.2 |  |  | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 | 354.375
12 | orientatiestudie | 1.1.2.2.1 |  | FS13;FS16;FS18 | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 144.375
13 | detailstudie | 1.1.2.2.2 | 12FS | FS14 | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 123.375
14 | financieel plan | 1.1.2.2.3 | 13FS;10FS |  | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 81.375
15 | uitvoeringsplan | 1.1.2.3 |  |  | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 | 269.375
16 | roads and hardstands | 1.1.2.3.1 | 5FS;12FS |  | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 17.375
17 | contracten | 1.1.2.3.2 | 5FS | FS18 | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 17.375
18 | extra vergunningen | 1.1.2.3.3 | 12FS;17FS | FS20 | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 249.375
19 | preconstruction | 1.1.3 |  |  | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 | 349.375
20 | Roads and hardstands | 1.1.3.1 | 24SF;18FS | SF22 | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 19.375
21 | Mark NMP pipe | 1.1.3.2 | 9SF |  | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 6.375
22 | Mark NMP pipe | 1.1.3.3 | 20SF |  | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 6.375
23 | Foundations | 1.1.4 |  |  | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 | 209.375
24 | settlement on construction site | 1.1.4.1 | 26SF | SF20 | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 6.375
25 | Piling | 1.1.4.2 |  |  | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 | 153.375
26 | foundation 1 | 1.1.4.2.1 | 34SF | SF24 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 6.375
27 | foundation 2 | 1.1.4.2.2 | 35SF |  | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 6.375
28 | foundation 3 | 1.1.4.2.3 | 36SF |  | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 6.375
29 | foundation 4 | 1.1.4.2.4 | 37SF |  | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 6.375
30 | foundation 5 | 1.1.4.2.5 | 38SF |  | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 6.375
31 | foundation 6 | 1.1.4.2.6 | 39SF |  | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 6.375
32 | foundation 7 | 1.1.4.2.7 | 40SF |  | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 6.375
33 | Concrete works foundations | 1.1.4.3 |  |  | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 | 167.375
34 | foundation 1 | 1.1.4.3.1 | 42SF | SF26 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 20.375
35 | foundation 2 | 1.1.4.3.2 | 43SF | SF27 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 20.375
36 | foundation 3 | 1.1.4.3.3 | 44SF | SF28 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 20.375
37 | foundation 4 | 1.1.4.3.4 | 45SF | SF29 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 20.375
38 | foundation 5 | 1.1.4.3.5 | 46SF | SF30 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 20.375
39 | foundation 6 | 1.1.4.3.6 | 47SF | SF31 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 20.375
40 | foundation 7 | 1.1.4.3.7 | 48SF | SF32 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 20.375
41 | Setting of concrete | 1.1.4.4 |  |  | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 | 174.375
42 | setting concrete 1 | 1.1.4.4.1 | 52SF | SF34 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 27.375
43 | setting concrete 2 | 1.1.4.4.2 | 58SF | SF35 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 27.375
44 | setting concrete 3 | 1.1.4.4.3 | 64SF | SF36 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 27.375
45 | setting concrete 4 | 1.1.4.4.4 | 70SF | SF37 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 27.375
46 | setting concrete 5 | 1.1.4.4.5 | 76SF | SF38 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 27.375
47 | setting concrete 6 | 1.1.4.4.6 | 82SF | SF39 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 27.375
48 | setting concrete 7 | 1.1.4.4.7 | 88SF | SF40 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 27.375
49 | Windturbines | 1.1.5 |  |  | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 | 205
50 | Tower | 1.1.5.1 |  |  | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 | 169
51 | WEC 1 | 1.1.5.1.1 |  |  | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 | 22
52 | Pre installation | 1.1.5.1.1.1 |  | SF42;FS53 | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
53 | Installation tower | 1.1.5.1.1.2 | 52FS | FS54;FS58;FS59 | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 13.375
54 | stressing tower | 1.1.5.1.1.3 | 53FS | FS55 | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
55 | injection of tower | 1.1.5.1.1.4 | 54FS | FS56 | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
56 | Finish | 1.1.5.1.1.5 | 55FS | FS94;FS151 | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
57 | WEC 2 | 1.1.5.1.2 |  |  | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 | 22
58 | Pre installation | 1.1.5.1.2.1 | 53FS | SF43;FS59 | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
59 | Installation tower | 1.1.5.1.2.2 | 58FS;53FS | FS60;FS64;FS65 | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 13.375
60 | stressing tower | 1.1.5.1.2.3 | 59FS | FS61 | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
61 | injection of tower | 1.1.5.1.2.4 | 60FS | FS62 | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
62 | Finish | 1.1.5.1.2.5 | 61FS | FS95 | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
63 | WEC 3 | 1.1.5.1.3 |  |  | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 | 22
64 | Pre installation | 1.1.5.1.3.1 | 59FS | SF44;FS65 | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
65 | Installation tower | 1.1.5.1.3.2 | 64FS;59FS | FS66;FS70;FS71 | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 13.375
66 | stressing tower | 1.1.5.1.3.3 | 65FS | FS67 | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
67 | injection of tower | 1.1.5.1.3.4 | 66FS | FS68 | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
68 | Finish | 1.1.5.1.3.5 | 67FS | FS96 | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
69 | WEC 4 | 1.1.5.1.4 |  |  | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 | 22
70 | Pre installation | 1.1.5.1.4.1 | 65FS | SF45;FS71 | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
71 | Installation tower | 1.1.5.1.4.2 | 70FS;65FS | FS72 | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 13.375
72 | stressing tower | 1.1.5.1.4.3 | 71FS | FS73 | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
73 | injection of tower | 1.1.5.1.4.4 | 72FS | FS74 | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
74 | Finish | 1.1.5.1.4.5 | 73FS | FS76;FS97 | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
75 | WEC 5 | 1.1.5.1.5 |  |  | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 | 22
76 | Pre installation | 1.1.5.1.5.1 | 74FS | SF46;FS77 | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
77 | Installation tower | 1.1.5.1.5.2 | 76FS | FS78 | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 13.375
78 | stressing tower | 1.1.5.1.5.3 | 77FS | FS79 | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
79 | injection of tower | 1.1.5.1.5.4 | 78FS | FS80 | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
80 | Finish | 1.1.5.1.5.5 | 79FS | FS82;FS83;FS98 | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
81 | WEC 6 | 1.1.5.1.6 |  |  | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 | 22
82 | Pre installation | 1.1.5.1.6.1 | 80FS | SF47 | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
83 | Installation tower | 1.1.5.1.6.2 | 80FS | FS84 | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 13.375
84 | stressing tower | 1.1.5.1.6.3 | 83FS | FS85 | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
85 | injection of tower | 1.1.5.1.6.4 | 84FS | FS86 | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 3.375
86 | Finish | 1.1.5.1.6.5 | 85FS | FS88;FS89;FS99 | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
87 | WEC 7 | 1.1.5.1.7 |  |  | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 | 22
88 | Pre installation | 1.1.5.1.7.1 | 86FS | SF48;FS89 | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
89 | Installation tower | 1.1.5.1.7.2 | 86FS;88FS | FS90 | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 13.375
90 | stressing tower | 1.1.5.1.7.3 | 89FS | FS91 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
91 | injection of tower | 1.1.5.1.7.4 | 90FS | FS92 | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
92 | Finish | 1.1.5.1.7.5 | 91FS | FS100 | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 1.375
93 | Erection machines | 1.1.5.2 |  |  | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 | 48.375
94 | WEC 1 | 1.1.5.2.1 | 95SF;56FS | FS102 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 6.375
95 | WEC 2 | 1.1.5.2.2 | 96SF;62FS | SF94;FS103 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 6.375
96 | WEC 3 | 1.1.5.2.3 | 97SF;68FS | SF95;FS104 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 6.375
97 | WEC 4 | 1.1.5.2.4 | 98SF;74FS | SF96;FS105 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 6.375
98 | WEC 5 | 1.1.5.2.5 | 99SF;80FS | SF97;FS106 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 6.375
99 | WEC 6 | 1.1.5.2.6 | 100SF;86FS | SF98;FS107 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 6.375
100 | WEC 7 | 1.1.5.2.7 | 92FS | SF99;FS108 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 6.375
101 | Grid | 1.1.5.3 |  |  | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 | 46.375
102 | WEC 1 | 1.1.5.3.1 | 94FS | FS110 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 4.375
103 | WEC 2 | 1.1.5.3.2 | 95FS | FS111 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 4.375
104 | WEC 3 | 1.1.5.3.3 | 96FS | FS112 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 4.375
105 | WEC 4 | 1.1.5.3.4 | 97FS | FS113 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 4.375
106 | WEC 5 | 1.1.5.3.5 | 98FS | FS114 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 4.375
107 | WEC 6 | 1.1.5.3.6 | 99FS | FS115 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 4.375
108 | WEC 7 | 1.1.5.3.7 | 100FS | FS116 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 4.375
109 | Energizing | 1.1.5.4 |  |  | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 | 42
110 | WEC 1 | 1.1.5.4.1 | 102FS;158FS | FS118 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
111 | WEC 2 | 1.1.5.4.2 | 103FS;158FS | FS119 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
112 | WEC 3 | 1.1.5.4.3 | 104FS;158FS | FS120 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
113 | WEC 4 | 1.1.5.4.4 | 105FS;158FS | FS121 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
114 | WEC 5 | 1.1.5.4.5 | 106FS;158FS | FS122 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
115 | WEC 6 | 1.1.5.4.6 | 107FS;158FS | FS123 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
116 | WEC 7 | 1.1.5.4.7 | 108FS;158FS | FS124 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
117 | Commissioning | 1.1.5.5 |  |  | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 | 44.375
118 | WEC 1 | 1.1.5.5.1 | 110FS | FS126 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2.375
119 | WEC 2 | 1.1.5.5.2 | 111FS | FS127 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2.375
120 | WEC 3 | 1.1.5.5.3 | 112FS | FS128 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2.375
121 | WEC 4 | 1.1.5.5.4 | 113FS | FS129 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2.375
122 | WEC 5 | 1.1.5.5.5 | 114FS | FS130 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2.375
123 | WEC 6 | 1.1.5.5.6 | 115FS | FS131 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2.375
124 | WEC 7 | 1.1.5.5.7 | 116FS | FS132 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2.375
125 | Trail period 300h | 1.1.5.6 |  |  | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 | 58.375
126 | WEC 1 | 1.1.5.6.1 | 118FS | FS134 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 16.375
127 | WEC 2 | 1.1.5.6.2 | 119FS | FS135 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 16.375
128 | WEC 3 | 1.1.5.6.3 | 120FS | FS136 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 16.375
129 | WEC 4 | 1.1.5.6.4 | 121FS | FS137 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 16.375
130 | WEC 5 | 1.1.5.6.5 | 122FS | FS138 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 16.375
131 | WEC 6 | 1.1.5.6.6 | 123FS | FS139 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 16.375
132 | WEC 7 | 1.1.5.6.7 | 124FS | FS140 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 | 16.375
133 | 300h Maintenace service | 1.1.5.7 |  |  | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 | 43.375
134 | WEC 1 | 1.1.5.7.1 | 126FS | FS142 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 1.375
135 | WEC 2 | 1.1.5.7.2 | 127FS | FS143 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 1.375
136 | WEC 3 | 1.1.5.7.3 | 128FS | FS144 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 1.375
137 | WEC 4 | 1.1.5.7.4 | 129FS | FS145 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 1.375
138 | WEC 5 | 1.1.5.7.5 | 130FS | FS146 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 1.375
139 | WEC 6 | 1.1.5.7.6 | 131FS | FS147 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 1.375
140 | WEC 7 | 1.1.5.7.7 | 132FS | FS148 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 | 1.375
141 | Take over | 1.1.5.8 |  |  | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 | 42
142 | WEC 1 | 1.1.5.8.1 | 134FS |  | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
143 | WEC 2 | 1.1.5.8.2 | 135FS |  | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
144 | WEC 3 | 1.1.5.8.3 | 136FS |  | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
145 | WEC 4 | 1.1.5.8.4 | 137FS |  | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
146 | WEC 5 | 1.1.5.8.5 | 138FS |  | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
147 | WEC 6 | 1.1.5.8.6 | 139FS |  | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
148 | WEC 7 | 1.1.5.8.7 | 140FS | FS166 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
149 | Electrical works | 1.1.6 |  |  | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 | 42.375
150 | Electricity distributor | 1.1.6.1 |  |  | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 | 42.375
151 | Mobilisation to site | 1.1.6.1.1 | 56FS | FS152;SF164 | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 3.375
152 | Excavation for cabin | 1.1.6.1.2 | 151FS | FS153;FS154 | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
153 | Building of the cabin | 1.1.6.1.3 | 152FS |  | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 0.375
154 | Excavation for cables | 1.1.6.1.4 | 152FS | SS155 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 17.375
155 | Laying of cables to WEC 1 | 1.1.6.1.5 | 154SS | FS156 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 17.375
156 | Sheet test | 1.1.6.1.6 | 155FS | FS157 | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 4.375
157 | Electrical connection to Turbines | 1.1.6.1.7 | 156FS | FS158 | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2.375
158 | Test of cables | 1.1.6.1.8 | 157FS | FS110;FS111;FS112;FS113;FS114;FS115;FS116;FS159 | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 8.375
159 | Energize | 1.1.6.1.9 | 158FS | FS165 | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
160 | Gridconnection | 1.1.7 |  |  | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 | 148
161 | Electricity distributor | 1.1.7.1 |  |  | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 | 148
162 | Order connection | 1.1.7.1.1 | 163SF |  | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
163 | Order material | 1.1.7.1.2 | 164SF | SF162 | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 55.375
164 | Lay cable | 1.1.7.1.3 | 151SF | SF163 | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 27.375
165 | Ready to Energize | 1.1.7.1.4 | 159FS |  | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 18.375
166 | Finish | 1.2 | 148FS |  | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Wind Farm | 4200h |  |  |  |  | 99 | 100 | 101
1 | Wind Farm | 4200h |  |  |  |  | 99 | 100 | 101
2 | Vergunningen | 112h |  |  |  |  | 99 | 100 | 101
3 | Milieuvergunning | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Bouwvergunning | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | RUP | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | studies | 2320h |  |  |  |  | 99 | 100 | 101
7 | sonderingen | 304h |  |  |  |  | 99 | 100 | 101
8 | offerte | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | sondering | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | sonderingsverslag | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Aansluitingen | 2040h |  |  |  |  | 99 | 100 | 101
12 | orientatiestudie | 840h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | detailstudie | 720h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | financieel plan | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | uitvoeringsplan | 1552h |  |  |  |  | 99 | 100 | 101
16 | roads and hardstands | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | contracten | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | extra vergunningen | 1440h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | preconstruction | 2000h |  |  |  |  | 99 | 100 | 101
20 | Roads and hardstands | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Mark NMP pipe | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Mark NMP pipe | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Foundations | 1200h |  |  |  |  | 99 | 100 | 101
24 | settlement on construction site | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Piling | 880h |  |  |  |  | 99 | 100 | 101
26 | foundation 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | foundation 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | foundation 3 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | foundation 4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | foundation 5 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | foundation 6 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | foundation 7 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Concrete works foundations | 960h |  |  |  |  | 99 | 100 | 101
34 | foundation 1 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | foundation 2 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | foundation 3 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | foundation 4 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | foundation 5 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | foundation 6 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | foundation 7 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Setting of concrete | 1000h |  |  |  |  | 99 | 100 | 101
42 | setting concrete 1 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | setting concrete 2 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | setting concrete 3 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | setting concrete 4 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | setting concrete 5 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | setting concrete 6 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | setting concrete 7 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Windturbines | 1176h |  |  |  |  | 99 | 100 | 101
50 | Tower | 968h |  |  |  |  | 99 | 100 | 101
51 | WEC 1 | 128h |  |  |  |  | 99 | 100 | 101
52 | Pre installation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Installation tower | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | stressing tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | injection of tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Finish | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | WEC 2 | 128h |  |  |  |  | 99 | 100 | 101
58 | Pre installation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Installation tower | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | stressing tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | injection of tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Finish | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | WEC 3 | 128h |  |  |  |  | 99 | 100 | 101
64 | Pre installation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Installation tower | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | stressing tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | injection of tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Finish | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | WEC 4 | 128h |  |  |  |  | 99 | 100 | 101
70 | Pre installation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Installation tower | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | stressing tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | injection of tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Finish | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | WEC 5 | 128h |  |  |  |  | 99 | 100 | 101
76 | Pre installation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | Installation tower | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | stressing tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | injection of tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | Finish | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | WEC 6 | 128h |  |  |  |  | 99 | 100 | 101
82 | Pre installation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Installation tower | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | stressing tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | injection of tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Finish | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | WEC 7 | 128h |  |  |  |  | 99 | 100 | 101
88 | Pre installation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | Installation tower | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | stressing tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | injection of tower | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Finish | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Erection machines | 280h |  |  |  |  | 99 | 100 | 101
94 | WEC 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | WEC 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | WEC 3 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | WEC 4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | WEC 5 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | WEC 6 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | WEC 7 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | Grid | 264h |  |  |  |  | 99 | 100 | 101
102 | WEC 1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | WEC 2 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | WEC 3 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | WEC 4 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | WEC 5 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | WEC 6 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | WEC 7 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Energizing | 240h |  |  |  |  | 99 | 100 | 101
110 | WEC 1 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | WEC 2 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | WEC 3 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | WEC 4 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | WEC 5 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | WEC 6 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | WEC 7 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | Commissioning | 264h |  |  |  |  | 99 | 100 | 101
118 | WEC 1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | WEC 2 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | WEC 3 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | WEC 4 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | WEC 5 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | WEC 6 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | WEC 7 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | Trail period 300h | 344h |  |  |  |  | 99 | 100 | 101
126 | WEC 1 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | WEC 2 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | WEC 3 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | WEC 4 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | WEC 5 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | WEC 6 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | WEC 7 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | 300h Maintenace service | 256h |  |  |  |  | 99 | 100 | 101
134 | WEC 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | WEC 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | WEC 3 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | WEC 4 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | WEC 5 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | WEC 6 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | WEC 7 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | Take over | 240h |  |  |  |  | 99 | 100 | 101
142 | WEC 1 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | WEC 2 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | WEC 3 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | WEC 4 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | WEC 5 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | WEC 6 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | WEC 7 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | Electrical works | 248h |  |  |  |  | 99 | 100 | 101
150 | Electricity distributor | 248h |  |  |  |  | 99 | 100 | 101
151 | Mobilisation to site | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | Excavation for cabin | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | Building of the cabin | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | Excavation for cables | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | Laying of cables to WEC 1 | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | Sheet test | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | Electrical connection to Turbines | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | Test of cables | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | Energize | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | Gridconnection | 848h |  |  |  |  | 99 | 100 | 101
161 | Electricity distributor | 848h |  |  |  |  | 99 | 100 | 101
162 | Order connection | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | Order material | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | Lay cable | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | Ready to Energize | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | Finish | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2008-10-26 17:00 |  | TP Name | 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 5d | [5 empty] | 56573.6211 |  | 0.2647% |  | 56573.6211 | 56573.6211
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 5d | [5 empty] | 56573.6211 |  | 0.2647% |  | 56573.6211 | 56573.6211
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 5d | [5 empty] | 56573.6211 |  | 18.26% |  | 56573.6211 | 56573.6211
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 5d | [5 empty] | 56573.6211 |  | 38.28% |  | 56573.6211 | 56573.6211
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 5d | 56573.6211 | 4759.9998 | 100d | 0 | 0 | 56573.6211 | 4759.9998 | 4.762% | Started | 56573.6211 | 56573.6211 | 100 | 4.7619 | 4.7619 | 100 | 92.2392 | 4.7619
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2008-11-02 17:00 |  | TP Name | 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 10d | [5 empty] | 56811.6211 |  | 0.2658% |  | 56811.6211 | 56811.6211
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 10d | [5 empty] | 56811.6211 |  | 0.2658% |  | 56811.6211 | 56811.6211
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 10d | [5 empty] | 56811.6211 |  | 18.34% |  | 56811.6211 | 56811.6211
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 10d | [5 empty] | 56811.6211 |  | 38.44% |  | 56811.6211 | 56811.6211
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 10d | 56811.6211 | 4521.9999 | 95d | 0 | 0 | 56811.6211 | 4521.9999 | 9.524% | Started | 56811.6211 | 56811.6211 | 100 | 9.5238 | 9.5238 | 100 | 92.6272 | 9.5238
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2008-11-09 17:00 |  | TP Name | 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 15d | [5 empty] | 57049.6211 |  | 0.267% |  | 57049.6211 | 57049.6211
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 15d | [5 empty] | 57049.6211 |  | 0.267% |  | 57049.6211 | 57049.6211
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 15d | [5 empty] | 57049.6211 |  | 18.42% |  | 57049.6211 | 57049.6211
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 15d | [5 empty] | 57049.6211 |  | 38.6% |  | 57049.6211 | 57049.6211
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 15d | 57049.6211 | 4283.9999 | 90d | 0 | 0 | 57049.6211 | 4283.9999 | 14.29% | Started | 57049.6211 | 57049.6211 | 100 | 14.2857 | 14.2857 | 100 | 93.0153 | 14.2857
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2008-11-16 17:00 |  | TP Name | 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 20d | [5 empty] | 57287.6211 |  | 0.2681% |  | 57287.6211 | 57287.6211
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 20d | [5 empty] | 57287.6211 |  | 0.2681% |  | 57287.6211 | 57287.6211
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 20d | [5 empty] | 57287.6211 |  | 18.49% |  | 57287.6211 | 57287.6211
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 20d | [5 empty] | 57287.6211 |  | 38.76% |  | 57287.6211 | 57287.6211
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 20d | 57287.6211 | 4045.9999 | 85d | 0 | 0 | 57287.6211 | 4045.9999 | 19.05% | Started | 57287.6211 | 57287.6211 | 100 | 19.0476 | 19.0476 | 100 | 93.4033 | 19.0476
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2008-11-23 17:00 |  | TP Name | 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 25d | [5 empty] | 57525.6211 |  | 0.2692% |  | 57525.6211 | 57525.6211
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 25d | [5 empty] | 57525.6211 |  | 0.2692% |  | 57525.6211 | 57525.6211
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 25d | [5 empty] | 57525.6211 |  | 18.57% |  | 57525.6211 | 57525.6211
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 25d | [5 empty] | 57525.6211 |  | 38.92% |  | 57525.6211 | 57525.6211
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 25d | 57525.6211 | 3807.9999 | 80d | 0 | 0 | 57525.6211 | 3807.9999 | 23.81% | Started | 57525.6211 | 57525.6211 | 100 | 23.8095 | 23.8095 | 100 | 93.7913 | 23.8095
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2008-11-30 17:00 |  | TP Name | 6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 30d | [5 empty] | 57763.621 |  | 0.2703% |  | 57763.6211 | 57763.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 30d | [5 empty] | 57763.621 |  | 0.2703% |  | 57763.6211 | 57763.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 30d | [5 empty] | 57763.621 |  | 18.65% |  | 57763.6211 | 57763.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 30d | [5 empty] | 57763.621 |  | 39.08% |  | 57763.6211 | 57763.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 30d | 57763.621 | 3569.9999 | 75d | 0 | 0 | 57763.621 | 3569.9999 | 28.57% | Started | 57763.6211 | 57763.621 | 100 | 28.5714 | 28.5714 | 100 | 94.1794 | 28.5714
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2008-12-07 17:00 |  | TP Name | 7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 35d | [5 empty] | 58001.621 |  | 0.2714% |  | 58001.6211 | 58001.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 35d | [5 empty] | 58001.621 |  | 0.2714% |  | 58001.6211 | 58001.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 35d | [5 empty] | 58001.621 |  | 18.72% |  | 58001.6211 | 58001.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 35d | [5 empty] | 58001.621 |  | 39.24% |  | 58001.6211 | 58001.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 35d | 58001.621 | 3331.9999 | 70d | 0 | 0 | 58001.621 | 3331.9999 | 33.33% | Started | 58001.6211 | 58001.621 | 100 | 33.3333 | 33.3333 | 100 | 94.5674 | 33.3333
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2008-12-14 17:00 |  | TP Name | 8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 40d | [5 empty] | 58239.621 |  | 0.2725% |  | 58239.6211 | 58239.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 40d | [5 empty] | 58239.621 |  | 0.2725% |  | 58239.6211 | 58239.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 40d | [5 empty] | 58239.621 |  | 18.8% |  | 58239.6211 | 58239.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 40d | [5 empty] | 58239.621 |  | 39.4% |  | 58239.6211 | 58239.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 40d | 58239.621 | 3093.9999 | 65d | 0 | 0 | 58239.621 | 3093.9999 | 38.1% | Started | 58239.6211 | 58239.621 | 100 | 38.0952 | 38.0952 | 100 | 94.9555 | 38.0952
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2008-12-21 17:00 |  | TP Name | 9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 45d | [5 empty] | 58477.621 |  | 0.2736% |  | 58477.621 | 58477.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 45d | [5 empty] | 58477.621 |  | 0.2736% |  | 58477.621 | 58477.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 45d | [5 empty] | 58477.621 |  | 18.88% |  | 58477.621 | 58477.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 45d | [5 empty] | 58477.621 |  | 39.56% |  | 58477.621 | 58477.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 45d | 58477.621 | 2855.9999 | 60d | 0 | 0 | 58477.621 | 2855.9999 | 42.86% | Started | 58477.621 | 58477.621 | 100 | 42.8571 | 42.8571 | 100 | 95.3435 | 42.8571
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2008-12-28 17:00 |  | TP Name | 10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 50d | [5 empty] | 58715.621 |  | 0.2748% |  | 58715.621 | 58715.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 50d | [5 empty] | 58715.621 |  | 0.2748% |  | 58715.621 | 58715.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 50d | [5 empty] | 58715.621 |  | 18.95% |  | 58715.621 | 58715.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 50d | [5 empty] | 58715.621 |  | 39.72% |  | 58715.621 | 58715.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 50d | 58715.621 | 2617.9999 | 55d | 0 | 0 | 58715.621 | 2617.9999 | 47.62% | Started | 58715.621 | 58715.621 | 100 | 47.619 | 47.619 | 100 | 95.7315 | 47.619
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2009-01-04 17:00 |  | TP Name | 11
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 55d | [5 empty] | 58953.621 |  | 0.2759% |  | 58953.6212 | 58953.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 55d | [5 empty] | 58953.621 |  | 0.2759% |  | 58953.6212 | 58953.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 55d | [5 empty] | 58953.621 |  | 19.03% |  | 58953.6212 | 58953.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 55d | [5 empty] | 58953.621 |  | 39.89% |  | 58953.6212 | 58953.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 55d | 58953.621 | 2379.9999 | 50d | 0 | 0 | 58953.621 | 2379.9999 | 52.38% | Started | 58953.6212 | 58953.621 | 100 | 52.381 | 52.381 | 100 | 96.1196 | 52.381
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2009-01-11 17:00 |  | TP Name | 12
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 60d | [5 empty] | 59191.621 |  | 0.277% |  | 59191.6211 | 59191.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 60d | [5 empty] | 59191.621 |  | 0.277% |  | 59191.6211 | 59191.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 60d | [5 empty] | 59191.621 |  | 19.11% |  | 59191.6211 | 59191.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 60d | [5 empty] | 59191.621 |  | 40.05% |  | 59191.6211 | 59191.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 60d | 59191.621 | 2141.9999 | 45d | 0 | 0 | 59191.621 | 2141.9999 | 57.14% | Started | 59191.6211 | 59191.621 | 100 | 57.1429 | 57.1429 | 100 | 96.5076 | 57.1429
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2009-01-18 17:00 |  | TP Name | 13
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 65d | [5 empty] | 59429.621 |  | 0.2781% |  | 59429.6211 | 59429.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 65d | [5 empty] | 59429.621 |  | 0.2781% |  | 59429.6211 | 59429.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 65d | [5 empty] | 59429.621 |  | 19.18% |  | 59429.6211 | 59429.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 65d | [5 empty] | 59429.621 |  | 40.21% |  | 59429.6211 | 59429.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 65d | 59429.621 | 1903.9999 | 40d | 0 | 0 | 59429.621 | 1903.9999 | 61.9% | Started | 59429.6211 | 59429.621 | 100 | 61.9048 | 61.9048 | 100 | 96.8957 | 61.9048
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2009-01-25 17:00 |  | TP Name | 14
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 70d | [5 empty] | 59667.621 |  | 0.2792% |  | 59667.6211 | 59667.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 70d | [5 empty] | 59667.621 |  | 0.2792% |  | 59667.6211 | 59667.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 70d | [5 empty] | 59667.621 |  | 19.26% |  | 59667.6211 | 59667.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 70d | [5 empty] | 59667.621 |  | 40.37% |  | 59667.6211 | 59667.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 70d | 59667.621 | 1665.9999 | 35d | 0 | 0 | 59667.621 | 1665.9999 | 66.67% | Started | 59667.6211 | 59667.621 | 100 | 66.6667 | 66.6667 | 100 | 97.2837 | 66.6667
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2009-02-01 17:00 |  | TP Name | 15
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 75d | [5 empty] | 59905.621 |  | 0.2803% |  | 59905.6211 | 59905.621
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 75d | [5 empty] | 59905.621 |  | 0.2803% |  | 59905.6211 | 59905.621
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 75d | [5 empty] | 59905.621 |  | 19.34% |  | 59905.6211 | 59905.621
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 |  | 0 | 0 | 6365.2998 | 10d | 0 | 0 | 0 | 6365.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 75d | [5 empty] | 59905.621 |  | 40.53% |  | 59905.6211 | 59905.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 75d | 59905.621 | 1428 | 30d | 0 | 0 | 59905.621 | 1428 | 71.43% | Started | 59905.6211 | 59905.621 | 100 | 71.4286 | 71.4286 | 100 | 97.6718 | 71.4286
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2009-02-08 17:00 |  | TP Name | 16
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 80d | [5 empty] | 65708.9208 |  | 0.3075% |  | 65708.9209 | 65708.9208
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 80d | [5 empty] | 65708.9208 |  | 0.3075% |  | 65708.9209 | 65708.9208
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 80d | [5 empty] | 65708.9208 |  | 21.21% |  | 65708.9209 | 65708.9208
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 2d | [5 empty] | 5565.2998 |  | 18.31% |  | 5565.2998 | 5565.2998
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 2d | 5565.2998 | 800 | 8d | 0 | 0 | 5565.2998 | 800 | 20% | Started | 5565.2998 | 5565.2998 | 100 | 20 | 20 | 100 | 87.4319 | 20
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 80d | [5 empty] | 60143.621 |  | 40.69% |  | 60143.621 | 60143.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 80d | 60143.621 | 1190 | 25d | 0 | 0 | 60143.621 | 1190 | 76.19% | Started | 60143.621 | 60143.621 | 100 | 76.1905 | 76.1905 | 100 | 98.0598 | 76.1905
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2009-02-15 17:00 |  | TP Name | 17
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 85d | [5 empty] | 106926.451 |  | 0.4873% |  | 104129.5714 | 104129.5712
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 85d | [5 empty] | 106926.451 |  | 0.4873% |  | 104129.5714 | 104129.5712
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 85d | [5 empty] | 66446.9208 |  | 21.45% |  | 66446.9208 | 66446.9208
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 7d | [5 empty] | 6065.2998 |  | 19.96% |  | 6065.2998 | 6065.2998
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 7d | 6065.2998 | 300 | 3d | 0 | 0 | 6065.2998 | 300 | 70% | Started | 6065.2998 | 6065.2998 | 100 | 70 | 70 | 100 | 95.2869 | 70
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 |  | 0 | 0 | 15511.0999 | 14d | 0 | 0 | 0 | 15511.0999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 85d | [5 empty] | 60381.621 |  | 40.85% |  | 60381.621 | 60381.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 85d | 60381.621 | 952 | 20d | 0 | 0 | 60381.621 | 952 | 80.95% | Started | 60381.621 | 60381.621 | 100 | 80.9524 | 80.9524 | 100 | 98.4478 | 80.9524
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 2d | [5 empty] | 40479.5303 |  | 3.097% |  | 37682.6505 | 37682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 2d | 37682.6504 | 15000 | 3d | 2796.8799 | 0 | 40479.5303 | 15000 | 40% | Started | 37682.6505 | 37682.6504 | 100 | 40 | 40 | 100 | 76.8365 | 40
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2009-02-22 17:00 |  | TP Name | 18
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 90d | [5 empty] | 136685.421 |  | 0.6069% |  | 129693.2311 | 129693.2311
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 90d | [5 empty] | 136685.421 |  | 0.6069% |  | 129693.2311 | 129693.2311
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 90d | [5 empty] | 77010.5807 |  | 24.86% |  | 77010.5808 | 77010.5807
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 12d | [5 empty] | 16390.9597 |  | 53.94% |  | 16390.9598 | 16390.9597
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 2d | 10025.6599 | 5485.4399 | 12d | 0 | 0 | 10025.6599 | 5485.4399 | 14.29% | Started | 10025.66 | 10025.6599 | 100 | 14.2857 | 14.2857 | 100 | 64.6354 | 14.2857
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 90d | [5 empty] | 60619.621 |  | 41.01% |  | 60619.621 | 60619.621
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 90d | 60619.621 | 714 | 15d | 0 | 0 | 60619.621 | 714 | 85.71% | Started | 60619.621 | 60619.621 | 100 | 85.7143 | 85.7143 | 100 | 98.8359 | 85.7143
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 7d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2009-03-01 17:00 |  | TP Name | 19
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 95d | [5 empty] | 139209.021 |  | 0.6187% |  | 132216.8311 | 132216.831
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 95d | [5 empty] | 139209.021 |  | 0.6187% |  | 132216.8311 | 132216.831
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 95d | [5 empty] | 79534.1806 |  | 25.67% |  | 79534.1807 | 79534.1806
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 17d | [5 empty] | 18676.5597 |  | 61.46% |  | 18676.5597 | 18676.5597
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 7d | 12311.2599 | 3199.84 | 7d | 0 | 0 | 12311.2599 | 3199.84 | 50% | Started | 12311.2599 | 12311.2599 | 100 | 50 | 50 | 100 | 79.3706 | 50
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 95d | [5 empty] | 60857.6209 |  | 41.17% |  | 60857.621 | 60857.6209
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 95d | 60857.6209 | 476 | 10d | 0 | 0 | 60857.6209 | 476 | 90.48% | Started | 60857.621 | 60857.6209 | 100 | 90.4762 | 90.4762 | 100 | 99.2239 | 90.4762
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 12d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2009-03-08 17:00 |  | TP Name | 20
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 100d | [5 empty] | 151815.5609 |  | 0.6777% |  | 144823.3711 | 144823.3709
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 100d | [5 empty] | 151815.5609 |  | 0.6777% |  | 144823.3711 | 144823.3709
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 100d | [5 empty] | 92140.7206 |  | 29.74% |  | 92140.7207 | 92140.7206
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 22d | [5 empty] | 20962.1597 |  | 68.98% |  | 20962.1597 | 20962.1597
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 12d | 14596.8599 | 914.24 | 2d | 0 | 0 | 14596.8599 | 914.24 | 85.71% | Started | 14596.8599 | 14596.8599 | 100 | 85.7143 | 85.7143 | 100 | 94.1059 | 85.7143
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 |  | 0 | 0 | 8511.58 | 14d | 0 | 0 | 0 | 8511.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 100d | [5 empty] | 61095.6209 |  | 41.33% |  | 61095.621 | 61095.6209
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 100d | 61095.6209 | 238 | 5d | 0 | 0 | 61095.6209 | 238 | 95.24% | Started | 61095.621 | 61095.6209 | 100 | 95.2381 | 95.2381 | 100 | 99.612 | 95.2381
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 4d | [5 empty] | 10082.9399 |  | 7.662% |  | 10082.9401 | 10082.9399
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 4d | 10082.9399 | 6428.8 | 10d | 0 | 0 | 10082.9399 | 6428.8 | 28.57% | Started | 10082.9401 | 10082.9399 | 100 | 28.5714 | 28.5714 | 100 | 61.0653 | 28.5714
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 17d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2009-03-15 17:00 |  | TP Name | 21
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 105d | [5 empty] | 163907.9408 |  | 0.7343% |  | 156915.7508 | 156915.7509
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 105d | [5 empty] | 163907.9408 |  | 0.7343% |  | 156915.7508 | 156915.7509
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 105d | [5 empty] | 104233.1005 |  | 33.65% |  | 104233.1004 | 104233.1005
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 27d | [5 empty] | 29602.1396 |  | 97.41% |  | 29602.1396 | 29602.1396
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 3d | 7725.7399 | 785.84 | 11d | 0 | 0 | 7725.7399 | 785.84 | 21.43% | Started | 7725.7399 | 7725.7399 | 100 | 21.4286 | 21.4286 | 100 | 90.7674 | 21.4286
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 105d | [5 empty] | 61333.6209 |  | 41.5% |  | 61333.6209 | 61333.6209
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 |  | 0 | 0 | 53284.4719 | 90d | 0 | 0 | 0 | 53284.4719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 9d | [5 empty] | 13297.34 |  | 10.1% |  | 13297.3399 | 13297.34
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 |  | 0 | 0 | 16511.74 | 14d | 0 | 0 | 0 | 16511.74 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 9d | 13297.34 | 3214.4 | 5d | 0 | 0 | 13297.34 | 3214.4 | 64.29% | Started | 13297.3399 | 13297.34 | 100 | 64.2857 | 64.2857 | 100 | 80.5326 | 64.2857
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 22d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2009-03-22 17:00 |  | TP Name | 22
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 110d | [5 empty] | 226770.6327 |  | 1.029% |  | 219838.4644 | 219778.4427
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 110d | [5 empty] | 226770.6327 |  | 1.029% |  | 219838.4644 | 219778.4427
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 110d | [5 empty] | 167095.7923 |  | 53.96% |  | 167155.8141 | 167095.7923
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 32d | [5 empty] | 29959.3396 |  | 98.59% |  | 29959.3396 | 29959.3396
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 8d | 8082.9399 | 428.64 | 6d | 0 | 0 | 8082.9399 | 428.64 | 57.14% | Started | 8082.94 | 8082.9399 | 100 | 57.1429 | 57.1429 | 100 | 94.964 | 57.1429
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 110d | [5 empty] | 109898.8928 |  | 74.39% |  | 109958.9144 | 109898.8928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 5d | 48565.2719 | 3830.88 | 69d | 0 | 0 | 48565.2719 | 3830.88 | 6.757% | Started | 48625.2935 | 48565.2719 | 100 | 5.5556 | 6.7568 | 100 | 91.1434 | 6.7568
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 14d | [5 empty] | 27237.5599 |  | 20.7% |  | 27237.56 | 27237.5599
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 5d | 10725.8199 | 5785.92 | 9d | 0 | 0 | 10725.8199 | 5785.92 | 35.71% | Started | 10725.82 | 10725.8199 | 100 | 35.7143 | 35.7143 | 100 | 64.9588 | 35.7143
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 27d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2009-03-29 17:00 |  | TP Name | 23
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 115d | [5 empty] | 230619.8327 |  | 1.047% |  | 223747.6861 | 322202.9865
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 115d | [5 empty] | 230619.8327 |  | 1.047% |  | 223747.6861 | 322202.9865
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 115d | [5 empty] | 170944.9924 |  | 55.22% |  | 171065.0357 | 269520.3361
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 37d | [5 empty] | 30316.5396 |  | 99.76% |  | 30316.5396 | 30316.5396
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 13d | 8440.14 | 71.44 | 1d | 0 | 0 | 8440.14 | 71.44 | 92.86% | Started | 8440.1399 | 8440.14 | 100 | 92.8571 | 92.8571 | 100 | 99.1607 | 92.8571
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 115d | [5 empty] | 110176.4928 |  | 74.62% |  | 110296.536 | 110176.4928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 10d | 48842.8719 | 3553.28 | 64d | 0 | 0 | 48842.8719 | 3553.28 | 13.51% | Started | 48962.9151 | 48842.8719 | 100 | 11.1111 | 13.5135 | 100 | 91.6644 | 13.5135
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 19d | [5 empty] | 30451.96 |  | 23.14% |  | 30451.9601 | 129027.3037
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 10d | 13940.22 | 2571.52 | 4d | 0 | 0 | 13940.22 | 2571.52 | 71.43% | Started | 13940.2201 | 13940.22 | 100 | 71.4286 | 71.4286 | 100 | 84.4261 | 71.4286
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 32d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2009-04-05 17:00 |  | TP Name | 24
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 120d | [5 empty] | 233540.3927 |  | 1.061% |  | 226728.2677 | 325123.5466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 120d | [5 empty] | 233540.3927 |  | 1.061% |  | 226728.2677 | 325123.5466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 120d | [5 empty] | 173865.5524 |  | 56.18% |  | 174045.6173 | 272440.8962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 120d | [5 empty] | 110454.0928 |  | 74.85% |  | 110634.1577 | 110454.0928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 15d | 49120.4719 | 3275.68 | 59d | 0 | 0 | 49120.4719 | 3275.68 | 20.27% | Started | 49300.5367 | 49120.4719 | 100 | 16.6667 | 20.2703 | 100 | 92.1853 | 20.2703
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 24d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 37d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2009-04-12 17:00 |  | TP Name | 25
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 125d | [5 empty] | 233817.9927 |  | 1.063% |  | 227065.8892 | 325401.1466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 125d | [5 empty] | 233817.9927 |  | 1.063% |  | 227065.8892 | 325401.1466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 125d | [5 empty] | 174143.1524 |  | 56.29% |  | 174383.2388 | 272718.4962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 125d | [5 empty] | 110731.6928 |  | 75.08% |  | 110971.7792 | 110731.6928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 20d | 49398.0719 | 2998.08 | 54d | 0 | 0 | 49398.0719 | 2998.08 | 27.03% | Started | 49638.1583 | 49398.0719 | 100 | 22.2222 | 27.027 | 100 | 92.7063 | 27.027
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 29d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 42d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2009-04-19 17:00 |  | TP Name | 26
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 130d | [5 empty] | 234095.5927 |  | 1.064% |  | 227403.511 | 325678.7466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 130d | [5 empty] | 234095.5927 |  | 1.064% |  | 227403.511 | 325678.7466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 130d | [5 empty] | 174420.7524 |  | 56.4% |  | 174720.8606 | 272996.0962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 130d | [5 empty] | 111009.2928 |  | 75.31% |  | 111309.401 | 111009.2928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 25d | 49675.6719 | 2720.48 | 49d | 0 | 0 | 49675.6719 | 2720.48 | 33.78% | Started | 49975.78 | 49675.6719 | 100 | 27.7778 | 33.7838 | 100 | 93.2273 | 33.7838
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 34d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 47d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2009-04-26 17:00 |  | TP Name | 27
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 135d | [5 empty] | 234373.1927 |  | 1.066% |  | 227741.1325 | 325956.3466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 135d | [5 empty] | 234373.1927 |  | 1.066% |  | 227741.1325 | 325956.3466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 135d | [5 empty] | 174698.3524 |  | 56.51% |  | 175058.4821 | 273273.6962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 135d | [5 empty] | 111286.8928 |  | 75.54% |  | 111647.0225 | 111286.8928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 30d | 49953.2719 | 2442.88 | 44d | 0 | 0 | 49953.2719 | 2442.88 | 40.54% | Started | 50313.4016 | 49953.2719 | 100 | 33.3333 | 40.5405 | 100 | 93.7483 | 40.5405
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 39d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 52d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2009-05-03 17:00 |  | TP Name | 28
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 140d | [5 empty] | 234650.7928 |  | 1.067% |  | 228078.7541 | 326233.9466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 140d | [5 empty] | 234650.7928 |  | 1.067% |  | 228078.7541 | 326233.9466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 140d | [5 empty] | 174975.9524 |  | 56.62% |  | 175396.1037 | 273551.2962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 140d | [5 empty] | 111564.4928 |  | 75.76% |  | 111984.6441 | 111564.4928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 35d | 50230.8719 | 2165.28 | 39d | 0 | 0 | 50230.8719 | 2165.28 | 47.3% | Started | 50651.0232 | 50230.8719 | 100 | 38.8889 | 47.2973 | 100 | 94.2692 | 47.2973
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 44d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 57d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2009-05-10 17:00 |  | TP Name | 29
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 145d | [5 empty] | 234928.3928 |  | 1.069% |  | 228416.3757 | 326511.5466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 145d | [5 empty] | 234928.3928 |  | 1.069% |  | 228416.3757 | 326511.5466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 145d | [5 empty] | 175253.5524 |  | 56.73% |  | 175733.7253 | 273828.8962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 145d | [5 empty] | 111842.0928 |  | 75.99% |  | 112322.2657 | 111842.0928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 40d | 50508.4719 | 1887.68 | 34d | 0 | 0 | 50508.4719 | 1887.68 | 54.05% | Started | 50988.6447 | 50508.4719 | 100 | 44.4444 | 54.0541 | 100 | 94.7902 | 54.0541
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 49d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 62d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP30
| TP Status Date | 2009-05-17 17:00 |  | TP Name | 30
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 150d | [5 empty] | 235205.9928 |  | 1.07% |  | 228753.9974 | 326789.1466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 150d | [5 empty] | 235205.9928 |  | 1.07% |  | 228753.9974 | 326789.1466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 150d | [5 empty] | 175531.1524 |  | 56.83% |  | 176071.347 | 274106.4962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 150d | [5 empty] | 112119.6928 |  | 76.22% |  | 112659.8874 | 112119.6928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 45d | 50786.0719 | 1610.08 | 29d | 0 | 0 | 50786.0719 | 1610.08 | 60.81% | Started | 51326.2665 | 50786.0719 | 100 | 50 | 60.8108 | 100 | 95.3112 | 60.8108
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 54d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 67d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP31
| TP Status Date | 2009-05-24 17:00 |  | TP Name | 31
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 155d | [5 empty] | 235483.5928 |  | 1.072% |  | 229091.6191 | 327066.7466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 155d | [5 empty] | 235483.5928 |  | 1.072% |  | 229091.6191 | 327066.7466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 155d | [5 empty] | 175808.7524 |  | 56.94% |  | 176408.9687 | 274384.0962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 155d | [5 empty] | 112397.2928 |  | 76.45% |  | 112997.5091 | 112397.2928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 50d | 51063.6719 | 1332.48 | 24d | 0 | 0 | 51063.6719 | 1332.48 | 67.57% | Started | 51663.8882 | 51063.6719 | 100 | 55.5556 | 67.5676 | 100 | 95.8322 | 67.5676
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 59d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 72d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP32
| TP Status Date | 2009-05-31 17:00 |  | TP Name | 32
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 160d | [5 empty] | 235761.1928 |  | 1.074% |  | 229429.2405 | 327344.3466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 160d | [5 empty] | 235761.1928 |  | 1.074% |  | 229429.2405 | 327344.3466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 160d | [5 empty] | 176086.3524 |  | 57.05% |  | 176746.5901 | 274661.6962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 160d | [5 empty] | 112674.8928 |  | 76.68% |  | 113335.1305 | 112674.8928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 55d | 51341.2719 | 1054.88 | 19d | 0 | 0 | 51341.2719 | 1054.88 | 74.32% | Started | 52001.5096 | 51341.2719 | 100 | 61.1111 | 74.3243 | 100 | 96.3532 | 74.3243
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 64d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 77d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP33
| TP Status Date | 2009-06-07 17:00 |  | TP Name | 33
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 165d | [5 empty] | 236038.7928 |  | 1.075% |  | 229766.8623 | 327621.9466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 165d | [5 empty] | 236038.7928 |  | 1.075% |  | 229766.8623 | 327621.9466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 165d | [5 empty] | 176363.9524 |  | 57.16% |  | 177084.2119 | 274939.2962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 165d | [5 empty] | 112952.4928 |  | 76.91% |  | 113672.7523 | 112952.4928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 60d | 51618.8719 | 777.28 | 14d | 0 | 0 | 51618.8719 | 777.28 | 81.08% | Started | 52339.1313 | 51618.8719 | 100 | 66.6667 | 81.0811 | 100 | 96.8741 | 81.0811
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 69d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 82d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP34
| TP Status Date | 2009-06-14 17:00 |  | TP Name | 34
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 170d | [5 empty] | 236316.3928 |  | 1.077% |  | 230104.484 | 327899.5466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 170d | [5 empty] | 236316.3928 |  | 1.077% |  | 230104.484 | 327899.5466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 170d | [5 empty] | 176641.5524 |  | 57.27% |  | 177421.8336 | 275216.8962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 170d | [5 empty] | 113230.0928 |  | 77.13% |  | 114010.374 | 113230.0928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 65d | 51896.4719 | 499.68 | 9d | 0 | 0 | 51896.4719 | 499.68 | 87.84% | Started | 52676.7531 | 51896.4719 | 100 | 72.2222 | 87.8378 | 100 | 97.3951 | 87.8378
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 74d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 87d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP35
| TP Status Date | 2009-06-21 17:00 |  | TP Name | 35
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 175d | [5 empty] | 236593.9928 |  | 1.078% |  | 230442.1054 | 328177.1466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 175d | [5 empty] | 236593.9928 |  | 1.078% |  | 230442.1054 | 328177.1466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 175d | [5 empty] | 176919.1524 |  | 57.38% |  | 177759.455 | 275494.4962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 175d | [5 empty] | 113507.6928 |  | 77.36% |  | 114347.9954 | 113507.6928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 70d | 52174.0719 | 222.08 | 4d | 0 | 0 | 52174.0719 | 222.08 | 94.59% | Started | 53014.3745 | 52174.0719 | 100 | 77.7778 | 94.5946 | 100 | 97.9161 | 94.5946
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 |  | 0 | 0 | 33190.1793 | 60d | 0 | 0 | 0 | 33190.1793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 79d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 92d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP36
| TP Status Date | 2009-06-28 17:00 |  | TP Name | 36
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 180d | [5 empty] | 269024.4921 |  | 1.23% |  | 262920.6221 | 328454.7466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 180d | [5 empty] | 269024.4921 |  | 1.23% |  | 262920.6221 | 328454.7466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 180d | [5 empty] | 209349.6517 |  | 67.86% |  | 210237.9717 | 275772.0962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 180d | [5 empty] | 145938.1921 |  | 99.34% |  | 146826.5121 | 113785.2928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 52451.6719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 1d | 32208.4193 | 981.76 | 59d | 0 | 0 | 32208.4193 | 981.76 | 1.667% | Started | 32208.4193 | 0 | 100 | 1.6667 | 1.6667 | 100 | 97.042 | 1.6667
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 84d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 97d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP37
| TP Status Date | 2009-07-05 17:00 |  | TP Name | 37
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 185d | [5 empty] | 269107.6921 |  | 1.231% |  | 263003.8221 | 328732.3466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 185d | [5 empty] | 269107.6921 |  | 1.231% |  | 263003.8221 | 328732.3466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 185d | [5 empty] | 209432.8517 |  | 67.89% |  | 210321.1717 | 276049.6962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 185d | [5 empty] | 146021.3921 |  | 99.39% |  | 146909.7121 | 114062.8928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 52729.2719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 6d | 32291.6193 | 898.56 | 54d | 0 | 0 | 32291.6193 | 898.56 | 10% | Started | 32291.6193 | 0 | 100 | 10 | 10 | 100 | 97.2927 | 10
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 89d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 102d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP38
| TP Status Date | 2009-07-12 17:00 |  | TP Name | 38
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 190d | [5 empty] | 269190.8921 |  | 1.231% |  | 263087.0221 | 329009.9466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 190d | [5 empty] | 269190.8921 |  | 1.231% |  | 263087.0221 | 329009.9466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 190d | [5 empty] | 209516.0517 |  | 67.92% |  | 210404.3717 | 276327.2962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 190d | [5 empty] | 146104.5921 |  | 99.45% |  | 146992.9121 | 114340.4928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53006.8719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 11d | 32374.8193 | 815.36 | 49d | 0 | 0 | 32374.8193 | 815.36 | 18.33% | Started | 32374.8193 | 0 | 100 | 18.3333 | 18.3333 | 100 | 97.5434 | 18.3333
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 94d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 107d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP39
| TP Status Date | 2009-07-19 17:00 |  | TP Name | 39
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 195d | [5 empty] | 269274.0921 |  | 1.232% |  | 263170.2221 | 329287.5466
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 195d | [5 empty] | 269274.0921 |  | 1.232% |  | 263170.2221 | 329287.5466
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 195d | [5 empty] | 209599.2517 |  | 67.94% |  | 210487.5717 | 276604.8962
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 195d | [5 empty] | 146187.7921 |  | 99.5% |  | 147076.1122 | 114618.0928
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 16d | 32458.0193 | 732.16 | 44d | 0 | 0 | 32458.0193 | 732.16 | 26.67% | Started | 32458.0193 | 0 | 100 | 26.6667 | 26.6667 | 100 | 97.794 | 26.6667
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 99d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 112d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP40
| TP Status Date | 2009-07-26 17:00 |  | TP Name | 40
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 200d | [5 empty] | 269357.2921 |  | 1.232% |  | 263253.4221 | 361562.5259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 200d | [5 empty] | 269357.2921 |  | 1.232% |  | 263253.4221 | 361562.5259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 200d | [5 empty] | 209682.4517 |  | 67.97% |  | 210570.7717 | 308879.8755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 200d | [5 empty] | 146270.9921 |  | 99.56% |  | 147159.3121 | 146893.0721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 21d | 32541.2193 | 648.96 | 39d | 0 | 0 | 32541.2193 | 648.96 | 35% | Started | 32541.2193 | 32274.9793 | 100 | 35 | 35 | 100 | 98.0447 | 35
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 104d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 117d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP41
| TP Status Date | 2009-08-02 17:00 |  | TP Name | 41
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 205d | [5 empty] | 269440.4921 |  | 1.232% |  | 263336.6221 | 361645.7259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 205d | [5 empty] | 269440.4921 |  | 1.232% |  | 263336.6221 | 361645.7259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 205d | [5 empty] | 209765.6517 |  | 68% |  | 210653.9717 | 308963.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 205d | [5 empty] | 146354.1921 |  | 99.62% |  | 147242.5121 | 146976.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 26d | 32624.4193 | 565.76 | 34d | 0 | 0 | 32624.4193 | 565.76 | 43.33% | Started | 32624.4193 | 32358.1793 | 100 | 43.3333 | 43.3333 | 100 | 98.2954 | 43.3333
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 109d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 122d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP42
| TP Status Date | 2009-08-09 17:00 |  | TP Name | 42
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 210d | [5 empty] | 269523.692 |  | 1.233% |  | 263419.8221 | 361728.9259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 210d | [5 empty] | 269523.692 |  | 1.233% |  | 263419.8221 | 361728.9259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 210d | [5 empty] | 209848.8517 |  | 68.02% |  | 210737.1717 | 309046.2755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 210d | [5 empty] | 146437.3921 |  | 99.67% |  | 147325.7121 | 147059.4721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 31d | 32707.6193 | 482.56 | 29d | 0 | 0 | 32707.6193 | 482.56 | 51.67% | Started | 32707.6193 | 32441.3793 | 100 | 51.6667 | 51.6667 | 100 | 98.5461 | 51.6667
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 114d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 127d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP43
| TP Status Date | 2009-08-16 17:00 |  | TP Name | 43
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 215d | [5 empty] | 269606.892 |  | 1.233% |  | 263503.0221 | 361812.1259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 215d | [5 empty] | 269606.892 |  | 1.233% |  | 263503.0221 | 361812.1259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 215d | [5 empty] | 209932.0517 |  | 68.05% |  | 210820.3717 | 309129.4755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 215d | [5 empty] | 146520.5921 |  | 99.73% |  | 147408.9121 | 147142.6721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 36d | 32790.8193 | 399.36 | 24d | 0 | 0 | 32790.8193 | 399.36 | 60% | Started | 32790.8193 | 32524.5793 | 100 | 60 | 60 | 100 | 98.7968 | 60
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 119d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 132d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP44
| TP Status Date | 2009-08-23 17:00 |  | TP Name | 44
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 220d | [5 empty] | 269690.092 |  | 1.233% |  | 263586.2221 | 361895.3259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 220d | [5 empty] | 269690.092 |  | 1.233% |  | 263586.2221 | 361895.3259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 220d | [5 empty] | 210015.2517 |  | 68.08% |  | 210903.5717 | 309212.6755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 220d | [5 empty] | 146603.7921 |  | 99.79% |  | 147492.1121 | 147225.8721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 41d | 32874.0193 | 316.16 | 19d | 0 | 0 | 32874.0193 | 316.16 | 68.33% | Started | 32874.0193 | 32607.7793 | 100 | 68.3333 | 68.3333 | 100 | 99.0474 | 68.3333
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 124d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 137d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP45
| TP Status Date | 2009-08-30 17:00 |  | TP Name | 45
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 225d | [5 empty] | 269773.292 |  | 1.234% |  | 263669.4221 | 361978.5259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 225d | [5 empty] | 269773.292 |  | 1.234% |  | 263669.4221 | 361978.5259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 225d | [5 empty] | 210098.4517 |  | 68.11% |  | 210986.7717 | 309295.8755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 225d | [5 empty] | 146686.9921 |  | 99.84% |  | 147575.3121 | 147309.0721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 46d | 32957.2193 | 232.96 | 14d | 0 | 0 | 32957.2193 | 232.96 | 76.67% | Started | 32957.2193 | 32690.9793 | 100 | 76.6667 | 76.6667 | 100 | 99.2981 | 76.6667
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 129d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 142d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP46
| TP Status Date | 2009-09-06 17:00 |  | TP Name | 46
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 230d | [5 empty] | 269856.492 |  | 1.234% |  | 263752.6221 | 362061.7259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 230d | [5 empty] | 269856.492 |  | 1.234% |  | 263752.6221 | 362061.7259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 230d | [5 empty] | 210181.6517 |  | 68.13% |  | 211069.9717 | 309379.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 230d | [5 empty] | 146770.1921 |  | 99.9% |  | 147658.5121 | 147392.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 51d | 33040.4193 | 149.76 | 9d | 0 | 0 | 33040.4193 | 149.76 | 85% | Started | 33040.4193 | 32774.1793 | 100 | 85 | 85 | 100 | 99.5488 | 85
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 134d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 147d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP47
| TP Status Date | 2009-09-13 17:00 |  | TP Name | 47
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 235d | [5 empty] | 269939.692 |  | 1.235% |  | 263835.8221 | 362144.9259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 235d | [5 empty] | 269939.692 |  | 1.235% |  | 263835.8221 | 362144.9259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 235d | [5 empty] | 210264.8517 |  | 68.16% |  | 211153.1717 | 309462.2755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 235d | [5 empty] | 146853.3921 |  | 99.95% |  | 147741.7121 | 147475.4721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 56d | 33123.6193 | 66.56 | 4d | 0 | 0 | 33123.6193 | 66.56 | 93.33% | Started | 33123.6193 | 32857.3793 | 100 | 93.3333 | 93.3333 | 100 | 99.7995 | 93.3333
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 139d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 152d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP48
| TP Status Date | 2009-09-20 17:00 |  | TP Name | 48
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 240d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362228.1259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 240d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362228.1259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 240d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309545.4755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147558.6721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 32940.5793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 144d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 157d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP49
| TP Status Date | 2009-09-27 17:00 |  | TP Name | 49
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 245d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362311.3259
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 245d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362311.3259
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 245d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309628.6755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147641.8721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33023.7793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 149d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 162d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP50
| TP Status Date | 2009-10-04 17:00 |  | TP Name | 50
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 250d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362394.5258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 250d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362394.5258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 250d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309711.8755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147725.0721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33106.9793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 154d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 167d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP51
| TP Status Date | 2009-10-11 17:00 |  | TP Name | 51
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 255d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 255d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 255d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 159d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 172d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP52
| TP Status Date | 2009-10-18 17:00 |  | TP Name | 52
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 260d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 260d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 260d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 164d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 177d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP53
| TP Status Date | 2009-10-25 17:00 |  | TP Name | 53
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 265d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 265d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 265d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 169d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 182d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP54
| TP Status Date | 2009-11-01 17:00 |  | TP Name | 54
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 270d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 270d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 270d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 174d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 187d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP55
| TP Status Date | 2009-11-08 17:00 |  | TP Name | 55
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 275d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 275d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 275d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 179d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 192d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP56
| TP Status Date | 2009-11-15 17:00 |  | TP Name | 56
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 280d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 280d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 280d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 184d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 197d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP57
| TP Status Date | 2009-11-22 17:00 |  | TP Name | 57
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 285d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 285d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 285d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 189d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 202d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP58
| TP Status Date | 2009-11-29 17:00 |  | TP Name | 58
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 290d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 290d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 290d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 194d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 207d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP59
| TP Status Date | 2009-12-06 17:00 |  | TP Name | 59
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 295d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 295d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 295d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 199d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 212d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP60
| TP Status Date | 2009-12-13 17:00 |  | TP Name | 60
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 300d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 300d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 300d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 204d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 217d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP61
| TP Status Date | 2009-12-20 17:00 |  | TP Name | 61
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 305d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 305d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 305d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 209d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 222d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP62
| TP Status Date | 2009-12-27 17:00 |  | TP Name | 62
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 310d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 310d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 362477.7258
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 310d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 214d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 227d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 52682.6504
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP63
| TP Status Date | 2010-01-03 17:00 |  | TP Name | 63
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 315d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 395160.3762
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 315d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 395160.3762
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 315d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 219d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 232d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 85365.3008
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 32682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP64
| TP Status Date | 2010-01-10 17:00 |  | TP Name | 64
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 320d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 594374.6809
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 320d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 594374.6809
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 320d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 224d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 237d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 284579.6055
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 179214.3047 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 52682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP65
| TP Status Date | 2010-01-17 17:00 |  | TP Name | 65
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 325d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 952889.095
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 325d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 952889.095
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 325d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 229d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 242d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 643094.0195
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 537728.7188 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 52682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP66
| TP Status Date | 2010-01-24 17:00 |  | TP Name | 66
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 330d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 1311403.509
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 330d | [5 empty] | 270006.252 |  | 1.235% |  | 263902.3821 | 1311403.509
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 330d | [5 empty] | 210331.4117 |  | 68.18% |  | 211219.7317 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 234d | [5 empty] | 33023.48 |  | 25.09% |  | 33023.48 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 |  | 0 | 0 | 98575.3438 | 180d | 0 | 0 | 0 | 98575.3438 | 0% | Not Started | 0 | 98575.3438 | 100 |  | 0 | 100 |  | 0
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 247d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 1001608.4336
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 896243.1328 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 52682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 |  | 0 | 0 | 295627.5957 | 40d | 0 | 0 | 0 | 295627.5957 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP67
| TP Status Date | 2010-01-31 17:00 |  | TP Name | 67
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 335d | [5 empty] | 396896.9454 |  | 1.829% |  | 390793.0756 | 1557510.157
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 335d | [5 empty] | 396896.9454 |  | 1.829% |  | 390793.0756 | 1557510.157
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 335d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 239d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 1d | 98575.3438 | 0 | 64d | 0 | 0 | 98575.3438 | 0 | 1.538% | Started | 98575.3438 | 98575.3438 | 100 | 0.55556 | 1.5385 | 100 | 100 | 1.5385
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 252d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 1111351.7812 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 52682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2682.6499
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 2682.6499 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 1d | [5 empty] | 28315.3496 |  | 3.282% |  | 28315.3497 | 28315.3496
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 1d | [5 empty] | 28315.3496 |  | 3.282% |  | 28315.3497 | 28315.3496
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 1d | 28315.3496 | 267312.2461 | 39d | 0 | 0 | 28315.3496 | 267312.2461 | 2.5% | Started | 28315.3497 | 28315.3496 | 100 | 2.5 | 2.5 | 100 | 9.578 | 2.5
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP68
| TP Status Date | 2010-02-07 17:00 |  | TP Name | 68
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 340d | [5 empty] | 431167.7462 |  | 1.989% |  | 425063.8779 | 1634164.159
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 340d | [5 empty] | 431167.7462 |  | 1.989% |  | 425063.8779 | 1634164.159
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 340d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 244d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 6d | 98575.3438 | 0 | 59d | 0 | 0 | 98575.3438 | 0 | 9.231% | Started | 98575.3438 | 98575.3438 | 100 | 3.3333 | 9.2308 | 100 | 100 | 9.2308
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 257d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 1111351.7812 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 52682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 45065.8511
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 2682.6499 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 42383.2012
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 42383.2012 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 6d | [5 empty] | 62586.1504 |  | 7.254% |  | 62586.152 | 62586.1504
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 6d | [5 empty] | 62586.1504 |  | 7.254% |  | 62586.152 | 62586.1504
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 6d | 62586.1504 | 233041.4453 | 34d | 0 | 0 | 62586.1504 | 233041.4453 | 15% | Started | 62586.152 | 62586.1504 | 100 | 15 | 15 | 100 | 21.1706 | 15
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP69
| TP Status Date | 2010-02-14 17:00 |  | TP Name | 69
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 345d | [5 empty] | 465438.547 |  | 2.149% |  | 459334.6787 | 1776698.3015
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 345d | [5 empty] | 465438.547 |  | 2.149% |  | 459334.6787 | 1776698.3015
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 345d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 249d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 11d | 98575.3438 | 0 | 54d | 0 | 0 | 98575.3438 | 0 | 16.92% | Started | 98575.3438 | 98575.3438 | 100 | 6.1111 | 16.9231 | 100 | 100 | 16.9231
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 262d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 1111351.7812 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 52682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 153329.1929
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 2682.6499 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 72597.5225
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 78049.0205
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 78049.0205 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 11d | [5 empty] | 96856.9512 |  | 11.23% |  | 96856.9528 | 96856.9512
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 11d | [5 empty] | 96856.9512 |  | 11.23% |  | 96856.9528 | 96856.9512
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 11d | 96856.9512 | 198770.6445 | 29d | 0 | 0 | 96856.9512 | 198770.6445 | 27.5% | Started | 96856.9528 | 96856.9512 | 100 | 27.5 | 27.5 | 100 | 32.7632 | 27.5
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP70
| TP Status Date | 2010-02-21 17:00 |  | TP Name | 70
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 350d | [5 empty] | 499709.3477 |  | 2.31% |  | 493605.4794 | 1880209.5032
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 350d | [5 empty] | 499709.3477 |  | 2.31% |  | 493605.4794 | 1880209.5032
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 350d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 254d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 16d | 98575.3438 | 0 | 49d | 0 | 0 | 98575.3438 | 0 | 24.62% | Started | 98575.3438 | 98575.3438 | 100 | 8.8889 | 24.6154 | 100 | 100 | 24.6154
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 267d | [5 empty] | 59674.8403 |  | 4.33% |  | 52682.6504 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 1111351.7812 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 |  | 0 | 0 | 52682.6504 | 5d | 0 | 0 | 0 | 52682.6504 | 0% | Not Started | 0 | 52682.6504 | 100 |  | 0 | 100 |  | 0
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 222569.5938
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 2682.6499 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 114980.7236
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 42383.2012 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104906.2202
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 104906.2202 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 16d | [5 empty] | 131127.752 |  | 15.2% |  | 131127.7536 | 131127.752
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 16d | [5 empty] | 131127.752 |  | 15.2% |  | 131127.7536 | 131127.752
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 16d | 131127.752 | 164499.8438 | 24d | 0 | 0 | 131127.752 | 164499.8438 | 40% | Started | 131127.7536 | 131127.752 | 100 | 40 | 40 | 100 | 44.3557 | 40
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP71
| TP Status Date | 2010-02-28 17:00 |  | TP Name | 71
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 355d | [5 empty] | 593654.9888 |  | 2.717% |  | 580558.9224 | 2049600.8455
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 355d | [5 empty] | 593654.9888 |  | 2.717% |  | 580558.9224 | 2049600.8455
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 355d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 259d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 21d | 98575.3438 | 0 | 44d | 0 | 0 | 98575.3438 | 0 | 32.31% | Started | 98575.3438 | 98575.3438 | 100 | 11.6667 | 32.3077 | 100 | 100 | 32.3077
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 272d | [5 empty] | 119349.6807 |  | 8.66% |  | 105365.3008 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 |  | 0 | 0 | 1111351.7812 | 14d | 0 | 0 | 0 | 1111351.7812 | 0% | Not Started | 0 | 1111351.7812 | 100 |  | 0 | 100 |  | 0
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 357690.1353
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 2682.6499 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 145195.0449
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 209812.4404
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 131763.4199 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 78049.0205 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 21d | [5 empty] | 165398.5527 |  | 19.17% |  | 165398.5462 | 165398.5527
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 21d | [5 empty] | 165398.5527 |  | 19.17% |  | 165398.5462 | 165398.5527
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 21d | 165398.5527 | 130229.043 | 19d | 0 | 0 | 165398.5527 | 130229.043 | 52.5% | Started | 165398.5462 | 165398.5527 | 100 | 52.5 | 52.5 | 100 | 55.9483 | 52.5
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP72
| TP Status Date | 2010-03-07 17:00 |  | TP Name | 72
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 360d | [5 empty] | 1097116.0655 |  | 3.914% |  | 836413.9166 | 2169226.377
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 360d | [5 empty] | 1097116.0655 |  | 3.914% |  | 836413.9166 | 2169226.377
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 360d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 264d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 26d | 98575.3438 | 0 | 39d | 0 | 0 | 98575.3438 | 0 | 40% | Started | 98575.3438 | 98575.3438 | 100 | 14.4444 | 40 | 100 | 100 | 40
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 277d | [5 empty] | 588539.9565 |  | 26.87% |  | 326949.4942 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 5d | 466025.8359 | 2796412.4297 | 39d | 3164.4399 | 0 | 469190.2759 | 2796412.4297 | 11.36% | Started | 221584.1934 | 1111351.7812 | 100 | 35.7143 | 11.3636 | 100 | 42.218 | 11.3636
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 443044.866
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 |  | 0 | 0 | 2682.6499 | 5d | 0 | 0 | 0 | 2682.6499 | 0% | Not Started | 0 | 2682.6499 | 100 |  | 0 | 100 |  | 0
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 187578.2461
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 42383.2012 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 252783.96
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 104906.2202 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.01
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 26d | [5 empty] | 199669.3535 |  | 23.14% |  | 199669.347 | 199669.3535
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 26d | [5 empty] | 199669.3535 |  | 23.14% |  | 199669.347 | 199669.3535
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 26d | 199669.3535 | 95958.2422 | 14d | 0 | 0 | 199669.3535 | 95958.2422 | 65% | Started | 199669.347 | 199669.3535 | 100 | 65 | 65 | 100 | 67.5408 | 65
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP73
| TP Status Date | 2010-03-14 17:00 |  | TP Name | 73
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 365d | [5 empty] | 1495849.8004 |  | 4.621% |  | 987440.1388 | 2338617.7192
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 365d | [5 empty] | 1495849.8004 |  | 4.621% |  | 987440.1388 | 2338617.7192
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 365d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 269d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 31d | 98575.3438 | 0 | 34d | 0 | 0 | 98575.3438 | 0 | 47.69% | Started | 98575.3438 | 98575.3438 | 100 | 17.2222 | 47.6923 | 100 | 100 | 47.6923
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 282d | [5 empty] | 950218.8008 |  | 36.25% |  | 441022.2657 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 10d | 824540.25 | 2437898.0156 | 34d | 6328.8701 | 0 | 830869.1201 | 2437898.0156 | 22.73% | Started | 335656.9649 | 1111351.7812 | 100 | 71.4286 | 22.7273 | 100 | 74.762 | 22.7273
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 5d | [5 empty] | 2784.0899 |  | 0.1735% |  | 2682.6499 | 578165.4075
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 217792.5674
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 357690.1802
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 131763.4199 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 78049.0205 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.01
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 31d | [5 empty] | 233940.1543 |  | 27.12% |  | 233940.1478 | 233940.1543
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 31d | [5 empty] | 233940.1543 |  | 27.12% |  | 233940.1478 | 233940.1543
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 31d | 233940.1543 | 61687.4414 | 9d | 0 | 0 | 233940.1543 | 61687.4414 | 77.5% | Started | 233940.1478 | 233940.1543 | 100 | 77.5 | 77.5 | 100 | 79.1334 | 77.5
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP74
| TP Status Date | 2010-03-21 17:00 |  | TP Name | 74
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 370d | [5 empty] | 1967142.2472 |  | 5.655% |  | 1208381.2261 | 2458243.2507
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 370d | [5 empty] | 1967142.2472 |  | 5.655% |  | 1208381.2261 | 2458243.2507
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 370d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 274d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 36d | 98575.3438 | 0 | 29d | 0 | 0 | 98575.3438 | 0 | 55.38% | Started | 98575.3438 | 98575.3438 | 100 | 20 | 55.3846 | 100 | 100 | 55.3846
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 287d | [5 empty] | 1311897.6543 |  | 45.62% |  | 555095.0297 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 15d | 1183054.6641 | 2079383.6016 | 29d | 9493.3096 | 0 | 1192547.9736 | 2079383.6016 | 34.09% | Started | 449729.7289 | 1111351.7812 | 100 | 107.1429 | 34.0909 | 100 | 107.3061 | 34.0909
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 10d | [5 empty] | 78126.8824 |  | 4.869% |  | 75280.1724 | 663520.1382
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 5d | [5 empty] | 75342.7925 |  | 14.29% |  | 72597.5225 | 260175.7686
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 42383.2012 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 400661.6997
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 104906.2202 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.02
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 36d | [5 empty] | 268210.9551 |  | 31.09% |  | 268210.9485 | 268210.9551
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 36d | [5 empty] | 268210.9551 |  | 31.09% |  | 268210.9485 | 268210.9551
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 36d | 268210.9551 | 27416.6406 | 4d | 0 | 0 | 268210.9551 | 27416.6406 | 90% | Started | 268210.9485 | 268210.9551 | 100 | 90 | 90 | 100 | 90.726 | 90
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP75
| TP Status Date | 2010-03-28 17:00 |  | TP Name | 75
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 375d | [5 empty] | 2431580.525 |  | 6.656% |  | 1422468.1747 | 2645219.343
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 375d | [5 empty] | 2431580.525 |  | 6.656% |  | 1422468.1747 | 2645219.343
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 375d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 279d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 41d | 98575.3438 | 0 | 24d | 0 | 0 | 98575.3438 | 0 | 63.08% | Started | 98575.3438 | 98575.3438 | 100 | 22.7778 | 63.0769 | 100 | 100 | 63.0769
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 292d | [5 empty] | 1673576.499 |  | 55% |  | 669167.8087 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 20d | 1541569.0781 | 1720869.1875 | 24d | 12657.7402 | 0 | 1554226.8184 | 1720869.1875 | 45.45% | Started | 563802.5079 | 1111351.7812 | 100 | 142.8571 | 45.4545 | 100 | 139.8501 | 45.4545
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 15d | [5 empty] | 153469.6749 |  | 9.565% |  | 147877.6948 | 798640.6797
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 10d | [5 empty] | 150685.585 |  | 28.57% |  | 145195.0449 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 505567.9199
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 131763.4199 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 78049.0205 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.02
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 41d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 320066.5059
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 41d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 320066.5059
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 24438.9102 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP76
| TP Status Date | 2010-04-04 17:00 |  | TP Name | 76
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 380d | [5 empty] | 2964629.5014 |  | 7.971% |  | 1703301.7873 | 3266477.689
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 380d | [5 empty] | 2964629.5014 |  | 7.971% |  | 1703301.7873 | 3266477.689
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 380d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 284d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 46d | 98575.3438 | 0 | 19d | 0 | 0 | 98575.3438 | 0 | 70.77% | Started | 98575.3438 | 98575.3438 | 100 | 25.5556 | 70.7692 | 100 | 100 | 70.7692
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 297d | [5 empty] | 2035255.3525 |  | 64.37% |  | 783240.5578 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 25d | 1900083.4922 | 1362354.7734 | 19d | 15822.1797 | 0 | 1915905.6719 | 1362354.7734 | 56.82% | Started | 677875.257 | 1111351.7812 | 100 | 178.5714 | 56.8182 | 100 | 172.3942 | 56.8182
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 20d | [5 empty] | 324839.7977 |  | 20.35% |  | 314638.5584 | 841612.2092
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 15d | [5 empty] | 226028.3774 |  | 42.86% |  | 217792.5674 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 72597.5225 | 100 |  | 0 | 100 |  | 0
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 5d | [5 empty] | 96027.3303 |  | 9.097% |  | 94163.3411 | 548539.4395
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 5d | 94163.3403 | 53714.3994 | 10d | 1863.99 | 0 | 96027.3303 | 53714.3994 | 33.33% | Started | 94163.3411 | 147877.7397 | 100 | 33.3333 | 33.3333 | 100 | 64.937 | 33.3333
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 104906.2202 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.03
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 509745.2148
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 509745.2148
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 509745.2148
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 509745.2148 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 46d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 388608.1074
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 46d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 388608.1074
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 92980.5117 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP77
| TP Status Date | 2010-04-11 17:00 |  | TP Name | 77
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 385d | [5 empty] | 3430372.3471 |  | 8.97% |  | 1916829.2893 | 3456296.0898
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 385d | [5 empty] | 3430372.3471 |  | 8.97% |  | 1916829.2893 | 3456296.0898
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 385d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 289d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 51d | 98575.3438 | 0 | 14d | 0 | 0 | 98575.3438 | 0 | 78.46% | Started | 98575.3438 | 98575.3438 | 100 | 28.3333 | 78.4615 | 100 | 100 | 78.4615
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 302d | [5 empty] | 2396934.2061 |  | 73.75% |  | 897313.3368 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 30d | 2258597.9062 | 1003840.3594 | 14d | 18986.6191 | 0 | 2277584.5254 | 1003840.3594 | 68.18% | Started | 791948.036 | 1111351.7812 | 100 | 214.2857 | 68.1818 | 100 | 204.9382 | 68.1818
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 25d | [5 empty] | 428903.7899 |  | 26.78% |  | 414093.2814 | 868469.4089
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 20d | [5 empty] | 301371.1699 |  | 57.14% |  | 290390.0898 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 10d | [5 empty] | 124748.53 |  | 11.69% |  | 121020.5416 | 575396.6392
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 10d | 121020.54 | 26857.1997 | 5d | 3727.99 | 0 | 124748.53 | 26857.1997 | 66.67% | Started | 121020.5416 | 147877.7397 | 100 | 66.6667 | 66.6667 | 100 | 84.3592 | 66.6667
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 131763.4199 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.03
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 604164.8145
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 604164.8145
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 604164.8145
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 604164.8145 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 51d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 457149.709
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 51d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 457149.709
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 161522.1133 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP78
| TP Status Date | 2010-04-18 17:00 |  | TP Name | 78
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 390d | [5 empty] | 3896115.1749 |  | 9.969% |  | 2130356.7889 | 4239512.3044
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 390d | [5 empty] | 3896115.1749 |  | 9.969% |  | 2130356.7889 | 4239512.3044
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 390d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 294d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 56d | 98575.3438 | 0 | 9d | 0 | 0 | 98575.3438 | 0 | 86.15% | Started | 98575.3438 | 98575.3438 | 100 | 31.1111 | 86.1538 | 100 | 100 | 86.1538
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 307d | [5 empty] | 2758613.0518 |  | 83.12% |  | 1011386.1158 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 35d | 2617112.3203 | 645325.9453 | 9d | 22151.0508 | 0 | 2639263.3711 | 645325.9453 | 79.55% | Started | 906020.815 | 1111351.7812 | 100 | 250 | 79.5455 | 100 | 237.4823 | 79.5455
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 30d | [5 empty] | 532967.772 |  | 33.22% |  | 513548.002 | 884583.7387
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 25d | [5 empty] | 376713.9624 |  | 71.43% |  | 362987.6123 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 15d | [5 empty] | 153469.7197 |  | 14.29% |  | 147877.7397 | 591510.959
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1302725.0977
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1302725.0977
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 792979.8828
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 509745.2148
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 509745.2148 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 56d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 525691.3105
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 56d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 525691.3105
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 230063.7148 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP79
| TP Status Date | 2010-04-25 17:00 |  | TP Name | 79
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 395d | [5 empty] | 4429164.1613 |  | 11.28% |  | 2411190.4414 | 4697364.8611
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 395d | [5 empty] | 4429164.1613 |  | 11.28% |  | 2411190.4414 | 4697364.8611
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 395d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 299d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 61d | 98575.3438 | 0 | 4d | 0 | 0 | 98575.3438 | 0 | 93.85% | Started | 98575.3438 | 98575.3438 | 100 | 33.8889 | 93.8462 | 100 | 100 | 93.8462
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 312d | [5 empty] | 3120291.9053 |  | 92.5% |  | 1125458.8947 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 40d | 2975626.7344 | 286811.5312 | 4d | 25315.4902 | 0 | 3000942.2246 | 286811.5312 | 90.91% | Started | 1020093.594 | 1111351.7812 | 100 | 285.7143 | 90.9091 | 100 | 270.0263 | 90.9091
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 35d | [5 empty] | 704337.9048 |  | 44% |  | 680308.8755 | 884583.7387
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 30d | [5 empty] | 452056.7549 |  | 85.71% |  | 435585.1348 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 |  | 0 | 0 | 72597.5225 | 5d | 0 | 0 | 0 | 72597.5225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 20d | [5 empty] | 249497.05 |  | 23.38% |  | 242041.0809 | 591510.959
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 5d | 94163.3403 | 53714.3994 | 10d | 1863.99 | 0 | 96027.3303 | 53714.3994 | 33.33% | Started | 94163.3411 | 147877.7397 | 100 | 33.3333 | 33.3333 | 100 | 64.937 | 33.3333
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 5d | [5 empty] | 0.01 |  | 14.29% |  | 0.01 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 5d | 0.01 | 0 | 40d | 0 | 0 | 0.01 | 0 | 11.11% | Started | 0.01 | 0.01 | 100 | 25 | 11.1111 | 100 | 100 | 11.1111
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1661471.3145
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1661471.3145
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 604164.8145
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 604164.8145 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 44273.0586
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 44273.0586
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 44273.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 61d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 580524.5918
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 61d | [5 empty] | 295627.5957 |  | 34.27% |  | 295627.5957 | 580524.5918
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 |  | 0 | 0 | 284896.9961 | 20d | 0 | 0 | 0 | 284896.9961 | 0% | Not Started | 0 | 284896.9961 | 100 |  | 0 | 100 |  | 0
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP80
| TP Status Date | 2010-05-02 17:00 |  | TP Name | 80
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 400d | [5 empty] | 4847010.1437 |  | 12.29% |  | 2626342.2621 | 5685999.0759
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 400d | [5 empty] | 4847010.1437 |  | 12.29% |  | 2626342.2621 | 5685999.0759
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 40d | [5 empty] | 808401.897 |  | 50.44% |  | 779763.5985 | 884583.7387
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 25d | [5 empty] | 278218.2498 |  | 25.98% |  | 268898.2814 | 591510.959
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 10d | 121020.54 | 26857.1997 | 5d | 3727.99 | 0 | 124748.53 | 26857.1997 | 66.67% | Started | 121020.5416 | 147877.7397 | 100 | 66.6667 | 66.6667 | 100 | 84.3592 | 66.6667
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 10d | [5 empty] | 0.01 |  | 14.29% |  | 0.01 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 10d | 0.01 | 0 | 35d | 0 | 0 | 0.01 | 0 | 22.22% | Started | 0.01 | 0.01 | 100 | 50 | 22.2222 | 100 | 100 | 22.2222
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2360031.5977
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2360031.5977
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 792979.8828
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 509745.2148
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 509745.2148 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 334346.9902
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 334346.9902
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 38368.6992 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 146368.7012 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 66d | [5 empty] | 320066.5059 |  | 37.1% |  | 320066.5061 | 580524.5918
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 66d | [5 empty] | 320066.5059 |  | 37.1% |  | 320066.5061 | 580524.5918
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 1d | 24438.9102 | 260458.0859 | 19d | 0 | 0 | 24438.9102 | 260458.0859 | 5% | Started | 24438.9104 | 284896.9961 | 100 | 5 | 5 | 100 | 8.5782 | 5
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP81
| TP Status Date | 2010-05-09 17:00 |  | TP Name | 81
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 405d | [5 empty] | 4944272.9349 |  | 12.74% |  | 2721741.0648 | 6121888.4909
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 405d | [5 empty] | 4944272.9349 |  | 12.74% |  | 2721741.0648 | 6121888.4909
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 45d | [5 empty] | 837123.0867 |  | 52.17% |  | 806620.7966 | 884583.7387
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 30d | [5 empty] | 306939.4395 |  | 28.57% |  | 295755.4795 | 591510.959
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 15d | [5 empty] | 0.01 |  | 14.29% |  | 0.01 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 15d | 0.01 | 0 | 30d | 0 | 0 | 0.01 | 0 | 33.33% | Started | 0.01 | 0.01 | 100 | 75 | 33.3333 | 100 | 100 | 33.3333
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2718777.8145
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2718777.8145
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 604164.8145
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 604164.8145 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 411490.1885
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 411490.1885
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 76940.2983 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 184940.3003 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 71d | [5 empty] | 388608.1074 |  | 45.04% |  | 388608.1107 | 580524.5918
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 71d | [5 empty] | 388608.1074 |  | 45.04% |  | 388608.1107 | 580524.5918
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 6d | 92980.5117 | 191916.4844 | 14d | 0 | 0 | 92980.5117 | 191916.4844 | 30% | Started | 92980.515 | 284896.9961 | 100 | 30 | 30 | 100 | 32.6365 | 30
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP82
| TP Status Date | 2010-05-16 17:00 |  | TP Name | 82
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 410d | [5 empty] | 5108841.8768 |  | 13.5% |  | 2884446.0175 | 6897591.9724
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 410d | [5 empty] | 5108841.8768 |  | 13.5% |  | 2884446.0175 | 6897591.9724
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 50d | [5 empty] | 933150.427 |  | 58.27% |  | 900784.1478 | 884583.7387
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 290390.0898
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 35d | [5 empty] | 402966.7698 |  | 37.67% |  | 389918.8206 | 591510.959
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 5d | 94163.3403 | 53714.3994 | 10d | 1863.99 | 0 | 96027.3303 | 53714.3994 | 33.33% | Started | 94163.3411 | 147877.7397 | 100 | 33.3333 | 33.3333 | 100 | 64.937 | 33.3333
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 20d | [5 empty] | 0.02 |  | 28.57% |  | 0.02 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 20d | 0.01 | 0 | 25d | 0 | 0 | 0.01 | 0 | 44.44% | Started | 0.01 | 0.01 | 100 | 100 | 44.4444 | 100 | 100 | 44.4444
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 5d | 0.01 | 0 | 15d | 0 | 0 | 0.01 | 0 | 25% | Started | 0.01 | 0.01 | 100 | 25 | 25 | 100 | 100 | 25
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3417338.0977
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3417338.0977
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 792979.8828
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 509745.2148
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 509745.2148 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 488633.3867
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 488633.3867
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 76d | [5 empty] | 457149.709 |  | 52.99% |  | 457149.7123 | 580524.5918
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 76d | [5 empty] | 457149.709 |  | 52.99% |  | 457149.7123 | 580524.5918
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 11d | 161522.1133 | 123374.8828 | 9d | 0 | 0 | 161522.1133 | 123374.8828 | 55% | Started | 161522.1165 | 284896.9961 | 100 | 55 | 55 | 100 | 56.6949 | 55
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP83
| TP Status Date | 2010-05-23 17:00 |  | TP Name | 83
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 415d | [5 empty] | 5206104.6781 |  | 13.94% |  | 2979844.8196 | 7366912.2214
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 415d | [5 empty] | 5206104.6781 |  | 13.94% |  | 2979844.8196 | 7366912.2214
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 55d | [5 empty] | 961871.6268 |  | 60% |  | 927641.3483 | 947109.8208
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 352916.1719
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 62526.082 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 40d | [5 empty] | 431687.9695 |  | 40.26% |  | 416776.0211 | 591510.959
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 10d | 121020.54 | 26857.1997 | 5d | 3727.99 | 0 | 124748.53 | 26857.1997 | 66.67% | Started | 121020.5416 | 147877.7397 | 100 | 66.6667 | 66.6667 | 100 | 84.3592 | 66.6667
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 25d | [5 empty] | 0.02 |  | 28.57% |  | 0.02 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 25d | 0.01 | 0 | 20d | 0 | 0 | 0.01 | 0 | 55.56% | Started | 0.01 | 0.01 | 100 | 125 | 55.5556 | 100 | 100 | 55.5556
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 10d | 0.01 | 0 | 10d | 0 | 0 | 0.01 | 0 | 50% | Started | 0.01 | 0.01 | 100 | 50 | 50 | 100 | 100 | 50
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3776084.3145
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3776084.3145
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 604164.8145
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 604164.8145 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 536681.3369
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 536681.3369
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 81d | [5 empty] | 525691.3105 |  | 60.93% |  | 525691.3138 | 580524.5918
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 81d | [5 empty] | 525691.3105 |  | 60.93% |  | 525691.3138 | 580524.5918
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 16d | 230063.7148 | 54833.2812 | 4d | 0 | 0 | 230063.7148 | 54833.2812 | 80% | Started | 230063.7181 | 284896.9961 | 100 | 80 | 80 | 100 | 80.7533 | 80
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP84
| TP Status Date | 2010-05-30 17:00 |  | TP Name | 84
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 420d | [5 empty] | 5289659.149 |  | 14.33% |  | 3061535.2957 | 7742241.6903
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 420d | [5 empty] | 5289659.149 |  | 14.33% |  | 3061535.2957 | 7742241.6903
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 60d | [5 empty] | 990592.8164 |  | 61.74% |  | 954498.5464 | 1045973.1616
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 362987.6123
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 45d | [5 empty] | 460409.1592 |  | 42.86% |  | 443633.2192 | 680302.8594
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 88791.9004 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 30d | [5 empty] | 0.02 |  | 28.57% |  | 0.02 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 30d | 0.01 | 0 | 15d | 0 | 0 | 0.01 | 0 | 66.67% | Started | 0.01 | 0.01 | 100 | 150 | 66.6667 | 100 | 100 | 66.6667
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 15d | 0.01 | 0 | 5d | 0 | 0 | 0.01 | 0 | 75% | Started | 0.01 | 0.01 | 100 | 75 | 75 | 100 | 100 | 75
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3964899.3828
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3964899.3828
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 792979.8828
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 624332.3966
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 624332.3966
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 14041.4697 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 86d | [5 empty] | 580524.5918 |  | 67.29% |  | 580524.5918 | 580524.5918
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 86d | [5 empty] | 580524.5918 |  | 67.29% |  | 580524.5918 | 580524.5918
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP85
| TP Status Date | 2010-06-06 17:00 |  | TP Name | 85
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 425d | [5 empty] | 5385686.4894 |  | 14.77% |  | 3155698.6468 | 8059139.9066
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 425d | [5 empty] | 5385686.4894 |  | 14.77% |  | 3155698.6468 | 8059139.9066
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 65d | [5 empty] | 1086620.1568 |  | 67.83% |  | 1048661.8975 | 1072830.3613
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 362987.6123
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 50d | [5 empty] | 556436.4895 |  | 51.95% |  | 537796.5604 | 707160.0591
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 5d | 94163.3403 | 53714.3994 | 10d | 1863.99 | 0 | 96027.3303 | 53714.3994 | 33.33% | Started | 94163.3411 | 147877.7397 | 100 | 33.3333 | 33.3333 | 100 | 64.937 | 33.3333
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 115649.1001 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 35d | [5 empty] | 0.03 |  | 42.86% |  | 0.03 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 35d | 0.01 | 0 | 10d | 0 | 0 | 0.01 | 0 | 77.78% | Started | 0.01 | 0.01 | 100 | 175 | 77.7778 | 100 | 100 | 77.7778
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 5d | 0.01 | 0 | 15d | 0 | 0 | 0.01 | 0 | 25% | Started | 0.01 | 0.01 | 100 | 25 | 25 | 100 | 100 | 25
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4229226
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4229226
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 91d | [5 empty] | 580524.5918 |  | 67.29% |  | 580524.5918 | 580524.5918
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 91d | [5 empty] | 580524.5918 |  | 67.29% |  | 580524.5918 | 580524.5918
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 |  | 0 | 0 | 282214.3467 | 15d | 0 | 0 | 0 | 282214.3467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP86
| TP Status Date | 2010-06-13 17:00 |  | TP Name | 86
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 430d | [5 empty] | 5513844.4381 |  | 15.36% |  | 3281992.599 | 8237888.4969
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 430d | [5 empty] | 5513844.4381 |  | 15.36% |  | 3281992.599 | 8237888.4969
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 70d | [5 empty] | 1115341.3565 |  | 69.57% |  | 1075519.098 | 1152142.2026
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 415442.2539
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 52454.6416 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 55d | [5 empty] | 585157.6892 |  | 54.55% |  | 564653.7609 | 734017.2588
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 10d | 121020.54 | 26857.1997 | 5d | 3727.99 | 0 | 124748.53 | 26857.1997 | 66.67% | Started | 121020.5416 | 147877.7397 | 100 | 66.6667 | 66.6667 | 100 | 84.3592 | 66.6667
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 142506.2998 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 40d | [5 empty] | 0.03 |  | 42.86% |  | 0.03 | 0.04
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 40d | 0.01 | 0 | 5d | 0 | 0 | 0.01 | 0 | 88.89% | Started | 0.01 | 0.01 | 100 | 200 | 88.8889 | 100 | 100 | 88.8889
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 10d | 0.01 | 0 | 10d | 0 | 0 | 0.01 | 0 | 50% | Started | 0.01 | 0.01 | 100 | 50 | 50 | 100 | 100 | 50
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4229226
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4229226
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 96d | [5 empty] | 679961.3408 |  | 78.81% |  | 679961.3435 | 679961.3408
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 96d | [5 empty] | 679961.3408 |  | 78.81% |  | 679961.3435 | 679961.3408
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 5d | 99436.749 | 182777.5977 | 10d | 0 | 0 | 99436.749 | 182777.5977 | 33.33% | Started | 99436.7517 | 99436.749 | 100 | 33.3333 | 33.3333 | 100 | 35.2345 | 33.3333
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP87
| TP Status Date | 2010-06-20 17:00 |  | TP Name | 87
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 435d | [5 empty] | 5633954.4266 |  | 15.91% |  | 3400238.5987 | 8438212.087
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 435d | [5 empty] | 5633954.4266 |  | 15.91% |  | 3400238.5987 | 8438212.087
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 75d | [5 empty] | 1144062.5462 |  | 71.3% |  | 1102376.2961 | 1261076.9938
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 435585.1348
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 60d | [5 empty] | 613878.8789 |  | 57.14% |  | 591510.959 | 822809.1592
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 83420.4604 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 45d | [5 empty] | 0.03 |  | 42.86% |  | 0.03 | 0.05
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 15d | 0.01 | 0 | 5d | 0 | 0 | 0.01 | 0 | 75% | Started | 0.01 | 0.01 | 100 | 75 | 75 | 100 | 100 | 75
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4229226
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4229226
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 101d | [5 empty] | 771350.1396 |  | 89.41% |  | 771350.1451 | 771350.1396
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 101d | [5 empty] | 771350.1396 |  | 89.41% |  | 771350.1451 | 771350.1396
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 10d | 190825.5479 | 91388.7988 | 5d | 0 | 0 | 190825.5479 | 91388.7988 | 66.67% | Started | 190825.5533 | 190825.5479 | 100 | 66.6667 | 66.6667 | 100 | 67.6172 | 66.6667
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP88
| TP Status Date | 2010-06-27 17:00 |  | TP Name | 88
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 440d | [5 empty] | 6400261.9203 |  | 19.43% |  | 4152187.7178 | 8556458.0855
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 440d | [5 empty] | 6400261.9203 |  | 19.43% |  | 4152187.7178 | 8556458.0855
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 80d | [5 empty] | 1240089.8865 |  | 77.4% |  | 1196539.6472 | 1287934.1936
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 435585.1348
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 0 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 65d | [5 empty] | 709906.2092 |  | 66.24% |  | 685674.3001 | 849666.3589
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 5d | 94163.3403 | 53714.3994 | 10d | 1863.99 | 0 | 96027.3303 | 53714.3994 | 33.33% | Started | 94163.3411 | 147877.7397 | 100 | 33.3333 | 33.3333 | 100 | 64.937 | 33.3333
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 110277.6602 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 50d | [5 empty] | 0.04 |  | 57.14% |  | 0.04 | 0.05
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 5d | 0.01 | 0 | 15d | 0 | 0 | 0.01 | 0 | 25% | Started | 0.01 | 0.01 | 100 | 25 | 25 | 100 | 100 | 25
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 5d | [5 empty] | 578891.3545 |  | 3.375% |  | 566396.9746 | 4229226
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 5d | [5 empty] | 578891.3545 |  | 7.653% |  | 566396.9746 | 4229226
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 5d | [5 empty] | 578891.3545 |  | 53.57% |  | 566396.9746 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 5d | 566396.9746 | 94419.5996 | 5d | 12494.3799 | 0 | 578891.3545 | 94419.5996 | 50% | Started | 566396.9746 | 660816.5742 | 100 | 50 | 50 | 100 | 87.6024 | 50
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 106d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 106d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP89
| TP Status Date | 2010-07-04 17:00 |  | TP Name | 89
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 445d | [5 empty] | 6535897.0995 |  | 20% |  | 4273464.5179 | 8625698.4864
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 445d | [5 empty] | 6535897.0995 |  | 20% |  | 4273464.5179 | 8625698.4864
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 85d | [5 empty] | 1268811.0862 |  | 79.13% |  | 1223396.8478 | 1357174.5944
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 477968.3359
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 42383.2012 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 70d | [5 empty] | 738627.4089 |  | 68.83% |  | 712531.5006 | 876523.5586
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 10d | 121020.54 | 26857.1997 | 5d | 3727.99 | 0 | 124748.53 | 26857.1997 | 66.67% | Started | 121020.5416 | 147877.7397 | 100 | 66.6667 | 66.6667 | 100 | 84.3592 | 66.6667
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 137134.8599 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 55d | [5 empty] | 0.04 |  | 57.14% |  | 0.04 | 0.05
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 10d | 0.01 | 0 | 10d | 0 | 0 | 0.01 | 0 | 50% | Started | 0.01 | 0.01 | 100 | 50 | 50 | 100 | 100 | 50
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 10d | [5 empty] | 685805.334 |  | 3.937% |  | 660816.5742 | 4229226
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 10d | [5 empty] | 685805.334 |  | 8.929% |  | 660816.5742 | 4229226
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 10d | [5 empty] | 685805.334 |  | 62.5% |  | 660816.5742 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 111d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 111d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP90
| TP Status Date | 2010-07-11 17:00 |  | TP Name | 90
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 450d | [5 empty] | 7533610.0294 |  | 24.54% |  | 5244324.6965 | 8744704.7181
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 450d | [5 empty] | 7533610.0294 |  | 24.54% |  | 5244324.6965 | 8744704.7181
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 90d | [5 empty] | 1297532.2759 |  | 80.87% |  | 1250254.0459 | 1476180.8261
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 75d | [5 empty] | 767348.5986 |  | 71.43% |  | 739388.6987 | 965315.459
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 78049.0205 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 60d | [5 empty] | 0.04 |  | 57.14% |  | 0.04 | 0.06
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 15d | 0.01 | 0 | 5d | 0 | 0 | 0.01 | 0 | 75% | Started | 0.01 | 0.01 | 100 | 75 | 75 | 100 | 100 | 75
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 15d | [5 empty] | 1654797.0742 |  | 9.561% |  | 1604819.5547 | 4229226
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 15d | [5 empty] | 1654797.0742 |  | 21.68% |  | 1604819.5547 | 4229226
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 15d | [5 empty] | 1075905.7197 |  | 98.21% |  | 1038422.5801 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 1d | 113279.3887 | 18883.9199 | 1d | 2498.8799 | 0 | 115778.2686 | 18883.9199 | 50% | Started | 113279.3887 | 132163.3086 | 100 | 50 | 50 | 100 | 87.6024 | 50
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 5d | [5 empty] | 578891.3545 |  | 53.57% |  | 566396.9746 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 5d | 566396.9746 | 94419.5996 | 5d | 12494.3799 | 0 | 578891.3545 | 94419.5996 | 50% | Started | 566396.9746 | 660816.5742 | 100 | 50 | 50 | 100 | 87.6024 | 50
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 116d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 116d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP91
| TP Status Date | 2010-07-18 17:00 |  | TP Name | 91
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 455d | [5 empty] | 7757934.1392 |  | 25.51% |  | 5451791.5384 | 9319074.9725
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 455d | [5 empty] | 7757934.1392 |  | 25.51% |  | 5451791.5384 | 9319074.9725
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 95d | [5 empty] | 1393559.6162 |  | 86.96% |  | 1344417.3682 | 1503038.0258
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 80d | [5 empty] | 863375.929 |  | 80.53% |  | 833552.011 | 992172.6587
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 5d | 94163.3403 | 53714.3994 | 10d | 1863.99 | 0 | 96027.3303 | 53714.3994 | 33.33% | Started | 94163.3123 | 147877.7397 | 100 | 33.3333 | 33.3333 | 100 | 64.937 | 33.3333
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 104906.2202 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 65d | [5 empty] | 0.05 |  | 71.43% |  | 0.05 | 0.06
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 5d | 0.01 | 0 | 15d | 0 | 0 | 0.01 | 0 | 25% | Started | 0.01 | 0.01 | 100 | 25 | 25 | 100 | 100 | 25
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 20d | [5 empty] | 1783093.8438 |  | 10.24% |  | 1718123.0742 | 4776739.0547
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 20d | [5 empty] | 1783093.8438 |  | 23.21% |  | 1718123.0742 | 4776739.0547
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 10d | [5 empty] | 685805.334 |  | 62.5% |  | 660816.5742 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 547513.0547
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 547513.0547 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 121d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 121d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP92
| TP Status Date | 2010-07-25 17:00 |  | TP Name | 92
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 460d | [5 empty] | 8755647.0792 |  | 30.05% |  | 6422651.7481 | 9440351.7718
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 460d | [5 empty] | 8755647.0792 |  | 30.05% |  | 6422651.7481 | 9440351.7718
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 100d | [5 empty] | 1422280.8159 |  | 88.7% |  | 1371274.5975 | 1529895.2255
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 85d | [5 empty] | 892097.1287 |  | 83.12% |  | 860409.2404 | 1019029.8584
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 10d | 121020.54 | 26857.1997 | 5d | 3727.99 | 0 | 124748.53 | 26857.1997 | 66.67% | Started | 121020.5416 | 147877.7397 | 100 | 66.6667 | 66.6667 | 100 | 84.3592 | 66.6667
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 131763.4199 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 70d | [5 empty] | 0.05 |  | 71.43% |  | 0.05 | 0.06
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 10d | 0.01 | 0 | 10d | 0 | 0 | 0.01 | 0 | 50% | Started | 0.01 | 0.01 | 100 | 50 | 50 | 100 | 100 | 50
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 25d | [5 empty] | 2752085.584 |  | 15.86% |  | 2662126.0547 | 4871158.6543
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 25d | [5 empty] | 2752085.584 |  | 35.97% |  | 2662126.0547 | 4871158.6543
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 15d | [5 empty] | 1075905.7197 |  | 98.21% |  | 1038422.5801 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 1d | 113279.3887 | 18883.9199 | 1d | 2498.8799 | 0 | 115778.2686 | 18883.9199 | 50% | Started | 113279.3887 | 132163.3086 | 100 | 50 | 50 | 100 | 87.6024 | 50
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 5d | [5 empty] | 578891.3545 |  | 53.57% |  | 566396.9746 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 5d | 566396.9746 | 94419.5996 | 5d | 12494.3799 | 0 | 578891.3545 | 94419.5996 | 50% | Started | 566396.9746 | 660816.5742 | 100 | 50 | 50 | 100 | 87.6024 | 50
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 641932.6543
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 641932.6543 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 126d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 126d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP93
| TP Status Date | 2010-08-01 17:00 |  | TP Name | 93
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 465d | [5 empty] | 8912665.0384 |  | 30.71% |  | 6562812.4658 | 9739676.6387
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 465d | [5 empty] | 8912665.0384 |  | 30.71% |  | 6562812.4658 | 9739676.6387
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 105d | [5 empty] | 1451002.0056 |  | 90.43% |  | 1398131.7956 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 90d | [5 empty] | 920818.3184 |  | 85.71% |  | 887266.4385 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 |  | 0 | 0 | 147877.7397 | 15d | 0 | 0 | 0 | 147877.7397 | 0% | Not Started | 0 | 147877.7397 | 100 |  | 0 | 100 |  | 0
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 75d | [5 empty] | 0.05 |  | 71.43% |  | 0.05 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 15d | 0.01 | 0 | 5d | 0 | 0 | 0.01 | 0 | 75% | Started | 0.01 | 0.01 | 100 | 75 | 75 | 100 | 100 | 75
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 30d | [5 empty] | 2880382.3535 |  | 16.54% |  | 2775429.5742 | 5154369.1914
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 30d | [5 empty] | 2880382.3535 |  | 37.5% |  | 2775429.5742 | 5154369.1914
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 10d | [5 empty] | 685805.334 |  | 62.5% |  | 660816.5742 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 925143.1914
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 131d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 131d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP94
| TP Status Date | 2010-08-08 17:00 |  | TP Name | 94
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 470d | [5 empty] | 9977684.119 |  | 35.57% |  | 7600978.7974 | 11468246.8985
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 470d | [5 empty] | 9977684.119 |  | 35.57% |  | 7600978.7974 | 11468246.8985
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 110d | [5 empty] | 1547029.3459 |  | 96.53% |  | 1492295.1467 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 95d | [5 empty] | 1016845.6487 |  | 94.81% |  | 981429.7796 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 5d | 94163.3403 | 53714.3994 | 10d | 1863.99 | 0 | 96027.3303 | 53714.3994 | 33.33% | Started | 94163.3411 | 147877.7397 | 100 | 33.3333 | 33.3333 | 100 | 64.937 | 33.3333
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 80d | [5 empty] | 0.06 |  | 85.71% |  | 0.06 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 5d | 0.01 | 0 | 15d | 0 | 0 | 0.01 | 0 | 25% | Started | 0.01 | 0.01 | 100 | 25 | 25 | 100 | 100 | 25
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 35d | [5 empty] | 3849374.0938 |  | 22.16% |  | 3719432.5547 | 6882939.4512
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 35d | [5 empty] | 3849374.0938 |  | 50.25% |  | 3719432.5547 | 5815161.6348
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 15d | [5 empty] | 1075905.7197 |  | 98.21% |  | 1038422.5801 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 1d | 113279.3887 | 18883.9199 | 1d | 2498.8799 | 0 | 115778.2686 | 18883.9199 | 50% | Started | 113279.3887 | 132163.3086 | 100 | 50 | 50 | 100 | 87.6024 | 50
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 5d | [5 empty] | 578891.3545 |  | 53.57% |  | 566396.9746 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 5d | 566396.9746 | 94419.5996 | 5d | 12494.3799 | 0 | 578891.3545 | 94419.5996 | 50% | Started | 566396.9746 | 660816.5742 | 100 | 50 | 50 | 100 | 87.6024 | 50
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 528629.1348
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 528629.1348 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1067777.8164
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1067777.8164 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 136d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 136d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP95
| TP Status Date | 2010-08-15 17:00 |  | TP Name | 95
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 475d | [5 empty] | 10134702.0882 |  | 36.22% |  | 7741139.5174 | 12839777.9405
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 475d | [5 empty] | 10134702.0882 |  | 36.22% |  | 7741139.5174 | 12839777.9405
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 115d | [5 empty] | 1575750.5457 |  | 98.26% |  | 1519152.3472 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 100d | [5 empty] | 1045566.8484 |  | 97.41% |  | 1008286.9801 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 10d | 121020.54 | 26857.1997 | 5d | 3727.99 | 0 | 124748.53 | 26857.1997 | 66.67% | Started | 121020.5416 | 147877.7397 | 100 | 66.6667 | 66.6667 | 100 | 84.3592 | 66.6667
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 85d | [5 empty] | 0.06 |  | 85.71% |  | 0.06 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 10d | 0.01 | 0 | 10d | 0 | 0 | 0.01 | 0 | 50% | Started | 0.01 | 0.01 | 100 | 50 | 50 | 100 | 100 | 50
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 40d | [5 empty] | 3977670.8633 |  | 22.83% |  | 3832736.0742 | 8254470.4932
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 40d | [5 empty] | 3977670.8633 |  | 51.79% |  | 3832736.0742 | 5909581.2344
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 10d | [5 empty] | 685805.334 |  | 62.5% |  | 660816.5742 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 623048.7344
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 623048.7344 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2328927.1484
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1067777.8164 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 15962.1104
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 15962.1104 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 141d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 141d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP96
| TP Status Date | 2010-08-22 17:00 |  | TP Name | 96
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 480d | [5 empty] | 11132415.0181 |  | 40.77% |  | 8711999.696 | 14433042.7897
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 480d | [5 empty] | 11132415.0181 |  | 40.77% |  | 8711999.696 | 14433042.7897
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 120d | [5 empty] | 1604471.7354 |  | 100% |  | 1546009.5454 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 90d | [5 empty] | 0.06 |  | 85.71% |  | 0.06 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 15d | 0.01 | 0 | 5d | 0 | 0 | 0.01 | 0 | 75% | Started | 0.01 | 0.01 | 100 | 75 | 75 | 100 | 100 | 75
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 20d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0.01 | 100 |  | 0 | 100 |  | 0
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 45d | [5 empty] | 4946662.6035 |  | 28.46% |  | 4776739.0547 | 9847735.3424
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 45d | [5 empty] | 4946662.6035 |  | 64.54% |  | 4776739.0547 | 6192791.7715
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 15d | [5 empty] | 1075905.7197 |  | 98.21% |  | 1038422.5801 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 1d | 113279.3887 | 18883.9199 | 1d | 2498.8799 | 0 | 115778.2686 | 18883.9199 | 50% | Started | 113279.3887 | 132163.3086 | 100 | 50 | 50 | 100 | 87.6024 | 50
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 5d | [5 empty] | 578891.3545 |  | 53.57% |  | 566396.9746 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 5d | 566396.9746 | 94419.5996 | 5d | 12494.3799 | 0 | 578891.3545 | 94419.5996 | 50% | Started | 566396.9746 | 660816.5742 | 100 | 50 | 50 | 100 | 87.6024 | 50
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 906259.2715
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 113279.3887 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3590076.4805
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1067777.8164 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 40876.541
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 15962.1104 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 23990.5494
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 146d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 146d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP97
| TP Status Date | 2010-08-29 17:00 |  | TP Name | 97
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 485d | [5 empty] | 12545706.2899 |  | 46.63% |  | 9965595.3603 | 16410864.4354
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 485d | [5 empty] | 12545706.2899 |  | 46.63% |  | 9965595.3603 | 16410864.4354
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 125d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 95d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 5d | 0.01 | 0 | 15d | 0 | 0 | 0.01 | 0 | 25% | Started | 0.01 | 0.01 | 100 | 25 | 25 | 100 | 100 | 25
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 50d | [5 empty] | 6359953.8652 |  | 35.93% |  | 6030334.709 | 11825556.988
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 50d | [5 empty] | 5074959.373 |  | 66.07% |  | 4890042.5742 | 6853584.2148
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 10d | [5 empty] | 685805.334 |  | 62.5% |  | 660816.5742 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 509745.2148
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 509745.2148 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 5d | [5 empty] | 1284994.4922 |  | 12.92% |  | 1140292.1348 | 4851225.8125
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 5d | 1261149.332 | 241714.3945 | 5d | 23845.1602 | 0 | 1284994.4922 | 241714.3945 | 50% | Started | 1140292.1348 | 1261149.332 | 100 | 100 | 50 | 100 | 101.8907 | 50
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1067777.8164 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 65790.9717
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 15962.1104 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47981.0989
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6974.8901
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 151d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 151d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP98
| TP Status Date | 2010-09-05 17:00 |  | TP Name | 98
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 490d | [5 empty] | 13201366.2186 |  | 48.97% |  | 10464058.5634 | 17822313.2373
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 490d | [5 empty] | 13201366.2186 |  | 48.97% |  | 10464058.5634 | 17822313.2373
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 130d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 100d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 10d | 0.01 | 0 | 10d | 0 | 0 | 0.01 | 0 | 50% | Started | 0.01 | 0.01 | 100 | 50 | 50 | 100 | 100 | 50
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 55d | [5 empty] | 7015613.7939 |  | 38.9% |  | 6528797.9121 | 13237005.7899
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 55d | [5 empty] | 5465059.7588 |  | 71.17% |  | 5267648.5801 | 6948003.8145
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 15d | [5 empty] | 1075905.7197 |  | 98.21% |  | 1038422.5801 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 1d | 113279.3887 | 18883.9199 | 1d | 2498.8799 | 0 | 115778.2686 | 18883.9199 | 50% | Started | 113279.3887 | 132163.3086 | 100 | 50 | 50 | 100 | 87.6024 | 50
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 604164.8145
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 604164.8145 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 10d | [5 empty] | 1550554.0352 |  | 14.29% |  | 1261149.332 | 6112375.1445
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1067777.8164 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 90705.4023
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 15962.1104 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 71971.6483
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 13949.7803
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 156d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 156d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP99
| TP Status Date | 2010-09-12 17:00 |  | TP Name | 99
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 495d | [5 empty] | 15065252.0555 |  | 56.95% |  | 12170747.6739 | 19351611.5289
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 495d | [5 empty] | 15065252.0555 |  | 56.95% |  | 12170747.6739 | 19351611.5289
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 135d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 105d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 15d | 0.01 | 0 | 5d | 0 | 0 | 0.01 | 0 | 75% | Started | 0.01 | 0.01 | 100 | 75 | 75 | 100 | 100 | 75
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 60d | [5 empty] | 8879499.6309 |  | 49.07% |  | 8235487.0226 | 14766304.0815
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 60d | [5 empty] | 6043951.1035 |  | 78.83% |  | 5834045.5558 | 7136818.8828
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 4d | [5 empty] | 557508.5547 |  | 51.78% |  | 547513.0558 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 4d | 547513.0547 | 113303.5195 | 6d | 9995.5 | 0 | 557508.5547 | 113303.5195 | 40% | Started | 547513.0558 | 660816.5742 | 100 | 40 | 40 | 100 | 84.3666 | 40
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 792979.8828
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 15d | [5 empty] | 2835548.5273 |  | 27.2% |  | 2401441.4668 | 7373524.4766
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 5d | 1261149.332 | 241714.3945 | 5d | 23845.1602 | 0 | 1284994.4922 | 241714.3945 | 50% | Started | 1140292.1348 | 1261149.332 | 100 | 100 | 50 | 100 | 101.8907 | 50
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1067777.8164 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 115619.833
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 15962.1104 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 95962.1978
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 20924.6704
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 23454.021
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 161d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 161d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP100
| TP Status Date | 2010-09-19 17:00 |  | TP Name | 100
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 500d | [5 empty] | 15437725.5789 |  | 57.96% |  | 12386024.4652 | 20956421.3693
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 500d | [5 empty] | 15437725.5789 |  | 57.96% |  | 12386024.4652 | 20956421.3693
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 65d | [5 empty] | 9251973.1543 |  | 50.35% |  | 8450763.8139 | 16371113.922
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 65d | [5 empty] | 6150865.084 |  | 80.1% |  | 5928465.1498 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 9d | [5 empty] | 664422.5352 |  | 60.71% |  | 641932.6498 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 9d | 641932.6543 | 18883.9199 | 1d | 22489.8809 | 0 | 664422.5352 | 18883.9199 | 90% | Started | 641932.6498 | 660816.5742 | 100 | 90 | 90 | 100 | 100.5457 | 90
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 20d | [5 empty] | 3101108.0703 |  | 28.57% |  | 2522298.6641 | 8634673.8086
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1067777.8164 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 140534.2637
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 15962.1104 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 119952.7472
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 27899.5605
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 46908.042
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 166d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 166d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP101
| TP Status Date | 2010-09-26 17:00 |  | TP Name | 101
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 505d | [5 empty] | 17018424.9871 |  | 64.62% |  | 13809527.1415 | 21229126.7762
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 505d | [5 empty] | 17018424.9871 |  | 64.62% |  | 13809527.1415 | 21229126.7762
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 70d | [5 empty] | 10832672.5625 |  | 58.83% |  | 9874266.4902 | 16643819.3289
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 70d | [5 empty] | 6446570 |  | 83.93% |  | 6211675.6914 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 14d | [5 empty] | 960127.4512 |  | 87.5% |  | 925143.1914 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 |  | 0 | 0 | 660816.5742 | 10d | 0 | 0 | 0 | 660816.5742 | 0% | Not Started | 0 | 660816.5742 | 100 |  | 0 | 100 |  | 0
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 25d | [5 empty] | 4386102.5625 |  | 41.49% |  | 3662590.7988 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 5d | 1261149.332 | 241714.3945 | 5d | 23845.1602 | 0 | 1284994.4922 | 241714.3945 | 50% | Started | 1140292.1348 | 1261149.332 | 100 | 100 | 50 | 100 | 101.8907 | 50
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 165448.6943
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 15962.1104 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 143943.2966
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 34874.4507
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 70362.063
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 |  | 0 | 0 | 49073.0586 | 2d | 0 | 0 | 0 | 49073.0586 | 0% | Not Started | 0 | 49073.0586 | 100 |  | 0 | 100 |  | 0
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 171d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 171d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP102
| TP Status Date | 2010-10-03 17:00 |  | TP Name | 102
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 510d | [5 empty] | 18006344.4119 |  | 68.51% |  | 14640249.843 | 21292498.5571
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 510d | [5 empty] | 18006344.4119 |  | 68.51% |  | 14640249.843 | 21292498.5571
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 75d | [5 empty] | 11771518.9287 |  | 63.49% |  | 10655916.1331 | 16707191.1097
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 75d | [5 empty] | 7119856.8232 |  | 92.86% |  | 6872468.137 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 3d | [5 empty] | 536125.7646 |  | 50% |  | 528629.137 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 3d | 528629.1348 | 132187.4395 | 7d | 7496.6299 | 0 | 536125.7646 | 132187.4395 | 30% | Started | 528629.137 | 660816.5742 | 100 | 30 | 30 | 100 | 81.1308 | 30
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 30d | [5 empty] | 4651662.1055 |  | 42.86% |  | 3783447.9961 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 41849.3408
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 93816.084
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 2d | [5 empty] | 49073.0586 |  | 7.549% |  | 49073.0586 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 2d | [5 empty] | 49073.0586 |  | 7.549% |  | 49073.0586 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 |  | 0 | 0 | 100536.5312 | 1d | 0 | 0 | 0 | 100536.5312 | 0% | Not Started | 0 | 100536.5312 | 100 |  | 0 | 100 |  | 0
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 |  | 0 | 0 | 115511.8975 | 14d | 0 | 0 | 0 | 115511.8975 | 0% | Not Started | 0 | 115511.8975 | 100 |  | 0 | 100 |  | 0
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 |  | 0 | 0 | 223511.8994 | 14d | 0 | 0 | 0 | 223511.8994 | 0% | Not Started | 0 | 223511.8994 | 100 |  | 0 | 100 |  | 0
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 176d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 176d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP103
| TP Status Date | 2010-10-10 17:00 |  | TP Name | 103
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 515d | [5 empty] | 19692669.744 |  | 75.64% |  | 16164092.6699 | 21322927.4682
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 515d | [5 empty] | 19692669.744 |  | 75.64% |  | 16164092.6699 | 21322927.4682
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 80d | [5 empty] | 13163427.4004 |  | 70.84% |  | 11890627.8675 | 16737620.0209
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 80d | [5 empty] | 7226770.8027 |  | 94.13% |  | 6966887.7366 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 8d | [5 empty] | 643039.7441 |  | 58.93% |  | 623048.7366 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 8d | 623048.7344 | 37767.8398 | 2d | 19991.0098 | 0 | 643039.7441 | 37767.8398 | 80% | Started | 623048.7366 | 660816.5742 | 100 | 80 | 80 | 100 | 97.3099 | 80
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 35d | [5 empty] | 5936656.5977 |  | 55.77% |  | 4923740.1309 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 5d | 1261149.332 | 241714.3945 | 5d | 23845.1602 | 0 | 1284994.4922 | 241714.3945 | 50% | Started | 1140292.1348 | 1261149.332 | 100 | 100 | 50 | 100 | 101.8907 | 50
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 117270.105
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 7d | [5 empty] | 343489.9189 |  | 52.03% |  | 338204.1511 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 7d | [5 empty] | 343489.9189 |  | 52.03% |  | 338204.1511 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 5d | 100536.5312 | 0 | 15d | 40000 | 0 | 140536.5312 | 0 | 25% | Started | 100536.5312 | 100536.5312 | 100 | 500 | 25 | 100 | 139.7865 | 25
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 5d | 46083.019 | 69428.8784 | 9d | -19285.7109 | 0 | 26797.3081 | 69428.8784 | 35.71% | Started | 46083.02 | 115511.8975 | 100 | 35.7143 | 35.7143 | 100 | 23.1987 | 35.7143
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 5d | 154083.021 | 115714.7974 | 15d | -27000 | 0 | 127083.021 | 115714.7974 | 25% | Started | 142511.5413 | 223511.8994 | 100 | 35.7143 | 25 | 100 | 56.8574 | 25
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 181d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 181d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP104
| TP Status Date | 2010-10-17 17:00 |  | TP Name | 104
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 520d | [5 empty] | 20324791.6834 |  | 77.84% |  | 16633732.1214 | 21346381.4892
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 520d | [5 empty] | 20324791.6834 |  | 77.84% |  | 16633732.1214 | 21346381.4892
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 85d | [5 empty] | 13724691.8604 |  | 73.25% |  | 12294695.5996 | 16761074.0419
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 85d | [5 empty] | 7522475.7197 |  | 97.96% |  | 7250098.2715 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 13d | [5 empty] | 938744.6611 |  | 85.71% |  | 906259.2715 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 1d | 113279.3887 | 18883.9199 | 1d | 2498.8799 | 0 | 115778.2686 | 18883.9199 | 50% | Started | 113279.3887 | 132163.3086 | 100 | 50 | 50 | 100 | 87.6024 | 50
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 |  | 0 | 0 | 132163.3086 | 2d | 0 | 0 | 0 | 132163.3086 | 0% | Not Started | 0 | 132163.3086 | 100 |  | 0 | 100 |  | 0
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 40d | [5 empty] | 6202216.1406 |  | 57.14% |  | 5044597.3281 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 140724.126
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 12d | [5 empty] | 414347.3984 |  | 62.11% |  | 403775.8705 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 12d | [5 empty] | 414347.3984 |  | 62.11% |  | 403775.8705 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 10d | 100536.5312 | 0 | 10d | 80000 | 0 | 180536.5312 | 0 | 50% | Started | 100536.5312 | 100536.5312 | 100 | 1000 | 50 | 100 | 179.5731 | 50
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 10d | 84654.6182 | 30857.2793 | 4d | -38571.4297 | 0 | 46083.1885 | 30857.2793 | 71.43% | Started | 84654.62 | 115511.8975 | 100 | 71.4286 | 71.4286 | 100 | 39.8948 | 71.4286
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 10d | 192654.6201 | 77143.1982 | 10d | -54000 | 0 | 138654.6201 | 77143.1982 | 50% | Started | 169511.6606 | 223511.8994 | 100 | 71.4286 | 50 | 100 | 62.0346 | 50
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 186d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 186d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP105
| TP Status Date | 2010-10-24 17:00 |  | TP Name | 105
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 525d | [5 empty] | 21835330.3323 |  | 84.15% |  | 17982928.8815 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 525d | [5 empty] | 21835330.3323 |  | 84.15% |  | 17982928.8815 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 90d | [5 empty] | 15168230.2012 |  | 80.94% |  | 13586034.9629 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 45d | [5 empty] | 7487210.6328 |  | 70.06% |  | 6184889.4629 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 5d | 1261149.332 | 241714.3945 | 5d | 23845.1602 | 0 | 1284994.4922 | 241714.3945 | 50% | Started | 1140292.1348 | 1261149.332 | 100 | 100 | 50 | 100 | 101.8907 | 50
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 17d | [5 empty] | 481347.7065 |  | 71.02% |  | 461633.2673 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 17d | [5 empty] | 481347.7065 |  | 71.02% |  | 461633.2673 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 15d | 100536.5312 | 0 | 5d | 120000 | 0 | 220536.5312 | 0 | 75% | Started | 100536.5312 | 100536.5312 | 100 | 1500 | 75 | 100 | 219.3596 | 75
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 15d | 231226.2192 | 38571.5991 | 5d | -81000 | 0 | 150226.2192 | 38571.5991 | 75% | Started | 196511.78 | 223511.8994 | 100 | 107.1429 | 75 | 100 | 67.2117 | 75
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 191d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 191d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP106
| TP Status Date | 2010-10-31 17:00 |  | TP Name | 106
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 530d | [5 empty] | 22152461.4744 |  | 84.84% |  | 18130786.1982 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 530d | [5 empty] | 22152461.4744 |  | 84.84% |  | 18130786.1982 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 95d | [5 empty] | 15433789.7441 |  | 81.66% |  | 13706892.1602 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 50d | [5 empty] | 7752770.1758 |  | 71.43% |  | 6305746.6602 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 22d | [5 empty] | 532919.3057 |  | 75.17% |  | 488633.3867 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 22d | [5 empty] | 532919.3057 |  | 75.17% |  | 488633.3867 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 |  | 0 | 0 | 48047.9502 | 5d | 0 | 0 | 0 | 48047.9502 | 0% | Not Started | 0 | 48047.9502 | 100 |  | 0 | 100 |  | 0
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 196d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 196d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP107
| TP Status Date | 2010-11-07 17:00 |  | TP Name | 107
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 535d | [5 empty] | 23485503.9168 |  | 90.4% |  | 19319126.2831 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 535d | [5 empty] | 23485503.9168 |  | 90.4% |  | 19319126.2831 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 100d | [5 empty] | 16718784.2363 |  | 88.46% |  | 14847184.2949 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 55d | [5 empty] | 9037764.668 |  | 84.35% |  | 7446038.7949 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 5d | 1261149.332 | 241714.3945 | 5d | 23845.1602 | 0 | 1284994.4922 | 241714.3945 | 50% | Started | 1140292.1348 | 1261149.332 | 100 | 100 | 50 | 100 | 101.8907 | 50
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 27d | [5 empty] | 580967.2559 |  | 82.56% |  | 536681.3369 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 27d | [5 empty] | 580967.2559 |  | 82.56% |  | 536681.3369 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 |  | 0 | 0 | 73609.59 | 3d | 0 | 0 | 0 | 73609.59 | 0% | Not Started | 0 | 73609.59 | 100 |  | 0 | 100 |  | 0
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 |  | 0 | 0 | 39755.8691 | 7d | 0 | 0 | 0 | 39755.8691 | 0% | Not Started | 0 | 39755.8691 | 100 |  | 0 | 100 |  | 0
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 201d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 201d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP108
| TP Status Date | 2010-11-14 17:00 |  | TP Name | 108
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 540d | [5 empty] | 23833571.6596 |  | 91.38% |  | 19527634.5406 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 540d | [5 empty] | 23833571.6596 |  | 91.38% |  | 19527634.5406 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 105d | [5 empty] | 16984343.7793 |  | 89.18% |  | 14968041.4922 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 60d | [5 empty] | 9303324.2109 |  | 85.71% |  | 7566895.9922 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 |  | 0 | 0 | 1261149.332 | 5d | 0 | 0 | 0 | 1261149.332 | 0% | Not Started | 0 | 1261149.332 | 100 |  | 0 | 100 |  | 0
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 32d | [5 empty] | 663475.4557 |  | 96.04% |  | 624332.3971 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 32d | [5 empty] | 663475.4557 |  | 96.04% |  | 624332.3971 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 2d | 14041.4697 | 25714.3994 | 5d | -5142.8599 | 0 | 8898.6099 | 25714.3994 | 28.57% | Started | 14041.4702 | 39755.8691 | 100 | 28.5714 | 28.5714 | 100 | 22.3831 | 28.5714
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 206d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 206d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP109
| TP Status Date | 2010-11-21 17:00 |  | TP Name | 109
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 545d | [5 empty] | 25131423.4111 |  | 96.84% |  | 20693641.0743 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 545d | [5 empty] | 25131423.4111 |  | 96.84% |  | 20693641.0743 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 110d | [5 empty] | 18269338.2715 |  | 95.97% |  | 16108333.627 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 65d | [5 empty] | 10588318.7031 |  | 98.63% |  | 8707188.127 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 5d | 1261149.332 | 241714.3945 | 5d | 23845.1602 | 0 | 1284994.4922 | 241714.3945 | 50% | Started | 1140292.1348 | 1261149.332 | 100 | 100 | 50 | 100 | 101.8907 | 50
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 37d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 37d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 211d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 211d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP110
| TP Status Date | 2010-11-28 17:00 |  | TP Name | 110
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 550d | [5 empty] | 25460798.9949 |  | 97.66% |  | 20870412.9469 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 550d | [5 empty] | 25460798.9949 |  | 97.66% |  | 20870412.9469 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
39 | foundation 6 | 2010-06-16 08:00 | 2010-07-06 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-07-12 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
40 | foundation 7 | 2010-07-08 08:00 | 2010-07-28 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-08-02 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
41 | Setting of concrete | 2010-03-04 08:00 | 2010-08-25 17:00 | 125d |  |  | 0.07 |  |  | 0.07 |  | 110d | [5 empty] | 0.07 |  | 100% |  | 0.07 | 0.07
42 | setting concrete 1 | 2010-03-04 08:00 | 2010-03-31 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-04-19 08:00 | 45d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 225 | 100 | 100 | 100 | 100
43 | setting concrete 2 | 2010-03-18 08:00 | 2010-04-14 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-10 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
44 | setting concrete 3 | 2010-04-01 08:00 | 2010-04-28 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-05-31 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
45 | setting concrete 4 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-06-21 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
46 | setting concrete 5 | 2010-06-15 08:00 | 2010-07-12 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-07-12 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
47 | setting concrete 6 | 2010-07-07 08:00 | 2010-08-03 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-02 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
48 | setting concrete 7 | 2010-07-29 08:00 | 2010-08-25 17:00 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2010-08-23 08:00 | 20d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 100 | 100 | 100 | 100 | 100 | 100
49 | Windturbines | 2010-03-31 17:00 | 2010-10-22 17:00 | 147d |  |  | 12570195.4637 |  |  | 16784528.0629 |  | 115d | [5 empty] | 18598713.8553 |  | 97.02% |  | 16285105.4995 | 16784528.0629
50 | Tower | 2010-03-31 17:00 | 2010-09-16 17:00 | 121d |  |  | 5286146.4688 |  |  | 7401145.5 |  | 88d | [5 empty] | 7681019.5684 |  | 100% |  | 7401145.5 | 7401145.5
51 | WEC 1 | 2010-03-31 17:00 | 2010-04-22 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
52 | Pre installation | 2010-03-31 17:00 | 2010-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-06-21 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | Installation tower | 2010-04-01 08:00 | 2010-04-14 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-06-21 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
54 | stressing tower | 2010-04-15 08:00 | 2010-04-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-05 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
55 | injection of tower | 2010-04-19 08:00 | 2010-04-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-07 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
56 | Finish | 2010-04-21 08:00 | 2010-04-22 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-09 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
57 | WEC 2 | 2010-04-14 17:00 | 2010-05-06 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
58 | Pre installation | 2010-04-14 17:00 | 2010-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
59 | Installation tower | 2010-04-15 08:00 | 2010-04-28 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-05 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
60 | stressing tower | 2010-04-29 08:00 | 2010-04-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
61 | injection of tower | 2010-05-03 08:00 | 2010-05-04 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
62 | Finish | 2010-05-05 08:00 | 2010-05-06 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-07-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
63 | WEC 3 | 2010-04-28 17:00 | 2010-05-20 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
64 | Pre installation | 2010-04-28 17:00 | 2010-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-07-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | Installation tower | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-07-19 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
66 | stressing tower | 2010-05-13 08:00 | 2010-05-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-02 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
67 | injection of tower | 2010-05-17 08:00 | 2010-05-18 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-04 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
68 | Finish | 2010-05-19 08:00 | 2010-05-20 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-06 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
69 | WEC 4 | 2010-05-12 17:00 | 2010-06-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
70 | Pre installation | 2010-05-12 17:00 | 2010-05-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | Installation tower | 2010-05-13 08:00 | 2010-05-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-02 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
72 | stressing tower | 2010-05-27 08:00 | 2010-05-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-16 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
73 | injection of tower | 2010-05-31 08:00 | 2010-06-01 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-18 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
74 | Finish | 2010-06-02 08:00 | 2010-06-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-20 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
75 | WEC 5 | 2010-07-12 17:00 | 2010-08-03 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
76 | Pre installation | 2010-07-12 17:00 | 2010-07-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-08-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
77 | Installation tower | 2010-07-13 08:00 | 2010-07-26 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-08-16 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
78 | stressing tower | 2010-07-27 08:00 | 2010-07-28 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-08-30 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
79 | injection of tower | 2010-07-29 08:00 | 2010-07-30 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-01 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
80 | Finish | 2010-08-02 08:00 | 2010-08-03 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-03 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
81 | WEC 6 | 2010-08-03 17:00 | 2010-08-25 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
82 | Pre installation | 2010-08-03 17:00 | 2010-08-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
83 | Installation tower | 2010-08-04 08:00 | 2010-08-17 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-07 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
84 | stressing tower | 2010-08-18 08:00 | 2010-08-19 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-21 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
85 | injection of tower | 2010-08-20 08:00 | 2010-08-23 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-23 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
86 | Finish | 2010-08-24 08:00 | 2010-08-25 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-09-27 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
87 | WEC 7 | 2010-08-25 17:00 | 2010-09-16 17:00 | 16d |  |  | 755163.7812 |  |  | 1057306.5 |  | 16d | [5 empty] | 1097288.5098 |  | 100% |  | 1057306.5 | 1057306.5
88 | Pre installation | 2010-08-25 17:00 | 2010-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
89 | Installation tower | 2010-08-26 08:00 | 2010-09-08 17:00 | 10d |  | 0 | 471977.375 | 2360.49 | 188839.1992 | 660816.5742 | 2010-09-29 08:00 | 10d | 660816.5742 | 0 | 0 | 24988.7598 | 0 | 685805.334 | 0 | 100% | Finished | 660816.5742 | 660816.5742 | 100 | 100 | 100 | 100 | 103.7815 | 100
90 | stressing tower | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-13 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
91 | injection of tower | 2010-09-13 08:00 | 2010-09-14 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-15 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
92 | Finish | 2010-09-15 08:00 | 2010-09-16 17:00 | 2d |  | 0 | 94395.4688 | 2360.49 | 37767.8398 | 132163.3086 | 2010-10-19 08:00 | 2d | 132163.3086 | 0 | 0 | 4997.75 | 0 | 137161.0586 | 0 | 100% | Finished | 132163.3086 | 132163.3086 | 100 | 100 | 100 | 100 | 103.7815 | 100
93 | Erection machines | 2010-08-06 08:00 | 2010-09-23 17:00 | 35d |  |  | 7136044.5625 |  |  | 8828045.3242 |  | 70d | [5 empty] | 10853878.2461 |  | 100% |  | 8828045.3242 | 8828045.3242
94 | WEC 1 | 2010-08-06 08:00 | 2010-08-12 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-08-23 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
95 | WEC 2 | 2010-08-13 08:00 | 2010-08-19 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-06 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
96 | WEC 3 | 2010-08-20 08:00 | 2010-08-26 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-09-20 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
97 | WEC 4 | 2010-08-27 08:00 | 2010-09-02 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-04 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
98 | WEC 5 | 2010-09-03 08:00 | 2010-09-09 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-10-18 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
99 | WEC 6 | 2010-09-10 08:00 | 2010-09-16 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-01 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
100 | WEC 7 | 2010-09-17 08:00 | 2010-09-23 17:00 | 5d |  | 0 | 1019434.9375 | 6042.8599 | 241714.3945 | 1261149.332 | 2010-11-15 08:00 | 10d | 1502863.7266 | 0 | 0 | 47690.3086 | 0 | 1550554.0352 | 0 | 100% | Finished | 1261149.332 | 1261149.332 | 100 | 200 | 100 | 100 | 122.9477 | 100
101 | Grid | 2010-08-13 08:00 | 2010-09-28 17:00 | 33d |  |  | 80401.6514 |  |  | 174401.0146 |  | 5d | [5 empty] | 46922.9312 |  | 26% |  | 45352.7014 | 174401.0146
102 | WEC 1 | 2010-08-13 08:00 | 2010-08-17 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-22 08:00 | 3d | 24914.4307 | 0 | 0 | 942.14 | 0 | 25856.5707 | 0 | 100% | Finished | 24914.4307 | 24914.4307 | 100 | 100 | 100 | 100 | 103.7815 | 100
103 | WEC 2 | 2010-08-20 08:00 | 2010-08-24 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 | 2010-11-25 08:00 | 2d | 20438.2705 | 4476.1602 | 1d | 628.09 | 0 | 21066.3605 | 4476.1602 | 66.67% | Started | 20438.2708 | 24914.4307 | 100 | 66.6667 | 66.6667 | 100 | 84.5549 | 66.6667
104 | WEC 3 | 2010-08-27 08:00 | 2010-08-31 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
105 | WEC 4 | 2010-09-03 08:00 | 2010-09-07 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
106 | WEC 5 | 2010-09-10 08:00 | 2010-09-14 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
107 | WEC 6 | 2010-09-17 08:00 | 2010-09-21 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
108 | WEC 7 | 2010-09-24 08:00 | 2010-09-28 17:00 | 3d |  | 0 | 11485.9502 | 559.52 | 13428.4805 | 24914.4307 |  | 0 | 0 | 24914.4307 | 3d | 0 | 0 | 0 | 24914.4307 | 0% | Not Started | 0 | 24914.4307 | 100 |  | 0 | 100 |  | 0
109 | Energizing | 2010-08-17 17:00 | 2010-09-28 17:00 | 30d |  |  | 0 |  |  | 0 |  | 2d | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | WEC 1 | 2010-08-17 17:00 | 2010-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-11-25 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
111 | WEC 2 | 2010-08-24 17:00 | 2010-08-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | WEC 3 | 2010-08-31 17:00 | 2010-08-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | WEC 4 | 2010-09-07 17:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | WEC 5 | 2010-09-14 17:00 | 2010-09-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | WEC 6 | 2010-09-21 17:00 | 2010-09-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | WEC 7 | 2010-09-28 17:00 | 2010-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Commissioning | 2010-08-18 08:00 | 2010-10-01 17:00 | 33d |  |  | 11267.1298 |  |  | 167933.8461 |  | 2d | [5 empty] | 16893.1096 |  | 6.289% |  | 10561.9739 | 167933.8461
118 | WEC 1 | 2010-08-18 08:00 | 2010-08-20 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 | 2010-11-25 08:00 | 2d | 16530.2296 | 22380.9595 | 3d | 362.88 | 0 | 16893.1096 | 22380.9595 | 40% | Started | 10561.9739 | 23990.5494 | 100 | 66.6667 | 40 | 100 | 70.4157 | 40
119 | WEC 2 | 2010-08-25 08:00 | 2010-08-27 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
120 | WEC 3 | 2010-09-01 08:00 | 2010-09-03 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
121 | WEC 4 | 2010-09-08 08:00 | 2010-09-10 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
122 | WEC 5 | 2010-09-15 08:00 | 2010-09-17 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
123 | WEC 6 | 2010-09-22 08:00 | 2010-09-24 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
124 | WEC 7 | 2010-09-29 08:00 | 2010-10-01 17:00 | 3d |  | 0 | 1609.59 | 932.54 | 22380.9595 | 23990.5494 |  | 0 | 0 | 23990.5494 | 3d | 0 | 0 | 0 | 23990.5494 | 0% | Not Started | 0 | 23990.5494 | 100 |  | 0 | 100 |  | 0
125 | Trail period 300h | 2010-08-23 08:00 | 2010-10-20 17:00 | 43d |  |  | 48824.231 |  |  | 48824.231 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48824.231
126 | WEC 1 | 2010-08-23 08:00 | 2010-09-08 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
127 | WEC 2 | 2010-08-30 08:00 | 2010-09-15 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
128 | WEC 3 | 2010-09-06 08:00 | 2010-09-22 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
129 | WEC 4 | 2010-09-13 08:00 | 2010-09-29 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
130 | WEC 5 | 2010-09-20 08:00 | 2010-10-06 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
131 | WEC 6 | 2010-09-27 08:00 | 2010-10-13 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
132 | WEC 7 | 2010-10-04 08:00 | 2010-10-20 17:00 | 13d |  | 0 | 6974.8901 | 0 | 0 | 6974.8901 |  | 0 | 0 | 6974.8901 | 13d | 0 | 0 | 0 | 6974.8901 | 0% | Not Started | 0 | 6974.8901 | 100 |  | 0 | 100 |  | 0
133 | 300h Maintenace service | 2010-09-09 08:00 | 2010-10-22 17:00 | 32d |  |  | 7511.4204 |  |  | 164178.147 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 164178.147
134 | WEC 1 | 2010-09-09 08:00 | 2010-09-10 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
135 | WEC 2 | 2010-09-16 08:00 | 2010-09-17 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
136 | WEC 3 | 2010-09-23 08:00 | 2010-09-24 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
137 | WEC 4 | 2010-09-30 08:00 | 2010-10-01 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
138 | WEC 5 | 2010-10-07 08:00 | 2010-10-08 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
139 | WEC 6 | 2010-10-14 08:00 | 2010-10-15 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
140 | WEC 7 | 2010-10-21 08:00 | 2010-10-22 17:00 | 2d |  | 0 | 1073.0601 | 1398.8101 | 22380.9609 | 23454.021 |  | 0 | 0 | 23454.021 | 2d | 0 | 0 | 0 | 23454.021 | 0% | Not Started | 0 | 23454.021 | 100 |  | 0 | 100 |  | 0
141 | Take over | 2010-09-10 17:00 | 2010-10-22 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | WEC 1 | 2010-09-10 17:00 | 2010-09-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | WEC 2 | 2010-09-17 17:00 | 2010-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | WEC 3 | 2010-09-24 17:00 | 2010-09-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | WEC 4 | 2010-10-01 17:00 | 2010-10-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | WEC 5 | 2010-10-08 17:00 | 2010-10-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | WEC 6 | 2010-10-15 17:00 | 2010-10-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | WEC 7 | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Electrical works | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 42d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
150 | Electricity distributor | 2010-04-23 08:00 | 2010-06-04 17:00 | 31d |  |  | 276445.6818 |  |  | 650046.796 |  | 42d | [5 empty] | 676332.715 |  | 100% |  | 650046.796 | 650046.796
151 | Mobilisation to site | 2010-04-23 08:00 | 2010-04-26 17:00 | 2d |  | 0 | 39473.0586 | 600 | 9600 | 49073.0586 | 2010-09-30 08:00 | 2d | 49073.0586 | 0 | 0 | 0 | 0 | 49073.0586 | 0 | 100% | Finished | 49073.0586 | 49073.0586 | 100 | 100 | 100 | 100 | 100 | 100
152 | Excavation for cabin | 2010-04-26 17:00 | 2010-04-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-10-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
153 | Building of the cabin | 2010-04-27 08:00 | 2010-04-27 17:00 | 1d |  | 0 | 100536.5312 | 0 | 0 | 100536.5312 | 2010-10-04 08:00 | 20d | 100536.5312 | 0 | 0 | 160000 | 0 | 260536.5312 | 0 | 100% | Finished | 100536.5312 | 100536.5312 | 100 | 2000 | 100 | 100 | 259.1461 | 100
154 | Excavation for cables | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 7511.4199 | 964.29 | 108000.4775 | 115511.8975 | 2010-10-04 08:00 | 14d | 115511.8975 | 0 | 0 | -54000 | 0 | 61511.8975 | 0 | 100% | Finished | 115511.8975 | 115511.8975 | 100 | 100 | 100 | 100 | 53.2516 | 100
155 | Laying of cables to WEC 1 | 2010-04-27 08:00 | 2010-05-14 17:00 | 14d |  | 0 | 115511.4219 | 964.29 | 108000.4775 | 223511.8994 | 2010-10-04 08:00 | 20d | 269797.8184 | 0 | 0 | -108000 | 0 | 161797.8184 | 0 | 100% | Finished | 223511.8994 | 223511.8994 | 100 | 142.8571 | 100 | 100 | 72.3889 | 100
156 | Sheet test | 2010-05-17 08:00 | 2010-05-21 17:00 | 5d |  | 0 | 8047.9502 | 1000 | 40000 | 48047.9502 | 2010-11-01 08:00 | 5d | 48047.9502 | 0 | 0 | 0 | 0 | 48047.9502 | 0 | 100% | Finished | 48047.9502 | 48047.9502 | 100 | 100 | 100 | 100 | 100 | 100
157 | Electrical connection to Turbines | 2010-05-24 08:00 | 2010-05-26 17:00 | 3d |  | 0 | 1609.59 | 3000 | 72000 | 73609.59 | 2010-11-08 08:00 | 3d | 73609.59 | 0 | 0 | 0 | 0 | 73609.59 | 0 | 100% | Finished | 73609.59 | 73609.59 | 100 | 100 | 100 | 100 | 100 | 100
158 | Test of cables | 2010-05-27 08:00 | 2010-06-04 17:00 | 7d |  | 0 | 3755.71 | 642.86 | 36000.1592 | 39755.8691 | 2010-11-11 08:00 | 7d | 39755.8691 | 0 | 0 | -18000 | 0 | 21755.8691 | 0 | 100% | Finished | 39755.8691 | 39755.8691 | 100 | 100 | 100 | 100 | 54.7237 | 100
159 | Energize | 2010-06-04 17:00 | 2010-06-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Gridconnection | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 216d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
161 | Electricity distributor | 2010-01-28 17:00 | 2010-06-25 17:00 | 106d |  |  | 40239.7295 |  |  | 862738.9385 |  | 216d | [5 empty] | 862738.9385 |  | 100% |  | 862738.9385 | 862738.9385
162 | Order connection | 2010-01-28 17:00 | 2010-01-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Order material | 2010-01-29 08:00 | 2010-03-25 17:00 | 40d |  | 0 | 21461.1895 | 856.77 | 274166.4062 | 295627.5957 | 2010-01-29 08:00 | 40d | 295627.5957 | 0 | 0 | 0 | 0 | 295627.5957 | 0 | 100% | Finished | 295627.5957 | 295627.5957 | 100 | 100 | 100 | 100 | 100 | 100
164 | Lay cable | 2010-03-26 08:00 | 2010-04-22 17:00 | 20d |  | 0 | 10730.5898 | 1713.54 | 274166.4062 | 284896.9961 | 2010-04-30 08:00 | 20d | 284896.9961 | 0 | 0 | 0 | 0 | 284896.9961 | 0 | 100% | Finished | 284896.9961 | 284896.9961 | 100 | 100 | 100 | 100 | 100 | 100
165 | Ready to Energize | 2010-06-07 08:00 | 2010-06-25 17:00 | 15d |  | 0 | 8047.9502 | 2284.72 | 274166.3965 | 282214.3467 | 2010-06-07 08:00 | 15d | 282214.3467 | 0 | 0 | 0 | 0 | 282214.3467 | 0 | 100% | Finished | 282214.3467 | 282214.3467 | 100 | 100 | 100 | 100 | 100 | 100
166 | Finish | 2010-10-22 17:00 | 2010-10-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP111
| TP Status Date | 2010-12-05 17:00 |  | TP Name | 111
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 555d | [5 empty] | 25579090.6647 |  | 98.09% |  | 20961769.2533 | 21369835.5102
1 | Wind Farm | 2008-10-20 08:00 | 2010-10-22 17:00 | 525d |  |  | 13951666.9396 |  |  | 21369835.5102 |  | 555d | [5 empty] | 25579090.6647 |  | 98.09% |  | 20961769.2533 | 21369835.5102
2 | Vergunningen | 2009-02-10 17:00 | 2009-03-02 17:00 | 14d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Milieuvergunning | 2009-02-12 17:00 | 2009-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouwvergunning | 2009-02-10 17:00 | 2009-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | RUP | 2009-03-02 17:00 | 2009-03-02 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | studies | 2008-10-20 08:00 | 2009-11-27 17:00 | 290d |  |  | 272401.3955 |  |  | 309795.0755 |  | 399d | [5 empty] | 308906.7554 |  | 100% |  | 309795.0755 | 309795.0755
7 | sonderingen | 2009-02-05 08:00 | 2009-03-30 17:00 | 38d |  |  | 21988.1396 |  |  | 30387.9796 |  | 38d | [5 empty] | 30387.9796 |  | 100% |  | 30387.9796 | 30387.9796
8 | offerte | 2009-02-05 08:00 | 2009-02-18 17:00 | 10d |  | 0 | 5365.2998 | 12.5 | 1000 | 6365.2998 | 2009-02-05 08:00 | 10d | 6365.2998 | 0 | 0 | 0 | 0 | 6365.2998 | 0 | 100% | Finished | 6365.2998 | 6365.2998 | 100 | 100 | 100 | 100 | 100 | 100
9 | sondering | 2009-02-19 08:00 | 2009-03-10 17:00 | 14d |  | 0 | 9111.4199 | 57.14 | 6399.6799 | 15511.0999 | 2009-02-19 08:00 | 14d | 15511.0999 | 0 | 0 | 0 | 0 | 15511.0999 | 0 | 100% | Finished | 15511.0999 | 15511.0999 | 100 | 100 | 100 | 100 | 100 | 100
10 | sonderingsverslag | 2009-03-11 08:00 | 2009-03-30 17:00 | 14d |  | 0 | 7511.4199 | 8.93 | 1000.16 | 8511.58 | 2009-03-11 08:00 | 14d | 8511.58 | 0 | 0 | 0 | 0 | 8511.58 | 0 | 100% | Finished | 8511.58 | 8511.58 | 100 | 100 | 100 | 100 | 100 | 100
11 | Aansluitingen | 2008-10-20 08:00 | 2009-10-09 17:00 | 255d |  |  | 136815.0723 |  |  | 147808.2721 |  | 239d | [5 empty] | 146919.9521 |  | 100% |  | 147808.2721 | 147808.2721
12 | orientatiestudie | 2008-10-20 08:00 | 2009-03-13 17:00 | 105d |  | 0 | 56335.6211 | 5.95 | 4997.9998 | 61333.6209 | 2008-10-20 08:00 | 105d | 61333.6209 | 0 | 0 | 0 | 0 | 61333.6209 | 0 | 100% | Finished | 61333.6209 | 61333.6209 | 100 | 100 | 100 | 100 | 100 | 100
13 | detailstudie | 2009-03-16 08:00 | 2009-07-17 17:00 | 90d |  | 0 | 48287.6719 | 6.94 | 4996.8 | 53284.4719 | 2009-03-16 08:00 | 74d | 52396.1519 | 0 | 0 | 0 | 0 | 52396.1519 | 0 | 100% | Finished | 53284.4719 | 53284.4719 | 100 | 82.2222 | 100 | 100 | 98.3329 | 100
14 | financieel plan | 2009-07-20 08:00 | 2009-10-09 17:00 | 60d |  | 0 | 32191.7793 | 2.08 | 998.4 | 33190.1793 | 2009-06-26 08:00 | 60d | 33190.1793 | 0 | 0 | 0 | 0 | 33190.1793 | 0 | 100% | Finished | 33190.1793 | 33190.1793 | 100 | 100 | 100 | 100 | 100 | 100
15 | uitvoeringsplan | 2009-03-03 08:00 | 2009-11-27 17:00 | 194d |  |  | 113598.1836 |  |  | 131598.8237 |  | 303d | [5 empty] | 131598.8237 |  | 100% |  | 131598.8237 | 131598.8237
16 | roads and hardstands | 2009-03-16 08:00 | 2009-04-02 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-16 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
17 | contracten | 2009-03-03 08:00 | 2009-03-20 17:00 | 14d |  | 0 | 7511.4199 | 80.36 | 9000.3201 | 16511.74 | 2009-03-03 08:00 | 14d | 16511.74 | 0 | 0 | 0 | 0 | 16511.74 | 0 | 100% | Finished | 16511.74 | 16511.74 | 100 | 100 | 100 | 100 | 100 | 100
18 | extra vergunningen | 2009-03-23 08:00 | 2009-11-27 17:00 | 180d |  | 0 | 98575.3438 | 0 | 0 | 98575.3438 | 2010-01-29 08:00 | 65d | 98575.3438 | 0 | 0 | 0 | 0 | 98575.3438 | 0 | 100% | Finished | 98575.3438 | 98575.3438 | 100 | 36.1111 | 100 | 100 | 100 | 100
19 | preconstruction | 2009-02-12 08:00 | 2010-01-27 17:00 | 250d |  |  | 162876.7227 |  |  | 1216717.082 |  | 316d | [5 empty] | 3409634.9854 |  | 100% |  | 1216717.082 | 1216717.082
20 | Roads and hardstands | 2010-01-08 08:00 | 2010-01-27 17:00 | 14d |  | 0 | 107511.4219 | 8962.8604 | 1003840.3594 | 1111351.7812 | 2010-03-01 08:00 | 44d | 3262438.2656 | 0 | 0 | 27847.0391 | 0 | 3290285.3047 | 0 | 100% | Finished | 1111351.7812 | 1111351.7812 | 100 | 314.2857 | 100 | 100 | 296.0615 | 100
21 | Mark NMP pipe | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2009-02-12 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
22 | Mark NMP pipe | 2010-01-01 08:00 | 2010-01-07 17:00 | 5d |  | 0 | 27682.6504 | 625 | 25000 | 52682.6504 | 2010-02-22 08:00 | 5d | 52682.6504 | 0 | 0 | 6992.1899 | 0 | 59674.8403 | 0 | 100% | Finished | 52682.6504 | 52682.6504 | 100 | 100 | 100 | 100 | 113.2723 | 100
23 | Foundations | 2010-01-28 08:00 | 2010-08-25 17:00 | 150d |  |  | 629507.9465 |  |  | 1546009.5554 |  | 140d | [5 empty] | 1604471.7454 |  | 100% |  | 1546009.5554 | 1546009.5554
24 | settlement on construction site | 2010-01-28 08:00 | 2010-02-03 17:00 | 5d |  | 0 | 2682.6499 | 0 | 0 | 2682.6499 | 2010-03-08 08:00 | 5d | 2682.6499 | 0 | 0 | 101.44 | 0 | 2784.0899 | 0 | 100% | Finished | 2682.6499 | 2682.6499 | 100 | 100 | 100 | 100 | 103.7813 | 100
25 | Piling | 2010-02-04 08:00 | 2010-07-07 17:00 | 110d |  |  | 155682.2422 |  |  | 508182.6572 |  | 35d | [5 empty] | 527399.5474 |  | 100% |  | 508182.6572 | 508182.6572
26 | foundation 1 | 2010-02-04 08:00 | 2010-02-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-15 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
27 | foundation 2 | 2010-02-18 08:00 | 2010-02-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-22 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
28 | foundation 3 | 2010-03-04 08:00 | 2010-03-10 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-03-29 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
29 | foundation 4 | 2010-03-18 08:00 | 2010-03-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-05 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
30 | foundation 5 | 2010-05-18 08:00 | 2010-05-24 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-12 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
31 | foundation 6 | 2010-06-09 08:00 | 2010-06-15 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-19 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
32 | foundation 7 | 2010-07-01 08:00 | 2010-07-07 17:00 | 5d |  | 0 | 22240.3203 | 1258.9301 | 50357.2021 | 72597.5225 | 2010-04-26 08:00 | 5d | 72597.5225 | 0 | 0 | 2745.27 | 0 | 75342.7925 | 0 | 100% | Finished | 72597.5225 | 72597.5225 | 100 | 100 | 100 | 100 | 103.7815 | 100
33 | Concrete works foundations | 2010-02-11 08:00 | 2010-07-28 17:00 | 120d |  |  | 471142.9844 |  |  | 1035144.1782 |  | 105d | [5 empty] | 1074288.0381 |  | 100% |  | 1035144.1782 | 1035144.1782
34 | foundation 1 | 2010-02-11 08:00 | 2010-03-03 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-03-29 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
35 | foundation 2 | 2010-02-25 08:00 | 2010-03-17 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-04-19 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
36 | foundation 3 | 2010-03-11 08:00 | 2010-03-31 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-10 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
37 | foundation 4 | 2010-03-25 08:00 | 2010-04-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-05-31 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100
38 | foundation 5 | 2010-05-25 08:00 | 2010-06-14 17:00 | 15d |  | 0 | 67306.1406 | 671.43 | 80571.5991 | 147877.7397 | 2010-06-21 08:00 | 15d | 147877.7397 | 0 | 0 | 5591.98 | 0 | 153469.7197 | 0 | 100% | Finished | 147877.7397 | 147877.7397 | 100 | 100 | 100 | 100 | 103.7815 | 100