## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | The Master Project | 1 |  |  | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 | 46.5
1 | X Course strategic management | 1.1 |  |  | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 0.16667
2 | A Course Marketing communications | 1.2 |  |  | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 0.125
3 | X Groupwork strategic management | 1.3 |  | FS15 | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 0.625
4 | S Groupwork FEC | 1.4 |  | FS23 | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 0.083333
6 | E Course B2B | 1.5 |  |  | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 0.125
7 | X Groupwork Projectmanagement | 1.6 |  | FS25 | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 0.625
8 | E Course CRM | 1.7 |  |  | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 0.16667
9 | E Groupwork B2B | 1.8 |  | FS33 | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 0.125
10 | A Groupwork Research Methods | 1.9 |  | FS20 | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 0.16667
11 | X Course Projectmanagement | 1.10 |  |  | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 0.16667
12 | A Course research methods | 1.11 |  |  | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 0.083333
13 | E Groupwork Service Management | 1.12 |  | FS26 | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 0.16667
14 | S Course FEC | 1.13 |  |  | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 0.16667
15 | X Deadline 1 Strategic management | 1.14 | 3FS | FS22 | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
16 | X Course strategic management | 1.15 |  |  | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 0.16667
17 | A Course Marketing Communications | 1.16 |  |  | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 0.125
18 | S Course B2B | 1.17 |  |  | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 0.041667
19 | A Course Research methods | 1.18 |  |  | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 0.083333
20 | A Groupwork Research methods | 1.19 | 10FS | FS24 | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 0.125
21 | E Exam CRM | 1.20 |  |  | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 0.16667
22 | X Groupwork Strategic management | 1.21 | 15FS | FS29 | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 0.125
23 | S Groupwork FEC | 1.22 | 4FS | FS47 | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 0.083333
24 | A Groupwork research methods | 1.23 | 20FS | FS70 | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 0.16667
25 | X Groupwork Project management | 1.24 | 7FS | FS43 | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 0.125
26 | E Groupwork Service management | 1.25 | 13FS | FS63 | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 0.16667
28 | S Course FEC | 1.26 |  |  | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 0.16667
29 | X Deadline 2 Strategic management | 1.27 | 22FS | FS34 | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
30 | A Course Research Methods | 1.28 |  |  | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 0.16667
31 | E+S Course systeemdynamica | 1.29 |  |  | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 0.16667
32 | E Course Service Management | 1.30 |  |  | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 0.083333
33 | E Groupwork B2B | 1.31 | 9FS | FS36 | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 0.083333
34 | X Group work strategisch management | 1.32 | 29FS | FS41 | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 0.625
36 | E Group work B2B | 1.33 | 33FS | FS40 | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 0.16667
37 | S Group work B2B | 1.34 |  | FS74 | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 0.20833
38 | X Course Strategisch management | 1.35 |  |  | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 0.16667
39 | A Course research methods | 1.36 |  |  | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 0.16667
40 | E Groupwork B2B | 1.37 | 36FS | FS53 | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 0.58333
41 | X Deadline 3 | 1.38 | 34FS | FS44 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
42 | A Groupwork Marketing Communications | 1.39 |  | FS62 | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 0.041667
43 | X Groupwork Project Management | 1.40 | 25FS | FS54 | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 0.625
44 | X Groupwork Strategic Management | 1.41 | 41FS | FS46 | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 0.041667
45 | E Course CRM | 1.42 |  |  | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 0.16667
46 | X Deadline 4 | 1.43 | 44FS | FS49 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
47 | S Groupwork FEC | 1.44 | 23FS | FS73 | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 0.125
48 | X Course Project Management | 1.45 |  |  | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 0.16667
49 | X Group Work Strategic Management | 1.46 | 46FS | FS52 | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 0.083333
50 | E Group Work Service Management | 1.47 |  |  | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 0.125
51 | S Course FEC | 1.48 |  |  | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 0.16667
52 | X Deadline 5 | 1.49 | 49FS | FS57 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
53 | E Group Work B2B | 1.50 | 40FS | FS71 | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 0.66667
54 | X Group Work Project Management | 1.51 | 43FS | FS59 | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 0.25
55 | X Course Strategic Management | 1.52 |  |  | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 0.16667
56 | A Course Marketing Communications | 1.53 |  |  | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 0.125
57 | X Group Work Strategic Management | 1.54 | 52FS | FS64 | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 0.125
58 | S Course B2B | 1.55 |  |  | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 | 0.125
59 | X Group Work Project Management | 1.56 | 54FS | FS69 | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 0.70833
60 | E Course CRM | 1.57 |  |  | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 0.16667
61 | X Course Project Management | 1.58 |  |  | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 0.16667
62 | A Group Work Marketing Communications | 1.59 | 42FS | FS77 | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 0.083333
63 | E Group Work Service Management | 1.60 | 26FS | FS68 | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 0.125
64 | Deadline 6 | 1.61 | 57FS | FS80 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
65 | S Course FEC | 1.62 |  |  | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 0.16667
66 | A Course Research Methods | 1.63 |  |  | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 0.083333
67 | E+S Course Systeemdynamica | 1.64 |  |  | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 0.16667
68 | E Group Work Service Management | 1.65 | 63FS | FS92 | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 0.083333
69 | X Group Work Project Management | 1.66 | 59FS | FS72 | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 0.083333
70 | A Group Work Research Methods | 1.67 | 24FS | FS87 | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 0.125
71 | E Group Work B2B | 1.68 | 53FS | FS93 | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2.6667
72 | X Group Work Project Management | 1.69 | 69FS | FS84 | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 0.083333
73 | S Group Work FEC | 1.70 | 47FS | FS82 | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 0.125
74 | S Group Work B2B | 1.71 | 37FS | FS94 | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 0.125
75 | X Course Strategic Management | 1.72 |  |  | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 0.16667
77 | A Group Work Marketing Communications | 1.73 | 62FS | FS97 | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 0.125
79 | A Course Marketing Communications | 1.74 |  |  | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 0.125
80 | X Group Work Strategic Management | 1.75 | 64FS | FS85 | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 0.083333
81 | E Course CRM | 1.76 |  |  | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 0.16667
82 | S Group Work FEC | 1.77 | 73FS |  | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 0.25
83 | S Course FEC | 1.78 |  |  | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 0.16667
84 | X Group Work Project Management | 1.79 | 72FS | FS91 | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 0.75
85 | X Deadline 7 | 1.80 | 80FS | FS102 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
86 | A Course Research Methods | 1.81 |  |  | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 0.16667
87 | A Group Work Research Methods | 1.82 | 70FS | FS100 | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 0.16667
88 | E+S Course Systeemdynamica | 1.83 |  |  | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 0.16667
89 | E Course Service Management | 1.84 |  |  | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 0.083333
91 | X Group Work Project Management | 1.85 | 84FS | FS101 | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 0.083333
92 | E Group Work Service Management | 1.86 | 68FS | FS106 | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 0.125
93 | E Group Work B2B | 1.87 | 71FS | FS98 | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 0.16667
94 | S Group Work B2B | 1.88 | 74FS | FS99 | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 0.66667
95 | X Course Strategic Management | 1.89 |  |  | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 0.16667
96 | A Course Marketing Communications | 1.90 |  |  | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 0.125
97 | A Group Work Marketing Communications | 1.91 | 77FS | FS113 | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 0.083333
98 | E Group Work B2B | 1.92 | 93FS | FS137 | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 0.66667
99 | S Group Work B2B | 1.93 | 94FS | FS115 | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 0.16667
100 | A Group Work Research Methods | 1.94 | 87FS | FS111 | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 0.125
101 | X Group Work Project Management | 1.95 | 91FS | FS112 | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 0.20833
102 | X Group Work Strategic Management | 1.96 | 85FS | FS104 | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 0.083333
103 | E Exam SAS | 1.97 |  |  | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 0.083333
104 | X Deadline 8 | 1.98 | 102FS | FS114 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
105 | X Course Project Management | 1.99 |  |  | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 0.16667
106 | E Group Work Service Management | 1.100 | 92FS | FS136 | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 0.16667
107 | S Course FEC | 1.101 |  |  | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 | 0.16667
108 | A Course Research Methods | 1.102 |  |  | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 0.083333
109 | E+S Course Systeemdynamica | 1.103 |  |  | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 0.16667
110 | E Course Service Management | 1.104 |  |  | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 0.16667
111 | A Group Work Research Methods | 1.105 | 100FS | FS126 | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 0.20833
112 | X Group Work Project Management | 1.106 | 101FS | FS120 | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2.6667
113 | A Group Work Marketing Communications | 1.107 | 97FS | FS125 | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 0.58333
114 | X Group Work Strategic Management | 1.108 | 104FS | FS116 | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 0.083333
115 | S Group Work B2B | 1.109 | 99FS | FS127 | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 0.16667
116 | X Deadline 9 | 1.110 | 114FS | FS119 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
117 | X Course Strategic Management | 1.111 |  |  | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 0.16667
118 | A Course Marketing Communications | 1.112 |  |  | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 | 0.041667
119 | X Group Work Strategic Management | 1.113 | 116FS | FS121 | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 0.041667
120 | X Group Work Project Management | 1.114 | 112FS | FS124 | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 0.70833
121 | X Deadline 10 | 1.115 | 119FS | FS123 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
122 | E Course CRM | 1.116 |  |  | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 0.16667
123 | X Group Work Strategic Management | 1.117 | 121FS | FS128 | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 0.041667
124 | X Group Work Project Management | 1.118 | 120FS | FS133 | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 0.16667
125 | A Group Work Marketing Communications | 1.119 | 113FS |  | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 0.041667
126 | A Group Work Research Methods | 1.120 | 111FS | FS130 | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 0.125
127 | S Group Work B2B | 1.121 | 115FS |  | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 0.083333
128 | X Deadline 11 | 1.122 | 123FS | FS131 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
129 | S Course FEC | 1.123 |  |  | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 0.16667
130 | A Group Work Research Methods | 1.124 | 126FS |  | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 0.125
131 | X Group Work Strategic Management | 1.125 | 128FS | FS132 | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 0.041667
132 | X Deadline 12 | 1.126 | 131FS | FS139 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
133 | X Presentation Project Management | 1.127 | 124FS |  | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 | 0.041667
134 | A Course Research Methods | 1.128 |  |  | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 0.16667
135 | E+S Course Systeemdynamica | 1.129 |  |  | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 0.16667
136 | E Presentation Service Management | 1.130 | 106FS |  | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 0.083333
137 | E Group Work B2B | 1.131 | 98FS |  | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 0.125
138 | E Exam CRM | 1.132 |  |  | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 0.16667
139 | X Group Work Strategic Management | 1.133 | 132FS | FS140 | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 0.083333
140 | X Deadline 13 | 1.134 | 139FS |  | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Ann-Sophie | Renewable | 1 #Ann-Sophie | 0 | 0 | 1;2;3;7;10;11;12;16;17;19;20;22;24;25;30;34;38;39;42;43;44;48;49;54;55;56;57;59;61;62;66;69;70;72;75;77;79;80;84;86;87;91;95;96;97;100;101;102;105;108;111;112;113;114;117;118;119;120;123;124;125;126;130;131;133;134;139; | 0
2 | Sanne | Renewable | 1 #Sanne | 0 | 0 | 1;3;4;7;11;14;16;18;22;23;25;28;31;34;37;38;43;44;47;48;49;51;54;55;57;58;59;61;65;67;69;72;73;74;75;80;82;83;84;88;91;94;95;99;101;102;105;107;109;112;114;115;117;119;120;123;124;127;129;131;133;135;139; | 0
3 | Eline | Renewable | 1 #Eline | 0 | 0 | 1;3;6;7;8;9;11;13;16;21;22;25;26;31;32;33;34;36;38;40;43;44;45;48;49;50;53;54;55;57;59;60;61;63;67;68;69;71;72;75;80;81;84;88;89;91;92;93;95;98;101;102;103;105;106;109;110;112;114;117;119;120;122;123;124;131;133;135;136;137;138;139; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | The Master Project | 352h |  |  |  |  | 99 | 100 | 101
1 | X Course strategic management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
2 | A Course Marketing communications | 3h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
3 | X Groupwork strategic management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | S Groupwork FEC | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | E Course B2B | 3h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
7 | X Groupwork Projectmanagement | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | E Course CRM | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | E Groupwork B2B | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | A Groupwork Research Methods | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | X Course Projectmanagement | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | A Course research methods | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
13 | E Groupwork Service Management | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | S Course FEC | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
15 | X Deadline 1 Strategic management | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
16 | X Course strategic management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
17 | A Course Marketing Communications | 3h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
18 | S Course B2B | 1h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
19 | A Course Research methods | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
20 | A Groupwork Research methods | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | E Exam CRM | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
22 | X Groupwork Strategic management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | S Groupwork FEC | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | A Groupwork research methods | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | X Groupwork Project management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | E Groupwork Service management | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | S Course FEC | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
29 | X Deadline 2 Strategic management | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
30 | A Course Research Methods | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
31 | E+S Course systeemdynamica | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
32 | E Course Service Management | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
33 | E Groupwork B2B | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | X Group work strategisch management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | E Group work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | S Group work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | X Course Strategisch management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
39 | A Course research methods | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
40 | E Groupwork B2B | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | X Deadline 3 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
42 | A Groupwork Marketing Communications | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | X Groupwork Project Management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | X Groupwork Strategic Management | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | E Course CRM | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
46 | X Deadline 4 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
47 | S Groupwork FEC | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | X Course Project Management | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
49 | X Group Work Strategic Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | E Group Work Service Management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | S Course FEC | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
52 | X Deadline 5 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
53 | E Group Work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | X Group Work Project Management | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | X Course Strategic Management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
56 | A Course Marketing Communications | 3h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
57 | X Group Work Strategic Management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | S Course B2B | 3h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
59 | X Group Work Project Management | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | E Course CRM | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
61 | X Course Project Management | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
62 | A Group Work Marketing Communications | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | E Group Work Service Management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Deadline 6 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
65 | S Course FEC | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
66 | A Course Research Methods | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
67 | E+S Course Systeemdynamica | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
68 | E Group Work Service Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | X Group Work Project Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | A Group Work Research Methods | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | E Group Work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | X Group Work Project Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | S Group Work FEC | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | S Group Work B2B | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | X Course Strategic Management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
77 | A Group Work Marketing Communications | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | A Course Marketing Communications | 3h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
80 | X Group Work Strategic Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | E Course CRM | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
82 | S Group Work FEC | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | S Course FEC | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
84 | X Group Work Project Management | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | X Deadline 7 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
86 | A Course Research Methods | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
87 | A Group Work Research Methods | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | E+S Course Systeemdynamica | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
89 | E Course Service Management | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
91 | X Group Work Project Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | E Group Work Service Management | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | E Group Work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | S Group Work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | X Course Strategic Management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
96 | A Course Marketing Communications | 3h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
97 | A Group Work Marketing Communications | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | E Group Work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | S Group Work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | A Group Work Research Methods | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | X Group Work Project Management | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | X Group Work Strategic Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | E Exam SAS | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
104 | X Deadline 8 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
105 | X Course Project Management | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
106 | E Group Work Service Management | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | S Course FEC | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
108 | A Course Research Methods | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
109 | E+S Course Systeemdynamica | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
110 | E Course Service Management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
111 | A Group Work Research Methods | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | X Group Work Project Management | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | A Group Work Marketing Communications | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | X Group Work Strategic Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | S Group Work B2B | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | X Deadline 9 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
117 | X Course Strategic Management | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
118 | A Course Marketing Communications | 1h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
119 | X Group Work Strategic Management | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | X Group Work Project Management | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | X Deadline 10 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
122 | E Course CRM | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
123 | X Group Work Strategic Management | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | X Group Work Project Management | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | A Group Work Marketing Communications | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | A Group Work Research Methods | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | S Group Work B2B | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | X Deadline 11 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
129 | S Course FEC | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
130 | A Group Work Research Methods | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | X Group Work Strategic Management | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | X Deadline 12 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
133 | X Presentation Project Management | 1h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
134 | A Course Research Methods | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
135 | E+S Course Systeemdynamica | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
136 | E Presentation Service Management | 2h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
137 | E Group Work B2B | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | E Exam CRM | 4h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
139 | X Group Work Strategic Management | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | X Deadline 13 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101

## Project Control - TP1
| TP Status Date | 2012-11-06 20:00 |  | TP Name | 6/11/2012 20:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 5d | [5 empty] | 32541.39 |  | 17.65% |  | 32739.95 | 31498.18
1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 10 | 10 | 100 | 150 | 100 | 100 | 150 | 100
6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 420 | 420 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 64 | 64 | 100 | 100 | 100 | 100 | 100 | 100
11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 27.84 | 0 | 100 | 75 | 100 | 100 | 75 | 100
14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 100% | Finished | 105 | 105 | 100 | 100 | 100 | 100 | 100 | 100
19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 0 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 100% | Finished | 10 | 10 | 100 | 50 | 100 | 100 | 50 | 100
24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 0 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 27.84 | 0 | 100 | 50 | 100 | 100 | 50 | 100
28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 |  | 0 | 0 | 60 | 2h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 |  | 0 | 0 | 10021.6 | 3h | 0 | 0 | 0 | 10021.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 100% | Finished | 24 | 0 | 100 | 150 | 100 | 100 | 150 | 100
37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 100 | 100 | 100 | 100 | 100
38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 0 | 100 | 100 | 100 | 100 | 100 | 100
41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 12.5 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 20.88 | 0 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | Finished | 24 | 0 | 100 | 100 | 100 | 100 | 100 | 100
54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 0 | 100 | 60 | 100 | 100 | 60 | 100
55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 |  | 0 | 0 | 10021.6 | 3h | 0 | 0 | 0 | 10021.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 |  | 0 | 0 | 315 | 3h | 0 | 0 | 0 | 315 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 0 | 100 | 60 | 100 | 100 | 60 | 100
60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 20.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 13.92 | 0 | 100 | 150 | 100 | 100 | 150 | 100
69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 100% | Finished | 12.5 | 0 | 100 | 50 | 100 | 100 | 50 | 100
70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 0 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 24 | 0 | 100 | 75 | 100 | 100 | 75 | 100
72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 0 | 100 | 100 | 100 | 100 | 100 | 100
73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 100% | Finished | 15 | 15 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 25.71 | 0 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 100% | Finished | 30 | 0 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 37.5 | 0 | 100 | 50 | 100 | 100 | 50 | 100
85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 0 | 100 | 125 | 100 | 100 | 125 | 100
88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 |  | 0 | 0 | 60 | 2h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 0 | 100 | 100 | 100 | 100 | 100 | 100
92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 20.88 | 0 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 24 | 0 | 100 | 125 | 100 | 100 | 125 | 100
94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 0 | 100 | 50 | 100 | 100 | 50 | 100
95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 24 | 0 | 100 | 50 | 100 | 100 | 50 | 100
99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 0 | 100 | 50 | 100 | 100 | 50 | 100
100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 0 | 100 | 100 | 100 | 100 | 100 | 100
101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 27.84 | 0 | 100 | 100 | 100 | 100 | 100 | 100
107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 |  | 0 | 0 | 20 | 4h | 0 | 0 | 0 | 20 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 0 | 100 | 125 | 100 | 100 | 125 | 100
112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 100% | Finished | 25 | 0 | 100 | 125 | 100 | 100 | 125 | 100
113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 0 | 100 | 100 | 100 | 100 | 100 | 100
114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 100% | Finished | 34.28 | 0 | 100 | 75 | 100 | 100 | 75 | 100
116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 |  | 0 | 0 | 18.75 | 1h | 0 | 0 | 0 | 18.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 31.25 | 0 | 100 | 80 | 100 | 100 | 80 | 100
121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 0 | 100 | 100 | 100 | 100 | 100 | 100
126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 0 | 100 | 100 | 100 | 100 | 100 | 100
127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 17.14 | 0 | 100 | 100 | 100 | 100 | 100 | 100
128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 0 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 1h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 0 | 100 | 100 | 100 | 100 | 100 | 100
138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 4h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-11-13 20:00 |  | TP Name | 13/11/2012 20:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 10d | [5 empty] | 52960.45 |  | 28.68% |  | 53191.43 | 52845.68
1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 10 | 10 | 100 | 150 | 100 | 100 | 150 | 100
6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 420 | 420 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 64 | 64 | 100 | 100 | 100 | 100 | 100 | 100
11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 75 | 100 | 100 | 75 | 100
14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 100% | Finished | 105 | 105 | 100 | 100 | 100 | 100 | 100 | 100
19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 100% | Finished | 10 | 10 | 100 | 50 | 100 | 100 | 50 | 100
24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 50 | 100 | 100 | 50 | 100
28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-07 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-08 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-08 09:00 | 2h | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 100% | Finished | 100 | 100 | 100 | 50 | 100 | 100 | 50 | 100
32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-08 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-08 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 100% | Finished | 24 | 24 | 100 | 150 | 100 | 100 | 150 | 100
37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 100 | 100 | 100 | 100 | 100
38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-12 09:00 | 3h | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 100% | Finished | 60 | 60 | 100 | 75 | 100 | 100 | 75 | 100
39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-12 14:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 75 | 100 | 100 | 75 | 100
40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-11-13 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-13 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | Finished | 24 | 12 | 100 | 100 | 100 | 100 | 100 | 100
54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 0 | 100 | 60 | 100 | 100 | 60 | 100
55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 |  | 0 | 0 | 10021.6 | 3h | 0 | 0 | 0 | 10021.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 |  | 0 | 0 | 315 | 3h | 0 | 0 | 0 | 315 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 0 | 100 | 60 | 100 | 100 | 60 | 100
60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 13.92 | 13.92 | 100 | 150 | 100 | 100 | 150 | 100
69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 100% | Finished | 12.5 | 0 | 100 | 50 | 100 | 100 | 50 | 100
70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 24 | 0 | 100 | 75 | 100 | 100 | 75 | 100
72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 0 | 100 | 100 | 100 | 100 | 100 | 100
73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 100% | Finished | 15 | 15 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 25.71 | 25.71 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 100% | Finished | 30 | 30 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 37.5 | 0 | 100 | 50 | 100 | 100 | 50 | 100
85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 |  | 0 | 0 | 60 | 2h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 0 | 100 | 100 | 100 | 100 | 100 | 100
92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 24 | 0 | 100 | 125 | 100 | 100 | 125 | 100
94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 24 | 0 | 100 | 50 | 100 | 100 | 50 | 100
99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 100 | 100 | 100 | 100 | 100
107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 |  | 0 | 0 | 20 | 4h | 0 | 0 | 0 | 20 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 100% | Finished | 25 | 0 | 100 | 125 | 100 | 100 | 125 | 100
113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 75 | 100 | 100 | 75 | 100
116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 |  | 0 | 0 | 18.75 | 1h | 0 | 0 | 0 | 18.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 31.25 | 0 | 100 | 80 | 100 | 100 | 80 | 100
121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 17.14 | 17.14 | 100 | 100 | 100 | 100 | 100 | 100
128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 1h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 0 | 100 | 100 | 100 | 100 | 100 | 100
138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 4h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-11-21 20:00 |  | TP Name | 21/11/2012 20:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 15d | [5 empty] | 73627.89 |  | 39.91% |  | 74020.12 | 73821.87
1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 10 | 10 | 100 | 150 | 100 | 100 | 150 | 100
6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 420 | 420 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 64 | 64 | 100 | 100 | 100 | 100 | 100 | 100
11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 75 | 100 | 100 | 75 | 100
14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 100% | Finished | 105 | 105 | 100 | 100 | 100 | 100 | 100 | 100
19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 100% | Finished | 10 | 10 | 100 | 50 | 100 | 100 | 50 | 100
24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 50 | 100 | 100 | 50 | 100
28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-07 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-08 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-08 09:00 | 2h | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 100% | Finished | 100 | 100 | 100 | 50 | 100 | 100 | 50 | 100
32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-08 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-08 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 100% | Finished | 24 | 24 | 100 | 150 | 100 | 100 | 150 | 100
37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 100 | 100 | 100 | 100 | 100
38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-12 09:00 | 3h | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 100% | Finished | 60 | 60 | 100 | 75 | 100 | 100 | 75 | 100
39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-12 14:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 75 | 100 | 100 | 75 | 100
40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-11-13 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-13 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-14 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-14 08:00 | 2h | 10014.4 | 0 | 0 | 0 | 0 | 10014.4 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 100 | 100 | 100 | 100 | 100
50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-14 09:00 | 6h | 68.58 | 0 | 0 | 0 | 0 | 68.58 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 150 | 100 | 100 | 150 | 100
52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | Finished | 24 | 24 | 100 | 100 | 100 | 100 | 100 | 100
54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-19 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-19 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-16 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 100 | 100 | 100 | 100 | 100
58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 | 2012-11-19 14:00 | 2h | 210 | 0 | 0 | 0 | 0 | 210 | 0 | 100% | Finished | 315 | 315 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-20 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-21 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-21 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 13.92 | 13.92 | 100 | 150 | 100 | 100 | 150 | 100
69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 50 | 100 | 100 | 50 | 100
70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 24 | 24 | 100 | 75 | 100 | 100 | 75 | 100
72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 100% | Finished | 15 | 15 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 25.71 | 25.71 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 100% | Finished | 30 | 30 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 37.5 | 0 | 100 | 50 | 100 | 100 | 50 | 100
85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 |  | 0 | 0 | 60 | 2h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 0 | 100 | 100 | 100 | 100 | 100 | 100
92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 24 | 24 | 100 | 125 | 100 | 100 | 125 | 100
94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 24 | 0 | 100 | 50 | 100 | 100 | 50 | 100
99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 100 | 100 | 100 | 100 | 100
107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 |  | 0 | 0 | 20 | 4h | 0 | 0 | 0 | 20 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 100% | Finished | 25 | 0 | 100 | 125 | 100 | 100 | 125 | 100
113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 75 | 100 | 100 | 75 | 100
116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 |  | 0 | 0 | 18.75 | 1h | 0 | 0 | 0 | 18.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 31.25 | 0 | 100 | 80 | 100 | 100 | 80 | 100
121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 0 | 100 | 100 | 100 | 100 | 100 | 100
125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 17.14 | 17.14 | 100 | 100 | 100 | 100 | 100 | 100
128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 1h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 0 | 100 | 100 | 100 | 100 | 100 | 100
138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 4h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2012-11-28 20:00 |  | TP Name | 28/11/2012 20:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 20d | [5 empty] | 84026.95 |  | 45.52% |  | 84425.73 | 84425.73
1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 10 | 10 | 100 | 150 | 100 | 100 | 150 | 100
6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 420 | 420 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 64 | 64 | 100 | 100 | 100 | 100 | 100 | 100
11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 75 | 100 | 100 | 75 | 100
14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 100% | Finished | 105 | 105 | 100 | 100 | 100 | 100 | 100 | 100
19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 100% | Finished | 10 | 10 | 100 | 50 | 100 | 100 | 50 | 100
24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 50 | 100 | 100 | 50 | 100
28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-07 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-08 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-08 09:00 | 2h | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 100% | Finished | 100 | 100 | 100 | 50 | 100 | 100 | 50 | 100
32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-08 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-08 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 100% | Finished | 24 | 24 | 100 | 150 | 100 | 100 | 150 | 100
37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 100 | 100 | 100 | 100 | 100
38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-12 09:00 | 3h | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 100% | Finished | 60 | 60 | 100 | 75 | 100 | 100 | 75 | 100
39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-12 14:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 75 | 100 | 100 | 75 | 100
40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-11-13 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-13 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-14 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-14 08:00 | 2h | 10014.4 | 0 | 0 | 0 | 0 | 10014.4 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 100 | 100 | 100 | 100 | 100
50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-14 09:00 | 6h | 68.58 | 0 | 0 | 0 | 0 | 68.58 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 150 | 100 | 100 | 150 | 100
52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | Finished | 24 | 24 | 100 | 100 | 100 | 100 | 100 | 100
54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-19 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-19 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-16 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 100 | 100 | 100 | 100 | 100
58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 | 2012-11-19 14:00 | 2h | 210 | 0 | 0 | 0 | 0 | 210 | 0 | 100% | Finished | 315 | 315 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-20 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-21 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-21 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-22 10:00 | 2h | 9.24 | 0 | 0 | 0 | 0 | 9.24 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 100 | 100 | 100 | 100 | 100
67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-22 09:00 | 3h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 100 | 100 | 100 | 75 | 100 | 100 | 75 | 100
68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 13.92 | 13.92 | 100 | 150 | 100 | 100 | 150 | 100
69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 50 | 100 | 100 | 50 | 100
70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 24 | 24 | 100 | 75 | 100 | 100 | 75 | 100
72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 100% | Finished | 15 | 15 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 25.71 | 25.71 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-26 09:00 | 6h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-26 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-22 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 150 | 100 | 100 | 100.0719 | 100
81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-27 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 100% | Finished | 30 | 30 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-28 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 37.5 | 37.5 | 100 | 50 | 100 | 100 | 50 | 100
85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 |  | 0 | 0 | 60 | 2h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 24 | 24 | 100 | 125 | 100 | 100 | 125 | 100
94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 |  | 0 | 0 | 56.25 | 3h | 0 | 0 | 0 | 56.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 24 | 24 | 100 | 50 | 100 | 100 | 50 | 100
99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 |  | 0 | 0 | 75 | 4h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 100 | 100 | 100 | 100 | 100
107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 |  | 0 | 0 | 20 | 4h | 0 | 0 | 0 | 20 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 100% | Finished | 25 | 25 | 100 | 125 | 100 | 100 | 125 | 100
113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 75 | 100 | 100 | 75 | 100
116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 |  | 0 | 0 | 18.75 | 1h | 0 | 0 | 0 | 18.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 80 | 100 | 100 | 80 | 100
121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 17.14 | 17.14 | 100 | 100 | 100 | 100 | 100 | 100
128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 1h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 4h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-12-05 20:00 |  | TP Name | 5/12/2012 20:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 25d | [5 empty] | 114487.33 |  | 61.92% |  | 114844.26 | 114844.26
1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 10 | 10 | 100 | 150 | 100 | 100 | 150 | 100
6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 420 | 420 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 64 | 64 | 100 | 100 | 100 | 100 | 100 | 100
11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 75 | 100 | 100 | 75 | 100
14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 100% | Finished | 105 | 105 | 100 | 100 | 100 | 100 | 100 | 100
19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 100% | Finished | 10 | 10 | 100 | 50 | 100 | 100 | 50 | 100
24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 50 | 100 | 100 | 50 | 100
28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-07 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-08 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-08 09:00 | 2h | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 100% | Finished | 100 | 100 | 100 | 50 | 100 | 100 | 50 | 100
32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-08 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-08 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 100% | Finished | 24 | 24 | 100 | 150 | 100 | 100 | 150 | 100
37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 100 | 100 | 100 | 100 | 100
38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-12 09:00 | 3h | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 100% | Finished | 60 | 60 | 100 | 75 | 100 | 100 | 75 | 100
39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-12 14:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 75 | 100 | 100 | 75 | 100
40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-11-13 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-13 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-14 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-14 08:00 | 2h | 10014.4 | 0 | 0 | 0 | 0 | 10014.4 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 100 | 100 | 100 | 100 | 100
50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-14 09:00 | 6h | 68.58 | 0 | 0 | 0 | 0 | 68.58 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 150 | 100 | 100 | 150 | 100
52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | Finished | 24 | 24 | 100 | 100 | 100 | 100 | 100 | 100
54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-19 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-19 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-16 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 100 | 100 | 100 | 100 | 100
58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 | 2012-11-19 14:00 | 2h | 210 | 0 | 0 | 0 | 0 | 210 | 0 | 100% | Finished | 315 | 315 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-20 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-21 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-21 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-22 10:00 | 2h | 9.24 | 0 | 0 | 0 | 0 | 9.24 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 100 | 100 | 100 | 100 | 100
67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-22 09:00 | 3h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 100 | 100 | 100 | 75 | 100 | 100 | 75 | 100
68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 13.92 | 13.92 | 100 | 150 | 100 | 100 | 150 | 100
69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 50 | 100 | 100 | 50 | 100
70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 24 | 24 | 100 | 75 | 100 | 100 | 75 | 100
72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 100% | Finished | 15 | 15 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 25.71 | 25.71 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-26 09:00 | 6h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-26 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-22 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 150 | 100 | 100 | 100.0719 | 100
81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-27 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 100% | Finished | 30 | 30 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-28 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 37.5 | 37.5 | 100 | 50 | 100 | 100 | 50 | 100
85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-29 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-29 09:00 | 6h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 100 | 100 | 100 | 150 | 100 | 100 | 150 | 100
89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-29 16:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 24 | 24 | 100 | 125 | 100 | 100 | 125 | 100
94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-12-03 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-12-03 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 24 | 24 | 100 | 50 | 100 | 100 | 50 | 100
99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-29 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 50 | 100 | 100 | 99.9281 | 100
103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-04 16:00 | 2h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-12-05 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 100 | 100 | 100 | 100 | 100
107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 | 2012-12-05 09:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 20 | 20 | 100 | 75 | 100 | 100 | 75 | 100
108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 |  | 0 | 0 | 9.24 | 2h | 0 | 0 | 0 | 9.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 100% | Finished | 25 | 25 | 100 | 125 | 100 | 100 | 125 | 100
113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-12-05 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 50 | 100 | 100 | 99.9281 | 100
115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 75 | 100 | 100 | 75 | 100
116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 |  | 0 | 0 | 60 | 4h | 0 | 0 | 0 | 60 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 |  | 0 | 0 | 18.75 | 1h | 0 | 0 | 0 | 18.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 80 | 100 | 100 | 80 | 100
121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 |  | 0 | 0 | 120 | 4h | 0 | 0 | 0 | 120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 17.14 | 17.14 | 100 | 100 | 100 | 100 | 100 | 100
128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 |  | 0 | 0 | 45.72 | 4h | 0 | 0 | 0 | 45.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 |  | 0 | 0 | 10007.2 | 1h | 0 | 0 | 0 | 10007.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 1h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 4h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-12-12 20:00 |  | TP Name | 12/12/2012 20:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 30d | [5 empty] | 154973.02 |  | 83.75% |  | 155339.57 | 155339.57
1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 10 | 10 | 100 | 150 | 100 | 100 | 150 | 100
6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 420 | 420 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 64 | 64 | 100 | 100 | 100 | 100 | 100 | 100
11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 75 | 100 | 100 | 75 | 100
14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 100% | Finished | 105 | 105 | 100 | 100 | 100 | 100 | 100 | 100
19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 100% | Finished | 10 | 10 | 100 | 50 | 100 | 100 | 50 | 100
24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 50 | 100 | 100 | 50 | 100
28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-07 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-08 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-08 09:00 | 2h | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 100% | Finished | 100 | 100 | 100 | 50 | 100 | 100 | 50 | 100
32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-08 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-08 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 100% | Finished | 24 | 24 | 100 | 150 | 100 | 100 | 150 | 100
37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 100 | 100 | 100 | 100 | 100
38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-12 09:00 | 3h | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 100% | Finished | 60 | 60 | 100 | 75 | 100 | 100 | 75 | 100
39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-12 14:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 75 | 100 | 100 | 75 | 100
40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-11-13 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-13 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-14 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-14 08:00 | 2h | 10014.4 | 0 | 0 | 0 | 0 | 10014.4 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 100 | 100 | 100 | 100 | 100
50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-14 09:00 | 6h | 68.58 | 0 | 0 | 0 | 0 | 68.58 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 150 | 100 | 100 | 150 | 100
52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | Finished | 24 | 24 | 100 | 100 | 100 | 100 | 100 | 100
54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-19 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-19 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-16 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 100 | 100 | 100 | 100 | 100
58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 | 2012-11-19 14:00 | 2h | 210 | 0 | 0 | 0 | 0 | 210 | 0 | 100% | Finished | 315 | 315 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-20 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-21 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-21 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-22 10:00 | 2h | 9.24 | 0 | 0 | 0 | 0 | 9.24 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 100 | 100 | 100 | 100 | 100
67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-22 09:00 | 3h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 100 | 100 | 100 | 75 | 100 | 100 | 75 | 100
68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 13.92 | 13.92 | 100 | 150 | 100 | 100 | 150 | 100
69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 50 | 100 | 100 | 50 | 100
70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 24 | 24 | 100 | 75 | 100 | 100 | 75 | 100
72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 100% | Finished | 15 | 15 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 25.71 | 25.71 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-26 09:00 | 6h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-26 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-22 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 150 | 100 | 100 | 100.0719 | 100
81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-27 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 100% | Finished | 30 | 30 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-28 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 37.5 | 37.5 | 100 | 50 | 100 | 100 | 50 | 100
85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-29 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-29 09:00 | 6h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 100 | 100 | 100 | 150 | 100 | 100 | 150 | 100
89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-29 16:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 24 | 24 | 100 | 125 | 100 | 100 | 125 | 100
94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-12-03 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-12-03 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 24 | 24 | 100 | 50 | 100 | 100 | 50 | 100
99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-29 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 50 | 100 | 100 | 99.9281 | 100
103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-04 16:00 | 2h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-12-05 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 100 | 100 | 100 | 100 | 100
107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 | 2012-12-05 09:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 20 | 20 | 100 | 75 | 100 | 100 | 75 | 100
108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-12-06 09:00 | 1h | 4.62 | 0 | 0 | 0 | 0 | 4.62 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 50 | 100 | 100 | 50 | 100
109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-12-06 09:00 | 5h | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 100% | Finished | 100 | 100 | 100 | 125 | 100 | 100 | 125 | 100
110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-12-06 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 120 | 120 | 100 | 50 | 100 | 100 | 50 | 100
111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 100% | Finished | 25 | 25 | 100 | 125 | 100 | 100 | 125 | 100
113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-12-05 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 50 | 100 | 100 | 99.9281 | 100
115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 75 | 100 | 100 | 75 | 100
116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-12-10 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 | 2012-12-10 14:00 | 1h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-10 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 80 | 100 | 100 | 80 | 100
121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-11 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-12-11 14:00 | 6h | 180 | 0 | 0 | 0 | 0 | 180 | 0 | 100% | Finished | 120 | 120 | 100 | 150 | 100 | 100 | 150 | 100
123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-11 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 17.14 | 17.14 | 100 | 100 | 100 | 100 | 100 | 100
128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-12-12 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-12 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-12 15:00 | 1h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 |  | 0 | 0 | 18.48 | 4h | 0 | 0 | 0 | 18.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 |  | 0 | 0 | 100 | 4h | 0 | 0 | 0 | 100 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 2h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 4h | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 |  | 0 | 0 | 10014.4 | 2h | 0 | 0 | 0 | 10014.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2012-12-19 20:00 |  | TP Name | 19/12/2012 20:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | The Master Project | 2012-10-29 08:00 | 2012-12-14 20:00 | 32d |  |  | 180000 |  |  | 185472.45 |  | 32d | [5 empty] | 185113.1 |  | 100% |  | 185472.45 | 185472.45
1 | X Course strategic management | 2012-10-29 09:00 | 2012-10-29 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-10-29 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
2 | A Course Marketing communications | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-10-29 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
3 | X Groupwork strategic management | 2012-10-29 19:00 | 2012-10-30 10:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-10-29 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
4 | S Groupwork FEC | 2012-10-29 14:00 | 2012-10-29 16:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 08:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 10 | 10 | 100 | 150 | 100 | 100 | 150 | 100
6 | E Course B2B | 2012-10-29 14:00 | 2012-10-29 17:00 | 3h | Eline | 0 | 0 | 140 | 420 | 420 | 2012-10-29 14:00 | 2h | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 420 | 420 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
7 | X Groupwork Projectmanagement | 2012-10-30 18:00 | 2012-10-31 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 08:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
8 | E Course CRM | 2012-10-30 14:00 | 2012-10-30 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-10-30 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
9 | E Groupwork B2B | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-29 08:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
10 | A Groupwork Research Methods | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-29 08:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 64 | 64 | 100 | 100 | 100 | 100 | 100 | 100
11 | X Course Projectmanagement | 2012-10-31 14:00 | 2012-10-31 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-10-31 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
12 | A Course research methods | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-10-31 18:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
13 | E Groupwork Service Management | 2012-11-07 15:00 | 2012-11-07 19:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 08:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 75 | 100 | 100 | 75 | 100
14 | S Course FEC | 2012-10-31 09:00 | 2012-10-31 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-10-31 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
15 | X Deadline 1 Strategic management | 2012-10-31 20:00 | 2012-10-31 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | X Course strategic management | 2012-11-05 09:00 | 2012-11-05 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-05 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
17 | A Course Marketing Communications | 2012-11-05 14:00 | 2012-11-05 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-05 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | S Course B2B | 2012-11-05 14:00 | 2012-11-05 15:00 | 1h | Sanne | 0 | 0 | 105 | 105 | 105 | 2012-11-05 14:00 | 1h | 105 | 0 | 0 | 0 | 0 | 105 | 0 | 100% | Finished | 105 | 105 | 100 | 100 | 100 | 100 | 100 | 100
19 | A Course Research methods | 2012-11-06 11:00 | 2012-11-06 13:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-06 11:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 150 | 100 | 100 | 150 | 100
20 | A Groupwork Research methods | 2012-11-07 09:00 | 2012-11-07 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 12:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
21 | E Exam CRM | 2012-11-06 14:00 | 2012-11-06 18:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-11-06 14:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
22 | X Groupwork Strategic management | 2012-11-05 17:00 | 2012-11-05 20:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-05 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
23 | S Groupwork FEC | 2012-10-29 16:00 | 2012-10-29 18:00 | 2h | Sanne | 0 | 0 | 5 | 10 | 10 | 2012-10-29 11:00 | 1h | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 100% | Finished | 10 | 10 | 100 | 50 | 100 | 100 | 50 | 100
24 | A Groupwork research methods | 2012-11-07 12:00 | 2012-11-07 16:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-29 17:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
25 | X Groupwork Project management | 2012-11-06 08:00 | 2012-11-06 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 10:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
26 | E Groupwork Service management | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-29 11:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 50 | 100 | 100 | 50 | 100
28 | S Course FEC | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-07 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
29 | X Deadline 2 Strategic management | 2012-11-07 20:00 | 2012-11-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | A Course Research Methods | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-08 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
31 | E+S Course systeemdynamica | 2012-11-08 09:00 | 2012-11-08 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-08 09:00 | 2h | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 100% | Finished | 100 | 100 | 100 | 50 | 100 | 100 | 50 | 100
32 | E Course Service Management | 2012-11-08 16:00 | 2012-11-08 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-08 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
33 | E Groupwork B2B | 2012-10-31 18:00 | 2012-10-31 20:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-29 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
34 | X Group work strategisch management | 2012-11-08 18:00 | 2012-11-09 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-08 08:00 | 4h | 10028.8 | 0 | 0 | 0 | 0 | 10028.8 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 133.3333 | 100 | 100 | 100.0718 | 100
36 | E Group work B2B | 2012-11-07 09:00 | 2012-11-07 13:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-29 14:00 | 6h | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 100% | Finished | 24 | 24 | 100 | 150 | 100 | 100 | 150 | 100
37 | S Group work B2B | 2012-11-06 11:00 | 2012-11-06 16:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 08:00 | 4h | 34.28 | 0 | 0 | 0 | 0 | 34.28 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 100 | 100 | 100 | 100 | 100
38 | X Course Strategisch management | 2012-11-12 09:00 | 2012-11-12 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-12 09:00 | 3h | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 100% | Finished | 60 | 60 | 100 | 75 | 100 | 100 | 75 | 100
39 | A Course research methods | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-12 14:00 | 3h | 13.86 | 0 | 0 | 0 | 0 | 13.86 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 75 | 100 | 100 | 75 | 100
40 | E Groupwork B2B | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Eline | 0 | 0 | 6 | 12 | 12 | 2012-10-30 08:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
41 | X Deadline 3 | 2012-11-12 20:00 | 2012-11-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
42 | A Groupwork Marketing Communications | 2012-10-29 08:00 | 2012-10-29 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 08:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
43 | X Groupwork Project Management | 2012-11-06 18:00 | 2012-11-07 09:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 18.75 | 18.75 | 2012-10-29 14:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
44 | X Groupwork Strategic Management | 2012-11-13 08:00 | 2012-11-13 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-11-13 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
45 | E Course CRM | 2012-11-13 14:00 | 2012-11-13 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-13 14:00 | 5h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 120 | 120 | 100 | 125 | 100 | 100 | 125 | 100
46 | X Deadline 4 | 2012-11-13 20:00 | 2012-11-13 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
47 | S Groupwork FEC | 2012-10-30 10:00 | 2012-10-30 13:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 12:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
48 | X Course Project Management | 2012-11-14 14:00 | 2012-11-14 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-14 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
49 | X Group Work Strategic Management | 2012-11-14 18:00 | 2012-11-14 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-14 08:00 | 2h | 10014.4 | 0 | 0 | 0 | 0 | 10014.4 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 100 | 100 | 100 | 100 | 100
50 | E Group Work Service Management | 2012-11-12 17:00 | 2012-11-12 20:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 08:00 | 2h | 13.92 | 0 | 0 | 0 | 0 | 13.92 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
51 | S Course FEC | 2012-11-14 09:00 | 2012-11-14 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-14 09:00 | 6h | 68.58 | 0 | 0 | 0 | 0 | 68.58 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 150 | 100 | 100 | 150 | 100
52 | X Deadline 5 | 2012-11-14 20:00 | 2012-11-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | E Group Work B2B | 2012-11-13 18:00 | 2012-11-14 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 10:00 | 4h | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | Finished | 24 | 24 | 100 | 100 | 100 | 100 | 100 | 100
54 | X Group Work Project Management | 2012-11-16 11:00 | 2012-11-16 17:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 16:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
55 | X Course Strategic Management | 2012-11-19 09:00 | 2012-11-19 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-19 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
56 | A Course Marketing Communications | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-19 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
57 | X Group Work Strategic Management | 2012-11-16 08:00 | 2012-11-16 11:00 | 3h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 21.6 | 10021.6 | 2012-11-16 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10021.6 | 10021.6 | 100 | 100 | 100 | 100 | 100 | 100
58 | S Course B2B | 2012-11-19 14:00 | 2012-11-19 17:00 | 3h | Sanne | 0 | 0 | 105 | 315 | 315 | 2012-11-19 14:00 | 2h | 210 | 0 | 0 | 0 | 0 | 210 | 0 | 100% | Finished | 315 | 315 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
59 | X Group Work Project Management | 2012-11-19 17:00 | 2012-11-20 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-29 19:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 60 | 100 | 100 | 60 | 100
60 | E Course CRM | 2012-11-20 14:00 | 2012-11-20 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-20 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
61 | X Course Project Management | 2012-11-21 14:00 | 2012-11-21 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-11-21 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 75 | 75 | 100 | 50 | 100 | 100 | 50 | 100
62 | A Group Work Marketing Communications | 2012-10-30 10:00 | 2012-10-30 12:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 09:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
63 | E Group Work Service Management | 2012-11-09 14:00 | 2012-11-09 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-29 14:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | Deadline 6 | 2012-11-21 20:00 | 2012-11-21 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
65 | S Course FEC | 2012-11-21 09:00 | 2012-11-21 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-21 09:00 | 2h | 22.86 | 0 | 0 | 0 | 0 | 22.86 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 50 | 100 | 100 | 50 | 100
66 | A Course Research Methods | 2012-11-22 10:00 | 2012-11-22 12:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-11-22 10:00 | 2h | 9.24 | 0 | 0 | 0 | 0 | 9.24 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 100 | 100 | 100 | 100 | 100
67 | E+S Course Systeemdynamica | 2012-11-22 09:00 | 2012-11-22 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-22 09:00 | 3h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 100 | 100 | 100 | 75 | 100 | 100 | 75 | 100
68 | E Group Work Service Management | 2012-11-09 17:00 | 2012-11-09 19:00 | 2h | Eline | 0 | 0 | 6.96 | 13.92 | 13.92 | 2012-10-29 17:00 | 3h | 20.88 | 0 | 0 | 0 | 0 | 20.88 | 0 | 100% | Finished | 13.92 | 13.92 | 100 | 150 | 100 | 100 | 150 | 100
69 | X Group Work Project Management | 2012-11-20 10:00 | 2012-11-20 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 10:00 | 1h | 6.25 | 0 | 0 | 0 | 0 | 6.25 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 50 | 100 | 100 | 50 | 100
70 | A Group Work Research Methods | 2012-11-07 16:00 | 2012-11-07 19:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 09:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
71 | E Group Work B2B | 2012-11-16 17:00 | 2012-11-19 09:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 15:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 24 | 24 | 100 | 75 | 100 | 100 | 75 | 100
72 | X Group Work Project Management | 2012-11-20 18:00 | 2012-11-20 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 11:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
73 | S Group Work FEC | 2012-10-30 14:00 | 2012-10-30 17:00 | 3h | Sanne | 0 | 0 | 5 | 15 | 15 | 2012-10-29 16:00 | 4h | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 100% | Finished | 15 | 15 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
74 | S Group Work B2B | 2012-11-07 14:00 | 2012-11-07 17:00 | 3h | Sanne | 0 | 0 | 8.57 | 25.71 | 25.71 | 2012-10-29 12:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 25.71 | 25.71 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
75 | X Course Strategic Management | 2012-11-26 09:00 | 2012-11-26 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-11-26 09:00 | 6h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
77 | A Group Work Marketing Communications | 2012-10-30 12:00 | 2012-10-30 15:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 11:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
79 | A Course Marketing Communications | 2012-11-26 14:00 | 2012-11-26 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-11-26 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
80 | X Group Work Strategic Management | 2012-11-22 14:00 | 2012-11-22 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-22 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 150 | 100 | 100 | 100.0719 | 100
81 | E Course CRM | 2012-11-27 14:00 | 2012-11-27 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-11-27 14:00 | 4h | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 100% | Finished | 120 | 120 | 100 | 100 | 100 | 100 | 100 | 100
82 | S Group Work FEC | 2012-11-09 14:00 | 2012-11-09 20:00 | 6h | Sanne | 0 | 0 | 5 | 30 | 30 | 2012-10-30 08:00 | 7h | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 100% | Finished | 30 | 30 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
83 | S Course FEC | 2012-11-28 09:00 | 2012-11-28 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-11-28 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
84 | X Group Work Project Management | 2012-11-22 16:00 | 2012-11-23 10:00 | 6h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 37.5 | 37.5 | 2012-10-30 14:00 | 3h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 37.5 | 37.5 | 100 | 50 | 100 | 100 | 50 | 100
85 | X Deadline 7 | 2012-11-28 20:00 | 2012-11-28 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
86 | A Course Research Methods | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-11-29 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
87 | A Group Work Research Methods | 2012-11-08 14:00 | 2012-11-08 18:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-30 14:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
88 | E+S Course Systeemdynamica | 2012-11-29 09:00 | 2012-11-29 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-11-29 09:00 | 6h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 100 | 100 | 100 | 150 | 100 | 100 | 150 | 100
89 | E Course Service Management | 2012-11-29 16:00 | 2012-11-29 18:00 | 2h | Eline | 0 | 0 | 30 | 60 | 60 | 2012-11-29 16:00 | 3h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 60 | 60 | 100 | 150 | 100 | 100 | 150 | 100
91 | X Group Work Project Management | 2012-11-23 10:00 | 2012-11-23 12:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 12.5 | 12.5 | 2012-10-30 17:00 | 2h | 12.5 | 0 | 0 | 0 | 0 | 12.5 | 0 | 100% | Finished | 12.5 | 12.5 | 100 | 100 | 100 | 100 | 100 | 100
92 | E Group Work Service Management | 2012-11-12 14:00 | 2012-11-12 17:00 | 3h | Eline | 0 | 0 | 6.96 | 20.88 | 20.88 | 2012-10-30 08:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 20.88 | 20.88 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
93 | E Group Work B2B | 2012-11-21 08:00 | 2012-11-21 12:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-30 18:00 | 5h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 24 | 24 | 100 | 125 | 100 | 100 | 125 | 100
94 | S Group Work B2B | 2012-11-07 17:00 | 2012-11-08 09:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 15:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
95 | X Course Strategic Management | 2012-12-03 09:00 | 2012-12-03 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-12-03 09:00 | 4h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
96 | A Course Marketing Communications | 2012-12-03 14:00 | 2012-12-03 17:00 | 3h | Ann-Sophie | 0 | 0 | 18.75 | 56.25 | 56.25 | 2012-12-03 14:00 | 2h | 37.5 | 0 | 0 | 0 | 0 | 37.5 | 0 | 100% | Finished | 56.25 | 56.25 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
97 | A Group Work Marketing Communications | 2012-10-30 15:00 | 2012-10-30 17:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 15:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
98 | E Group Work B2B | 2012-11-27 18:00 | 2012-11-28 10:00 | 4h | Eline | 0 | 0 | 6 | 24 | 24 | 2012-10-31 11:00 | 2h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 24 | 24 | 100 | 50 | 100 | 100 | 50 | 100
99 | S Group Work B2B | 2012-11-09 09:00 | 2012-11-09 13:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 17:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 50 | 100 | 100 | 50 | 100
100 | A Group Work Research Methods | 2012-11-09 09:00 | 2012-11-09 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-30 19:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
101 | X Group Work Project Management | 2012-11-23 12:00 | 2012-11-23 17:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-30 19:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
102 | X Group Work Strategic Management | 2012-11-29 14:00 | 2012-11-29 16:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-11-29 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 50 | 100 | 100 | 99.9281 | 100
103 | E Exam SAS | 2012-12-04 16:00 | 2012-12-04 18:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-04 16:00 | 2h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
104 | X Deadline 8 | 2012-12-04 20:00 | 2012-12-04 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
105 | X Course Project Management | 2012-12-05 14:00 | 2012-12-05 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 18.75 | 75 | 75 | 2012-12-05 14:00 | 4h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
106 | E Group Work Service Management | 2012-11-13 09:00 | 2012-11-13 13:00 | 4h | Eline | 0 | 0 | 6.96 | 27.84 | 27.84 | 2012-10-30 12:00 | 4h | 27.84 | 0 | 0 | 0 | 0 | 27.84 | 0 | 100% | Finished | 27.84 | 27.84 | 100 | 100 | 100 | 100 | 100 | 100
107 | S Course FEC | 2012-12-05 09:00 | 2012-12-05 13:00 | 4h | Sanne | 0 | 0 | 5 | 20 | 20 | 2012-12-05 09:00 | 3h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 20 | 20 | 100 | 75 | 100 | 100 | 75 | 100
108 | A Course Research Methods | 2012-12-06 09:00 | 2012-12-06 11:00 | 2h | Ann-Sophie | 0 | 0 | 4.62 | 9.24 | 9.24 | 2012-12-06 09:00 | 1h | 4.62 | 0 | 0 | 0 | 0 | 4.62 | 0 | 100% | Finished | 9.24 | 9.24 | 100 | 50 | 100 | 100 | 50 | 100
109 | E+S Course Systeemdynamica | 2012-12-06 09:00 | 2012-12-06 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-12-06 09:00 | 5h | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 100% | Finished | 100 | 100 | 100 | 125 | 100 | 100 | 125 | 100
110 | E Course Service Management | 2012-12-06 16:00 | 2012-12-06 20:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-12-06 16:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 120 | 120 | 100 | 50 | 100 | 100 | 50 | 100
111 | A Group Work Research Methods | 2012-11-09 12:00 | 2012-11-09 17:00 | 4h | Ann-Sophie | 0 | 0 | 16 | 64 | 64 | 2012-10-31 10:00 | 5h | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 100% | Finished | 64 | 64 | 100 | 125 | 100 | 100 | 125 | 100
112 | X Group Work Project Management | 2012-11-23 17:00 | 2012-11-26 09:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-10-31 11:00 | 5h | 31.25 | 0 | 0 | 0 | 0 | 31.25 | 0 | 100% | Finished | 25 | 25 | 100 | 125 | 100 | 100 | 125 | 100
113 | A Group Work Marketing Communications | 2012-11-07 19:00 | 2012-11-08 09:00 | 2h | Ann-Sophie | 0 | 0 | 30 | 60 | 60 | 2012-10-29 17:00 | 2h | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 60 | 60 | 100 | 100 | 100 | 100 | 100 | 100
114 | X Group Work Strategic Management | 2012-12-05 18:00 | 2012-12-05 20:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-12-05 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 50 | 100 | 100 | 99.9281 | 100
115 | S Group Work B2B | 2012-11-12 14:00 | 2012-11-12 18:00 | 4h | Sanne | 0 | 0 | 8.57 | 34.28 | 34.28 | 2012-10-29 19:00 | 3h | 25.71 | 0 | 0 | 0 | 0 | 25.71 | 0 | 100% | Finished | 34.28 | 34.28 | 100 | 75 | 100 | 100 | 75 | 100
116 | X Deadline 9 | 2012-12-07 20:00 | 2012-12-07 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
117 | X Course Strategic Management | 2012-12-10 09:00 | 2012-12-10 13:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 15 | 60 | 60 | 2012-12-10 09:00 | 2h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 60 | 60 | 100 | 50 | 100 | 100 | 50 | 100
118 | A Course Marketing Communications | 2012-12-10 14:00 | 2012-12-10 15:00 | 1h | Ann-Sophie | 0 | 0 | 18.75 | 18.75 | 18.75 | 2012-12-10 14:00 | 1h | 18.75 | 0 | 0 | 0 | 0 | 18.75 | 0 | 100% | Finished | 18.75 | 18.75 | 100 | 100 | 100 | 100 | 100 | 100
119 | X Group Work Strategic Management | 2012-12-10 08:00 | 2012-12-10 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-10 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
120 | X Group Work Project Management | 2012-11-26 17:00 | 2012-11-27 10:00 | 5h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 31.25 | 31.25 | 2012-10-31 17:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 31.25 | 31.25 | 100 | 80 | 100 | 100 | 80 | 100
121 | X Deadline 10 | 2012-12-10 20:00 | 2012-12-10 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-11 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
122 | E Course CRM | 2012-12-11 14:00 | 2012-12-11 18:00 | 4h | Eline | 0 | 0 | 30 | 120 | 120 | 2012-12-11 14:00 | 6h | 180 | 0 | 0 | 0 | 0 | 180 | 0 | 100% | Finished | 120 | 120 | 100 | 150 | 100 | 100 | 150 | 100
123 | X Group Work Strategic Management | 2012-12-11 08:00 | 2012-12-11 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-11 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
124 | X Group Work Project Management | 2012-11-28 14:00 | 2012-11-28 18:00 | 4h | Ann-Sophie;Sanne;Eline | 0 | 0 | 6.25 | 25 | 25 | 2012-11-05 09:00 | 4h | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 100% | Finished | 25 | 25 | 100 | 100 | 100 | 100 | 100 | 100
125 | A Group Work Marketing Communications | 2012-11-12 08:00 | 2012-11-12 09:00 | 1h | Ann-Sophie | 0 | 0 | 30 | 30 | 30 | 2012-10-29 19:00 | 1h | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 30 | 30 | 100 | 100 | 100 | 100 | 100 | 100
126 | A Group Work Research Methods | 2012-11-09 17:00 | 2012-11-09 20:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 16:00 | 3h | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 48 | 48 | 100 | 100 | 100 | 100 | 100 | 100
127 | S Group Work B2B | 2012-11-12 18:00 | 2012-11-12 20:00 | 2h | Sanne | 0 | 0 | 8.57 | 17.14 | 17.14 | 2012-10-30 10:00 | 2h | 17.14 | 0 | 0 | 0 | 0 | 17.14 | 0 | 100% | Finished | 17.14 | 17.14 | 100 | 100 | 100 | 100 | 100 | 100
128 | X Deadline 11 | 2012-12-11 20:00 | 2012-12-11 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-12 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
129 | S Course FEC | 2012-12-12 09:00 | 2012-12-12 13:00 | 4h | Sanne | 0 | 0 | 11.43 | 45.72 | 45.72 | 2012-12-12 09:00 | 4h | 45.72 | 0 | 0 | 0 | 0 | 45.72 | 0 | 100% | Finished | 45.72 | 45.72 | 100 | 100 | 100 | 100 | 100 | 100
130 | A Group Work Research Methods | 2012-11-13 09:00 | 2012-11-13 12:00 | 3h | Ann-Sophie | 0 | 0 | 16 | 48 | 48 | 2012-10-31 19:00 | 4h | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 100% | Finished | 48 | 48 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
131 | X Group Work Strategic Management | 2012-12-12 08:00 | 2012-12-12 09:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 7.2 | 10007.2 | 2012-12-12 08:00 | 1h | 10007.2 | 0 | 0 | 0 | 0 | 10007.2 | 0 | 100% | Finished | 10007.2 | 10007.2 | 100 | 100 | 100 | 100 | 100 | 100
132 | X Deadline 12 | 2012-12-12 20:00 | 2012-12-12 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-13 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
133 | X Presentation Project Management | 2012-12-12 15:00 | 2012-12-12 16:00 | 1h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-12 15:00 | 1h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
134 | A Course Research Methods | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Ann-Sophie | 0 | 0 | 4.62 | 18.48 | 18.48 | 2012-12-13 09:00 | 4h | 18.48 | 0 | 0 | 0 | 0 | 18.48 | 0 | 100% | Finished | 18.48 | 18.48 | 100 | 100 | 100 | 100 | 100 | 100
135 | E+S Course Systeemdynamica | 2012-12-13 09:00 | 2012-12-13 13:00 | 4h | Sanne;Eline | 0 | 0 | 25 | 100 | 100 | 2012-12-13 09:00 | 4h | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 100% | Finished | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
136 | E Presentation Service Management | 2012-12-13 14:00 | 2012-12-13 16:00 | 2h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-13 14:00 | 3h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 150 | 100 | 100 | 100 | 100
137 | E Group Work B2B | 2012-11-28 10:00 | 2012-11-28 13:00 | 3h | Eline | 0 | 0 | 6 | 18 | 18 | 2012-10-31 14:00 | 3h | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 18 | 18 | 100 | 100 | 100 | 100 | 100 | 100
138 | E Exam CRM | 2012-12-14 09:00 | 2012-12-14 13:00 | 4h | Eline | 0 | 10000 | 0 | 0 | 10000 | 2012-12-14 09:00 | 4h | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
139 | X Group Work Strategic Management | 2012-12-13 16:00 | 2012-12-13 18:00 | 2h | Ann-Sophie;Sanne;Eline | 0 | 10000 | 7.2 | 14.4 | 10014.4 | 2012-12-13 08:00 | 3h | 10021.6 | 0 | 0 | 0 | 0 | 10021.6 | 0 | 100% | Finished | 10014.4 | 10014.4 | 100 | 150 | 100 | 100 | 100.0719 | 100
140 | X Deadline 13 | 2012-12-14 20:00 | 2012-12-14 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-12-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2012-11-01
1:00 - 2:00 | No | Tuesday | Yes | 2012-11-15
2:00 - 3:00 | No | Wednesday | Yes | 2012-12-25
3:00 - 4:00 | No | Thursday | Yes | 2012-11-02
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | Yes
13:00 - 14:00 | No
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | Yes
18:00 - 19:00 | Yes
19:00 - 20:00 | Yes
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
6/11/2012 20:00 | 2012-10-29 08:00 | 2012-11-06 20:00 | 31498.18 | 32739.95 | 32541.39 | 2012-11-08 19:00 | 1241.77 | 103.9% | 198.56 | 100.6% | 1d 10h | 138.2% | 75.71% | 2012-12-14 18:00 | 2012-12-13 18:00 | 2012-12-13 16:00 | 2012-12-14 18:00 | 2012-12-13 18:00 | 2012-12-13 16:00 | 2012-12-13 09:00 | 2012-12-04 10:00 | 2012-12-04 09:00 | 185273.89 | 184347.6038 | 179481.0089 | 143071.4887 | 178589.8552 | 142401.15 | 183348.6657 | 173797.5279 | 1.3818 | 1.0061 | 1.0394 | 0.75713 | 1.9091 | 1.0061 | 1 | 1.3818 | 1
13/11/2012 20:00 | 2012-11-06 20:00 | 2012-11-13 20:00 | 52845.68 | 53191.43 | 52960.45 | 2012-11-14 19:00 | 345.75 | 100.7% | 230.98 | 100.4% | 10h | 109.1% | 83.92% | 2012-12-14 19:00 | 2012-12-14 18:00 | 2012-12-14 16:00 | 2012-12-14 19:00 | 2012-12-14 18:00 | 2012-12-14 17:00 | 2012-12-14 09:00 | 2012-12-12 12:00 | 2012-12-12 11:00 | 185241.47 | 184667.0491 | 184381.6292 | 174218.0517 | 183810.9421 | 173691.4992 | 184609.866 | 182435.6248 | 1.0909 | 1.0044 | 1.0065 | 0.8392 | 0.90909 | 1.0044 | 1 | 1.0909 | 1
21/11/2012 20:00 | 2012-11-13 20:00 | 2012-11-21 20:00 | 73821.87 | 74020.12 | 73627.89 | 2012-11-22 15:00 | 198.25 | 100.3% | 392.23 | 100.5% | 6h | 103.6% | 87.95% | 2012-12-14 20:00 | 2012-12-14 19:00 | 2012-12-14 17:00 | 2012-12-14 20:00 | 2012-12-14 19:00 | 2012-12-14 18:00 | 2012-12-14 13:00 | 2012-12-13 19:00 | 2012-12-13 18:00 | 185080.22 | 184489.638 | 184781.7143 | 181169.6119 | 184192.7142 | 180599.7521 | 184547.9304 | 183809.3341 | 1.0364 | 1.0053 | 1.0027 | 0.87948 | 0.54545 | 1.0053 | 1 | 1.0364 | 1
28/11/2012 20:00 | 2012-11-21 20:00 | 2012-11-28 20:00 | 84425.73 | 84425.73 | 84026.95 | 2012-11-28 20:00 | 0 | 100% | 398.78 | 100.5% | 0 | 100% | 100% | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 18:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 19:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 19:00 | 185073.67 | 184596.3817 | 185073.67 | 185073.67 | 184596.3817 | 184596.3817 | 184691.4783 | 184691.4783 | 1 | 1.0047 | 1 | 1 | 0 | 1.0047 | 1 | 1 | 1
5/12/2012 20:00 | 2012-11-28 20:00 | 2012-12-05 20:00 | 114844.26 | 114844.26 | 114487.33 | 2012-12-05 20:00 | 0 | 100% | 356.93 | 100.3% | 0 | 100% | 100% | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 19:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 185115.52 | 184896.0112 | 185115.52 | 185115.52 | 184896.0112 | 184896.0112 | 184939.8038 | 184939.8038 | 1 | 1.0031 | 1 | 1 | 0 | 1.0031 | 1 | 1 | 1
12/12/2012 20:00 | 2012-12-05 20:00 | 2012-12-12 20:00 | 155339.57 | 155339.57 | 154973.02 | 2012-12-12 20:00 | 0 | 100% | 366.55 | 100.2% | 0 | 100% | 100% | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 19:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 20:00 | 185105.9 | 185034.7964 | 185105.9 | 185105.9 | 185034.7964 | 185034.7964 | 185048.9902 | 185048.9902 | 1 | 1.0024 | 1 | 1 | 0 | 1.0024 | 1 | 1 | 1
19/12/2012 20:00 | 2012-12-12 20:00 | 2012-12-19 20:00 | 185472.45 | 185472.45 | 185113.1 | 2012-12-14 20:00 | 0 | 100% | 359.35 | 100.2% | -3d | 91.43% | 100% | 2012-12-14 20:00 | 2012-12-14 20:00 | 2012-12-14 19:00 | 2012-12-19 20:00 | 2012-12-19 20:00 | 2012-12-19 20:00 | 2012-12-19 20:00 | 2012-12-19 20:00 | 2012-12-19 20:00 | 185113.1 | 185113.1 | 185113.1 | 185113.1 | 185113.1 | 185113.1 | 185113.1 | 185113.1 | 0.91429 | 1.0019 | 1 | 1 | -3 | 1.0019 | 1 | 0.91429 | 1