## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building (3) | 1 |  |  | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 | 492.375
1 | Sondering | 1.1 |  | FS2 | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 0.375
2 | Inrichting | 1.2 | 1FS | FS5 | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 0.375
3 | Bouwput + Kelders | 1.3 | 5FS | FS4 | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 27.375
4 | Bouw rioleringen | 1.4 | 3FS | FS6;FS23 | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 41.375
5 | Afbraakwerken | 1.5 | 2FS | FS3 | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 27.375
6 | Ruwbouw | 1.6 | 4FS | FS7;FS10 | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 125.375
7 | Dakstructuur | 1.7 | 6FS | FS8;FS9 | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 41.375
8 | Dakisolatie | 1.8 | 7FS |  | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 27.375
9 | Dakbedekking & Zinkwerk | 1.9 | 7FS | FS11;FS12;FS13 | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 41.375
10 | Plaatsen Ramen | 1.10 | 6FS | FS17;FS21 | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 20.375
11 | Sanitaire technieken | 1.11 | 9FS | FS21 | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 69.375
12 | Elektriciteitstechnieken | 1.12 | 9FS | FS21 | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 69.375
13 | Ventilatietechnieken | 1.13 | 9FS | FS21 | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 41.375
14 | Trappen en Deuren | 1.14 | 16FS | FS24 | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 | 27.375
15 | Keukens | 1.15 | 16FS | FS24 | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 | 27.375
16 | Pleisterwerken | 1.16 | 22FS | FS14;FS15;FS18;FS19;FS20 | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 | 27.375
17 | Buitenpleisterwerk | 1.17 | 10FS |  | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 20.375
18 | Afwerking Ventilatie | 1.18 | 16FS | FS24 | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 | 13.375
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 1.19 | 16FS | FS24 | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 | 27.375
20 | Afwerking | 1.20 | 16FS | FS24 | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 | 20.375
21 | Chapewerken | 1.21 | 10FS;11FS;12FS;13FS | FS22 | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 20.375
22 | Vloeren | 1.22 | 21FS | FS16 | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 | 27.375
23 | Tuinaanleg | 1.23 | 4FS |  | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 13.375
24 | Schilderwerken | 1.24 | 14FS;15FS;18FS;19FS;20FS | FS25 | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 | 6.375
25 | Opkuis | 1.25 | 24FS |  | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building (3) | 2824h |  |  |  |  | 99 | 100 | 101
1 | Sondering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Inrichting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Bouwput + Kelders | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Bouw rioleringen | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Afbraakwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Ruwbouw | 720h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Dakstructuur | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Dakisolatie | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Dakbedekking & Zinkwerk | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Plaatsen Ramen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Sanitaire technieken | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Elektriciteitstechnieken | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Ventilatietechnieken | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Trappen en Deuren | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Keukens | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Pleisterwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Buitenpleisterwerk | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Afwerking Ventilatie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Afwerking | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Chapewerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Vloeren | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Tuinaanleg | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Schilderwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Opkuis | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2010-01-05 17:00 |  | TP Name | 05/01, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 22d | [5 empty] | 20618.6196 |  | 1.352% |  | 14905.9344 | 20618.6196
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 |  | 0 | 0 | 51323.6685 | 20d | 0 | 0 | 0 | 51323.6685 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 |  | 0 | 0 | 61347.3975 | 30d | 0 | 0 | 0 | 61347.3975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 20d | 16661.7996 | 9997.1997 | 15d | 0 | 0 | 16661.7996 | 9997.1997 | 57.14% | Started | 10949.1144 | 16661.7996 | 100 | 100 | 57.1429 | 100 | 100 | 57.1429
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 |  | 0 | 0 | 283886.7812 | 90d | 0 | 0 | 0 | 283886.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 |  | 0 | 0 | 35352.3005 | 30d | 0 | 0 | 0 | 35352.3005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 |  | 0 | 0 | 7499.6002 | 20d | 0 | 0 | 0 | 7499.6002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 |  | 0 | 0 | 55714.2109 | 30d | 0 | 0 | 0 | 55714.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 |  | 0 | 0 | 76855.061 | 15d | 0 | 0 | 0 | 76855.061 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 |  | 0 | 0 | 64896.58 | 50d | 0 | 0 | 0 | 64896.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 |  | 0 | 0 | 40662.4614 | 50d | 0 | 0 | 0 | 40662.4614 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 |  | 0 | 0 | 17095.0002 | 30d | 0 | 0 | 0 | 17095.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 |  | 0 | 0 | 35087.8394 | 15d | 0 | 0 | 0 | 35087.8394 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 |  | 0 | 0 | 33445.8696 | 10d | 0 | 0 | 0 | 33445.8696 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2010-02-02 17:00 |  | TP Name | 02/02, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 42d | [5 empty] | 54994.6886 |  | 3.81% |  | 42003.6225 | 71942.2881
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 5d | 24378.8693 | 44907.9987 | 25d | 0 | 0 | 24378.8693 | 44907.9987 | 16.67% | Started | 21385.0029 | 51323.6685 | 100 | 25 | 16.6667 | 100 | 47.5002 | 16.6667
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 |  | 0 | 0 | 61347.3975 | 30d | 0 | 0 | 0 | 61347.3975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 |  | 0 | 0 | 283886.7812 | 90d | 0 | 0 | 0 | 283886.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 |  | 0 | 0 | 35352.3005 | 30d | 0 | 0 | 0 | 35352.3005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 |  | 0 | 0 | 7499.6002 | 20d | 0 | 0 | 0 | 7499.6002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 |  | 0 | 0 | 55714.2109 | 30d | 0 | 0 | 0 | 55714.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 |  | 0 | 0 | 76855.061 | 15d | 0 | 0 | 0 | 76855.061 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 |  | 0 | 0 | 64896.58 | 50d | 0 | 0 | 0 | 64896.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 |  | 0 | 0 | 40662.4614 | 50d | 0 | 0 | 0 | 40662.4614 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 |  | 0 | 0 | 17095.0002 | 30d | 0 | 0 | 0 | 17095.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 |  | 0 | 0 | 35087.8394 | 15d | 0 | 0 | 0 | 35087.8394 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 |  | 0 | 0 | 33445.8696 | 10d | 0 | 0 | 0 | 33445.8696 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2010-03-16 17:00 |  | TP Name | 16/03, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 72d | [5 empty] | 125464.0862 |  | 8.681% |  | 95714.3871 | 133289.6855
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 5d | 25561.3989 | 50100.3979 | 35d | 0 | 0 | 25561.3989 | 50100.3979 | 12.5% | Started | 23772.099 | 61347.3975 | 100 | 16.6667 | 12.5 | 100 | 41.6666 | 12.5
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 |  | 0 | 0 | 283886.7812 | 90d | 0 | 0 | 0 | 283886.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 |  | 0 | 0 | 35352.3005 | 30d | 0 | 0 | 0 | 35352.3005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 |  | 0 | 0 | 7499.6002 | 20d | 0 | 0 | 0 | 7499.6002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 |  | 0 | 0 | 55714.2109 | 30d | 0 | 0 | 0 | 55714.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 |  | 0 | 0 | 76855.061 | 15d | 0 | 0 | 0 | 76855.061 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 |  | 0 | 0 | 64896.58 | 50d | 0 | 0 | 0 | 64896.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 |  | 0 | 0 | 40662.4614 | 50d | 0 | 0 | 0 | 40662.4614 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 |  | 0 | 0 | 17095.0002 | 30d | 0 | 0 | 0 | 17095.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 |  | 0 | 0 | 35087.8394 | 15d | 0 | 0 | 0 | 35087.8394 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 |  | 0 | 0 | 33445.8696 | 10d | 0 | 0 | 0 | 33445.8696 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2010-05-04 17:00 |  | TP Name | 04/05, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 107d | [5 empty] | 175564.4841 |  | 12.09% |  | 133289.6855 | 329182.3364
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 |  | 0 | 0 | 283886.7812 | 90d | 0 | 0 | 0 | 283886.7812 | 0% | Not Started | 0 | 162446.7812 | 100 |  | 0 | 100 |  | 0
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 |  | 0 | 0 | 35352.3005 | 30d | 0 | 0 | 0 | 35352.3005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 |  | 0 | 0 | 7499.6002 | 20d | 0 | 0 | 0 | 7499.6002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 |  | 0 | 0 | 55714.2109 | 30d | 0 | 0 | 0 | 55714.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 |  | 0 | 0 | 76855.061 | 15d | 0 | 0 | 0 | 76855.061 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 |  | 0 | 0 | 64896.58 | 50d | 0 | 0 | 0 | 64896.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 |  | 0 | 0 | 40662.4614 | 50d | 0 | 0 | 0 | 40662.4614 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 |  | 0 | 0 | 17095.0002 | 30d | 0 | 0 | 0 | 17095.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 |  | 0 | 0 | 35087.8394 | 15d | 0 | 0 | 0 | 35087.8394 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 |  | 0 | 0 | 33445.8696 | 10d | 0 | 0 | 0 | 33445.8696 | 0% | Not Started | 0 | 33445.8696 | 100 |  | 0 | 100 |  | 0
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2010-08-10 17:00 |  | TP Name | 10/08, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 177d | [5 empty] | 460443.1347 |  | 35.46% |  | 391006.334 | 550456.4979
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 70d | 239726.7812 | 66240 | 30d | 0 | 0 | 239726.7812 | 66240 | 70% | Started | 224270.7789 | 283886.7812 | 100 | 77.7778 | 70 | 100 | 84.4445 | 70
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 |  | 0 | 0 | 35352.3005 | 30d | 0 | 0 | 0 | 35352.3005 | 0% | Not Started | 0 | 22979.1005 | 100 |  | 0 | 100 |  | 0
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 |  | 0 | 0 | 7499.6002 | 20d | 0 | 0 | 0 | 7499.6002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 |  | 0 | 0 | 55714.2109 | 30d | 0 | 0 | 0 | 55714.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 |  | 0 | 0 | 76855.061 | 15d | 0 | 0 | 0 | 76855.061 | 0% | Not Started | 0 | 76855.061 | 100 |  | 0 | 100 |  | 0
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 |  | 0 | 0 | 64896.58 | 50d | 0 | 0 | 0 | 64896.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 |  | 0 | 0 | 40662.4614 | 50d | 0 | 0 | 0 | 40662.4614 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 |  | 0 | 0 | 17095.0002 | 30d | 0 | 0 | 0 | 17095.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 |  | 0 | 0 | 35087.8394 | 15d | 0 | 0 | 0 | 35087.8394 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2010-10-12 17:00 |  | TP Name | 12/10, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 222d | [5 empty] | 715526.7372 |  | 52.56% |  | 579496.338 | 661131.3485
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 |  | 0 | 0 | 7499.6002 | 20d | 0 | 0 | 0 | 7499.6002 | 0% | Not Started | 0 | 7499.6002 | 100 |  | 0 | 100 |  | 0
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 |  | 0 | 0 | 55714.2109 | 30d | 0 | 0 | 0 | 55714.2109 | 0% | Not Started | 0 | 55714.2109 | 100 |  | 0 | 100 |  | 0
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 |  | 0 | 0 | 64896.58 | 50d | 0 | 0 | 0 | 64896.58 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 |  | 0 | 0 | 40662.4614 | 50d | 0 | 0 | 0 | 40662.4614 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 |  | 0 | 0 | 17095.0002 | 30d | 0 | 0 | 0 | 17095.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 5d | 18713.4399 | 24561.5991 | 15d | 0 | 0 | 18713.4399 | 24561.5991 | 25% | Started | 16666.64 | 35087.8394 | 100 | 33.3333 | 25 | 100 | 53.3331 | 25
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2010-11-23 17:00 |  | TP Name | 23/11, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 252d | [5 empty] | 803302.1474 |  | 59.96% |  | 661131.3485 | 754228.5896
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 |  | 0 | 0 | 64896.58 | 50d | 0 | 0 | 0 | 64896.58 | 0% | Not Started | 0 | 46725.38 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 |  | 0 | 0 | 40662.4614 | 50d | 0 | 0 | 0 | 40662.4614 | 0% | Not Started | 0 | 29276.8608 | 100 |  | 0 | 100 |  | 0
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 |  | 0 | 0 | 17095.0002 | 30d | 0 | 0 | 0 | 17095.0002 | 0% | Not Started | 0 | 17095.0002 | 100 |  | 0 | 100 |  | 0
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2011-01-11 17:00 |  | TP Name | 11/01, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 287d | [5 empty] | 905782.9887 |  | 68.82% |  | 758726.9162 | 809456.8999
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 35d | 51268.18 | 18171.2 | 20d | 0 | 0 | 51268.18 | 18171.2 | 63.64% | Started | 48377.3068 | 64896.58 | 100 | 70 | 63.6364 | 100 | 78.9998 | 63.6364
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 35d | 32123.261 | 8539.2004 | 15d | 0 | 0 | 32123.261 | 8539.2004 | 70% | Started | 32123.2606 | 40662.4614 | 100 | 70 | 70 | 100 | 78.9998 | 70
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 100% | Finished | 17095.0002 | 17095.0002 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 |  | 0 | 0 | 25671.5098 | 15d | 0 | 0 | 0 | 25671.5098 | 0% | Not Started | 0 | 25671.5098 | 100 |  | 0 | 100 |  | 0
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2011-02-08 17:00 |  | TP Name | 08/02, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 307d | [5 empty] | 946184.8988 |  | 72.2% |  | 795979.3999 | 877502.6518
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 55d | 69439.3799 | 0 | 0 | 0 | 0 | 69439.3799 | 0 | 100% | Finished | 64896.58 | 64896.58 | 100 | 110 | 100 | 100 | 107.0001 | 100
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 50d | 40662.4614 | 0 | 0 | 0 | 0 | 40662.4614 | 0 | 100% | Finished | 40662.4614 | 40662.4614 | 100 | 100 | 100 | 100 | 100 | 100
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 100% | Finished | 17095.0002 | 17095.0002 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 2011-02-02 08:00 | 5d | 13691.5098 | 17970 | 15d | 0 | 0 | 13691.5098 | 17970 | 25% | Started | 12194.0098 | 25671.5098 | 100 | 33.3333 | 25 | 100 | 53.3335 | 25
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 |  | 0 | 0 | 68045.752 | 20d | 0 | 0 | 0 | 68045.752 | 0% | Not Started | 0 | 68045.752 | 100 |  | 0 | 100 |  | 0
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2011-03-08 17:00 |  | TP Name | 08/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 327d | [5 empty] | 996476.6493 |  | 76.35% |  | 841778.6504 | 930133.6113
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 55d | 69439.3799 | 0 | 0 | 0 | 0 | 69439.3799 | 0 | 100% | Finished | 64896.58 | 64896.58 | 100 | 110 | 100 | 100 | 107.0001 | 100
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 50d | 40662.4614 | 0 | 0 | 0 | 0 | 40662.4614 | 0 | 100% | Finished | 40662.4614 | 40662.4614 | 100 | 100 | 100 | 100 | 100 | 100
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 100% | Finished | 17095.0002 | 17095.0002 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 |  | 0 | 0 | 52630.9595 | 20d | 0 | 0 | 0 | 52630.9595 | 0% | Not Started | 0 | 52630.9595 | 100 |  | 0 | 100 |  | 0
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 2011-02-02 08:00 | 20d | 31661.5098 | 0 | 0 | 0 | 0 | 31661.5098 | 0 | 100% | Finished | 25671.5098 | 25671.5098 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 | 2011-03-02 08:00 | 5d | 32321.7505 | 35724.0015 | 15d | 0 | 0 | 32321.7505 | 35724.0015 | 25% | Started | 32321.7505 | 68045.752 | 100 | 25 | 25 | 100 | 47.5 | 25
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2011-04-05 17:00 |  | TP Name | 05/04, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 347d | [5 empty] | 1057200.4109 |  | 81.86% |  | 902502.412 | 1082351.7833
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 55d | 69439.3799 | 0 | 0 | 0 | 0 | 69439.3799 | 0 | 100% | Finished | 64896.58 | 64896.58 | 100 | 110 | 100 | 100 | 107.0001 | 100
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 50d | 40662.4614 | 0 | 0 | 0 | 0 | 40662.4614 | 0 | 100% | Finished | 40662.4614 | 40662.4614 | 100 | 100 | 100 | 100 | 100 | 100
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 100% | Finished | 17095.0002 | 17095.0002 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 |  | 0 | 0 | 41890.5708 | 20d | 0 | 0 | 0 | 41890.5708 | 0% | Not Started | 0 | 41890.5708 | 100 |  | 0 | 100 |  | 0
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 |  | 0 | 0 | 42224.2993 | 20d | 0 | 0 | 0 | 42224.2993 | 0% | Not Started | 0 | 42224.2993 | 100 |  | 0 | 100 |  | 0
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 | 2011-03-30 08:00 | 5d | 24999.7601 | 27631.1993 | 15d | 0 | 0 | 24999.7601 | 27631.1993 | 25% | Started | 24999.7601 | 52630.9595 | 100 | 25 | 25 | 100 | 47.5001 | 25
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 |  | 0 | 0 | 8547.5001 | 10d | 0 | 0 | 0 | 8547.5001 | 0% | Not Started | 0 | 8547.5001 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 |  | 0 | 0 | 32447.8911 | 20d | 0 | 0 | 0 | 32447.8911 | 0% | Not Started | 0 | 32447.8911 | 100 |  | 0 | 100 |  | 0
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 |  | 0 | 0 | 27107.9106 | 15d | 0 | 0 | 0 | 27107.9106 | 0% | Not Started | 0 | 27107.9106 | 100 |  | 0 | 100 |  | 0
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 2011-02-02 08:00 | 20d | 31661.5098 | 0 | 0 | 0 | 0 | 31661.5098 | 0 | 100% | Finished | 25671.5098 | 25671.5098 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 | 2011-03-02 08:00 | 20d | 68045.752 | 0 | 0 | 0 | 0 | 68045.752 | 0 | 100% | Finished | 68045.752 | 68045.752 | 100 | 100 | 100 | 100 | 100 | 100
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2011-05-17 17:00 |  | TP Name | 17/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 377d | [5 empty] | 1216651.382 |  | 95.76% |  | 1055844.1041 | 1102536.7838
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 55d | 69439.3799 | 0 | 0 | 0 | 0 | 69439.3799 | 0 | 100% | Finished | 64896.58 | 64896.58 | 100 | 110 | 100 | 100 | 107.0001 | 100
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 50d | 40662.4614 | 0 | 0 | 0 | 0 | 40662.4614 | 0 | 100% | Finished | 40662.4614 | 40662.4614 | 100 | 100 | 100 | 100 | 100 | 100
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 100% | Finished | 17095.0002 | 17095.0002 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 | 2011-04-27 08:00 | 15d | 34559.7706 | 14661.6003 | 10d | 0 | 0 | 34559.7706 | 14661.6003 | 60% | Started | 30161.2912 | 41890.5708 | 100 | 75 | 60 | 100 | 82.5001 | 60
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 | 2011-04-27 08:00 | 15d | 34835.0995 | 22167.5995 | 15d | 0 | 0 | 34835.0995 | 22167.5995 | 50% | Started | 27445.8997 | 42224.2993 | 100 | 75 | 50 | 100 | 82.5001 | 50
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 | 2011-03-30 08:00 | 20d | 52630.9595 | 0 | 0 | 0 | 0 | 52630.9595 | 0 | 100% | Finished | 52630.9595 | 52630.9595 | 100 | 100 | 100 | 100 | 100 | 100
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 | 2011-04-27 08:00 | 10d | 8547.5001 | 0 | 0 | 0 | 0 | 8547.5001 | 0 | 100% | Finished | 8547.5001 | 8547.5001 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 | 2011-04-27 08:00 | 15d | 26769.4908 | 0 | 0 | 0 | 0 | 26769.4908 | 0 | 100% | Finished | 32447.8911 | 32447.8911 | 100 | 75 | 100 | 100 | 82.4999 | 100
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 | 2011-04-27 08:00 | 15d | 27107.9106 | 0 | 0 | 0 | 0 | 27107.9106 | 0 | 100% | Finished | 27107.9106 | 27107.9106 | 100 | 100 | 100 | 100 | 100 | 100
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 2011-02-02 08:00 | 20d | 31661.5098 | 0 | 0 | 0 | 0 | 31661.5098 | 0 | 100% | Finished | 25671.5098 | 25671.5098 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 | 2011-03-02 08:00 | 20d | 68045.752 | 0 | 0 | 0 | 0 | 68045.752 | 0 | 100% | Finished | 68045.752 | 68045.752 | 100 | 100 | 100 | 100 | 100 | 100
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 18072.0005 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 2113 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2011-06-07 17:00 |  | TP Name | 07/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 392d | [5 empty] | 1253480.5818 |  | 98.17% |  | 1082351.7833 | 1102536.7838
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 55d | 69439.3799 | 0 | 0 | 0 | 0 | 69439.3799 | 0 | 100% | Finished | 64896.58 | 64896.58 | 100 | 110 | 100 | 100 | 107.0001 | 100
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 50d | 40662.4614 | 0 | 0 | 0 | 0 | 40662.4614 | 0 | 100% | Finished | 40662.4614 | 40662.4614 | 100 | 100 | 100 | 100 | 100 | 100
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 100% | Finished | 17095.0002 | 17095.0002 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 | 2011-04-27 08:00 | 25d | 49221.371 | 0 | 0 | 0 | 0 | 49221.371 | 0 | 100% | Finished | 41890.5708 | 41890.5708 | 100 | 125 | 100 | 100 | 117.4999 | 100
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 | 2011-04-27 08:00 | 30d | 57002.699 | 0 | 0 | 0 | 0 | 57002.699 | 0 | 100% | Finished | 42224.2993 | 42224.2993 | 100 | 150 | 100 | 100 | 134.9998 | 100
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 | 2011-03-30 08:00 | 20d | 52630.9595 | 0 | 0 | 0 | 0 | 52630.9595 | 0 | 100% | Finished | 52630.9595 | 52630.9595 | 100 | 100 | 100 | 100 | 100 | 100
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 | 2011-04-27 08:00 | 10d | 8547.5001 | 0 | 0 | 0 | 0 | 8547.5001 | 0 | 100% | Finished | 8547.5001 | 8547.5001 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 | 2011-04-27 08:00 | 15d | 26769.4908 | 0 | 0 | 0 | 0 | 26769.4908 | 0 | 100% | Finished | 32447.8911 | 32447.8911 | 100 | 75 | 100 | 100 | 82.4999 | 100
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 | 2011-04-27 08:00 | 15d | 27107.9106 | 0 | 0 | 0 | 0 | 27107.9106 | 0 | 100% | Finished | 27107.9106 | 27107.9106 | 100 | 100 | 100 | 100 | 100 | 100
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 2011-02-02 08:00 | 20d | 31661.5098 | 0 | 0 | 0 | 0 | 31661.5098 | 0 | 100% | Finished | 25671.5098 | 25671.5098 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 | 2011-03-02 08:00 | 20d | 68045.752 | 0 | 0 | 0 | 0 | 68045.752 | 0 | 100% | Finished | 68045.752 | 68045.752 | 100 | 100 | 100 | 100 | 100 | 100
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 |  | 0 | 0 | 18072.0005 | 5d | 0 | 0 | 0 | 18072.0005 | 0% | Not Started | 0 | 18072.0005 | 100 |  | 0 | 100 |  | 0
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 |  | 0 | 0 | 2113 | 1d | 0 | 0 | 0 | 2113 | 0% | Not Started | 0 | 2113 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2011-06-23 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (3) | 2009-12-07 08:00 | 2011-04-13 17:00 | 353d |  |  | 328751.1024 |  |  | 1102536.7838 |  | 404d | [5 empty] | 1289696.7828 |  | 100% |  | 1102536.7838 | 1102536.7838
1 | Sondering | 2009-12-07 08:00 | 2009-12-07 17:00 | 1d |  | 0 | 0 | 55.63 | 445.04 | 445.04 | 2009-12-07 08:00 | 1d | 445.04 | 0 | 0 | 0 | 0 | 445.04 | 0 | 100% | Finished | 445.04 | 445.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | Inrichting | 2009-12-08 08:00 | 2009-12-08 17:00 | 1d |  | 0 | 1053.54 | 307.28 | 2458.24 | 3511.78 | 2009-12-08 08:00 | 1d | 3511.78 | 0 | 0 | 0 | 0 | 3511.78 | 0 | 100% | Finished | 3511.78 | 3511.78 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bouwput + Kelders | 2010-01-06 08:00 | 2010-02-02 17:00 | 20d |  | 0 | 15397.2695 | 224.54 | 35926.3989 | 51323.6685 | 2010-01-27 08:00 | 30d | 69286.8679 | 0 | 0 | 0 | 0 | 69286.8679 | 0 | 100% | Finished | 51323.6685 | 51323.6685 | 100 | 150 | 100 | 100 | 134.9998 | 100
4 | Bouw rioleringen | 2010-02-03 08:00 | 2010-03-16 17:00 | 30d |  | 0 | 18404.1992 | 178.93 | 42943.1982 | 61347.3975 | 2010-03-10 08:00 | 40d | 75661.7969 | 0 | 0 | 0 | 0 | 75661.7969 | 0 | 100% | Finished | 61347.3975 | 61347.3975 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
5 | Afbraakwerken | 2009-12-09 08:00 | 2010-01-05 17:00 | 20d |  | 0 | 3332.2 | 83.31 | 13329.5996 | 16661.7996 | 2009-12-09 08:00 | 35d | 26658.9993 | 0 | 0 | 0 | 0 | 26658.9993 | 0 | 100% | Finished | 16661.7996 | 16661.7996 | 100 | 175 | 100 | 100 | 160.0007 | 100
6 | Ruwbouw | 2010-03-17 08:00 | 2010-07-20 17:00 | 90d |  | 0 | 85166.7812 | 276 | 198720 | 283886.7812 | 2010-05-05 08:00 | 100d | 305966.7812 | 0 | 0 | 0 | 0 | 305966.7812 | 0 | 100% | Finished | 283886.7812 | 283886.7812 | 100 | 111.1111 | 100 | 100 | 107.7777 | 100
7 | Dakstructuur | 2010-07-21 08:00 | 2010-08-31 17:00 | 30d |  | 0 | 10605.9004 | 103.11 | 24746.4001 | 35352.3005 | 2010-08-25 08:00 | 35d | 39476.7006 | 0 | 0 | 0 | 0 | 39476.7006 | 0 | 100% | Finished | 35352.3005 | 35352.3005 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
8 | Dakisolatie | 2010-09-01 08:00 | 2010-09-28 17:00 | 20d |  | 0 | 2250 | 32.81 | 5249.6002 | 7499.6002 | 2010-10-13 08:00 | 20d | 7499.6002 | 0 | 0 | 0 | 0 | 7499.6002 | 0 | 100% | Finished | 7499.6002 | 7499.6002 | 100 | 100 | 100 | 100 | 100 | 100
9 | Dakbedekking & Zinkwerk | 2010-09-01 08:00 | 2010-10-12 17:00 | 30d |  | 0 | 16714.2109 | 162.5 | 39000 | 55714.2109 | 2010-10-13 08:00 | 30d | 55714.2109 | 0 | 0 | 0 | 0 | 55714.2109 | 0 | 100% | Finished | 55714.2109 | 55714.2109 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen Ramen | 2010-07-21 08:00 | 2010-08-10 17:00 | 15d |  | 0 | 23056.6602 | 448.32 | 53798.4009 | 76855.061 | 2010-08-25 08:00 | 30d | 130653.4619 | 0 | 0 | 0 | 0 | 130653.4619 | 0 | 100% | Finished | 76855.061 | 76855.061 | 100 | 200 | 100 | 100 | 169.9998 | 100
11 | Sanitaire technieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 19468.5801 | 113.57 | 45427.9999 | 64896.58 | 2010-11-24 08:00 | 55d | 69439.3799 | 0 | 0 | 0 | 0 | 69439.3799 | 0 | 100% | Finished | 64896.58 | 64896.58 | 100 | 110 | 100 | 100 | 107.0001 | 100
12 | Elektriciteitstechnieken | 2010-10-13 08:00 | 2010-12-21 17:00 | 50d |  | 0 | 12198.46 | 71.16 | 28464.0015 | 40662.4614 | 2010-11-24 08:00 | 50d | 40662.4614 | 0 | 0 | 0 | 0 | 40662.4614 | 0 | 100% | Finished | 40662.4614 | 40662.4614 | 100 | 100 | 100 | 100 | 100 | 100
13 | Ventilatietechnieken | 2010-10-13 08:00 | 2010-11-23 17:00 | 30d |  | 0 | 5128.6001 | 49.86 | 11966.4001 | 17095.0002 | 2010-11-24 08:00 | 35d | 19089.4003 | 0 | 0 | 0 | 0 | 19089.4003 | 0 | 100% | Finished | 17095.0002 | 17095.0002 | 100 | 116.6667 | 100 | 100 | 111.6666 | 100
14 | Trappen en Deuren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12567.3701 | 183.27 | 29323.2007 | 41890.5708 | 2011-04-27 08:00 | 25d | 49221.371 | 0 | 0 | 0 | 0 | 49221.371 | 0 | 100% | Finished | 41890.5708 | 41890.5708 | 100 | 125 | 100 | 100 | 117.4999 | 100
15 | Keukens | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 12667.5 | 184.73 | 29556.7993 | 42224.2993 | 2011-04-27 08:00 | 30d | 57002.699 | 0 | 0 | 0 | 0 | 57002.699 | 0 | 100% | Finished | 42224.2993 | 42224.2993 | 100 | 150 | 100 | 100 | 134.9998 | 100
16 | Pleisterwerken | 2011-02-09 08:00 | 2011-03-08 17:00 | 20d |  | 0 | 15789.3604 | 230.26 | 36841.5991 | 52630.9595 | 2011-03-30 08:00 | 20d | 52630.9595 | 0 | 0 | 0 | 0 | 52630.9595 | 0 | 100% | Finished | 52630.9595 | 52630.9595 | 100 | 100 | 100 | 100 | 100 | 100
17 | Buitenpleisterwerk | 2010-08-11 08:00 | 2010-08-31 17:00 | 15d |  | 0 | 10526.2402 | 204.68 | 24561.5991 | 35087.8394 | 2010-10-06 08:00 | 20d | 43275.0391 | 0 | 0 | 0 | 0 | 43275.0391 | 0 | 100% | Finished | 35087.8394 | 35087.8394 | 100 | 133.3333 | 100 | 100 | 123.3334 | 100
18 | Afwerking Ventilatie | 2011-03-09 08:00 | 2011-03-22 17:00 | 10d |  | 0 | 2564.3 | 74.79 | 5983.2001 | 8547.5001 | 2011-04-27 08:00 | 10d | 8547.5001 | 0 | 0 | 0 | 0 | 8547.5001 | 0 | 100% | Finished | 8547.5001 | 8547.5001 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen Sanitaire Toestellen & Radiatoren | 2011-03-09 08:00 | 2011-04-05 17:00 | 20d |  | 0 | 9734.29 | 141.96 | 22713.6011 | 32447.8911 | 2011-04-27 08:00 | 15d | 26769.4908 | 0 | 0 | 0 | 0 | 26769.4908 | 0 | 100% | Finished | 32447.8911 | 32447.8911 | 100 | 75 | 100 | 100 | 82.4999 | 100
20 | Afwerking | 2011-03-09 08:00 | 2011-03-29 17:00 | 15d |  | 0 | 8132.3101 | 158.13 | 18975.6006 | 27107.9106 | 2011-04-27 08:00 | 15d | 27107.9106 | 0 | 0 | 0 | 0 | 27107.9106 | 0 | 100% | Finished | 27107.9106 | 27107.9106 | 100 | 100 | 100 | 100 | 100 | 100
21 | Chapewerken | 2010-12-22 08:00 | 2011-01-11 17:00 | 15d |  | 0 | 7701.5098 | 149.75 | 17970 | 25671.5098 | 2011-02-02 08:00 | 20d | 31661.5098 | 0 | 0 | 0 | 0 | 31661.5098 | 0 | 100% | Finished | 25671.5098 | 25671.5098 | 100 | 133.3333 | 100 | 100 | 123.3333 | 100
22 | Vloeren | 2011-01-12 08:00 | 2011-02-08 17:00 | 20d |  | 0 | 20413.75 | 297.7 | 47632.002 | 68045.752 | 2011-03-02 08:00 | 20d | 68045.752 | 0 | 0 | 0 | 0 | 68045.752 | 0 | 100% | Finished | 68045.752 | 68045.752 | 100 | 100 | 100 | 100 | 100 | 100
23 | Tuinaanleg | 2010-03-17 08:00 | 2010-03-30 17:00 | 10d |  | 0 | 10033.8701 | 292.65 | 23411.9995 | 33445.8696 | 2010-05-05 08:00 | 15d | 45151.8694 | 0 | 0 | 0 | 0 | 45151.8694 | 0 | 100% | Finished | 33445.8696 | 33445.8696 | 100 | 150 | 100 | 100 | 134.9998 | 100
24 | Schilderwerken | 2011-04-06 08:00 | 2011-04-12 17:00 | 5d |  | 0 | 5421.6001 | 316.26 | 12650.4004 | 18072.0005 | 2011-06-08 08:00 | 10d | 30722.4009 | 0 | 0 | 0 | 0 | 30722.4009 | 0 | 100% | Finished | 18072.0005 | 18072.0005 | 100 | 200 | 100 | 100 | 170 | 100
25 | Opkuis | 2011-04-13 08:00 | 2011-04-13 17:00 | 1d |  | 0 | 422.6 | 211.3 | 1690.4 | 2113 | 2011-06-21 08:00 | 3d | 5493.8001 | 0 | 0 | 0 | 0 | 5493.8001 | 0 | 100% | Finished | 2113 | 2113 | 100 | 300 | 100 | 100 | 260 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
05/01, 2010 | 2009-12-07 08:00 | 2010-01-05 17:00 | 20618.6196 | 14905.9344 | 20618.6196 | 2009-12-24 11:00 | -5712.6852 | 72.29% | -5712.6852 | 72.29% | -8d 5h | 60.8% | 100% | 2011-04-15 16:00 | 2011-10-20 10:00 | 2012-07-09 11:00 | 2011-04-22 09:00 | 2011-10-20 10:00 | 2012-06-26 17:00 | 2011-04-26 14:00 | 2012-02-27 14:00 | 2012-12-21 15:00 | 1108249.469 | 1525082.9596 | 1525082.9596 | 1809618.8953 | 2101667.4898 | 2495251.5527 | 1525082.9596 | 1574511.5003 | 0.60795 | 0.72294 | 0.72294 | 1 | -8.625 | 0.72294 | 1 | 0.60795 | 1
02/02, 2010 | 2010-01-05 17:00 | 2010-02-02 17:00 | 71942.2881 | 42003.6225 | 54994.6886 | 2010-01-11 10:00 | -29938.6656 | 58.39% | -12991.0661 | 76.38% | -16d 6h | 60.12% | 100% | 2011-04-27 14:00 | 2012-03-30 14:00 | 2012-12-18 14:00 | 2011-05-09 12:00 | 2012-03-30 14:00 | 2012-11-29 14:00 | 2011-05-06 15:00 | 2012-03-07 09:00 | 2012-10-29 15:00 | 1115527.8499 | 1443534.236 | 1871437.5979 | 1819049.848 | 2433235.0936 | 2364644.6289 | 1512189.1212 | 1505278.8287 | 0.60119 | 0.76378 | 0.58385 | 1 | -16.75 | 0.76378 | 1 | 0.60119 | 1
16/03, 2010 | 2010-02-02 17:00 | 2010-03-16 17:00 | 133289.6855 | 95714.3871 | 125464.0862 | 2010-02-08 15:00 | -37575.2985 | 71.81% | -29749.6991 | 76.29% | -26d 2h | 63.54% | 100% | 2011-04-29 17:00 | 2011-10-25 14:00 | 2012-05-25 11:00 | 2011-05-12 10:00 | 2011-10-25 14:00 | 2012-04-24 17:00 | 2011-05-20 10:00 | 2012-01-23 12:00 | 2012-08-20 16:00 | 1132286.4829 | 1445224.4254 | 1527542.1307 | 1709971.4647 | 1963332.4149 | 2202463.9642 | 1460905.5029 | 1490851.5122 | 0.63542 | 0.76288 | 0.71809 | 1 | -26.25 | 0.76288 | 1 | 0.63542 | 1
04/05, 2010 | 2010-03-16 17:00 | 2010-05-04 17:00 | 329182.3364 | 133289.6855 | 175564.4841 | 2010-03-16 17:00 | -195892.6509 | 40.49% | -42274.7986 | 75.92% | -35d | 67.29% | 100% | 2011-07-11 15:00 | 2013-04-09 15:00 | 2014-05-01 10:00 | 2011-07-12 14:00 | 2013-04-09 15:00 | 2014-03-14 11:00 | 2011-06-01 17:00 | 2011-12-09 14:00 | 2012-06-12 17:00 | 1144811.5824 | 1452222.66 | 2569290.7738 | 1615973.3663 | 3328496.532 | 2072820.3844 | 1583642.8155 | 1481924.9837 | 0.6729 | 0.75921 | 0.40491 | 1 | -35 | 0.75921 | 1 | 0.6729 | 1
10/08, 2010 | 2010-05-04 17:00 | 2010-08-10 17:00 | 550456.4979 | 391006.334 | 460443.1347 | 2010-06-11 17:00 | -159450.1639 | 71.03% | -69436.8007 | 84.92% | -42d | 76.27% | 100% | 2011-06-23 17:00 | 2011-11-01 17:00 | 2012-03-05 10:00 | 2011-06-24 10:00 | 2011-11-01 17:00 | 2012-01-19 15:00 | 2011-06-10 17:00 | 2011-09-14 16:00 | 2011-11-24 14:00 | 1171973.5845 | 1298330.6119 | 1462131.6637 | 1393338.6133 | 1640016.3696 | 1559006.7159 | 1326660.2308 | 1315751.8938 | 0.76271 | 0.8492 | 0.71033 | 1 | -42 | 0.8492 | 1 | 0.76271 | 1
12/10, 2010 | 2010-08-10 17:00 | 2010-10-12 17:00 | 661131.3485 | 579496.338 | 715526.7372 | 2010-08-20 12:00 | -81635.0105 | 87.65% | -136030.3992 | 80.99% | -37d 4h | 83.11% | 98.94% | 2011-05-20 09:00 | 2011-06-22 15:00 | 2011-11-02 10:00 | 2011-05-23 11:00 | 2011-06-22 15:00 | 2011-08-22 09:00 | 2011-06-06 12:00 | 2011-07-22 15:00 | 2011-09-28 11:00 | 1238567.183 | 1361345.1817 | 1312249.1193 | 1344876.2167 | 1452323.1431 | 1492609.0932 | 1350890.1221 | 1357982.7935 | 0.83108 | 0.80989 | 0.87652 | 0.9894 | -37.5 | 0.80989 | 1 | 0.83108 | 1
23/11, 2010 | 2010-10-12 17:00 | 2010-11-23 17:00 | 754228.5896 | 661131.3485 | 803302.1474 | 2010-10-12 17:00 | -93097.2411 | 87.66% | -142170.799 | 82.3% | -30d | 88.1% | 100% | 2011-05-25 15:00 | 2011-06-22 15:00 | 2011-10-21 10:00 | 2011-05-27 09:00 | 2011-06-22 15:00 | 2011-08-08 09:00 | 2011-05-25 17:00 | 2011-06-20 15:00 | 2011-08-03 14:00 | 1244707.5828 | 1339628.1512 | 1306864.1093 | 1304356.9659 | 1415150.922 | 1412104.6382 | 1332738.6398 | 1332182.1694 | 0.88095 | 0.82302 | 0.87657 | 1 | -30 | 0.82302 | 1 | 0.88095 | 1
11/01, 2011 | 2010-11-23 17:00 | 2011-01-11 17:00 | 809456.8999 | 758726.9162 | 905782.9887 | 2010-11-26 17:00 | -50729.9837 | 93.73% | -147056.0725 | 83.76% | -32d | 88.85% | 99.86% | 2011-05-06 10:00 | 2011-05-17 14:00 | 2011-08-26 14:00 | 2011-05-09 17:00 | 2011-05-17 14:00 | 2011-06-09 17:00 | 2011-05-27 17:00 | 2011-06-15 10:00 | 2011-07-14 14:00 | 1249592.8563 | 1316229.9134 | 1272580.6648 | 1292737.624 | 1343673.2074 | 1367736.9785 | 1306688.296 | 1311305.9958 | 0.8885 | 0.83765 | 0.93733 | 0.99858 | -32 | 0.83765 | 1 | 0.8885 | 1
08/02, 2011 | 2011-01-11 17:00 | 2011-02-08 17:00 | 877502.6518 | 795979.3999 | 946184.8988 | 2010-12-27 15:00 | -81523.252 | 90.71% | -150205.499 | 84.13% | -31d 2h | 89.82% | 100% | 2011-05-20 09:00 | 2011-06-03 09:00 | 2011-09-14 14:00 | 2011-05-24 12:00 | 2011-06-03 09:00 | 2011-06-24 14:00 | 2011-05-27 10:00 | 2011-06-08 17:00 | 2011-07-01 10:00 | 1252742.2828 | 1310591.2734 | 1284139.521 | 1287483.6001 | 1347913.3356 | 1351888.46 | 1304974.7674 | 1305722.7617 | 0.89821 | 0.84125 | 0.9071 | 1 | -31.25 | 0.84125 | 1 | 0.89821 | 1
08/03, 2011 | 2011-02-08 17:00 | 2011-03-08 17:00 | 930133.6113 | 841778.6504 | 996476.6493 | 2011-01-18 17:00 | -88354.9609 | 90.5% | -154697.999 | 84.48% | -35d | 89.3% | 100% | 2011-05-24 10:00 | 2011-06-03 17:00 | 2011-09-13 15:00 | 2011-05-26 17:00 | 2011-06-03 17:00 | 2011-06-21 14:00 | 2011-06-01 17:00 | 2011-06-13 10:00 | 2011-06-29 16:00 | 1257234.7828 | 1305155.6482 | 1284604.5369 | 1288490.0385 | 1337555.2831 | 1342154.8433 | 1300814.1909 | 1301672.063 | 0.89297 | 0.84476 | 0.90501 | 1 | -35 | 0.84476 | 1 | 0.89297 | 1
05/04, 2011 | 2011-03-08 17:00 | 2011-04-05 17:00 | 1082351.7833 | 902502.412 | 1057200.4109 | 2011-02-15 17:00 | -179849.3713 | 83.38% | -154697.999 | 85.37% | -35d | 89.91% | 100% | 2011-07-04 14:00 | 2011-07-21 11:00 | 2011-10-31 16:00 | 2011-07-04 14:00 | 2011-07-21 11:00 | 2011-08-09 11:00 | 2011-06-01 17:00 | 2011-06-08 14:00 | 2011-06-20 11:00 | 1257234.7828 | 1291522.6879 | 1297097.3422 | 1279674.536 | 1338218.0913 | 1317808.8407 | 1292616.7952 | 1289053.1633 | 0.89914 | 0.85367 | 0.83383 | 1 | -35 | 0.85367 | 1 | 0.89914 | 1
17/05, 2011 | 2011-04-05 17:00 | 2011-05-17 17:00 | 1102536.7838 | 1055844.1041 | 1216651.382 | 2011-03-28 15:00 | -46692.6798 | 95.76% | -160807.2779 | 86.78% | -36d 2h | 90.38% | 99.23% | 2011-05-04 17:00 | 2011-05-05 14:00 | 2011-07-22 15:00 | 2011-06-08 17:00 | 2011-06-09 14:00 | 2011-06-14 10:00 | 2011-06-03 10:00 | 2011-06-06 12:00 | 2011-06-08 14:00 | 1263344.0617 | 1270455.4551 | 1265408.9559 | 1268311.3681 | 1272834.837 | 1276179.2926 | 1269364.2786 | 1270012.5168 | 0.90385 | 0.86783 | 0.95765 | 0.99232 | -36.25 | 0.86783 | 1 | 0.90385 | 1
07/06, 2011 | 2011-05-17 17:00 | 2011-06-07 17:00 | 1102536.7838 | 1082351.7833 | 1253480.5818 | 2011-04-05 17:00 | -20185.0005 | 98.17% | -171128.7985 | 86.35% | -45d | 88.52% | 100% | 2011-04-22 12:00 | 2011-04-22 14:00 | 2011-07-12 11:00 | 2011-06-17 09:00 | 2011-06-17 10:00 | 2011-06-20 12:00 | 2011-06-15 17:00 | 2011-06-16 15:00 | 2011-06-17 16:00 | 1273665.5823 | 1276856.9984 | 1274042.0166 | 1276283.2337 | 1277292.95 | 1279888.5222 | 1276233.9834 | 1276739.9471 | 0.8852 | 0.86348 | 0.98169 | 1 | -45 | 0.86348 | 1 | 0.8852 | 1
Actual Schedule | 2011-06-07 17:00 | 2011-06-23 17:00 | 1102536.7838 | 1102536.7838 | 1289696.7828 | 2011-04-13 17:00 | 0 | 100% | -187159.999 | 85.49% | -51d | 87.38% | 100% | 2011-04-13 17:00 | 2011-04-13 17:00 | 2011-07-06 16:00 | 2011-06-23 17:00 | 2011-06-23 17:00 | 2011-06-23 17:00 | 2011-06-23 17:00 | 2011-06-23 17:00 | 2011-06-23 17:00 | 1289696.7828 | 1289696.7828 | 1289696.7828 | 1289696.7828 | 1289696.7828 | 1289696.7828 | 1289696.7828 | 1289696.7828 | 0.87376 | 0.85488 | 1 | 1 | -51 | 0.85488 | 1 | 0.87376 | 1