## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Young Cattle Barn (2) | 1 |  |  | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 | 182.375
1 | werfinstallatie | 1.1 |  | FF5 | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 13.375
2 | Afbraak jongveestal | 1.2 |  | FS6 | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 6.375
3 | omleggen elektrische kabel | 1.3 |  |  | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 0.375
4 | Bijkomende sloopwerken | 1.4 |  |  | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 0.041667
5 | Grondwerken | 1.5 | 1FF | SS6 | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 6.375
6 | Aanvulling afbraak jongveestal | 1.6 | 2FS;5SS | FS7 | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 6.375
7 | plaatfundering-ondergronds | 1.7 | 6FS | FS8 | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 13.375
8 | funderingswanden | 1.8 | 7FS | FS9 | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 27.375
9 | Draagvloeren | 1.9 | 8FS | FS10 | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 13.375
10 | wederaanvulling-binnen | 1.10 | 9FS | FS11 | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 | 1.375
11 | Plaatfundering op volle grond | 1.11 | 10FS | FS12 | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 | 6.375
12 | wederaanvulling-buiten | 1.12 | 11FS | FS14 | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 | 2.375
13 | betonnen binnenwanden | 1.13 |  |  | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 0.041667
14 | Structuurelementen-staal | 1.14 | 12FS | FS15 | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 | 4.375
15 | structuurelementen-gew.beton | 1.15 | 14FS | FS17 | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 | 4.375
16 | Dakstructuur | 1.16 |  |  | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 0.041667
17 | Dakwerken | 1.17 | 15FS | FS23;FS18-4d | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 | 13.375
18 | Buitenramen, -deuren, -poorten | 1.18 | 17FS-4d | FS19-4d | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 | 13.375
19 | Gevelbekledingen | 1.19 | 18FS-4d | FS20-4d | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 | 13.375
20 | Rioleringen | 1.20 | 19FS-4d | FS21 | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 | 13.375
21 | Omgevingeswerken | 1.21 | 20FS |  | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 | 27.375
22 | Elektrische windzeilen | 1.22 |  |  | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 0.041667
23 | Binnenplaatafwerking | 1.23 | 17FS | FS24 | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 | 13.375
24 | Bedrijfsvloeren | 1.24 | 23FS | FS25 | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 | 6.375
25 | Hekkens | 1.25 | 24FS | SS26;SS27 | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 | 20.375
26 | Sanitair | 1.26 | 25SS |  | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 | 27.375
27 | Brandbestrijding | 1.27 | 25SS |  | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 | 27.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Young Cattle Barn (2) | 1048h |  |  |  |  | 99 | 100 | 101
1 | werfinstallatie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Afbraak jongveestal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | omleggen elektrische kabel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Bijkomende sloopwerken | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Grondwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Aanvulling afbraak jongveestal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | plaatfundering-ondergronds | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | funderingswanden | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Draagvloeren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | wederaanvulling-binnen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Plaatfundering op volle grond | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | wederaanvulling-buiten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | betonnen binnenwanden | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Structuurelementen-staal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | structuurelementen-gew.beton | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Dakstructuur | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Dakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Buitenramen, -deuren, -poorten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Gevelbekledingen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Rioleringen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Omgevingeswerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Elektrische windzeilen | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Binnenplaatafwerking | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Bedrijfsvloeren | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Hekkens | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Sanitair | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Brandbestrijding | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2010-10-13 08:00 |  | TP Name | 13/10, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 25d | [5 empty] | 64229.9755 |  | 8.803% |  | 53943.4388 | 108303.4381
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 |  | 0 | 0 | 14601.9995 | 5d | 0 | 0 | 0 | 14601.9995 | 0% | Not Started | 0 | 14601.9995 | 100 |  | 0 | 100 |  | 0
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 |  | 0 | 0 | 21814.3994 | 10d | 0 | 0 | 0 | 21814.3994 | 0% | Not Started | 0 | 21814.3994 | 100 |  | 0 | 100 |  | 0
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 |  | 0 | 0 | 71766.4014 | 20d | 0 | 0 | 0 | 71766.4014 | 0% | Not Started | 0 | 17941.6003 | 100 |  | 0 | 100 |  | 0
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 |  | 0 | 0 | 49276.001 | 10d | 0 | 0 | 0 | 49276.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 |  | 0 | 0 | 2030.4 | 2d | 0 | 0 | 0 | 2030.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 |  | 0 | 0 | 6304.0002 | 5d | 0 | 0 | 0 | 6304.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 |  | 0 | 0 | 3045.6 | 3d | 0 | 0 | 0 | 3045.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 |  | 0 | 0 | 62395.2002 | 5d | 0 | 0 | 0 | 62395.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 |  | 0 | 0 | 67186.8018 | 5d | 0 | 0 | 0 | 67186.8018 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 |  | 0 | 0 | 66583.1982 | 10d | 0 | 0 | 0 | 66583.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 |  | 0 | 0 | 34111.9995 | 10d | 0 | 0 | 0 | 34111.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 |  | 0 | 0 | 19178.3997 | 10d | 0 | 0 | 0 | 19178.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 |  | 0 | 0 | 27883.2007 | 10d | 0 | 0 | 0 | 27883.2007 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 |  | 0 | 0 | 4623.9999 | 10d | 0 | 0 | 0 | 4623.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 |  | 0 | 0 | 1832.4001 | 5d | 0 | 0 | 0 | 1832.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 |  | 0 | 0 | 45640.7996 | 15d | 0 | 0 | 0 | 45640.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 |  | 0 | 0 | 35160 | 20d | 0 | 0 | 0 | 35160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 |  | 0 | 0 | 1302.4001 | 20d | 0 | 0 | 0 | 1302.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2010-11-17 16:00 |  | TP Name | 17/11, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 50d 7h | [5 empty] | 162225.9257 |  | 21.71% |  | 133050.3444 | 210788.2901
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 |  | 0 | 0 | 14601.9995 | 5d | 0 | 0 | 0 | 14601.9995 | 0% | Not Started | 0 | 14601.9995 | 100 |  | 0 | 100 |  | 0
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 11d 7h | 42611.3008 | 10764.9602 | 3d | 26823.75 | 6705.9399 | 69435.0508 | 17470.9001 | 79.83% | Started | 57292.5062 | 71766.4014 | 100 | 59.375 | 79.8319 | 100 | 96.7515 | 79.8319
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 |  | 0 | 0 | 49276.001 | 10d | 0 | 0 | 0 | 49276.001 | 0% | Not Started | 0 | 48660.051 | 100 |  | 0 | 100 |  | 0
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 |  | 0 | 0 | 2030.4 | 2d | 0 | 0 | 0 | 2030.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 |  | 0 | 0 | 6304.0002 | 5d | 0 | 0 | 0 | 6304.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 |  | 0 | 0 | 3045.6 | 3d | 0 | 0 | 0 | 3045.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 |  | 0 | 0 | 62395.2002 | 5d | 0 | 0 | 0 | 62395.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 |  | 0 | 0 | 67186.8018 | 5d | 0 | 0 | 0 | 67186.8018 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 |  | 0 | 0 | 66583.1982 | 10d | 0 | 0 | 0 | 66583.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 |  | 0 | 0 | 34111.9995 | 10d | 0 | 0 | 0 | 34111.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 |  | 0 | 0 | 19178.3997 | 10d | 0 | 0 | 0 | 19178.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 |  | 0 | 0 | 27883.2007 | 10d | 0 | 0 | 0 | 27883.2007 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 |  | 0 | 0 | 4623.9999 | 10d | 0 | 0 | 0 | 4623.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 |  | 0 | 0 | 1832.4001 | 5d | 0 | 0 | 0 | 1832.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 |  | 0 | 0 | 45640.7996 | 15d | 0 | 0 | 0 | 45640.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 |  | 0 | 0 | 35160 | 20d | 0 | 0 | 0 | 35160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 |  | 0 | 0 | 1302.4001 | 20d | 0 | 0 | 0 | 1302.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2010-12-22 16:00 |  | TP Name | 22/12, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 75d 7h | [5 empty] | 206085.8242 |  | 26.46% |  | 162127.2391 | 364851.592
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 100% | Finished | 1 | 1 | 100 | 12000 | 100 | 100 | 1105000 | 100
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 57.5 | 100 | 100 | 105.0473 | 100
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 100% | Finished | 71766.4014 | 71766.4014 | 100 | 75 | 100 | 100 | 121.0956 | 100
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 |  | 0 | 0 | 49276.001 | 10d | 0 | 0 | 0 | 49276.001 | 0% | Not Started | 0 | 49276.001 | 100 |  | 0 | 100 |  | 0
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 |  | 0 | 0 | 2030.4 | 2d | 0 | 0 | 0 | 2030.4 | 0% | Not Started | 0 | 2030.4 | 100 |  | 0 | 100 |  | 0
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 |  | 0 | 0 | 6304.0002 | 5d | 0 | 0 | 0 | 6304.0002 | 0% | Not Started | 0 | 6304.0002 | 100 |  | 0 | 100 |  | 0
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 |  | 0 | 0 | 3045.6 | 3d | 0 | 0 | 0 | 3045.6 | 0% | Not Started | 0 | 3045.6 | 100 |  | 0 | 100 |  | 0
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 |  | 0 | 0 | 62395.2002 | 5d | 0 | 0 | 0 | 62395.2002 | 0% | Not Started | 0 | 62395.2002 | 100 |  | 0 | 100 |  | 0
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 |  | 0 | 0 | 67186.8018 | 5d | 0 | 0 | 0 | 67186.8018 | 0% | Not Started | 0 | 67186.8018 | 100 |  | 0 | 100 |  | 0
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 |  | 0 | 0 | 66583.1982 | 10d | 0 | 0 | 0 | 66583.1982 | 0% | Not Started | 0 | 12484.3497 | 100 |  | 0 | 100 |  | 0
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 |  | 0 | 0 | 34111.9995 | 10d | 0 | 0 | 0 | 34111.9995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 |  | 0 | 0 | 19178.3997 | 10d | 0 | 0 | 0 | 19178.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 |  | 0 | 0 | 27883.2007 | 10d | 0 | 0 | 0 | 27883.2007 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 |  | 0 | 0 | 4623.9999 | 10d | 0 | 0 | 0 | 4623.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 |  | 0 | 0 | 1832.4001 | 5d | 0 | 0 | 0 | 1832.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 |  | 0 | 0 | 45640.7996 | 15d | 0 | 0 | 0 | 45640.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 |  | 0 | 0 | 35160 | 20d | 0 | 0 | 0 | 35160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 |  | 0 | 0 | 1302.4001 | 20d | 0 | 0 | 0 | 1302.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-01-26 16:00 |  | TP Name | 26/01, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 100d 7h | [5 empty] | 249017.9047 |  | 34.5% |  | 211403.2401 | 467509.7499
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 100% | Finished | 1 | 1 | 100 | 12000 | 100 | 100 | 1105000 | 100
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 57.5 | 100 | 100 | 105.0473 | 100
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 100% | Finished | 71766.4014 | 71766.4014 | 100 | 75 | 100 | 100 | 121.0956 | 100
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 2011-01-17 08:00 | 5d | 24638.0005 | 0 | 0 | 18294.0801 | 0 | 42932.0806 | 0 | 100% | Finished | 49276.001 | 49276.001 | 100 | 50 | 100 | 100 | 87.1257 | 100
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 |  | 0 | 0 | 2030.4 | 2d | 0 | 0 | 0 | 2030.4 | 0% | Not Started | 0 | 2030.4 | 100 |  | 0 | 100 |  | 0
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 |  | 0 | 0 | 6304.0002 | 5d | 0 | 0 | 0 | 6304.0002 | 0% | Not Started | 0 | 6304.0002 | 100 |  | 0 | 100 |  | 0
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 |  | 0 | 0 | 3045.6 | 3d | 0 | 0 | 0 | 3045.6 | 0% | Not Started | 0 | 3045.6 | 100 |  | 0 | 100 |  | 0
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 |  | 0 | 0 | 62395.2002 | 5d | 0 | 0 | 0 | 62395.2002 | 0% | Not Started | 0 | 62395.2002 | 100 |  | 0 | 100 |  | 0
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 |  | 0 | 0 | 67186.8018 | 5d | 0 | 0 | 0 | 67186.8018 | 0% | Not Started | 0 | 67186.8018 | 100 |  | 0 | 100 |  | 0
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 |  | 0 | 0 | 66583.1982 | 10d | 0 | 0 | 0 | 66583.1982 | 0% | Not Started | 0 | 66583.1982 | 100 |  | 0 | 100 |  | 0
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 |  | 0 | 0 | 34111.9995 | 10d | 0 | 0 | 0 | 34111.9995 | 0% | Not Started | 0 | 34111.9995 | 100 |  | 0 | 100 |  | 0
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 |  | 0 | 0 | 19178.3997 | 10d | 0 | 0 | 0 | 19178.3997 | 0% | Not Started | 0 | 11267.3098 | 100 |  | 0 | 100 |  | 0
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 |  | 0 | 0 | 27883.2007 | 10d | 0 | 0 | 0 | 27883.2007 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 |  | 0 | 0 | 4623.9999 | 10d | 0 | 0 | 0 | 4623.9999 | 0% | Not Started | 0 | 3179 | 100 |  | 0 | 100 |  | 0
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 |  | 0 | 0 | 1832.4001 | 5d | 0 | 0 | 0 | 1832.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 |  | 0 | 0 | 45640.7996 | 15d | 0 | 0 | 0 | 45640.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 |  | 0 | 0 | 35160 | 20d | 0 | 0 | 0 | 35160 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 |  | 0 | 0 | 1302.4001 | 20d | 0 | 0 | 0 | 1302.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-03-02 16:00 |  | TP Name | 02/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 126d | [5 empty] | 313663.2048 |  | 45.51% |  | 278874.4404 | 600900.4599
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 100% | Finished | 1 | 1 | 100 | 12000 | 100 | 100 | 1105000 | 100
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 57.5 | 100 | 100 | 105.0473 | 100
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 100% | Finished | 71766.4014 | 71766.4014 | 100 | 75 | 100 | 100 | 121.0956 | 100
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 2011-01-17 08:00 | 5d | 24638.0005 | 0 | 0 | 18294.0801 | 0 | 42932.0806 | 0 | 100% | Finished | 49276.001 | 49276.001 | 100 | 50 | 100 | 100 | 87.1257 | 100
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | -669.93 | 0 | 2375.67 | 0 | 100% | Finished | 2030.4 | 2030.4 | 100 | 150 | 100 | 100 | 117.005 | 100
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 |  | 0 | 0 | 6304.0002 | 5d | 0 | 0 | 0 | 6304.0002 | 0% | Not Started | 0 | 6304.0002 | 100 |  | 0 | 100 |  | 0
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | 518.03 | 0 | 3563.6301 | 0 | 100% | Finished | 3045.6 | 3045.6 | 100 | 100 | 100 | 100 | 117.0091 | 100
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 | 2011-02-21 08:00 | 8d | 99832.3203 | 0 | 0 | -41126.3203 | 0 | 58706 | 0 | 100% | Finished | 62395.2002 | 62395.2002 | 100 | 160 | 100 | 100 | 94.0874 | 100
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 |  | 0 | 0 | 67186.8018 | 5d | 0 | 0 | 0 | 67186.8018 | 0% | Not Started | 0 | 67186.8018 | 100 |  | 0 | 100 |  | 0
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 |  | 0 | 0 | 66583.1982 | 10d | 0 | 0 | 0 | 66583.1982 | 0% | Not Started | 0 | 66583.1982 | 100 |  | 0 | 100 |  | 0
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 |  | 0 | 0 | 34111.9995 | 10d | 0 | 0 | 0 | 34111.9995 | 0% | Not Started | 0 | 34111.9995 | 100 |  | 0 | 100 |  | 0
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 |  | 0 | 0 | 19178.3997 | 10d | 0 | 0 | 0 | 19178.3997 | 0% | Not Started | 0 | 19178.3997 | 100 |  | 0 | 100 |  | 0
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 |  | 0 | 0 | 27883.2007 | 10d | 0 | 0 | 0 | 27883.2007 | 0% | Not Started | 0 | 27883.2007 | 100 |  | 0 | 100 |  | 0
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 17913.0699 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 |  | 0 | 0 | 4623.9999 | 10d | 0 | 0 | 0 | 4623.9999 | 0% | Not Started | 0 | 4623.9999 | 100 |  | 0 | 100 |  | 0
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 |  | 0 | 0 | 1832.4001 | 5d | 0 | 0 | 0 | 1832.4001 | 0% | Not Started | 0 | 1832.4001 | 100 |  | 0 | 100 |  | 0
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 |  | 0 | 0 | 45640.7996 | 15d | 0 | 0 | 0 | 45640.7996 | 0% | Not Started | 0 | 45640.7996 | 100 |  | 0 | 100 |  | 0
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 |  | 0 | 0 | 35160 | 20d | 0 | 0 | 0 | 35160 | 0% | Not Started | 0 | 29666.25 | 100 |  | 0 | 100 |  | 0
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 |  | 0 | 0 | 1302.4001 | 20d | 0 | 0 | 0 | 1302.4001 | 0% | Not Started | 0 | 1098.9 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2011-04-06 16:00 |  | TP Name | 06/04, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 150d 7h | [5 empty] | 428397.0269 |  | 57.5% |  | 352367.2424 | 612769.4399
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 100% | Finished | 1 | 1 | 100 | 12000 | 100 | 100 | 1105000 | 100
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 57.5 | 100 | 100 | 105.0473 | 100
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 100% | Finished | 71766.4014 | 71766.4014 | 100 | 75 | 100 | 100 | 121.0956 | 100
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 2011-01-17 08:00 | 5d | 24638.0005 | 0 | 0 | 18294.0801 | 0 | 42932.0806 | 0 | 100% | Finished | 49276.001 | 49276.001 | 100 | 50 | 100 | 100 | 87.1257 | 100
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | -669.93 | 0 | 2375.67 | 0 | 100% | Finished | 2030.4 | 2030.4 | 100 | 150 | 100 | 100 | 117.005 | 100
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 | 2011-03-07 08:00 | 9d | 11347.2004 | 0 | 0 | -5422.3901 | 0 | 5924.8103 | 0 | 100% | Finished | 6304.0002 | 6304.0002 | 100 | 180 | 100 | 100 | 93.9849 | 100
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | 518.03 | 0 | 3563.6301 | 0 | 100% | Finished | 3045.6 | 3045.6 | 100 | 100 | 100 | 100 | 117.0091 | 100
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 10d | 80 | 0 | 0 | 10301.5 | 0 | 10381.5 | 0 | 100% | Finished | 1 | 1 | 100 | 8000 | 100 | 100 | 1038150 | 100
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 | 2011-02-21 08:00 | 8d | 99832.3203 | 0 | 0 | -41126.3203 | 0 | 58706 | 0 | 100% | Finished | 62395.2002 | 62395.2002 | 100 | 160 | 100 | 100 | 94.0874 | 100
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 | 2011-03-07 08:00 | 5d | 67186.8018 | 0 | 0 | 15457.2695 | 0 | 82644.0713 | 0 | 100% | Finished | 67186.8018 | 67186.8018 | 100 | 100 | 100 | 100 | 123.0064 | 100
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 5d | 40 | 0 | 0 | 15743.4404 | 0 | 15783.4404 | 0 | 100% | Finished | 1 | 1 | 100 | 4000 | 100 | 100 | 1578344.043 | 100
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 |  | 0 | 0 | 66583.1982 | 10d | 0 | 0 | 0 | 66583.1982 | 0% | Not Started | 0 | 66583.1982 | 100 |  | 0 | 100 |  | 0
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 |  | 0 | 0 | 34111.9995 | 10d | 0 | 0 | 0 | 34111.9995 | 0% | Not Started | 0 | 34111.9995 | 100 |  | 0 | 100 |  | 0
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 |  | 0 | 0 | 19178.3997 | 10d | 0 | 0 | 0 | 19178.3997 | 0% | Not Started | 0 | 19178.3997 | 100 |  | 0 | 100 |  | 0
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 |  | 0 | 0 | 27883.2007 | 10d | 0 | 0 | 0 | 27883.2007 | 0% | Not Started | 0 | 27883.2007 | 100 |  | 0 | 100 |  | 0
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 24084.7998 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 |  | 0 | 0 | 4623.9999 | 10d | 0 | 0 | 0 | 4623.9999 | 0% | Not Started | 0 | 4623.9999 | 100 |  | 0 | 100 |  | 0
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 |  | 0 | 0 | 1832.4001 | 5d | 0 | 0 | 0 | 1832.4001 | 0% | Not Started | 0 | 1832.4001 | 100 |  | 0 | 100 |  | 0
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 |  | 0 | 0 | 45640.7996 | 15d | 0 | 0 | 0 | 45640.7996 | 0% | Not Started | 0 | 45640.7996 | 100 |  | 0 | 100 |  | 0
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 |  | 0 | 0 | 35160 | 20d | 0 | 0 | 0 | 35160 | 0% | Not Started | 0 | 35160 | 100 |  | 0 | 100 |  | 0
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 |  | 0 | 0 | 1302.4001 | 20d | 0 | 0 | 0 | 1302.4001 | 0% | Not Started | 0 | 1302.4001 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2011-05-11 16:00 |  | TP Name | 11/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 175d 7h | [5 empty] | 528318.2154 |  | 80.99% |  | 496257.9888 | 612769.4399
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 100% | Finished | 1 | 1 | 100 | 12000 | 100 | 100 | 1105000 | 100
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 57.5 | 100 | 100 | 105.0473 | 100
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 100% | Finished | 71766.4014 | 71766.4014 | 100 | 75 | 100 | 100 | 121.0956 | 100
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 2011-01-17 08:00 | 5d | 24638.0005 | 0 | 0 | 18294.0801 | 0 | 42932.0806 | 0 | 100% | Finished | 49276.001 | 49276.001 | 100 | 50 | 100 | 100 | 87.1257 | 100
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | -669.93 | 0 | 2375.67 | 0 | 100% | Finished | 2030.4 | 2030.4 | 100 | 150 | 100 | 100 | 117.005 | 100
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 | 2011-03-07 08:00 | 9d | 11347.2004 | 0 | 0 | -5422.3901 | 0 | 5924.8103 | 0 | 100% | Finished | 6304.0002 | 6304.0002 | 100 | 180 | 100 | 100 | 93.9849 | 100
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | 518.03 | 0 | 3563.6301 | 0 | 100% | Finished | 3045.6 | 3045.6 | 100 | 100 | 100 | 100 | 117.0091 | 100
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 10d | 80 | 0 | 0 | 10301.5 | 0 | 10381.5 | 0 | 100% | Finished | 1 | 1 | 100 | 8000 | 100 | 100 | 1038150 | 100
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 | 2011-02-21 08:00 | 8d | 99832.3203 | 0 | 0 | -41126.3203 | 0 | 58706 | 0 | 100% | Finished | 62395.2002 | 62395.2002 | 100 | 160 | 100 | 100 | 94.0874 | 100
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 | 2011-03-07 08:00 | 5d | 67186.8018 | 0 | 0 | 15457.2695 | 0 | 82644.0713 | 0 | 100% | Finished | 67186.8018 | 67186.8018 | 100 | 100 | 100 | 100 | 123.0064 | 100
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 5d | 40 | 0 | 0 | 15743.4404 | 0 | 15783.4404 | 0 | 100% | Finished | 1 | 1 | 100 | 4000 | 100 | 100 | 1578344.043 | 100
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 | 2011-04-20 08:00 | 7d | 46608.2388 | 0 | 0 | -8569.29 | 0 | 38038.9487 | 0 | 100% | Finished | 66583.1982 | 66583.1982 | 100 | 70 | 100 | 100 | 57.13 | 100
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 | 2011-04-15 08:00 | 6d | 20467.1997 | 0 | 0 | 12194.2002 | 0 | 32661.3999 | 0 | 100% | Finished | 34111.9995 | 34111.9995 | 100 | 60 | 100 | 100 | 95.7475 | 100
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 | 2011-05-04 08:00 | 5d 7h | 11267.3098 | 7911.0899 | 4d 1h | -8291.3096 | -5527.54 | 2976.0002 | 2383.5498 | 58.75% | Started | 11267.3093 | 19178.3997 | 100 | 58.75 | 58.75 | 100 | 15.5175 | 58.75
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 |  | 0 | 0 | 27883.2007 | 10d | 0 | 0 | 0 | 27883.2007 | 0% | Not Started | 0 | 27883.2007 | 100 |  | 0 | 100 |  | 0
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 24084.7998 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 | 2011-05-11 08:00 | 1h | 57.8 | 0 | 0 | -57.8 | 0 | 0 | 0 | 100% | Finished | 4623.9999 | 4623.9999 | 100 | 1.25 | 100 | 100 |  | 100
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 |  | 0 | 0 | 1832.4001 | 5d | 0 | 0 | 0 | 1832.4001 | 0% | Not Started | 0 | 1832.4001 | 100 |  | 0 | 100 |  | 0
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 | 2011-05-04 08:00 | 5d 7h | 17875.9798 | 15213.5999 | 5d | 5616.6899 | 4680.5698 | 23492.6698 | 19894.1697 | 54.02% | Started | 24656.5226 | 45640.7996 | 100 | 39.1667 | 54.023 | 100 | 51.473 | 54.023
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 | 2011-05-11 08:00 | 7h | 1538.25 | 19338 | 11d | 1156.9399 | 12726.3203 | 2695.1899 | 32064.3203 | 7.368% | Started | 2590.7368 | 35160 | 100 | 4.375 | 7.3684 | 100 | 7.6655 | 7.3684
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 | 2011-05-11 08:00 | 7h | 56.98 | 1245.4201 | 19d 1h | 0 | 0 | 56.98 | 1245.4201 | 4.375% | Started | 56.98 | 1302.4001 | 100 | 4.375 | 4.375 | 100 | 4.375 | 4.375

## TP8
| TP Status Date | 2011-06-15 16:00 |  | TP Name | 15/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 200d 7h | [5 empty] | 605852.8848 |  | 94.68% |  | 580197.4489 | 612769.4399
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 100% | Finished | 1 | 1 | 100 | 12000 | 100 | 100 | 1105000 | 100
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 57.5 | 100 | 100 | 105.0473 | 100
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 100% | Finished | 71766.4014 | 71766.4014 | 100 | 75 | 100 | 100 | 121.0956 | 100
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 2011-01-17 08:00 | 5d | 24638.0005 | 0 | 0 | 18294.0801 | 0 | 42932.0806 | 0 | 100% | Finished | 49276.001 | 49276.001 | 100 | 50 | 100 | 100 | 87.1257 | 100
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | -669.93 | 0 | 2375.67 | 0 | 100% | Finished | 2030.4 | 2030.4 | 100 | 150 | 100 | 100 | 117.005 | 100
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 | 2011-03-07 08:00 | 9d | 11347.2004 | 0 | 0 | -5422.3901 | 0 | 5924.8103 | 0 | 100% | Finished | 6304.0002 | 6304.0002 | 100 | 180 | 100 | 100 | 93.9849 | 100
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | 518.03 | 0 | 3563.6301 | 0 | 100% | Finished | 3045.6 | 3045.6 | 100 | 100 | 100 | 100 | 117.0091 | 100
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 10d | 80 | 0 | 0 | 10301.5 | 0 | 10381.5 | 0 | 100% | Finished | 1 | 1 | 100 | 8000 | 100 | 100 | 1038150 | 100
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 | 2011-02-21 08:00 | 8d | 99832.3203 | 0 | 0 | -41126.3203 | 0 | 58706 | 0 | 100% | Finished | 62395.2002 | 62395.2002 | 100 | 160 | 100 | 100 | 94.0874 | 100
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 | 2011-03-07 08:00 | 5d | 67186.8018 | 0 | 0 | 15457.2695 | 0 | 82644.0713 | 0 | 100% | Finished | 67186.8018 | 67186.8018 | 100 | 100 | 100 | 100 | 123.0064 | 100
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 5d | 40 | 0 | 0 | 15743.4404 | 0 | 15783.4404 | 0 | 100% | Finished | 1 | 1 | 100 | 4000 | 100 | 100 | 1578344.043 | 100
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 | 2011-04-20 08:00 | 7d | 46608.2388 | 0 | 0 | -8569.29 | 0 | 38038.9487 | 0 | 100% | Finished | 66583.1982 | 66583.1982 | 100 | 70 | 100 | 100 | 57.13 | 100
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 | 2011-04-15 08:00 | 6d | 20467.1997 | 0 | 0 | 12194.2002 | 0 | 32661.3999 | 0 | 100% | Finished | 34111.9995 | 34111.9995 | 100 | 60 | 100 | 100 | 95.7475 | 100
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 | 2011-05-04 08:00 | 9d | 17260.5597 | 0 | 0 | -13006.5098 | 0 | 4254.0499 | 0 | 100% | Finished | 19178.3997 | 19178.3997 | 100 | 90 | 100 | 100 | 22.1815 | 100
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 | 2011-05-25 08:00 | 16d | 44613.1211 | 19518.2405 | 7d | -26155.3809 | -11442.9404 | 18457.7402 | 8075.3 | 69.57% | Started | 19397.0095 | 27883.2007 | 100 | 160 | 69.5652 | 100 | 66.1966 | 69.5652
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 |  | 0 | 0 | 24084.7998 | 20d | 0 | 0 | 0 | 24084.7998 | 0% | Not Started | 0 | 24084.7998 | 100 |  | 0 | 100 |  | 0
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 |  | 0 | 0 | 1 | 1h | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 | 2011-05-11 08:00 | 1h | 57.8 | 0 | 0 | -57.8 | 0 | 0 | 0 | 100% | Finished | 4623.9999 | 4623.9999 | 100 | 1.25 | 100 | 100 |  | 100
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 | 2011-06-15 08:00 | 7h | 320.67 | 0 | 0 | 1231.58 | 0 | 1552.25 | 0 | 100% | Finished | 1832.4001 | 1832.4001 | 100 | 17.5 | 100 | 100 | 84.7113 | 100
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 | 2011-05-04 08:00 | 11d | 33469.9197 | 0 | 0 | 12959.6396 | 0 | 46429.5593 | 0 | 100% | Finished | 45640.7996 | 45640.7996 | 100 | 73.3333 | 100 | 100 | 101.7282 | 100
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 | 2011-05-11 08:00 | 12d | 21096 | 0 | 0 | 13663.5098 | 0 | 34759.5098 | 0 | 100% | Finished | 35160 | 35160 | 100 | 60 | 100 | 100 | 98.8609 | 100
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 | 2011-05-11 08:00 | 20d | 1302.4001 | 0 | 0 | 0 | 0 | 1302.4001 | 0 | 100% | Finished | 1302.4001 | 1302.4001 | 100 | 100 | 100 | 100 | 100 | 100

## TP9
| TP Status Date | 2011-06-28 16:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn (2) | 2010-09-08 08:00 | 2011-03-09 17:00 | 131d |  |  | 0 |  |  | 612769.4399 |  | 209d 7h | [5 empty] | 646473.646 |  | 100% |  | 612769.4399 | 612769.4399
1 | werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 0 | 104.63 | 8370.3998 | 8370.3998 | 2010-09-08 08:00 | 10d | 8370.3998 | 0 | 0 | 0 | 0 | 8370.3998 | 0 | 100% | Finished | 8370.3998 | 8370.3998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-09-13 08:00 | 15d | 43805.9985 | 0 | 0 | -26666.0293 | 0 | 17139.9692 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 300 | 100 | 100 | 117.381 | 100
3 | omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 0 | 2424.1299 | 19393.0391 | 19393.0391 | 2010-09-13 08:00 | 3d | 58179.1172 | 0 | 0 | -38786.1211 | 0 | 19392.9961 | 0 | 100% | Finished | 19393.0391 | 19393.0391 | 100 | 300 | 100 | 100 | 99.9998 | 100
4 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2010-11-29 08:00 | 15d | 120 | 0 | 0 | 10930 | 0 | 11050 | 0 | 100% | Finished | 1 | 1 | 100 | 12000 | 100 | 100 | 1105000 | 100
5 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 289.45 | 11578.0005 | 11578.0005 | 2010-10-04 08:00 | 2d | 4631.2002 | 0 | 0 | 14695.4102 | 0 | 19326.6104 | 0 | 100% | Finished | 11578.0005 | 11578.0005 | 100 | 40 | 100 | 100 | 166.9253 | 100
6 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 0 | 365.05 | 14601.9995 | 14601.9995 | 2010-12-20 08:00 | 2d 7h | 8396.1497 | 0 | 0 | 6942.8501 | 0 | 15338.9998 | 0 | 100% | Finished | 14601.9995 | 14601.9995 | 100 | 57.5 | 100 | 100 | 105.0473 | 100
7 | plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 0 | 272.68 | 21814.3994 | 21814.3994 | 2010-10-14 08:00 | 10d | 21814.3994 | 0 | 0 | 6746.5 | 0 | 28560.8994 | 0 | 100% | Finished | 21814.3994 | 21814.3994 | 100 | 100 | 100 | 100 | 130.9268 | 100
8 | funderingswanden | 2010-10-06 08:00 | 2010-11-02 17:00 | 20d |  | 0 | 0 | 448.54 | 71766.4014 | 71766.4014 | 2010-11-02 08:00 | 15d | 53824.801 | 0 | 0 | 33081.1484 | 0 | 86905.9495 | 0 | 100% | Finished | 71766.4014 | 71766.4014 | 100 | 75 | 100 | 100 | 121.0956 | 100
9 | Draagvloeren | 2010-11-04 08:00 | 2010-11-17 17:00 | 10d |  | 0 | 0 | 615.95 | 49276.001 | 49276.001 | 2011-01-17 08:00 | 5d | 24638.0005 | 0 | 0 | 18294.0801 | 0 | 42932.0806 | 0 | 100% | Finished | 49276.001 | 49276.001 | 100 | 50 | 100 | 100 | 87.1257 | 100
10 | wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 0 | 126.9 | 2030.4 | 2030.4 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | -669.93 | 0 | 2375.67 | 0 | 100% | Finished | 2030.4 | 2030.4 | 100 | 150 | 100 | 100 | 117.005 | 100
11 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 0 | 157.6 | 6304.0002 | 6304.0002 | 2011-03-07 08:00 | 9d | 11347.2004 | 0 | 0 | -5422.3901 | 0 | 5924.8103 | 0 | 100% | Finished | 6304.0002 | 6304.0002 | 100 | 180 | 100 | 100 | 93.9849 | 100
12 | wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 0 | 126.9 | 3045.6 | 3045.6 | 2011-02-14 08:00 | 3d | 3045.6 | 0 | 0 | 518.03 | 0 | 3563.6301 | 0 | 100% | Finished | 3045.6 | 3045.6 | 100 | 100 | 100 | 100 | 117.0091 | 100
13 | betonnen binnenwanden | 2010-09-08 08:00 | 2010-09-08 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 10d | 80 | 0 | 0 | 10301.5 | 0 | 10381.5 | 0 | 100% | Finished | 1 | 1 | 100 | 8000 | 100 | 100 | 1038150 | 100
14 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 0 | 1559.88 | 62395.2002 | 62395.2002 | 2011-02-21 08:00 | 8d | 99832.3203 | 0 | 0 | -41126.3203 | 0 | 58706 | 0 | 100% | Finished | 62395.2002 | 62395.2002 | 100 | 160 | 100 | 100 | 94.0874 | 100
15 | structuurelementen-gew.beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 0 | 1679.67 | 67186.8018 | 67186.8018 | 2011-03-07 08:00 | 5d | 67186.8018 | 0 | 0 | 15457.2695 | 0 | 82644.0713 | 0 | 100% | Finished | 67186.8018 | 67186.8018 | 100 | 100 | 100 | 100 | 123.0064 | 100
16 | Dakstructuur | 2010-12-20 08:00 | 2010-12-20 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-03-21 08:00 | 5d | 40 | 0 | 0 | 15743.4404 | 0 | 15783.4404 | 0 | 100% | Finished | 1 | 1 | 100 | 4000 | 100 | 100 | 1578344.043 | 100
17 | Dakwerken | 2010-12-21 08:00 | 2011-01-03 17:00 | 10d |  | 0 | 0 | 832.29 | 66583.1982 | 66583.1982 | 2011-04-20 08:00 | 7d | 46608.2388 | 0 | 0 | -8569.29 | 0 | 38038.9487 | 0 | 100% | Finished | 66583.1982 | 66583.1982 | 100 | 70 | 100 | 100 | 57.13 | 100
18 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 0 | 426.4 | 34111.9995 | 34111.9995 | 2011-04-15 08:00 | 6d | 20467.1997 | 0 | 0 | 12194.2002 | 0 | 32661.3999 | 0 | 100% | Finished | 34111.9995 | 34111.9995 | 100 | 60 | 100 | 100 | 95.7475 | 100
19 | Gevelbekledingen | 2011-01-19 08:00 | 2011-02-01 17:00 | 10d |  | 0 | 0 | 239.73 | 19178.3997 | 19178.3997 | 2011-05-04 08:00 | 9d | 17260.5597 | 0 | 0 | -13006.5098 | 0 | 4254.0499 | 0 | 100% | Finished | 19178.3997 | 19178.3997 | 100 | 90 | 100 | 100 | 22.1815 | 100
20 | Rioleringen | 2011-01-27 08:00 | 2011-02-09 17:00 | 10d |  | 0 | 0 | 348.54 | 27883.2007 | 27883.2007 | 2011-05-25 08:00 | 23d | 64131.3616 | 0 | 0 | -37598.3594 | 0 | 26533.0022 | 0 | 100% | Finished | 27883.2007 | 27883.2007 | 100 | 230 | 100 | 100 | 95.1577 | 100
21 | Omgevingeswerken | 2011-02-10 08:00 | 2011-03-09 17:00 | 20d |  | 0 | 0 | 150.53 | 24084.7998 | 24084.7998 | 2011-06-17 08:00 | 7d 7h | 9483.3899 | 0 | 0 | 17458.6094 | 0 | 26941.9993 | 0 | 100% | Finished | 24084.7998 | 24084.7998 | 100 | 39.375 | 100 | 100 | 111.8631 | 100
22 | Elektrische windzeilen | 2011-01-04 08:00 | 2011-01-04 09:00 | 1h |  | 0 | 0 | 1 | 1 | 1 | 2011-06-23 08:00 | 2d | 16 | 0 | 0 | 5587.5 | 0 | 5603.5 | 0 | 100% | Finished | 1 | 1 | 100 | 1600 | 100 | 100 | 560350 | 100
23 | Binnenplaatafwerking | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 0 | 57.8 | 4623.9999 | 4623.9999 | 2011-05-11 08:00 | 1h | 57.8 | 0 | 0 | -57.8 | 0 | 0 | 0 | 100% | Finished | 4623.9999 | 4623.9999 | 100 | 1.25 | 100 | 100 |  | 100
24 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 0 | 45.81 | 1832.4001 | 1832.4001 | 2011-06-15 08:00 | 7h | 320.67 | 0 | 0 | 1231.58 | 0 | 1552.25 | 0 | 100% | Finished | 1832.4001 | 1832.4001 | 100 | 17.5 | 100 | 100 | 84.7113 | 100
25 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 0 | 380.34 | 45640.7996 | 45640.7996 | 2011-05-04 08:00 | 11d | 33469.9197 | 0 | 0 | 12959.6396 | 0 | 46429.5593 | 0 | 100% | Finished | 45640.7996 | 45640.7996 | 100 | 73.3333 | 100 | 100 | 101.7282 | 100
26 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 219.75 | 35160 | 35160 | 2011-05-11 08:00 | 12d | 21096 | 0 | 0 | 13663.5098 | 0 | 34759.5098 | 0 | 100% | Finished | 35160 | 35160 | 100 | 60 | 100 | 100 | 98.8609 | 100
27 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 0 | 8.14 | 1302.4001 | 1302.4001 | 2011-05-11 08:00 | 20d | 1302.4001 | 0 | 0 | 0 | 0 | 1302.4001 | 0 | 100% | Finished | 1302.4001 | 1302.4001 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
13/10, 2010 | 2010-09-08 08:00 | 2010-10-13 08:00 | 108303.4381 | 53943.4388 | 64229.9755 | 2010-09-17 12:00 | -54359.9993 | 49.81% | -10286.5366 | 83.98% | -17d 4h | 30% | 86.31% | 2011-03-25 14:00 | 2011-09-09 17:00 | 2011-11-21 09:00 | 2011-03-28 12:00 | 2011-09-09 17:00 | 2011-11-14 11:00 | 2011-04-04 12:00 | 2012-05-10 14:00 | 2012-08-29 09:00 | 623055.9765 | 729619.1517 | 1186197.3271 | 1926983.3123 | 1400146.5765 | 2282193.8963 | 788572.5636 | 827780.0241 | 0.3 | 0.83985 | 0.49808 | 0.86315 | -17.5 | 0.83985 | 1 | 0.3 | 1
17/11, 2010 | 2010-10-13 08:00 | 2010-11-17 16:00 | 210788.2901 | 133050.3444 | 162225.9257 | 2010-10-21 16:00 | -77737.9457 | 63.12% | -29175.5813 | 82.02% | -19d | 62.65% | 89.02% | 2011-04-01 14:00 | 2011-06-24 12:00 | 2011-08-26 17:00 | 2011-04-05 15:00 | 2011-06-24 12:00 | 2011-08-11 16:00 | 2011-04-05 17:00 | 2011-06-28 09:00 | 2011-08-15 15:00 | 641945.0212 | 747138.9124 | 922232.736 | 927895.2271 | 1088888.753 | 1095792.928 | 775391.6959 | 776124.2727 | 0.62654 | 0.82015 | 0.6312 | 0.89017 | -19 | 0.82015 | 1 | 0.62654 | 1
22/12, 2010 | 2010-11-17 16:00 | 2010-12-22 16:00 | 364851.592 | 162127.2391 | 206085.8242 | 2010-11-02 16:00 | -202724.3529 | 44.44% | -43958.585 | 78.67% | -36d | 52.55% | 100% | 2011-05-10 11:00 | 2011-10-25 15:00 | 2012-02-14 15:00 | 2011-05-09 09:00 | 2011-10-25 15:00 | 2012-01-17 09:00 | 2011-04-28 17:00 | 2011-08-23 10:00 | 2011-10-27 10:00 | 656728.0249 | 778913.4985 | 1220212.2921 | 1063577.4099 | 1495178.8233 | 1296074.5336 | 833519.2337 | 819650.8848 | 0.52554 | 0.7867 | 0.44436 | 0.99999 | -36 | 0.7867 | 1 | 0.52554 | 1
26/01, 2011 | 2010-12-22 16:00 | 2011-01-26 16:00 | 467509.7499 | 211403.2401 | 249017.9047 | 2010-11-17 16:00 | -256106.5098 | 45.22% | -37614.6646 | 84.89% | -50d | 50.43% | 100% | 2011-05-25 15:00 | 2011-10-18 15:00 | 2011-12-29 10:00 | 2011-05-26 10:00 | 2011-10-18 15:00 | 2011-12-05 10:00 | 2011-05-18 17:00 | 2011-09-06 15:00 | 2011-10-14 17:00 | 650384.1045 | 721798.5964 | 1136623.0879 | 1044847.2001 | 1294553.3602 | 1186447.9249 | 770546.0961 | 763572.9547 | 0.50434 | 0.84895 | 0.45219 | 1 | -50 | 0.84895 | 1 | 0.50434 | 1
02/03, 2011 | 2011-01-26 16:00 | 2011-03-02 16:00 | 600900.4599 | 278874.4404 | 313663.2048 | 2010-12-10 11:00 | -322026.0196 | 46.41% | -34788.7645 | 88.91% | -58d 4h | 53.53% | 97.73% | 2011-06-14 16:00 | 2011-10-07 10:00 | 2011-11-25 12:00 | 2011-06-13 12:00 | 2011-10-07 10:00 | 2011-11-03 15:00 | 2011-05-31 12:00 | 2011-08-16 15:00 | 2011-09-06 14:00 | 647558.2043 | 689210.6214 | 1033118.3779 | 937470.7457 | 1122868.2902 | 1015288.8977 | 728909.0709 | 721687.3444 | 0.53525 | 0.88909 | 0.46409 | 0.97727 | -58.5 | 0.88909 | 1 | 0.53525 | 1
06/04, 2011 | 2011-03-02 16:00 | 2011-04-06 16:00 | 612769.4399 | 352367.2424 | 428397.0269 | 2010-12-20 17:00 | -260402.1975 | 57.5% | -76029.7845 | 82.25% | -76d 7h | 49.05% | 100% | 2011-05-26 14:00 | 2011-07-22 15:00 | 2011-09-29 17:00 | 2011-07-05 17:00 | 2011-09-09 11:00 | 2011-10-13 11:00 | 2011-06-24 16:00 | 2011-09-16 09:00 | 2011-10-21 09:00 | 688799.2244 | 744985.8404 | 881238.5215 | 959318.3991 | 978947.4942 | 1073874.5572 | 765256.9828 | 772792.2597 | 0.49047 | 0.82252 | 0.57504 | 1 | -76.875 | 0.82252 | 1 | 0.49047 | 1
11/05, 2011 | 2011-04-06 16:00 | 2011-05-11 16:00 | 612769.4399 | 496257.9888 | 528318.2154 | 2011-02-04 11:00 | -116511.4511 | 80.99% | -32060.2266 | 93.93% | -68d 4h | 61.05% | 94.57% | 2011-04-13 16:00 | 2011-04-21 15:00 | 2011-05-06 10:00 | 2011-06-28 11:00 | 2011-07-08 09:00 | 2011-07-12 16:00 | 2011-06-14 12:00 | 2011-07-05 14:00 | 2011-07-08 09:00 | 644829.6665 | 652356.7666 | 672184.2251 | 719158.2756 | 681478.5377 | 731487.2975 | 655872.6495 | 661694.127 | 0.61052 | 0.93932 | 0.80986 | 0.9457 | -68.5 | 0.93932 | 1 | 0.61052 | 1
15/06, 2011 | 2011-05-11 16:00 | 2011-06-15 16:00 | 612769.4399 | 580197.4489 | 605852.8848 | 2011-02-24 12:00 | -32571.991 | 94.68% | -25655.4358 | 95.77% | -79d 3h | 60.49% | 96.36% | 2011-03-18 17:00 | 2011-03-21 11:00 | 2011-03-29 12:00 | 2011-06-30 12:00 | 2011-07-01 09:00 | 2011-07-01 14:00 | 2011-06-29 11:00 | 2011-07-07 14:00 | 2011-07-08 10:00 | 638424.8757 | 639865.1589 | 640253.4508 | 659703.9027 | 641774.5907 | 662085.1116 | 639942.1144 | 642570.518 | 0.60485 | 0.95765 | 0.94684 | 0.96357 | -79.375 | 0.95765 | 1 | 0.60485 | 1
Actual Schedule | 2011-06-15 16:00 | 2011-06-28 16:00 | 612769.4399 | 612769.4399 | 646473.646 | 2011-03-09 17:00 | 0 | 100% | -33704.2061 | 94.79% | -78d 7h | 62.42% | 100% | 2011-03-09 17:00 | 2011-03-09 17:00 | 2011-03-21 10:00 | 2011-06-28 16:00 | 2011-06-28 16:00 | 2011-06-28 16:00 | 2011-06-28 16:00 | 2011-06-28 16:00 | 2011-06-28 16:00 | 646473.646 | 646473.646 | 646473.646 | 646473.646 | 646473.646 | 646473.646 | 646473.646 | 646473.646 | 0.62418 | 0.94786 | 1 | 1 | -78.875 | 0.94786 | 1 | 0.62418 | 1