## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Station (1) | 1 |  |  | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 | 582.375
49 | Grondwerken en infrastructuur-zone B | 1.1 |  |  | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 | 179.375
1 | Werfinstalatie | 1.1.1 |  | FS54-3w 4d | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 94.375
2 | afbraakwerken en ontmanteling perrons | 1.1.2 |  | FS4-3w 4d;FS29-3d;SS26 | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 39.375
3 | test uitvoering talud | 1.1.3 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
4 | grondwerken (1ste) | 1.1.4 | 2FS-3w 4d | FF5-1d;FF6+1w;FF12+4w;FF11+1d | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 31.375
5 | vermaling talud 1ste niveau | 1.1.5 | 4FF-1d |  | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 17.375
6 | bescherming talud 1ste niveau | 1.1.6 | 4FF+1w | SS8+1w;FS8-2w 4d | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 24.375
7 | afbraakwerken (deel 2) | 1.1.7 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
8 | grondwerken (2de) | 1.1.8 | 6SS+1w;6FS-2w 4d | FF9+1d;FF10+1d | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 27.375
9 | vermaling beschoeiing & talud (2de niveau) | 1.1.9 | 8FF+1d | SS11-3w 3d | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 22.375
10 | bescherming talud - 2de niveau | 1.1.10 | 8FF+1d | FF12+1w 3d | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 18.375
11 | beschoeiing | 1.1.11 | 4FF+1d;9SS-3w 3d |  | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 32.375
12 | grondwerken fase 3 | 1.1.12 | 4FF+4w;10FF+1w 3d |  | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 14.375
13 | diepe fundering | 1.1.13 |  | FS15-3d;FS29-7w | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 13.375
14 | riolering en aarding | 1.1.14 |  | FF15+5w 3d | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 58.375
15 | vloerplaat -1 | 1.1.15 | 13FS-3d;14FF+5w 3d | FF16+4d | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 91.375
16 | vloerkolommen en wanden | 1.1.16 | 15FF+4d | FF17+4d;FF70+4d | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 84.375
17 | vloerplaat gelijkvloers | 1.1.17 | 16FF+4d |  | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 | 63.375
18 | verankering talud 3de niveau | 1.1.18 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
19 | beton bescherming talud - 3de niv | 1.1.19 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
20 | uitvoering inspectieput | 1.1.20 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
21 | zuiverheidsbeton | 1.1.21 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
22 | ontdubbelde vloerplaat -1 | 1.1.22 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
23 | kolommen staal overspanning 1 | 1.1.23 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
24 | kolommen staal overspanning 2 | 1.1.24 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
50 | Grondwerken en infrastructuur-zone C | 1.2 |  |  | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 | 284.375
25 | plaatsing bescherming reizigers | 1.2.1 |  | FS28-3w 2d | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 48.375
26 | afbraakwerken en ontmanteling perron | 1.2.2 | 2SS | FF29+4w 1d | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 49.375
27 | afbraakwerken reizigerstunnel | 1.2.3 | 28FS-5w 3d | FF33-1w | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 66.375
28 | afbraakwerken diensttunnel | 1.2.4 | 25FS-3w 2d | FS27-5w 3d | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 44.375
29 | grondwerken(1ste) | 1.2.5 | 2FS-3d;13FS-7w;26FF+4w 1d | FS33+4d;FF36-3d;FS55+4w | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 47.375
30 | vermaling talud - 1ste niv | 1.2.6 |  | FF31+3d;FS33+2w | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 18.375
31 | bescherming talud - 1ste niv | 1.2.7 | 30FF+3d | FS33+1w 2d | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 20.375
32 | afbraakwerken (deel 2) | 1.2.8 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
33 | grondwerken (2de niv) | 1.2.9 | 27FF-1w;30FS+2w;31FS+1w 2d;29FS+4d | FF34+4d;FF35+4d;FS40;FS37-3d;FS55-1w 4d | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 32.375
34 | vermaling beschoeiing & talud - 2de niv | 1.2.10 | 33FF+4d |  | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 28.375
35 | bescherming talud - 2de niv | 1.2.11 | 33FF+4d | FF36-7w 1d;FF37+1w 4d | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 16.375
36 | beschoeiiing | 1.2.12 | 35FF-7w 1d;29FF-3d | FF37+9w | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 36.375
37 | grondwerken - fase 3 | 1.2.13 | 36FF+9w;35FF+1w 4d;33FS-3d |  | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 21.375
38 | verankering talud - 3de niv | 1.2.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
39 | beton bescherming talud - 3de niv | 1.2.15 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
40 | diepe fundering | 1.2.16 | 33FS | FF41+10w 2d | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 31.375
41 | riolering en aarding | 1.2.17 | 40FF+10w 2d | FF42+3w 4d | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 | 103.375
42 | vloerplaat -1 | 1.2.18 | 41FF+3w 4d | SS43+3w | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 124.375
43 | kolommen en wanden | 1.2.19 | 42SS+3w | FF44+1w 1d | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 119.375
44 | vloerplaat gelijkvloers | 1.2.20 | 43FF+1w 1d |  | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 | 74.375
45 | uitvoering inspectieput | 1.2.21 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
46 | zuiverheidsbeton | 1.2.22 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
47 | ontdubbelde vloerplaat | 1.2.23 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
48 | kolommen staal | 1.2.24 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
69 | Grondwerken en infrastructuur-zone D | 1.3 |  |  | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 | 281.375
51 | plaatsing bescherming reizigers | 1.3.1 | 52FS-5w 4d | FS53-3w 3d | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 45.375
52 | afbraakwerken wegtunnel | 1.3.2 |  | SS55+14w 4d;FS51-5w 4d | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 64.375
53 | afbraakwerken tramtunnel (deel 1) | 1.3.3 | 51FS-3w 3d | FS54-3w | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 42.375
54 | afbraakwerken tramtunnel (deel 2) | 1.3.4 | 1FS-3w 4d;53FS-3w | FF59+7w 2d;FS62+5w 3d;FF58+5w | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 44.375
55 | grondwerken (1ste niv) | 1.3.5 | 29FS+4w;33FS-1w 4d;52SS+14w 4d | FS56-2w | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 34.375
56 | vermalling talud - 1ste niv | 1.3.6 | 55FS-2w | FS57-1w 3d | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 17.375
57 | grondwerken | 1.3.7 | 56FS-1w 3d | FF58 | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 20.375
58 | Beschoeiing liftput | 1.3.8 | 54FF+5w;57FF |  | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 18.375
59 | diepe fundering 1 | 1.3.9 | 54FF+7w 2d | SS61+1w 4d | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 24.375
60 | diepe fundering 2 | 1.3.10 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
61 | riolering en aarding | 1.3.11 | 59SS+1w 4d | SS62+1d | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 | 77.375
62 | funderingszolen | 1.3.12 | 54FS+5w 3d;61SS+1d | FS116-7w | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 119.375
63 | Bufferbekken onder | 1.3.13 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
64 | Bufferbekken midden | 1.3.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
65 | verplatsing doorgang reizigers | 1.3.15 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
66 | funderingszolen | 1.3.16 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
67 | bufferbekken | 1.3.17 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
68 | beschoeiing achter lift | 1.3.18 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
87 | Superstructuur-zone B | 1.4 |  |  | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 | 262.375
70 | uitvoering kolommen | 1.4.1 | 16FF+4d | SS71+1w | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 | 57.375
71 | uitvoering structuur overspanning 1 | 1.4.2 | 70SS+1w | FS72-3w 1d;FS73-4w 4d | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 | 46.375
72 | structurele afwerking overspanning 1 | 1.4.3 | 71FS-3w 1d | FS74-7w;FS75-7w | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 63.375
73 | uitvoering structuur overspanning 2 | 1.4.4 | 71FS-4w 4d | FS74-5w 2d;FF152+19w 3d | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 52.375
74 | structurele afwerking overspanning 2 | 1.4.5 | 72FS-7w;73FS-5w 2d | FS76-4w 2d;FS77-4w 2d | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 63.375
75 | uitvoering structuur overspanning 3 | 1.4.6 | 72FS-7w | FS76-2w 4d;FS166-2w 4d | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 | 53.375
76 | structurele afwerking overspanning 3 | 1.4.7 | 74FS-4w 2d;75FS-2w 4d | SS77;FS78-4w;FS93-4w | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 | 42.375
77 | uitvoering structuur overspanning 4 | 1.4.8 | 74FS-4w 2d;76SS | FS78-2w;FS93-2w;FS117+6w | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 | 28.375
78 | structurele afwerking overspanning 4 | 1.4.9 | 76FS-4w;77FS-2w | FS94-4w;FS95-4w | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 41.375
79 | plaatsing kolommen staal-overspanning 1 | 1.4.10 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
80 | plaatsing kolommen staal-overspanning 2 | 1.4.11 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
81 | opstorten vloerplaat | 1.4.12 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
82 | opstorten vloerplaat | 1.4.13 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
83 | ontkisten 1 | 1.4.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
84 | ontkisten 2 | 1.4.15 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
85 | ontkisten 3 | 1.4.16 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
86 | ontkisten 4 | 1.4.17 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
115 | Superstructuur-zone C | 1.5 |  |  | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 | 372.375
88 | uitvoering kolommen | 1.5.1 |  | SS89+2w;SS91+7w;SS99+4w 1d | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 89.375
89 | uitvoering structuur groot overspanning 1 | 1.5.2 | 88SS+2w | FS91-8w 3d;FF166+4w 1d | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 | 92.375
90 | uitvoering structuur groot overspanning 2 | 1.5.3 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 | 0.375
91 | structurele afwerking groot overspanning 1 | 1.5.4 | 88SS+7w;89FS-8w 3d | FF170+29w 3d | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 89.375
92 | structurele afwerking groot overspanning 2 | 1.5.5 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
93 | uitvoering structuur overspanning 5 | 1.5.6 | 76FS-4w;77FS-2w | FS94-2w;FS95-2w | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 27.375
94 | structurele afwerking overspanning 5 | 1.5.7 | 78FS-4w;93FS-2w | FS96-4w;FS97-4w | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 41.375
95 | uitvoering structuur overspanning 6 | 1.5.8 | 78FS-4w;93FS-2w | FS96-2w;FS97-2w | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 27.375
96 | structurele afwerking overspanning 6 | 1.5.9 | 94FS-4w;95FS-2w | FS98-4w;FS99-4w | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 41.375
97 | uitvoering structuur overspanning 7 | 1.5.10 | 94FS-4w;95FS-2w | FS98-2w;FS99-2w | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 27.375
98 | structurele afwerking overspanning 7 | 1.5.11 | 97FS-2w;96FS-4w | FS100-4w 4d;FS117-4w 4d | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 | 47.375
99 | uitvoering structuur overspanning 8 | 1.5.12 | 88SS+4w 1d;97FS-2w;96FS-4w | FS100-2w;FS117-2w;FS136-2w;FF166+6w 1d | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 27.375
100 | structurele afwerking overspanning 8 | 1.5.13 | 98FS-4w 4d;99FS-2w |  | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 | 46.375
101 | opstorten vloerplaat na naspanning | 1.5.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
102 | kolommen staal | 1.5.15 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
103 | opstorten vloerplaat na aanspanning | 1.5.16 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
104 | kolommen staal | 1.5.17 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
105 | opstorten vloerplaat na aanspanning | 1.5.18 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
106 | kolommen staal | 1.5.19 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
107 | opstorten vloerplaat na plaatsing kolommen | 1.5.20 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
108 | dichtstellen openingen vloerplaat boven -1 | 1.5.21 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
109 | verplaatsing doorgang reizigers | 1.5.22 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
111 | ontkisten 5 | 1.5.23 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
112 | ontkisten 7 | 1.5.24 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
113 | ontkisten 6 | 1.5.25 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
114 | ontkisten 8 | 1.5.26 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
135 | Superstructuur-zone D | 1.6 |  |  | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 | 400.375
116 | uitvoering kolommen | 1.6.1 | 62FS-7w | FS117-6w 1d | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 89.375
117 | uitvoering structuur overspanning 9 | 1.6.2 | 77FS+6w;98FS-4w 4d;99FS-2w;116FS-6w 1d | FS118-2w 4d;FF119+2w 3d | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 37.375
118 | structurele afwerking overspanning 9 | 1.6.3 | 117FS-2w 4d | FS120-3w 2d | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 | 49.375
119 | uitvoering structuur overspanning 10 | 1.6.4 | 117FF+2w 3d | FF121+4w 4d;FS120-2w 3d | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 39.375
120 | structurele afwerking overspanning 10 | 1.6.5 | 118FS-3w 2d;119FS-2w 3d | FS122-8w 4d | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 64.375
121 | uitvoering structuur overspanning 11 | 1.6.6 | 119FF+4w 4d | FS122-5w;FF136+1w;FS139+5w | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 52.375
122 | structurele afwerking overspanning 11 | 1.6.7 | 120FS-8w 4d;121FS-5w | FS139+3d | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 64.375
123 | kolommen staal | 1.6.8 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
124 | opstorten vloerplaat na naspanning | 1.6.9 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
125 | kolommen staal | 1.6.10 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
126 | opstorten vloerplaat na naspanning | 1.6.11 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
127 | kolommen staal | 1.6.12 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
128 | opstorten vloerplaat na naspanning | 1.6.13 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
129 | kolommen staal | 1.6.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
130 | opstorten vloerplaat na naspanning | 1.6.15 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
131 | kolommen staal | 1.6.16 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
132 | opstorten vloerplaat na naspanning | 1.6.17 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
133 | Plaatsing HS kabel | 1.6.18 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
134 | montage bekisting | 1.6.19 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
150 | KOK A | 1.7 |  |  | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 | 577.375
136 | Plaatsing staalstructuur | 1.7.1 | 99FS-2w;121FF+1w | FS137-1w 1d;FS138+1w | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 | 71.375
137 | dackdichting-beplanting | 1.7.2 | 136FS-1w 1d |  | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 | 73.375
138 | dakdichting-waterdichting | 1.7.3 | 136FS+1w | SS140+3w 3d;FF139+12w 1d | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 | 107.375
139 | afwerking perron | 1.7.4 | 121FS+5w;122FS+3d;138FF+12w 1d;140FF+6w 3d |  | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 | 171.375
140 | plaatsing lift | 1.7.5 | 138SS+3w 3d | FF139+6w 3d | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 | 123.375
141 | regenwater afvoer | 1.7.6 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
142 | voorbereiding perron | 1.7.7 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
143 | integratie speciale technieken | 1.7.8 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
144 | kolommen staalstructuur | 1.7.9 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
145 | structuur levenslijn | 1.7.10 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
146 | start inrichting bovenleiding spoor | 1.7.11 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
147 | ophangconstructie voor bovenleiding | 1.7.12 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
148 | ophangconstructie voor toestellen perron | 1.7.13 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
149 | bekleding onderkant staalstructuur | 1.7.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
165 | KOK B | 1.8 |  |  | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 | 571.375
151 | voorbereiding perron | 1.8.1 | 205FF+3w 3d | SS152+3w | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 | 92.375
152 | plaatsing staalstructuur | 1.8.2 | 73FF+19w 3d;151SS+3w | FS153-9w;FS154-6w 2d;FS155-4w 2d | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 | 104.375
153 | dakdichting - beplanting | 1.8.3 | 152FS-9w | FF166-8w 3d | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 | 74.375
154 | dakdichting - waterdichting | 1.8.4 | 152FS-6w 2d | FF155+20w 1d | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 | 101.375
155 | afwerking perron | 1.8.5 | 152FS-4w 2d;154FF+20w 1d |  | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 | 228.375
156 | regenwater afvoer | 1.8.6 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
157 | integrateie speciale technieken in structuur | 1.8.7 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
158 | beglazing gevel | 1.8.8 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
159 | kolommen staalstructuur | 1.8.9 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
160 | structuur levenslijn | 1.8.10 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
161 | start inrichting bovenleiding spoor | 1.8.11 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
162 | ophangconstructie voor bovenleiding | 1.8.12 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
163 | ophangconstructie voor toestellen perron | 1.8.13 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
164 | bekleding onderkant staalstructuur | 1.8.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
199 | GOK | 1.9 |  |  | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 | 582.375
166 | plaatsing staalstructuur | 1.9.1 | 75FS-2w 4d;89FF+4w 1d;99FF+6w 1d;153FF-8w 3d | FF167+5w 4d;FF170+30w 1d | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 | 164.375
167 | dakdichting - beplanting | 1.9.2 | 166FF+5w 4d | FF168+4w | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 | 164.375
168 | plaatsing beglazing | 1.9.3 | 167FF+4w | FF169+2w | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 | 158.375
169 | dakdichting - waterdichting | 1.9.4 | 168FF+2w | SS170+2w 2d | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 | 156.375
170 | afwerking perron | 1.9.5 | 91FF+29w 3d;166FF+30w 1d;169SS+2w 2d |  | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 | 270.375
171 | diepe fundering kolommen gevel | 1.9.6 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
172 | funderingszolen kolommen gevel | 1.9.7 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
173 | kolommen gevel | 1.9.8 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
174 | ontrokingskoker langs gevel | 1.9.9 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
175 | slibvanger langs gevel | 1.9.10 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
176 | voorlopige aansluiting riolering | 1.9.11 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
177 | regenwater afvoer | 1.9.12 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
178 | integratie speciale technieken in structuur | 1.9.13 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
179 | Gevelbekleding metaal | 1.9.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
180 | integratie elec in gevel | 1.9.15 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
181 | beplanting onderkant dakstructuur | 1.9.16 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
182 | bekledingen staalstructuur | 1.9.17 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
183 | onderhoud en veiligheidsuitrusting - structuur | 1.9.18 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
184 | elektrische voorzieningen op dak | 1.9.19 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
185 | extractoren en wateraanvoer op dak | 1.9.20 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
186 | structuur levenslijn | 1.9.21 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 1.9.22 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
188 | voorlopige trap toegang perron | 1.9.23 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
189 | start inrichting bovenleiding spoor | 1.9.24 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
190 | ophangconstructie voor bovenleiding | 1.9.25 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
191 | Herstellingen staalstructuur 1 | 1.9.26 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
192 | herstellingen staalstructuur 2 | 1.9.27 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
193 | Herstellingen staalstructuur 3 | 1.9.28 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
194 | herstellingen staalstructuur 4 | 1.9.29 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
195 | herstellingen staalstructuur | 1.9.30 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
196 | Bekabeling in portieken | 1.9.31 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
197 | ophangconstructie voor toestellen perron | 1.9.32 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
198 | Paaltjes bovendaks | 1.9.33 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
200 | Technieken | 1.10 |  |  | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 | 131.375
227 | Superstructuur-zone A | 1.11 |  |  | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 | 435.375
201 | vloerplaat en keermuur reservelokaal 1 | 1.11.1 |  | FS202-6w 3d | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 | 93.375
202 | vloerplaat en keermuur reservelokaal 2 | 1.11.2 | 201FS-6w 3d | FS203-6w 3d | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 91.375
203 | vloerplaat en keermuur reservelokaal 3 | 1.11.3 | 202FS-6w 3d | FS204-9w 1d | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 | 110.375
204 | vloerplaat en keermuur reservelokaal 4 | 1.11.4 | 203FS-9w 1d | FS205-6w | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 | 105.375
205 | vloerplaat en keermuur reservelokaal 5 | 1.11.5 | 204FS-6w | FF206+17w 1d;FF151+3w 3d | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 89.375
206 | Dakplaat reservelokaal (incl. technische koker) | 1.11.6 | 205FF+17w 1d |  | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 313.375
207 | Beschoeiing onderstation | 1.11.7 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
208 | Verankering keermuur onderstation | 1.11.8 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
209 | Keerwand onderstation | 1.11.9 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
210 | Vloerplaat onderstation | 1.11.10 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
211 | Wanden onderstation | 1.11.11 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
212 | Vloerplaat +x onderstation | 1.11.12 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
213 | Structuur spoor boven onderstation | 1.11.13 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
214 | profielen voor beschoeiing | 1.11.14 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
215 | Afbraak en grondwerk (fase 1) | 1.11.15 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
216 | Verankering beschoeiing | 1.11.16 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
217 | Vloerplaat | 1.11.17 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
218 | Keerwand (fase 1) | 1.11.18 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 1.11.19 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
220 | Vloerplaat & keermuur | 1.11.20 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
221 | Voorbereidende afbraakwerken | 1.11.21 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
222 | Beschoeiing fase 1 tem niv verankering | 1.11.22 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
223 | Beschoeiing fase (fase 2) | 1.11.23 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
224 | Afbraakwerken (fase 2) | 1.11.24 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
225 | Dakplaat reservelokaal dienstperron | 1.11.25 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375
226 | Beton kolommen | 1.11.26 |  |  | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Station (1) | 3336h |  |  |  |  | 99 | 100 | 101
49 | Grondwerken en infrastructuur-zone B | 1040h |  |  |  |  | 99 | 100 | 101
1 | Werfinstalatie | 552h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | afbraakwerken en ontmanteling perrons | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | test uitvoering talud | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | grondwerken (1ste) | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | vermaling talud 1ste niveau | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | bescherming talud 1ste niveau | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | afbraakwerken (deel 2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | grondwerken (2de) | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | vermaling beschoeiing & talud (2de niveau) | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | bescherming talud - 2de niveau | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | beschoeiing | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | grondwerken fase 3 | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | diepe fundering | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | riolering en aarding | 344h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | vloerplaat -1 | 528h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | vloerkolommen en wanden | 488h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | vloerplaat gelijkvloers | 368h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | verankering talud 3de niveau | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | beton bescherming talud - 3de niv | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | uitvoering inspectieput | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | zuiverheidsbeton | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | ontdubbelde vloerplaat -1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | kolommen staal overspanning 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | kolommen staal overspanning 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Grondwerken en infrastructuur-zone C | 1640h |  |  |  |  | 99 | 100 | 101
25 | plaatsing bescherming reizigers | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | afbraakwerken en ontmanteling perron | 288h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | afbraakwerken reizigerstunnel | 376h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | afbraakwerken diensttunnel | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | grondwerken(1ste) | 272h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | vermaling talud - 1ste niv | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | bescherming talud - 1ste niv | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | afbraakwerken (deel 2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | grondwerken (2de niv) | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | vermaling beschoeiing & talud - 2de niv | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | bescherming talud - 2de niv | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | beschoeiiing | 216h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | grondwerken - fase 3 | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | verankering talud - 3de niv | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | beton bescherming talud - 3de niv | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | diepe fundering | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | riolering en aarding | 592h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | vloerplaat -1 | 712h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | kolommen en wanden | 688h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | vloerplaat gelijkvloers | 440h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | uitvoering inspectieput | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | zuiverheidsbeton | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | ontdubbelde vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Grondwerken en infrastructuur-zone D | 1616h |  |  |  |  | 99 | 100 | 101
51 | plaatsing bescherming reizigers | 272h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | afbraakwerken wegtunnel | 376h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | afbraakwerken tramtunnel (deel 1) | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | afbraakwerken tramtunnel (deel 2) | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | grondwerken (1ste niv) | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | vermalling talud - 1ste niv | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | grondwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Beschoeiing liftput | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | diepe fundering 1 | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | diepe fundering 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | riolering en aarding | 448h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | funderingszolen | 688h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Bufferbekken onder | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Bufferbekken midden | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | verplatsing doorgang reizigers | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | funderingszolen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | bufferbekken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | beschoeiing achter lift | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | Superstructuur-zone B | 1512h |  |  |  |  | 99 | 100 | 101
70 | uitvoering kolommen | 336h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | uitvoering structuur overspanning 1 | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | structurele afwerking overspanning 1 | 368h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | uitvoering structuur overspanning 2 | 312h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | structurele afwerking overspanning 2 | 368h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | uitvoering structuur overspanning 3 | 304h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | structurele afwerking overspanning 3 | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | uitvoering structuur overspanning 4 | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | structurele afwerking overspanning 4 | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | plaatsing kolommen staal-overspanning 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | plaatsing kolommen staal-overspanning 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | opstorten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | opstorten vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | ontkisten 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | ontkisten 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | ontkisten 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | ontkisten 4 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | Superstructuur-zone C | 2136h |  |  |  |  | 99 | 100 | 101
88 | uitvoering kolommen | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | uitvoering structuur groot overspanning 1 | 536h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | uitvoering structuur groot overspanning 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | structurele afwerking groot overspanning 1 | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | structurele afwerking groot overspanning 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | uitvoering structuur overspanning 5 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | structurele afwerking overspanning 5 | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | uitvoering structuur overspanning 6 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | structurele afwerking overspanning 6 | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | uitvoering structuur overspanning 7 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | structurele afwerking overspanning 7 | 272h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | uitvoering structuur overspanning 8 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | structurele afwerking overspanning 8 | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | opstorten vloerplaat na naspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | opstorten vloerplaat na aanspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | opstorten vloerplaat na aanspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | opstorten vloerplaat na plaatsing kolommen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | dichtstellen openingen vloerplaat boven -1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | verplaatsing doorgang reizigers | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | ontkisten 5 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | ontkisten 7 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | ontkisten 6 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | ontkisten 8 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | Superstructuur-zone D | 2296h |  |  |  |  | 99 | 100 | 101
116 | uitvoering kolommen | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | uitvoering structuur overspanning 9 | 224h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | structurele afwerking overspanning 9 | 288h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | uitvoering structuur overspanning 10 | 224h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | structurele afwerking overspanning 10 | 376h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | uitvoering structuur overspanning 11 | 312h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | structurele afwerking overspanning 11 | 376h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | opstorten vloerplaat na naspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | opstorten vloerplaat na naspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | opstorten vloerplaat na naspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | opstorten vloerplaat na naspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | kolommen staal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | opstorten vloerplaat na naspanning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | Plaatsing HS kabel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | montage bekisting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | KOK A | 3312h |  |  |  |  | 99 | 100 | 101
136 | Plaatsing staalstructuur | 416h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | dackdichting-beplanting | 416h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | dakdichting-waterdichting | 624h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | afwerking perron | 992h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | plaatsing lift | 704h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | regenwater afvoer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | voorbereiding perron | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | integratie speciale technieken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | kolommen staalstructuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | structuur levenslijn | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | start inrichting bovenleiding spoor | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | ophangconstructie voor bovenleiding | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | ophangconstructie voor toestellen perron | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | bekleding onderkant staalstructuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | KOK B | 3280h |  |  |  |  | 99 | 100 | 101
151 | voorbereiding perron | 536h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | plaatsing staalstructuur | 600h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | dakdichting - beplanting | 424h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | dakdichting - waterdichting | 592h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | afwerking perron | 1320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | regenwater afvoer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | integrateie speciale technieken in structuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | beglazing gevel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | kolommen staalstructuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | structuur levenslijn | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | start inrichting bovenleiding spoor | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | ophangconstructie voor bovenleiding | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | ophangconstructie voor toestellen perron | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | bekleding onderkant staalstructuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
199 | GOK | 3336h |  |  |  |  | 99 | 100 | 101
166 | plaatsing staalstructuur | 936h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | dakdichting - beplanting | 952h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
168 | plaatsing beglazing | 920h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
169 | dakdichting - waterdichting | 904h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | afwerking perron | 1544h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | diepe fundering kolommen gevel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
172 | funderingszolen kolommen gevel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
173 | kolommen gevel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
174 | ontrokingskoker langs gevel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | slibvanger langs gevel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | voorlopige aansluiting riolering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
177 | regenwater afvoer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
178 | integratie speciale technieken in structuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
179 | Gevelbekleding metaal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
180 | integratie elec in gevel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
181 | beplanting onderkant dakstructuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
182 | bekledingen staalstructuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | onderhoud en veiligheidsuitrusting - structuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | elektrische voorzieningen op dak | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
185 | extractoren en wateraanvoer op dak | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
186 | structuur levenslijn | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
188 | voorlopige trap toegang perron | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
189 | start inrichting bovenleiding spoor | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
190 | ophangconstructie voor bovenleiding | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
191 | Herstellingen staalstructuur 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | herstellingen staalstructuur 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
193 | Herstellingen staalstructuur 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
194 | herstellingen staalstructuur 4 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | herstellingen staalstructuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
196 | Bekabeling in portieken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
197 | ophangconstructie voor toestellen perron | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
198 | Paaltjes bovendaks | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
200 | Technieken | 752h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
227 | Superstructuur-zone A | 2496h |  |  |  |  | 99 | 100 | 101
201 | vloerplaat en keermuur reservelokaal 1 | 544h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
202 | vloerplaat en keermuur reservelokaal 2 | 528h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
203 | vloerplaat en keermuur reservelokaal 3 | 632h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
204 | vloerplaat en keermuur reservelokaal 4 | 608h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
205 | vloerplaat en keermuur reservelokaal 5 | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
206 | Dakplaat reservelokaal (incl. technische koker) | 1792h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
207 | Beschoeiing onderstation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
208 | Verankering keermuur onderstation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
209 | Keerwand onderstation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
210 | Vloerplaat onderstation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
211 | Wanden onderstation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
212 | Vloerplaat +x onderstation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
213 | Structuur spoor boven onderstation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
214 | profielen voor beschoeiing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
215 | Afbraak en grondwerk (fase 1) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
216 | Verankering beschoeiing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
217 | Vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | Keerwand (fase 1) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
220 | Vloerplaat & keermuur | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
221 | Voorbereidende afbraakwerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
222 | Beschoeiing fase 1 tem niv verankering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
223 | Beschoeiing fase (fase 2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
224 | Afbraakwerken (fase 2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
225 | Dakplaat reservelokaal dienstperron | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
226 | Beton kolommen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-03-25 17:00 |  | TP Name | 25/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 55d | [5 empty] | 155665.9983 |  | 12.8% |  | 143541.3379 | 177181.1186
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 55d | [5 empty] | 141622.9584 |  | 65.52% |  | 140192.3225 | 150546.4785
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 55d | 132589.5984 | 36160.7996 | 15d | 0 | 0 | 132589.5984 | 36160.7996 | 78.57% | Started | 130695.4584 | 130178.8784 | 100 | 79.7101 | 78.5714 | 100 | 79.7101 | 78.5714
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 5d | 636.8 | 1400.96 | 11d | 0 | 0 | 636.8 | 1400.96 | 31.25% | Started | 796 | 2547.2 | 100 | 25 | 31.25 | 100 | 25 | 31.25
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 3d | 382.08 | 1528.32 | 12d | 0 | 0 | 382.08 | 1528.32 | 20% | Started | 433.024 | 2165.12 | 100 | 17.6471 | 20 | 100 | 17.6471 | 20
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 1d | 127.36 | 1528.32 | 12d | 0 | 0 | 127.36 | 1528.32 | 7.692% | Started | 127.36 | 1655.68 | 100 | 7.6923 | 7.6923 | 100 | 7.6923 | 7.6923
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 |  | 0 | 0 | 2929.28 | 23d | 0 | 0 | 0 | 2929.28 | 0% | Not Started | 0 | 2929.28 | 100 |  | 0 | 100 |  | 0
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 |  | 0 | 0 | 1400.96 | 11d | 0 | 0 | 0 | 1400.96 | 0% | Not Started | 0 | 1400.96 | 100 |  | 0 | 100 |  | 0
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 |  | 0 | 0 | 1273.6 | 10d | 0 | 0 | 0 | 1273.6 | 0% | Not Started | 0 | 891.52 | 100 |  | 0 | 100 |  | 0
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 |  | 0 | 0 | 5476.48 | 43d | 0 | 0 | 0 | 5476.48 | 0% | Not Started | 0 | 636.8 | 100 |  | 0 | 100 |  | 0
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 |  | 0 | 0 | 8405.76 | 66d | 0 | 0 | 0 | 8405.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 |  | 0 | 0 | 7768.96 | 61d | 0 | 0 | 0 | 7768.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 |  | 0 | 0 | 5858.56 | 46d | 0 | 0 | 0 | 5858.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 55d | [5 empty] | 1849.68 |  | 2.934% |  | 1968.68 | 13418.9601
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 15d | 440.4 | 469.76 | 16d | 0 | 0 | 440.4 | 469.76 | 48.39% | Started | 497.2258 | 1027.6 | 100 | 42.8571 | 48.3871 | 100 | 42.8571 | 48.3871
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 6d | 176.16 | 822.08 | 28d | 0 | 0 | 176.16 | 822.08 | 17.65% | Started | 243.5153 | 322.96 | 100 | 12.766 | 17.6471 | 100 | 12.766 | 17.6471
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 6d | 176.16 | 822.08 | 28d | 0 | 0 | 176.16 | 822.08 | 17.65% | Started | 170.9788 | 822.08 | 100 | 18.1818 | 17.6471 | 100 | 18.1818 | 17.6471
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 |  | 0 | 0 | 4330.24 | 34d | 0 | 0 | 0 | 4330.24 | 0% | Not Started | 0 | 3566.08 | 100 |  | 0 | 100 |  | 0
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 |  | 0 | 0 | 1910.4 | 15d | 0 | 0 | 0 | 1910.4 | 0% | Not Started | 0 | 1910.4 | 100 |  | 0 | 100 |  | 0
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 |  | 0 | 0 | 2674.56 | 21d | 0 | 0 | 0 | 2674.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 |  | 0 | 0 | 3438.72 | 27d | 0 | 0 | 0 | 3438.72 | 0% | Not Started | 0 | 3056.64 | 100 |  | 0 | 100 |  | 0
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 |  | 0 | 0 | 2037.76 | 16d | 0 | 0 | 0 | 2037.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 |  | 0 | 0 | 3056.64 | 24d | 0 | 0 | 0 | 3056.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 |  | 0 | 0 | 9424.64 | 74d | 0 | 0 | 0 | 9424.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 |  | 0 | 0 | 11335.0401 | 89d | 0 | 0 | 0 | 11335.0401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 |  | 0 | 0 | 10952.9601 | 86d | 0 | 0 | 0 | 10952.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 |  | 0 | 0 | 7004.8 | 55d | 0 | 0 | 0 | 7004.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 52d | [5 empty] | 1379.92 |  | 4.144% |  | 1379.92 | 2848.4801
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 |  | 0 | 0 | 998.24 | 34d | 0 | 0 | 0 | 998.24 | 0% | Not Started | 0 | 998.24 | 100 |  | 0 | 100 |  | 0
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 |  | 0 | 0 | 910.16 | 31d | 0 | 0 | 0 | 910.16 | 0% | Not Started | 0 | 469.76 | 100 |  | 0 | 100 |  | 0
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 |  | 0 | 0 | 968.88 | 33d | 0 | 0 | 0 | 968.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 |  | 0 | 0 | 1783.04 | 14d | 0 | 0 | 0 | 1783.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 |  | 0 | 0 | 1910.4 | 15d | 0 | 0 | 0 | 1910.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 |  | 0 | 0 | 2419.84 | 19d | 0 | 0 | 0 | 2419.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 |  | 0 | 0 | 7132.16 | 56d | 0 | 0 | 0 | 7132.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 |  | 0 | 0 | 10952.9601 | 86d | 0 | 0 | 0 | 10952.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.64
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 |  | 0 | 0 | 7431.5999 | 33d | 0 | 0 | 0 | 7431.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 |  | 0 | 0 | 8557.5999 | 38d | 0 | 0 | 0 | 8557.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 |  | 0 | 0 | 6981.1999 | 31d | 0 | 0 | 0 | 6981.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 |  | 0 | 0 | 4729.1999 | 21d | 0 | 0 | 0 | 4729.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 226.32
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 |  | 0 | 0 | 15088.3998 | 67d | 0 | 0 | 0 | 15088.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 |  | 0 | 0 | 225.2 | 1d | 0 | 0 | 0 | 225.2 | 0% | Not Started | 0 | 225.2 | 100 |  | 0 | 100 |  | 0
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 |  | 0 | 0 | 7656.7999 | 34d | 0 | 0 | 0 | 7656.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 |  | 0 | 0 | 7881.9999 | 35d | 0 | 0 | 0 | 7881.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.96
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 |  | 0 | 0 | 8107.1999 | 36d | 0 | 0 | 0 | 8107.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.72
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 |  | 0 | 0 | 11193.5997 | 88d | 0 | 0 | 0 | 11193.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.72
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2.24
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 |  | 0 | 0 | 29764.7993 | 117d | 0 | 0 | 0 | 29764.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 |  | 0 | 0 | 177314.075 | 94d | 0 | 0 | 0 | 177314.075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 17d | [5 empty] | 10813.4398 |  | 0.0003197% |  | 0.41545 | 10135.5999
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 9007.9999 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 |  | 0 | 0 | 14863.1998 | 66d | 0 | 0 | 0 | 14863.1998 | 0% | Not Started | 0 | 1126 | 100 |  | 0 | 100 |  | 0
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 |  | 0 | 0 | 17790.7998 | 79d | 0 | 0 | 0 | 17790.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 |  | 0 | 0 | 17115.1998 | 76d | 0 | 0 | 0 | 17115.1998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 |  | 0 | 0 | 50444.7993 | 224d | 0 | 0 | 0 | 50444.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 11d | 0.88 | 0.16 | 2d | 2477.2 | 225.2 | 2478.08 | 225.36 | 84.62% | Started | 0.067692 | 0.08 | 100 | 1100 | 84.6154 | 100 | 3097600.0082 | 84.6154
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 17d | 1.36 | 2.56 | 32d | 3828.3999 | 7206.3999 | 3829.7599 | 7208.9599 | 34.69% | Started | 0.027755 | 0.08 | 100 | 1700 | 34.6939 | 100 | 4787199.9849 | 34.6939
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-06-10 17:00 |  | TP Name | 10/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 110d | [5 empty] | 280538.3171 |  | 18.2% |  | 204121.3443 | 300186.3979
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 110d | [5 empty] | 237590.0774 |  | 85.89% |  | 183777.5981 | 207976.3982
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 |  | 0 | 0 | 1400.96 | 11d | 0 | 0 | 0 | 1400.96 | 0% | Not Started | 0 | 1400.96 | 100 |  | 0 | 100 |  | 0
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 |  | 0 | 0 | 1273.6 | 10d | 0 | 0 | 0 | 1273.6 | 0% | Not Started | 0 | 1273.6 | 100 |  | 0 | 100 |  | 0
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 |  | 0 | 0 | 5476.48 | 43d | 0 | 0 | 0 | 5476.48 | 0% | Not Started | 0 | 5476.48 | 100 |  | 0 | 100 |  | 0
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 |  | 0 | 0 | 8405.76 | 66d | 0 | 0 | 0 | 8405.76 | 0% | Not Started | 0 | 7004.8 | 100 |  | 0 | 100 |  | 0
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 |  | 0 | 0 | 7768.96 | 61d | 0 | 0 | 0 | 7768.96 | 0% | Not Started | 0 | 5731.2 | 100 |  | 0 | 100 |  | 0
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 |  | 0 | 0 | 5858.56 | 46d | 0 | 0 | 0 | 5858.56 | 0% | Not Started | 0 | 3311.36 | 100 |  | 0 | 100 |  | 0
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 110d | [5 empty] | 14662.8001 |  | 24.18% |  | 16220.4834 | 31816.3202
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 14d | 1783.04 | 891.52 | 7d | 0 | 0 | 1783.04 | 891.52 | 66.67% | Started | 2122.6667 | 3184 | 100 | 56 | 66.6667 | 100 | 56 | 66.6667
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 8d | 1018.88 | 1146.24 | 9d | 0 | 0 | 1018.88 | 1146.24 | 47.06% | Started | 1258.6165 | 2674.56 | 100 | 38.0952 | 47.0588 | 100 | 38.0952 | 47.0588
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 4d | 509.44 | 1146.24 | 9d | 0 | 0 | 509.44 | 1146.24 | 30.77% | Started | 509.44 | 1655.68 | 100 | 30.7692 | 30.7692 | 100 | 30.7692 | 30.7692
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 |  | 0 | 0 | 3438.72 | 27d | 0 | 0 | 0 | 3438.72 | 0% | Not Started | 0 | 3438.72 | 100 |  | 0 | 100 |  | 0
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 |  | 0 | 0 | 2037.76 | 16d | 0 | 0 | 0 | 2037.76 | 0% | Not Started | 0 | 2037.76 | 100 |  | 0 | 100 |  | 0
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 |  | 0 | 0 | 3056.64 | 24d | 0 | 0 | 0 | 3056.64 | 0% | Not Started | 0 | 2547.2 | 100 |  | 0 | 100 |  | 0
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 |  | 0 | 0 | 9424.64 | 74d | 0 | 0 | 0 | 9424.64 | 0% | Not Started | 0 | 2292.48 | 100 |  | 0 | 100 |  | 0
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 |  | 0 | 0 | 11335.0401 | 89d | 0 | 0 | 0 | 11335.0401 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 |  | 0 | 0 | 10952.9601 | 86d | 0 | 0 | 0 | 10952.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 |  | 0 | 0 | 7004.8 | 55d | 0 | 0 | 0 | 7004.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 107d | [5 empty] | 4179.4401 |  | 12.38% |  | 4122.4641 | 11517.2801
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 18d | 528.48 | 440.4 | 15d | 0 | 0 | 528.48 | 440.4 | 54.55% | Started | 528.48 | 968.88 | 100 | 54.5455 | 54.5455 | 100 | 54.5455 | 54.5455
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 3184 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 |  | 0 | 0 | 1783.04 | 14d | 0 | 0 | 0 | 1783.04 | 0% | Not Started | 0 | 1783.04 | 100 |  | 0 | 100 |  | 0
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 4d | 509.44 | 2674.56 | 21d | 0 | 0 | 509.44 | 2674.56 | 16% | Started | 305.664 | 1018.88 | 100 | 26.6667 | 16 | 100 | 26.6667 | 16
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 764.16 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 |  | 0 | 0 | 2419.84 | 19d | 0 | 0 | 0 | 2419.84 | 0% | Not Started | 0 | 509.44 | 100 |  | 0 | 100 |  | 0
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 |  | 0 | 0 | 7132.16 | 56d | 0 | 0 | 0 | 7132.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 |  | 0 | 0 | 10952.9601 | 86d | 0 | 0 | 0 | 10952.9601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 8783.4399
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 4954.3999 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 |  | 0 | 0 | 7431.5999 | 33d | 0 | 0 | 0 | 7431.5999 | 0% | Not Started | 0 | 3828.3999 | 100 |  | 0 | 100 |  | 0
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 |  | 0 | 0 | 8557.5999 | 38d | 0 | 0 | 0 | 8557.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 |  | 0 | 0 | 6981.1999 | 31d | 0 | 0 | 0 | 6981.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 |  | 0 | 0 | 4729.1999 | 21d | 0 | 0 | 0 | 4729.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 226.32
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 |  | 0 | 0 | 15088.3998 | 67d | 0 | 0 | 0 | 15088.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 |  | 0 | 0 | 225.2 | 1d | 0 | 0 | 0 | 225.2 | 0% | Not Started | 0 | 225.2 | 100 |  | 0 | 100 |  | 0
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 |  | 0 | 0 | 7656.7999 | 34d | 0 | 0 | 0 | 7656.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 |  | 0 | 0 | 7881.9999 | 35d | 0 | 0 | 0 | 7881.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.96
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 |  | 0 | 0 | 8107.1999 | 36d | 0 | 0 | 0 | 8107.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.72
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 |  | 0 | 0 | 11193.5997 | 88d | 0 | 0 | 0 | 11193.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.72
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2.24
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 |  | 0 | 0 | 29764.7993 | 117d | 0 | 0 | 0 | 29764.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 |  | 0 | 0 | 177314.075 | 94d | 0 | 0 | 0 | 177314.075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 72d | [5 empty] | 24105.9995 |  | 0.0006147% |  | 0.79873 | 39861.9995
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 15313.5998 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 |  | 0 | 0 | 14863.1998 | 66d | 0 | 0 | 0 | 14863.1998 | 0% | Not Started | 0 | 13511.9998 | 100 |  | 0 | 100 |  | 0
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 |  | 0 | 0 | 17790.7998 | 79d | 0 | 0 | 0 | 17790.7998 | 0% | Not Started | 0 | 6080.3999 | 100 |  | 0 | 100 |  | 0
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 |  | 0 | 0 | 17115.1998 | 76d | 0 | 0 | 0 | 17115.1998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 |  | 0 | 0 | 50444.7993 | 224d | 0 | 0 | 0 | 50444.7993 | 0% | Not Started | 0 | 4954.3999 | 100 |  | 0 | 100 |  | 0
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 5d | 0.4 | 0.32 | 4d | 1126 | 900.8 | 1126.4 | 901.12 | 55.56% | Started | 0.044444 | 0.08 | 100 | 500 | 55.5556 | 100 | 1408000.0315 | 55.5556
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 3d | 0.24 | 0.32 | 4d | 675.6 | 900.8 | 675.84 | 901.12 | 42.86% | Started | 0.034286 | 0.08 | 100 | 300 | 42.8571 | 100 | 844799.9884 | 42.8571
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-08-26 17:00 |  | TP Name | 26/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 165d | [5 empty] | 316002.7971 |  | 19.49% |  | 218502.0301 | 442506.7167
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 165d | [5 empty] | 251091.4375 |  | 88.44% |  | 189222.3702 | 213962.3182
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 10d | 1273.6 | 8151.04 | 64d | 0 | 0 | 1273.6 | 8151.04 | 13.51% | Started | 189.3189 | 1400.96 | 100 | 90.9091 | 13.5135 | 100 | 90.9091 | 13.5135
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 7d | 891.52 | 5094.4 | 40d | 0 | 0 | 891.52 | 5094.4 | 14.89% | Started | 189.6851 | 1273.6 | 100 | 70 | 14.8936 | 100 | 70 | 14.8936
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 67d | 8533.12 | 4330.24 | 34d | 0 | 0 | 8533.12 | 4330.24 | 66.34% | Started | 3632.9124 | 5476.48 | 100 | 155.814 | 66.3366 | 100 | 155.814 | 66.3366
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 15d | 1910.4 | 9297.28 | 73d | 0 | 0 | 1910.4 | 9297.28 | 17.05% | Started | 1432.8 | 8405.76 | 100 | 22.7273 | 17.0455 | 100 | 22.7273 | 17.0455
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 |  | 0 | 0 | 7768.96 | 61d | 0 | 0 | 0 | 7768.96 | 0% | Not Started | 0 | 7768.96 | 100 |  | 0 | 100 |  | 0
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 |  | 0 | 0 | 5858.56 | 46d | 0 | 0 | 0 | 5858.56 | 0% | Not Started | 0 | 5858.56 | 100 |  | 0 | 100 |  | 0
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 7d | 0.56 | 0.4 | 5d | 891.52 | 636.8 | 892.08 | 637.2 | 58.33% | Started | 0.046667 | 0.08 | 100 | 700 | 58.3333 | 100 | 1115100.0493 | 58.3333
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 8d | 0.64 | 5.04 | 63d | 0 | 0 | 0.64 | 5.04 | 11.27% | Started | 0.0090141 | 0.08 | 100 | 800 | 11.2676 | 100 | 800 | 11.2676
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 165d | [5 empty] | 21795.6801 |  | 34.45% |  | 23110.9368 | 54995.8403
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3184 | 3184 | 100 | 84 | 100 | 100 | 84 | 100
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2674.56 | 2674.56 | 100 | 80.9524 | 100 | 100 | 80.9524 | 100
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 12d | 1528.32 | 1146.24 | 9d | 0 | 0 | 1528.32 | 1146.24 | 57.14% | Started | 1964.983 | 3438.72 | 100 | 44.4444 | 57.1429 | 100 | 44.4444 | 57.1429
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 7d | 891.52 | 1400.96 | 11d | 0 | 0 | 891.52 | 1400.96 | 38.89% | Started | 792.4622 | 2037.76 | 100 | 43.75 | 38.8889 | 100 | 43.75 | 38.8889
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 5d | 0.4 | 0.72 | 9d | 636.8 | 1146.24 | 637.2 | 1146.96 | 35.71% | Started | 0.028571 | 0.08 | 100 | 500 | 35.7143 | 100 | 796500.0025 | 35.7143
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 4d | 0.32 | 0.8 | 10d | 509.44 | 1273.6 | 509.76 | 1274.4 | 28.57% | Started | 0.022857 | 0.08 | 100 | 400 | 28.5714 | 100 | 637200.0173 | 28.5714
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 3d | 382.08 | 1910.4 | 15d | 0 | 0 | 382.08 | 1910.4 | 16.67% | Started | 509.44 | 3056.64 | 100 | 12.5 | 16.6667 | 100 | 12.5 | 16.6667
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 |  | 0 | 0 | 9424.64 | 74d | 0 | 0 | 0 | 9424.64 | 0% | Not Started | 0 | 9297.28 | 100 |  | 0 | 100 |  | 0
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 |  | 0 | 0 | 11335.0401 | 89d | 0 | 0 | 0 | 11335.0401 | 0% | Not Started | 0 | 8660.48 | 100 |  | 0 | 100 |  | 0
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 |  | 0 | 0 | 10952.9601 | 86d | 0 | 0 | 0 | 10952.9601 | 0% | Not Started | 0 | 6750.08 | 100 |  | 0 | 100 |  | 0
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 |  | 0 | 0 | 7004.8 | 55d | 0 | 0 | 0 | 7004.8 | 0% | Not Started | 0 | 1910.4 | 100 |  | 0 | 100 |  | 0
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 162d | [5 empty] | 7294.4001 |  | 18.52% |  | 6167.6001 | 27819.3602
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 3184 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 |  | 0 | 0 | 1783.04 | 14d | 0 | 0 | 0 | 1783.04 | 0% | Not Started | 0 | 1783.04 | 100 |  | 0 | 100 |  | 0
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 |  | 0 | 0 | 2419.84 | 19d | 0 | 0 | 0 | 2419.84 | 0% | Not Started | 0 | 2419.84 | 100 |  | 0 | 100 |  | 0
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 |  | 0 | 0 | 7132.16 | 56d | 0 | 0 | 0 | 7132.16 | 0% | Not Started | 0 | 6368 | 100 |  | 0 | 100 |  | 0
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 |  | 0 | 0 | 10952.9601 | 86d | 0 | 0 | 0 | 10952.9601 | 0% | Not Started | 0 | 6240.64 | 100 |  | 0 | 100 |  | 0
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 63056.6391
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 |  | 0 | 0 | 7431.5999 | 33d | 0 | 0 | 0 | 7431.5999 | 0% | Not Started | 0 | 7431.5999 | 100 |  | 0 | 100 |  | 0
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 10359.1999 | 100 |  | 0 | 100 |  | 0
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 8782.7999 | 100 |  | 0 | 100 |  | 0
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 |  | 0 | 0 | 8557.5999 | 38d | 0 | 0 | 0 | 8557.5999 | 0% | Not Started | 0 | 8557.5999 | 100 |  | 0 | 100 |  | 0
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 |  | 0 | 0 | 6981.1999 | 31d | 0 | 0 | 0 | 6981.1999 | 0% | Not Started | 0 | 3828.3999 | 100 |  | 0 | 100 |  | 0
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 |  | 0 | 0 | 4729.1999 | 21d | 0 | 0 | 0 | 4729.1999 | 0% | Not Started | 0 | 3828.3999 | 100 |  | 0 | 100 |  | 0
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 1351.2 | 100 |  | 0 | 100 |  | 0
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1577.52
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 |  | 0 | 0 | 15088.3998 | 67d | 0 | 0 | 0 | 15088.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 |  | 0 | 0 | 225.2 | 1d | 0 | 0 | 0 | 225.2 | 0% | Not Started | 0 | 225.2 | 100 |  | 0 | 100 |  | 0
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 1351.2 | 100 |  | 0 | 100 |  | 0
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 |  | 0 | 0 | 7656.7999 | 34d | 0 | 0 | 0 | 7656.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 |  | 0 | 0 | 7881.9999 | 35d | 0 | 0 | 0 | 7881.9999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.96
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 |  | 0 | 0 | 8107.1999 | 36d | 0 | 0 | 0 | 8107.1999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.72
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 |  | 0 | 0 | 11193.5997 | 88d | 0 | 0 | 0 | 11193.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0.72
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4072.6399
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 |  | 0 | 0 | 29764.7993 | 117d | 0 | 0 | 0 | 29764.7993 | 0% | Not Started | 0 | 4070.3999 | 100 |  | 0 | 100 |  | 0
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 |  | 0 | 0 | 177314.075 | 94d | 0 | 0 | 0 | 177314.075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 127d | [5 empty] | 35821.2794 |  | 0.0008642% |  | 1.123 | 77019.999
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 15313.5998 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 |  | 0 | 0 | 14863.1998 | 66d | 0 | 0 | 0 | 14863.1998 | 0% | Not Started | 0 | 14863.1998 | 100 |  | 0 | 100 |  | 0
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 |  | 0 | 0 | 17790.7998 | 79d | 0 | 0 | 0 | 17790.7998 | 0% | Not Started | 0 | 17790.7998 | 100 |  | 0 | 100 |  | 0
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 |  | 0 | 0 | 17115.1998 | 76d | 0 | 0 | 0 | 17115.1998 | 0% | Not Started | 0 | 11034.7999 | 100 |  | 0 | 100 |  | 0
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 675.6 | 100 |  | 0 | 100 |  | 0
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 |  | 0 | 0 | 50444.7993 | 224d | 0 | 0 | 0 | 50444.7993 | 0% | Not Started | 0 | 17340.3998 | 100 |  | 0 | 100 |  | 0
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2535300.0811 | 100
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 19d | 1.52 | 0.48 | 6d | 4278.7998 | 1351.2 | 4280.3198 | 1351.68 | 76% | Started | 0.0608 | 0.08 | 100 | 1900 | 76 | 100 | 5350399.8754 | 76
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 5d | 0.4 | 1.04 | 13d | 1126 | 2927.6001 | 1126.4 | 2928.6401 | 27.78% | Started | 0.022222 | 0.08 | 100 | 500 | 27.7778 | 100 | 1408000.0315 | 27.7778
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-11-11 17:00 |  | TP Name | 11/11, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 220d | [5 empty] | 386758.9176 |  | 23.4% |  | 262407.2912 | 717168.5516
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 220d | [5 empty] | 281785.1579 |  | 94.85% |  | 202938.0851 | 213962.3182
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 64d | 8151.04 | 1018.88 | 8d | 0 | 0 | 8151.04 | 1018.88 | 88.89% | Started | 1245.2978 | 1400.96 | 100 | 581.8182 | 88.8889 | 100 | 581.8182 | 88.8889
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1273.6 | 1273.6 | 100 | 150 | 100 | 100 | 150 | 100
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 67d | 8533.12 | 1528.32 | 12d | 0 | 0 | 8533.12 | 1528.32 | 84.81% | Started | 4644.6096 | 5476.48 | 100 | 155.814 | 84.8101 | 100 | 155.814 | 84.8101
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 70d | 8915.2 | 2292.48 | 18d | 0 | 0 | 8915.2 | 2292.48 | 79.55% | Started | 6686.4002 | 8405.76 | 100 | 106.0606 | 79.5455 | 100 | 106.0606 | 79.5455
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 2011-08-30 08:00 | 54d | 6877.44 | 3184 | 25d | 0 | 0 | 6877.44 | 3184 | 68.35% | Started | 5310.4282 | 7768.96 | 100 | 88.5246 | 68.3544 | 100 | 88.5246 | 68.3544
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 |  | 0 | 0 | 5858.56 | 46d | 0 | 0 | 0 | 5858.56 | 0% | Not Started | 0 | 5858.56 | 100 |  | 0 | 100 |  | 0
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 65d | 5.2 | 0.64 | 8d | 8273.4004 | 1018.88 | 8278.6004 | 1019.52 | 89.04% | Started | 0.071233 | 0.08 | 100 | 6500 | 89.0411 | 100 | 10348250.7194 | 89.0411
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 220d | [5 empty] | 35553.8402 |  | 49.35% |  | 33108.4753 | 67095.0404
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3184 | 3184 | 100 | 84 | 100 | 100 | 84 | 100
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2674.56 | 2674.56 | 100 | 80.9524 | 100 | 100 | 80.9524 | 100
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3438.72 | 3438.72 | 100 | 77.7778 | 100 | 100 | 77.7778 | 100
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 2037.76 | 2037.76 | 100 | 112.5 | 100 | 100 | 112.5 | 100
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 14d | 1.12 | 0 | 0 | 1783.04 | 0 | 1784.16 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1400 | 100 | 100 | 2230200.0986 | 100
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 30d | 2.4 | 0 | 0 | 1783.04 | 0 | 1785.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3000 | 100 | 100 | 2231800.0986 | 100
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 75 | 100 | 100 | 75 | 100
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 |  | 0 | 0 | 9424.64 | 74d | 0 | 0 | 0 | 9424.64 | 0% | Not Started | 0 | 9424.64 | 100 |  | 0 | 100 |  | 0
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 2011-09-07 08:00 | 48d | 6113.28 | 8533.12 | 67d | 0 | 0 | 6113.28 | 8533.12 | 41.74% | Started | 4731.1471 | 11335.0401 | 100 | 53.9326 | 41.7391 | 100 | 53.9326 | 41.7391
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 |  | 0 | 0 | 10952.9601 | 86d | 0 | 0 | 0 | 10952.9601 | 0% | Not Started | 0 | 10952.9601 | 100 |  | 0 | 100 |  | 0
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 |  | 0 | 0 | 7004.8 | 55d | 0 | 0 | 0 | 7004.8 | 0% | Not Started | 0 | 7004.8 | 100 |  | 0 | 100 |  | 0
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-07 08:00 | 6d | 0.48 | 0.32 | 4d | 764.16 | 509.44 | 764.64 | 509.76 | 60% | Started | 0.048 | 0.08 | 100 | 600 | 60 | 100 | 955799.9878 | 60
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 217d | [5 empty] | 8823.2001 |  | 29.28% |  | 9749.1977 | 33295.8402
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 3184 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 |  | 0 | 0 | 1783.04 | 14d | 0 | 0 | 0 | 1783.04 | 0% | Not Started | 0 | 1783.04 | 100 |  | 0 | 100 |  | 0
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-10-12 08:00 | 5d | 636.8 | 0 | 0 | 0 | 0 | 636.8 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 26.3158 | 100 | 100 | 26.3158 | 100
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-29 08:00 | 6d | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 600 | 100
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 |  | 0 | 0 | 7132.16 | 56d | 0 | 0 | 0 | 7132.16 | 0% | Not Started | 0 | 7132.16 | 100 |  | 0 | 100 |  | 0
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2011-11-03 08:00 | 7d | 891.52 | 7514.24 | 59d | 0 | 0 | 891.52 | 7514.24 | 10.61% | Started | 1161.6776 | 10952.9601 | 100 | 8.1395 | 10.6061 | 100 | 8.1395 | 10.6061
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 20d | [5 empty] | 5406.7199 |  | 0.0004359% |  | 0.32 | 73415.839
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 |  | 0 | 0 | 7431.5999 | 33d | 0 | 0 | 0 | 7431.5999 | 0% | Not Started | 0 | 7431.5999 | 100 |  | 0 | 100 |  | 0
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 10359.1999 | 100 |  | 0 | 100 |  | 0
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 8782.7999 | 100 |  | 0 | 100 |  | 0
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 10359.1999 | 100 |  | 0 | 100 |  | 0
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 |  | 0 | 0 | 8557.5999 | 38d | 0 | 0 | 0 | 8557.5999 | 0% | Not Started | 0 | 8557.5999 | 100 |  | 0 | 100 |  | 0
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 |  | 0 | 0 | 6981.1999 | 31d | 0 | 0 | 0 | 6981.1999 | 0% | Not Started | 0 | 6981.1999 | 100 |  | 0 | 100 |  | 0
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 |  | 0 | 0 | 4729.1999 | 21d | 0 | 0 | 0 | 4729.1999 | 0% | Not Started | 0 | 4729.1999 | 100 |  | 0 | 100 |  | 0
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 68236.7191
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 11710.3998 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 |  | 0 | 0 | 15088.3998 | 67d | 0 | 0 | 0 | 15088.3998 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 |  | 0 | 0 | 225.2 | 1d | 0 | 0 | 0 | 225.2 | 0% | Not Started | 0 | 225.2 | 100 |  | 0 | 100 |  | 0
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 3828.3999 | 100 |  | 0 | 100 |  | 0
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 |  | 0 | 0 | 7656.7999 | 34d | 0 | 0 | 0 | 7656.7999 | 0% | Not Started | 0 | 6981.1999 | 100 |  | 0 | 100 |  | 0
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 |  | 0 | 0 | 7881.9999 | 35d | 0 | 0 | 0 | 7881.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 19368.1597
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 11935.5998 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 |  | 0 | 0 | 8107.1999 | 36d | 0 | 0 | 0 | 8107.1999 | 0% | Not Started | 0 | 1351.2 | 100 |  | 0 | 100 |  | 0
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 1576.4 | 100 |  | 0 | 100 |  | 0
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 255.12
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 254.4 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 |  | 0 | 0 | 11193.5997 | 88d | 0 | 0 | 0 | 11193.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 8628.6398
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 5225.3599 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 3402.5599 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 36381.4391
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 |  | 0 | 0 | 29764.7993 | 117d | 0 | 0 | 0 | 29764.7993 | 0% | Not Started | 0 | 18062.3996 | 100 |  | 0 | 100 |  | 0
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 11193.5997 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 5087.9999 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 2035.2 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 |  | 0 | 0 | 177314.075 | 94d | 0 | 0 | 0 | 177314.075 | 0% | Not Started | 0 | 88657.0375 | 100 |  | 0 | 100 |  | 0
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 182d | [5 empty] | 55189.9995 |  | 12.78% |  | 16611.2131 | 107872.3985
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 15313.5998 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 2011-08-29 08:00 | 55d | 12385.9998 | 4954.3999 | 22d | 0 | 0 | 12385.9998 | 4954.3999 | 71.43% | Started | 10616.5715 | 14863.1998 | 100 | 83.3333 | 71.4286 | 100 | 83.3333 | 71.4286
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 |  | 0 | 0 | 17790.7998 | 79d | 0 | 0 | 0 | 17790.7998 | 0% | Not Started | 0 | 17790.7998 | 100 |  | 0 | 100 |  | 0
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 |  | 0 | 0 | 17115.1998 | 76d | 0 | 0 | 0 | 17115.1998 | 0% | Not Started | 0 | 17115.1998 | 100 |  | 0 | 100 |  | 0
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 13061.5998 | 100 |  | 0 | 100 |  | 0
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 2011-10-27 08:00 | 12d | 2702.4 | 20042.7997 | 89d | 0 | 0 | 2702.4 | 20042.7997 | 11.88% | Started | 5993.4416 | 29726.3996 | 100 | 5.3571 | 11.8812 | 100 | 5.3571 | 11.8812
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2535300.0811 | 100
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 25d | 2 | 0 | 0 | 5630 | 0 | 5632 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 7040000.1573 | 100
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 18d | 1.44 | 0 | 0 | 4053.6001 | 0 | 4055.0401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1800 | 100 | 100 | 5068800.2353 | 100
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-01-27 17:00 |  | TP Name | 27/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 275d | [5 empty] | 478487.0768 |  | 32.56% |  | 365123.8854 | 981713.8255
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 275d | [5 empty] | 298725.4778 |  | 99.19% |  | 212220.5041 | 213962.3182
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 72d | 9169.92 | 0 | 0 | 0 | 0 | 9169.92 | 0 | 100% | Finished | 1400.96 | 1400.96 | 100 | 654.5455 | 100 | 100 | 654.5455 | 100
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1273.6 | 1273.6 | 100 | 150 | 100 | 100 | 150 | 100
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 5476.48 | 5476.48 | 100 | 183.7209 | 100 | 100 | 183.7209 | 100
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 88d | 11207.6801 | 0 | 0 | 0 | 0 | 11207.6801 | 0 | 100% | Finished | 8405.76 | 8405.76 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 2011-08-30 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 7768.96 | 7768.96 | 100 | 129.5082 | 100 | 100 | 129.5082 | 100
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 | 2011-11-17 08:00 | 52d | 6622.72 | 2801.92 | 22d | 0 | 0 | 6622.72 | 2801.92 | 70.27% | Started | 4116.826 | 5858.56 | 100 | 113.0435 | 70.2703 | 100 | 113.0435 | 70.2703
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 73d | 5.84 | 0 | 0 | 9292.2803 | 0 | 9298.1203 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7300 | 100 | 100 | 11622650.6014 | 100
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-18 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-25 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 275d | [5 empty] | 53134.1601 |  | 75.36% |  | 50562.2389 | 67095.0404
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3184 | 3184 | 100 | 84 | 100 | 100 | 84 | 100
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2674.56 | 2674.56 | 100 | 80.9524 | 100 | 100 | 80.9524 | 100
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3438.72 | 3438.72 | 100 | 77.7778 | 100 | 100 | 77.7778 | 100
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 2037.76 | 2037.76 | 100 | 112.5 | 100 | 100 | 112.5 | 100
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 14d | 1.12 | 0 | 0 | 1783.04 | 0 | 1784.16 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1400 | 100 | 100 | 2230200.0986 | 100
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 30d | 2.4 | 0 | 0 | 1783.04 | 0 | 1785.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3000 | 100 | 100 | 2231800.0986 | 100
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 75 | 100 | 100 | 75 | 100
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 | 2011-11-25 08:00 | 10d | 1273.6 | 0 | 0 | 0 | 0 | 1273.6 | 0 | 100% | Finished | 9424.64 | 9424.64 | 100 | 13.5135 | 100 | 100 | 13.5135 | 100
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 2011-09-07 08:00 | 103d | 13118.0801 | 1528.32 | 12d | 0 | 0 | 13118.0801 | 1528.32 | 89.57% | Started | 10152.2533 | 11335.0401 | 100 | 115.7303 | 89.5652 | 100 | 115.7303 | 89.5652
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2012-01-09 08:00 | 15d | 1910.4 | 6113.28 | 48d | 0 | 0 | 1910.4 | 6113.28 | 23.81% | Started | 2607.8476 | 10952.9601 | 100 | 17.4419 | 23.8095 | 100 | 17.4419 | 23.8095
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 |  | 0 | 0 | 7004.8 | 55d | 0 | 0 | 0 | 7004.8 | 0% | Not Started | 0 | 7004.8 | 100 |  | 0 | 100 |  | 0
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-23 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-29 08:00 | 44d | 3.52 | 1.36 | 17d | 5603.8398 | 2165.1201 | 5607.3598 | 2166.4801 | 72.13% | Started | 0.057705 | 0.08 | 100 | 4400 | 72.1311 | 100 | 7009199.9613 | 72.1311
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-07 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 272d | [5 empty] | 20540.3202 |  | 71.27% |  | 23730.0586 | 33295.8402
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 3184 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 |  | 0 | 0 | 1783.04 | 14d | 0 | 0 | 0 | 1783.04 | 0% | Not Started | 0 | 1783.04 | 100 |  | 0 | 100 |  | 0
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-10-12 08:00 | 5d | 636.8 | 0 | 0 | 0 | 0 | 636.8 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 26.3158 | 100 | 100 | 26.3158 | 100
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-29 08:00 | 6d | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 600 | 100
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 | 2011-12-08 08:00 | 37d | 4712.32 | 509.44 | 4d | 0 | 0 | 4712.32 | 509.44 | 90.24% | Started | 6436.3394 | 7132.16 | 100 | 66.0714 | 90.2439 | 100 | 66.0714 | 90.2439
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2011-11-03 08:00 | 62d | 7896.32 | 2037.76 | 16d | 0 | 0 | 7896.32 | 2037.76 | 79.49% | Started | 8706.1991 | 10952.9601 | 100 | 72.093 | 79.4872 | 100 | 72.093 | 79.4872
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 75d | [5 empty] | 15540.7198 |  | 7.118% |  | 5225.6637 | 73415.839
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 | 2011-11-28 08:00 | 45d | 10133.9999 | 4278.7999 | 19d | 0 | 0 | 10133.9999 | 4278.7999 | 70.31% | Started | 5225.3437 | 7431.5999 | 100 | 136.3636 | 70.3125 | 100 | 136.3636 | 70.3125
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 10359.1999 | 100 |  | 0 | 100 |  | 0
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 8782.7999 | 100 |  | 0 | 100 |  | 0
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 |  | 0 | 0 | 10359.1999 | 46d | 0 | 0 | 0 | 10359.1999 | 0% | Not Started | 0 | 10359.1999 | 100 |  | 0 | 100 |  | 0
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 |  | 0 | 0 | 8557.5999 | 38d | 0 | 0 | 0 | 8557.5999 | 0% | Not Started | 0 | 8557.5999 | 100 |  | 0 | 100 |  | 0
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 |  | 0 | 0 | 6981.1999 | 31d | 0 | 0 | 0 | 6981.1999 | 0% | Not Started | 0 | 6981.1999 | 100 |  | 0 | 100 |  | 0
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 |  | 0 | 0 | 4729.1999 | 21d | 0 | 0 | 0 | 4729.1999 | 0% | Not Started | 0 | 4729.1999 | 100 |  | 0 | 100 |  | 0
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 91207.1188
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 |  | 0 | 0 | 15088.3998 | 67d | 0 | 0 | 0 | 15088.3998 | 0% | Not Started | 0 | 15088.3998 | 100 |  | 0 | 100 |  | 0
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 |  | 0 | 0 | 225.2 | 1d | 0 | 0 | 0 | 225.2 | 0% | Not Started | 0 | 225.2 | 100 |  | 0 | 100 |  | 0
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 |  | 0 | 0 | 7656.7999 | 34d | 0 | 0 | 0 | 7656.7999 | 0% | Not Started | 0 | 7656.7999 | 100 |  | 0 | 100 |  | 0
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 |  | 0 | 0 | 7881.9999 | 35d | 0 | 0 | 0 | 7881.9999 | 0% | Not Started | 0 | 7881.9999 | 100 |  | 0 | 100 |  | 0
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 60804.9592
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 6305.5999 | 100 |  | 0 | 100 |  | 0
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 |  | 0 | 0 | 8107.1999 | 36d | 0 | 0 | 0 | 8107.1999 | 0% | Not Started | 0 | 8107.1999 | 100 |  | 0 | 100 |  | 0
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 6305.5999 | 100 |  | 0 | 100 |  | 0
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 9007.9999 | 100 |  | 0 | 100 |  | 0
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 8782.7999 | 100 |  | 0 | 100 |  | 0
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 7881.9999 | 100 |  | 0 | 100 |  | 0
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 8014.3198
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 6614.3998 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 1399.2 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 |  | 0 | 0 | 11193.5997 | 88d | 0 | 0 | 0 | 11193.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 31960.4791
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 8141.8398 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 9113.9997 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 6197.5198 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 4860.7999 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 3645.5999 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 103034.2375
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 |  | 0 | 0 | 29764.7993 | 117d | 0 | 0 | 0 | 29764.7993 | 0% | Not Started | 0 | 29764.7993 | 100 |  | 0 | 100 |  | 0
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 25185.5994 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 19079.9995 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 16027.1996 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 12974.3997 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 |  | 0 | 0 | 177314.075 | 94d | 0 | 0 | 0 | 177314.075 | 0% | Not Started | 0 | 177314.075 | 100 |  | 0 | 100 |  | 0
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 237d | [5 empty] | 90546.399 |  | 56.48% |  | 73385.4201 | 121609.5984
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 15313.5998 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 2011-08-29 08:00 | 77d | 17340.3998 | 0 | 0 | 0 | 0 | 17340.3998 | 0 | 100% | Finished | 14863.1998 | 14863.1998 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 | 2011-11-28 08:00 | 45d | 10133.9999 | 1351.2 | 6d | 0 | 0 | 10133.9999 | 1351.2 | 88.24% | Started | 15697.7646 | 17790.7998 | 100 | 56.962 | 88.2353 | 100 | 56.962 | 88.2353
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 | 2011-12-12 08:00 | 35d | 7881.9999 | 6530.7999 | 29d | 0 | 0 | 7881.9999 | 6530.7999 | 54.69% | Started | 9359.8749 | 17115.1998 | 100 | 46.0526 | 54.6875 | 100 | 46.0526 | 54.6875
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 2011-10-27 08:00 | 67d | 15088.3998 | 7656.7999 | 34d | 0 | 0 | 15088.3998 | 7656.7999 | 66.34% | Started | 33463.3808 | 42112.3994 | 100 | 29.9107 | 66.3366 | 100 | 29.9107 | 66.3366
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2535300.0811 | 100
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 25d | 2 | 0 | 0 | 5630 | 0 | 5632 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 7040000.1573 | 100
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 18d | 1.44 | 0 | 0 | 4053.6001 | 0 | 4055.0401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1800 | 100 | 100 | 5068800.2353 | 100
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-04-13 17:00 |  | TP Name | 13/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 330d | [5 empty] | 570971.7963 |  | 41.01% |  | 459860.5981 | 1069364.9435
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 330d | [5 empty] | 301909.7178 |  | 100% |  | 213962.2682 | 213962.3182
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 72d | 9169.92 | 0 | 0 | 0 | 0 | 9169.92 | 0 | 100% | Finished | 1400.96 | 1400.96 | 100 | 654.5455 | 100 | 100 | 654.5455 | 100
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1273.6 | 1273.6 | 100 | 150 | 100 | 100 | 150 | 100
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 5476.48 | 5476.48 | 100 | 183.7209 | 100 | 100 | 183.7209 | 100
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 88d | 11207.6801 | 0 | 0 | 0 | 0 | 11207.6801 | 0 | 100% | Finished | 8405.76 | 8405.76 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 2011-08-30 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 7768.96 | 7768.96 | 100 | 129.5082 | 100 | 100 | 129.5082 | 100
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 | 2011-11-17 08:00 | 74d | 9424.64 | 0 | 0 | 0 | 0 | 9424.64 | 0 | 100% | Finished | 5858.56 | 5858.56 | 100 | 160.8696 | 100 | 100 | 160.8696 | 100
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 73d | 5.84 | 0 | 0 | 9292.2803 | 0 | 9298.1203 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7300 | 100 | 100 | 11622650.6014 | 100
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 3d | 0.24 | 0.4 | 5d | 382.08 | 636.8 | 382.32 | 637.2 | 37.5% | Started | 0.03 | 0.08 | 100 | 300 | 37.5 | 100 | 477899.9939 | 37.5
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-18 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-25 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 330d | [5 empty] | 66509.0402 |  | 97.19% |  | 65209.1326 | 67095.0404
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3184 | 3184 | 100 | 84 | 100 | 100 | 84 | 100
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2674.56 | 2674.56 | 100 | 80.9524 | 100 | 100 | 80.9524 | 100
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3438.72 | 3438.72 | 100 | 77.7778 | 100 | 100 | 77.7778 | 100
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 2037.76 | 2037.76 | 100 | 112.5 | 100 | 100 | 112.5 | 100
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 14d | 1.12 | 0 | 0 | 1783.04 | 0 | 1784.16 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1400 | 100 | 100 | 2230200.0986 | 100
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 30d | 2.4 | 0 | 0 | 1783.04 | 0 | 1785.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3000 | 100 | 100 | 2231800.0986 | 100
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 75 | 100 | 100 | 75 | 100
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 | 2011-11-25 08:00 | 10d | 1273.6 | 0 | 0 | 0 | 0 | 1273.6 | 0 | 100% | Finished | 9424.64 | 9424.64 | 100 | 13.5135 | 100 | 100 | 13.5135 | 100
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 2011-09-07 08:00 | 115d | 14646.4001 | 0 | 0 | 0 | 0 | 14646.4001 | 0 | 100% | Finished | 11335.0401 | 11335.0401 | 100 | 129.2135 | 100 | 100 | 129.2135 | 100
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2012-01-09 08:00 | 63d | 8023.68 | 0 | 0 | 0 | 0 | 8023.68 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 73.2558 | 100 | 100 | 73.2558 | 100
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 | 2012-03-20 08:00 | 19d | 2419.84 | 891.52 | 7d | 0 | 0 | 2419.84 | 891.52 | 73.08% | Started | 5118.8922 | 7004.8 | 100 | 34.5455 | 73.0769 | 100 | 34.5455 | 73.0769
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-23 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-29 08:00 | 61d | 4.88 | 0 | 0 | 7768.96 | 0 | 7773.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 6100 | 100 | 100 | 9717300.1682 | 100
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 9d | 0.72 | 0 | 0 | 1146.24 | 0 | 1146.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 1433700.0198 | 100
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-07 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 327d | [5 empty] | 27546.7201 |  | 85.46% |  | 28455.7469 | 33295.8402
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 3184 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2012-03-12 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 107.1429 | 100 | 100 | 107.1429 | 100
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-10-12 08:00 | 5d | 636.8 | 0 | 0 | 0 | 0 | 636.8 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 26.3158 | 100 | 100 | 26.3158 | 100
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-29 08:00 | 6d | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 600 | 100
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 | 2011-12-08 08:00 | 41d | 5221.76 | 0 | 0 | 0 | 0 | 5221.76 | 0 | 100% | Finished | 7132.16 | 7132.16 | 100 | 73.2143 | 100 | 100 | 73.2143 | 100
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2011-11-03 08:00 | 78d | 9934.08 | 0 | 0 | 0 | 0 | 9934.08 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 90.6977 | 100 | 100 | 90.6977 | 100
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-19 08:00 | 20d | 1.6 | 0.32 | 4d | 2547.2 | 509.44 | 2548.8 | 509.76 | 83.33% | Started | 0.066667 | 0.08 | 100 | 2000 | 83.3333 | 100 | 3186000.0101 | 83.3333
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 130d | [5 empty] | 34007.6796 |  | 43.97% |  | 32279.0661 | 73415.839
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 | 2011-11-28 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 7431.5999 | 7431.5999 | 100 | 193.9394 | 100 | 100 | 193.9394 | 100
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-02-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 10359.1999 | 10359.1999 | 100 | 43.4783 | 100 | 100 | 43.4783 | 100
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-03-27 08:00 | 14d | 3152.8 | 1801.6 | 8d | 0 | 0 | 3152.8 | 1801.6 | 63.64% | Started | 5589.0544 | 8782.7999 | 100 | 35.8974 | 63.6364 | 100 | 35.8974 | 63.6364
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-04-04 08:00 | 8d | 1801.6 | 3603.2 | 16d | 0 | 0 | 1801.6 | 3603.2 | 33.33% | Started | 3453.0667 | 10359.1999 | 100 | 17.3913 | 33.3333 | 100 | 17.3913 | 33.3333
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 | 2012-03-27 08:00 | 14d | 3152.8 | 1801.6 | 8d | 0 | 0 | 3152.8 | 1801.6 | 63.64% | Started | 5445.7453 | 8557.5999 | 100 | 36.8421 | 63.6364 | 100 | 36.8421 | 63.6364
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 |  | 0 | 0 | 6981.1999 | 31d | 0 | 0 | 0 | 6981.1999 | 0% | Not Started | 0 | 6981.1999 | 100 |  | 0 | 100 |  | 0
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 |  | 0 | 0 | 4729.1999 | 21d | 0 | 0 | 0 | 4729.1999 | 0% | Not Started | 0 | 4729.1999 | 100 |  | 0 | 100 |  | 0
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 35d | [5 empty] | 11037.7599 |  | 5.839% |  | 5325.8777 | 91207.1188
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 | 2012-03-29 08:00 | 12d | 2702.4 | 4954.3999 | 22d | 0 | 0 | 2702.4 | 4954.3999 | 35.29% | Started | 5325.3177 | 15088.3998 | 100 | 17.9104 | 35.2941 | 100 | 17.9104 | 35.2941
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 |  | 0 | 0 | 225.2 | 1d | 0 | 0 | 0 | 225.2 | 0% | Not Started | 0 | 225.2 | 100 |  | 0 | 100 |  | 0
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 |  | 0 | 0 | 7656.7999 | 34d | 0 | 0 | 0 | 7656.7999 | 0% | Not Started | 0 | 7656.7999 | 100 |  | 0 | 100 |  | 0
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 |  | 0 | 0 | 4503.9999 | 20d | 0 | 0 | 0 | 4503.9999 | 0% | Not Started | 0 | 4503.9999 | 100 |  | 0 | 100 |  | 0
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 |  | 0 | 0 | 7881.9999 | 35d | 0 | 0 | 0 | 7881.9999 | 0% | Not Started | 0 | 7881.9999 | 100 |  | 0 | 100 |  | 0
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-26 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-02-27 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-28 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 25d | [5 empty] | 6082.5599 |  | 0.0007129% |  | 0.464 | 65083.7591
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 6305.5999 | 100 |  | 0 | 100 |  | 0
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 |  | 0 | 0 | 8107.1999 | 36d | 0 | 0 | 0 | 8107.1999 | 0% | Not Started | 0 | 8107.1999 | 100 |  | 0 | 100 |  | 0
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 |  | 0 | 0 | 6305.5999 | 28d | 0 | 0 | 0 | 6305.5999 | 0% | Not Started | 0 | 6305.5999 | 100 |  | 0 | 100 |  | 0
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 10584.3999 | 100 |  | 0 | 100 |  | 0
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 |  | 0 | 0 | 8782.7999 | 39d | 0 | 0 | 0 | 8782.7999 | 0% | Not Started | 0 | 8782.7999 | 100 |  | 0 | 100 |  | 0
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 10584.3999 | 100 |  | 0 | 100 |  | 0
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 3d | 0.24 | 0.16 | 2d | 675.6 | 450.4 | 675.84 | 450.56 | 60% | Started | 0.048 | 0.08 | 100 | 300 | 60 | 100 | 844799.9884 | 60
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 1d | 0.08 | 0.32 | 4d | 225.2 | 900.8 | 225.28 | 901.12 | 20% | Started | 0.016 | 0.08 | 100 | 100 | 20 | 100 | 281600.0025 | 20
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-23 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-04 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 30019.9193
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 6614.3998 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 6614.3998 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 6995.9998 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 5087.9999 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 |  | 0 | 0 | 11193.5997 | 88d | 0 | 0 | 0 | 11193.5997 | 0% | Not Started | 0 | 4706.3999 | 100 |  | 0 | 100 |  | 0
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 43018.7988
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 8141.8398 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 9113.9997 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 6440.5598 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 8992.4798 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 10329.1997 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 145010.2365
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 |  | 0 | 0 | 29764.7993 | 117d | 0 | 0 | 0 | 29764.7993 | 0% | Not Started | 0 | 29764.7993 | 100 |  | 0 | 100 |  | 0
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 30273.5993 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 29255.9993 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 28747.1993 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 26966.3994 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 |  | 0 | 0 | 177314.075 | 94d | 0 | 0 | 0 | 177314.075 | 0% | Not Started | 0 | 177314.075 | 100 |  | 0 | 100 |  | 0
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 292d | [5 empty] | 123878.3188 |  | 88.21% |  | 114628.0426 | 129941.9982
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 15313.5998 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 2011-08-29 08:00 | 77d | 17340.3998 | 0 | 0 | 0 | 0 | 17340.3998 | 0 | 100% | Finished | 14863.1998 | 14863.1998 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 | 2011-11-28 08:00 | 51d | 11485.1998 | 0 | 0 | 0 | 0 | 11485.1998 | 0 | 100% | Finished | 17790.7998 | 17790.7998 | 100 | 64.557 | 100 | 100 | 64.557 | 100
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 | 2011-12-12 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 17115.1998 | 17115.1998 | 100 | 84.2105 | 100 | 100 | 84.2105 | 100
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-02-06 08:00 | 50d | 11259.9998 | 0 | 0 | 0 | 0 | 11259.9998 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 78.125 | 100 | 100 | 78.125 | 100
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 2011-10-27 08:00 | 101d | 22745.1997 | 0 | 0 | 0 | 0 | 22745.1997 | 0 | 100% | Finished | 50444.7993 | 50444.7993 | 100 | 45.0893 | 100 | 100 | 45.0893 | 100
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2535300.0811 | 100
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 25d | 2 | 0 | 0 | 5630 | 0 | 5632 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 7040000.1573 | 100
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-12 08:00 | 2d | 0.16 | 1.6 | 20d | 450.4 | 4504 | 450.56 | 4505.6 | 9.091% | Started | 0.0072727 | 0.08 | 100 | 200 | 9.0909 | 100 | 563200.005 | 9.0909
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 18d | 1.44 | 0 | 0 | 4053.6001 | 0 | 4055.0401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1800 | 100 | 100 | 5068800.2353 | 100
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-09 08:00 | 26d | 2.08 | 3.68 | 46d | 5855.2002 | 10359.2002 | 5857.2802 | 10362.8802 | 36.11% | Started | 0.028889 | 0.08 | 100 | 2600 | 36.1111 | 100 | 7321600.4077 | 36.1111
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 1d | 0.08 | 0.72 | 9d | 225.2 | 2026.8 | 225.28 | 2027.52 | 10% | Started | 0.008 | 0.08 | 100 | 100 | 10 | 100 | 281600.0025 | 10

## TP7
| TP Status Date | 2012-06-29 17:00 |  | TP Name | 29/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 385d | [5 empty] | 714927.8758 |  | 50.32% |  | 564213.6759 | 1106449.3426
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 335d | [5 empty] | 302546.9178 |  | 100% |  | 213962.3182 | 213962.3182
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 72d | 9169.92 | 0 | 0 | 0 | 0 | 9169.92 | 0 | 100% | Finished | 1400.96 | 1400.96 | 100 | 654.5455 | 100 | 100 | 654.5455 | 100
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1273.6 | 1273.6 | 100 | 150 | 100 | 100 | 150 | 100
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 5476.48 | 5476.48 | 100 | 183.7209 | 100 | 100 | 183.7209 | 100
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 88d | 11207.6801 | 0 | 0 | 0 | 0 | 11207.6801 | 0 | 100% | Finished | 8405.76 | 8405.76 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 2011-08-30 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 7768.96 | 7768.96 | 100 | 129.5082 | 100 | 100 | 129.5082 | 100
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 | 2011-11-17 08:00 | 74d | 9424.64 | 0 | 0 | 0 | 0 | 9424.64 | 0 | 100% | Finished | 5858.56 | 5858.56 | 100 | 160.8696 | 100 | 100 | 160.8696 | 100
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 73d | 5.84 | 0 | 0 | 9292.2803 | 0 | 9298.1203 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7300 | 100 | 100 | 11622650.6014 | 100
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-18 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-25 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 337d | [5 empty] | 67400.5602 |  | 100% |  | 67095.0404 | 67095.0404
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3184 | 3184 | 100 | 84 | 100 | 100 | 84 | 100
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2674.56 | 2674.56 | 100 | 80.9524 | 100 | 100 | 80.9524 | 100
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3438.72 | 3438.72 | 100 | 77.7778 | 100 | 100 | 77.7778 | 100
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 2037.76 | 2037.76 | 100 | 112.5 | 100 | 100 | 112.5 | 100
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 14d | 1.12 | 0 | 0 | 1783.04 | 0 | 1784.16 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1400 | 100 | 100 | 2230200.0986 | 100
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 30d | 2.4 | 0 | 0 | 1783.04 | 0 | 1785.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3000 | 100 | 100 | 2231800.0986 | 100
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 75 | 100 | 100 | 75 | 100
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 | 2011-11-25 08:00 | 10d | 1273.6 | 0 | 0 | 0 | 0 | 1273.6 | 0 | 100% | Finished | 9424.64 | 9424.64 | 100 | 13.5135 | 100 | 100 | 13.5135 | 100
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 2011-09-07 08:00 | 115d | 14646.4001 | 0 | 0 | 0 | 0 | 14646.4001 | 0 | 100% | Finished | 11335.0401 | 11335.0401 | 100 | 129.2135 | 100 | 100 | 129.2135 | 100
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2012-01-09 08:00 | 63d | 8023.68 | 0 | 0 | 0 | 0 | 8023.68 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 73.2558 | 100 | 100 | 73.2558 | 100
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 | 2012-03-20 08:00 | 26d | 3311.36 | 0 | 0 | 0 | 0 | 3311.36 | 0 | 100% | Finished | 7004.8 | 7004.8 | 100 | 47.2727 | 100 | 100 | 47.2727 | 100
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-23 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-29 08:00 | 61d | 4.88 | 0 | 0 | 7768.96 | 0 | 7773.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 6100 | 100 | 100 | 9717300.1682 | 100
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 9d | 0.72 | 0 | 0 | 1146.24 | 0 | 1146.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 1433700.0198 | 100
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-07 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 382d | [5 empty] | 32899.2001 |  | 85.46% |  | 28456.0002 | 33295.8402
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 3184 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2012-03-12 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 107.1429 | 100 | 100 | 107.1429 | 100
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-10-12 08:00 | 5d | 636.8 | 0 | 0 | 0 | 0 | 636.8 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 26.3158 | 100 | 100 | 26.3158 | 100
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-29 08:00 | 6d | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 600 | 100
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 | 2011-12-08 08:00 | 41d | 5221.76 | 0 | 0 | 0 | 0 | 5221.76 | 0 | 100% | Finished | 7132.16 | 7132.16 | 100 | 73.2143 | 100 | 100 | 73.2143 | 100
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2011-11-03 08:00 | 78d | 9934.08 | 0 | 0 | 0 | 0 | 9934.08 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 90.6977 | 100 | 100 | 90.6977 | 100
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-04 08:00 | 25d | 2 | 0 | 0 | 3184 | 0 | 3186 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 3982500.089 | 100
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-30 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-19 08:00 | 24d | 1.92 | 0 | 0 | 3056.6399 | 0 | 3058.5599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2400 | 100 | 100 | 3823199.9511 | 100
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 185d | [5 empty] | 59456.9594 |  | 87.12% |  | 63957.4391 | 73415.839
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 | 2011-11-28 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 7431.5999 | 7431.5999 | 100 | 193.9394 | 100 | 100 | 193.9394 | 100
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-02-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 10359.1999 | 10359.1999 | 100 | 43.4783 | 100 | 100 | 43.4783 | 100
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 100% | Finished | 8782.7999 | 8782.7999 | 100 | 56.4103 | 100 | 100 | 56.4103 | 100
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-04-04 08:00 | 24d | 5404.7999 | 0 | 0 | 0 | 0 | 5404.7999 | 0 | 100% | Finished | 10359.1999 | 10359.1999 | 100 | 52.1739 | 100 | 100 | 52.1739 | 100
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 100% | Finished | 8557.5999 | 8557.5999 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 | 2012-04-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6981.1999 | 6981.1999 | 100 | 64.5161 | 100 | 100 | 64.5161 | 100
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 | 2012-05-02 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4729.1999 | 4729.1999 | 100 | 95.2381 | 100 | 100 | 95.2381 | 100
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-05-31 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6755.9999 | 6755.9999 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-31 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 90d | [5 empty] | 55856.6395 |  | 61.13% |  | 55757.5111 | 91207.1188
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 | 2012-03-29 08:00 | 34d | 7656.7999 | 0 | 0 | 0 | 0 | 7656.7999 | 0 | 100% | Finished | 15088.3998 | 15088.3998 | 100 | 50.7463 | 100 | 100 | 50.7463 | 100
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 | 2012-04-25 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 225.2 | 225.2 | 100 | 1500 | 100 | 100 | 1500 | 100
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-06-14 08:00 | 12d | 2702.4 | 675.6 | 3d | 0 | 0 | 2702.4 | 675.6 | 80% | Started | 11530.24 | 14412.7998 | 100 | 18.75 | 80 | 100 | 18.75 | 80
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-23 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 100 | 100 | 100 | 100 | 100
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-06-15 08:00 | 11d | 2477.2 | 900.8 | 4d | 0 | 0 | 2477.2 | 900.8 | 73.33% | Started | 4954.4 | 6755.9999 | 100 | 36.6667 | 73.3333 | 100 | 36.6667 | 73.3333
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-20 08:00 | 8d | 1801.6 | 1576.4 | 7d | 0 | 0 | 1801.6 | 1576.4 | 53.33% | Started | 2402.1334 | 4503.9999 | 100 | 40 | 53.3333 | 100 | 40 | 53.3333
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 |  | 0 | 0 | 6755.9999 | 30d | 0 | 0 | 0 | 6755.9999 | 0% | Not Started | 0 | 6755.9999 | 100 |  | 0 | 100 |  | 0
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-06 08:00 | 18d | 4053.5999 | 450.4 | 2d | 0 | 0 | 4053.5999 | 450.4 | 90% | Started | 4053.5998 | 4503.9999 | 100 | 90 | 90 | 100 | 90 | 90
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 | 2012-06-28 08:00 | 2d | 450.4 | 5179.5999 | 23d | 0 | 0 | 450.4 | 5179.5999 | 8% | Started | 612.544 | 7656.7999 | 100 | 5.8824 | 8 | 100 | 5.8824 | 8
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-09 08:00 | 25d | 5629.9999 | 0 | 0 | 0 | 0 | 5629.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 125 | 100 | 100 | 125 | 100
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 | 2012-06-08 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 7881.9999 | 7881.9999 | 100 | 42.8571 | 100 | 100 | 42.8571 | 100
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-26 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-02-27 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-28 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-18 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 2816000.0629 | 100
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-15 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-14 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-27 08:00 | 3d | 0.24 | 0.32 | 4d | 675.6 | 900.8 | 675.84 | 901.12 | 42.86% | Started | 0.034286 | 0.08 | 100 | 300 | 42.8571 | 100 | 844799.9884 | 42.8571
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 80d | [5 empty] | 30182.9597 |  | 31.28% |  | 20356.6695 | 65083.7591
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-05-25 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6305.5999 | 6305.5999 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 | 2012-06-27 08:00 | 3d | 675.6 | 6080.3999 | 27d | 0 | 0 | 675.6 | 6080.3999 | 10% | Started | 810.72 | 8107.1999 | 100 | 8.3333 | 10 | 100 | 8.3333 | 10
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-06-04 08:00 | 19d | 4278.7999 | 0 | 0 | 0 | 0 | 4278.7999 | 0 | 100% | Finished | 6305.5999 | 6305.5999 | 100 | 67.8571 | 100 | 100 | 67.8571 | 100
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 10584.3999 | 100 |  | 0 | 100 |  | 0
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-06-11 08:00 | 15d | 3378 | 900.8 | 4d | 0 | 0 | 3378 | 900.8 | 78.95% | Started | 6933.7896 | 8782.7999 | 100 | 38.4615 | 78.9474 | 100 | 38.4615 | 78.9474
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 |  | 0 | 0 | 10584.3999 | 47d | 0 | 0 | 0 | 10584.3999 | 0% | Not Started | 0 | 10584.3999 | 100 |  | 0 | 100 |  | 0
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-23 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-04 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-19 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 33d | [5 empty] | 4200.2401 |  | 0.0001386% |  | 0.069474 | 46428.7189
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 6614.3998 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 6614.3998 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 9921.5998 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 12083.9997 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 |  | 0 | 0 | 11193.5997 | 88d | 0 | 0 | 0 | 11193.5997 | 0% | Not Started | 0 | 11193.5997 | 100 |  | 0 | 100 |  | 0
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 33d | 2.64 | 0.4 | 5d | 4197.6001 | 636 | 4200.2401 | 636.4 | 86.84% | Started | 0.069474 | 0.08 | 100 | 3300 | 86.8421 | 100 | 5250300.2393 | 86.8421
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 49702.3986
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 8141.8398 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 9113.9997 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 6440.5598 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 8992.4798 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 17012.7995 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 55d | [5 empty] | 9670.24 |  | 0.0001436% |  | 0.24 | 159002.2362
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 |  | 0 | 0 | 29764.7993 | 117d | 0 | 0 | 0 | 29764.7993 | 0% | Not Started | 0 | 29764.7993 | 100 |  | 0 | 100 |  | 0
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 30273.5993 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 29255.9993 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 28747.1993 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 40958.399 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-16 08:00 | 12d | 0.96 | 0 | 0 | 3052.8 | 0 | 3053.76 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3817200.1463 | 100
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 16d | 1.28 | 0 | 0 | 4070.3999 | 0 | 4071.6799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1600 | 100 | 100 | 5089599.9917 | 100
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-14 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 3181000.0711 | 100
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 |  | 0 | 0 | 177314.075 | 94d | 0 | 0 | 0 | 177314.075 | 0% | Not Started | 0 | 177314.075 | 100 |  | 0 | 100 |  | 0
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 347d | [5 empty] | 152714.159 |  | 88.22% |  | 114628.3879 | 129941.9982
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 15313.5998 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 2011-08-29 08:00 | 77d | 17340.3998 | 0 | 0 | 0 | 0 | 17340.3998 | 0 | 100% | Finished | 14863.1998 | 14863.1998 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 | 2011-11-28 08:00 | 51d | 11485.1998 | 0 | 0 | 0 | 0 | 11485.1998 | 0 | 100% | Finished | 17790.7998 | 17790.7998 | 100 | 64.557 | 100 | 100 | 64.557 | 100
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 | 2011-12-12 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 17115.1998 | 17115.1998 | 100 | 84.2105 | 100 | 100 | 84.2105 | 100
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-02-06 08:00 | 50d | 11259.9998 | 0 | 0 | 0 | 0 | 11259.9998 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 78.125 | 100 | 100 | 78.125 | 100
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 2011-10-27 08:00 | 101d | 22745.1997 | 0 | 0 | 0 | 0 | 22745.1997 | 0 | 100% | Finished | 50444.7993 | 50444.7993 | 100 | 45.0893 | 100 | 100 | 45.0893 | 100
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2535300.0811 | 100
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 25d | 2 | 0 | 0 | 5630 | 0 | 5632 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 7040000.1573 | 100
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-12 08:00 | 22d | 1.76 | 0 | 0 | 4954.3999 | 0 | 4956.1599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2200 | 100 | 100 | 6195200.0164 | 100
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-26 08:00 | 20d | 1.6 | 0 | 0 | 4504 | 0 | 4505.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2000 | 100 | 100 | 5632000.1258 | 100
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 33d | 2.64 | 0.4 | 5d | 7431.6001 | 1126 | 7434.2401 | 1126.4 | 86.84% | Started | 0.069474 | 0.08 | 100 | 3300 | 86.8421 | 100 | 9292800.3297 | 86.8421
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 18d | 1.44 | 0 | 0 | 4053.6001 | 0 | 4055.0401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1800 | 100 | 100 | 5068800.2353 | 100
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-09 08:00 | 72d | 5.76 | 0 | 0 | 16214.4004 | 0 | 16220.1604 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7200 | 100 | 100 | 20275200.9413 | 100
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 2816000.0629 | 100

## TP8
| TP Status Date | 2012-09-14 17:00 |  | TP Name | 14/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 440d | [5 empty] | 802496.7537 |  | 62.53% |  | 701153.4401 | 1121316.9422
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 335d | [5 empty] | 302546.9178 |  | 100% |  | 213962.3182 | 213962.3182
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 72d | 9169.92 | 0 | 0 | 0 | 0 | 9169.92 | 0 | 100% | Finished | 1400.96 | 1400.96 | 100 | 654.5455 | 100 | 100 | 654.5455 | 100
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1273.6 | 1273.6 | 100 | 150 | 100 | 100 | 150 | 100
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 5476.48 | 5476.48 | 100 | 183.7209 | 100 | 100 | 183.7209 | 100
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 88d | 11207.6801 | 0 | 0 | 0 | 0 | 11207.6801 | 0 | 100% | Finished | 8405.76 | 8405.76 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 2011-08-30 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 7768.96 | 7768.96 | 100 | 129.5082 | 100 | 100 | 129.5082 | 100
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 | 2011-11-17 08:00 | 74d | 9424.64 | 0 | 0 | 0 | 0 | 9424.64 | 0 | 100% | Finished | 5858.56 | 5858.56 | 100 | 160.8696 | 100 | 100 | 160.8696 | 100
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 73d | 5.84 | 0 | 0 | 9292.2803 | 0 | 9298.1203 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7300 | 100 | 100 | 11622650.6014 | 100
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-18 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-25 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 337d | [5 empty] | 67400.5602 |  | 100% |  | 67095.0404 | 67095.0404
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3184 | 3184 | 100 | 84 | 100 | 100 | 84 | 100
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2674.56 | 2674.56 | 100 | 80.9524 | 100 | 100 | 80.9524 | 100
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3438.72 | 3438.72 | 100 | 77.7778 | 100 | 100 | 77.7778 | 100
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 2037.76 | 2037.76 | 100 | 112.5 | 100 | 100 | 112.5 | 100
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 14d | 1.12 | 0 | 0 | 1783.04 | 0 | 1784.16 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1400 | 100 | 100 | 2230200.0986 | 100
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 30d | 2.4 | 0 | 0 | 1783.04 | 0 | 1785.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3000 | 100 | 100 | 2231800.0986 | 100
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 75 | 100 | 100 | 75 | 100
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 | 2011-11-25 08:00 | 10d | 1273.6 | 0 | 0 | 0 | 0 | 1273.6 | 0 | 100% | Finished | 9424.64 | 9424.64 | 100 | 13.5135 | 100 | 100 | 13.5135 | 100
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 2011-09-07 08:00 | 115d | 14646.4001 | 0 | 0 | 0 | 0 | 14646.4001 | 0 | 100% | Finished | 11335.0401 | 11335.0401 | 100 | 129.2135 | 100 | 100 | 129.2135 | 100
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2012-01-09 08:00 | 63d | 8023.68 | 0 | 0 | 0 | 0 | 8023.68 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 73.2558 | 100 | 100 | 73.2558 | 100
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 | 2012-03-20 08:00 | 26d | 3311.36 | 0 | 0 | 0 | 0 | 3311.36 | 0 | 100% | Finished | 7004.8 | 7004.8 | 100 | 47.2727 | 100 | 100 | 47.2727 | 100
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-23 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-29 08:00 | 61d | 4.88 | 0 | 0 | 7768.96 | 0 | 7773.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 6100 | 100 | 100 | 9717300.1682 | 100
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 9d | 0.72 | 0 | 0 | 1146.24 | 0 | 1146.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 1433700.0198 | 100
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-07 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 437d | [5 empty] | 35320.5602 |  | 85.46% |  | 28456.0509 | 33295.8402
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 |  | 0 | 0 | 3184 | 25d | 0 | 0 | 0 | 3184 | 0% | Not Started | 0 | 3184 | 100 |  | 0 | 100 |  | 0
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2012-03-12 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 107.1429 | 100 | 100 | 107.1429 | 100
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 |  | 0 | 0 | 1655.68 | 13d | 0 | 0 | 0 | 1655.68 | 0% | Not Started | 0 | 1655.68 | 100 |  | 0 | 100 |  | 0
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-10-12 08:00 | 5d | 636.8 | 0 | 0 | 0 | 0 | 636.8 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 26.3158 | 100 | 100 | 26.3158 | 100
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-29 08:00 | 6d | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 600 | 100
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 | 2011-12-08 08:00 | 41d | 5221.76 | 0 | 0 | 0 | 0 | 5221.76 | 0 | 100% | Finished | 7132.16 | 7132.16 | 100 | 73.2143 | 100 | 100 | 73.2143 | 100
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2011-11-03 08:00 | 78d | 9934.08 | 0 | 0 | 0 | 0 | 9934.08 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 90.6977 | 100 | 100 | 90.6977 | 100
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-04 08:00 | 25d | 2 | 0 | 0 | 3184 | 0 | 3186 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 3982500.089 | 100
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-30 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-19 08:00 | 24d | 1.92 | 0 | 0 | 3056.6399 | 0 | 3058.5599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2400 | 100 | 100 | 3823199.9511 | 100
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-08-21 08:00 | 19d | 1.52 | 0.88 | 11d | 2419.8401 | 1400.96 | 2421.3601 | 1401.84 | 63.33% | Started | 0.050667 | 0.08 | 100 | 1900 | 63.3333 | 100 | 3026700.1775 | 63.3333
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 240d | [5 empty] | 59456.9594 |  | 87.12% |  | 63957.4391 | 73415.839
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 |  | 0 | 0 | 9458.3999 | 42d | 0 | 0 | 0 | 9458.3999 | 0% | Not Started | 0 | 9458.3999 | 100 |  | 0 | 100 |  | 0
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 | 2011-11-28 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 7431.5999 | 7431.5999 | 100 | 193.9394 | 100 | 100 | 193.9394 | 100
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-02-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 10359.1999 | 10359.1999 | 100 | 43.4783 | 100 | 100 | 43.4783 | 100
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 100% | Finished | 8782.7999 | 8782.7999 | 100 | 56.4103 | 100 | 100 | 56.4103 | 100
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-04-04 08:00 | 24d | 5404.7999 | 0 | 0 | 0 | 0 | 5404.7999 | 0 | 100% | Finished | 10359.1999 | 10359.1999 | 100 | 52.1739 | 100 | 100 | 52.1739 | 100
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 100% | Finished | 8557.5999 | 8557.5999 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 | 2012-04-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6981.1999 | 6981.1999 | 100 | 64.5161 | 100 | 100 | 64.5161 | 100
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 | 2012-05-02 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4729.1999 | 4729.1999 | 100 | 95.2381 | 100 | 100 | 95.2381 | 100
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-05-31 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6755.9999 | 6755.9999 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-31 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 145d | [5 empty] | 71396.2393 |  | 84.2% |  | 76794.319 | 91207.1188
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 | 2012-03-29 08:00 | 34d | 7656.7999 | 0 | 0 | 0 | 0 | 7656.7999 | 0 | 100% | Finished | 15088.3998 | 15088.3998 | 100 | 50.7463 | 100 | 100 | 50.7463 | 100
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 | 2012-04-25 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 225.2 | 225.2 | 100 | 1500 | 100 | 100 | 1500 | 100
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-06-14 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 23.4375 | 100 | 100 | 23.4375 | 100
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-23 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 100 | 100 | 100 | 100 | 100
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-06-15 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 6755.9999 | 6755.9999 | 100 | 50 | 100 | 100 | 50 | 100
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-20 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 75 | 100 | 100 | 75 | 100
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-07-09 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6755.9999 | 6755.9999 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-06 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 100 | 100 | 100 | 100 | 100
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 | 2012-06-28 08:00 | 25d | 5629.9999 | 0 | 0 | 0 | 0 | 5629.9999 | 0 | 100% | Finished | 7656.7999 | 7656.7999 | 100 | 73.5294 | 100 | 100 | 73.5294 | 100
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-09 08:00 | 25d | 5629.9999 | 0 | 0 | 0 | 0 | 5629.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 125 | 100 | 100 | 125 | 100
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 | 2012-06-08 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 7881.9999 | 7881.9999 | 100 | 42.8571 | 100 | 100 | 42.8571 | 100
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-26 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-02-27 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-28 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-18 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 2816000.0629 | 100
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-15 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-07-06 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-14 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-27 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 135d | [5 empty] | 48874.5595 |  | 77.85% |  | 50670.9593 | 65083.7591
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 |  | 0 | 0 | 14412.7998 | 64d | 0 | 0 | 0 | 14412.7998 | 0% | Not Started | 0 | 14412.7998 | 100 |  | 0 | 100 |  | 0
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-05-25 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6305.5999 | 6305.5999 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 | 2012-06-27 08:00 | 30d | 6755.9999 | 0 | 0 | 0 | 0 | 6755.9999 | 0 | 100% | Finished | 8107.1999 | 8107.1999 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-06-04 08:00 | 19d | 4278.7999 | 0 | 0 | 0 | 0 | 4278.7999 | 0 | 100% | Finished | 6305.5999 | 6305.5999 | 100 | 67.8571 | 100 | 100 | 67.8571 | 100
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 2012-08-01 08:00 | 21d | 4729.1999 | 0 | 0 | 0 | 0 | 4729.1999 | 0 | 100% | Finished | 10584.3999 | 10584.3999 | 100 | 44.6809 | 100 | 100 | 44.6809 | 100
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-06-11 08:00 | 19d | 4278.7999 | 0 | 0 | 0 | 0 | 4278.7999 | 0 | 100% | Finished | 8782.7999 | 8782.7999 | 100 | 48.7179 | 100 | 100 | 48.7179 | 100
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 2012-07-11 08:00 | 31d | 6981.1999 | 0 | 0 | 0 | 0 | 6981.1999 | 0 | 100% | Finished | 10584.3999 | 10584.3999 | 100 | 65.9574 | 100 | 100 | 65.9574 | 100
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-23 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-04 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-19 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 88d | [5 empty] | 6235.8401 |  | 22.33% |  | 11193.6797 | 50117.5188
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 6614.3998 | 100 |  | 0 | 100 |  | 0
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 |  | 0 | 0 | 6614.3998 | 52d | 0 | 0 | 0 | 6614.3998 | 0% | Not Started | 0 | 6614.3998 | 100 |  | 0 | 100 |  | 0
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 |  | 0 | 0 | 9921.5998 | 78d | 0 | 0 | 0 | 9921.5998 | 0% | Not Started | 0 | 9921.5998 | 100 |  | 0 | 100 |  | 0
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 |  | 0 | 0 | 15772.7996 | 124d | 0 | 0 | 0 | 15772.7996 | 0% | Not Started | 0 | 15772.7996 | 100 |  | 0 | 100 |  | 0
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 | 2012-08-13 08:00 | 11d | 1399.2 | 0 | 0 | 0 | 0 | 1399.2 | 0 | 100% | Finished | 11193.5997 | 11193.5997 | 100 | 12.5 | 100 | 100 | 12.5 | 100
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 38d | 3.04 | 0 | 0 | 4833.6001 | 0 | 4836.6401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3800 | 100 | 100 | 6045800.2571 | 100
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 52740.3985
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 |  | 0 | 0 | 8141.8398 | 67d | 0 | 0 | 0 | 8141.8398 | 0% | Not Started | 0 | 8141.8398 | 100 |  | 0 | 100 |  | 0
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 |  | 0 | 0 | 9113.9997 | 75d | 0 | 0 | 0 | 9113.9997 | 0% | Not Started | 0 | 9113.9997 | 100 |  | 0 | 100 |  | 0
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 |  | 0 | 0 | 6440.5598 | 53d | 0 | 0 | 0 | 6440.5598 | 0% | Not Started | 0 | 6440.5598 | 100 |  | 0 | 100 |  | 0
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 |  | 0 | 0 | 8992.4798 | 74d | 0 | 0 | 0 | 8992.4798 | 0% | Not Started | 0 | 8992.4798 | 100 |  | 0 | 100 |  | 0
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 |  | 0 | 0 | 20050.7994 | 165d | 0 | 0 | 0 | 20050.7994 | 0% | Not Started | 0 | 20050.7994 | 100 |  | 0 | 100 |  | 0
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 110d | [5 empty] | 17811.8398 |  | 13.99% |  | 23387.0755 | 167143.036
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 | 2012-08-16 08:00 | 22d | 5596.7999 | 1526.4 | 6d | 0 | 0 | 5596.7999 | 1526.4 | 78.57% | Started | 23386.6275 | 29764.7993 | 100 | 18.8034 | 78.5714 | 100 | 18.8034 | 78.5714
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 |  | 0 | 0 | 30273.5993 | 119d | 0 | 0 | 0 | 30273.5993 | 0% | Not Started | 0 | 30273.5993 | 100 |  | 0 | 100 |  | 0
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 |  | 0 | 0 | 29255.9993 | 115d | 0 | 0 | 0 | 29255.9993 | 0% | Not Started | 0 | 29255.9993 | 100 |  | 0 | 100 |  | 0
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 |  | 0 | 0 | 28747.1993 | 113d | 0 | 0 | 0 | 28747.1993 | 0% | Not Started | 0 | 28747.1993 | 100 |  | 0 | 100 |  | 0
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 |  | 0 | 0 | 49099.1988 | 193d | 0 | 0 | 0 | 49099.1988 | 0% | Not Started | 0 | 49099.1988 | 100 |  | 0 | 100 |  | 0
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-16 08:00 | 12d | 0.96 | 0 | 0 | 3052.8 | 0 | 3053.76 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3817200.1463 | 100
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 16d | 1.28 | 0 | 0 | 4070.3999 | 0 | 4071.6799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1600 | 100 | 100 | 5089599.9917 | 100
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-08-13 08:00 | 2d | 0.16 | 0 | 0 | 508.8 | 0 | 508.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 200 | 100 | 100 | 636199.999 | 100
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-14 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 3181000.0711 | 100
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-05 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-12 08:00 | 3d | 0.24 | 0.16 | 2d | 763.2 | 508.8 | 763.44 | 508.96 | 60% | Started | 0.048 | 0.08 | 100 | 300 | 60 | 100 | 954300.0366 | 60
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 |  | 0 | 0 | 0.08 | 1d | 0 | 0 | 0 | 0.08 | 0% | Not Started | 0 | 0.08 | 100 |  | 0 | 100 |  | 0
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 | 2012-08-17 08:00 | 21d | 39612.7189 | 98088.6372 | 52d | 0 | 0 | 39612.7189 | 98088.6372 | 28.77% | Started | 51008.1595 | 177314.075 | 100 | 22.3404 | 28.7671 | 100 | 22.3404 | 28.7671
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 402d | [5 empty] | 153840.5585 |  | 88.22% |  | 114628.3984 | 129941.9982
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 |  | 0 | 0 | 15313.5998 | 68d | 0 | 0 | 0 | 15313.5998 | 0% | Not Started | 0 | 15313.5998 | 100 |  | 0 | 100 |  | 0
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 2011-08-29 08:00 | 77d | 17340.3998 | 0 | 0 | 0 | 0 | 17340.3998 | 0 | 100% | Finished | 14863.1998 | 14863.1998 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 | 2011-11-28 08:00 | 51d | 11485.1998 | 0 | 0 | 0 | 0 | 11485.1998 | 0 | 100% | Finished | 17790.7998 | 17790.7998 | 100 | 64.557 | 100 | 100 | 64.557 | 100
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 | 2011-12-12 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 17115.1998 | 17115.1998 | 100 | 84.2105 | 100 | 100 | 84.2105 | 100
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-02-06 08:00 | 50d | 11259.9998 | 0 | 0 | 0 | 0 | 11259.9998 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 78.125 | 100 | 100 | 78.125 | 100
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 2011-10-27 08:00 | 101d | 22745.1997 | 0 | 0 | 0 | 0 | 22745.1997 | 0 | 100% | Finished | 50444.7993 | 50444.7993 | 100 | 45.0893 | 100 | 100 | 45.0893 | 100
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2535300.0811 | 100
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 25d | 2 | 0 | 0 | 5630 | 0 | 5632 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 7040000.1573 | 100
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-12 08:00 | 22d | 1.76 | 0 | 0 | 4954.3999 | 0 | 4956.1599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2200 | 100 | 100 | 6195200.0164 | 100
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-26 08:00 | 20d | 1.6 | 0 | 0 | 4504 | 0 | 4505.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2000 | 100 | 100 | 5632000.1258 | 100
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 38d | 3.04 | 0 | 0 | 8557.5996 | 0 | 8560.6396 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3800 | 100 | 100 | 10700799.7508 | 100
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 18d | 1.44 | 0 | 0 | 4053.6001 | 0 | 4055.0401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1800 | 100 | 100 | 5068800.2353 | 100
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-09 08:00 | 72d | 5.76 | 0 | 0 | 16214.4004 | 0 | 16220.1604 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7200 | 100 | 100 | 20275200.9413 | 100
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 2816000.0629 | 100

## TP9
| TP Status Date | 2012-12-10 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station (1) | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 1121316.9422 |  | 501d | [5 empty] | 967988.7905 |  | 100% |  | 1121316.9422 | 1121316.9422
49 | Grondwerken en infrastructuur-zone B | 2011-01-10 08:00 | 2011-07-08 17:00 | 130d |  |  | 0 |  |  | 213962.3182 |  | 335d | [5 empty] | 302546.9178 |  | 100% |  | 213962.3182 | 213962.3182
1 | Werfinstalatie | 2011-01-11 08:00 | 2011-04-15 17:00 | 69d |  | 0 | 0 | 301.34 | 166339.678 | 166339.678 | 2011-01-10 08:00 | 90d | 216964.7974 | 0 | 0 | 0 | 0 | 216964.7974 | 0 | 100% | Finished | 166339.678 | 166339.678 | 100 | 130.4348 | 100 | 100 | 130.4348 | 100
2 | afbraakwerken en ontmanteling perrons | 2011-01-10 08:00 | 2011-02-18 17:00 | 30d |  | 0 | 0 | 3.67 | 880.8 | 880.8 | 2011-01-10 08:00 | 30d | 880.8 | 0 | 0 | 0 | 0 | 880.8 | 0 | 100% | Finished | 880.8 | 880.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | test uitvoering talud | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-02-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
4 | grondwerken (1ste) | 2011-01-25 08:00 | 2011-02-25 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-02-21 08:00 | 12d | 1528.32 | 0 | 0 | 0 | 0 | 1528.32 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 50 | 100 | 100 | 50 | 100
5 | vermaling talud 1ste niveau | 2011-02-07 08:00 | 2011-02-24 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2011-02-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 92.8571 | 100 | 100 | 92.8571 | 100
6 | bescherming talud 1ste niveau | 2011-02-08 08:00 | 2011-03-04 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-02-28 08:00 | 11d | 1400.96 | 0 | 0 | 0 | 0 | 1400.96 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
7 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 11d | 0.88 | 0 | 0 | 1400.96 | 0 | 1401.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 1752299.9903 | 100
8 | grondwerken (2de) | 2011-02-15 08:00 | 2011-03-14 17:00 | 20d |  | 0 | 0 | 15.92 | 2547.2 | 2547.2 | 2011-03-21 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 2547.2 | 2547.2 | 100 | 80 | 100 | 100 | 80 | 100
9 | vermaling beschoeiing & talud (2de niveau) | 2011-02-21 08:00 | 2011-03-15 17:00 | 17d |  | 0 | 0 | 15.92 | 2165.12 | 2165.12 | 2011-03-23 08:00 | 27d | 3438.72 | 0 | 0 | 0 | 0 | 3438.72 | 0 | 100% | Finished | 2165.12 | 2165.12 | 100 | 158.8235 | 100 | 100 | 158.8235 | 100
10 | bescherming talud - 2de niveau | 2011-02-25 08:00 | 2011-03-15 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-03-25 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
11 | beschoeiing | 2011-01-28 08:00 | 2011-03-01 17:00 | 23d |  | 0 | 0 | 15.92 | 2929.28 | 2929.28 | 2011-04-07 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2929.28 | 2929.28 | 100 | 73.913 | 100 | 100 | 73.913 | 100
12 | grondwerken fase 3 | 2011-03-11 08:00 | 2011-03-25 17:00 | 11d |  | 0 | 0 | 15.92 | 1400.96 | 1400.96 | 2011-08-15 08:00 | 72d | 9169.92 | 0 | 0 | 0 | 0 | 9169.92 | 0 | 100% | Finished | 1400.96 | 1400.96 | 100 | 654.5455 | 100 | 100 | 654.5455 | 100
13 | diepe fundering | 2011-03-17 08:00 | 2011-03-30 17:00 | 10d |  | 0 | 0 | 15.92 | 1273.6 | 1273.6 | 2011-08-18 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1273.6 | 1273.6 | 100 | 150 | 100 | 100 | 150 | 100
14 | riolering en aarding | 2011-03-21 08:00 | 2011-05-18 17:00 | 43d |  | 0 | 0 | 15.92 | 5476.48 | 5476.48 | 2011-08-16 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 5476.48 | 5476.48 | 100 | 183.7209 | 100 | 100 | 183.7209 | 100
15 | vloerplaat -1 | 2011-03-28 08:00 | 2011-06-27 17:00 | 66d |  | 0 | 0 | 15.92 | 8405.76 | 8405.76 | 2011-08-08 08:00 | 88d | 11207.6801 | 0 | 0 | 0 | 0 | 11207.6801 | 0 | 100% | Finished | 8405.76 | 8405.76 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
16 | vloerkolommen en wanden | 2011-04-11 08:00 | 2011-07-04 17:00 | 61d |  | 0 | 0 | 15.92 | 7768.96 | 7768.96 | 2011-08-30 08:00 | 79d | 10061.44 | 0 | 0 | 0 | 0 | 10061.44 | 0 | 100% | Finished | 7768.96 | 7768.96 | 100 | 129.5082 | 100 | 100 | 129.5082 | 100
17 | vloerplaat gelijkvloers | 2011-05-06 08:00 | 2011-07-08 17:00 | 46d |  | 0 | 0 | 15.92 | 5858.56 | 5858.56 | 2011-11-17 08:00 | 74d | 9424.64 | 0 | 0 | 0 | 0 | 9424.64 | 0 | 100% | Finished | 5858.56 | 5858.56 | 100 | 160.8696 | 100 | 100 | 160.8696 | 100
18 | verankering talud 3de niveau | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-19 08:00 | 15d | 1.2 | 0 | 0 | 1910.4 | 0 | 1911.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 2389500.0839 | 100
19 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-26 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
20 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-18 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
21 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-17 08:00 | 73d | 5.84 | 0 | 0 | 9292.2803 | 0 | 9298.1203 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7300 | 100 | 100 | 11622650.6014 | 100
22 | ontdubbelde vloerplaat -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
23 | kolommen staal overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-18 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
24 | kolommen staal overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-25 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
50 | Grondwerken en infrastructuur-zone C | 2011-01-10 08:00 | 2011-10-21 17:00 | 205d |  |  | 0 |  |  | 67095.0404 |  | 337d | [5 empty] | 67400.5602 |  | 100% |  | 67095.0404 | 67095.0404
25 | plaatsing bescherming reizigers | 2011-01-21 08:00 | 2011-03-10 17:00 | 35d |  | 0 | 0 | 3.67 | 1027.6 | 1027.6 | 2011-03-07 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 1027.6 | 1027.6 | 100 | 88.5714 | 100 | 100 | 88.5714 | 100
26 | afbraakwerken en ontmanteling perron | 2011-01-10 08:00 | 2011-02-28 17:00 | 36d |  | 0 | 0 | 3.67 | 1056.96 | 1056.96 | 2011-01-10 08:00 | 36d | 1056.96 | 0 | 0 | 0 | 0 | 1056.96 | 0 | 100% | Finished | 1056.96 | 1056.96 | 100 | 100 | 100 | 100 | 100 | 100
27 | afbraakwerken reizigerstunnel | 2011-03-11 08:00 | 2011-05-16 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 72.3404 | 100 | 100 | 72.3404 | 100
28 | afbraakwerken diensttunnel | 2011-02-16 08:00 | 2011-04-01 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-03-18 08:00 | 34d | 998.24 | 0 | 0 | 0 | 0 | 998.24 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 103.0303 | 100 | 100 | 103.0303 | 100
29 | grondwerken(1ste) | 2011-02-16 08:00 | 2011-04-04 17:00 | 34d |  | 0 | 0 | 15.92 | 4330.24 | 4330.24 | 2011-05-06 08:00 | 16d | 2037.76 | 0 | 0 | 0 | 0 | 2037.76 | 0 | 100% | Finished | 4330.24 | 4330.24 | 100 | 47.0588 | 100 | 100 | 47.0588 | 100
30 | vermaling talud - 1ste niv | 2011-03-03 08:00 | 2011-03-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-05-16 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 115.3846 | 100 | 100 | 115.3846 | 100
31 | bescherming talud - 1ste niv | 2011-03-04 08:00 | 2011-03-24 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-05-17 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 100 | 100 | 100 | 100 | 100
32 | afbraakwerken (deel 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-20 08:00 | 12d | 0.96 | 0 | 0 | 1528.3199 | 0 | 1529.2799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1911599.9756 | 100
33 | grondwerken (2de niv) | 2011-04-11 08:00 | 2011-05-13 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2011-05-24 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3184 | 3184 | 100 | 84 | 100 | 100 | 84 | 100
34 | vermaling beschoeiing & talud - 2de niv | 2011-04-21 08:00 | 2011-05-19 17:00 | 21d |  | 0 | 0 | 15.92 | 2674.56 | 2674.56 | 2011-06-01 08:00 | 17d | 2165.12 | 0 | 0 | 0 | 0 | 2165.12 | 0 | 100% | Finished | 2674.56 | 2674.56 | 100 | 80.9524 | 100 | 100 | 80.9524 | 100
35 | bescherming talud - 2de niv | 2011-05-03 08:00 | 2011-05-19 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2011-06-07 08:00 | 13d | 1655.68 | 0 | 0 | 0 | 0 | 1655.68 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 100 | 100 | 100 | 100 | 100
36 | beschoeiiing | 2011-02-22 08:00 | 2011-03-30 17:00 | 27d |  | 0 | 0 | 15.92 | 3438.72 | 3438.72 | 2011-08-11 08:00 | 21d | 2674.56 | 0 | 0 | 0 | 0 | 2674.56 | 0 | 100% | Finished | 3438.72 | 3438.72 | 100 | 77.7778 | 100 | 100 | 77.7778 | 100
37 | grondwerken - fase 3 | 2011-05-11 08:00 | 2011-06-01 17:00 | 16d |  | 0 | 0 | 15.92 | 2037.76 | 2037.76 | 2011-08-18 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 2037.76 | 2037.76 | 100 | 112.5 | 100 | 100 | 112.5 | 100
38 | verankering talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 14d | 1.12 | 0 | 0 | 1783.04 | 0 | 1784.16 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1400 | 100 | 100 | 2230200.0986 | 100
39 | beton bescherming talud - 3de niv | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-23 08:00 | 30d | 2.4 | 0 | 0 | 1783.04 | 0 | 1785.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3000 | 100 | 100 | 2231800.0986 | 100
40 | diepe fundering | 2011-05-16 08:00 | 2011-06-16 17:00 | 24d |  | 0 | 0 | 15.92 | 3056.64 | 3056.64 | 2011-08-24 08:00 | 18d | 2292.48 | 0 | 0 | 0 | 0 | 2292.48 | 0 | 100% | Finished | 3056.64 | 3056.64 | 100 | 75 | 100 | 100 | 75 | 100
41 | riolering en aarding | 2011-05-18 08:00 | 2011-08-29 17:00 | 74d |  | 0 | 0 | 15.92 | 9424.64 | 9424.64 | 2011-11-25 08:00 | 10d | 1273.6 | 0 | 0 | 0 | 0 | 1273.6 | 0 | 100% | Finished | 9424.64 | 9424.64 | 100 | 13.5135 | 100 | 100 | 13.5135 | 100
42 | vloerplaat -1 | 2011-05-25 08:00 | 2011-09-26 17:00 | 89d |  | 0 | 0 | 15.92 | 11335.0401 | 11335.0401 | 2011-09-07 08:00 | 115d | 14646.4001 | 0 | 0 | 0 | 0 | 14646.4001 | 0 | 100% | Finished | 11335.0401 | 11335.0401 | 100 | 129.2135 | 100 | 100 | 129.2135 | 100
43 | kolommen en wanden | 2011-06-15 08:00 | 2011-10-12 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2012-01-09 08:00 | 63d | 8023.68 | 0 | 0 | 0 | 0 | 8023.68 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 73.2558 | 100 | 100 | 73.2558 | 100
44 | vloerplaat gelijkvloers | 2011-08-08 08:00 | 2011-10-21 17:00 | 55d |  | 0 | 0 | 15.92 | 7004.8 | 7004.8 | 2012-03-20 08:00 | 26d | 3311.36 | 0 | 0 | 0 | 0 | 3311.36 | 0 | 100% | Finished | 7004.8 | 7004.8 | 100 | 47.2727 | 100 | 100 | 47.2727 | 100
45 | uitvoering inspectieput | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-23 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
46 | zuiverheidsbeton | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-29 08:00 | 61d | 4.88 | 0 | 0 | 7768.96 | 0 | 7773.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 6100 | 100 | 100 | 9717300.1682 | 100
47 | ontdubbelde vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 9d | 0.72 | 0 | 0 | 1146.24 | 0 | 1146.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 1433700.0198 | 100
48 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-11-07 08:00 | 10d | 0.8 | 0 | 0 | 1273.6 | 0 | 1274.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 1593000.0051 | 100
69 | Grondwerken en infrastructuur-zone D | 2011-01-10 08:00 | 2011-10-18 17:00 | 202d |  |  | 0 |  |  | 33295.8402 |  | 498d | [5 empty] | 39271.0401 |  | 100% |  | 33295.8402 | 33295.8402
51 | plaatsing bescherming reizigers | 2011-02-08 08:00 | 2011-03-25 17:00 | 34d |  | 0 | 0 | 3.67 | 998.24 | 998.24 | 2011-04-14 08:00 | 31d | 910.16 | 0 | 0 | 0 | 0 | 910.16 | 0 | 100% | Finished | 998.24 | 998.24 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
52 | afbraakwerken wegtunnel | 2011-01-13 08:00 | 2011-03-18 17:00 | 47d |  | 0 | 0 | 3.67 | 1379.92 | 1379.92 | 2011-01-13 08:00 | 47d | 1379.92 | 0 | 0 | 0 | 0 | 1379.92 | 0 | 100% | Finished | 1379.92 | 1379.92 | 100 | 100 | 100 | 100 | 100 | 100
53 | afbraakwerken tramtunnel (deel 1) | 2011-03-04 08:00 | 2011-04-15 17:00 | 31d |  | 0 | 0 | 3.67 | 910.16 | 910.16 | 2011-04-26 08:00 | 29d | 851.44 | 0 | 0 | 0 | 0 | 851.44 | 0 | 100% | Finished | 910.16 | 910.16 | 100 | 93.5484 | 100 | 100 | 93.5484 | 100
54 | afbraakwerken tramtunnel (deel 2) | 2011-03-28 08:00 | 2011-05-11 17:00 | 33d |  | 0 | 0 | 3.67 | 968.88 | 968.88 | 2011-05-18 08:00 | 33d | 968.88 | 0 | 0 | 0 | 0 | 968.88 | 0 | 100% | Finished | 968.88 | 968.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | grondwerken (1ste niv) | 2011-05-03 08:00 | 2011-06-06 17:00 | 25d |  | 0 | 0 | 15.92 | 3184 | 3184 | 2012-12-10 08:00 | 1d | 127.36 | 0 | 0 | 0 | 0 | 127.36 | 0 | 100% | Finished | 3184 | 3184 | 100 | 4 | 100 | 100 | 4 | 100
56 | vermalling talud - 1ste niv | 2011-05-24 08:00 | 2011-06-10 17:00 | 14d |  | 0 | 0 | 15.92 | 1783.04 | 1783.04 | 2012-03-12 08:00 | 15d | 1910.4 | 0 | 0 | 0 | 0 | 1910.4 | 0 | 100% | Finished | 1783.04 | 1783.04 | 100 | 107.1429 | 100 | 100 | 107.1429 | 100
57 | grondwerken | 2011-06-01 08:00 | 2011-06-21 17:00 | 15d |  | 0 | 0 | 15.92 | 1910.4 | 1910.4 | 2011-06-07 08:00 | 25d | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 100% | Finished | 1910.4 | 1910.4 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
58 | Beschoeiing liftput | 2011-06-03 08:00 | 2011-06-21 17:00 | 13d |  | 0 | 0 | 15.92 | 1655.68 | 1655.68 | 2012-12-10 08:00 | 1d | 127.36 | 0 | 0 | 0 | 0 | 127.36 | 0 | 100% | Finished | 1655.68 | 1655.68 | 100 | 7.6923 | 100 | 100 | 7.6923 | 100
59 | diepe fundering 1 | 2011-06-07 08:00 | 2011-07-01 17:00 | 19d |  | 0 | 0 | 15.92 | 2419.84 | 2419.84 | 2011-10-12 08:00 | 5d | 636.8 | 0 | 0 | 0 | 0 | 636.8 | 0 | 100% | Finished | 2419.84 | 2419.84 | 100 | 26.3158 | 100 | 100 | 26.3158 | 100
60 | diepe fundering 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-29 08:00 | 6d | 0.48 | 0 | 0 | 0 | 0 | 0.48 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 600 | 100
61 | riolering en aarding | 2011-06-20 08:00 | 2011-09-05 17:00 | 56d |  | 0 | 0 | 15.92 | 7132.16 | 7132.16 | 2011-12-08 08:00 | 41d | 5221.76 | 0 | 0 | 0 | 0 | 5221.76 | 0 | 100% | Finished | 7132.16 | 7132.16 | 100 | 73.2143 | 100 | 100 | 73.2143 | 100
62 | funderingszolen | 2011-06-21 08:00 | 2011-10-18 17:00 | 86d |  | 0 | 0 | 15.92 | 10952.9601 | 10952.9601 | 2011-11-03 08:00 | 78d | 9934.08 | 0 | 0 | 0 | 0 | 9934.08 | 0 | 100% | Finished | 10952.9601 | 10952.9601 | 100 | 90.6977 | 100 | 100 | 90.6977 | 100
63 | Bufferbekken onder | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 5d | 0.4 | 0 | 0 | 636.8 | 0 | 637.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 796500.0025 | 100
64 | Bufferbekken midden | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-04 08:00 | 25d | 2 | 0 | 0 | 3184 | 0 | 3186 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 3982500.089 | 100
65 | verplatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-30 08:00 | 8d | 0.64 | 0 | 0 | 1018.88 | 0 | 1019.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 1274400.0346 | 100
66 | funderingszolen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-19 08:00 | 24d | 1.92 | 0 | 0 | 3056.6399 | 0 | 3058.5599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2400 | 100 | 100 | 3823199.9511 | 100
67 | bufferbekken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-08-21 08:00 | 30d | 2.4 | 0 | 0 | 3820.8 | 0 | 3823.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3000 | 100 | 100 | 4779000.1678 | 100
68 | beschoeiing achter lift | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-18 08:00 | 18d | 1.44 | 0 | 0 | 2292.48 | 0 | 2293.92 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1800 | 100 | 100 | 2867400.0396 | 100
87 | Superstructuur-zone B | 2011-01-10 08:00 | 2011-09-29 17:00 | 189d |  |  | 0 |  |  | 73415.839 |  | 301d | [5 empty] | 59682.1594 |  | 100% |  | 73415.839 | 73415.839
70 | uitvoering kolommen | 2011-05-12 08:00 | 2011-07-08 17:00 | 42d |  | 0 | 0 | 28.15 | 9458.3999 | 9458.3999 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 100% | Finished | 9458.3999 | 9458.3999 | 100 | 2.381 | 100 | 100 | 2.381 | 100
71 | uitvoering structuur overspanning 1 | 2011-05-19 08:00 | 2011-07-04 17:00 | 33d |  | 0 | 0 | 28.15 | 7431.5999 | 7431.5999 | 2011-11-28 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 7431.5999 | 7431.5999 | 100 | 193.9394 | 100 | 100 | 193.9394 | 100
72 | structurele afwerking overspanning 1 | 2011-06-14 08:00 | 2011-08-16 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-02-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 10359.1999 | 10359.1999 | 100 | 43.4783 | 100 | 100 | 43.4783 | 100
73 | uitvoering structuur overspanning 2 | 2011-06-14 08:00 | 2011-08-05 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 100% | Finished | 8782.7999 | 8782.7999 | 100 | 56.4103 | 100 | 100 | 56.4103 | 100
74 | structurele afwerking overspanning 2 | 2011-06-30 08:00 | 2011-09-01 17:00 | 46d |  | 0 | 0 | 28.15 | 10359.1999 | 10359.1999 | 2012-04-04 08:00 | 24d | 5404.7999 | 0 | 0 | 0 | 0 | 5404.7999 | 0 | 100% | Finished | 10359.1999 | 10359.1999 | 100 | 52.1739 | 100 | 100 | 52.1739 | 100
75 | uitvoering structuur overspanning 3 | 2011-06-30 08:00 | 2011-08-22 17:00 | 38d |  | 0 | 0 | 28.15 | 8557.5999 | 8557.5999 | 2012-03-27 08:00 | 22d | 4954.3999 | 0 | 0 | 0 | 0 | 4954.3999 | 0 | 100% | Finished | 8557.5999 | 8557.5999 | 100 | 57.8947 | 100 | 100 | 57.8947 | 100
76 | structurele afwerking overspanning 3 | 2011-08-04 08:00 | 2011-09-15 17:00 | 31d |  | 0 | 0 | 28.15 | 6981.1999 | 6981.1999 | 2012-04-24 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6981.1999 | 6981.1999 | 100 | 64.5161 | 100 | 100 | 64.5161 | 100
77 | uitvoering structuur overspanning 4 | 2011-08-04 08:00 | 2011-09-01 17:00 | 21d |  | 0 | 0 | 28.15 | 4729.1999 | 4729.1999 | 2012-05-02 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4729.1999 | 4729.1999 | 100 | 95.2381 | 100 | 100 | 95.2381 | 100
78 | structurele afwerking overspanning 4 | 2011-08-19 08:00 | 2011-09-29 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-05-31 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6755.9999 | 6755.9999 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
79 | plaatsing kolommen staal-overspanning 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
80 | plaatsing kolommen staal-overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-17 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
81 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
82 | opstorten vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-10-21 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
83 | ontkisten 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
84 | ontkisten 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
85 | ontkisten 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-20 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
86 | ontkisten 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-31 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
115 | Superstructuur-zone C | 2011-01-10 08:00 | 2012-01-17 17:00 | 267d |  |  | 0 |  |  | 91207.1188 |  | 206d | [5 empty] | 71621.4393 |  | 100% |  | 91207.1188 | 91207.1188
88 | uitvoering kolommen | 2011-09-01 08:00 | 2011-11-29 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 1.5625 | 100 | 100 | 1.5625 | 100
89 | uitvoering structuur groot overspanning 1 | 2011-09-15 08:00 | 2011-12-16 17:00 | 67d |  | 0 | 0 | 28.15 | 15088.3998 | 15088.3998 | 2012-03-29 08:00 | 34d | 7656.7999 | 0 | 0 | 0 | 0 | 7656.7999 | 0 | 100% | Finished | 15088.3998 | 15088.3998 | 100 | 50.7463 | 100 | 100 | 50.7463 | 100
90 | uitvoering structuur groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 28.15 | 225.2 | 225.2 | 2012-04-25 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 225.2 | 225.2 | 100 | 1500 | 100 | 100 | 1500 | 100
91 | structurele afwerking groot overspanning 1 | 2011-10-20 08:00 | 2012-01-17 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-06-14 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 23.4375 | 100 | 100 | 23.4375 | 100
92 | structurele afwerking groot overspanning 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
93 | uitvoering structuur overspanning 5 | 2011-08-19 08:00 | 2011-09-15 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-23 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 100 | 100 | 100 | 100 | 100
94 | structurele afwerking overspanning 5 | 2011-09-02 08:00 | 2011-10-13 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-06-15 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 6755.9999 | 6755.9999 | 100 | 50 | 100 | 100 | 50 | 100
95 | uitvoering structuur overspanning 6 | 2011-09-02 08:00 | 2011-09-29 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-20 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 75 | 100 | 100 | 75 | 100
96 | structurele afwerking overspanning 6 | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 0 | 28.15 | 6755.9999 | 6755.9999 | 2012-07-09 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6755.9999 | 6755.9999 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
97 | uitvoering structuur overspanning 7 | 2011-09-16 08:00 | 2011-10-13 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-06-06 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 100 | 100 | 100 | 100 | 100
98 | structurele afwerking overspanning 7 | 2011-09-30 08:00 | 2011-11-16 17:00 | 34d |  | 0 | 0 | 28.15 | 7656.7999 | 7656.7999 | 2012-06-28 08:00 | 25d | 5629.9999 | 0 | 0 | 0 | 0 | 5629.9999 | 0 | 100% | Finished | 7656.7999 | 7656.7999 | 100 | 73.5294 | 100 | 100 | 73.5294 | 100
99 | uitvoering structuur overspanning 8 | 2011-09-30 08:00 | 2011-10-27 17:00 | 20d |  | 0 | 0 | 28.15 | 4503.9999 | 4503.9999 | 2012-05-09 08:00 | 25d | 5629.9999 | 0 | 0 | 0 | 0 | 5629.9999 | 0 | 100% | Finished | 4503.9999 | 4503.9999 | 100 | 125 | 100 | 100 | 125 | 100
100 | structurele afwerking overspanning 8 | 2011-10-17 08:00 | 2011-12-02 17:00 | 35d |  | 0 | 0 | 28.15 | 7881.9999 | 7881.9999 | 2012-06-08 08:00 | 15d | 3378 | 0 | 0 | 0 | 0 | 3378 | 0 | 100% | Finished | 7881.9999 | 7881.9999 | 100 | 42.8571 | 100 | 100 | 42.8571 | 100
101 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
102 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-26 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
103 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-02-27 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
104 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
105 | opstorten vloerplaat na aanspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
106 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-28 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
107 | opstorten vloerplaat na plaatsing kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-08 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
108 | dichtstellen openingen vloerplaat boven -1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-18 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
109 | verplaatsing doorgang reizigers | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-24 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 2816000.0629 | 100
111 | ontkisten 5 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-15 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
112 | ontkisten 7 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-07-06 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
113 | ontkisten 6 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-14 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
114 | ontkisten 8 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-06-27 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
135 | Superstructuur-zone D | 2011-01-10 08:00 | 2012-02-14 17:00 | 287d |  |  | 0 |  |  | 65083.7591 |  | 196d | [5 empty] | 49099.7595 |  | 100% |  | 65083.7591 | 65083.7591
116 | uitvoering kolommen | 2011-08-31 08:00 | 2011-11-28 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 1.5625 | 100 | 100 | 1.5625 | 100
117 | uitvoering structuur overspanning 9 | 2011-10-17 08:00 | 2011-11-23 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-05-25 08:00 | 20d | 4503.9999 | 0 | 0 | 0 | 0 | 4503.9999 | 0 | 100% | Finished | 6305.5999 | 6305.5999 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
118 | structurele afwerking overspanning 9 | 2011-11-04 08:00 | 2011-12-23 17:00 | 36d |  | 0 | 0 | 28.15 | 8107.1999 | 8107.1999 | 2012-06-27 08:00 | 30d | 6755.9999 | 0 | 0 | 0 | 0 | 6755.9999 | 0 | 100% | Finished | 8107.1999 | 8107.1999 | 100 | 83.3333 | 100 | 100 | 83.3333 | 100
119 | uitvoering structuur overspanning 10 | 2011-11-03 08:00 | 2011-12-12 17:00 | 28d |  | 0 | 0 | 28.15 | 6305.5999 | 6305.5999 | 2012-06-04 08:00 | 19d | 4278.7999 | 0 | 0 | 0 | 0 | 4278.7999 | 0 | 100% | Finished | 6305.5999 | 6305.5999 | 100 | 67.8571 | 100 | 100 | 67.8571 | 100
120 | structurele afwerking overspanning 10 | 2011-12-05 08:00 | 2012-02-07 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 2012-08-01 08:00 | 21d | 4729.1999 | 0 | 0 | 0 | 0 | 4729.1999 | 0 | 100% | Finished | 10584.3999 | 10584.3999 | 100 | 44.6809 | 100 | 100 | 44.6809 | 100
121 | uitvoering structuur overspanning 11 | 2011-11-22 08:00 | 2012-01-13 17:00 | 39d |  | 0 | 0 | 28.15 | 8782.7999 | 8782.7999 | 2012-06-11 08:00 | 19d | 4278.7999 | 0 | 0 | 0 | 0 | 4278.7999 | 0 | 100% | Finished | 8782.7999 | 8782.7999 | 100 | 48.7179 | 100 | 100 | 48.7179 | 100
122 | structurele afwerking overspanning 11 | 2011-12-12 08:00 | 2012-02-14 17:00 | 47d |  | 0 | 0 | 28.15 | 10584.3999 | 10584.3999 | 2012-07-11 08:00 | 31d | 6981.1999 | 0 | 0 | 0 | 0 | 6981.1999 | 0 | 100% | Finished | 10584.3999 | 10584.3999 | 100 | 65.9574 | 100 | 100 | 65.9574 | 100
123 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-30 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
124 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-12 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
125 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-11 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
126 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-14 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
127 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
128 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-23 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
129 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
130 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-04 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
131 | kolommen staal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-19 08:00 | 5d | 0.4 | 0 | 0 | 1126 | 0 | 1126.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1408000.0315 | 100
132 | opstorten vloerplaat na naspanning | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-17 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
133 | Plaatsing HS kabel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
134 | montage bekisting | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-02 08:00 | 15d | 1.2 | 0 | 0 | 3378 | 0 | 3379.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4224000.0944 | 100
150 | KOK A | 2011-01-10 08:00 | 2012-08-09 17:00 | 414d |  |  | 0 |  |  | 50117.5188 |  | 149d | [5 empty] | 12470.96 |  | 100% |  | 50117.5188 | 50117.5188
136 | Plaatsing staalstructuur | 2011-11-10 08:00 | 2012-01-20 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 | 2012-10-01 08:00 | 10d | 1272 | 0 | 0 | 0 | 0 | 1272 | 0 | 100% | Finished | 6614.3998 | 6614.3998 | 100 | 19.2308 | 100 | 100 | 19.2308 | 100
137 | dackdichting-beplanting | 2012-01-13 08:00 | 2012-03-26 17:00 | 52d |  | 0 | 0 | 15.9 | 6614.3998 | 6614.3998 | 2012-10-17 08:00 | 5d | 636 | 0 | 0 | 0 | 0 | 636 | 0 | 100% | Finished | 6614.3998 | 6614.3998 | 100 | 9.6154 | 100 | 100 | 9.6154 | 100
138 | dakdichting-waterdichting | 2012-01-30 08:00 | 2012-05-16 17:00 | 78d |  | 0 | 0 | 15.9 | 9921.5998 | 9921.5998 | 2012-10-25 08:00 | 4d | 508.8 | 0 | 0 | 0 | 0 | 508.8 | 0 | 100% | Finished | 9921.5998 | 9921.5998 | 100 | 5.1282 | 100 | 100 | 5.1282 | 100
139 | afwerking perron | 2012-02-20 08:00 | 2012-08-09 17:00 | 124d |  | 0 | 0 | 15.9 | 15772.7996 | 15772.7996 | 2012-12-10 08:00 | 1d | 127.2 | 0 | 0 | 0 | 0 | 127.2 | 0 | 100% | Finished | 15772.7996 | 15772.7996 | 100 | 0.80645 | 100 | 100 | 0.80645 | 100
140 | plaatsing lift | 2012-02-23 08:00 | 2012-06-25 17:00 | 88d |  | 0 | 0 | 15.9 | 11193.5997 | 11193.5997 | 2012-08-13 08:00 | 11d | 1399.2 | 0 | 0 | 0 | 0 | 1399.2 | 0 | 100% | Finished | 11193.5997 | 11193.5997 | 100 | 12.5 | 100 | 100 | 12.5 | 100
141 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-22 08:00 | 5d | 0.4 | 0 | 0 | 636 | 0 | 636.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 795500.0178 | 100
142 | voorbereiding perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 38d | 3.04 | 0 | 0 | 4833.6001 | 0 | 4836.6401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3800 | 100 | 100 | 6045800.2571 | 100
143 | integratie speciale technieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-17 08:00 | 5d | 0.4 | 0 | 0 | 636 | 0 | 636.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 795500.0178 | 100
144 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-26 08:00 | 3d | 0.24 | 0 | 0 | 381.6 | 0 | 381.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 477300.0183 | 100
145 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-31 08:00 | 5d | 0.4 | 0 | 0 | 636 | 0 | 636.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 795500.0178 | 100
146 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 1d | 0.08 | 0 | 0 | 127.2 | 0 | 127.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 159099.9997 | 100
147 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-26 08:00 | 3d | 0.24 | 0 | 0 | 381.6 | 0 | 381.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 477300.0183 | 100
148 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-04 08:00 | 3d | 0.24 | 0 | 0 | 381.6 | 0 | 381.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 477300.0183 | 100
149 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-25 08:00 | 4d | 0.32 | 0 | 0 | 508.8 | 0 | 509.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 636399.999 | 100
165 | KOK B | 2011-01-10 08:00 | 2012-08-03 17:00 | 410d |  |  | 0 |  |  | 52740.3985 |  | 56d | [5 empty] | 6443.0398 |  | 100% |  | 52740.3985 | 52740.3985
151 | voorbereiding perron | 2011-09-14 08:00 | 2011-12-15 17:00 | 67d |  | 0 | 0 | 15.19 | 8141.8398 | 8141.8398 | 2012-12-10 08:00 | 1d | 121.52 | 0 | 0 | 0 | 0 | 121.52 | 0 | 100% | Finished | 8141.8398 | 8141.8398 | 100 | 1.4925 | 100 | 100 | 1.4925 | 100
152 | plaatsing staalstructuur | 2011-10-05 08:00 | 2012-01-17 17:00 | 75d |  | 0 | 0 | 15.19 | 9113.9997 | 9113.9997 | 2012-10-01 08:00 | 10d | 1215.2 | 0 | 0 | 0 | 0 | 1215.2 | 0 | 100% | Finished | 9113.9997 | 9113.9997 | 100 | 13.3333 | 100 | 100 | 13.3333 | 100
153 | dakdichting - beplanting | 2011-11-18 08:00 | 2012-01-31 17:00 | 53d |  | 0 | 0 | 15.19 | 6440.5598 | 6440.5598 | 2012-10-15 08:00 | 5d | 607.6 | 0 | 0 | 0 | 0 | 607.6 | 0 | 100% | Finished | 6440.5598 | 6440.5598 | 100 | 9.434 | 100 | 100 | 9.434 | 100
154 | dakdichting - waterdichting | 2011-12-05 08:00 | 2012-03-15 17:00 | 74d |  | 0 | 0 | 15.19 | 8992.4798 | 8992.4798 | 2012-10-23 08:00 | 5d | 607.6 | 0 | 0 | 0 | 0 | 607.6 | 0 | 100% | Finished | 8992.4798 | 8992.4798 | 100 | 6.7568 | 100 | 100 | 6.7568 | 100
155 | afwerking perron | 2011-12-19 08:00 | 2012-08-03 17:00 | 165d |  | 0 | 0 | 15.19 | 20050.7994 | 20050.7994 | 2012-12-10 08:00 | 1d | 121.52 | 0 | 0 | 0 | 0 | 121.52 | 0 | 100% | Finished | 20050.7994 | 20050.7994 | 100 | 0.60606 | 100 | 100 | 0.60606 | 100
156 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-19 08:00 | 4d | 0.32 | 0 | 0 | 486.08 | 0 | 486.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 607999.9968 | 100
157 | integrateie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-17 08:00 | 4d | 0.32 | 0 | 0 | 486.08 | 0 | 486.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 607999.9968 | 100
158 | beglazing gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-15 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 456000.0071 | 100
159 | kolommen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 456000.0071 | 100
160 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 5d | 0.4 | 0 | 0 | 607.6 | 0 | 608 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 759999.9865 | 100
161 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 1d | 0.08 | 0 | 0 | 121.52 | 0 | 121.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 151999.9992 | 100
162 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 456000.0071 | 100
163 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-04 08:00 | 3d | 0.24 | 0 | 0 | 364.56 | 0 | 364.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 456000.0071 | 100
164 | bekleding onderkant staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-22 08:00 | 5d | 0.4 | 0 | 0 | 607.6 | 0 | 608 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 759999.9865 | 100
199 | GOK | 2011-01-10 08:00 | 2012-08-14 17:00 | 417d |  |  | 0 |  |  | 167143.036 |  | 171d | [5 empty] | 67685.7998 |  | 100% |  | 167143.036 | 167143.036
166 | plaatsing staalstructuur | 2011-08-05 08:00 | 2012-01-16 17:00 | 117d |  | 0 | 0 | 31.8 | 29764.7993 | 29764.7993 | 2012-08-16 08:00 | 28d | 7123.1998 | 0 | 0 | 0 | 0 | 7123.1998 | 0 | 100% | Finished | 29764.7993 | 29764.7993 | 100 | 23.9316 | 100 | 100 | 23.9316 | 100
167 | dakdichting - beplanting | 2011-09-13 08:00 | 2012-02-24 17:00 | 119d |  | 0 | 0 | 31.8 | 30273.5993 | 30273.5993 | 2012-09-25 08:00 | 20d | 5087.9999 | 0 | 0 | 0 | 0 | 5087.9999 | 0 | 100% | Finished | 30273.5993 | 30273.5993 | 100 | 16.8067 | 100 | 100 | 16.8067 | 100
168 | plaatsing beglazing | 2011-10-17 08:00 | 2012-03-23 17:00 | 115d |  | 0 | 0 | 31.8 | 29255.9993 | 29255.9993 | 2012-11-16 08:00 | 7d | 1780.8 | 0 | 0 | 0 | 0 | 1780.8 | 0 | 100% | Finished | 29255.9993 | 29255.9993 | 100 | 6.087 | 100 | 100 | 6.087 | 100
169 | dakdichting - waterdichting | 2011-11-02 08:00 | 2012-04-06 17:00 | 113d |  | 0 | 0 | 31.8 | 28747.1993 | 28747.1993 | 2012-10-16 08:00 | 10d | 2543.9999 | 0 | 0 | 0 | 0 | 2543.9999 | 0 | 100% | Finished | 28747.1993 | 28747.1993 | 100 | 8.8496 | 100 | 100 | 8.8496 | 100
170 | afwerking perron | 2011-11-18 08:00 | 2012-08-14 17:00 | 193d |  | 0 | 0 | 31.8 | 49099.1988 | 49099.1988 | 2012-12-10 08:00 | 1d | 254.4 | 0 | 0 | 0 | 0 | 254.4 | 0 | 100% | Finished | 49099.1988 | 49099.1988 | 100 | 0.51813 | 100 | 100 | 0.51813 | 100
171 | diepe fundering kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-16 08:00 | 12d | 0.96 | 0 | 0 | 3052.8 | 0 | 3053.76 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3817200.1463 | 100
172 | funderingszolen kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-23 08:00 | 16d | 1.28 | 0 | 0 | 4070.3999 | 0 | 4071.6799 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1600 | 100 | 100 | 5089599.9917 | 100
173 | kolommen gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-08-13 08:00 | 2d | 0.16 | 0 | 0 | 508.8 | 0 | 508.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 200 | 100 | 100 | 636199.999 | 100
174 | ontrokingskoker langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 3181000.0711 | 100
175 | slibvanger langs gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-23 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
176 | voorlopige aansluiting riolering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-14 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 3181000.0711 | 100
177 | regenwater afvoer | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-02 08:00 | 15d | 1.2 | 0 | 0 | 3816 | 0 | 3817.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4771500.1066 | 100
178 | integratie speciale technieken in structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-02 08:00 | 15d | 1.2 | 0 | 0 | 3816 | 0 | 3817.2 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1500 | 100 | 100 | 4771500.1066 | 100
179 | Gevelbekleding metaal | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-12-10 08:00 | 1d | 0.08 | 0 | 0 | 254.2 | 0 | 254.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 317850.0033 | 100
180 | integratie elec in gevel | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-11-21 08:00 | 14d | 1.12 | 0 | 0 | 3561.6001 | 0 | 3562.7201 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1400 | 100 | 100 | 4453400.2216 | 100
181 | beplanting onderkant dakstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-12-10 08:00 | 1d | 0.08 | 0 | 0 | 254.2 | 0 | 254.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 317850.0033 | 100
182 | bekledingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-11-05 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 3181000.0711 | 100
183 | onderhoud en veiligheidsuitrusting - structuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-09 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 3181000.0711 | 100
184 | elektrische voorzieningen op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 7d | 0.56 | 0 | 0 | 1780.8 | 0 | 1781.36 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 2226700.1108 | 100
185 | extractoren en wateraanvoer op dak | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 7d | 0.56 | 0 | 0 | 1780.8 | 0 | 1781.36 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 2226700.1108 | 100
186 | structuur levenslijn | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-30 08:00 | 7d | 0.56 | 0 | 0 | 1780.8 | 0 | 1781.36 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 2226700.1108 | 100
187 | Onderhoud en veiligheidsuitrusting - toebehoren | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-11-06 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
188 | voorlopige trap toegang perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-29 08:00 | 10d | 0.8 | 0 | 0 | 2544 | 0 | 2544.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 3181000.0711 | 100
189 | start inrichting bovenleiding spoor | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 1d | 0.08 | 0 | 0 | 254.2 | 0 | 254.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 317850.0033 | 100
190 | ophangconstructie voor bovenleiding | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-24 08:00 | 3d | 0.24 | 0 | 0 | 763.2 | 0 | 763.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 954300.0366 | 100
191 | Herstellingen staalstructuur 1 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-05 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
192 | herstellingen staalstructuur 2 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-12 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
193 | Herstellingen staalstructuur 3 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-19 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
194 | herstellingen staalstructuur 4 | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-09-26 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
195 | herstellingen staalstructuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-03 08:00 | 5d | 0.4 | 0 | 0 | 1272 | 0 | 1272.4 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 500 | 100 | 100 | 1590500.0355 | 100
196 | Bekabeling in portieken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-01 08:00 | 8d | 0.64 | 0 | 0 | 2035.2 | 0 | 2035.84 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2544799.9958 | 100
197 | ophangconstructie voor toestellen perron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-03 08:00 | 3d | 0.24 | 0 | 0 | 763.2 | 0 | 763.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 954300.0366 | 100
198 | Paaltjes bovendaks | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-10-25 08:00 | 3d | 0.24 | 0 | 0 | 763.2 | 0 | 763.44 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 300 | 100 | 100 | 954300.0366 | 100
200 | Technieken | 2011-09-08 08:00 | 2012-01-17 17:00 | 94d |  | 0 | 0 | 235.79 | 177314.075 | 177314.075 | 2012-08-17 08:00 | 73d | 137701.3561 | 0 | 0 | 0 | 0 | 137701.3561 | 0 | 100% | Finished | 177314.075 | 177314.075 | 100 | 77.6596 | 100 | 100 | 77.6596 | 100
227 | Superstructuur-zone A | 2011-01-10 08:00 | 2012-03-20 17:00 | 312d |  |  | 0 |  |  | 129941.9982 |  | 463d | [5 empty] | 154065.7585 |  | 100% |  | 129941.9982 | 129941.9982
201 | vloerplaat en keermuur reservelokaal 1 | 2011-01-31 08:00 | 2011-05-04 17:00 | 68d |  | 0 | 0 | 28.15 | 15313.5998 | 15313.5998 | 2012-12-10 08:00 | 1d | 225.2 | 0 | 0 | 0 | 0 | 225.2 | 0 | 100% | Finished | 15313.5998 | 15313.5998 | 100 | 1.4706 | 100 | 100 | 1.4706 | 100
202 | vloerplaat en keermuur reservelokaal 2 | 2011-03-21 08:00 | 2011-06-20 17:00 | 66d |  | 0 | 0 | 28.15 | 14863.1998 | 14863.1998 | 2011-08-29 08:00 | 77d | 17340.3998 | 0 | 0 | 0 | 0 | 17340.3998 | 0 | 100% | Finished | 14863.1998 | 14863.1998 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
203 | vloerplaat en keermuur reservelokaal 3 | 2011-05-05 08:00 | 2011-08-23 17:00 | 79d |  | 0 | 0 | 28.15 | 17790.7998 | 17790.7998 | 2011-11-28 08:00 | 51d | 11485.1998 | 0 | 0 | 0 | 0 | 11485.1998 | 0 | 100% | Finished | 17790.7998 | 17790.7998 | 100 | 64.557 | 100 | 100 | 64.557 | 100
204 | vloerplaat en keermuur reservelokaal 4 | 2011-06-21 08:00 | 2011-10-04 17:00 | 76d |  | 0 | 0 | 28.15 | 17115.1998 | 17115.1998 | 2011-12-12 08:00 | 64d | 14412.7998 | 0 | 0 | 0 | 0 | 14412.7998 | 0 | 100% | Finished | 17115.1998 | 17115.1998 | 100 | 84.2105 | 100 | 100 | 84.2105 | 100
205 | vloerplaat en keermuur reservelokaal 5 | 2011-08-24 08:00 | 2011-11-21 17:00 | 64d |  | 0 | 0 | 28.15 | 14412.7998 | 14412.7998 | 2012-02-06 08:00 | 50d | 11259.9998 | 0 | 0 | 0 | 0 | 11259.9998 | 0 | 100% | Finished | 14412.7998 | 14412.7998 | 100 | 78.125 | 100 | 100 | 78.125 | 100
206 | Dakplaat reservelokaal (incl. technische koker) | 2011-05-12 08:00 | 2012-03-20 17:00 | 224d |  | 0 | 0 | 28.15 | 50444.7993 | 50444.7993 | 2011-10-27 08:00 | 101d | 22745.1997 | 0 | 0 | 0 | 0 | 22745.1997 | 0 | 100% | Finished | 50444.7993 | 50444.7993 | 100 | 45.0893 | 100 | 100 | 45.0893 | 100
207 | Beschoeiing onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-06 08:00 | 9d | 0.72 | 0 | 0 | 2027.52 | 0 | 2028.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2535300.0811 | 100
208 | Verankering keermuur onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-08 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
209 | Keerwand onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-07-05 08:00 | 11d | 0.88 | 0 | 0 | 2477.2 | 0 | 2478.08 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1100 | 100 | 100 | 3097600.0082 | 100
210 | Vloerplaat onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-02 08:00 | 25d | 2 | 0 | 0 | 5630 | 0 | 5632 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2500 | 100 | 100 | 7040000.1573 | 100
211 | Wanden onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-12 08:00 | 22d | 1.76 | 0 | 0 | 4954.3999 | 0 | 4956.1599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2200 | 100 | 100 | 6195200.0164 | 100
212 | Vloerplaat +x onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-26 08:00 | 20d | 1.6 | 0 | 0 | 4504 | 0 | 4505.6 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 2000 | 100 | 100 | 5632000.1258 | 100
213 | Structuur spoor boven onderstation | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-05-16 08:00 | 38d | 3.04 | 0 | 0 | 8557.5996 | 0 | 8560.6396 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 3800 | 100 | 100 | 10700799.7508 | 100
214 | profielen voor beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 1d | 0.08 | 0 | 0 | 225.2 | 0 | 225.28 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 100 | 100 | 100 | 281600.0025 | 100
215 | Afbraak en grondwerk (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-10 08:00 | 7d | 0.56 | 0 | 0 | 1576.4 | 0 | 1576.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 700 | 100 | 100 | 1971200.0746 | 100
216 | Verankering beschoeiing | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-11 08:00 | 13d | 1.04 | 0 | 0 | 2702.3999 | 0 | 2703.4399 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1300 | 100 | 100 | 3379299.9534 | 100
217 | Vloerplaat | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-05-12 08:00 | 12d | 0.96 | 0 | 0 | 0 | 0 | 0.96 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 1200 | 100
218 | Keerwand (fase 1) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-06-21 08:00 | 9d | 0.72 | 0 | 0 | 2026.8 | 0 | 2027.52 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 900 | 100 | 100 | 2534400.1177 | 100
219 | Verwijderen verdeelprofielen + keerwand (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-08-22 08:00 | 18d | 1.44 | 0 | 0 | 4053.6001 | 0 | 4055.0401 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1800 | 100 | 100 | 5068800.2353 | 100
220 | Vloerplaat & keermuur | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 49d | 3.92 | 0 | 0 | 11034.7998 | 0 | 11038.7198 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 4900 | 100 | 100 | 13798400.0642 | 100
221 | Voorbereidende afbraakwerken | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-03 08:00 | 4d | 0.32 | 0 | 0 | 900.8 | 0 | 901.12 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 400 | 100 | 100 | 1126400.0099 | 100
222 | Beschoeiing fase 1 tem niv verankering | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-03-04 08:00 | 8d | 0.64 | 0 | 0 | 1801.6 | 0 | 1802.24 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 800 | 100 | 100 | 2252800.0198 | 100
223 | Beschoeiing fase (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-14 08:00 | 12d | 0.96 | 0 | 0 | 2702.3999 | 0 | 2703.3599 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1200 | 100 | 100 | 3379199.9534 | 100
224 | Afbraakwerken (fase 2) | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2011-04-08 08:00 | 6d | 0.48 | 0 | 0 | 1351.2 | 0 | 1351.68 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 600 | 100 | 100 | 1689599.9767 | 100
225 | Dakplaat reservelokaal dienstperron | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-03-09 08:00 | 72d | 5.76 | 0 | 0 | 16214.4004 | 0 | 16220.1604 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 7200 | 100 | 100 | 20275200.9413 | 100
226 | Beton kolommen | 2011-01-10 08:00 | 2011-01-10 17:00 | 1d |  | 0 | 0 | 0.01 | 0.08 | 0.08 | 2012-04-13 08:00 | 10d | 0.8 | 0 | 0 | 2252 | 0 | 2252.8 | 0 | 100% | Finished | 0.08 | 0.08 | 100 | 1000 | 100 | 100 | 2816000.0629 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
25/03, 2011 | 2011-01-10 08:00 | 2011-03-25 17:00 | 177181.1186 | 143541.3379 | 155665.9983 | 2011-03-14 15:00 | -33639.7806 | 81.01% | -12124.6604 | 92.21% | -9d 2h | 83.18% | 84.01% | 2012-08-31 12:00 | 2012-12-28 15:00 | 2013-02-28 10:00 | 2012-08-29 12:00 | 2012-12-28 15:00 | 2013-02-21 12:00 | 2012-08-28 10:00 | 2012-12-11 10:00 | 2013-01-31 17:00 | 1133441.6026 | 1216032.4248 | 1362589.2286 | 1331133.9379 | 1464535.7094 | 1430423.4509 | 1242425.4866 | 1237213.3923 | 0.83182 | 0.92211 | 0.81014 | 0.84008 | -9.25 | 0.92211 | 1 | 0.83182 | 1
10/06, 2011 | 2011-03-25 17:00 | 2011-06-10 17:00 | 300186.3979 | 204121.3443 | 280538.3171 | 2011-04-06 16:00 | -96065.0536 | 68% | -76416.9728 | 72.76% | -47d 1h | 57.16% | 88.89% | 2012-10-03 15:00 | 2013-05-16 10:00 | 2014-04-02 16:00 | 2012-10-03 10:00 | 2013-05-16 10:00 | 2014-02-04 14:00 | 2012-10-19 09:00 | 2013-10-25 12:00 | 2014-09-16 12:00 | 1197733.915 | 1541104.7237 | 1629391.0972 | 1885174.7509 | 2134361.5429 | 2485903.0047 | 1557825.1583 | 1597585.6176 | 0.57159 | 0.72761 | 0.67998 | 0.88892 | -47.125 | 0.72761 | 1 | 0.57159 | 1
26/08, 2011 | 2011-06-10 17:00 | 2011-08-26 17:00 | 442506.7167 | 218502.0301 | 316002.7971 | 2011-04-13 09:00 | -224004.6866 | 49.38% | -97500.7669 | 69.15% | -97d 7h | 40.68% | 90.85% | 2012-12-10 10:00 | 2014-04-04 12:00 | 2015-09-15 11:00 | 2012-12-10 12:00 | 2014-04-04 12:00 | 2015-06-03 15:00 | 2012-12-28 16:00 | 2014-12-12 17:00 | 2016-06-02 15:00 | 1218817.7092 | 1621675.0479 | 2144368.7047 | 2535212.637 | 2960228.7595 | 3525476.4862 | 1700855.4452 | 1738815.1726 | 0.40682 | 0.69146 | 0.49378 | 0.90845 | -97.875 | 0.69146 | 1 | 0.40682 | 1
11/11, 2011 | 2011-08-26 17:00 | 2011-11-11 17:00 | 717168.5516 | 262407.2912 | 386758.9176 | 2011-05-19 11:00 | -454761.2603 | 36.59% | -124351.6264 | 67.85% | -126d 5h | 42.44% | 91.18% | 2013-04-09 09:00 | 2015-05-22 14:00 | 2017-06-16 15:00 | 2013-02-26 12:00 | 2015-05-22 14:00 | 2017-01-23 12:00 | 2013-02-07 14:00 | 2014-10-15 12:00 | 2016-03-03 16:00 | 1245668.5686 | 1652695.4142 | 2734189.8424 | 2410428.2426 | 3846608.8303 | 3369420.5429 | 1781181.4247 | 1755171.7756 | 0.42443 | 0.67848 | 0.36589 | 0.91184 | -126.625 | 0.67848 | 1 | 0.42443 | 1
27/01, 2012 | 2011-11-11 17:00 | 2012-01-27 17:00 | 981713.8255 | 365123.8854 | 478487.0768 | 2011-07-15 14:00 | -616589.9402 | 37.19% | -113363.1915 | 76.31% | -140d 3h | 48.95% | 85.83% | 2013-07-02 10:00 | 2015-04-28 10:00 | 2016-08-26 10:00 | 2013-04-12 15:00 | 2015-04-28 10:00 | 2016-04-28 16:00 | 2013-02-27 11:00 | 2014-04-15 15:00 | 2014-12-22 16:00 | 1234680.1337 | 1469461.9755 | 2511674.1907 | 2023171.1299 | 3142935.4949 | 2502762.6358 | 1582662.0479 | 1545993.9117 | 0.48955 | 0.76308 | 0.37192 | 0.8583 | -140.375 | 0.76308 | 1 | 0.48955 | 1
13/04, 2012 | 2012-01-27 17:00 | 2012-04-13 17:00 | 1069364.9435 | 459860.5981 | 570971.7963 | 2011-09-05 15:00 | -609504.3454 | 43% | -111111.1982 | 80.54% | -159d 2h | 51.74% | 85.64% | 2013-06-27 14:00 | 2014-09-26 15:00 | 2015-08-20 17:00 | 2013-05-06 09:00 | 2014-09-26 15:00 | 2015-05-01 10:00 | 2013-03-26 10:00 | 2014-02-10 16:00 | 2014-07-21 16:00 | 1232428.1404 | 1392248.7627 | 2109129.7271 | 1849335.4482 | 2480778.3775 | 2158212.7855 | 1476671.6954 | 1455502.6373 | 0.51742 | 0.8054 | 0.43003 | 0.85643 | -159.25 | 0.8054 | 1 | 0.51742 | 1
29/06, 2012 | 2012-04-13 17:00 | 2012-06-29 17:00 | 1106449.3426 | 564213.6759 | 714927.8758 | 2011-10-04 10:00 | -542235.6667 | 50.99% | -150714.1999 | 78.92% | -193d 6h | 49.68% | 82.97% | 2013-05-23 14:00 | 2014-02-26 15:00 | 2014-12-30 10:00 | 2013-05-06 14:00 | 2014-02-26 15:00 | 2014-08-07 11:00 | 2013-05-13 15:00 | 2014-03-28 12:00 | 2014-09-15 16:00 | 1272031.1421 | 1420845.9912 | 1807433.3734 | 1836416.804 | 2099266.2355 | 2135991.7943 | 1474609.241 | 1477349.4762 | 0.49675 | 0.78919 | 0.50993 | 0.8297 | -193.75 | 0.78919 | 1 | 0.49675 | 1
14/09, 2012 | 2012-06-29 17:00 | 2012-09-14 17:00 | 1121316.9422 | 701153.4401 | 802496.7537 | 2011-11-09 09:00 | -420163.5022 | 62.53% | -101343.3136 | 87.37% | -222d 7h | 49.35% | 84.55% | 2013-03-21 10:00 | 2013-07-30 16:00 | 2013-12-12 10:00 | 2013-05-03 16:00 | 2013-09-19 14:00 | 2013-11-12 15:00 | 2013-06-21 16:00 | 2014-04-04 17:00 | 2014-06-26 14:00 | 1222660.2559 | 1283389.8468 | 1474441.6185 | 1653950.7132 | 1571563.1832 | 1777018.1628 | 1312384.789 | 1329238.4463 | 0.49347 | 0.87371 | 0.62529 | 0.84553 | -222.875 | 0.87371 | 1 | 0.49347 | 1
Actual Schedule | 2012-09-14 17:00 | 2012-12-10 17:00 | 1121316.9422 | 1121316.9422 | 967988.7905 | 2012-08-14 17:00 | 0 | 100% | 153328.1517 | 115.8% | -84d | 83.23% | 100% | 2012-08-14 17:00 | 2012-08-14 17:00 | 2012-05-25 17:00 | 2012-12-10 17:00 | 2012-12-10 17:00 | 2012-12-10 17:00 | 2012-12-10 17:00 | 2012-12-10 17:00 | 2012-12-10 17:00 | 967988.7905 | 967988.7905 | 967988.7905 | 967988.7905 | 967988.7905 | 967988.7905 | 967988.7905 | 967988.7905 | 0.83234 | 1.1584 | 1 | 1 | -84 | 1.1584 | 1 | 0.83234 | 1