## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building (6) | 1 |  |  | 2013-01-14 08:00 | 2013-06-28 17:00 | 120d |  |  | 0 |  |  | 2524765.1855 | 165.375
1 | Dakwerken | 1.1 |  | FS3;FS2 | 2013-01-14 08:00 | 2013-01-18 17:00 | 5d |  | 0 | 0 | 2578.95 | 103157.998 | 103157.998 | 4.375
2 | Sanitair | 1.2 | 1FS | FS4 | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 4.375
3 | Dakwerken | 1.3 | 1FS | FS5;FS7 | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 3546.05 | 141842.002 | 141842.002 | 4.375
4 | Elektriciteit | 1.4 | 2FS | FS6 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 4.375
5 | Ventilatie | 1.5 | 3FS |  | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 10000 | 400000 | 400000 | 4.375
6 | Plakwerken | 1.6 | 4FS | FS8-1w | 2013-02-04 08:00 | 2013-02-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 18.375
7 | Sanitair | 1.7 | 3FS | FS10 | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 4.375
8 | Plakwerken | 1.8 | 6FS-1w | FS9-7w;FS24-2w | 2013-02-18 08:00 | 2013-04-05 17:00 | 35d |  | 0 | 0 | 421.05 | 117893.9966 | 117893.9966 | 46.375
9 | Isolatie zolder | 1.9 | 8FS-7w |  | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 4.375
10 | Sanitair | 1.10 | 7FS | FS11;FS12 | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 4.375
11 | Sanitair | 1.11 | 10FS | FS14 | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 4.375
12 | Elektriciteit | 1.12 | 10FS | FS15 | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 4.375
13 | Sanitair | 1.13 |  | FS16 | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 833.33 | 33333.2007 | 33333.2007 | 4.375
14 | Elektriciteit | 1.14 | 11FS | FS17 | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 4.375
15 | Plakwerken | 1.15 | 12FS | FS18-6w | 2013-03-04 08:00 | 2013-03-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 18.375
16 | Isolatie chape/pure | 1.16 | 13FS | FS19 | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 4.375
17 | Elektriciteit | 1.17 | 14FS |  | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1085.53 | 43421.2012 | 43421.2012 | 4.375
18 | Isolatie zolder | 1.18 | 15FS-6w |  | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 4.375
19 | Chape | 1.19 | 16FS | FS21 | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 4.375
20 | Sanitair | 1.20 |  | FS22 | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 4.375
21 | Vloer | 1.21 | 19FS | FS25 | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 4.375
22 | Isolatie chap/pure | 1.22 | 20FS | FS26 | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 4.375
23 | Sanitair | 1.23 |  | FS27 | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1041.67 | 41666.8018 | 41666.8018 | 4.375
24 | Plakwerk | 1.24 | 8FS-2w |  | 2013-03-25 08:00 | 2013-04-19 17:00 | 20d |  | 0 | 0 | 421.05 | 67367.998 | 67367.998 | 25.375
25 | Vloer | 1.25 | 21FS | FS28 | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 4.375
26 | Chape | 1.26 | 22FS | FS29 | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 4.375
27 | Isolatie chap/pure | 1.27 | 23FS | FS30 | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 4.375
28 | Elektriciteit | 1.28 | 25FS | FS34+1w | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 4.375
29 | Vloer | 1.29 | 26FS | FS31 | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 4.375
30 | Chape | 1.30 | 27FS | FS32 | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 4.375
31 | Elektriciteit | 1.31 | 29FS | FS39+1w | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 4.375
32 | Vloer | 1.32 | 30FS | FS35;FS36 | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1822.92 | 72916.8018 | 72916.8018 | 4.375
33 | Sanitair | 1.33 |  | FS37 | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 4.375
34 | Sanitair | 1.34 | 28FS+1w | FS38;FS42 | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 4.375
35 | Elektriciteit | 1.35 | 32FS | FS44 | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 4.375
36 | Vloer | 1.36 | 32FS | FS40 | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 4.375
37 | Isolatie chap/pure | 1.37 | 33FS | FS41 | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 4.375
38 | Keuken | 1.38 | 34FS |  | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 4.375
39 | Sanitair | 1.39 | 31FS+1w | FS43 | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 4.375
40 | Elektriciteit | 1.40 | 36FS | FS48+1w;FS54+2w | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 4.375
41 | Chape | 1.41 | 37FS | FS45 | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 4.375
42 | Isolatie chap/pure | 1.42 | 34FS | FS46;FS50 | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 4.375
43 | Keuken | 1.43 | 39FS |  | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 4.375
44 | Sanitair | 1.44 | 35FS | FS47 | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 4.375
45 | Vloer | 1.45 | 41FS | FS52;FS49 | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 4.375
46 | Chape | 1.46 | 42FS | FS49 | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 4.375
47 | Keuken | 1.47 | 44FS |  | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 4.375
48 | Sanitair | 1.48 | 40FS+1w | FS51 | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 4.375
49 | Vloer | 1.49 | 45FS;46FS | FS53 | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 4.375
50 | Chape | 1.50 | 42FS | FS53 | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 4.375
51 | Keuken | 1.51 | 48FS |  | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 4.375
52 | Elektriciteit | 1.52 | 45FS | FS58+1w | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 4.375
53 | Vloer | 1.53 | 50FS;49FS | FS55;FS56 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 4.375
54 | Sanitair | 1.54 | 40FS+2w | FS57 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 4.375
55 | Elektriciteit | 1.55 | 53FS | FS61+1w | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 4.375
56 | Vloer | 1.56 | 53FS | FS59 | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 4.375
57 | Keuken | 1.57 | 54FS |  | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 4.375
58 | Sanitair | 1.58 | 52FS+1w | FS60 | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 4.375
59 | Elektriciteit | 1.59 | 56FS | FS63+1w | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 4.375
60 | Keuken | 1.60 | 58FS |  | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 4.375
61 | Sanitair | 1.61 | 55FS+1w | FS62 | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 4.375
62 | Keuken | 1.62 | 61FS |  | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1298.08 | 51923.1982 | 51923.1982 | 4.375
63 | Sanitair | 1.63 | 59FS+1w | FS64 | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 4.375
64 | Keuken | 1.64 | 63FS |  | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building (6) | 960h |  |  |  |  | 99 | 100 | 101
1 | Dakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Dakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Ventilatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Plakwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Plakwerken | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Plakwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Isolatie chape/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Plakwerk | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-03-01 17:00 |  | TP Name | 01/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (6) | 2013-01-14 08:00 | 2013-06-28 17:00 | 120d |  |  | 0 |  |  | 2524765.1855 |  | 35d | [5 empty] | 1037105.1929 |  | 41.08% |  | 1037105.1944 | 1131434.7949
1 | Dakwerken | 2013-01-14 08:00 | 2013-01-18 17:00 | 5d |  | 0 | 0 | 2578.95 | 103157.998 | 103157.998 | 2013-01-14 08:00 | 5d | 103157.998 | 0 | 0 | 0 | 0 | 103157.998 | 0 | 100% | Finished | 103157.998 | 103157.998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Sanitair | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-01-21 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
3 | Dakwerken | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 3546.05 | 141842.002 | 141842.002 | 2013-01-21 08:00 | 5d | 141842.002 | 0 | 0 | 0 | 0 | 141842.002 | 0 | 100% | Finished | 141842.002 | 141842.002 | 100 | 100 | 100 | 100 | 100 | 100
4 | Elektriciteit | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-01-28 08:00 | 5d | 57894.7998 | 0 | 0 | 0 | 0 | 57894.7998 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 100 | 100
5 | Ventilatie | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 10000 | 400000 | 400000 | 2013-01-28 08:00 | 5d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plakwerken | 2013-02-04 08:00 | 2013-02-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-02-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-04 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plakwerken | 2013-02-18 08:00 | 2013-04-05 17:00 | 35d |  | 0 | 0 | 421.05 | 117893.9966 | 117893.9966 | 2013-02-18 08:00 | 10d | 33683.999 | 84209.9976 | 25d | 0 | 0 | 33683.999 | 84209.9976 | 28.57% | Started | 33684.0005 | 33683.999 | 100 | 28.5714 | 28.5714 | 100 | 28.5714 | 28.5714
9 | Isolatie zolder | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 5952.3999 | 100 |  | 0 | 100 |  | 0
10 | Sanitair | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-18 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 |  | 0 | 0 | 66666.8018 | 5d | 0 | 0 | 0 | 66666.8018 | 0% | Not Started | 0 | 66666.8018 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 |  | 0 | 0 | 21710.4004 | 5d | 0 | 0 | 0 | 21710.4004 | 0% | Not Started | 0 | 21710.4004 | 100 |  | 0 | 100 |  | 0
13 | Sanitair | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 833.33 | 33333.2007 | 33333.2007 |  | 0 | 0 | 33333.2007 | 5d | 0 | 0 | 0 | 33333.2007 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 |  | 0 | 0 | 57894.7998 | 5d | 0 | 0 | 0 | 57894.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plakwerken | 2013-03-04 08:00 | 2013-03-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 |  | 0 | 0 | 50525.9985 | 15d | 0 | 0 | 0 | 50525.9985 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Isolatie chape/pure | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 |  | 0 | 0 | 11904.7998 | 5d | 0 | 0 | 0 | 11904.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Elektriciteit | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1085.53 | 43421.2012 | 43421.2012 |  | 0 | 0 | 43421.2012 | 5d | 0 | 0 | 0 | 43421.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Chape | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 |  | 0 | 0 | 11904.7998 | 5d | 0 | 0 | 0 | 11904.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Vloer | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 |  | 0 | 0 | 14583.1995 | 5d | 0 | 0 | 0 | 14583.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1041.67 | 41666.8018 | 41666.8018 |  | 0 | 0 | 41666.8018 | 5d | 0 | 0 | 0 | 41666.8018 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plakwerk | 2013-03-25 08:00 | 2013-04-19 17:00 | 20d |  | 0 | 0 | 421.05 | 67367.998 | 67367.998 |  | 0 | 0 | 67367.998 | 20d | 0 | 0 | 0 | 67367.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Vloer | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Chape | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Isolatie chap/pure | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 |  | 0 | 0 | 14880.7996 | 5d | 0 | 0 | 0 | 14880.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 |  | 0 | 0 | 7236.7999 | 5d | 0 | 0 | 0 | 7236.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Vloer | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Chape | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 |  | 0 | 0 | 14880.7996 | 5d | 0 | 0 | 0 | 14880.7996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 |  | 0 | 0 | 14473.5999 | 5d | 0 | 0 | 0 | 14473.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Vloer | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1822.92 | 72916.8018 | 72916.8018 |  | 0 | 0 | 72916.8018 | 5d | 0 | 0 | 0 | 72916.8018 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 |  | 0 | 0 | 14473.5999 | 5d | 0 | 0 | 0 | 14473.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Vloer | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Isolatie chap/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Keuken | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 |  | 0 | 0 | 21710.4004 | 5d | 0 | 0 | 0 | 21710.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Keuken | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Vloer | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 |  | 0 | 0 | 14583.1995 | 5d | 0 | 0 | 0 | 14583.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Keuken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloer | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Chape | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keuken | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 |  | 0 | 0 | 7236.7999 | 5d | 0 | 0 | 0 | 7236.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Vloer | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 |  | 0 | 0 | 21710.4004 | 5d | 0 | 0 | 0 | 21710.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Vloer | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 |  | 0 | 0 | 14583.1995 | 5d | 0 | 0 | 0 | 14583.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Keuken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Sanitair | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Elektriciteit | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 |  | 0 | 0 | 7236.7999 | 5d | 0 | 0 | 0 | 7236.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Keuken | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 |  | 0 | 0 | 25000 | 5d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1298.08 | 51923.1982 | 51923.1982 |  | 0 | 0 | 51923.1982 | 5d | 0 | 0 | 0 | 51923.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-04-12 17:00 |  | TP Name | 12/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (6) | 2013-01-14 08:00 | 2013-06-28 17:00 | 120d |  |  | 0 |  |  | 2524765.1855 |  | 65d | [5 empty] | 1593639.6542 |  | 63.61% |  | 1605920.394 | 1705011.1896
1 | Dakwerken | 2013-01-14 08:00 | 2013-01-18 17:00 | 5d |  | 0 | 0 | 2578.95 | 103157.998 | 103157.998 | 2013-01-14 08:00 | 5d | 103157.998 | 0 | 0 | 0 | 0 | 103157.998 | 0 | 100% | Finished | 103157.998 | 103157.998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Sanitair | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-01-21 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
3 | Dakwerken | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 3546.05 | 141842.002 | 141842.002 | 2013-01-21 08:00 | 5d | 141842.002 | 0 | 0 | 0 | 0 | 141842.002 | 0 | 100% | Finished | 141842.002 | 141842.002 | 100 | 100 | 100 | 100 | 100 | 100
4 | Elektriciteit | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-01-28 08:00 | 5d | 57894.7998 | 0 | 0 | 0 | 0 | 57894.7998 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 100 | 100
5 | Ventilatie | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 10000 | 400000 | 400000 | 2013-01-28 08:00 | 5d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plakwerken | 2013-02-04 08:00 | 2013-02-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-02-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-04 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plakwerken | 2013-02-18 08:00 | 2013-04-05 17:00 | 35d |  | 0 | 0 | 421.05 | 117893.9966 | 117893.9966 | 2013-02-18 08:00 | 10d | 33683.999 | 84209.9976 | 25d | 0 | 0 | 33683.999 | 84209.9976 | 28.57% | Started | 33684.0005 | 117893.9966 | 100 | 28.5714 | 28.5714 | 100 | 28.5714 | 28.5714
9 | Isolatie zolder | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
10 | Sanitair | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-18 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-03-04 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-03-25 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 833.33 | 33333.2007 | 33333.2007 | 2013-03-04 08:00 | 5d | 33333.2007 | 0 | 0 | 16666.6602 | 0 | 49999.8608 | 0 | 100% | Finished | 33333.2007 | 33333.2007 | 100 | 100 | 100 | 100 | 150.0002 | 100
14 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-03-04 08:00 | 5d | 57894.7998 | 0 | 0 | -28947.4004 | 0 | 28947.3994 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 50 | 100
15 | Plakwerken | 2013-03-04 08:00 | 2013-03-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-03-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
16 | Isolatie chape/pure | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-11 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
17 | Elektriciteit | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1085.53 | 43421.2012 | 43421.2012 | 2013-03-11 08:00 | 10d | 86842.4023 | 0 | 0 | -43421.1992 | 0 | 43421.2031 | 0 | 100% | Finished | 43421.2012 | 43421.2012 | 100 | 200 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-01 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chape | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-18 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
20 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-03-04 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
21 | Vloer | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-03-25 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
22 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
23 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1041.67 | 41666.8018 | 41666.8018 | 2013-04-01 08:00 | 5d | 41666.8018 | 0 | 0 | 0 | 0 | 41666.8018 | 0 | 100% | Finished | 41666.8018 | 41666.8018 | 100 | 100 | 100 | 100 | 100 | 100
24 | Plakwerk | 2013-03-25 08:00 | 2013-04-19 17:00 | 20d |  | 0 | 0 | 421.05 | 67367.998 | 67367.998 | 2013-03-25 08:00 | 15d | 50525.9985 | 16841.9995 | 5d | 0 | 0 | 50525.9985 | 16841.9995 | 75% | Started | 50525.9985 | 50525.9985 | 100 | 75 | 75 | 100 | 75 | 75
25 | Vloer | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-01 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 100 | 100
26 | Chape | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-25 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie chap/pure | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-08 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 100% | Finished | 14880.7996 | 14880.7996 | 100 | 100 | 100 | 100 | 100 | 100
28 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-04-08 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
29 | Vloer | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-03-25 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 100 | 100 | 100 | 100 | 100
30 | Chape | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 |  | 0 | 0 | 14880.7996 | 5d | 0 | 0 | 0 | 14880.7996 | 0% | Not Started | 0 | 14880.7996 | 100 |  | 0 | 100 |  | 0
31 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 |  | 0 | 0 | 14473.5999 | 5d | 0 | 0 | 0 | 14473.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Vloer | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1822.92 | 72916.8018 | 72916.8018 |  | 0 | 0 | 72916.8018 | 5d | 0 | 0 | 0 | 72916.8018 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 |  | 0 | 0 | 14473.5999 | 5d | 0 | 0 | 0 | 14473.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Vloer | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Isolatie chap/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Keuken | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 |  | 0 | 0 | 21710.4004 | 5d | 0 | 0 | 0 | 21710.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Keuken | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Vloer | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 |  | 0 | 0 | 14583.1995 | 5d | 0 | 0 | 0 | 14583.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Keuken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloer | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Chape | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 |  | 0 | 0 | 5952.3999 | 5d | 0 | 0 | 0 | 5952.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Keuken | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 |  | 0 | 0 | 7236.7999 | 5d | 0 | 0 | 0 | 7236.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Vloer | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 |  | 0 | 0 | 21710.4004 | 5d | 0 | 0 | 0 | 21710.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Vloer | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 |  | 0 | 0 | 14583.1995 | 5d | 0 | 0 | 0 | 14583.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Keuken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Sanitair | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Elektriciteit | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 |  | 0 | 0 | 7236.7999 | 5d | 0 | 0 | 0 | 7236.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Keuken | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 |  | 0 | 0 | 25000 | 5d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1298.08 | 51923.1982 | 51923.1982 |  | 0 | 0 | 51923.1982 | 5d | 0 | 0 | 0 | 51923.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-05-24 17:00 |  | TP Name | 24/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (6) | 2013-01-14 08:00 | 2013-06-28 17:00 | 120d |  |  | 0 |  |  | 2524765.1855 |  | 95d | [5 empty] | 2070923.0662 |  | 82.04% |  | 2071298.3524 | 2335722.3871
1 | Dakwerken | 2013-01-14 08:00 | 2013-01-18 17:00 | 5d |  | 0 | 0 | 2578.95 | 103157.998 | 103157.998 | 2013-01-14 08:00 | 5d | 103157.998 | 0 | 0 | 0 | 0 | 103157.998 | 0 | 100% | Finished | 103157.998 | 103157.998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Sanitair | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-01-21 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
3 | Dakwerken | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 3546.05 | 141842.002 | 141842.002 | 2013-01-21 08:00 | 5d | 141842.002 | 0 | 0 | 0 | 0 | 141842.002 | 0 | 100% | Finished | 141842.002 | 141842.002 | 100 | 100 | 100 | 100 | 100 | 100
4 | Elektriciteit | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-01-28 08:00 | 5d | 57894.7998 | 0 | 0 | 0 | 0 | 57894.7998 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 100 | 100
5 | Ventilatie | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 10000 | 400000 | 400000 | 2013-01-28 08:00 | 5d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plakwerken | 2013-02-04 08:00 | 2013-02-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-02-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-04 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plakwerken | 2013-02-18 08:00 | 2013-04-05 17:00 | 35d |  | 0 | 0 | 421.05 | 117893.9966 | 117893.9966 | 2013-02-18 08:00 | 10d | 33683.999 | 84209.9976 | 25d | 0 | 0 | 33683.999 | 84209.9976 | 28.57% | Started | 33684.0005 | 117893.9966 | 100 | 28.5714 | 28.5714 | 100 | 28.5714 | 28.5714
9 | Isolatie zolder | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
10 | Sanitair | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-18 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-03-04 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-03-25 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 833.33 | 33333.2007 | 33333.2007 | 2013-03-04 08:00 | 5d | 33333.2007 | 0 | 0 | 16666.6602 | 0 | 49999.8608 | 0 | 100% | Finished | 33333.2007 | 33333.2007 | 100 | 100 | 100 | 100 | 150.0002 | 100
14 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-03-04 08:00 | 5d | 57894.7998 | 0 | 0 | -28947.4004 | 0 | 28947.3994 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 50 | 100
15 | Plakwerken | 2013-03-04 08:00 | 2013-03-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-03-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
16 | Isolatie chape/pure | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-11 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
17 | Elektriciteit | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1085.53 | 43421.2012 | 43421.2012 | 2013-03-11 08:00 | 10d | 86842.4023 | 0 | 0 | -43421.1992 | 0 | 43421.2031 | 0 | 100% | Finished | 43421.2012 | 43421.2012 | 100 | 200 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-01 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chape | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-18 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
20 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-03-04 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
21 | Vloer | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-03-25 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
22 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
23 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1041.67 | 41666.8018 | 41666.8018 | 2013-04-01 08:00 | 5d | 41666.8018 | 0 | 0 | 0 | 0 | 41666.8018 | 0 | 100% | Finished | 41666.8018 | 41666.8018 | 100 | 100 | 100 | 100 | 100 | 100
24 | Plakwerk | 2013-03-25 08:00 | 2013-04-19 17:00 | 20d |  | 0 | 0 | 421.05 | 67367.998 | 67367.998 | 2013-03-25 08:00 | 15d | 50525.9985 | 16841.9995 | 5d | 0 | 0 | 50525.9985 | 16841.9995 | 75% | Started | 50525.9985 | 67367.998 | 100 | 75 | 75 | 100 | 75 | 75
25 | Vloer | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-01 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 100 | 100
26 | Chape | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-25 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie chap/pure | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-08 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 100% | Finished | 14880.7996 | 14880.7996 | 100 | 100 | 100 | 100 | 100 | 100
28 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-04-08 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
29 | Vloer | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-03-25 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 100 | 100 | 100 | 100 | 100
30 | Chape | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-15 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 100% | Finished | 14880.7996 | 14880.7996 | 100 | 100 | 100 | 100 | 100 | 100
31 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 100% | Finished | 14473.5999 | 14473.5999 | 100 | 100 | 100 | 100 | 100 | 100
32 | Vloer | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1822.92 | 72916.8018 | 72916.8018 | 2013-04-15 08:00 | 30d | 437500.8105 | 0 | 0 | -364583.1875 | 0 | 72917.623 | 0 | 100% | Finished | 72916.8018 | 72916.8018 | 100 | 600 | 100 | 100 | 100.0011 | 100
33 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-04-22 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
34 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-04-15 08:00 | 25d | 291665.9912 | 0 | 0 | -233333 | 0 | 58332.9912 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 500 | 100 | 100 | 99.9996 | 100
35 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 100% | Finished | 14473.5999 | 14473.5999 | 100 | 100 | 100 | 100 | 100 | 100
36 | Vloer | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-29 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 100 | 100
37 | Isolatie chap/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
38 | Keuken | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-05-13 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
40 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-05-13 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 100 | 100 | 100 | 100 | 100
41 | Chape | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-05-06 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
42 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-22 08:00 | 25d | 89285.9985 | 0 | 0 | -71428.7969 | 0 | 17857.2017 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 500 | 100 | 100 | 100 | 100
43 | Keuken | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-05-20 08:00 | 5d | 34615.2002 | 0 | 0 | 0 | 0 | 34615.2002 | 0 | 100% | Finished | 34615.2002 | 34615.2002 | 100 | 100 | 100 | 100 | 100 | 100
44 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 10d | 33333.6011 | 33333.6011 | 10d | -16666.8008 | 0 | 16666.8003 | 33333.6011 | 50% | Started | 8333.4003 | 16666.8005 | 100 | 200 | 50 | 100 | 100 | 50
45 | Vloer | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-05-13 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
46 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-29 08:00 | 20d | 71428.7988 | 17857.1997 | 5d | -53571.6016 | 0 | 17857.1973 | 17857.1997 | 80% | Started | 14285.76 | 17857.1997 | 100 | 400 | 80 | 100 | 100 | 80
47 | Keuken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 34615.2002 | 100 |  | 0 | 100 |  | 0
48 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 |  | 0 | 0 | 16666.8005 | 5d | 0 | 0 | 0 | 16666.8005 | 0% | Not Started | 0 | 16666.8005 | 100 |  | 0 | 100 |  | 0
49 | Vloer | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-05-20 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 100 | 100 | 100 | 100 | 100
50 | Chape | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
51 | Keuken | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 |  | 0 | 0 | 34615.2002 | 5d | 0 | 0 | 0 | 34615.2002 | 0% | Not Started | 0 | 34615.2002 | 100 |  | 0 | 100 |  | 0
52 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 |  | 0 | 0 | 7236.7999 | 5d | 0 | 0 | 0 | 7236.7999 | 0% | Not Started | 0 | 7236.7999 | 100 |  | 0 | 100 |  | 0
53 | Vloer | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 |  | 0 | 0 | 58333.1982 | 5d | 0 | 0 | 0 | 58333.1982 | 0% | Not Started | 0 | 58333.1982 | 100 |  | 0 | 100 |  | 0
54 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-05-13 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 100% | Finished | 8333.2001 | 8333.2001 | 100 | 100 | 100 | 100 | 100 | 100
55 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 |  | 0 | 0 | 21710.4004 | 5d | 0 | 0 | 0 | 21710.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Vloer | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 |  | 0 | 0 | 14583.1995 | 5d | 0 | 0 | 0 | 14583.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Keuken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Sanitair | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Elektriciteit | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 |  | 0 | 0 | 7236.7999 | 5d | 0 | 0 | 0 | 7236.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Keuken | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 |  | 0 | 0 | 25000 | 5d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1298.08 | 51923.1982 | 51923.1982 |  | 0 | 0 | 51923.1982 | 5d | 0 | 0 | 0 | 51923.1982 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 |  | 0 | 0 | 8333.2001 | 5d | 0 | 0 | 0 | 8333.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 |  | 0 | 0 | 17307.6001 | 5d | 0 | 0 | 0 | 17307.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-07-08 09:00 |  | TP Name | 08/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (6) | 2013-01-14 08:00 | 2013-06-28 17:00 | 120d |  |  | 0 |  |  | 2524765.1855 |  | 125d 1h | [5 empty] | 2428840.7484 |  | 94.66% |  | 2389930.0712 | 2524765.1855
1 | Dakwerken | 2013-01-14 08:00 | 2013-01-18 17:00 | 5d |  | 0 | 0 | 2578.95 | 103157.998 | 103157.998 | 2013-01-14 08:00 | 5d | 103157.998 | 0 | 0 | 0 | 0 | 103157.998 | 0 | 100% | Finished | 103157.998 | 103157.998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Sanitair | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-01-21 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
3 | Dakwerken | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 3546.05 | 141842.002 | 141842.002 | 2013-01-21 08:00 | 5d | 141842.002 | 0 | 0 | 0 | 0 | 141842.002 | 0 | 100% | Finished | 141842.002 | 141842.002 | 100 | 100 | 100 | 100 | 100 | 100
4 | Elektriciteit | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-01-28 08:00 | 5d | 57894.7998 | 0 | 0 | 0 | 0 | 57894.7998 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 100 | 100
5 | Ventilatie | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 10000 | 400000 | 400000 | 2013-01-28 08:00 | 5d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plakwerken | 2013-02-04 08:00 | 2013-02-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-02-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-04 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plakwerken | 2013-02-18 08:00 | 2013-04-05 17:00 | 35d |  | 0 | 0 | 421.05 | 117893.9966 | 117893.9966 | 2013-02-18 08:00 | 10d | 33683.999 | 84209.9976 | 25d | 0 | 0 | 33683.999 | 84209.9976 | 28.57% | Started | 33684.0005 | 117893.9966 | 100 | 28.5714 | 28.5714 | 100 | 28.5714 | 28.5714
9 | Isolatie zolder | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
10 | Sanitair | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-18 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-03-04 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-03-25 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 833.33 | 33333.2007 | 33333.2007 | 2013-03-04 08:00 | 5d | 33333.2007 | 0 | 0 | 16666.6602 | 0 | 49999.8608 | 0 | 100% | Finished | 33333.2007 | 33333.2007 | 100 | 100 | 100 | 100 | 150.0002 | 100
14 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-03-04 08:00 | 5d | 57894.7998 | 0 | 0 | -28947.4004 | 0 | 28947.3994 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 50 | 100
15 | Plakwerken | 2013-03-04 08:00 | 2013-03-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-03-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
16 | Isolatie chape/pure | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-11 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
17 | Elektriciteit | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1085.53 | 43421.2012 | 43421.2012 | 2013-03-11 08:00 | 10d | 86842.4023 | 0 | 0 | -43421.1992 | 0 | 43421.2031 | 0 | 100% | Finished | 43421.2012 | 43421.2012 | 100 | 200 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-01 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chape | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-18 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
20 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-03-04 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
21 | Vloer | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-03-25 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
22 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
23 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1041.67 | 41666.8018 | 41666.8018 | 2013-04-01 08:00 | 5d | 41666.8018 | 0 | 0 | 0 | 0 | 41666.8018 | 0 | 100% | Finished | 41666.8018 | 41666.8018 | 100 | 100 | 100 | 100 | 100 | 100
24 | Plakwerk | 2013-03-25 08:00 | 2013-04-19 17:00 | 20d |  | 0 | 0 | 421.05 | 67367.998 | 67367.998 | 2013-03-25 08:00 | 20d | 67367.998 | 0 | 0 | 0 | 0 | 67367.998 | 0 | 100% | Finished | 67367.998 | 67367.998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-01 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 100 | 100
26 | Chape | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-25 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie chap/pure | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-08 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 100% | Finished | 14880.7996 | 14880.7996 | 100 | 100 | 100 | 100 | 100 | 100
28 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-04-08 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
29 | Vloer | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-03-25 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 100 | 100 | 100 | 100 | 100
30 | Chape | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-15 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 100% | Finished | 14880.7996 | 14880.7996 | 100 | 100 | 100 | 100 | 100 | 100
31 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 100% | Finished | 14473.5999 | 14473.5999 | 100 | 100 | 100 | 100 | 100 | 100
32 | Vloer | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1822.92 | 72916.8018 | 72916.8018 | 2013-04-15 08:00 | 30d | 437500.8105 | 0 | 0 | -364583.1875 | 0 | 72917.623 | 0 | 100% | Finished | 72916.8018 | 72916.8018 | 100 | 600 | 100 | 100 | 100.0011 | 100
33 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-04-22 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
34 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-04-15 08:00 | 25d | 291665.9912 | 0 | 0 | -233333 | 0 | 58332.9912 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 500 | 100 | 100 | 99.9996 | 100
35 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 100% | Finished | 14473.5999 | 14473.5999 | 100 | 100 | 100 | 100 | 100 | 100
36 | Vloer | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-29 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 100 | 100
37 | Isolatie chap/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
38 | Keuken | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-05-13 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
40 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-05-13 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 100 | 100 | 100 | 100 | 100
41 | Chape | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-05-06 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
42 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-22 08:00 | 25d | 89285.9985 | 0 | 0 | -71428.7969 | 0 | 17857.2017 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 500 | 100 | 100 | 100 | 100
43 | Keuken | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-05-20 08:00 | 5d | 34615.2002 | 0 | 0 | 0 | 0 | 34615.2002 | 0 | 100% | Finished | 34615.2002 | 34615.2002 | 100 | 100 | 100 | 100 | 100 | 100
44 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 20d | 66667.2021 | 0 | 0 | -16666.8008 | 0 | 50000.4014 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 400 | 100 | 100 | 300 | 100
45 | Vloer | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-05-13 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
46 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-29 08:00 | 25d | 89285.9985 | 0 | 0 | -53571.6016 | 0 | 35714.397 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 500 | 100 | 100 | 200 | 100
47 | Keuken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-06-24 08:00 | 10d | 69230.4004 | 0 | 0 | -34615.1992 | 0 | 34615.2012 | 0 | 100% | Finished | 34615.2002 | 34615.2002 | 100 | 200 | 100 | 100 | 100 | 100
48 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-06-17 08:00 | 10d | 33333.6011 | 0 | 0 | -16666.8008 | 0 | 16666.8003 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 200 | 100 | 100 | 100 | 100
49 | Vloer | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-05-20 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 100 | 100 | 100 | 100 | 100
50 | Chape | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
51 | Keuken | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-06-24 08:00 | 10d | 69230.4004 | 0 | 0 | -34615.1992 | 0 | 34615.2012 | 0 | 100% | Finished | 34615.2002 | 34615.2002 | 100 | 200 | 100 | 100 | 100 | 100
52 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-06-03 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
53 | Vloer | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-06-03 08:00 | 10d | 116666.3965 | 0 | 0 | -58333.1992 | 0 | 58333.1973 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 200 | 100 | 100 | 100 | 100
54 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-05-13 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 100% | Finished | 8333.2001 | 8333.2001 | 100 | 100 | 100 | 100 | 100 | 100
55 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-05-27 08:00 | 20d | 86841.6016 | 0 | 0 | -65131.1992 | 0 | 21710.4023 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 400 | 100 | 100 | 100 | 100
56 | Vloer | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-05-27 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
57 | Keuken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-05-27 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100
58 | Sanitair | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-06-17 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 100% | Finished | 8333.2001 | 8333.2001 | 100 | 100 | 100 | 100 | 100 | 100
59 | Elektriciteit | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-05-27 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
60 | Keuken | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-06-24 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100
61 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-07-01 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
62 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1298.08 | 51923.1982 | 51923.1982 | 2013-07-08 08:00 | 1h | 1298.08 | 50625.1183 | 4d 7h | 0 | 0 | 1298.08 | 50625.1183 | 2.5% | Started | 1298.08 | 51923.1982 | 100 | 2.5 | 2.5 | 100 | 2.5 | 2.5
63 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-06-03 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 100% | Finished | 8333.2001 | 8333.2001 | 100 | 100 | 100 | 100 | 100 | 100
64 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-06-10 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100

## TP5
| TP Status Date | 2013-07-15 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (6) | 2013-01-14 08:00 | 2013-06-28 17:00 | 120d |  |  | 0 |  |  | 2524765.1855 |  | 130d | [5 empty] | 2563675.8643 |  | 100% |  | 2524765.1855 | 2524765.1855
1 | Dakwerken | 2013-01-14 08:00 | 2013-01-18 17:00 | 5d |  | 0 | 0 | 2578.95 | 103157.998 | 103157.998 | 2013-01-14 08:00 | 5d | 103157.998 | 0 | 0 | 0 | 0 | 103157.998 | 0 | 100% | Finished | 103157.998 | 103157.998 | 100 | 100 | 100 | 100 | 100 | 100
2 | Sanitair | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-01-21 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
3 | Dakwerken | 2013-01-21 08:00 | 2013-01-25 17:00 | 5d |  | 0 | 0 | 3546.05 | 141842.002 | 141842.002 | 2013-01-21 08:00 | 5d | 141842.002 | 0 | 0 | 0 | 0 | 141842.002 | 0 | 100% | Finished | 141842.002 | 141842.002 | 100 | 100 | 100 | 100 | 100 | 100
4 | Elektriciteit | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-01-28 08:00 | 5d | 57894.7998 | 0 | 0 | 0 | 0 | 57894.7998 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 100 | 100
5 | Ventilatie | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 10000 | 400000 | 400000 | 2013-01-28 08:00 | 5d | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | 100% | Finished | 400000 | 400000 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plakwerken | 2013-02-04 08:00 | 2013-02-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-02-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-04 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
8 | Plakwerken | 2013-02-18 08:00 | 2013-04-05 17:00 | 35d |  | 0 | 0 | 421.05 | 117893.9966 | 117893.9966 | 2013-02-18 08:00 | 35d | 117893.9966 | 0 | 0 | 0 | 0 | 117893.9966 | 0 | 100% | Finished | 117893.9966 | 117893.9966 | 100 | 100 | 100 | 100 | 100 | 100
9 | Isolatie zolder | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
10 | Sanitair | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 2291.6699 | 91666.7969 | 91666.7969 | 2013-02-18 08:00 | 5d | 91666.7969 | 0 | 0 | 0 | 0 | 91666.7969 | 0 | 100% | Finished | 91666.7969 | 91666.7969 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1666.67 | 66666.8018 | 66666.8018 | 2013-03-04 08:00 | 5d | 66666.8018 | 0 | 0 | 0 | 0 | 66666.8018 | 0 | 100% | Finished | 66666.8018 | 66666.8018 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-03-25 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 833.33 | 33333.2007 | 33333.2007 | 2013-03-04 08:00 | 5d | 33333.2007 | 0 | 0 | 16666.6602 | 0 | 49999.8608 | 0 | 100% | Finished | 33333.2007 | 33333.2007 | 100 | 100 | 100 | 100 | 150.0002 | 100
14 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 1447.37 | 57894.7998 | 57894.7998 | 2013-03-04 08:00 | 5d | 57894.7998 | 0 | 0 | -28947.4004 | 0 | 28947.3994 | 0 | 100% | Finished | 57894.7998 | 57894.7998 | 100 | 100 | 100 | 100 | 50 | 100
15 | Plakwerken | 2013-03-04 08:00 | 2013-03-22 17:00 | 15d |  | 0 | 0 | 421.05 | 50525.9985 | 50525.9985 | 2013-03-04 08:00 | 15d | 50525.9985 | 0 | 0 | 0 | 0 | 50525.9985 | 0 | 100% | Finished | 50525.9985 | 50525.9985 | 100 | 100 | 100 | 100 | 100 | 100
16 | Isolatie chape/pure | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-11 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
17 | Elektriciteit | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1085.53 | 43421.2012 | 43421.2012 | 2013-03-11 08:00 | 10d | 86842.4023 | 0 | 0 | -43421.1992 | 0 | 43421.2031 | 0 | 100% | Finished | 43421.2012 | 43421.2012 | 100 | 200 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-01 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chape | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 297.62 | 11904.7998 | 11904.7998 | 2013-03-18 08:00 | 5d | 11904.7998 | 0 | 0 | 0 | 0 | 11904.7998 | 0 | 100% | Finished | 11904.7998 | 11904.7998 | 100 | 100 | 100 | 100 | 100 | 100
20 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-03-04 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
21 | Vloer | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-03-25 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
22 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-11 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
23 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1041.67 | 41666.8018 | 41666.8018 | 2013-04-01 08:00 | 5d | 41666.8018 | 0 | 0 | 0 | 0 | 41666.8018 | 0 | 100% | Finished | 41666.8018 | 41666.8018 | 100 | 100 | 100 | 100 | 100 | 100
24 | Plakwerk | 2013-03-25 08:00 | 2013-04-19 17:00 | 20d |  | 0 | 0 | 421.05 | 67367.998 | 67367.998 | 2013-03-25 08:00 | 20d | 67367.998 | 0 | 0 | 0 | 0 | 67367.998 | 0 | 100% | Finished | 67367.998 | 67367.998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-01 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 100 | 100
26 | Chape | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-03-25 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie chap/pure | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-08 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 100% | Finished | 14880.7996 | 14880.7996 | 100 | 100 | 100 | 100 | 100 | 100
28 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-04-08 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
29 | Vloer | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-03-25 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 100 | 100 | 100 | 100 | 100
30 | Chape | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 372.02 | 14880.7996 | 14880.7996 | 2013-04-15 08:00 | 5d | 14880.7996 | 0 | 0 | 0 | 0 | 14880.7996 | 0 | 100% | Finished | 14880.7996 | 14880.7996 | 100 | 100 | 100 | 100 | 100 | 100
31 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 100% | Finished | 14473.5999 | 14473.5999 | 100 | 100 | 100 | 100 | 100 | 100
32 | Vloer | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1822.92 | 72916.8018 | 72916.8018 | 2013-04-15 08:00 | 30d | 437500.8105 | 0 | 0 | -364583.1875 | 0 | 72917.623 | 0 | 100% | Finished | 72916.8018 | 72916.8018 | 100 | 600 | 100 | 100 | 100.0011 | 100
33 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-04-22 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
34 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-04-15 08:00 | 25d | 291665.9912 | 0 | 0 | -233333 | 0 | 58332.9912 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 500 | 100 | 100 | 99.9996 | 100
35 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 361.84 | 14473.5999 | 14473.5999 | 2013-04-29 08:00 | 5d | 14473.5999 | 0 | 0 | 0 | 0 | 14473.5999 | 0 | 100% | Finished | 14473.5999 | 14473.5999 | 100 | 100 | 100 | 100 | 100 | 100
36 | Vloer | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-04-29 08:00 | 5d | 43750 | 0 | 0 | 0 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 100 | 100
37 | Isolatie chap/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
38 | Keuken | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-05-13 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 5d | 16666.8005 | 0 | 0 | 0 | 0 | 16666.8005 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 100 | 100 | 100 | 100 | 100
40 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-05-13 08:00 | 5d | 21710.4004 | 0 | 0 | 0 | 0 | 21710.4004 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 100 | 100 | 100 | 100 | 100
41 | Chape | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-05-06 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
42 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-22 08:00 | 25d | 89285.9985 | 0 | 0 | -71428.7969 | 0 | 17857.2017 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 500 | 100 | 100 | 100 | 100
43 | Keuken | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-05-20 08:00 | 5d | 34615.2002 | 0 | 0 | 0 | 0 | 34615.2002 | 0 | 100% | Finished | 34615.2002 | 34615.2002 | 100 | 100 | 100 | 100 | 100 | 100
44 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-05-13 08:00 | 20d | 66667.2021 | 0 | 0 | -16666.8008 | 0 | 50000.4014 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 400 | 100 | 100 | 300 | 100
45 | Vloer | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-05-13 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
46 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-04-29 08:00 | 25d | 89285.9985 | 0 | 0 | -53571.6016 | 0 | 35714.397 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 500 | 100 | 100 | 200 | 100
47 | Keuken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-06-24 08:00 | 10d | 69230.4004 | 0 | 0 | -34615.1992 | 0 | 34615.2012 | 0 | 100% | Finished | 34615.2002 | 34615.2002 | 100 | 200 | 100 | 100 | 100 | 100
48 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 416.67 | 16666.8005 | 16666.8005 | 2013-06-17 08:00 | 10d | 33333.6011 | 0 | 0 | -16666.8008 | 0 | 16666.8003 | 0 | 100% | Finished | 16666.8005 | 16666.8005 | 100 | 200 | 100 | 100 | 100 | 100
49 | Vloer | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-05-20 08:00 | 5d | 58333.1982 | 0 | 0 | 0 | 0 | 58333.1982 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 100 | 100 | 100 | 100 | 100
50 | Chape | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 148.81 | 5952.3999 | 5952.3999 | 2013-04-29 08:00 | 5d | 5952.3999 | 0 | 0 | 0 | 0 | 5952.3999 | 0 | 100% | Finished | 5952.3999 | 5952.3999 | 100 | 100 | 100 | 100 | 100 | 100
51 | Keuken | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 865.38 | 34615.2002 | 34615.2002 | 2013-06-24 08:00 | 10d | 69230.4004 | 0 | 0 | -34615.1992 | 0 | 34615.2012 | 0 | 100% | Finished | 34615.2002 | 34615.2002 | 100 | 200 | 100 | 100 | 100 | 100
52 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-06-03 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
53 | Vloer | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1458.33 | 58333.1982 | 58333.1982 | 2013-06-03 08:00 | 10d | 116666.3965 | 0 | 0 | -58333.1992 | 0 | 58333.1973 | 0 | 100% | Finished | 58333.1982 | 58333.1982 | 100 | 200 | 100 | 100 | 100 | 100
54 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-05-13 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 100% | Finished | 8333.2001 | 8333.2001 | 100 | 100 | 100 | 100 | 100 | 100
55 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 542.76 | 21710.4004 | 21710.4004 | 2013-05-27 08:00 | 20d | 86841.6016 | 0 | 0 | -65131.1992 | 0 | 21710.4023 | 0 | 100% | Finished | 21710.4004 | 21710.4004 | 100 | 400 | 100 | 100 | 100 | 100
56 | Vloer | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 364.58 | 14583.1995 | 14583.1995 | 2013-05-27 08:00 | 5d | 14583.1995 | 0 | 0 | 0 | 0 | 14583.1995 | 0 | 100% | Finished | 14583.1995 | 14583.1995 | 100 | 100 | 100 | 100 | 100 | 100
57 | Keuken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-05-27 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100
58 | Sanitair | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-06-17 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 100% | Finished | 8333.2001 | 8333.2001 | 100 | 100 | 100 | 100 | 100 | 100
59 | Elektriciteit | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 180.92 | 7236.7999 | 7236.7999 | 2013-05-27 08:00 | 5d | 7236.7999 | 0 | 0 | 0 | 0 | 7236.7999 | 0 | 100% | Finished | 7236.7999 | 7236.7999 | 100 | 100 | 100 | 100 | 100 | 100
60 | Keuken | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-06-24 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100
61 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 625 | 25000 | 25000 | 2013-07-01 08:00 | 5d | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 100% | Finished | 25000 | 25000 | 100 | 100 | 100 | 100 | 100 | 100
62 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1298.08 | 51923.1982 | 51923.1982 | 2013-07-08 08:00 | 5d | 51923.1982 | 0 | 0 | 0 | 0 | 51923.1982 | 0 | 100% | Finished | 51923.1982 | 51923.1982 | 100 | 100 | 100 | 100 | 100 | 100
63 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 208.33 | 8333.2001 | 8333.2001 | 2013-06-03 08:00 | 5d | 8333.2001 | 0 | 0 | 0 | 0 | 8333.2001 | 0 | 100% | Finished | 8333.2001 | 8333.2001 | 100 | 100 | 100 | 100 | 100 | 100
64 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 432.69 | 17307.6001 | 17307.6001 | 2013-06-10 08:00 | 5d | 17307.6001 | 0 | 0 | 0 | 0 | 17307.6001 | 0 | 100% | Finished | 17307.6001 | 17307.6001 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
01/03, 2013 | 2013-01-14 08:00 | 2013-03-01 17:00 | 1131434.7949 | 1037105.1944 | 1037105.1929 | 2013-02-25 12:00 | -94329.6005 | 91.66% | 0.0015058 | 100% | -4d 4h | 87.14% | 98.57% | 2013-07-05 12:00 | 2013-07-15 16:00 | 2013-07-15 16:00 | 2013-07-03 16:00 | 2013-07-15 16:00 | 2013-07-15 16:00 | 2013-07-05 12:00 | 2013-07-24 15:00 | 2013-07-24 15:00 | 2524765.184 | 2524765.1819 | 2660074.8648 | 2744256.0024 | 2660074.8624 | 2744255.9999 | 2549991.5527 | 2564028.9357 | 0.87143 | 1 | 0.91663 | 0.98573 | -4.5 | 1 | 1 | 0.87143 | 1
12/04, 2013 | 2013-03-01 17:00 | 2013-04-12 17:00 | 1705011.1896 | 1605920.394 | 1593639.6542 | 2013-04-05 16:00 | -99090.7956 | 94.19% | 12280.7398 | 100.8% | -5d 1h | 92.12% | 94.78% | 2013-07-05 15:00 | 2013-07-10 11:00 | 2013-07-09 11:00 | 2013-07-04 15:00 | 2013-07-10 11:00 | 2013-07-09 16:00 | 2013-07-08 09:00 | 2013-07-15 10:00 | 2013-07-12 15:00 | 2512484.4458 | 2505457.8871 | 2569180.3205 | 2591132.9561 | 2561720.1991 | 2583504.9593 | 2517527.5812 | 2521394.9361 | 0.92115 | 1.0077 | 0.94188 | 0.9478 | -5.125 | 1.0077 | 1 | 0.92115 | 1
24/05, 2013 | 2013-04-12 17:00 | 2013-05-24 17:00 | 2335722.3871 | 2071298.3524 | 2070923.0662 | 2013-05-08 12:00 | -264424.0347 | 88.68% | 375.2863 | 100% | -12d 4h | 86.84% | 95.12% | 2013-07-17 14:00 | 2013-07-22 11:00 | 2013-07-22 10:00 | 2013-07-15 15:00 | 2013-07-22 11:00 | 2013-07-22 10:00 | 2013-07-17 12:00 | 2013-07-25 09:00 | 2013-07-25 09:00 | 2524389.8993 | 2524307.7383 | 2582279.9321 | 2593096.9952 | 2582187.2824 | 2593002.3856 | 2534826.2178 | 2536576.4277 | 0.86842 | 1.0002 | 0.88679 | 0.95118 | -12.5 | 1.0002 | 1 | 0.86842 | 1
08/07, 2013 | 2013-05-24 17:00 | 2013-07-08 09:00 | 2524765.1855 | 2389930.0712 | 2428840.7484 | 2013-06-03 09:00 | -134835.1143 | 94.66% | -38910.6772 | 98.4% | -25d | 80.02% | 96.48% | 2013-07-09 11:00 | 2013-07-09 15:00 | 2013-07-11 16:00 | 2013-07-16 15:00 | 2013-07-17 09:00 | 2013-07-17 10:00 | 2013-08-02 17:00 | 2013-08-09 17:00 | 2013-08-12 11:00 | 2563675.8627 | 2565871.126 | 2571282.9924 | 2597342.5579 | 2573602.1081 | 2600085.9518 | 2566920.3489 | 2571188.4406 | 0.8002 | 0.98398 | 0.94659 | 0.96476 | -25 | 0.98398 | 1 | 0.8002 | 1
Actual Schedule | 2013-07-08 09:00 | 2013-07-15 17:00 | 2524765.1855 | 2524765.1855 | 2563675.8643 | 2013-06-28 17:00 | 0 | 100% | -38910.6787 | 98.48% | -11d | 91.6% | 100% | 2013-06-28 17:00 | 2013-06-28 17:00 | 2013-07-02 16:00 | 2013-07-15 17:00 | 2013-07-15 17:00 | 2013-07-15 17:00 | 2013-07-15 17:00 | 2013-07-15 17:00 | 2013-07-15 17:00 | 2563675.8643 | 2563675.8643 | 2563675.8643 | 2563675.8643 | 2563675.8643 | 2563675.8643 | 2563675.8643 | 2563675.8643 | 0.91603 | 0.98482 | 1 | 1 | -11 | 0.98482 | 1 | 0.91603 | 1