## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Broker Account Conversion System | 1 |  |  | 2013-11-28 08:00 | 2014-05-09 17:00 | 117d |  |  | 0 |  |  | 12735 | 162.375
25 | supporting tasks | 1.1 |  |  | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h |  |  | 0 |  |  | 3060 | 6.0833
1 | project management | 1.1.1 |  | FS20 | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 6.0833
26 | requirements | 1.2 |  |  | 2014-01-10 08:00 | 2014-01-30 17:00 | 15d |  |  | 0 |  |  | 150 | 20.375
2 | requirements | 1.2.1 |  | FS3 | 2014-01-10 08:00 | 2014-01-10 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 0.083333
3 | requirements validated | 1.2.2 | 2FS | FS20 | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
27 | analysis | 1.3 |  |  | 2014-01-31 08:00 | 2014-02-18 17:00 | 13d |  |  | 0 |  |  | 150 | 18.375
4 | analysis - solution concept | 1.3.1 |  | FS5 | 2014-01-31 08:00 | 2014-01-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 0.083333
5 | analysis validated | 1.3.2 | 4FS | FS20 | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
28 | design | 1.4 |  |  | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  |  | 0 |  |  | 150 | 5.375
6 | design - data design upload passieve makelaars | 1.4.1 |  | FS7 | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 0.041667
33 | design - data design upload passieve makelaars | 1.4.2 |  | FS7 | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 0.041667
7 | design validated | 1.4.3 | 6FS;33FS | FS20 | 2014-01-29 17:00 | 2014-01-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | development | 1.5 |  |  | 2014-01-24 08:00 | 2014-03-21 17:00 | 41d |  |  | 0 |  |  | 4650 | 56.375
8 | development - TAT testing | 1.5.1 |  | FS11 | 2014-01-24 08:00 | 2014-01-28 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 4.1667
9 | development - TAT testing | 1.5.2 |  | FS11 | 2014-01-24 08:00 | 2014-01-29 11:00 | 3d 3h | Employee E | 2025 | 0 | 0 | 0 | 2025 | 5.125
10 | development - TAT testing | 1.5.3 |  | FS11 | 2014-01-24 08:00 | 2014-01-27 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 3.3333
11 | development completed | 1.5.4 | 8FS;9FS;10FS | FS20 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
30 | test ict | 1.6 |  |  | 2014-01-31 08:00 | 2014-04-04 17:00 | 46d |  |  | 0 |  |  | 3600 | 63.375
12 | test ict - build bugfixing | 1.6.1 | 16FS | FS17 | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 0.375
13 | test ict - build bugfixing | 1.6.2 | 16FS | FS17 | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 0.375
14 | test ict - test coordination | 1.6.3 |  | FS16 | 2014-01-31 08:00 | 2014-02-03 09:00 | 1d 1h | Employee G | 675 | 0 | 0 | 0 | 675 | 3.0417
15 | test ict - test execution | 1.6.4 | 16FS | FS17 | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 1.3333
16 | test ict - test preparation | 1.6.5 | 14FS | FS12;FS13;FS15 | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 0.375
17 | ict test completed | 1.6.6 | 12FS;13FS;15FS | FS20 | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
31 | implementation | 1.7 |  |  | 2014-05-05 08:00 | 2014-05-09 17:00 | 5d |  |  | 0 |  |  | 975 | 4.375
18 | implementation - preparation | 1.7.1 |  | FS20 | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 0.375
34 | implementation - preparation | 1.7.2 |  | FS20 | 2014-05-05 08:00 | 2014-05-05 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 0.041667
19 | implementation - preparation | 1.7.3 |  | FS20 | 2014-05-05 08:00 | 2014-05-05 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 0.16667
20 | go live | 1.7.4 | 18FS;19FS;3FS;1FS;5FS;7FS;11FS;17FS;34FS |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 3060
2 | Employee B | Renewable | 1 | 0 | 75 | 2;4;33; | 375
3 | Employee C | Renewable | 1 | 0 | 75 | 6; | 75
4 | Employee D | Renewable | 1 | 0 | 75 | 8;12;34; | 2175
5 | Employee E | Renewable | 1 | 0 | 75 | 9;13;18; | 3225
6 | Employee F | Renewable | 1 | 0 | 75 | 10;19; | 1425
7 | Employee G | Renewable | 1 | 0 | 75 | 14;15;16; | 2400

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Broker Account Conversion System | 936h |  |  |  |  | 99 | 100 | 101
25 | supporting tasks | 34h |  |  |  |  | 99 | 100 | 101
1 | project management | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | requirements | 120h |  |  |  |  | 99 | 100 | 101
2 | requirements | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | requirements validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | analysis | 104h |  |  |  |  | 99 | 100 | 101
4 | analysis - solution concept | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | design | 32h |  |  |  |  | 99 | 100 | 101
6 | design - data design upload passieve makelaars | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | design - data design upload passieve makelaars | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | development | 328h |  |  |  |  | 99 | 100 | 101
8 | development - TAT testing | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | development - TAT testing | 27h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | development - TAT testing | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | test ict | 368h |  |  |  |  | 99 | 100 | 101
12 | test ict - build bugfixing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | test ict - build bugfixing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | test ict - test coordination | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | test ict - test execution | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | test ict - test preparation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | implementation | 40h |  |  |  |  | 99 | 100 | 101
18 | implementation - preparation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | implementation - preparation | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | implementation - preparation | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-01-20 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Broker Account Conversion System | 2013-11-28 08:00 | 2014-05-09 17:00 | 117d |  |  | 0 |  |  | 12735 |  | 38d | [5 empty] | 1185 |  | 10.04% |  | 1278 | 3210
25 | supporting tasks | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h |  |  | 0 |  |  | 3060 |  | 38d | [5 empty] | 810 |  | 30% |  | 918 | 3060
1 | project management | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2013-11-28 08:00 | 1d 1h | 810 | 720 | 1d | 0 | 0 | 810 | 720 | 30% | Started | 918 | 3060 | 100 | 26.4706 | 30 | 100 | 26.4706 | 30
26 | requirements | 2014-01-10 08:00 | 2014-01-30 17:00 | 15d |  |  | 0 |  |  | 150 |  | 11d | [5 empty] | 150 |  | 100% |  | 150 | 150
2 | requirements | 2014-01-10 08:00 | 2014-01-10 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-06 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
3 | requirements validated | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | analysis | 2014-01-31 08:00 | 2014-02-18 17:00 | 13d |  |  | 0 |  |  | 150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | analysis - solution concept | 2014-01-31 08:00 | 2014-01-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | analysis validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | design | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  |  | 0 |  |  | 150 |  | 1d | [5 empty] | 75 |  | 50% |  | 75 | 0
6 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-01-20 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 0 | 100 | 100 | 100 | 100 | 100 | 100
33 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | design validated | 2014-01-29 17:00 | 2014-01-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | development | 2014-01-24 08:00 | 2014-03-21 17:00 | 41d |  |  | 0 |  |  | 4650 |  | 1d | [5 empty] | 150 |  | 2.903% |  | 135 | 0
8 | development - TAT testing | 2014-01-24 08:00 | 2014-01-28 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | development - TAT testing | 2014-01-24 08:00 | 2014-01-29 11:00 | 3d 3h | Employee E | 2025 | 0 | 0 | 0 | 2025 |  | 0 | 0 | 2025 | 3d 3h | 0 | 0 | 0 | 2025 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | development - TAT testing | 2014-01-24 08:00 | 2014-01-27 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-01-20 08:00 | 2h | 150 | 450 | 6h | 0 | 0 | 150 | 450 | 12% | Started | 135 | 0 | 100 | 13.3333 | 12 | 100 | 13.3333 | 12
11 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | test ict | 2014-01-31 08:00 | 2014-04-04 17:00 | 46d |  |  | 0 |  |  | 3600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | test ict - test coordination | 2014-01-31 08:00 | 2014-02-03 09:00 | 1d 1h | Employee G | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | test ict - test execution | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | test ict - test preparation | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | ict test completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | implementation | 2014-05-05 08:00 | 2014-05-09 17:00 | 5d |  |  | 0 |  |  | 975 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-02-17 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Broker Account Conversion System | 2013-11-28 08:00 | 2014-05-09 17:00 | 117d |  |  | 0 |  |  | 12735 |  | 58d 7h | [5 empty] | 4560 |  | 45.16% |  | 5750.7 | 8835
25 | supporting tasks | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h |  |  | 0 |  |  | 3060 |  | 58d | [5 empty] | 1710 |  | 62% |  | 1897.2 | 3060
1 | project management | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2013-11-28 08:00 | 2d 3h | 1710 | 90 | 1h | 0 | 0 | 1710 | 90 | 62% | Started | 1897.2 | 3060 | 100 | 55.8824 | 62 | 100 | 55.8824 | 62
26 | requirements | 2014-01-10 08:00 | 2014-01-30 17:00 | 15d |  |  | 0 |  |  | 150 |  | 18d 7h | [5 empty] | 150 |  | 100% |  | 150 | 150
2 | requirements | 2014-01-10 08:00 | 2014-01-10 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-06 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
3 | requirements validated | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | analysis | 2014-01-31 08:00 | 2014-02-18 17:00 | 13d |  |  | 0 |  |  | 150 |  | 16d | [5 empty] | 150 |  | 100% |  | 150 | 150
4 | analysis - solution concept | 2014-01-31 08:00 | 2014-01-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-27 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
5 | analysis validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | design | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  |  | 0 |  |  | 150 |  | 21d | [5 empty] | 75 |  | 50% |  | 75 | 150
6 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-01-20 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
33 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 75 | 100 |  | 0 | 100 |  | 0
7 | design validated | 2014-01-29 17:00 | 2014-01-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | development | 2014-01-24 08:00 | 2014-03-21 17:00 | 41d |  |  | 0 |  |  | 4650 |  | 21d 7h | [5 empty] | 2400 |  | 73.06% |  | 3397.5 | 4650
8 | development - TAT testing | 2014-01-24 08:00 | 2014-01-28 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2014-02-03 08:00 | 1d 1h | 675 | 750 | 1d 2h | 0 | 0 | 675 | 750 | 45% | Started | 675 | 1500 | 100 | 45 | 45 | 100 | 45 | 45
9 | development - TAT testing | 2014-01-24 08:00 | 2014-01-29 11:00 | 3d 3h | Employee E | 2025 | 0 | 0 | 0 | 2025 | 2014-02-17 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 2025 | 2025 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
10 | development - TAT testing | 2014-01-24 08:00 | 2014-01-27 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-01-20 08:00 | 1d | 600 | 75 | 1h | 0 | 0 | 600 | 75 | 62% | Started | 697.5 | 1125 | 100 | 53.3333 | 62 | 100 | 53.3333 | 62
11 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | test ict | 2014-01-31 08:00 | 2014-04-04 17:00 | 46d |  |  | 0 |  |  | 3600 |  | 16d | [5 empty] | 75 |  | 2.25% |  | 81 | 675
12 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | test ict - test coordination | 2014-01-31 08:00 | 2014-02-03 09:00 | 1d 1h | Employee G | 675 | 0 | 0 | 0 | 675 | 2014-01-27 08:00 | 1h | 75 | 450 | 6h | 0 | 0 | 75 | 450 | 12% | Started | 81 | 675 | 100 | 11.1111 | 12 | 100 | 11.1111 | 12
15 | test ict - test execution | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | test ict - test preparation | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | ict test completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | implementation | 2014-05-05 08:00 | 2014-05-09 17:00 | 5d |  |  | 0 |  |  | 975 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-03-31 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Broker Account Conversion System | 2013-11-28 08:00 | 2014-05-09 17:00 | 117d |  |  | 0 |  |  | 12735 |  | 88d | [5 empty] | 8790 |  | 85.16% |  | 10845.1499 | 11760
25 | supporting tasks | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h |  |  | 0 |  |  | 3060 |  | 88d | [5 empty] | 2340 |  | 84% |  | 2570.3999 | 3060
1 | project management | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2013-11-28 08:00 | 3d 2h | 2340 | 90 | 1h | 0 | 0 | 2340 | 90 | 84% | Started | 2570.3999 | 3060 | 100 | 76.4706 | 84 | 100 | 76.4706 | 84
26 | requirements | 2014-01-10 08:00 | 2014-01-30 17:00 | 15d |  |  | 0 |  |  | 150 |  | 18d 7h | [5 empty] | 150 |  | 100% |  | 150 | 150
2 | requirements | 2014-01-10 08:00 | 2014-01-10 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-06 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
3 | requirements validated | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | analysis | 2014-01-31 08:00 | 2014-02-18 17:00 | 13d |  |  | 0 |  |  | 150 |  | 16d 7h | [5 empty] | 150 |  | 100% |  | 150 | 150
4 | analysis - solution concept | 2014-01-31 08:00 | 2014-01-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-27 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
5 | analysis validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | design | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  |  | 0 |  |  | 150 |  | 51d | [5 empty] | 75 |  | 50% |  | 75 | 150
6 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-01-20 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
33 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 75 | 100 |  | 0 | 100 |  | 0
7 | design validated | 2014-01-29 17:00 | 2014-01-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | development | 2014-01-24 08:00 | 2014-03-21 17:00 | 41d |  |  | 0 |  |  | 4650 |  | 44d 7h | [5 empty] | 3600 |  | 100% |  | 4650 | 4650
8 | development - TAT testing | 2014-01-24 08:00 | 2014-01-28 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2014-02-03 08:00 | 2d 4h | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
9 | development - TAT testing | 2014-01-24 08:00 | 2014-01-29 11:00 | 3d 3h | Employee E | 2025 | 0 | 0 | 0 | 2025 | 2014-02-17 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 2025 | 2025 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
10 | development - TAT testing | 2014-01-24 08:00 | 2014-01-27 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-01-20 08:00 | 1d 5h | 975 | 0 | 0 | 0 | 0 | 975 | 0 | 100% | Finished | 1125 | 1125 | 100 | 86.6667 | 100 | 100 | 86.6667 | 100
11 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | test ict | 2014-01-31 08:00 | 2014-04-04 17:00 | 46d |  |  | 0 |  |  | 3600 |  | 46d | [5 empty] | 2250 |  | 88.96% |  | 3202.5 | 3600
12 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 4h | 300 | 300 | 4h | 0 | 0 | 300 | 300 | 54% | Started | 324 | 600 | 100 | 50 | 54 | 100 | 50 | 54
13 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
14 | test ict - test coordination | 2014-01-31 08:00 | 2014-02-03 09:00 | 1d 1h | Employee G | 675 | 0 | 0 | 0 | 675 | 2014-01-27 08:00 | 1d | 600 | 75 | 1h | 0 | 0 | 600 | 75 | 82% | Started | 553.5 | 675 | 100 | 88.8889 | 82 | 100 | 88.8889 | 82
15 | test ict - test execution | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 1125 | 1125 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
16 | test ict - test preparation | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 600 | 600 | 100 | 150 | 100 | 100 | 150 | 100
17 | ict test completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | implementation | 2014-05-05 08:00 | 2014-05-09 17:00 | 5d |  |  | 0 |  |  | 975 |  | 6d | [5 empty] | 225 |  | 4.846% |  | 47.25 | 0
18 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-03-24 08:00 | 3h | 225 | 375 | 5h | 0 | 0 | 225 | 375 | 63% | Started | 47.25 | 0 | 100 | 300 | 63 | 100 | 300 | 63
19 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-05-12 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Broker Account Conversion System | 2013-11-28 08:00 | 2014-05-09 17:00 | 117d |  |  | 0 |  |  | 12735 |  | 116d 7h | [5 empty] | 9990 |  | 100% |  | 12735 | 12735
25 | supporting tasks | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h |  |  | 0 |  |  | 3060 |  | 3d 7h | [5 empty] | 2790 |  | 100% |  | 3060 | 3060
1 | project management | 2013-11-28 08:00 | 2013-12-04 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2013-11-28 08:00 | 3d 7h | 2790 | 0 | 0 | 0 | 0 | 2790 | 0 | 100% | Finished | 3060 | 3060 | 100 | 91.1765 | 100 | 100 | 91.1765 | 100
26 | requirements | 2014-01-10 08:00 | 2014-01-30 17:00 | 15d |  |  | 0 |  |  | 150 |  | 18d 7h | [5 empty] | 150 |  | 100% |  | 150 | 150
2 | requirements | 2014-01-10 08:00 | 2014-01-10 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-06 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
3 | requirements validated | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | analysis | 2014-01-31 08:00 | 2014-02-18 17:00 | 13d |  |  | 0 |  |  | 150 |  | 16d 7h | [5 empty] | 150 |  | 100% |  | 150 | 150
4 | analysis - solution concept | 2014-01-31 08:00 | 2014-01-31 10:00 | 2h | Employee B | 150 | 0 | 0 | 0 | 150 | 2014-01-27 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
5 | analysis validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | design | 2014-01-24 08:00 | 2014-01-29 17:00 | 4d |  |  | 0 |  |  | 150 |  | 65d 7h | [5 empty] | 300 |  | 100% |  | 150 | 150
6 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2014-01-20 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
33 | design - data design upload passieve makelaars | 2014-01-24 08:00 | 2014-01-24 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-04-21 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 75 | 75 | 100 | 300 | 100 | 100 | 300 | 100
7 | design validated | 2014-01-29 17:00 | 2014-01-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | development | 2014-01-24 08:00 | 2014-03-21 17:00 | 41d |  |  | 0 |  |  | 4650 |  | 44d 7h | [5 empty] | 3600 |  | 100% |  | 4650 | 4650
8 | development - TAT testing | 2014-01-24 08:00 | 2014-01-28 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2014-02-03 08:00 | 2d 4h | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
9 | development - TAT testing | 2014-01-24 08:00 | 2014-01-29 11:00 | 3d 3h | Employee E | 2025 | 0 | 0 | 0 | 2025 | 2014-02-17 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 2025 | 2025 | 100 | 55.5556 | 100 | 100 | 55.5556 | 100
10 | development - TAT testing | 2014-01-24 08:00 | 2014-01-27 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2014-01-20 08:00 | 1d 5h | 975 | 0 | 0 | 0 | 0 | 975 | 0 | 100% | Finished | 1125 | 1125 | 100 | 86.6667 | 100 | 100 | 86.6667 | 100
11 | development completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | test ict | 2014-01-31 08:00 | 2014-04-04 17:00 | 46d |  |  | 0 |  |  | 3600 |  | 60d 7h | [5 empty] | 2550 |  | 100% |  | 3600 | 3600
12 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee D | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 600 | 600 | 100 | 87.5 | 100 | 100 | 87.5 | 100
13 | test ict - build bugfixing | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
14 | test ict - test coordination | 2014-01-31 08:00 | 2014-02-03 09:00 | 1d 1h | Employee G | 675 | 0 | 0 | 0 | 675 | 2014-01-27 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
15 | test ict - test execution | 2014-03-24 08:00 | 2014-03-25 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 1125 | 1125 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
16 | test ict - test preparation | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 600 | 600 | 100 | 150 | 100 | 100 | 150 | 100
17 | ict test completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
31 | implementation | 2014-05-05 08:00 | 2014-05-09 17:00 | 5d |  |  | 0 |  |  | 975 |  | 34d 7h | [5 empty] | 450 |  | 100% |  | 975 | 975
18 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-05-05 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
34 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-03-24 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 75 | 75 | 100 | 400 | 100 | 100 | 400 | 100
19 | implementation - preparation | 2014-05-05 08:00 | 2014-05-05 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-04-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
20 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-11-28 08:00 | 2014-01-20 22:00 | 3210 | 1278 | 1185 | 2013-11-29 15:00 | -1932 | 39.81% | 93 | 107.8% | -36d 2h | 4.605% | 72.86% | 2014-06-04 15:00 | 2015-01-13 16:00 | 2014-12-15 12:00 | 2014-06-11 16:00 | 2015-01-13 16:00 | 2014-12-18 10:00 | 2014-07-01 10:00 | 2023-08-24 14:00 | 2022-12-13 12:00 | 12642 | 11808.2743 | 29961.971 | 249965.5707 | 27867.8715 | 231861.8142 | 13342.1161 | 14323.8314 | 0.046053 | 1.0785 | 0.39813 | 0.72857 | -36.25 | 1.0785 | 1 | 0.046053 | 1
Tracking 2 | 2014-01-20 22:00 | 2014-02-17 22:00 | 8835 | 5750.7 | 4560 | 2014-01-27 10:00 | -3084.3 | 65.09% | 1190.7 | 126.1% | -15d 6h | 72.84% | 75.66% | 2014-06-19 11:00 | 2014-08-06 15:00 | 2014-06-16 12:00 | 2014-06-09 10:00 | 2014-08-06 15:00 | 2014-07-02 12:00 | 2014-06-02 15:00 | 2014-07-10 14:00 | 2014-06-11 11:00 | 11544.3 | 10098.1794 | 15290.2225 | 14147.9148 | 13068.4972 | 12162.7077 | 10691.5557 | 10609.1897 | 0.72845 | 1.2611 | 0.6509 | 0.75663 | -15.75 | 1.2611 | 1 | 0.72845 | 1
Tracking 3 | 2014-02-17 22:00 | 2014-03-31 22:00 | 11760 | 10845.1499 | 8790 | 2014-03-24 15:00 | -914.8501 | 92.22% | 2055.1499 | 123.4% | -5d 2h | 94.03% | 92.47% | 2014-05-22 11:00 | 2014-05-23 16:00 | 2014-04-21 16:00 | 2014-05-20 16:00 | 2014-05-23 16:00 | 2014-05-14 12:00 | 2014-05-19 10:00 | 2014-05-21 11:00 | 2014-05-12 12:00 | 10679.8501 | 10321.7245 | 10839.2697 | 10799.7499 | 10450.9342 | 10418.9034 | 10403.208 | 10398.229 | 0.94034 | 1.2338 | 0.92221 | 0.9247 | -5.25 | 1.2338 | 1 | 0.94034 | 1
Closure | 2014-03-31 22:00 | 2014-05-12 08:00 | 12735 | 12735 | 9990 | 2014-05-09 17:00 | 0 | 100% | 2745 | 127.5% | 0 | 100% | 100% | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-04-04 15:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 9990 | 9990 | 9990 | 9990 | 9990 | 9990 | 9990 | 9990 | 1 | 1.2748 | 1 | 1 | 0 | 1.2748 | 1 | 1 | 1