## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Supplementary Pensions Database | 1 |  |  | 2013-11-19 08:00 | 2014-05-12 09:00 | 124d 1h |  |  | 0 |  |  | 34260 | 174.0417
25 | supporting tasks | 1.1 |  |  | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h |  |  | 0 |  |  | 4320 | 6.1667
1 | project management | 1.1.1 |  | FS23 | 2013-11-19 08:00 | 2013-11-21 10:00 | 2d 2h | Employee F | 1620 | 0 | 0 | 0 | 1620 | 2.0833
2 | project management | 1.1.2 |  | FS23 | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h | Employee G | 2700 | 0 | 0 | 0 | 2700 | 6.1667
26 | requirements | 1.2 |  |  | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h |  |  | 0 |  |  | 225 | 0.083333
3 | requirements | 1.2.1 |  | FS23 | 2013-12-02 08:00 | 2013-12-02 09:00 | 1h | Employee I | 75 | 0 | 0 | 0 | 75 | 0.041667
4 | requirements | 1.2.2 |  | FS23 | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee G | 150 | 0 | 0 | 0 | 150 | 0.083333
27 | analysis | 1.3 |  |  | 2014-01-31 16:00 | 2014-03-06 17:00 | 24d 1h |  |  | 0 |  |  | 3975 | 34.0417
5 | analysis - functioneel | 1.3.1 | 7FS | FS8 | 2014-02-03 08:00 | 2014-02-10 09:00 | 5d 1h | Employee A | 3075 | 0 | 0 | 0 | 3075 | 7.0417
6 | analysis - functioneel | 1.3.2 | 7FS | FS8 | 2014-02-03 08:00 | 2014-02-04 11:00 | 1d 3h | Employee G | 825 | 0 | 0 | 0 | 825 | 1.125
7 | analysis - support by code & test | 1.3.3 |  | FS5;FS6 | 2014-01-31 16:00 | 2014-01-31 17:00 | 1h | Employee G | 75 | 0 | 0 | 0 | 75 | 0.041667
8 | analysis validated | 1.3.4 | 5FS;6FS | FS23 | 2014-03-06 17:00 | 2014-03-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
28 | design | 1.4 |  |  | 2014-03-10 08:00 | 2014-03-28 17:00 | 15d |  |  | 0 |  |  | 3870 | 18.375
9 | design - AIA | 1.4.1 |  | FS10 | 2014-03-10 08:00 | 2014-03-17 11:00 | 5d 3h | Employee F | 3870 | 0 | 0 | 0 | 3870 | 7.125
10 | design validated | 1.4.2 | 9FS |  | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | development | 1.5 |  |  | 2014-03-03 08:00 | 2014-04-04 17:00 | 25d |  |  | 0 |  |  | 9495 | 32.375
11 | development - AIA | 1.5.1 | 12FS | FS13 | 2014-03-24 08:00 | 2014-04-01 14:00 | 6d 5h | Employee F | 4770 | 0 | 0 | 0 | 4770 | 8.25
12 | development - progress | 1.5.2 |  | FS11 | 2014-03-03 08:00 | 2014-03-12 16:00 | 7d 7h | Employee D | 4725 | 0 | 0 | 0 | 4725 | 9.3333
13 | development completed | 1.5.3 | 11FS | FS23 | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
30 | build | 1.6 |  |  | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 2325 | 16.375
14 | build - bugfixing | 1.6.1 |  | FS16 | 2014-04-14 08:00 | 2014-04-16 11:00 | 2d 3h | Employee J | 1425 | 0 | 0 | 0 | 1425 | 2.125
15 | build - bugfixing | 1.6.2 |  | FS16 | 2014-04-14 08:00 | 2014-04-15 12:00 | 1d 4h | Employee D | 900 | 0 | 0 | 0 | 900 | 1.1667
16 | build completed | 1.6.3 | 14FS;15FS | FS23 | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
31 | ict test | 1.7 |  |  | 2014-02-26 08:00 | 2014-04-24 17:00 | 42d |  |  | 0 |  |  | 9975 | 57.375
17 | test coordination | 1.7.1 | 20FS | FS18;FS19 | 2014-03-10 08:00 | 2014-03-11 09:00 | 1d 1h | Employee L | 675 | 0 | 0 | 0 | 675 | 1.0417
18 | test execution | 1.7.2 | 17FS | FS21 | 2014-03-31 08:00 | 2014-04-03 15:00 | 3d 6h | Employee F | 2700 | 0 | 0 | 0 | 2700 | 3.2917
19 | test execution | 1.7.3 | 17FS | FS21 | 2014-03-31 08:00 | 2014-04-07 14:00 | 5d 5h | Employee M | 3375 | 0 | 0 | 0 | 3375 | 7.25
20 | test preparation | 1.7.4 |  | FS17 | 2014-02-26 08:00 | 2014-03-05 11:00 | 5d 3h | Employee M | 3225 | 0 | 0 | 0 | 3225 | 7.125
21 | ict test completed | 1.7.5 | 18FS;19FS | FS23 | 2014-04-24 17:00 | 2014-04-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
32 | implementation | 1.8 |  |  | 2014-04-25 17:00 | 2014-05-09 17:00 | 10d |  |  | 0 |  |  | 0 | 14
22 | code freeze | 1.8.1 |  | FS23 | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
23 | go live | 1.8.2 | 22FS;21FS;16FS;13FS;8FS;1FS;2FS;3FS;4FS |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
33 | post implementation | 1.9 |  |  | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h |  |  | 0 |  |  | 75 | 0.041667
24 | post implementation - post go live support | 1.9.1 |  |  | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 0.041667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 75 | 5; | 3075
2 | Employee B | Renewable | 1 | 0 | 75 |  | 0
3 | Employee C | Renewable | 1 | 0 | 75 |  | 0
4 | Employee D | Renewable | 1 | 0 | 75 | 12;15;24; | 5700
5 | Employee E | Renewable | 1 | 0 | 75 |  | 0
6 | Employee F | Renewable | 1 | 0 | 90 | 1;9;11;18; | 12960
7 | Employee G | Renewable | 1 | 0 | 75 | 2;4;6;7; | 3750
8 | Employee H | Renewable | 1 | 0 | 75 |  | 0
9 | Employee I | Renewable | 1 | 0 | 75 | 3; | 75
10 | Employee J | Renewable | 1 | 0 | 75 | 14; | 1425
11 | Employee K | Renewable | 1 | 0 | 75 |  | 0
12 | Employee L | Renewable | 1 | 0 | 75 | 17; | 675
13 | Employee M | Renewable | 1 | 0 | 75 | 19;20; | 6600

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Supplementary Pensions Database | 993h |  |  |  |  | 99 | 100 | 101
25 | supporting tasks | 36h |  |  |  |  | 99 | 100 | 101
1 | project management | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | project management | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | requirements | 2h |  |  |  |  | 99 | 100 | 101
3 | requirements | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | requirements | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | analysis | 193h |  |  |  |  | 99 | 100 | 101
5 | analysis - functioneel | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | analysis - functioneel | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | analysis - support by code & test | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | design | 120h |  |  |  |  | 99 | 100 | 101
9 | design - AIA | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | development | 200h |  |  |  |  | 99 | 100 | 101
11 | development - AIA | 53h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | development - progress | 63h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | build | 104h |  |  |  |  | 99 | 100 | 101
14 | build - bugfixing | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | build - bugfixing | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | build completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | ict test | 336h |  |  |  |  | 99 | 100 | 101
17 | test coordination | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | test execution | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | test execution | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | test preparation | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | implementation | 80h |  |  |  |  | 99 | 100 | 101
22 | code freeze | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | post implementation | 1h |  |  |  |  | 99 | 100 | 101
24 | post implementation - post go live support | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-01-20 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Supplementary Pensions Database | 2013-11-19 08:00 | 2014-05-12 09:00 | 124d 1h |  |  | 0 |  |  | 34260 |  | 45d | [5 empty] | 600 |  | 3.687% |  | 1263 | 4545
25 | supporting tasks | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h |  |  | 0 |  |  | 4320 |  | 45d | [5 empty] | 525 |  | 27.5% |  | 1188 | 4320
1 | project management | 2013-11-19 08:00 | 2013-11-21 10:00 | 2d 2h | Employee F | 1620 | 0 | 0 | 0 | 1620 |  | 0 | 0 | 1620 | 2d 2h | 0 | 0 | 0 | 1620 | 0% | Not Started | 0 | 1620 | 100 |  | 0 | 100 |  | 0
2 | project management | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h | Employee G | 2700 | 0 | 0 | 0 | 2700 | 2013-11-19 08:00 | 7h | 525 | 975 | 1d 5h | 0 | 0 | 525 | 975 | 44% | Started | 1188 | 2700 | 100 | 19.4444 | 44 | 100 | 19.4444 | 44
26 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h |  |  | 0 |  |  | 225 |  | 36d | [5 empty] | 75 |  | 33.33% |  | 75 | 225
3 | requirements | 2013-12-02 08:00 | 2013-12-02 09:00 | 1h | Employee I | 75 | 0 | 0 | 0 | 75 | 2013-12-02 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
4 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee G | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 150 | 100 |  | 0 | 100 |  | 0
27 | analysis | 2014-01-31 16:00 | 2014-03-06 17:00 | 24d 1h |  |  | 0 |  |  | 3975 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
5 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-10 09:00 | 5d 1h | Employee A | 3075 | 0 | 0 | 0 | 3075 |  | 0 | 0 | 3075 | 5d 1h | 0 | 0 | 0 | 3075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-04 11:00 | 1d 3h | Employee G | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | analysis - support by code & test | 2014-01-31 16:00 | 2014-01-31 17:00 | 1h | Employee G | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | analysis validated | 2014-03-06 17:00 | 2014-03-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | design | 2014-03-10 08:00 | 2014-03-28 17:00 | 15d |  |  | 0 |  |  | 3870 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | design - AIA | 2014-03-10 08:00 | 2014-03-17 11:00 | 5d 3h | Employee F | 3870 | 0 | 0 | 0 | 3870 |  | 0 | 0 | 3870 | 5d 3h | 0 | 0 | 0 | 3870 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | design validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | development | 2014-03-03 08:00 | 2014-04-04 17:00 | 25d |  |  | 0 |  |  | 9495 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | development - AIA | 2014-03-24 08:00 | 2014-04-01 14:00 | 6d 5h | Employee F | 4770 | 0 | 0 | 0 | 4770 |  | 0 | 0 | 4770 | 6d 5h | 0 | 0 | 0 | 4770 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | development - progress | 2014-03-03 08:00 | 2014-03-12 16:00 | 7d 7h | Employee D | 4725 | 0 | 0 | 0 | 4725 |  | 0 | 0 | 4725 | 7d 7h | 0 | 0 | 0 | 4725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | development completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | build | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | build - bugfixing | 2014-04-14 08:00 | 2014-04-16 11:00 | 2d 3h | Employee J | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | build - bugfixing | 2014-04-14 08:00 | 2014-04-15 12:00 | 1d 4h | Employee D | 900 | 0 | 0 | 0 | 900 |  | 0 | 0 | 900 | 1d 4h | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | build completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | ict test | 2014-02-26 08:00 | 2014-04-24 17:00 | 42d |  |  | 0 |  |  | 9975 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | test coordination | 2014-03-10 08:00 | 2014-03-11 09:00 | 1d 1h | Employee L | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | test execution | 2014-03-31 08:00 | 2014-04-03 15:00 | 3d 6h | Employee F | 2700 | 0 | 0 | 0 | 2700 |  | 0 | 0 | 2700 | 3d 6h | 0 | 0 | 0 | 2700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | test execution | 2014-03-31 08:00 | 2014-04-07 14:00 | 5d 5h | Employee M | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | test preparation | 2014-02-26 08:00 | 2014-03-05 11:00 | 5d 3h | Employee M | 3225 | 0 | 0 | 0 | 3225 |  | 0 | 0 | 3225 | 5d 3h | 0 | 0 | 0 | 3225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | ict test completed | 2014-04-24 17:00 | 2014-04-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | implementation | 2014-04-25 17:00 | 2014-05-09 17:00 | 10d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | post implementation | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h |  |  | 0 |  |  | 75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-02-24 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Supplementary Pensions Database | 2013-11-19 08:00 | 2014-05-12 09:00 | 124d 1h |  |  | 0 |  |  | 34260 |  | 70d | [5 empty] | 4875 |  | 15.91% |  | 5450.9999 | 8520
25 | supporting tasks | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h |  |  | 0 |  |  | 4320 |  | 70d | [5 empty] | 975 |  | 50.63% |  | 2187 | 4320
1 | project management | 2013-11-19 08:00 | 2013-11-21 10:00 | 2d 2h | Employee F | 1620 | 0 | 0 | 0 | 1620 |  | 0 | 0 | 1620 | 2d 2h | 0 | 0 | 0 | 1620 | 0% | Not Started | 0 | 1620 | 100 |  | 0 | 100 |  | 0
2 | project management | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h | Employee G | 2700 | 0 | 0 | 0 | 2700 | 2013-11-19 08:00 | 1d 5h | 975 | 600 | 1d | 0 | 0 | 975 | 600 | 81% | Started | 2187 | 2700 | 100 | 36.1111 | 81 | 100 | 36.1111 | 81
26 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h |  |  | 0 |  |  | 225 |  | 61d | [5 empty] | 225 |  | 73.33% |  | 165 | 225
3 | requirements | 2013-12-02 08:00 | 2013-12-02 09:00 | 1h | Employee I | 75 | 0 | 0 | 0 | 75 | 2013-12-02 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
4 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee G | 150 | 0 | 0 | 0 | 150 | 2014-02-17 08:00 | 2h | 150 | 75 | 1h | 0 | 0 | 150 | 75 | 60% | Started | 90 | 150 | 100 | 100 | 60 | 100 | 100 | 60
27 | analysis | 2014-01-31 16:00 | 2014-03-06 17:00 | 24d 1h |  |  | 0 |  |  | 3975 |  | 16d | [5 empty] | 2475 |  | 60.11% |  | 2389.4999 | 3975
5 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-10 09:00 | 5d 1h | Employee A | 3075 | 0 | 0 | 0 | 3075 | 2014-02-03 08:00 | 4d | 2400 | 75 | 1h | 0 | 0 | 2400 | 75 | 77% | Started | 2367.7499 | 3075 | 100 | 78.0488 | 77 | 100 | 78.0488 | 77
6 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-04 11:00 | 1d 3h | Employee G | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 825 | 100 |  | 0 | 100 |  | 0
7 | analysis - support by code & test | 2014-01-31 16:00 | 2014-01-31 17:00 | 1h | Employee G | 75 | 0 | 0 | 0 | 75 | 2014-02-03 08:00 | 1h | 75 | 75 | 1h | 0 | 0 | 75 | 75 | 29% | Started | 21.75 | 75 | 100 | 100 | 29 | 100 | 100 | 29
8 | analysis validated | 2014-03-06 17:00 | 2014-03-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | design | 2014-03-10 08:00 | 2014-03-28 17:00 | 15d |  |  | 0 |  |  | 3870 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | design - AIA | 2014-03-10 08:00 | 2014-03-17 11:00 | 5d 3h | Employee F | 3870 | 0 | 0 | 0 | 3870 |  | 0 | 0 | 3870 | 5d 3h | 0 | 0 | 0 | 3870 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | design validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | development | 2014-03-03 08:00 | 2014-04-04 17:00 | 25d |  |  | 0 |  |  | 9495 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | development - AIA | 2014-03-24 08:00 | 2014-04-01 14:00 | 6d 5h | Employee F | 4770 | 0 | 0 | 0 | 4770 |  | 0 | 0 | 4770 | 6d 5h | 0 | 0 | 0 | 4770 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | development - progress | 2014-03-03 08:00 | 2014-03-12 16:00 | 7d 7h | Employee D | 4725 | 0 | 0 | 0 | 4725 |  | 0 | 0 | 4725 | 7d 7h | 0 | 0 | 0 | 4725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | development completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | build | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | build - bugfixing | 2014-04-14 08:00 | 2014-04-16 11:00 | 2d 3h | Employee J | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | build - bugfixing | 2014-04-14 08:00 | 2014-04-15 12:00 | 1d 4h | Employee D | 900 | 0 | 0 | 0 | 900 |  | 0 | 0 | 900 | 1d 4h | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | build completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | ict test | 2014-02-26 08:00 | 2014-04-24 17:00 | 42d |  |  | 0 |  |  | 9975 |  | 1d | [5 empty] | 1200 |  | 7.113% |  | 709.5 | 0
17 | test coordination | 2014-03-10 08:00 | 2014-03-11 09:00 | 1d 1h | Employee L | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | test execution | 2014-03-31 08:00 | 2014-04-03 15:00 | 3d 6h | Employee F | 2700 | 0 | 0 | 0 | 2700 |  | 0 | 0 | 2700 | 3d 6h | 0 | 0 | 0 | 2700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | test execution | 2014-03-31 08:00 | 2014-04-07 14:00 | 5d 5h | Employee M | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | test preparation | 2014-02-26 08:00 | 2014-03-05 11:00 | 5d 3h | Employee M | 3225 | 0 | 0 | 0 | 3225 | 2014-02-24 08:00 | 2d | 1200 | 450 | 6h | 0 | 0 | 1200 | 450 | 22% | Started | 709.5 | 0 | 100 | 37.2093 | 22 | 100 | 37.2093 | 22
21 | ict test completed | 2014-04-24 17:00 | 2014-04-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | implementation | 2014-04-25 17:00 | 2014-05-09 17:00 | 10d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | post implementation | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h |  |  | 0 |  |  | 75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-03-31 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Supplementary Pensions Database | 2013-11-19 08:00 | 2014-05-12 09:00 | 124d 1h |  |  | 0 |  |  | 34260 |  | 95d | [5 empty] | 14715 |  | 64.58% |  | 22125.1498 | 26655
25 | supporting tasks | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h |  |  | 0 |  |  | 4320 |  | 95d | [5 empty] | 2550 |  | 93.62% |  | 4044.6 | 4320
1 | project management | 2013-11-19 08:00 | 2013-11-21 10:00 | 2d 2h | Employee F | 1620 | 0 | 0 | 0 | 1620 | 2014-03-03 08:00 | 1d 7h | 1350 | 360 | 4h | 0 | 0 | 1350 | 360 | 83% | Started | 1344.6 | 1620 | 100 | 83.3333 | 83 | 100 | 83.3333 | 83
2 | project management | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h | Employee G | 2700 | 0 | 0 | 0 | 2700 | 2013-11-19 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 2700 | 2700 | 100 | 44.4444 | 100 | 100 | 44.4444 | 100
26 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h |  |  | 0 |  |  | 225 |  | 55d 3h | [5 empty] | 300 |  | 100% |  | 225 | 225
3 | requirements | 2013-12-02 08:00 | 2013-12-02 09:00 | 1h | Employee I | 75 | 0 | 0 | 0 | 75 | 2013-12-02 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
4 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee G | 150 | 0 | 0 | 0 | 150 | 2014-02-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 150 | 150 | 100 | 150 | 100 | 100 | 150 | 100
27 | analysis | 2014-01-31 16:00 | 2014-03-06 17:00 | 24d 1h |  |  | 0 |  |  | 3975 |  | 23d 7h | [5 empty] | 4200 |  | 100% |  | 3975 | 3975
5 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-10 09:00 | 5d 1h | Employee A | 3075 | 0 | 0 | 0 | 3075 | 2014-02-03 08:00 | 5d 1h | 3075 | 0 | 0 | 0 | 0 | 3075 | 0 | 100% | Finished | 3075 | 3075 | 100 | 100 | 100 | 100 | 100 | 100
6 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-04 11:00 | 1d 3h | Employee G | 825 | 0 | 0 | 0 | 825 | 2014-03-03 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 825 | 825 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - support by code & test | 2014-01-31 16:00 | 2014-01-31 17:00 | 1h | Employee G | 75 | 0 | 0 | 0 | 75 | 2014-02-03 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 75 | 75 | 100 | 400 | 100 | 100 | 400 | 100
8 | analysis validated | 2014-03-06 17:00 | 2014-03-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-06 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | design | 2014-03-10 08:00 | 2014-03-28 17:00 | 15d |  |  | 0 |  |  | 3870 |  | 21d | [5 empty] | 1800 |  | 84% |  | 3250.7999 | 3870
9 | design - AIA | 2014-03-10 08:00 | 2014-03-17 11:00 | 5d 3h | Employee F | 3870 | 0 | 0 | 0 | 3870 | 2014-03-03 08:00 | 2d 4h | 1800 | 2070 | 2d 7h | 0 | 0 | 1800 | 2070 | 84% | Started | 3250.7999 | 3870 | 100 | 46.5116 | 84 | 100 | 46.5116 | 84
10 | design validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | development | 2014-03-03 08:00 | 2014-04-04 17:00 | 25d |  |  | 0 |  |  | 9495 |  | 16d | [5 empty] | 825 |  | 49.76% |  | 4725 | 9045
11 | development - AIA | 2014-03-24 08:00 | 2014-04-01 14:00 | 6d 5h | Employee F | 4770 | 0 | 0 | 0 | 4770 |  | 0 | 0 | 4770 | 6d 5h | 0 | 0 | 0 | 4770 | 0% | Not Started | 0 | 4320 | 100 |  | 0 | 100 |  | 0
12 | development - progress | 2014-03-03 08:00 | 2014-03-12 16:00 | 7d 7h | Employee D | 4725 | 0 | 0 | 0 | 4725 | 2014-03-10 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 4725 | 4725 | 100 | 17.4603 | 100 | 100 | 17.4603 | 100
13 | development completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | build | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | build - bugfixing | 2014-04-14 08:00 | 2014-04-16 11:00 | 2d 3h | Employee J | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | build - bugfixing | 2014-04-14 08:00 | 2014-04-15 12:00 | 1d 4h | Employee D | 900 | 0 | 0 | 0 | 900 |  | 0 | 0 | 900 | 1d 4h | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | build completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | ict test | 2014-02-26 08:00 | 2014-04-24 17:00 | 42d |  |  | 0 |  |  | 9975 |  | 26d | [5 empty] | 5040 |  | 59.2% |  | 5904.75 | 5220
17 | test coordination | 2014-03-10 08:00 | 2014-03-11 09:00 | 1d 1h | Employee L | 675 | 0 | 0 | 0 | 675 | 2014-03-03 08:00 | 5h | 375 | 225 | 3h | 0 | 0 | 375 | 225 | 83% | Started | 560.25 | 675 | 100 | 55.5556 | 83 | 100 | 55.5556 | 83
18 | test execution | 2014-03-31 08:00 | 2014-04-03 15:00 | 3d 6h | Employee F | 2700 | 0 | 0 | 0 | 2700 | 2014-03-31 08:00 | 1h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 2700 | 720 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
19 | test execution | 2014-03-31 08:00 | 2014-04-07 14:00 | 5d 5h | Employee M | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
20 | test preparation | 2014-02-26 08:00 | 2014-03-05 11:00 | 5d 3h | Employee M | 3225 | 0 | 0 | 0 | 3225 | 2014-02-24 08:00 | 7d 5h | 4575 | 75 | 1h | 0 | 0 | 4575 | 75 | 82% | Started | 2644.5 | 3225 | 100 | 141.8605 | 82 | 100 | 141.8605 | 82
21 | ict test completed | 2014-04-24 17:00 | 2014-04-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | implementation | 2014-04-25 17:00 | 2014-05-09 17:00 | 10d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | post implementation | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h |  |  | 0 |  |  | 75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-05-12 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Supplementary Pensions Database | 2013-11-19 08:00 | 2014-05-12 09:00 | 124d 1h |  |  | 0 |  |  | 34260 |  | 123d 7h | [5 empty] | 18285 |  | 100% |  | 34260 | 34185
25 | supporting tasks | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h |  |  | 0 |  |  | 4320 |  | 76d 2h | [5 empty] | 2820 |  | 100% |  | 4320 | 4320
1 | project management | 2013-11-19 08:00 | 2013-11-21 10:00 | 2d 2h | Employee F | 1620 | 0 | 0 | 0 | 1620 | 2014-03-03 08:00 | 2d 2h | 1620 | 0 | 0 | 0 | 0 | 1620 | 0 | 100% | Finished | 1620 | 1620 | 100 | 100 | 100 | 100 | 100 | 100
2 | project management | 2013-11-19 08:00 | 2013-11-25 12:00 | 4d 4h | Employee G | 2700 | 0 | 0 | 0 | 2700 | 2013-11-19 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 2700 | 2700 | 100 | 44.4444 | 100 | 100 | 44.4444 | 100
26 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h |  |  | 0 |  |  | 225 |  | 55d 3h | [5 empty] | 300 |  | 100% |  | 225 | 225
3 | requirements | 2013-12-02 08:00 | 2013-12-02 09:00 | 1h | Employee I | 75 | 0 | 0 | 0 | 75 | 2013-12-02 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
4 | requirements | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee G | 150 | 0 | 0 | 0 | 150 | 2014-02-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 150 | 150 | 100 | 150 | 100 | 100 | 150 | 100
27 | analysis | 2014-01-31 16:00 | 2014-03-06 17:00 | 24d 1h |  |  | 0 |  |  | 3975 |  | 23d 7h | [5 empty] | 4200 |  | 100% |  | 3975 | 3975
5 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-10 09:00 | 5d 1h | Employee A | 3075 | 0 | 0 | 0 | 3075 | 2014-02-03 08:00 | 5d 1h | 3075 | 0 | 0 | 0 | 0 | 3075 | 0 | 100% | Finished | 3075 | 3075 | 100 | 100 | 100 | 100 | 100 | 100
6 | analysis - functioneel | 2014-02-03 08:00 | 2014-02-04 11:00 | 1d 3h | Employee G | 825 | 0 | 0 | 0 | 825 | 2014-03-03 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 825 | 825 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - support by code & test | 2014-01-31 16:00 | 2014-01-31 17:00 | 1h | Employee G | 75 | 0 | 0 | 0 | 75 | 2014-02-03 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 75 | 75 | 100 | 400 | 100 | 100 | 400 | 100
8 | analysis validated | 2014-03-06 17:00 | 2014-03-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-06 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | design | 2014-03-10 08:00 | 2014-03-28 17:00 | 15d |  |  | 0 |  |  | 3870 |  | 35d 7h | [5 empty] | 2070 |  | 100% |  | 3870 | 3870
9 | design - AIA | 2014-03-10 08:00 | 2014-03-17 11:00 | 5d 3h | Employee F | 3870 | 0 | 0 | 0 | 3870 | 2014-03-03 08:00 | 2d 7h | 2070 | 0 | 0 | 0 | 0 | 2070 | 0 | 100% | Finished | 3870 | 3870 | 100 | 53.4884 | 100 | 100 | 53.4884 | 100
10 | design validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | development | 2014-03-03 08:00 | 2014-04-04 17:00 | 25d |  |  | 0 |  |  | 9495 |  | 35d 7h | [5 empty] | 1005 |  | 100% |  | 9495 | 9495
11 | development - AIA | 2014-03-24 08:00 | 2014-04-01 14:00 | 6d 5h | Employee F | 4770 | 0 | 0 | 0 | 4770 | 2014-04-28 08:00 | 2h | 180 | 0 | 0 | 0 | 0 | 180 | 0 | 100% | Finished | 4770 | 4770 | 100 | 3.7736 | 100 | 100 | 3.7736 | 100
12 | development - progress | 2014-03-03 08:00 | 2014-03-12 16:00 | 7d 7h | Employee D | 4725 | 0 | 0 | 0 | 4725 | 2014-03-10 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 4725 | 4725 | 100 | 17.4603 | 100 | 100 | 17.4603 | 100
13 | development completed | 2014-04-04 17:00 | 2014-04-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | build | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 2325 |  | 12d 7h | [5 empty] | 450 |  | 100% |  | 2325 | 2325
14 | build - bugfixing | 2014-04-14 08:00 | 2014-04-16 11:00 | 2d 3h | Employee J | 1425 | 0 | 0 | 0 | 1425 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1425 | 1425 | 100 | 5.2632 | 100 | 100 | 5.2632 | 100
15 | build - bugfixing | 2014-04-14 08:00 | 2014-04-15 12:00 | 1d 4h | Employee D | 900 | 0 | 0 | 0 | 900 | 2014-04-21 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 900 | 900 | 100 | 41.6667 | 100 | 100 | 41.6667 | 100
16 | build completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
31 | ict test | 2014-02-26 08:00 | 2014-04-24 17:00 | 42d |  |  | 0 |  |  | 9975 |  | 43d 7h | [5 empty] | 7365 |  | 100% |  | 9975 | 9975
17 | test coordination | 2014-03-10 08:00 | 2014-03-11 09:00 | 1d 1h | Employee L | 675 | 0 | 0 | 0 | 675 | 2014-03-03 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 675 | 675 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
18 | test execution | 2014-03-31 08:00 | 2014-04-03 15:00 | 3d 6h | Employee F | 2700 | 0 | 0 | 0 | 2700 | 2014-03-31 08:00 | 1h | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 100% | Finished | 2700 | 2700 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
19 | test execution | 2014-03-31 08:00 | 2014-04-07 14:00 | 5d 5h | Employee M | 3375 | 0 | 0 | 0 | 3375 | 2014-04-21 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 3375 | 3375 | 100 | 37.7778 | 100 | 100 | 37.7778 | 100
20 | test preparation | 2014-02-26 08:00 | 2014-03-05 11:00 | 5d 3h | Employee M | 3225 | 0 | 0 | 0 | 3225 | 2014-02-24 08:00 | 9d 2h | 5550 | 0 | 0 | 0 | 0 | 5550 | 0 | 100% | Finished | 3225 | 3225 | 100 | 172.093 | 100 | 100 | 172.093 | 100
21 | ict test completed | 2014-04-24 17:00 | 2014-04-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
32 | implementation | 2014-04-25 17:00 | 2014-05-09 17:00 | 10d |  |  | 0 |  |  | 0 |  | 10d | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
23 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | post implementation | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h |  |  | 0 |  |  | 75 |  | 1h | [5 empty] | 75 |  | 100% |  | 75 | 0
24 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-04-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 0 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-11-19 08:00 | 2014-01-20 22:00 | 4545 | 1263 | 600 | 2013-11-19 16:00 | -3282 | 27.79% | 663 | 210.5% | -44d 1h | 1.944% | 45.45% | 2014-05-27 17:00 | 2015-08-05 14:00 | 2014-09-11 10:00 | 2014-06-25 14:00 | 2015-08-05 14:00 | 2014-10-14 16:00 | 2014-07-11 10:00 | 2038-05-07 14:00 | 2025-08-06 10:00 | 33597 | 16275.5345 | 119342.174 | 1697588.5718 | 57009.5841 | 806770.347 | 19568.3984 | 20149.2727 | 0.019444 | 2.105 | 0.27789 | 0.45455 | -44.125 | 2.105 | 1 | 0.019444 | 1
Tracking 2 | 2014-01-20 22:00 | 2014-02-24 22:00 | 8520 | 5450.9999 | 4875 | 2014-02-03 14:00 | -3069.0001 | 63.98% | 575.9999 | 111.8% | -15d 3h | 78.04% | 51.19% | 2014-05-27 10:00 | 2014-08-15 17:00 | 2014-07-18 12:00 | 2014-06-16 11:00 | 2014-08-15 17:00 | 2014-07-29 16:00 | 2014-06-02 12:00 | 2014-06-27 17:00 | 2014-06-16 14:00 | 33684.0001 | 30639.7912 | 49903.9273 | 41792.7117 | 45145.7802 | 37891.666 | 33050.5899 | 32296.6171 | 0.78036 | 1.1182 | 0.63979 | 0.51187 | -15.375 | 1.1182 | 1 | 0.78036 | 1
Tracking 3 | 2014-02-24 22:00 | 2014-03-31 22:00 | 26655 | 22125.1498 | 14715 | 2014-03-25 12:00 | -4529.8502 | 83.01% | 7410.1498 | 150.4% | -4d 4h | 95.26% | 87.92% | 2014-06-03 12:00 | 2014-06-16 12:00 | 2014-04-07 12:00 | 2014-06-03 10:00 | 2014-06-16 12:00 | 2014-05-21 10:00 | 2014-05-16 14:00 | 2014-05-20 10:00 | 2014-05-02 12:00 | 26849.8502 | 22785.6491 | 29334.3103 | 27453.2405 | 24438.0144 | 23186.9521 | 23579.8433 | 23423.8766 | 0.95263 | 1.5036 | 0.83006 | 0.87916 | -4.5 | 1.5036 | 1 | 0.95263 | 1
Closure | 2014-03-31 22:00 | 2014-05-12 08:00 | 34185 | 34260 | 18285 | 2014-05-12 09:00 | 75 | 100.2% | 15975 | 187.4% | 1h | 100.1% | 100% | 2014-05-09 16:00 | 2014-05-09 16:00 | 2014-02-19 09:00 | 2014-05-09 16:00 | 2014-05-09 16:00 | 2014-05-09 16:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 18285 | 18285 | 18285 | 18285 | 18285 | 18285 | 18285 | 18285 | 1.001 | 1.8737 | 1.0022 | 1 | 0.125 | 1.8737 | 1 | 1.001 | 1