## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Policy Numbering System | 1 |  |  | 2013-09-09 08:00 | 2014-05-05 17:00 | 171d |  |  | 0 |  |  | 12645 | 238.375
12 | supporting tasks | 1.1 |  |  | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  |  | 0 |  |  | 720 | 0.375
1 | project management | 1.1.1 |  | FS11 | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 0.375
13 | analysis | 1.2 |  |  | 2013-09-16 08:00 | 2013-11-13 17:00 | 43d |  |  | 0 |  |  | 1050 | 58.375
2 | analysis - business analysis | 1.2.1 |  | FS4 | 2013-09-16 08:00 | 2013-09-17 15:00 | 1d 6h | Employee B | 1050 | 0 | 0 | 0 | 1050 | 1.2917
4 | analysis validated | 1.2.2 | 2FS | FS11 | 2013-11-13 17:00 | 2013-11-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
14 | design | 1.3 |  |  | 2013-09-10 08:00 | 2013-12-03 17:00 | 61d |  |  | 0 |  |  | 3075 | 84.375
3 | design - technical design | 1.3.1 |  | FS5 | 2013-09-10 08:00 | 2013-09-17 09:00 | 5d 1h | Employee C | 3075 | 0 | 0 | 0 | 3075 | 7.0417
5 | design validated | 1.3.2 | 3FS | FS11 | 2013-12-03 17:00 | 2013-12-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
15 | development | 1.4 |  |  | 2013-09-09 08:00 | 2014-03-07 17:00 | 130d |  |  | 0 |  |  | 7800 | 179.375
6 | development - coding | 1.4.1 |  | FS9 | 2013-09-09 08:00 | 2013-09-17 10:00 | 6d 2h | Employee D | 3750 | 0 | 0 | 0 | 3750 | 8.0833
7 | development - coding | 1.4.2 |  | FS9 | 2013-09-09 08:00 | 2013-09-13 16:00 | 4d 7h | Employee E | 2925 | 0 | 0 | 0 | 2925 | 4.3333
8 | development - coding | 1.4.3 |  | FS9 | 2013-09-09 08:00 | 2013-09-10 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 1.3333
9 | development completed | 1.4.4 | 6FS;7FS;8FS | FS11 | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
16 | implementation | 1.5 |  |  | 2014-04-25 17:00 | 2014-05-05 17:00 | 6d |  |  | 0 |  |  | 0 | 10
10 | code freeze | 1.5.1 |  | FS11 | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
11 | go live | 1.5.2 | 1FS;4FS;5FS;9FS;10FS |  | 2014-05-05 17:00 | 2014-05-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 720
2 | Employee B | Renewable | 1 | 0 | 75 | 2; | 1050
3 | Employee C | Renewable | 1 | 0 | 75 | 3; | 3075
4 | Employee D | Renewable | 1 | 0 | 75 | 6; | 3750
5 | Employee E | Renewable | 1 | 0 | 75 | 7; | 2925
6 | Employee F | Renewable | 1 | 0 | 75 | 8; | 1125

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Policy Numbering System | 1368h |  |  |  |  | 99 | 100 | 101
12 | supporting tasks | 8h |  |  |  |  | 99 | 100 | 101
1 | project management | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | analysis | 344h |  |  |  |  | 99 | 100 | 101
2 | analysis - business analysis | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | design | 488h |  |  |  |  | 99 | 100 | 101
3 | design - technical design | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | development | 1040h |  |  |  |  | 99 | 100 | 101
6 | development - coding | 50h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | development - coding | 39h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | development - coding | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | implementation | 48h |  |  |  |  | 99 | 100 | 101
10 | code freeze | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-10-14 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Policy Numbering System | 2013-09-09 08:00 | 2014-05-05 17:00 | 171d |  |  | 0 |  |  | 12645 |  | 26d | [5 empty] | 9645 |  | 89.19% |  | 11278.4999 | 12645
12 | supporting tasks | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  |  | 0 |  |  | 720 |  | 21d | [5 empty] | 270 |  | 30% |  | 216 | 720
1 | project management | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2013-09-16 08:00 | 3h | 270 | 90 | 1h | 0 | 0 | 270 | 90 | 30% | Started | 216 | 720 | 100 | 37.5 | 30 | 100 | 37.5 | 30
13 | analysis | 2013-09-16 08:00 | 2013-11-13 17:00 | 43d |  |  | 0 |  |  | 1050 |  | 21d | [5 empty] | 75 |  | 100% |  | 1050 | 1050
2 | analysis - business analysis | 2013-09-16 08:00 | 2013-09-17 15:00 | 1d 6h | Employee B | 1050 | 0 | 0 | 0 | 1050 | 2013-09-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1050 | 1050 | 100 | 7.1429 | 100 | 100 | 7.1429 | 100
4 | analysis validated | 2013-11-13 17:00 | 2013-11-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | design | 2013-09-10 08:00 | 2013-12-03 17:00 | 61d |  |  | 0 |  |  | 3075 |  | 26d | [5 empty] | 2325 |  | 100% |  | 3075 | 3075
3 | design - technical design | 2013-09-10 08:00 | 2013-09-17 09:00 | 5d 1h | Employee C | 3075 | 0 | 0 | 0 | 3075 | 2013-09-09 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 3075 | 3075 | 100 | 75.6098 | 100 | 100 | 75.6098 | 100
5 | design validated | 2013-12-03 17:00 | 2013-12-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | development | 2013-09-09 08:00 | 2014-03-07 17:00 | 130d |  |  | 0 |  |  | 7800 |  | 26d | [5 empty] | 6975 |  | 88.94% |  | 6937.4999 | 7800
6 | development - coding | 2013-09-09 08:00 | 2013-09-17 10:00 | 6d 2h | Employee D | 3750 | 0 | 0 | 0 | 3750 | 2013-09-09 08:00 | 4d 7h | 2925 | 75 | 1h | 0 | 0 | 2925 | 75 | 77% | Started | 2887.4999 | 3750 | 100 | 78 | 77 | 100 | 78 | 77
7 | development - coding | 2013-09-09 08:00 | 2013-09-13 16:00 | 4d 7h | Employee E | 2925 | 0 | 0 | 0 | 2925 | 2013-09-09 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 2925 | 2925 | 100 | 100 | 100 | 100 | 100 | 100
8 | development - coding | 2013-09-09 08:00 | 2013-09-10 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2013-09-09 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
9 | development completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | implementation | 2014-04-25 17:00 | 2014-05-05 17:00 | 6d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | go live | 2014-05-05 17:00 | 2014-05-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-01-06 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Policy Numbering System | 2013-09-09 08:00 | 2014-05-05 17:00 | 171d |  |  | 0 |  |  | 12645 |  | 86d | [5 empty] | 10215 |  | 93.46% |  | 11817.6 | 12645
12 | supporting tasks | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  |  | 0 |  |  | 720 |  | 81d | [5 empty] | 540 |  | 58% |  | 417.6 | 720
1 | project management | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2013-09-16 08:00 | 6h | 540 | 90 | 1h | 0 | 0 | 540 | 90 | 58% | Started | 417.6 | 720 | 100 | 75 | 58 | 100 | 75 | 58
13 | analysis | 2013-09-16 08:00 | 2013-11-13 17:00 | 43d |  |  | 0 |  |  | 1050 |  | 42d 7h | [5 empty] | 75 |  | 100% |  | 1050 | 1050
2 | analysis - business analysis | 2013-09-16 08:00 | 2013-09-17 15:00 | 1d 6h | Employee B | 1050 | 0 | 0 | 0 | 1050 | 2013-09-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1050 | 1050 | 100 | 7.1429 | 100 | 100 | 7.1429 | 100
4 | analysis validated | 2013-11-13 17:00 | 2013-11-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-13 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | design | 2013-09-10 08:00 | 2013-12-03 17:00 | 61d |  |  | 0 |  |  | 3075 |  | 61d 7h | [5 empty] | 2325 |  | 100% |  | 3075 | 3075
3 | design - technical design | 2013-09-10 08:00 | 2013-09-17 09:00 | 5d 1h | Employee C | 3075 | 0 | 0 | 0 | 3075 | 2013-09-09 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 3075 | 3075 | 100 | 75.6098 | 100 | 100 | 75.6098 | 100
5 | design validated | 2013-12-03 17:00 | 2013-12-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-03 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | development | 2013-09-09 08:00 | 2014-03-07 17:00 | 130d |  |  | 0 |  |  | 7800 |  | 86d | [5 empty] | 7275 |  | 93.27% |  | 7275.0001 | 7800
6 | development - coding | 2013-09-09 08:00 | 2013-09-17 10:00 | 6d 2h | Employee D | 3750 | 0 | 0 | 0 | 3750 | 2013-09-09 08:00 | 5d 3h | 3225 | 75 | 1h | 0 | 0 | 3225 | 75 | 86% | Started | 3225.0001 | 3750 | 100 | 86 | 86 | 100 | 86 | 86
7 | development - coding | 2013-09-09 08:00 | 2013-09-13 16:00 | 4d 7h | Employee E | 2925 | 0 | 0 | 0 | 2925 | 2013-09-09 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 2925 | 2925 | 100 | 100 | 100 | 100 | 100 | 100
8 | development - coding | 2013-09-09 08:00 | 2013-09-10 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2013-09-09 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
9 | development completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | implementation | 2014-04-25 17:00 | 2014-05-05 17:00 | 6d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | go live | 2014-05-05 17:00 | 2014-05-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-02-24 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Policy Numbering System | 2013-09-09 08:00 | 2014-05-05 17:00 | 171d |  |  | 0 |  |  | 12645 |  | 121d | [5 empty] | 11010 |  | 99.43% |  | 12573 | 12645
12 | supporting tasks | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  |  | 0 |  |  | 720 |  | 116d | [5 empty] | 810 |  | 90% |  | 648 | 720
1 | project management | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2013-09-16 08:00 | 1d 1h | 810 | 90 | 1h | 0 | 0 | 810 | 90 | 90% | Started | 648 | 720 | 100 | 112.5 | 90 | 100 | 112.5 | 90
13 | analysis | 2013-09-16 08:00 | 2013-11-13 17:00 | 43d |  |  | 0 |  |  | 1050 |  | 42d 7h | [5 empty] | 75 |  | 100% |  | 1050 | 1050
2 | analysis - business analysis | 2013-09-16 08:00 | 2013-09-17 15:00 | 1d 6h | Employee B | 1050 | 0 | 0 | 0 | 1050 | 2013-09-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1050 | 1050 | 100 | 7.1429 | 100 | 100 | 7.1429 | 100
4 | analysis validated | 2013-11-13 17:00 | 2013-11-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-13 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | design | 2013-09-10 08:00 | 2013-12-03 17:00 | 61d |  |  | 0 |  |  | 3075 |  | 61d 7h | [5 empty] | 2325 |  | 100% |  | 3075 | 3075
3 | design - technical design | 2013-09-10 08:00 | 2013-09-17 09:00 | 5d 1h | Employee C | 3075 | 0 | 0 | 0 | 3075 | 2013-09-09 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 3075 | 3075 | 100 | 75.6098 | 100 | 100 | 75.6098 | 100
5 | design validated | 2013-12-03 17:00 | 2013-12-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-03 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | development | 2013-09-09 08:00 | 2014-03-07 17:00 | 130d |  |  | 0 |  |  | 7800 |  | 121d | [5 empty] | 7800 |  | 100% |  | 7800 | 7800
6 | development - coding | 2013-09-09 08:00 | 2013-09-17 10:00 | 6d 2h | Employee D | 3750 | 0 | 0 | 0 | 3750 | 2013-09-09 08:00 | 6d 2h | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
7 | development - coding | 2013-09-09 08:00 | 2013-09-13 16:00 | 4d 7h | Employee E | 2925 | 0 | 0 | 0 | 2925 | 2013-09-09 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 2925 | 2925 | 100 | 100 | 100 | 100 | 100 | 100
8 | development - coding | 2013-09-09 08:00 | 2013-09-10 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2013-09-09 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
9 | development completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | implementation | 2014-04-25 17:00 | 2014-05-05 17:00 | 6d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | go live | 2014-05-05 17:00 | 2014-05-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-04-21 22:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Policy Numbering System | 2013-09-09 08:00 | 2014-05-05 17:00 | 171d |  |  | 0 |  |  | 12645 |  | 161d | [5 empty] | 11100 |  | 100% |  | 12645 | 12645
12 | supporting tasks | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d |  |  | 0 |  |  | 720 |  | 1d 2h | [5 empty] | 900 |  | 100% |  | 720 | 720
1 | project management | 2013-09-19 08:00 | 2013-09-19 17:00 | 1d | Employee A | 720 | 0 | 0 | 0 | 720 | 2013-09-16 08:00 | 1d 2h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 720 | 720 | 100 | 125 | 100 | 100 | 125 | 100
13 | analysis | 2013-09-16 08:00 | 2013-11-13 17:00 | 43d |  |  | 0 |  |  | 1050 |  | 42d 7h | [5 empty] | 75 |  | 100% |  | 1050 | 1050
2 | analysis - business analysis | 2013-09-16 08:00 | 2013-09-17 15:00 | 1d 6h | Employee B | 1050 | 0 | 0 | 0 | 1050 | 2013-09-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1050 | 1050 | 100 | 7.1429 | 100 | 100 | 7.1429 | 100
4 | analysis validated | 2013-11-13 17:00 | 2013-11-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-13 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | design | 2013-09-10 08:00 | 2013-12-03 17:00 | 61d |  |  | 0 |  |  | 3075 |  | 61d 7h | [5 empty] | 2325 |  | 100% |  | 3075 | 3075
3 | design - technical design | 2013-09-10 08:00 | 2013-09-17 09:00 | 5d 1h | Employee C | 3075 | 0 | 0 | 0 | 3075 | 2013-09-09 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 3075 | 3075 | 100 | 75.6098 | 100 | 100 | 75.6098 | 100
5 | design validated | 2013-12-03 17:00 | 2013-12-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-03 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | development | 2013-09-09 08:00 | 2014-03-07 17:00 | 130d |  |  | 0 |  |  | 7800 |  | 161d | [5 empty] | 7800 |  | 100% |  | 7800 | 7800
6 | development - coding | 2013-09-09 08:00 | 2013-09-17 10:00 | 6d 2h | Employee D | 3750 | 0 | 0 | 0 | 3750 | 2013-09-09 08:00 | 6d 2h | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
7 | development - coding | 2013-09-09 08:00 | 2013-09-13 16:00 | 4d 7h | Employee E | 2925 | 0 | 0 | 0 | 2925 | 2013-09-09 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 2925 | 2925 | 100 | 100 | 100 | 100 | 100 | 100
8 | development - coding | 2013-09-09 08:00 | 2013-09-10 16:00 | 1d 7h | Employee F | 1125 | 0 | 0 | 0 | 1125 | 2013-09-09 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
9 | development completed | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | implementation | 2014-04-25 17:00 | 2014-05-05 17:00 | 6d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | go live | 2014-05-05 17:00 | 2014-05-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-09-09 08:00 | 2013-10-14 22:00 | 12645 | 11278.4999 | 9645 | 2013-09-16 17:00 | -1366.5001 | 89.19% | 1633.4999 | 116.9% | -20d | 23.08% | 93.67% | 2014-05-30 12:00 | 2014-06-03 15:00 | 2014-04-24 17:00 | 2014-05-08 15:00 | 2014-06-03 15:00 | 2014-04-30 15:00 | 2014-06-02 17:00 | 2016-07-11 17:00 | 2016-02-17 12:00 | 11011.5001 | 10813.5856 | 11177.0648 | 15566.5003 | 10955.1712 | 14708.8711 | 10871.7966 | 11037.053 | 0.23077 | 1.1694 | 0.89193 | 0.93667 | -20 | 1.1694 | 1 | 0.23077 | 1
Tracking 2 | 2013-10-14 22:00 | 2014-01-06 22:00 | 12645 | 11817.6 | 10215 | 2013-09-17 12:00 | -827.4 | 93.46% | 1602.6 | 115.7% | -79d 4h | 7.558% | 95.54% | 2014-05-21 10:00 | 2014-05-21 17:00 | 2014-04-17 09:00 | 2014-05-13 14:00 | 2014-05-21 17:00 | 2014-05-02 16:00 | 2014-08-25 12:00 | 2022-05-11 12:00 | 2021-03-24 10:00 | 11042.4 | 10930.1952 | 11100.3297 | 21162.1379 | 10980.269 | 19677.5824 | 10958.7818 | 11094.6271 | 0.075581 | 1.1569 | 0.93457 | 0.95541 | -79.5 | 1.1569 | 1 | 0.075581 | 1
Tracking 3 | 2014-01-06 22:00 | 2014-02-24 22:00 | 12645 | 12573 | 11010 | 2013-09-19 16:00 | -72 | 99.43% | 1563 | 114.2% | -112d 1h | 7.335% | 100% | 2014-05-06 17:00 | 2014-05-06 17:00 | 2014-04-07 14:00 | 2014-05-06 15:00 | 2014-05-06 17:00 | 2014-04-28 14:00 | 2014-10-09 09:00 | 2022-08-16 11:00 | 2021-07-27 14:00 | 11082 | 11073.0494 | 11082.4123 | 11991.634 | 11073.4105 | 11869.6032 | 11074.7231 | 11087.5663 | 0.073347 | 1.142 | 0.99431 | 1 | -112.125 | 1.142 | 1 | 0.073347 | 1
Closure | 2014-02-24 22:00 | 2014-04-21 22:00 | 12645 | 12645 | 11100 | 2014-04-21 17:00 | 0 | 100% | 1545 | 113.9% | 0 | 100% | 100% | 2014-05-05 17:00 | 2014-05-05 17:00 | 2014-04-07 09:00 | 2014-05-05 17:00 | 2014-05-05 17:00 | 2014-05-02 15:00 | 2014-05-05 17:00 | 2014-05-05 17:00 | 2014-05-02 15:00 | 11100 | 11100 | 11100 | 11100 | 11100 | 11100 | 11100 | 11100 | 1 | 1.1392 | 1 | 1 | 0 | 1.1392 | 1 | 1 | 1