## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Bridge (2) | 1 |  |  | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 | 339.375
1 | Voorbereidende studie | 1.1 |  |  | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 41.375
2 | Werfinrichting | 1.2 |  | FS3 | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 6.375
3 | Afbraak brug | 1.3 | 2FS | FS4 | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 1.375
4 | Uitgraving bouwputten | 1.4 | 3FS | FS5 | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 11.375
5 | Uitvoering paalfunderingen | 1.5 | 4FS | FS6 | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 11.375
24 | Uitvoeren van funderingsbalken | 1.6 |  |  | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 | 25.375
6 | LH spoor B | 1.6.1 | 5FS |  | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 11.375
7 | LH spoor A | 1.6.2 |  |  | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 11.375
25 | Brug fase 1 | 1.7 |  |  | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 | 25.375
8 | Plaatsen bekisting (incl. reiniging) | 1.7.1 |  | FS9 | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 1.375
9 | Wapenen + randkist | 1.7.2 | 8FS | FS10 | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 13.375
10 | Betonneren | 1.7.3 | 9FS | SF11+6d | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 | 0.375
11 | Ontkisten | 1.7.4 | 10SF+6d | FS12 | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 | 0.375
26 | Brug fase 2 | 1.8 |  |  | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 | 50.375
12 | Reinigen | 1.8.1 | 11FS | FS13 | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 | 1.375
13 | Wapenen + randkist | 1.8.2 | 12FS | FS14 | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 | 34.375
14 | Betonneren | 1.8.3 | 13FS | SF15+6d | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 | 0.375
15 | Ontkisten | 1.8.4 | 14SF+6d | FS16 | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 | 0.375
27 | Brug fase 3 | 1.9 |  |  | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 | 18.375
16 | Reinigen | 1.9.1 | 15FS | FS17 | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 | 0.375
17 | Wapenen + randkist | 1.9.2 | 16FS | FS18 | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 | 7.375
18 | Betonneren | 1.9.3 | 17FS | SF19+6d | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 | 0.375
19 | Ontkisten | 1.9.4 | 18SF+6d | FS20 | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 | 0.375
20 | Verbindingsbalken brug | 1.10 | 19FS | FS21 | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 | 4.375
21 | Aanbrengen waterdichte rok | 1.11 | 20FS | FS22 | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 4.375
22 | Aanvullingen en wegeniswerken | 1.12 | 21FS |  | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 | 30.375
23 | Afwerkingen | 1.13 |  |  | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 | 55.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Bridge (2) | 1832h |  |  |  |  | 99 | 100 | 101
1 | Voorbereidende studie | 240h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
2 | Werfinrichting | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
3 | Afbraak brug | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
4 | Uitgraving bouwputten | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
5 | Uitvoering paalfunderingen | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
24 | Uitvoeren van funderingsbalken | 160h |  |  |  |  | 99 | 100 | 101
6 | LH spoor B | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
7 | LH spoor A | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
25 | Brug fase 1 | 160h |  |  |  |  | 99 | 100 | 101
8 | Plaatsen bekisting (incl. reiniging) | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
9 | Wapenen + randkist | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
11 | Ontkisten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Brug fase 2 | 176h |  |  |  |  | 99 | 100 | 101
12 | Reinigen | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
13 | Wapenen + randkist | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
15 | Ontkisten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Brug fase 3 | 120h |  |  |  |  | 99 | 100 | 101
16 | Reinigen | 8h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
17 | Wapenen + randkist | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
19 | Ontkisten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Verbindingsbalken brug | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
21 | Aanbrengen waterdichte rok | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
22 | Aanvullingen en wegeniswerken | 184h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
23 | Afwerkingen | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-02-04 07:00 |  | TP Name | T1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 6d | [5 empty] | 10455.7402 |  | 1.087% |  | 10455.7403 | 10455.7402
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 6d | 10455.7402 | 11520 | 24d | 0 | 0 | 10455.7402 | 11520 | 20% | Started | 10455.7403 | 10455.7402 | 100 | 20 | 20 | 100 | 47.5786 | 20
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 |  | 0 | 0 | 28903.5801 | 5d | 0 | 0 | 0 | 28903.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 |  | 0 | 0 | 55669.3711 | 2d | 0 | 0 | 0 | 55669.3711 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 |  | 0 | 0 | 74193.9688 | 10d | 0 | 0 | 0 | 74193.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 |  | 0 | 0 | 245223.1875 | 10d | 0 | 0 | 0 | 245223.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 |  | 0 | 0 | 71202.2188 | 10d | 0 | 0 | 0 | 71202.2188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 |  | 0 | 0 | 34323.1191 | 10d | 0 | 0 | 0 | 34323.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 |  | 0 | 0 | 11316.6904 | 2d | 0 | 0 | 0 | 11316.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 |  | 0 | 0 | 19060.2002 | 10d | 0 | 0 | 0 | 19060.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-03-04 07:00 |  | TP Name | T2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 26d | [5 empty] | 44479.3203 |  | 4.623% |  | 44479.3204 | 44479.3203
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 26d | 20055.7402 | 1920 | 4d | 0 | 0 | 20055.7402 | 1920 | 86.67% | Started | 20055.7403 | 20055.7402 | 100 | 86.6667 | 86.6667 | 100 | 91.2631 | 86.6667
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 1d | 24423.5801 | 4480 | 4d | 0 | 0 | 24423.5801 | 4480 | 20% | Started | 24423.5801 | 24423.5801 | 100 | 20 | 20 | 100 | 84.5002 | 20
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 |  | 0 | 0 | 55669.3711 | 2d | 0 | 0 | 0 | 55669.3711 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 |  | 0 | 0 | 74193.9688 | 10d | 0 | 0 | 0 | 74193.9688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 |  | 0 | 0 | 245223.1875 | 10d | 0 | 0 | 0 | 245223.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 |  | 0 | 0 | 71202.2188 | 10d | 0 | 0 | 0 | 71202.2188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 |  | 0 | 0 | 34323.1191 | 10d | 0 | 0 | 0 | 34323.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 |  | 0 | 0 | 11316.6904 | 2d | 0 | 0 | 0 | 11316.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 |  | 0 | 0 | 19060.2002 | 10d | 0 | 0 | 0 | 19060.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-04-01 07:00 |  | TP Name | T3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 48d | [5 empty] | 420765.8477 |  | 43.41% |  | 417645.8477 | 420765.8477
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 5d | 240023.1875 | 20800 | 20d | 0 | 0 | 240023.1875 | 20800 | 20% | Started | 236903.1875 | 240023.1875 | 100 | 50 | 20 | 100 | 97.8795 | 20
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 |  | 0 | 0 | 71202.2188 | 10d | 0 | 0 | 0 | 71202.2188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 |  | 0 | 0 | 34323.1191 | 10d | 0 | 0 | 0 | 34323.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 |  | 0 | 0 | 11316.6904 | 2d | 0 | 0 | 0 | 11316.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 |  | 0 | 0 | 19060.2002 | 10d | 0 | 0 | 0 | 19060.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-05-06 07:00 |  | TP Name | T4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 73d | [5 empty] | 441565.8477 |  | 44.27% |  | 425965.8477 | 492368.0664
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 66402.2188
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 |  | 0 | 0 | 71202.2188 | 10d | 0 | 0 | 0 | 71202.2188 | 0% | Not Started | 0 | 66402.2188 | 100 |  | 0 | 100 |  | 0
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 |  | 0 | 0 | 34323.1191 | 10d | 0 | 0 | 0 | 34323.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 |  | 0 | 0 | 11316.6904 | 2d | 0 | 0 | 0 | 11316.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 |  | 0 | 0 | 19060.2002 | 10d | 0 | 0 | 0 | 19060.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-06-03 07:00 |  | TP Name | T5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 93d | [5 empty] | 504128.0664 |  | 51.67% |  | 497168.0664 | 531491.1855
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 19d | [5 empty] | 62562.2188 |  | 67.47% |  | 71202.2188 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 |  | 0 | 0 | 34323.1191 | 10d | 0 | 0 | 0 | 34323.1191 | 0% | Not Started | 0 | 34323.1191 | 100 |  | 0 | 100 |  | 0
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 |  | 0 | 0 | 11316.6904 | 2d | 0 | 0 | 0 | 11316.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 |  | 0 | 0 | 19060.2002 | 10d | 0 | 0 | 0 | 19060.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-07-01 07:00 |  | TP Name | T6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 113d | [5 empty] | 532691.1855 |  | 54.57% |  | 525091.1856 | 592736.0156
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 39d | [5 empty] | 91125.3379 |  | 93.94% |  | 99125.338 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 4d | 28563.1191 | 7680 | 8d | 0 | 0 | 28563.1191 | 7680 | 33.33% | Started | 27923.1192 | 34323.1191 | 100 | 40 | 33.3333 | 100 | 83.2183 | 33.3333
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 61244.8301
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 |  | 0 | 0 | 11316.6904 | 2d | 0 | 0 | 0 | 11316.6904 | 0% | Not Started | 0 | 11316.6904 | 100 |  | 0 | 100 |  | 0
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 |  | 0 | 0 | 19060.2002 | 10d | 0 | 0 | 0 | 19060.2002 | 0% | Not Started | 0 | 19060.2002 | 100 |  | 0 | 100 |  | 0
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 30867.9395 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-08-05 07:00 |  | TP Name | T7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 128d | [5 empty] | 540371.1855 |  | 55.24% |  | 531491.1855 | 614876.1357
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 100% |  | 105525.3379 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 100% | Finished | 34323.1191 | 34323.1191 | 100 | 120 | 100 | 100 | 105.5939 | 100
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 66146.4302
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 |  | 0 | 0 | 11316.6904 | 2d | 0 | 0 | 0 | 11316.6904 | 0% | Not Started | 0 | 11316.6904 | 100 |  | 0 | 100 |  | 0
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 |  | 0 | 0 | 19060.2002 | 10d | 0 | 0 | 0 | 19060.2002 | 0% | Not Started | 0 | 19060.2002 | 100 |  | 0 | 100 |  | 0
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 30867.9395 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 4901.6001 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 17238.52
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 4518.0601 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 12720.46 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2013-09-02 07:00 |  | TP Name | T8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 143d | [5 empty] | 564988.0762 |  | 57.9% |  | 557068.0762 | 638959.7259
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 100% |  | 105525.3379 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 100% | Finished | 34323.1191 | 34323.1191 | 100 | 120 | 100 | 100 | 105.5939 | 100
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 7d | [5 empty] | 24616.8906 |  | 38.67% |  | 25576.8906 | 66146.4302
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 2013-08-22 07:00 | 2d | 11316.6904 | 0 | 0 | 0 | 0 | 11316.6904 | 0 | 100% | Finished | 11316.6904 | 11316.6904 | 100 | 100 | 100 | 100 | 100 | 100
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 2013-08-27 07:00 | 4d | 13300.2002 | 3840 | 4d | 0 | 0 | 13300.2002 | 3840 | 50% | Started | 14260.2002 | 19060.2002 | 100 | 40 | 50 | 100 | 69.78 | 50
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 |  | 0 | 0 | 30867.9395 | 1d | 0 | 0 | 0 | 30867.9395 | 0% | Not Started | 0 | 30867.9395 | 100 |  | 0 | 100 |  | 0
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 |  | 0 | 0 | 4901.6001 | 1d | 0 | 0 | 0 | 4901.6001 | 0% | Not Started | 0 | 4901.6001 | 100 |  | 0 | 100 |  | 0
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 41322.1102
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 |  | 0 | 0 | 4518.0601 | 2d | 0 | 0 | 0 | 4518.0601 | 0% | Not Started | 0 | 4518.0601 | 100 |  | 0 | 100 |  | 0
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 |  | 0 | 0 | 14960.46 | 10d | 0 | 0 | 0 | 14960.46 | 0% | Not Started | 0 | 14960.46 | 100 |  | 0 | 100 |  | 0
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 |  | 0 | 0 | 20067.1602 | 1d | 0 | 0 | 0 | 20067.1602 | 0% | Not Started | 0 | 20067.1602 | 100 |  | 0 | 100 |  | 0
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 1776.43 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2013-10-07 07:00 |  | TP Name | T9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 168d | [5 empty] | 640783.2959 |  | 66.22% |  | 637183.2959 | 750824.1053
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 100% |  | 105525.3379 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 100% | Finished | 34323.1191 | 34323.1191 | 100 | 120 | 100 | 100 | 105.5939 | 100
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 18d | [5 empty] | 64226.4302 |  | 100% |  | 66146.4302 | 66146.4302
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 2013-08-22 07:00 | 2d | 11316.6904 | 0 | 0 | 0 | 0 | 11316.6904 | 0 | 100% | Finished | 11316.6904 | 11316.6904 | 100 | 100 | 100 | 100 | 100 | 100
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 2013-08-27 07:00 | 8d | 17140.2002 | 0 | 0 | 0 | 0 | 17140.2002 | 0 | 100% | Finished | 19060.2002 | 19060.2002 | 100 | 80 | 100 | 100 | 89.9267 | 100
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 | 2013-09-06 07:00 | 1d | 30867.9395 | 0 | 0 | 0 | 0 | 30867.9395 | 0 | 100% | Finished | 30867.9395 | 30867.9395 | 100 | 100 | 100 | 100 | 100 | 100
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 | 2013-09-16 07:00 | 1d | 4901.6001 | 0 | 0 | 0 | 0 | 4901.6001 | 0 | 100% | Finished | 4901.6001 | 4901.6001 | 100 | 100 | 100 | 100 | 100 | 100
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 14d | [5 empty] | 36185.6802 |  | 95.7% |  | 39545.6802 | 41322.1102
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 | 2013-09-17 07:00 | 2d | 4518.0601 | 0 | 0 | 0 | 0 | 4518.0601 | 0 | 100% | Finished | 4518.0601 | 4518.0601 | 100 | 100 | 100 | 100 | 100 | 100
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 | 2013-09-18 07:00 | 7d | 11600.46 | 0 | 0 | 0 | 0 | 11600.46 | 0 | 100% | Finished | 14960.46 | 14960.46 | 100 | 70 | 100 | 100 | 77.5408 | 100
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 | 2013-09-27 07:00 | 1d | 20067.1602 | 0 | 0 | 0 | 0 | 20067.1602 | 0 | 100% | Finished | 20067.1602 | 20067.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 |  | 0 | 0 | 1776.43 | 1d | 0 | 0 | 0 | 1776.43 | 0% | Not Started | 0 | 1776.43 | 100 |  | 0 | 100 |  | 0
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 40505.9009
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 |  | 0 | 0 | 4513.1499 | 1d | 0 | 0 | 0 | 4513.1499 | 0% | Not Started | 0 | 4513.1499 | 100 |  | 0 | 100 |  | 0
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 |  | 0 | 0 | 12658.8501 | 6d | 0 | 0 | 0 | 12658.8501 | 0% | Not Started | 0 | 12658.8501 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 |  | 0 | 0 | 20498.7109 | 1d | 0 | 0 | 0 | 20498.7109 | 0% | Not Started | 0 | 20498.7109 | 100 |  | 0 | 100 |  | 0
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 |  | 0 | 0 | 2835.1899 | 1d | 0 | 0 | 0 | 2835.1899 | 0% | Not Started | 0 | 2835.1899 | 100 |  | 0 | 100 |  | 0
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 |  | 0 | 0 | 26016.3496 | 5d | 0 | 0 | 0 | 26016.3496 | 0% | Not Started | 0 | 26016.3496 | 100 |  | 0 | 100 |  | 0
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 45342.1289 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2013-11-04 07:00 |  | TP Name | T10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 188d | [5 empty] | 708041.9764 |  | 73.21% |  | 704441.9764 | 870408.449
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 100% |  | 105525.3379 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 100% | Finished | 34323.1191 | 34323.1191 | 100 | 120 | 100 | 100 | 105.5939 | 100
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 18d | [5 empty] | 64226.4302 |  | 100% |  | 66146.4302 | 66146.4302
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 2013-08-22 07:00 | 2d | 11316.6904 | 0 | 0 | 0 | 0 | 11316.6904 | 0 | 100% | Finished | 11316.6904 | 11316.6904 | 100 | 100 | 100 | 100 | 100 | 100
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 2013-08-27 07:00 | 8d | 17140.2002 | 0 | 0 | 0 | 0 | 17140.2002 | 0 | 100% | Finished | 19060.2002 | 19060.2002 | 100 | 80 | 100 | 100 | 89.9267 | 100
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 | 2013-09-06 07:00 | 1d | 30867.9395 | 0 | 0 | 0 | 0 | 30867.9395 | 0 | 100% | Finished | 30867.9395 | 30867.9395 | 100 | 100 | 100 | 100 | 100 | 100
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 | 2013-09-16 07:00 | 1d | 4901.6001 | 0 | 0 | 0 | 0 | 4901.6001 | 0 | 100% | Finished | 4901.6001 | 4901.6001 | 100 | 100 | 100 | 100 | 100 | 100
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 15d | [5 empty] | 37962.1102 |  | 100% |  | 41322.1102 | 41322.1102
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 | 2013-09-17 07:00 | 2d | 4518.0601 | 0 | 0 | 0 | 0 | 4518.0601 | 0 | 100% | Finished | 4518.0601 | 4518.0601 | 100 | 100 | 100 | 100 | 100 | 100
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 | 2013-09-18 07:00 | 7d | 11600.46 | 0 | 0 | 0 | 0 | 11600.46 | 0 | 100% | Finished | 14960.46 | 14960.46 | 100 | 70 | 100 | 100 | 77.5408 | 100
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 | 2013-09-27 07:00 | 1d | 20067.1602 | 0 | 0 | 0 | 0 | 20067.1602 | 0 | 100% | Finished | 20067.1602 | 20067.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 | 2013-10-07 07:00 | 1d | 1776.43 | 0 | 0 | 0 | 0 | 1776.43 | 0 | 100% | Finished | 1776.43 | 1776.43 | 100 | 100 | 100 | 100 | 100 | 100
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 15d | [5 empty] | 40505.9009 |  | 100% |  | 40505.9009 | 40505.9009
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 | 2013-10-08 07:00 | 1d | 4513.1499 | 0 | 0 | 0 | 0 | 4513.1499 | 0 | 100% | Finished | 4513.1499 | 4513.1499 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 | 2013-10-09 07:00 | 6d | 12658.8501 | 0 | 0 | 0 | 0 | 12658.8501 | 0 | 100% | Finished | 12658.8501 | 12658.8501 | 100 | 100 | 100 | 100 | 100 | 100
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 | 2013-10-18 07:00 | 1d | 20498.7109 | 0 | 0 | 0 | 0 | 20498.7109 | 0 | 100% | Finished | 20498.7109 | 20498.7109 | 100 | 100 | 100 | 100 | 100 | 100
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 | 2013-10-28 07:00 | 1d | 2835.1899 | 0 | 0 | 0 | 0 | 2835.1899 | 0 | 100% | Finished | 2835.1899 | 2835.1899 | 100 | 100 | 100 | 100 | 100 | 100
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 | 2013-10-29 07:00 | 4d | 24976.3496 | 1040 | 1d | 0 | 0 | 24976.3496 | 1040 | 80% | Started | 24976.3497 | 26016.3496 | 100 | 80 | 80 | 100 | 96.0025 | 80
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 45342.1289 | 100 |  | 0 | 100 |  | 0
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 |  | 0 | 0 | 122584.3438 | 23d | 0 | 0 | 0 | 122584.3438 | 0% | Not Started | 0 | 119584.3438 | 100 |  | 0 | 100 |  | 0
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 |  | 0 | 0 | 88773.1094 | 40d | 0 | 0 | 0 | 88773.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2013-12-02 07:00 |  | TP Name | T11
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 208d | [5 empty] | 935581.5584 |  | 96.73% |  | 930706.892 | 942021.5584
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 100% |  | 105525.3379 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 100% | Finished | 34323.1191 | 34323.1191 | 100 | 120 | 100 | 100 | 105.5939 | 100
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 18d | [5 empty] | 64226.4302 |  | 100% |  | 66146.4302 | 66146.4302
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 2013-08-22 07:00 | 2d | 11316.6904 | 0 | 0 | 0 | 0 | 11316.6904 | 0 | 100% | Finished | 11316.6904 | 11316.6904 | 100 | 100 | 100 | 100 | 100 | 100
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 2013-08-27 07:00 | 8d | 17140.2002 | 0 | 0 | 0 | 0 | 17140.2002 | 0 | 100% | Finished | 19060.2002 | 19060.2002 | 100 | 80 | 100 | 100 | 89.9267 | 100
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 | 2013-09-06 07:00 | 1d | 30867.9395 | 0 | 0 | 0 | 0 | 30867.9395 | 0 | 100% | Finished | 30867.9395 | 30867.9395 | 100 | 100 | 100 | 100 | 100 | 100
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 | 2013-09-16 07:00 | 1d | 4901.6001 | 0 | 0 | 0 | 0 | 4901.6001 | 0 | 100% | Finished | 4901.6001 | 4901.6001 | 100 | 100 | 100 | 100 | 100 | 100
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 15d | [5 empty] | 37962.1102 |  | 100% |  | 41322.1102 | 41322.1102
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 | 2013-09-17 07:00 | 2d | 4518.0601 | 0 | 0 | 0 | 0 | 4518.0601 | 0 | 100% | Finished | 4518.0601 | 4518.0601 | 100 | 100 | 100 | 100 | 100 | 100
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 | 2013-09-18 07:00 | 7d | 11600.46 | 0 | 0 | 0 | 0 | 11600.46 | 0 | 100% | Finished | 14960.46 | 14960.46 | 100 | 70 | 100 | 100 | 77.5408 | 100
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 | 2013-09-27 07:00 | 1d | 20067.1602 | 0 | 0 | 0 | 0 | 20067.1602 | 0 | 100% | Finished | 20067.1602 | 20067.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 | 2013-10-07 07:00 | 1d | 1776.43 | 0 | 0 | 0 | 0 | 1776.43 | 0 | 100% | Finished | 1776.43 | 1776.43 | 100 | 100 | 100 | 100 | 100 | 100
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 15d | [5 empty] | 40505.9009 |  | 100% |  | 40505.9009 | 40505.9009
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 | 2013-10-08 07:00 | 1d | 4513.1499 | 0 | 0 | 0 | 0 | 4513.1499 | 0 | 100% | Finished | 4513.1499 | 4513.1499 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 | 2013-10-09 07:00 | 6d | 12658.8501 | 0 | 0 | 0 | 0 | 12658.8501 | 0 | 100% | Finished | 12658.8501 | 12658.8501 | 100 | 100 | 100 | 100 | 100 | 100
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 | 2013-10-18 07:00 | 1d | 20498.7109 | 0 | 0 | 0 | 0 | 20498.7109 | 0 | 100% | Finished | 20498.7109 | 20498.7109 | 100 | 100 | 100 | 100 | 100 | 100
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 | 2013-10-28 07:00 | 1d | 2835.1899 | 0 | 0 | 0 | 0 | 2835.1899 | 0 | 100% | Finished | 2835.1899 | 2835.1899 | 100 | 100 | 100 | 100 | 100 | 100
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 | 2013-10-29 07:00 | 4d | 24976.3496 | 0 | 0 | 0 | 0 | 24976.3496 | 0 | 100% | Finished | 26016.3496 | 26016.3496 | 100 | 80 | 100 | 100 | 96.0025 | 100
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-11-05 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 | 2013-11-12 07:00 | 14d | 113584.3438 | 7000 | 7d | 0 | 0 | 113584.3438 | 7000 | 66.67% | Started | 114917.6775 | 122584.3438 | 100 | 60.8696 | 66.6667 | 100 | 92.6581 | 66.6667
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 | 2013-11-05 07:00 | 19d | 68613.1094 | 29760 | 31d | 0 | 0 | 68613.1094 | 29760 | 38% | Started | 64965.1092 | 68613.1094 | 100 | 47.5 | 38 | 100 | 77.2904 | 38

## TP12
| TP Status Date | 2014-01-06 07:00 |  | TP Name | T12
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 233d | [5 empty] | 966581.5584 |  | 99.52% |  | 957573.5582 | 962181.5584
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 100% |  | 105525.3379 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 100% | Finished | 34323.1191 | 34323.1191 | 100 | 120 | 100 | 100 | 105.5939 | 100
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 18d | [5 empty] | 64226.4302 |  | 100% |  | 66146.4302 | 66146.4302
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 2013-08-22 07:00 | 2d | 11316.6904 | 0 | 0 | 0 | 0 | 11316.6904 | 0 | 100% | Finished | 11316.6904 | 11316.6904 | 100 | 100 | 100 | 100 | 100 | 100
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 2013-08-27 07:00 | 8d | 17140.2002 | 0 | 0 | 0 | 0 | 17140.2002 | 0 | 100% | Finished | 19060.2002 | 19060.2002 | 100 | 80 | 100 | 100 | 89.9267 | 100
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 | 2013-09-06 07:00 | 1d | 30867.9395 | 0 | 0 | 0 | 0 | 30867.9395 | 0 | 100% | Finished | 30867.9395 | 30867.9395 | 100 | 100 | 100 | 100 | 100 | 100
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 | 2013-09-16 07:00 | 1d | 4901.6001 | 0 | 0 | 0 | 0 | 4901.6001 | 0 | 100% | Finished | 4901.6001 | 4901.6001 | 100 | 100 | 100 | 100 | 100 | 100
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 15d | [5 empty] | 37962.1102 |  | 100% |  | 41322.1102 | 41322.1102
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 | 2013-09-17 07:00 | 2d | 4518.0601 | 0 | 0 | 0 | 0 | 4518.0601 | 0 | 100% | Finished | 4518.0601 | 4518.0601 | 100 | 100 | 100 | 100 | 100 | 100
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 | 2013-09-18 07:00 | 7d | 11600.46 | 0 | 0 | 0 | 0 | 11600.46 | 0 | 100% | Finished | 14960.46 | 14960.46 | 100 | 70 | 100 | 100 | 77.5408 | 100
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 | 2013-09-27 07:00 | 1d | 20067.1602 | 0 | 0 | 0 | 0 | 20067.1602 | 0 | 100% | Finished | 20067.1602 | 20067.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 | 2013-10-07 07:00 | 1d | 1776.43 | 0 | 0 | 0 | 0 | 1776.43 | 0 | 100% | Finished | 1776.43 | 1776.43 | 100 | 100 | 100 | 100 | 100 | 100
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 15d | [5 empty] | 40505.9009 |  | 100% |  | 40505.9009 | 40505.9009
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 | 2013-10-08 07:00 | 1d | 4513.1499 | 0 | 0 | 0 | 0 | 4513.1499 | 0 | 100% | Finished | 4513.1499 | 4513.1499 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 | 2013-10-09 07:00 | 6d | 12658.8501 | 0 | 0 | 0 | 0 | 12658.8501 | 0 | 100% | Finished | 12658.8501 | 12658.8501 | 100 | 100 | 100 | 100 | 100 | 100
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 | 2013-10-18 07:00 | 1d | 20498.7109 | 0 | 0 | 0 | 0 | 20498.7109 | 0 | 100% | Finished | 20498.7109 | 20498.7109 | 100 | 100 | 100 | 100 | 100 | 100
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 | 2013-10-28 07:00 | 1d | 2835.1899 | 0 | 0 | 0 | 0 | 2835.1899 | 0 | 100% | Finished | 2835.1899 | 2835.1899 | 100 | 100 | 100 | 100 | 100 | 100
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 | 2013-10-29 07:00 | 4d | 24976.3496 | 0 | 0 | 0 | 0 | 24976.3496 | 0 | 100% | Finished | 26016.3496 | 26016.3496 | 100 | 80 | 100 | 100 | 96.0025 | 100
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-11-05 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 | 2013-11-12 07:00 | 21d | 120584.3438 | 0 | 0 | 0 | 0 | 120584.3438 | 0 | 100% | Finished | 122584.3438 | 122584.3438 | 100 | 91.3043 | 100 | 100 | 98.3685 | 100
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 | 2013-11-05 07:00 | 44d | 92613.1094 | 5760 | 6d | 0 | 0 | 92613.1094 | 5760 | 88% | Started | 84165.1092 | 88773.1094 | 100 | 110 | 88 | 100 | 104.3256 | 88

## TP13
| TP Status Date | 2014-02-03 07:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (2) | 2013-01-25 07:00 | 2013-12-30 16:00 | 229d |  |  | 788781.5584 |  |  | 962181.5584 |  | 239d | [5 empty] | 972341.5584 |  | 100% |  | 962181.5584 | 962181.5584
1 | Voorbereidende studie | 2013-01-25 07:00 | 2013-03-07 16:00 | 30d |  | 0 | 7575.7402 | 60 | 14400 | 21975.7402 | 2013-01-25 07:00 | 30d | 21975.7402 | 0 | 0 | 0 | 0 | 21975.7402 | 0 | 100% | Finished | 21975.7402 | 21975.7402 | 100 | 100 | 100 | 100 | 100 | 100
2 | Werfinrichting | 2013-03-01 07:00 | 2013-03-07 16:00 | 5d |  | 0 | 23303.5801 | 140 | 5600 | 28903.5801 | 2013-03-01 07:00 | 5d | 28903.5801 | 0 | 0 | 0 | 0 | 28903.5801 | 0 | 100% | Finished | 28903.5801 | 28903.5801 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak brug | 2013-03-09 07:00 | 2013-03-10 16:00 | 2d |  | 0 | 51669.3711 | 250 | 4000 | 55669.3711 | 2013-03-09 07:00 | 2d | 55669.3711 | 0 | 0 | 0 | 0 | 55669.3711 | 0 | 100% | Finished | 55669.3711 | 55669.3711 | 100 | 100 | 100 | 100 | 100 | 100
4 | Uitgraving bouwputten | 2013-03-11 07:00 | 2013-03-22 16:00 | 10d |  | 0 | 64593.9688 | 120 | 9600 | 74193.9688 | 2013-03-11 07:00 | 10d | 74193.9688 | 0 | 0 | 0 | 0 | 74193.9688 | 0 | 100% | Finished | 74193.9688 | 74193.9688 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitvoering paalfunderingen | 2013-03-25 07:00 | 2013-04-05 16:00 | 10d |  | 0 | 234823.1875 | 130 | 10400 | 245223.1875 | 2013-03-25 07:00 | 25d | 260823.1875 | 0 | 0 | 0 | 0 | 260823.1875 | 0 | 100% | Finished | 245223.1875 | 245223.1875 | 100 | 250 | 100 | 100 | 106.3616 | 100
24 | Uitvoeren van funderingsbalken | 2013-04-29 07:00 | 2013-05-24 16:00 | 20d |  |  | 86325.3379 |  |  | 105525.3379 |  | 47d | [5 empty] | 98805.3379 |  | 100% |  | 105525.3379 | 105525.3379
6 | LH spoor B | 2013-04-29 07:00 | 2013-05-10 16:00 | 10d |  | 0 | 61602.2188 | 120 | 9600 | 71202.2188 | 2013-05-07 07:00 | 1d | 62562.2188 | 0 | 0 | 0 | 0 | 62562.2188 | 0 | 100% | Finished | 71202.2188 | 71202.2188 | 100 | 10 | 100 | 100 | 87.8655 | 100
7 | LH spoor A | 2013-05-13 07:00 | 2013-05-24 16:00 | 10d |  | 0 | 24723.1191 | 120 | 9600 | 34323.1191 | 2013-06-25 07:00 | 12d | 36243.1191 | 0 | 0 | 0 | 0 | 36243.1191 | 0 | 100% | Finished | 34323.1191 | 34323.1191 | 100 | 120 | 100 | 100 | 105.5939 | 100
25 | Brug fase 1 | 2013-06-10 07:00 | 2013-07-05 16:00 | 20d |  |  | 52066.4302 |  |  | 66146.4302 |  | 18d | [5 empty] | 64226.4302 |  | 100% |  | 66146.4302 | 66146.4302
8 | Plaatsen bekisting (incl. reiniging) | 2013-06-10 07:00 | 2013-06-11 16:00 | 2d |  | 0 | 9076.6904 | 140 | 2240 | 11316.6904 | 2013-08-22 07:00 | 2d | 11316.6904 | 0 | 0 | 0 | 0 | 11316.6904 | 0 | 100% | Finished | 11316.6904 | 11316.6904 | 100 | 100 | 100 | 100 | 100 | 100
9 | Wapenen + randkist | 2013-06-12 07:00 | 2013-06-25 16:00 | 10d |  | 0 | 9460.2002 | 120 | 9600 | 19060.2002 | 2013-08-27 07:00 | 8d | 17140.2002 | 0 | 0 | 0 | 0 | 17140.2002 | 0 | 100% | Finished | 19060.2002 | 19060.2002 | 100 | 80 | 100 | 100 | 89.9267 | 100
10 | Betonneren | 2013-06-26 07:00 | 2013-06-26 16:00 | 1d |  | 0 | 29587.9395 | 160 | 1280 | 30867.9395 | 2013-09-06 07:00 | 1d | 30867.9395 | 0 | 0 | 0 | 0 | 30867.9395 | 0 | 100% | Finished | 30867.9395 | 30867.9395 | 100 | 100 | 100 | 100 | 100 | 100
11 | Ontkisten | 2013-07-05 07:00 | 2013-07-05 16:00 | 1d |  | 0 | 3941.6001 | 120 | 960 | 4901.6001 | 2013-09-16 07:00 | 1d | 4901.6001 | 0 | 0 | 0 | 0 | 4901.6001 | 0 | 100% | Finished | 4901.6001 | 4901.6001 | 100 | 100 | 100 | 100 | 100 | 100
26 | Brug fase 2 | 2013-07-08 07:00 | 2013-08-27 16:00 | 22d |  |  | 26282.1102 |  |  | 41322.1102 |  | 15d | [5 empty] | 37962.1102 |  | 100% |  | 41322.1102 | 41322.1102
12 | Reinigen | 2013-07-08 07:00 | 2013-07-09 16:00 | 2d |  | 0 | 2598.0601 | 120 | 1920 | 4518.0601 | 2013-09-17 07:00 | 2d | 4518.0601 | 0 | 0 | 0 | 0 | 4518.0601 | 0 | 100% | Finished | 4518.0601 | 4518.0601 | 100 | 100 | 100 | 100 | 100 | 100
13 | Wapenen + randkist | 2013-07-10 07:00 | 2013-08-13 16:00 | 10d |  | 0 | 3760.46 | 140 | 11200 | 14960.46 | 2013-09-18 07:00 | 7d | 11600.46 | 0 | 0 | 0 | 0 | 11600.46 | 0 | 100% | Finished | 14960.46 | 14960.46 | 100 | 70 | 100 | 100 | 77.5408 | 100
14 | Betonneren | 2013-08-16 07:00 | 2013-08-16 16:00 | 1d |  | 0 | 19107.1602 | 120 | 960 | 20067.1602 | 2013-09-27 07:00 | 1d | 20067.1602 | 0 | 0 | 0 | 0 | 20067.1602 | 0 | 100% | Finished | 20067.1602 | 20067.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Ontkisten | 2013-08-27 07:00 | 2013-08-27 16:00 | 1d |  | 0 | 816.43 | 120 | 960 | 1776.43 | 2013-10-07 07:00 | 1d | 1776.43 | 0 | 0 | 0 | 0 | 1776.43 | 0 | 100% | Finished | 1776.43 | 1776.43 | 100 | 100 | 100 | 100 | 100 | 100
27 | Brug fase 3 | 2013-09-02 07:00 | 2013-09-20 16:00 | 15d |  |  | 30825.9009 |  |  | 40505.9009 |  | 15d | [5 empty] | 40505.9009 |  | 100% |  | 40505.9009 | 40505.9009
16 | Reinigen | 2013-09-02 07:00 | 2013-09-02 16:00 | 1d |  | 0 | 3473.1499 | 130 | 1040 | 4513.1499 | 2013-10-08 07:00 | 1d | 4513.1499 | 0 | 0 | 0 | 0 | 4513.1499 | 0 | 100% | Finished | 4513.1499 | 4513.1499 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen + randkist | 2013-09-03 07:00 | 2013-09-10 16:00 | 6d |  | 0 | 5938.8501 | 140 | 6720 | 12658.8501 | 2013-10-09 07:00 | 6d | 12658.8501 | 0 | 0 | 0 | 0 | 12658.8501 | 0 | 100% | Finished | 12658.8501 | 12658.8501 | 100 | 100 | 100 | 100 | 100 | 100
18 | Betonneren | 2013-09-11 07:00 | 2013-09-11 16:00 | 1d |  | 0 | 19538.7109 | 120 | 960 | 20498.7109 | 2013-10-18 07:00 | 1d | 20498.7109 | 0 | 0 | 0 | 0 | 20498.7109 | 0 | 100% | Finished | 20498.7109 | 20498.7109 | 100 | 100 | 100 | 100 | 100 | 100
19 | Ontkisten | 2013-09-20 07:00 | 2013-09-20 16:00 | 1d |  | 0 | 1875.1899 | 120 | 960 | 2835.1899 | 2013-10-28 07:00 | 1d | 2835.1899 | 0 | 0 | 0 | 0 | 2835.1899 | 0 | 100% | Finished | 2835.1899 | 2835.1899 | 100 | 100 | 100 | 100 | 100 | 100
20 | Verbindingsbalken brug | 2013-09-23 07:00 | 2013-09-27 16:00 | 5d |  | 0 | 20816.3496 | 130 | 5200 | 26016.3496 | 2013-10-29 07:00 | 4d | 24976.3496 | 0 | 0 | 0 | 0 | 24976.3496 | 0 | 100% | Finished | 26016.3496 | 26016.3496 | 100 | 80 | 100 | 100 | 96.0025 | 100
21 | Aanbrengen waterdichte rok | 2013-09-30 07:00 | 2013-10-04 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-11-05 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanvullingen en wegeniswerken | 2013-10-07 07:00 | 2013-11-06 16:00 | 23d |  | 0 | 99584.3438 | 125 | 23000 | 122584.3438 | 2013-11-12 07:00 | 21d | 120584.3438 | 0 | 0 | 0 | 0 | 120584.3438 | 0 | 100% | Finished | 122584.3438 | 122584.3438 | 100 | 91.3043 | 100 | 100 | 98.3685 | 100
23 | Afwerkingen | 2013-11-05 07:00 | 2013-12-30 16:00 | 40d |  | 0 | 50373.1094 | 120 | 38400 | 88773.1094 | 2013-11-05 07:00 | 50d | 98373.1094 | 0 | 0 | 0 | 0 | 98373.1094 | 0 | 100% | Finished | 88773.1094 | 88773.1094 | 100 | 125 | 100 | 100 | 110.8141 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2013-01-26
1:00 - 2:00 | No | Tuesday | Yes | 2013-01-27
2:00 - 3:00 | No | Wednesday | Yes | 2013-02-02
3:00 - 4:00 | No | Thursday | Yes | 2013-02-03
4:00 - 5:00 | No | Friday | Yes | 2013-02-09
5:00 - 6:00 | No | Saturday | Yes | 2013-02-10
6:00 - 7:00 | No | Sunday | Yes | 2013-02-16
7:00 - 8:00 | Yes |  |  | 2013-02-17
8:00 - 9:00 | Yes |  |  | 2013-02-23
9:00 - 10:00 | Yes |  |  | 2013-02-24
10:00 - 11:00 | Yes |  |  | 2013-03-02
11:00 - 12:00 | Yes |  |  | 2013-03-03
12:00 - 13:00 | No |  |  | 2013-03-16
13:00 - 14:00 | Yes |  |  | 2013-03-17
14:00 - 15:00 | Yes |  |  | 2013-03-23
15:00 - 16:00 | Yes |  |  | 2013-03-24
16:00 - 17:00 | No |  |  | 2013-03-30
17:00 - 18:00 | No |  |  | 2013-03-31
18:00 - 19:00 | No |  |  | 2013-04-06
19:00 - 20:00 | No |  |  | 2013-04-07
20:00 - 21:00 | No |  |  | 2013-04-13
21:00 - 22:00 | No |  |  | 2013-04-14
22:00 - 23:00 | No |  |  | 2013-04-20
23:00 - 0:00 | No |  |  | 2013-04-21
2013-04-27
2013-04-28
Generated by PMConverter v1.1.3 |  |  |  | 2013-05-04
2013-05-05
2013-05-11
2013-05-12
2013-05-18
2013-05-19
2013-05-25
2013-05-26
2013-06-01
2013-06-02
2013-06-08
2013-06-09
2013-06-15
2013-06-16
2013-06-22
2013-06-23
2013-06-29
2013-06-30
2013-07-06
2013-07-07
2013-07-13
2013-07-14
2013-07-20
2013-07-21
2013-07-27
2013-07-28
2013-08-03
2013-08-04
2013-08-10
2013-08-11
2013-08-17
2013-08-18
2013-08-24
2013-08-25
2013-08-31
2013-09-01
2013-09-07
2013-09-08
2013-09-14
2013-09-15
2013-09-21
2013-09-22
2013-09-28
2013-09-29
2013-10-05
2013-10-06
2013-10-12
2013-10-13
2013-10-19
2013-10-20
2013-10-26
2013-10-27
2013-11-02
2013-11-03
2013-11-09
2013-11-10
2013-11-16
2013-11-17
2013-11-23
2013-11-24
2013-11-30
2013-12-01
2013-12-07
2013-12-08
2013-12-14
2013-12-15
2013-12-21
2013-12-22
2013-12-28
2013-12-29
2014-01-04
2014-01-05
2014-01-11
2014-01-12
2014-01-18
2014-01-19
2014-01-25
2014-01-26
2014-02-01
2014-02-02
2014-02-08
2014-02-09
2014-02-15
2014-02-16
2014-02-22
2014-02-23
2014-03-01
2014-03-02
2014-03-08
2014-03-09
2014-03-15
2014-03-16
2014-03-22
2014-03-23
2014-03-29
2014-03-30
2014-04-05
2014-04-06
2014-04-12
2014-04-13
2014-04-19
2014-04-20
2014-04-26
2014-04-27
2014-05-03
2014-05-04
2014-05-10
2014-05-11
2014-05-17
2014-05-18
2014-05-24
2014-05-25
2014-05-31
2014-06-01
2014-06-07
2014-06-08
2014-06-14
2014-06-15
2014-06-21
2014-06-22
2014-06-28
2014-06-29
2014-07-05
2014-07-06
2013-07-22
2013-07-23
2013-07-24
2013-07-25
2013-07-26
2013-07-29
2013-07-30
2013-07-31
2013-08-01
2013-08-02
2013-08-05
2013-08-06
2013-08-07
2013-08-08
2013-08-09

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
T1 | 2013-01-25 07:00 | 2013-02-04 07:00 | 10455.7402 | 10455.7403 | 10455.7402 | 2013-02-01 16:00 | 4.2915e-05 | 100% | 4.2915e-05 | 100% | 0 | 100% | 100% | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 962181.5584 | 962181.5545 | 962181.5545 | 962181.5584 | 962181.5506 | 962181.5545 | 962181.5545 | 962181.5552 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T2 | 2013-02-04 07:00 | 2013-03-04 07:00 | 44479.3203 | 44479.3204 | 44479.3203 | 2013-03-01 16:00 | 0.00013113 | 100% | 0.00013113 | 100% | 0 | 100% | 100% | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 2013-12-30 16:00 | 962181.5583 | 962181.5556 | 962181.5556 | 962181.5583 | 962181.5529 | 962181.5556 | 962181.5556 | 962181.5561 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T3 | 2013-03-04 07:00 | 2013-04-01 07:00 | 420765.8477 | 417645.8477 | 420765.8477 | 2013-03-26 16:00 | -3120 | 99.26% | -3120 | 99.26% | -3d | 93.75% | 100% | 2013-12-31 14:00 | 2014-01-01 14:00 | 2014-01-03 10:00 | 2013-12-31 10:00 | 2014-01-01 14:00 | 2014-01-03 08:00 | 2014-01-02 16:00 | 2014-01-21 09:00 | 2014-01-22 14:00 | 965301.5584 | 969369.482 | 969369.482 | 1001603.9391 | 973467.7948 | 1005943.0576 | 969369.482 | 975526.9372 | 0.9375 | 0.99258 | 0.99258 | 1 | -3 | 0.99258 | 1 | 0.9375 | 1
T4 | 2013-04-01 07:00 | 2013-05-06 07:00 | 492368.0664 | 425965.8477 | 441565.8477 | 2013-04-26 16:00 | -66402.2188 | 86.51% | -15600 | 96.47% | -5d | 93.15% | 100% | 2014-01-21 14:00 | 2014-02-18 14:00 | 2014-03-04 10:00 | 2014-01-13 15:00 | 2014-02-18 14:00 | 2014-02-27 14:00 | 2014-01-06 16:00 | 2014-01-22 15:00 | 2014-01-31 08:00 | 977781.5584 | 997419.201 | 1061370.2149 | 1017209.1842 | 1084069.096 | 1038290.7711 | 1009131.4106 | 1001267.5868 | 0.93151 | 0.96467 | 0.86514 | 1 | -5 | 0.96467 | 1 | 0.93151 | 1
T5 | 2013-05-06 07:00 | 2013-06-03 07:00 | 531491.1855 | 497168.0664 | 504128.0664 | 2013-05-10 16:00 | -34323.1191 | 93.54% | -6960 | 98.62% | -15d | 83.87% | 100% | 2014-01-10 08:00 | 2014-01-21 14:00 | 2014-01-27 09:00 | 2014-01-07 16:00 | 2014-01-21 14:00 | 2014-01-23 15:00 | 2014-01-20 16:00 | 2014-02-28 16:00 | 2014-03-05 11:00 | 969141.5584 | 975651.4172 | 1001244.814 | 1058567.2299 | 1008204.0955 | 1066328.9847 | 980557.0804 | 990189.4132 | 0.83871 | 0.98619 | 0.93542 | 1 | -15 | 0.98619 | 1 | 0.83871 | 1
T6 | 2013-06-03 07:00 | 2013-07-01 07:00 | 592736.0156 | 525091.1856 | 532691.1855 | 2013-05-16 09:00 | -67644.83 | 88.59% | -7599.9999 | 98.57% | -31d 6h | 71.9% | 100% | 2014-01-22 08:00 | 2014-02-10 11:00 | 2014-02-14 09:00 | 2014-01-16 15:00 | 2014-02-10 11:00 | 2014-02-12 12:00 | 2014-02-12 14:00 | 2014-05-05 11:00 | 2014-05-08 11:00 | 969781.5583 | 976107.8629 | 1026089.6906 | 1140583.0271 | 1033230.9809 | 1149381.4569 | 985277.3614 | 1001475.3188 | 0.71903 | 0.98573 | 0.88588 | 1 | -31.75 | 0.98573 | 1 | 0.71903 | 1
T7 | 2013-07-01 07:00 | 2013-08-05 07:00 | 614876.1357 | 531491.1855 | 540371.1855 | 2013-06-07 16:00 | -83384.9502 | 86.44% | -8880 | 98.36% | -30d | 76.56% | 100% | 2014-01-27 15:00 | 2014-02-18 15:00 | 2014-02-25 10:00 | 2014-01-23 10:00 | 2014-02-18 15:00 | 2014-02-21 09:00 | 2014-02-10 16:00 | 2014-04-08 08:00 | 2014-04-10 16:00 | 971061.5584 | 978257.4078 | 1038632.0022 | 1102905.5501 | 1046956.7989 | 1112304.2105 | 989132.7553 | 998562.9224 | 0.76562 | 0.98357 | 0.86439 | 1 | -30 | 0.98357 | 1 | 0.76562 | 1
T8 | 2013-08-05 07:00 | 2013-09-02 07:00 | 638959.7259 | 557068.0762 | 564988.0762 | 2013-06-18 16:00 | -81891.6497 | 87.18% | -7920 | 98.6% | -38d | 73.43% | 100% | 2014-01-27 11:00 | 2014-02-14 12:00 | 2014-02-20 10:00 | 2014-01-24 10:00 | 2014-02-14 12:00 | 2014-02-18 10:00 | 2014-02-20 16:00 | 2014-04-24 15:00 | 2014-04-29 09:00 | 970101.5584 | 975861.1754 | 1029655.162 | 1116714.0567 | 1036261.4701 | 1124558.1066 | 985599.9278 | 997968.7344 | 0.73427 | 0.98598 | 0.87184 | 1 | -38 | 0.98598 | 1 | 0.73427 | 1
T9 | 2013-09-02 07:00 | 2013-10-07 07:00 | 750824.1053 | 637183.2959 | 640783.2959 | 2013-08-26 16:00 | -113640.8094 | 84.86% | -3600 | 99.44% | -29d | 82.74% | 100% | 2014-02-05 16:00 | 2014-02-25 15:00 | 2014-02-27 10:00 | 2014-02-04 10:00 | 2014-02-25 15:00 | 2014-02-26 10:00 | 2014-02-07 16:00 | 2014-03-06 14:00 | 2014-03-07 10:00 | 965781.5584 | 967617.7549 | 1023744.5745 | 1033586.9513 | 1025908.2542 | 1035806.2392 | 977487.223 | 978977.3171 | 0.82738 | 0.99438 | 0.84865 | 1 | -29 | 0.99438 | 1 | 0.82738 | 1
T10 | 2013-10-07 07:00 | 2013-11-04 07:00 | 870408.449 | 704441.9764 | 708041.9764 | 2013-09-26 16:00 | -165966.4726 | 80.93% | -3599.9999 | 99.49% | -26d | 86.17% | 100% | 2014-02-24 11:00 | 2014-03-14 16:00 | 2014-03-18 10:00 | 2014-02-18 15:00 | 2014-03-14 16:00 | 2014-03-17 11:00 | 2014-02-04 16:00 | 2014-02-19 14:00 | 2014-02-20 08:00 | 965781.5583 | 967098.7179 | 1026504.983 | 1007147.1703 | 1028132.4652 | 1008675.7258 | 977138.1891 | 974226.8401 | 0.8617 | 0.99492 | 0.80932 | 1 | -26 | 0.99492 | 1 | 0.8617 | 1
T11 | 2013-11-04 07:00 | 2013-12-02 07:00 | 942021.5584 | 930706.892 | 935581.5584 | 2013-11-14 08:00 | -11314.6664 | 98.8% | -4874.6664 | 99.48% | -11d 7h | 94.29% | 99.18% | 2014-01-02 14:00 | 2014-01-02 14:00 | 2014-01-03 16:00 | 2014-01-02 11:00 | 2014-01-02 14:00 | 2014-01-02 15:00 | 2014-01-15 15:00 | 2014-01-17 15:00 | 2014-01-17 16:00 | 967056.2248 | 967221.0764 | 967438.8644 | 968961.9567 | 967605.7201 | 969136.7897 | 967264.3954 | 967554.5726 | 0.94291 | 0.99479 | 0.98799 | 0.99176 | -11.875 | 0.99479 | 1 | 0.94291 | 1
T12 | 2013-12-02 07:00 | 2014-01-06 07:00 | 962181.5584 | 957573.5582 | 966581.5584 | 2013-12-24 08:00 | -4608.0002 | 99.52% | -9008.0002 | 99.07% | -8d 7h | 96.19% | 100% | 2014-01-01 08:00 | 2014-01-01 08:00 | 2014-01-03 09:00 | 2014-01-07 08:00 | 2014-01-07 08:00 | 2014-01-07 08:00 | 2014-01-10 15:00 | 2014-01-13 08:00 | 2014-01-13 08:00 | 971189.5586 | 971232.9066 | 971211.733 | 971372.0282 | 971255.2896 | 971417.0927 | 971228.6564 | 971260.0807 | 0.96191 | 0.99068 | 0.99521 | 1 | -8.875 | 0.99068 | 1 | 0.96191 | 1
Actual Schedule | 2014-01-06 07:00 | 2014-02-03 07:00 | 962181.5584 | 962181.5584 | 972341.5584 | 2013-12-30 16:00 | 0 | 100% | -10160 | 98.96% | -24d | 90.51% | 100% | 2013-12-30 16:00 | 2013-12-30 16:00 | 2014-01-02 10:00 | 2014-01-31 16:00 | 2014-01-31 16:00 | 2014-01-31 16:00 | 2014-01-31 16:00 | 2014-01-31 16:00 | 2014-01-31 16:00 | 972341.5584 | 972341.5584 | 972341.5584 | 972341.5584 | 972341.5584 | 972341.5584 | 972341.5584 | 972341.5584 | 0.90514 | 0.98955 | 1 | 1 | -24 | 0.98955 | 1 | 0.90514 | 1