## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Bridge (5) | 1 |  |  | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 | 282.375
1 | Voorbereidende werken afbraak | 1.1 |  | FS2 | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 4.375
2 | Afbraak | 1.2 | 1FS | FS3 | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 1.375
3 | Voorbereiding werkplatform spoor A | 1.3 | 2FS | FS4;FS6 | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 4.375
4 | Installatie paalfunderingen | 1.4 | 3FS | FS5 | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 1.375
5 | Boren paalfundering spoor A | 1.5 | 4FS | FS7;FS8 | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 13.375
6 | Voorbereiding werkplatform spoor B | 1.6 | 3FS |  | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 9.375
7 | Boren paalfundering spoor B | 1.7 | 5FS |  | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 13.375
8 | Grachtelementen A | 1.8 | 5FS | FS9 | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2.375
9 | Plaatsen schanskorven A | 1.9 | 8FS | FS10 | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 8.375
10 | Zuiveringsbeton spoor A | 1.10 | 9FS | FS11;FS14 | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 0.375
11 | Grachtelementen B | 1.11 | 10FS | FS12 | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 18.375
12 | Schanskorven B | 1.12 | 11FS | FS13 | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 8.375
13 | Zuiveringsbeton B | 1.13 | 12FS | FS16 | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 0.375
14 | Betonneren palen A | 1.14 | 10FS | FS15 | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 1.375
15 | Funderingszool A | 1.15 | 14FS |  | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 4.375
16 | Betonneren palen B | 1.16 | 13FS | FS17 | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 3.375
17 | Funderingszool B | 1.17 | 16FS | SF18+1w 3d | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 6.375
33 | Boog fase 1 | 1.18 |  |  | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 | 15.375
18 | Plaatsen bekisting | 1.18.1 | 17SF+1w 3d | FS19 | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2.375
19 | Wapenen | 1.18.2 | 18FS | FS20 | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 11.375
20 | Betonneren | 1.18.3 | 19FS | SF21+2w 1d | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 0.375
34 | Boog fase 2 | 1.19 |  |  | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 | 34.375
21 | Verplaatsen bekisting | 1.19.1 | 20SF+2w 1d | FS22;FS25 | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 6.375
22 | Wapenen | 1.19.2 | 21FS | FS23 | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 11.375
23 | Betonneren | 1.19.3 | 22FS | SF24+1w 5d | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 0.375
24 | Ontkisten | 1.19.4 | 23SF+1w 5d | FS26 | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 | 0.375
25 | Wanden fase 1 | 1.20 | 21FS | FS30 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 34.375
26 | Wanden fase 2 | 1.21 | 24FS | FS27 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 | 34.375
27 | Waterdichting | 1.22 | 26FS | FS28 | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 | 13.375
28 | Aanvullen | 1.23 | 27FS | FS29 | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 | 6.375
29 | Wegenis | 1.24 | 28FS | FS32 | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 | 41.375
30 | Metselwerk fase 1 | 1.25 | 25FS | FS31 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 | 20.375
31 | Metselwerk fase 2 | 1.26 | 30FS |  | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 | 20.375
32 | Afwerkingen | 1.27 | 29FS |  | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 | 27.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Bridge (5) | 1560h |  |  |  |  | 99 | 100 | 101
1 | Voorbereidende werken afbraak | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
2 | Afbraak | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
3 | Voorbereiding werkplatform spoor A | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
4 | Installatie paalfunderingen | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
5 | Boren paalfundering spoor A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Voorbereiding werkplatform spoor B | 64h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
7 | Boren paalfundering spoor B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Grachtelementen A | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Plaatsen schanskorven A | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Zuiveringsbeton spoor A | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
11 | Grachtelementen B | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Schanskorven B | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Zuiveringsbeton B | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
14 | Betonneren palen A | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
15 | Funderingszool A | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
16 | Betonneren palen B | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
17 | Funderingszool B | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
33 | Boog fase 1 | 96h |  |  |  |  | 99 | 100 | 101
18 | Plaatsen bekisting | 24h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
19 | Wapenen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
34 | Boog fase 2 | 200h |  |  |  |  | 99 | 100 | 101
21 | Verplaatsen bekisting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Wapenen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
24 | Ontkisten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Wanden fase 1 | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Wanden fase 2 | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Waterdichting | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
28 | Aanvullen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Wegenis | 240h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
30 | Metselwerk fase 1 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Metselwerk fase 2 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Afwerkingen | 160h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200

## Project Control - TP1
| TP Status Date | 2014-12-01 07:00 |  | TP Name | T1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 22d | [5 empty] | 194758.9893 |  | 23.39% |  | 194758.9894 | 194758.9893
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 8d | 49194.6406 | 3040 | 2d | 0 | 0 | 49194.6406 | 3040 | 80% | Started | 49194.6408 | 49194.6406 | 100 | 80 | 80 | 100 | 94.1801 | 80
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 |  | 0 | 0 | 49542.1289 | 10d | 0 | 0 | 0 | 49542.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 |  | 0 | 0 | 5918.28 | 3d | 0 | 0 | 0 | 5918.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 |  | 0 | 0 | 9004.6299 | 7d | 0 | 0 | 0 | 9004.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 |  | 0 | 0 | 3180.75 | 1d | 0 | 0 | 0 | 3180.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 |  | 0 | 0 | 5598.3701 | 3d | 0 | 0 | 0 | 5598.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 |  | 0 | 0 | 8013.29 | 7d | 0 | 0 | 0 | 8013.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 |  | 0 | 0 | 2365.85 | 1d | 0 | 0 | 0 | 2365.85 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 |  | 0 | 0 | 60312.1602 | 2d | 0 | 0 | 0 | 60312.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 |  | 0 | 0 | 13805.8101 | 5d | 0 | 0 | 0 | 13805.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 |  | 0 | 0 | 51696.1406 | 2d | 0 | 0 | 0 | 51696.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 |  | 0 | 0 | 16027.4404 | 5d | 0 | 0 | 0 | 16027.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 |  | 0 | 0 | 15822.7197 | 3d | 0 | 0 | 0 | 15822.7197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 |  | 0 | 0 | 27586.2402 | 8d | 0 | 0 | 0 | 27586.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 |  | 0 | 0 | 23260.5801 | 1d | 0 | 0 | 0 | 23260.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 |  | 0 | 0 | 6572.8 | 5d | 0 | 0 | 0 | 6572.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 |  | 0 | 0 | 21352.8096 | 8d | 0 | 0 | 0 | 21352.8096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 |  | 0 | 0 | 25892.6992 | 1d | 0 | 0 | 0 | 25892.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 |  | 0 | 0 | 8172.8599 | 1d | 0 | 0 | 0 | 8172.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 |  | 0 | 0 | 30149.0195 | 25d | 0 | 0 | 0 | 30149.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 |  | 0 | 0 | 27290.0596 | 25d | 0 | 0 | 0 | 27290.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 |  | 0 | 0 | 46152.9609 | 10d | 0 | 0 | 0 | 46152.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 |  | 0 | 0 | 36216.3203 | 5d | 0 | 0 | 0 | 36216.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 |  | 0 | 0 | 52980.4004 | 30d | 0 | 0 | 0 | 52980.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 |  | 0 | 0 | 7160.59 | 15d | 0 | 0 | 0 | 7160.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 |  | 0 | 0 | 8281.21 | 15d | 0 | 0 | 0 | 8281.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2015-01-05 07:00 |  | TP Name | T2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 37d | [5 empty] | 330315.3083 |  | 39.68% |  | 330315.3084 | 330315.3083
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 2d | 4558.3701 | 1040 | 1d | 0 | 0 | 4558.3701 | 1040 | 66.67% | Started | 4558.3702 | 4558.3701 | 100 | 66.6667 | 66.6667 | 100 | 81.4232 | 66.6667
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 |  | 0 | 0 | 8013.29 | 7d | 0 | 0 | 0 | 8013.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 |  | 0 | 0 | 2365.85 | 1d | 0 | 0 | 0 | 2365.85 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 |  | 0 | 0 | 13805.8101 | 5d | 0 | 0 | 0 | 13805.8101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 |  | 0 | 0 | 51696.1406 | 2d | 0 | 0 | 0 | 51696.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 |  | 0 | 0 | 16027.4404 | 5d | 0 | 0 | 0 | 16027.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 |  | 0 | 0 | 15822.7197 | 3d | 0 | 0 | 0 | 15822.7197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 |  | 0 | 0 | 27586.2402 | 8d | 0 | 0 | 0 | 27586.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 |  | 0 | 0 | 23260.5801 | 1d | 0 | 0 | 0 | 23260.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 |  | 0 | 0 | 6572.8 | 5d | 0 | 0 | 0 | 6572.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 |  | 0 | 0 | 21352.8096 | 8d | 0 | 0 | 0 | 21352.8096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 |  | 0 | 0 | 25892.6992 | 1d | 0 | 0 | 0 | 25892.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 |  | 0 | 0 | 8172.8599 | 1d | 0 | 0 | 0 | 8172.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 |  | 0 | 0 | 30149.0195 | 25d | 0 | 0 | 0 | 30149.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 |  | 0 | 0 | 27290.0596 | 25d | 0 | 0 | 0 | 27290.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 |  | 0 | 0 | 46152.9609 | 10d | 0 | 0 | 0 | 46152.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 |  | 0 | 0 | 36216.3203 | 5d | 0 | 0 | 0 | 36216.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 |  | 0 | 0 | 52980.4004 | 30d | 0 | 0 | 0 | 52980.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 |  | 0 | 0 | 7160.59 | 15d | 0 | 0 | 0 | 7160.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 |  | 0 | 0 | 8281.21 | 15d | 0 | 0 | 0 | 8281.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2015-02-02 07:00 |  | TP Name | T3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 57d | [5 empty] | 423263.8395 |  | 50.84% |  | 423263.8395 | 423263.8395
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 |  | 0 | 0 | 15822.7197 | 3d | 0 | 0 | 0 | 15822.7197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 |  | 0 | 0 | 27586.2402 | 8d | 0 | 0 | 0 | 27586.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 |  | 0 | 0 | 23260.5801 | 1d | 0 | 0 | 0 | 23260.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 |  | 0 | 0 | 6572.8 | 5d | 0 | 0 | 0 | 6572.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 |  | 0 | 0 | 21352.8096 | 8d | 0 | 0 | 0 | 21352.8096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 |  | 0 | 0 | 25892.6992 | 1d | 0 | 0 | 0 | 25892.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 |  | 0 | 0 | 8172.8599 | 1d | 0 | 0 | 0 | 8172.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 |  | 0 | 0 | 30149.0195 | 25d | 0 | 0 | 0 | 30149.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 |  | 0 | 0 | 27290.0596 | 25d | 0 | 0 | 0 | 27290.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 |  | 0 | 0 | 46152.9609 | 10d | 0 | 0 | 0 | 46152.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 |  | 0 | 0 | 36216.3203 | 5d | 0 | 0 | 0 | 36216.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 |  | 0 | 0 | 52980.4004 | 30d | 0 | 0 | 0 | 52980.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 |  | 0 | 0 | 7160.59 | 15d | 0 | 0 | 0 | 7160.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 |  | 0 | 0 | 8281.21 | 15d | 0 | 0 | 0 | 8281.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2015-03-02 07:00 |  | TP Name | T4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 77d | [5 empty] | 489933.3795 |  | 58.85% |  | 489933.3795 | 489933.3795
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 100% |  | 66669.54 | 66669.54
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 100% | Finished | 15822.7197 | 15822.7197 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 100% | Finished | 27586.2402 | 27586.2402 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 100% | Finished | 23260.5801 | 23260.5801 | 100 | 100 | 100 | 100 | 100 | 100
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 |  | 0 | 0 | 6572.8 | 5d | 0 | 0 | 0 | 6572.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 |  | 0 | 0 | 21352.8096 | 8d | 0 | 0 | 0 | 21352.8096 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 |  | 0 | 0 | 25892.6992 | 1d | 0 | 0 | 0 | 25892.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 |  | 0 | 0 | 8172.8599 | 1d | 0 | 0 | 0 | 8172.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 |  | 0 | 0 | 30149.0195 | 25d | 0 | 0 | 0 | 30149.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 |  | 0 | 0 | 27290.0596 | 25d | 0 | 0 | 0 | 27290.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 |  | 0 | 0 | 46152.9609 | 10d | 0 | 0 | 0 | 46152.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 |  | 0 | 0 | 36216.3203 | 5d | 0 | 0 | 0 | 36216.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 |  | 0 | 0 | 52980.4004 | 30d | 0 | 0 | 0 | 52980.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 |  | 0 | 0 | 7160.59 | 15d | 0 | 0 | 0 | 7160.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 |  | 0 | 0 | 8281.21 | 15d | 0 | 0 | 0 | 8281.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2015-04-06 07:00 |  | TP Name | T5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 102d | [5 empty] | 568700.7079 |  | 68.31% |  | 568700.7082 | 569740.7079
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 100% |  | 66669.54 | 66669.54
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 100% | Finished | 15822.7197 | 15822.7197 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 100% | Finished | 27586.2402 | 27586.2402 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 100% | Finished | 23260.5801 | 23260.5801 | 100 | 100 | 100 | 100 | 100 | 100
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 20d | [5 empty] | 53818.3088 |  | 86.82% |  | 53818.3088 | 53818.3088
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 2015-03-09 07:00 | 5d | 6572.8 | 0 | 0 | 0 | 0 | 6572.8 | 0 | 100% | Finished | 6572.8 | 6572.8 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 2015-03-16 07:00 | 8d | 21352.8096 | 0 | 0 | 0 | 0 | 21352.8096 | 0 | 100% | Finished | 21352.8096 | 21352.8096 | 100 | 100 | 100 | 100 | 100 | 100
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 2015-03-26 07:00 | 1d | 25892.6992 | 0 | 0 | 0 | 0 | 25892.6992 | 0 | 100% | Finished | 25892.6992 | 25892.6992 | 100 | 100 | 100 | 100 | 100 | 100
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 |  | 0 | 0 | 8172.8599 | 1d | 0 | 0 | 0 | 8172.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 2015-03-16 07:00 | 15d | 24949.0195 | 5200 | 10d | 0 | 0 | 24949.0195 | 5200 | 60% | Started | 24949.0198 | 25989.0195 | 100 | 60 | 60 | 100 | 82.7523 | 60
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 |  | 0 | 0 | 27290.0596 | 25d | 0 | 0 | 0 | 27290.0596 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 |  | 0 | 0 | 46152.9609 | 10d | 0 | 0 | 0 | 46152.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 |  | 0 | 0 | 36216.3203 | 5d | 0 | 0 | 0 | 36216.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 |  | 0 | 0 | 52980.4004 | 30d | 0 | 0 | 0 | 52980.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 |  | 0 | 0 | 7160.59 | 15d | 0 | 0 | 0 | 7160.59 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 |  | 0 | 0 | 8281.21 | 15d | 0 | 0 | 0 | 8281.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2015-05-04 07:00 |  | TP Name | T6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 122d | [5 empty] | 609724.2173 |  | 73.24% |  | 609724.2177 | 611484.2173
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 100% |  | 66669.54 | 66669.54
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 100% | Finished | 15822.7197 | 15822.7197 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 100% | Finished | 27586.2402 | 27586.2402 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 100% | Finished | 23260.5801 | 23260.5801 | 100 | 100 | 100 | 100 | 100 | 100
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 25d | [5 empty] | 61991.1687 |  | 100% |  | 61991.1687 | 61991.1687
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 2015-03-09 07:00 | 5d | 6572.8 | 0 | 0 | 0 | 0 | 6572.8 | 0 | 100% | Finished | 6572.8 | 6572.8 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 2015-03-16 07:00 | 8d | 21352.8096 | 0 | 0 | 0 | 0 | 21352.8096 | 0 | 100% | Finished | 21352.8096 | 21352.8096 | 100 | 100 | 100 | 100 | 100 | 100
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 2015-03-26 07:00 | 1d | 25892.6992 | 0 | 0 | 0 | 0 | 25892.6992 | 0 | 100% | Finished | 25892.6992 | 25892.6992 | 100 | 100 | 100 | 100 | 100 | 100
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 | 2015-04-10 07:00 | 1d | 8172.8599 | 0 | 0 | 0 | 0 | 8172.8599 | 0 | 100% | Finished | 8172.8599 | 8172.8599 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 2015-03-16 07:00 | 25d | 30149.0195 | 0 | 0 | 0 | 0 | 30149.0195 | 0 | 100% | Finished | 30149.0195 | 30149.0195 | 100 | 100 | 100 | 100 | 100 | 100
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 | 2015-04-13 07:00 | 15d | 22490.0596 | 4800 | 10d | 0 | 0 | 22490.0596 | 4800 | 60% | Started | 22490.0599 | 23450.0596 | 100 | 60 | 60 | 100 | 82.4112 | 60
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 |  | 0 | 0 | 46152.9609 | 10d | 0 | 0 | 0 | 46152.9609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 |  | 0 | 0 | 36216.3203 | 5d | 0 | 0 | 0 | 36216.3203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 |  | 0 | 0 | 52980.4004 | 30d | 0 | 0 | 0 | 52980.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 | 2015-04-20 07:00 | 10d | 5160.59 | 2000 | 5d | 0 | 0 | 5160.59 | 2000 | 66.67% | Started | 5160.5901 | 5960.59 | 100 | 66.6667 | 66.6667 | 100 | 72.0693 | 66.6667
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 |  | 0 | 0 | 8281.21 | 15d | 0 | 0 | 0 | 8281.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2015-06-01 07:00 |  | TP Name | T7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 142d | [5 empty] | 670958.3882 |  | 80.6% |  | 670958.3882 | 702854.7085
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 100% |  | 66669.54 | 66669.54
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 100% | Finished | 15822.7197 | 15822.7197 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 100% | Finished | 27586.2402 | 27586.2402 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 100% | Finished | 23260.5801 | 23260.5801 | 100 | 100 | 100 | 100 | 100 | 100
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 25d | [5 empty] | 61991.1687 |  | 100% |  | 61991.1687 | 61991.1687
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 2015-03-09 07:00 | 5d | 6572.8 | 0 | 0 | 0 | 0 | 6572.8 | 0 | 100% | Finished | 6572.8 | 6572.8 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 2015-03-16 07:00 | 8d | 21352.8096 | 0 | 0 | 0 | 0 | 21352.8096 | 0 | 100% | Finished | 21352.8096 | 21352.8096 | 100 | 100 | 100 | 100 | 100 | 100
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 2015-03-26 07:00 | 1d | 25892.6992 | 0 | 0 | 0 | 0 | 25892.6992 | 0 | 100% | Finished | 25892.6992 | 25892.6992 | 100 | 100 | 100 | 100 | 100 | 100
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 | 2015-04-10 07:00 | 1d | 8172.8599 | 0 | 0 | 0 | 0 | 8172.8599 | 0 | 100% | Finished | 8172.8599 | 8172.8599 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 2015-03-16 07:00 | 25d | 30149.0195 | 0 | 0 | 0 | 0 | 30149.0195 | 0 | 100% | Finished | 30149.0195 | 30149.0195 | 100 | 100 | 100 | 100 | 100 | 100
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 | 2015-04-13 07:00 | 25d | 27290.0596 | 0 | 0 | 0 | 0 | 27290.0596 | 0 | 100% | Finished | 27290.0596 | 27290.0596 | 100 | 100 | 100 | 100 | 100 | 100
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 | 2015-05-18 07:00 | 10d | 46152.9609 | 0 | 0 | 0 | 0 | 46152.9609 | 0 | 100% | Finished | 46152.9609 | 46152.9609 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 |  | 0 | 0 | 36216.3203 | 5d | 0 | 0 | 0 | 36216.3203 | 0% | Not Started | 0 | 31896.3203 | 100 |  | 0 | 100 |  | 0
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 |  | 0 | 0 | 52980.4004 | 30d | 0 | 0 | 0 | 52980.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 | 2015-04-20 07:00 | 15d | 7160.59 | 0 | 0 | 0 | 0 | 7160.59 | 0 | 100% | Finished | 7160.59 | 7160.59 | 100 | 100 | 100 | 100 | 100 | 100
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 | 2015-05-11 07:00 | 15d | 8281.21 | 0 | 0 | 0 | 0 | 8281.21 | 0 | 100% | Finished | 8281.21 | 8281.21 | 100 | 100 | 100 | 100 | 100 | 100
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2015-07-01 07:00 |  | TP Name | T8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 164d | [5 empty] | 749355.1089 |  | 90.01% |  | 749355.1095 | 748275.1089
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 100% |  | 66669.54 | 66669.54
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 100% | Finished | 15822.7197 | 15822.7197 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 100% | Finished | 27586.2402 | 27586.2402 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 100% | Finished | 23260.5801 | 23260.5801 | 100 | 100 | 100 | 100 | 100 | 100
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 25d | [5 empty] | 61991.1687 |  | 100% |  | 61991.1687 | 61991.1687
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 2015-03-09 07:00 | 5d | 6572.8 | 0 | 0 | 0 | 0 | 6572.8 | 0 | 100% | Finished | 6572.8 | 6572.8 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 2015-03-16 07:00 | 8d | 21352.8096 | 0 | 0 | 0 | 0 | 21352.8096 | 0 | 100% | Finished | 21352.8096 | 21352.8096 | 100 | 100 | 100 | 100 | 100 | 100
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 2015-03-26 07:00 | 1d | 25892.6992 | 0 | 0 | 0 | 0 | 25892.6992 | 0 | 100% | Finished | 25892.6992 | 25892.6992 | 100 | 100 | 100 | 100 | 100 | 100
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 | 2015-04-10 07:00 | 1d | 8172.8599 | 0 | 0 | 0 | 0 | 8172.8599 | 0 | 100% | Finished | 8172.8599 | 8172.8599 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 2015-03-16 07:00 | 25d | 30149.0195 | 0 | 0 | 0 | 0 | 30149.0195 | 0 | 100% | Finished | 30149.0195 | 30149.0195 | 100 | 100 | 100 | 100 | 100 | 100
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 | 2015-04-13 07:00 | 25d | 27290.0596 | 0 | 0 | 0 | 0 | 27290.0596 | 0 | 100% | Finished | 27290.0596 | 27290.0596 | 100 | 100 | 100 | 100 | 100 | 100
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 | 2015-05-18 07:00 | 10d | 46152.9609 | 0 | 0 | 0 | 0 | 46152.9609 | 0 | 100% | Finished | 46152.9609 | 46152.9609 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 | 2015-06-01 07:00 | 5d | 36216.3203 | 0 | 0 | 0 | 0 | 36216.3203 | 0 | 100% | Finished | 36216.3203 | 36216.3203 | 100 | 100 | 100 | 100 | 100 | 100
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 | 2015-06-08 07:00 | 20d | 42180.4004 | 10800 | 10d | 0 | 0 | 42180.4004 | 10800 | 66.67% | Started | 42180.401 | 41100.4004 | 100 | 66.6667 | 66.6667 | 100 | 79.6151 | 66.6667
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 | 2015-04-20 07:00 | 15d | 7160.59 | 0 | 0 | 0 | 0 | 7160.59 | 0 | 100% | Finished | 7160.59 | 7160.59 | 100 | 100 | 100 | 100 | 100 | 100
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 | 2015-05-11 07:00 | 15d | 8281.21 | 0 | 0 | 0 | 0 | 8281.21 | 0 | 100% | Finished | 8281.21 | 8281.21 | 100 | 100 | 100 | 100 | 100 | 100
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 |  | 0 | 0 | 72342.3516 | 20d | 0 | 0 | 0 | 72342.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2015-08-03 07:00 |  | TP Name | T9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 187d | [5 empty] | 816897.4604 |  | 98.13% |  | 816897.4604 | 820017.4604
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 100% |  | 66669.54 | 66669.54
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 100% | Finished | 15822.7197 | 15822.7197 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 100% | Finished | 27586.2402 | 27586.2402 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 100% | Finished | 23260.5801 | 23260.5801 | 100 | 100 | 100 | 100 | 100 | 100
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 25d | [5 empty] | 61991.1687 |  | 100% |  | 61991.1687 | 61991.1687
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 2015-03-09 07:00 | 5d | 6572.8 | 0 | 0 | 0 | 0 | 6572.8 | 0 | 100% | Finished | 6572.8 | 6572.8 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 2015-03-16 07:00 | 8d | 21352.8096 | 0 | 0 | 0 | 0 | 21352.8096 | 0 | 100% | Finished | 21352.8096 | 21352.8096 | 100 | 100 | 100 | 100 | 100 | 100
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 2015-03-26 07:00 | 1d | 25892.6992 | 0 | 0 | 0 | 0 | 25892.6992 | 0 | 100% | Finished | 25892.6992 | 25892.6992 | 100 | 100 | 100 | 100 | 100 | 100
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 | 2015-04-10 07:00 | 1d | 8172.8599 | 0 | 0 | 0 | 0 | 8172.8599 | 0 | 100% | Finished | 8172.8599 | 8172.8599 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 2015-03-16 07:00 | 25d | 30149.0195 | 0 | 0 | 0 | 0 | 30149.0195 | 0 | 100% | Finished | 30149.0195 | 30149.0195 | 100 | 100 | 100 | 100 | 100 | 100
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 | 2015-04-13 07:00 | 25d | 27290.0596 | 0 | 0 | 0 | 0 | 27290.0596 | 0 | 100% | Finished | 27290.0596 | 27290.0596 | 100 | 100 | 100 | 100 | 100 | 100
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 | 2015-05-18 07:00 | 10d | 46152.9609 | 0 | 0 | 0 | 0 | 46152.9609 | 0 | 100% | Finished | 46152.9609 | 46152.9609 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 | 2015-06-01 07:00 | 5d | 36216.3203 | 0 | 0 | 0 | 0 | 36216.3203 | 0 | 100% | Finished | 36216.3203 | 36216.3203 | 100 | 100 | 100 | 100 | 100 | 100
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 | 2015-06-08 07:00 | 30d | 52980.4004 | 0 | 0 | 0 | 0 | 52980.4004 | 0 | 100% | Finished | 52980.4004 | 52980.4004 | 100 | 100 | 100 | 100 | 100 | 100
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 | 2015-04-20 07:00 | 15d | 7160.59 | 0 | 0 | 0 | 0 | 7160.59 | 0 | 100% | Finished | 7160.59 | 7160.59 | 100 | 100 | 100 | 100 | 100 | 100
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 | 2015-05-11 07:00 | 15d | 8281.21 | 0 | 0 | 0 | 0 | 8281.21 | 0 | 100% | Finished | 8281.21 | 8281.21 | 100 | 100 | 100 | 100 | 100 | 100
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 | 2015-07-20 07:00 | 10d | 56742.3516 | 15600 | 10d | 0 | 0 | 56742.3516 | 15600 | 50% | Started | 56742.3516 | 59862.3516 | 100 | 50 | 50 | 100 | 78.4359 | 50

## TP10
| TP Status Date | 2015-09-07 07:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (5) | 2014-11-03 07:00 | 2015-08-12 16:00 | 195d |  |  | 579697.4604 |  |  | 832497.4604 |  | 197d | [5 empty] | 832497.4604 |  | 100% |  | 832497.4604 | 832497.4604
1 | Voorbereidende werken afbraak | 2014-11-03 07:00 | 2014-11-07 16:00 | 5d |  | 0 | 22673.4492 | 130 | 5200 | 27873.4492 | 2014-11-03 07:00 | 5d | 27873.4492 | 0 | 0 | 0 | 0 | 27873.4492 | 0 | 100% | Finished | 27873.4492 | 27873.4492 | 100 | 100 | 100 | 100 | 100 | 100
2 | Afbraak | 2014-11-08 07:00 | 2014-11-09 16:00 | 2d |  | 0 | 59376.7305 | 350 | 5600 | 64976.7305 | 2014-11-08 07:00 | 2d | 64976.7305 | 0 | 0 | 0 | 0 | 64976.7305 | 0 | 100% | Finished | 64976.7305 | 64976.7305 | 100 | 100 | 100 | 100 | 100 | 100
3 | Voorbereiding werkplatform spoor A | 2014-11-10 07:00 | 2014-11-14 16:00 | 5d |  | 0 | 5143 | 165 | 6600 | 11743 | 2014-11-10 07:00 | 5d | 11743 | 0 | 0 | 0 | 0 | 11743 | 0 | 100% | Finished | 11743 | 11743 | 100 | 100 | 100 | 100 | 100 | 100
4 | Installatie paalfunderingen | 2014-11-17 07:00 | 2014-11-18 16:00 | 2d |  | 0 | 24394.2891 | 185 | 2960 | 27354.2891 | 2014-11-17 07:00 | 2d | 27354.2891 | 0 | 0 | 0 | 0 | 27354.2891 | 0 | 100% | Finished | 27354.2891 | 27354.2891 | 100 | 100 | 100 | 100 | 100 | 100
5 | Boren paalfundering spoor A | 2014-11-19 07:00 | 2014-12-02 16:00 | 10d |  | 0 | 37034.6406 | 190 | 15200 | 52234.6406 | 2014-11-19 07:00 | 10d | 52234.6406 | 0 | 0 | 0 | 0 | 52234.6406 | 0 | 100% | Finished | 52234.6406 | 52234.6406 | 100 | 100 | 100 | 100 | 100 | 100
6 | Voorbereiding werkplatform spoor B | 2014-11-17 07:00 | 2014-11-26 16:00 | 8d |  | 0 | 6576.8799 | 110 | 7040 | 13616.8799 | 2014-11-17 07:00 | 8d | 13616.8799 | 0 | 0 | 0 | 0 | 13616.8799 | 0 | 100% | Finished | 13616.8799 | 13616.8799 | 100 | 100 | 100 | 100 | 100 | 100
7 | Boren paalfundering spoor B | 2014-12-03 07:00 | 2014-12-16 16:00 | 10d |  | 0 | 34742.1289 | 185 | 14800 | 49542.1289 | 2014-12-03 07:00 | 10d | 49542.1289 | 0 | 0 | 0 | 0 | 49542.1289 | 0 | 100% | Finished | 49542.1289 | 49542.1289 | 100 | 100 | 100 | 100 | 100 | 100
8 | Grachtelementen A | 2014-12-03 07:00 | 2014-12-05 16:00 | 3d |  | 0 | 3158.28 | 115 | 2760 | 5918.28 | 2014-12-03 07:00 | 3d | 5918.28 | 0 | 0 | 0 | 0 | 5918.28 | 0 | 100% | Finished | 5918.28 | 5918.28 | 100 | 100 | 100 | 100 | 100 | 100
9 | Plaatsen schanskorven A | 2014-12-08 07:00 | 2014-12-16 16:00 | 7d |  | 0 | 3124.6299 | 105 | 5880 | 9004.6299 | 2014-12-08 07:00 | 7d | 9004.6299 | 0 | 0 | 0 | 0 | 9004.6299 | 0 | 100% | Finished | 9004.6299 | 9004.6299 | 100 | 100 | 100 | 100 | 100 | 100
10 | Zuiveringsbeton spoor A | 2014-12-17 07:00 | 2014-12-17 16:00 | 1d |  | 0 | 1740.75 | 180 | 1440 | 3180.75 | 2014-12-17 07:00 | 1d | 3180.75 | 0 | 0 | 0 | 0 | 3180.75 | 0 | 100% | Finished | 3180.75 | 3180.75 | 100 | 100 | 100 | 100 | 100 | 100
11 | Grachtelementen B | 2014-12-18 07:00 | 2015-01-05 16:00 | 3d |  | 0 | 2478.3701 | 130 | 3120 | 5598.3701 | 2014-12-18 07:00 | 3d | 5598.3701 | 0 | 0 | 0 | 0 | 5598.3701 | 0 | 100% | Finished | 5598.3701 | 5598.3701 | 100 | 100 | 100 | 100 | 100 | 100
12 | Schanskorven B | 2015-01-06 07:00 | 2015-01-14 16:00 | 7d |  | 0 | 3813.29 | 75 | 4200 | 8013.29 | 2015-01-06 07:00 | 7d | 8013.29 | 0 | 0 | 0 | 0 | 8013.29 | 0 | 100% | Finished | 8013.29 | 8013.29 | 100 | 100 | 100 | 100 | 100 | 100
13 | Zuiveringsbeton B | 2015-01-15 07:00 | 2015-01-15 16:00 | 1d |  | 0 | 1165.85 | 150 | 1200 | 2365.85 | 2015-01-15 07:00 | 1d | 2365.85 | 0 | 0 | 0 | 0 | 2365.85 | 0 | 100% | Finished | 2365.85 | 2365.85 | 100 | 100 | 100 | 100 | 100 | 100
14 | Betonneren palen A | 2014-12-18 07:00 | 2014-12-19 16:00 | 2d |  | 0 | 56952.1602 | 210 | 3360 | 60312.1602 | 2014-12-18 07:00 | 2d | 60312.1602 | 0 | 0 | 0 | 0 | 60312.1602 | 0 | 100% | Finished | 60312.1602 | 60312.1602 | 100 | 100 | 100 | 100 | 100 | 100
15 | Funderingszool A | 2015-01-05 07:00 | 2015-01-09 16:00 | 5d |  | 0 | 7605.8101 | 155 | 6200 | 13805.8101 | 2015-01-05 07:00 | 5d | 13805.8101 | 0 | 0 | 0 | 0 | 13805.8101 | 0 | 100% | Finished | 13805.8101 | 13805.8101 | 100 | 100 | 100 | 100 | 100 | 100
16 | Betonneren palen B | 2015-01-16 07:00 | 2015-01-19 16:00 | 2d |  | 0 | 48416.1406 | 205 | 3280 | 51696.1406 | 2015-01-16 07:00 | 2d | 51696.1406 | 0 | 0 | 0 | 0 | 51696.1406 | 0 | 100% | Finished | 51696.1406 | 51696.1406 | 100 | 100 | 100 | 100 | 100 | 100
17 | Funderingszool B | 2015-01-20 07:00 | 2015-01-26 16:00 | 5d |  | 0 | 9827.4404 | 155 | 6200 | 16027.4404 | 2015-01-20 07:00 | 5d | 16027.4404 | 0 | 0 | 0 | 0 | 16027.4404 | 0 | 100% | Finished | 16027.4404 | 16027.4404 | 100 | 100 | 100 | 100 | 100 | 100
33 | Boog fase 1 | 2015-02-03 07:00 | 2015-02-18 16:00 | 12d |  |  | 49789.54 |  |  | 66669.54 |  | 12d | [5 empty] | 66669.54 |  | 100% |  | 66669.54 | 66669.54
18 | Plaatsen bekisting | 2015-02-03 07:00 | 2015-02-05 16:00 | 3d |  | 0 | 11142.7197 | 195 | 4680 | 15822.7197 | 2015-02-05 07:00 | 3d | 15822.7197 | 0 | 0 | 0 | 0 | 15822.7197 | 0 | 100% | Finished | 15822.7197 | 15822.7197 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapenen | 2015-02-06 07:00 | 2015-02-17 16:00 | 8d |  | 0 | 17346.2402 | 160 | 10240 | 27586.2402 | 2015-02-10 07:00 | 8d | 27586.2402 | 0 | 0 | 0 | 0 | 27586.2402 | 0 | 100% | Finished | 27586.2402 | 27586.2402 | 100 | 100 | 100 | 100 | 100 | 100
20 | Betonneren | 2015-02-18 07:00 | 2015-02-18 16:00 | 1d |  | 0 | 21300.5801 | 245 | 1960 | 23260.5801 | 2015-02-20 07:00 | 1d | 23260.5801 | 0 | 0 | 0 | 0 | 23260.5801 | 0 | 100% | Finished | 23260.5801 | 23260.5801 | 100 | 100 | 100 | 100 | 100 | 100
34 | Boog fase 2 | 2015-03-05 07:00 | 2015-04-08 16:00 | 25d |  |  | 44511.1687 |  |  | 61991.1687 |  | 25d | [5 empty] | 61991.1687 |  | 100% |  | 61991.1687 | 61991.1687
21 | Verplaatsen bekisting | 2015-03-05 07:00 | 2015-03-11 16:00 | 5d |  | 0 | 2372.8 | 105 | 4200 | 6572.8 | 2015-03-09 07:00 | 5d | 6572.8 | 0 | 0 | 0 | 0 | 6572.8 | 0 | 100% | Finished | 6572.8 | 6572.8 | 100 | 100 | 100 | 100 | 100 | 100
22 | Wapenen | 2015-03-12 07:00 | 2015-03-23 16:00 | 8d |  | 0 | 11752.8096 | 150 | 9600 | 21352.8096 | 2015-03-16 07:00 | 8d | 21352.8096 | 0 | 0 | 0 | 0 | 21352.8096 | 0 | 100% | Finished | 21352.8096 | 21352.8096 | 100 | 100 | 100 | 100 | 100 | 100
23 | Betonneren | 2015-03-24 07:00 | 2015-03-24 16:00 | 1d |  | 0 | 23932.6992 | 245 | 1960 | 25892.6992 | 2015-03-26 07:00 | 1d | 25892.6992 | 0 | 0 | 0 | 0 | 25892.6992 | 0 | 100% | Finished | 25892.6992 | 25892.6992 | 100 | 100 | 100 | 100 | 100 | 100
24 | Ontkisten | 2015-04-08 07:00 | 2015-04-08 16:00 | 1d |  | 0 | 6452.8599 | 215 | 1720 | 8172.8599 | 2015-04-10 07:00 | 1d | 8172.8599 | 0 | 0 | 0 | 0 | 8172.8599 | 0 | 100% | Finished | 8172.8599 | 8172.8599 | 100 | 100 | 100 | 100 | 100 | 100
25 | Wanden fase 1 | 2015-03-12 07:00 | 2015-04-15 16:00 | 25d |  | 0 | 17149.0195 | 65 | 13000 | 30149.0195 | 2015-03-16 07:00 | 25d | 30149.0195 | 0 | 0 | 0 | 0 | 30149.0195 | 0 | 100% | Finished | 30149.0195 | 30149.0195 | 100 | 100 | 100 | 100 | 100 | 100
26 | Wanden fase 2 | 2015-04-09 07:00 | 2015-05-13 16:00 | 25d |  | 0 | 15290.0596 | 60 | 12000 | 27290.0596 | 2015-04-13 07:00 | 25d | 27290.0596 | 0 | 0 | 0 | 0 | 27290.0596 | 0 | 100% | Finished | 27290.0596 | 27290.0596 | 100 | 100 | 100 | 100 | 100 | 100
27 | Waterdichting | 2015-05-14 07:00 | 2015-05-27 16:00 | 10d |  | 0 | 30552.9609 | 195 | 15600 | 46152.9609 | 2015-05-18 07:00 | 10d | 46152.9609 | 0 | 0 | 0 | 0 | 46152.9609 | 0 | 100% | Finished | 46152.9609 | 46152.9609 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanvullen | 2015-05-28 07:00 | 2015-06-03 16:00 | 5d |  | 0 | 29016.3203 | 180 | 7200 | 36216.3203 | 2015-06-01 07:00 | 5d | 36216.3203 | 0 | 0 | 0 | 0 | 36216.3203 | 0 | 100% | Finished | 36216.3203 | 36216.3203 | 100 | 100 | 100 | 100 | 100 | 100
29 | Wegenis | 2015-06-04 07:00 | 2015-07-15 16:00 | 30d |  | 0 | 20580.4004 | 135 | 32400 | 52980.4004 | 2015-06-08 07:00 | 30d | 52980.4004 | 0 | 0 | 0 | 0 | 52980.4004 | 0 | 100% | Finished | 52980.4004 | 52980.4004 | 100 | 100 | 100 | 100 | 100 | 100
30 | Metselwerk fase 1 | 2015-04-16 07:00 | 2015-05-06 16:00 | 15d |  | 0 | 1160.59 | 50 | 6000 | 7160.59 | 2015-04-20 07:00 | 15d | 7160.59 | 0 | 0 | 0 | 0 | 7160.59 | 0 | 100% | Finished | 7160.59 | 7160.59 | 100 | 100 | 100 | 100 | 100 | 100
31 | Metselwerk fase 2 | 2015-05-07 07:00 | 2015-05-27 16:00 | 15d |  | 0 | 2281.21 | 50 | 6000 | 8281.21 | 2015-05-11 07:00 | 15d | 8281.21 | 0 | 0 | 0 | 0 | 8281.21 | 0 | 100% | Finished | 8281.21 | 8281.21 | 100 | 100 | 100 | 100 | 100 | 100
32 | Afwerkingen | 2015-07-16 07:00 | 2015-08-12 16:00 | 20d |  | 0 | 41142.3516 | 195 | 31200 | 72342.3516 | 2015-07-20 07:00 | 20d | 72342.3516 | 0 | 0 | 0 | 0 | 72342.3516 | 0 | 100% | Finished | 72342.3516 | 72342.3516 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2014-12-22
1:00 - 2:00 | No | Tuesday | Yes | 2014-12-23
2:00 - 3:00 | No | Wednesday | Yes | 2014-12-24
3:00 - 4:00 | No | Thursday | Yes | 2014-12-25
4:00 - 5:00 | No | Friday | Yes | 2014-12-26
5:00 - 6:00 | No | Saturday | Yes | 2014-12-29
6:00 - 7:00 | No | Sunday | Yes | 2014-12-30
7:00 - 8:00 | Yes |  |  | 2014-12-31
8:00 - 9:00 | Yes |  |  | 2015-01-01
9:00 - 10:00 | Yes |  |  | 2015-01-02
10:00 - 11:00 | Yes |  |  | 2014-11-15
11:00 - 12:00 | Yes |  |  | 2014-11-16
12:00 - 13:00 | No |  |  | 2014-11-22
13:00 - 14:00 | Yes |  |  | 2014-11-23
14:00 - 15:00 | Yes |  |  | 2014-11-29
15:00 - 16:00 | Yes |  |  | 2014-11-30
16:00 - 17:00 | No |  |  | 2014-12-06
17:00 - 18:00 | No |  |  | 2014-12-07
18:00 - 19:00 | No |  |  | 2014-12-13
19:00 - 20:00 | No |  |  | 2014-12-14
20:00 - 21:00 | No |  |  | 2014-12-20
21:00 - 22:00 | No |  |  | 2014-12-21
22:00 - 23:00 | No |  |  | 2014-12-27
23:00 - 0:00 | No |  |  | 2014-12-28
2015-01-03
2015-01-04
Generated by PMConverter v1.1.3 |  |  |  | 2015-01-10
2015-01-11
2015-01-17
2015-01-18
2015-01-24
2015-01-25
2015-01-31
2015-02-01
2015-02-07
2015-02-08
2015-02-14
2015-02-15
2015-02-21
2015-02-22
2015-02-28
2015-03-01
2015-03-07
2015-03-08
2015-03-14
2015-03-15
2015-03-21
2015-03-22
2015-03-28
2015-03-29
2015-04-04
2015-04-05
2015-04-11
2015-04-12
2015-04-18
2015-04-19
2015-04-25
2015-04-26
2015-05-02
2015-05-03
2015-05-09
2015-05-10
2015-05-16
2015-05-17
2015-05-23
2015-05-24
2015-05-30
2015-05-31
2015-06-06
2015-06-07
2015-06-13
2015-06-14
2015-06-20
2015-06-21
2015-06-27
2015-06-28
2015-07-04
2015-07-05
2015-07-11
2015-07-12
2015-07-18
2015-07-19
2015-07-25
2015-07-26
2015-08-01
2015-08-02
2015-08-08
2015-08-09
2015-08-15
2015-08-16
2015-08-22
2015-08-23
2015-08-29
2015-08-30
2015-09-05
2015-09-06
2015-09-12
2015-09-13
2015-09-19
2015-09-20
2015-09-26
2015-09-27
2015-10-03
2015-10-04
2015-10-10
2015-10-11
2015-10-17
2015-10-18
2015-10-24
2015-10-25
2015-10-31
2015-11-01
2015-11-07
2015-11-08
2015-11-14
2015-11-15
2015-11-21
2015-11-22
2015-11-28
2015-11-29
2015-12-05
2015-12-06
2015-12-12
2015-12-13
2015-12-19
2015-12-20
2015-12-26
2015-12-27
2016-01-02
2016-01-03
2016-01-09
2016-01-10
2016-01-16
2016-01-17
2016-01-23
2016-01-24
2016-01-30
2016-01-31

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
T1 | 2014-11-03 07:00 | 2014-12-01 07:00 | 194758.9893 | 194758.9894 | 194758.9893 | 2014-11-28 16:00 | 0.0001812 | 100% | 0.0001812 | 100% | 0 | 100% | 100% | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 832497.4603 | 832497.4597 | 832497.4597 | 832497.4603 | 832497.4591 | 832497.4597 | 832497.4597 | 832497.4598 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T2 | 2014-12-01 07:00 | 2015-01-05 07:00 | 330315.3083 | 330315.3084 | 330315.3083 | 2014-12-19 16:00 | 6.1989e-05 | 100% | 6.1989e-05 | 100% | 0 | 100% | 100% | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 832497.4604 | 832497.4603 | 832497.4603 | 832497.4604 | 832497.4602 | 832497.4603 | 832497.4603 | 832497.4603 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T3 | 2015-01-05 07:00 | 2015-02-02 07:00 | 423263.8395 | 423263.8395 | 423263.8395 | 2015-01-30 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T4 | 2015-02-02 07:00 | 2015-03-02 07:00 | 489933.3795 | 489933.3795 | 489933.3795 | 2015-02-27 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T5 | 2015-03-02 07:00 | 2015-04-06 07:00 | 569740.7079 | 568700.7082 | 568700.7079 | 2015-04-01 16:00 | -1039.9997 | 99.82% | 0.00030994 | 100% | -2d | 98.04% | 100% | 2015-08-13 09:00 | 2015-08-13 10:00 | 2015-08-13 10:00 | 2015-08-13 08:00 | 2015-08-13 10:00 | 2015-08-13 10:00 | 2015-08-14 16:00 | 2015-08-18 15:00 | 2015-08-18 15:00 | 832497.4601 | 832497.46 | 832979.873 | 837773.3952 | 832979.8729 | 837773.395 | 832593.8017 | 833536.0299 | 0.98039 | 1 | 0.99817 | 1 | -2 | 1 | 1 | 0.98039 | 1
T6 | 2015-04-06 07:00 | 2015-05-04 07:00 | 611484.2173 | 609724.2177 | 609724.2173 | 2015-04-29 16:00 | -1759.9996 | 99.71% | 0.00040531 | 100% | -2d | 98.36% | 100% | 2015-08-13 10:00 | 2015-08-13 12:00 | 2015-08-13 12:00 | 2015-08-13 10:00 | 2015-08-13 12:00 | 2015-08-13 12:00 | 2015-08-14 16:00 | 2015-08-18 09:00 | 2015-08-18 09:00 | 832497.46 | 832497.4599 | 833140.5062 | 836210.3474 | 833140.5061 | 836210.3473 | 832625.7729 | 833230.2666 | 0.98361 | 1 | 0.99712 | 1 | -2 | 1 | 1 | 0.98361 | 1
T7 | 2015-05-04 07:00 | 2015-06-01 07:00 | 702854.7085 | 670958.3882 | 670958.3882 | 2015-05-27 16:00 | -31896.3203 | 95.46% | 0 | 100% | -2d | 98.59% | 100% | 2015-08-24 11:00 | 2015-08-26 09:00 | 2015-08-26 09:00 | 2015-08-21 11:00 | 2015-08-26 09:00 | 2015-08-26 09:00 | 2015-08-14 16:00 | 2015-08-17 14:00 | 2015-08-17 14:00 | 832497.4604 | 832497.4604 | 840176.7772 | 834805.1615 | 840176.7772 | 834805.1615 | 833977.0537 | 832953.7855 | 0.98592 | 1 | 0.95462 | 1 | -2 | 1 | 1 | 0.98592 | 1
T8 | 2015-06-01 07:00 | 2015-07-01 07:00 | 748275.1089 | 749355.1095 | 749355.1089 | 2015-07-01 16:00 | 1080.0006 | 100.1% | 0.00064373 | 100% | 1d | 100.6% | 100% | 2015-08-12 14:00 | 2015-08-12 14:00 | 2015-08-12 14:00 | 2015-08-12 14:00 | 2015-08-12 14:00 | 2015-08-12 14:00 | 2015-08-11 16:00 | 2015-08-11 15:00 | 2015-08-11 15:00 | 832497.4598 | 832497.4597 | 832377.6317 | 831993.5668 | 832377.6316 | 831993.5667 | 832473.4665 | 832396.1901 | 1.0061 | 1 | 1.0014 | 1 | 1 | 1 | 1 | 1.0061 | 1
T9 | 2015-07-01 07:00 | 2015-08-03 07:00 | 820017.4604 | 816897.4604 | 816897.4604 | 2015-07-29 16:00 | -3120 | 99.62% | 0 | 100% | -2d | 98.93% | 100% | 2015-08-13 14:00 | 2015-08-13 14:00 | 2015-08-13 14:00 | 2015-08-13 14:00 | 2015-08-13 14:00 | 2015-08-13 14:00 | 2015-08-14 16:00 | 2015-08-17 08:00 | 2015-08-17 08:00 | 832497.4604 | 832497.4604 | 832557.042 | 832666.1091 | 832557.042 | 832666.1091 | 832509.3405 | 832530.901 | 0.9893 | 1 | 0.9962 | 1 | -2 | 1 | 1 | 0.9893 | 1
Actual Schedule | 2015-08-03 07:00 | 2015-09-07 07:00 | 832497.4604 | 832497.4604 | 832497.4604 | 2015-08-12 16:00 | 0 | 100% | 0 | 100% | -17d | 91.98% | 100% | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-08-12 16:00 | 2015-09-04 16:00 | 2015-09-04 16:00 | 2015-09-04 16:00 | 2015-09-04 16:00 | 2015-09-04 16:00 | 2015-09-04 16:00 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 832497.4604 | 0.91981 | 1 | 1 | 1 | -17 | 1 | 1 | 0.91981 | 1