## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House (3) | 1 |  |  | 2016-03-08 08:00 | 2017-05-09 17:00 | 306d |  |  | 367952 |  |  | 367952 | 427.375
53 | Voorbereiding | 1.1 |  |  | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  |  | 34516 |  |  | 34516 | 10.375
1 | Werfinrichting/Werftoiletten | 1.1.1 |  | FS5 | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 29347 | 0 | 0 | 29347 | 6.375
2 | Voorbereiding oplevering | 1.1.2 |  | FS5 | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 450 | 0 | 0 | 450 | 1.375
3 | Studiekosten projectontwikkelaar | 1.1.3 |  | FS5 | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  | 0 | 2517 | 0 | 0 | 2517 | 10.375
4 | Passief | 1.1.4 |  | FS5 | 2016-03-08 08:00 | 2016-03-17 17:00 | 8d |  | 0 | 2202 | 0 | 0 | 2202 | 9.375
54 | Funderingen | 1.2 |  |  | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  |  | 12709 |  |  | 12709 | 36.375
5 | Funderingen | 1.2.1 | 1FS;2FS;3FS;4FS | FS6 | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  | 0 | 12709 | 0 | 0 | 12709 | 36.375
55 | Ruwbouw | 1.3 |  |  | 2016-04-27 08:00 | 2016-09-28 17:00 | 111d |  |  | 93013 |  |  | 93013 | 154.375
6 | GEWA/Metselwerken | 1.3.1 | 5FS | FS7;FS8 | 2016-04-27 08:00 | 2016-05-24 17:00 | 20d |  | 0 | 17864 | 0 | 0 | 17864 | 27.375
7 | Gewelven/Structuur | 1.3.2 | 6FS | FS9 | 2016-05-25 08:00 | 2016-06-16 17:00 | 17d |  | 0 | 15388 | 0 | 0 | 15388 | 22.375
8 | Uitbranden GEWA | 1.3.3 | 6FS | FS9 | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 562 | 0 | 0 | 562 | 1.375
9 | Isolatie | 1.3.4 | 7FS;8FS | FS10 | 2016-06-17 08:00 | 2016-07-01 17:00 | 11d |  | 0 | 10384 | 0 | 0 | 10384 | 14.375
10 | Parament | 1.3.5 | 9FS | FS11 | 2016-07-04 08:00 | 2016-08-29 17:00 | 41d |  | 0 | 37120 | 0 | 0 | 37120 | 56.375
11 | Ytong/Gipswanden | 1.3.6 | 10FS | FS12;FS13 | 2016-08-30 08:00 | 2016-09-01 17:00 | 3d |  | 0 | 2517 | 0 | 0 | 2517 | 2.375
12 | Dorpels | 1.3.7 | 11FS | FS14 | 2016-09-02 08:00 | 2016-09-07 17:00 | 4d |  | 0 | 3081 | 0 | 0 | 3081 | 5.375
13 | Voegwerk | 1.3.8 | 11FS | FS14 | 2016-09-02 08:00 | 2016-09-16 17:00 | 11d |  | 0 | 3082 | 0 | 0 | 3082 | 14.375
14 | Stelling | 1.3.9 | 12FS;13FS | FS15 | 2016-09-19 08:00 | 2016-09-27 17:00 | 7d |  | 0 | 2815 | 0 | 0 | 2815 | 8.375
15 | Karweien | 1.3.10 | 14FS | FS16 | 2016-09-28 08:00 | 2016-09-28 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 0.375
56 | Dakwerken | 1.4 |  |  | 2016-09-29 08:00 | 2016-12-07 17:00 | 50d |  |  | 45039 |  |  | 45039 | 69.375
16 | Daktimmer traditioneel/prefabkap | 1.4.1 | 15FS | FS17 | 2016-09-29 08:00 | 2016-11-21 17:00 | 38d |  | 0 | 38651 | 0 | 0 | 38651 | 53.375
17 | Dakdekken | 1.4.2 | 16FS | FS18 | 2016-11-22 08:00 | 2016-12-02 17:00 | 9d |  | 0 | 5171 | 0 | 0 | 5171 | 10.375
18 | Goten & afleiders | 1.4.3 | 17FS | FS19 | 2016-12-05 08:00 | 2016-12-07 17:00 | 3d |  | 0 | 1217 | 0 | 0 | 1217 | 2.375
57 | Buitenschrijnwerk | 1.5 |  |  | 2016-12-08 08:00 | 2016-12-28 17:00 | 15d |  |  | 25604 |  |  | 25604 | 20.375
19 | Kader buitenschrijnwerk / Wachtbuizen | 1.5.1 | 18FS | FS20 | 2016-12-08 08:00 | 2016-12-09 17:00 | 2d |  | 0 | 1895 | 0 | 0 | 1895 | 1.375
20 | Buitenschrijnwerk plaatsen | 1.5.2 | 19FS | FS21;FS22;FS23;FS33;FS34 | 2016-12-12 08:00 | 2016-12-22 17:00 | 9d |  | 0 | 18502 | 0 | 0 | 18502 | 10.375
21 | Elastische voegen | 1.5.3 | 20FS |  | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 657 | 0 | 0 | 657 | 4.375
22 | Poort | 1.5.4 | 20FS |  | 2016-12-23 08:00 | 2016-12-28 17:00 | 4d |  | 0 | 3650 | 0 | 0 | 3650 | 5.375
23 | Karwei buitenschrijnwerk | 1.5.5 | 20FS |  | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 4.375
58 | Binnenafwerking | 1.6 |  |  | 2017-01-27 08:00 | 2017-04-04 17:00 | 48d |  |  | 58308 |  |  | 58308 | 67.375
24 | Plakwerken | 1.6.1 | 43FS | FS25 | 2017-01-27 08:00 | 2017-02-13 17:00 | 12d |  | 0 | 10564 | 0 | 0 | 10564 | 17.375
25 | Chapes | 1.6.2 | 24FS | FS36 | 2017-02-14 08:00 | 2017-02-20 17:00 | 5d |  | 0 | 6259 | 0 | 0 | 6259 | 6.375
26 | Vloerisolatie | 1.6.3 | 36FS | FS27 | 2017-02-22 08:00 | 2017-03-01 17:00 | 6d |  | 0 | 5374 | 0 | 0 | 5374 | 7.375
27 | Tegelwerken | 1.6.4 | 26FS | FS28;FS29;FS30;FS31;FS32;FS40 | 2017-03-02 08:00 | 2017-03-22 17:00 | 15d |  | 0 | 17507 | 0 | 0 | 17507 | 20.375
28 | Buisbek/Zoldluik/Platen zold/Stijl | 1.6.5 | 27FS |  | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 4.375
29 | Binnendeuren/Uitbekledingen | 1.6.6 | 27FS |  | 2017-03-23 08:00 | 2017-03-29 17:00 | 5d |  | 0 | 8030 | 0 | 0 | 8030 | 6.375
30 | Trap | 1.6.7 | 27FS |  | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 6700 | 0 | 0 | 6700 | 4.375
31 | Luchtdichten | 1.6.8 | 27FS |  | 2017-03-23 08:00 | 2017-04-04 17:00 | 9d |  | 0 | 2849 | 0 | 0 | 2849 | 12.375
32 | Karweiploeg | 1.6.9 | 27FS |  | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 400 | 0 | 0 | 400 | 1.375
59 | Technieken | 1.7 |  |  | 2016-12-23 08:00 | 2017-04-18 17:00 | 83d |  |  | 44115 |  |  | 44115 | 116.375
33 | UZL | 1.7.1 | 20FS | FS35 | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 846 | 0 | 0 | 846 | 4.375
34 | Betonplexplaten | 1.7.2 | 20FS | FS35 | 2016-12-23 08:00 | 2016-12-26 17:00 | 2d |  | 0 | 300 | 0 | 0 | 300 | 3.375
35 | Slijpen technieken/boringen | 1.7.3 | 33FS;34FS | FS37 | 2016-12-28 08:00 | 2017-01-03 17:00 | 5d |  | 0 | 6473 | 0 | 0 | 6473 | 6.375
36 | Bad en douche | 1.7.4 | 25FS | FS26 | 2017-02-21 08:00 | 2017-02-21 17:00 | 1d |  | 0 | 342 | 0 | 0 | 342 | 0.375
37 | Leidingen ventilatie | 1.7.5 | 35FS | FS38 | 2017-01-04 08:00 | 2017-01-06 17:00 | 3d |  | 0 | 1927 | 0 | 0 | 1927 | 2.375
38 | Leidingen san/WP/CV | 1.7.6 | 37FS | FS39 | 2017-01-09 08:00 | 2017-01-12 17:00 | 4d |  | 0 | 2454 | 0 | 0 | 2454 | 3.375
39 | Leidingen vloerverwarming | 1.7.7 | 38FS | FS43 | 2017-01-13 08:00 | 2017-01-20 17:00 | 6d |  | 0 | 5467 | 0 | 0 | 5467 | 7.375
40 | Afwerken ventilatie | 1.7.8 | 27FS | FS41 | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 1887 | 0 | 0 | 1887 | 1.375
41 | Afwerken sanitair | 1.7.9 | 40FS | FS42 | 2017-03-27 08:00 | 2017-03-29 17:00 | 3d |  | 0 | 3539 | 0 | 0 | 3539 | 2.375
42 | Afwerken CV/WP | 1.7.10 | 41FS | FS44 | 2017-03-30 08:00 | 2017-04-04 17:00 | 4d |  | 0 | 5752 | 0 | 0 | 5752 | 5.375
43 | Leidingen electro | 1.7.11 | 39FS | FS24 | 2017-01-23 08:00 | 2017-01-26 17:00 | 4d |  | 0 | 2737 | 0 | 0 | 2737 | 3.375
44 | Afwerken electro | 1.7.12 | 42FS | FS45;FS46;FS47 | 2017-04-05 08:00 | 2017-04-11 17:00 | 5d |  | 0 | 4986 | 0 | 0 | 4986 | 6.375
45 | Verlichting | 1.7.13 | 44FS | FS48;FS50;FS51 | 2017-04-12 08:00 | 2017-04-13 17:00 | 2d |  | 0 | 1500 | 0 | 0 | 1500 | 1.375
46 | Diepsondering, bron en aansluiting | 1.7.14 | 44FS | FS48;FS50;FS51 | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 4905 | 0 | 0 | 4905 | 6.375
47 | Karweien | 1.7.15 | 44FS | FS48;FS50;FS51 | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 1000 | 0 | 0 | 1000 | 6.375
60 | Omgevingswerken | 1.8 |  |  | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  |  | 2885 |  |  | 2885 | 7.375
48 | Opkuis werf (afvoer puin en afval) | 1.8.1 | 45FS;46FS;47FS |  | 2017-04-19 08:00 | 2017-04-25 17:00 | 5d |  | 0 | 1398 | 0 | 0 | 1398 | 6.375
50 | Grondafvoer | 1.8.2 | 45FS;46FS;47FS |  | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  | 0 | 1487 | 0 | 0 | 1487 | 7.375
61 | Schilderwerken | 1.9 |  |  | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  |  | 6000 |  |  | 6000 | 13.375
51 | Schilderwerken | 1.9.1 | 45FS;46FS;47FS | FS52 | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  | 0 | 6000 | 0 | 0 | 6000 | 13.375
62 | Restklasse | 1.10 |  |  | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  |  | 45763 |  |  | 45763 | 6.375
52 | Rest | 1.10.1 | 51FS |  | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  | 0 | 45763 | 0 | 0 | 45763 | 6.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House (3) | 2448h |  |  |  |  | 99 | 100 | 101
53 | Voorbereiding | 72h |  |  |  |  | 99 | 100 | 101
1 | Werfinrichting/Werftoiletten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Voorbereiding oplevering | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Studiekosten projectontwikkelaar | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Passief | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Funderingen | 216h |  |  |  |  | 99 | 100 | 101
5 | Funderingen | 216h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
55 | Ruwbouw | 888h |  |  |  |  | 99 | 100 | 101
6 | GEWA/Metselwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Gewelven/Structuur | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Uitbranden GEWA | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Isolatie | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Parament | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Ytong/Gipswanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Dorpels | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Voegwerk | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Stelling | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Karweien | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Dakwerken | 400h |  |  |  |  | 99 | 100 | 101
16 | Daktimmer traditioneel/prefabkap | 304h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
17 | Dakdekken | 72h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
18 | Goten & afleiders | 24h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
57 | Buitenschrijnwerk | 120h |  |  |  |  | 99 | 100 | 101
19 | Kader buitenschrijnwerk / Wachtbuizen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Buitenschrijnwerk plaatsen | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Elastische voegen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Poort | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Karwei buitenschrijnwerk | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Binnenafwerking | 384h |  |  |  |  | 99 | 100 | 101
24 | Plakwerken | 96h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | Chapes | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
26 | Vloerisolatie | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
27 | Tegelwerken | 120h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
28 | Buisbek/Zoldluik/Platen zold/Stijl | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | Binnendeuren/Uitbekledingen | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Trap | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
31 | Luchtdichten | 72h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
32 | Karweiploeg | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
59 | Technieken | 664h |  |  |  |  | 99 | 100 | 101
33 | UZL | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
34 | Betonplexplaten | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
35 | Slijpen technieken/boringen | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
36 | Bad en douche | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
37 | Leidingen ventilatie | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
38 | Leidingen san/WP/CV | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
39 | Leidingen vloerverwarming | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
40 | Afwerken ventilatie | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
41 | Afwerken sanitair | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
42 | Afwerken CV/WP | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
43 | Leidingen electro | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
44 | Afwerken electro | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
45 | Verlichting | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
46 | Diepsondering, bron en aansluiting | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
47 | Karweien | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
60 | Omgevingswerken | 48h |  |  |  |  | 99 | 100 | 101
48 | Opkuis werf (afvoer puin en afval) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Grondafvoer | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Schilderwerken | 80h |  |  |  |  | 99 | 100 | 101
51 | Schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Restklasse | 40h |  |  |  |  | 99 | 100 | 101
52 | Rest | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2016-05-10 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (3) | 2016-03-08 08:00 | 2017-05-09 17:00 | 306d |  |  | 367952 |  |  | 367952 |  | 45d | [5 empty] | 49705 |  | 12.83% |  | 47225 | 65089
53 | Voorbereiding | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  |  | 34516 |  |  | 34516 |  | 13d | [5 empty] | 35174 |  | 100% |  | 34516 | 34516
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 29347 | 0 | 0 | 29347 | 2016-03-08 08:00 | 5d | 29347 | 0 | 0 | 7 | 0 | 29354 | 0 | 100% | Finished | 29347 | 29347 | 100 | 100 | 100 | 100 | 100.0239 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 450 | 0 | 0 | 450 | 2016-03-08 08:00 | 3d | 450 | 0 | 0 | 378 | 0 | 828 | 0 | 100% | Finished | 450 | 450 | 100 | 150 | 100 | 100 | 184 | 100
3 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-03-08 08:00 | 13d | 2517 | 0 | 0 | 1675 | 0 | 4192 | 0 | 100% | Finished | 2517 | 2517 | 100 | 144.4444 | 100 | 100 | 166.5475 | 100
4 | Passief | 2016-03-08 08:00 | 2016-03-17 17:00 | 8d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-08 08:00 | 3d | 2202 | 0 | 0 | -1402 | 0 | 800 | 0 | 100% | Finished | 2202 | 2202 | 100 | 37.5 | 100 | 100 | 36.3306 | 100
54 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  |  | 12709 |  |  | 12709 |  | 32d | [5 empty] | 14531 |  | 100% |  | 12709 | 12709
5 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  | 0 | 12709 | 0 | 0 | 12709 | 2016-03-25 08:00 | 32d | 12709 | 0 | 0 | 1822 | 0 | 14531 | 0 | 100% | Finished | 12709 | 12709 | 100 | 118.5185 | 100 | 100 | 114.3363 | 100
55 | Ruwbouw | 2016-04-27 08:00 | 2016-09-28 17:00 | 111d |  |  | 93013 |  |  | 93013 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 17864
6 | GEWA/Metselwerken | 2016-04-27 08:00 | 2016-05-24 17:00 | 20d |  | 0 | 17864 | 0 | 0 | 17864 |  | 0 | 0 | 17864 | 20d | 0 | 0 | 0 | 17864 | 0% | Not Started | 0 | 17864 | 100 |  | 0 | 100 |  | 0
7 | Gewelven/Structuur | 2016-05-25 08:00 | 2016-06-16 17:00 | 17d |  | 0 | 15388 | 0 | 0 | 15388 |  | 0 | 0 | 15388 | 17d | 0 | 0 | 0 | 15388 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Uitbranden GEWA | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 562 | 0 | 0 | 562 |  | 0 | 0 | 562 | 2d | 0 | 0 | 0 | 562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Isolatie | 2016-06-17 08:00 | 2016-07-01 17:00 | 11d |  | 0 | 10384 | 0 | 0 | 10384 |  | 0 | 0 | 10384 | 11d | 0 | 0 | 0 | 10384 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Parament | 2016-07-04 08:00 | 2016-08-29 17:00 | 41d |  | 0 | 37120 | 0 | 0 | 37120 |  | 0 | 0 | 37120 | 41d | 0 | 0 | 0 | 37120 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Ytong/Gipswanden | 2016-08-30 08:00 | 2016-09-01 17:00 | 3d |  | 0 | 2517 | 0 | 0 | 2517 |  | 0 | 0 | 2517 | 3d | 0 | 0 | 0 | 2517 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Dorpels | 2016-09-02 08:00 | 2016-09-07 17:00 | 4d |  | 0 | 3081 | 0 | 0 | 3081 |  | 0 | 0 | 3081 | 4d | 0 | 0 | 0 | 3081 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Voegwerk | 2016-09-02 08:00 | 2016-09-16 17:00 | 11d |  | 0 | 3082 | 0 | 0 | 3082 |  | 0 | 0 | 3082 | 11d | 0 | 0 | 0 | 3082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Stelling | 2016-09-19 08:00 | 2016-09-27 17:00 | 7d |  | 0 | 2815 | 0 | 0 | 2815 |  | 0 | 0 | 2815 | 7d | 0 | 0 | 0 | 2815 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Karweien | 2016-09-28 08:00 | 2016-09-28 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Dakwerken | 2016-09-29 08:00 | 2016-12-07 17:00 | 50d |  |  | 45039 |  |  | 45039 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Daktimmer traditioneel/prefabkap | 2016-09-29 08:00 | 2016-11-21 17:00 | 38d |  | 0 | 38651 | 0 | 0 | 38651 |  | 0 | 0 | 38651 | 38d | 0 | 0 | 0 | 38651 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Dakdekken | 2016-11-22 08:00 | 2016-12-02 17:00 | 9d |  | 0 | 5171 | 0 | 0 | 5171 |  | 0 | 0 | 5171 | 9d | 0 | 0 | 0 | 5171 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Goten & afleiders | 2016-12-05 08:00 | 2016-12-07 17:00 | 3d |  | 0 | 1217 | 0 | 0 | 1217 |  | 0 | 0 | 1217 | 3d | 0 | 0 | 0 | 1217 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Buitenschrijnwerk | 2016-12-08 08:00 | 2016-12-28 17:00 | 15d |  |  | 25604 |  |  | 25604 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Kader buitenschrijnwerk / Wachtbuizen | 2016-12-08 08:00 | 2016-12-09 17:00 | 2d |  | 0 | 1895 | 0 | 0 | 1895 |  | 0 | 0 | 1895 | 2d | 0 | 0 | 0 | 1895 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Buitenschrijnwerk plaatsen | 2016-12-12 08:00 | 2016-12-22 17:00 | 9d |  | 0 | 18502 | 0 | 0 | 18502 |  | 0 | 0 | 18502 | 9d | 0 | 0 | 0 | 18502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Elastische voegen | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 657 | 0 | 0 | 657 |  | 0 | 0 | 657 | 3d | 0 | 0 | 0 | 657 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Poort | 2016-12-23 08:00 | 2016-12-28 17:00 | 4d |  | 0 | 3650 | 0 | 0 | 3650 |  | 0 | 0 | 3650 | 4d | 0 | 0 | 0 | 3650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Karwei buitenschrijnwerk | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 |  | 0 | 0 | 900 | 3d | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Binnenafwerking | 2017-01-27 08:00 | 2017-04-04 17:00 | 48d |  |  | 58308 |  |  | 58308 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | Plakwerken | 2017-01-27 08:00 | 2017-02-13 17:00 | 12d |  | 0 | 10564 | 0 | 0 | 10564 |  | 0 | 0 | 10564 | 12d | 0 | 0 | 0 | 10564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Chapes | 2017-02-14 08:00 | 2017-02-20 17:00 | 5d |  | 0 | 6259 | 0 | 0 | 6259 |  | 0 | 0 | 6259 | 5d | 0 | 0 | 0 | 6259 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Vloerisolatie | 2017-02-22 08:00 | 2017-03-01 17:00 | 6d |  | 0 | 5374 | 0 | 0 | 5374 |  | 0 | 0 | 5374 | 6d | 0 | 0 | 0 | 5374 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Tegelwerken | 2017-03-02 08:00 | 2017-03-22 17:00 | 15d |  | 0 | 17507 | 0 | 0 | 17507 |  | 0 | 0 | 17507 | 15d | 0 | 0 | 0 | 17507 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnendeuren/Uitbekledingen | 2017-03-23 08:00 | 2017-03-29 17:00 | 5d |  | 0 | 8030 | 0 | 0 | 8030 |  | 0 | 0 | 8030 | 5d | 0 | 0 | 0 | 8030 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Trap | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 6700 | 0 | 0 | 6700 |  | 0 | 0 | 6700 | 3d | 0 | 0 | 0 | 6700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-04 17:00 | 9d |  | 0 | 2849 | 0 | 0 | 2849 |  | 0 | 0 | 2849 | 9d | 0 | 0 | 0 | 2849 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Karweiploeg | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 400 | 0 | 0 | 400 |  | 0 | 0 | 400 | 2d | 0 | 0 | 0 | 400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Technieken | 2016-12-23 08:00 | 2017-04-18 17:00 | 83d |  |  | 44115 |  |  | 44115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | UZL | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 846 | 0 | 0 | 846 |  | 0 | 0 | 846 | 3d | 0 | 0 | 0 | 846 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Betonplexplaten | 2016-12-23 08:00 | 2016-12-26 17:00 | 2d |  | 0 | 300 | 0 | 0 | 300 |  | 0 | 0 | 300 | 2d | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Slijpen technieken/boringen | 2016-12-28 08:00 | 2017-01-03 17:00 | 5d |  | 0 | 6473 | 0 | 0 | 6473 |  | 0 | 0 | 6473 | 5d | 0 | 0 | 0 | 6473 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Bad en douche | 2017-02-21 08:00 | 2017-02-21 17:00 | 1d |  | 0 | 342 | 0 | 0 | 342 |  | 0 | 0 | 342 | 1d | 0 | 0 | 0 | 342 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Leidingen ventilatie | 2017-01-04 08:00 | 2017-01-06 17:00 | 3d |  | 0 | 1927 | 0 | 0 | 1927 |  | 0 | 0 | 1927 | 3d | 0 | 0 | 0 | 1927 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Leidingen san/WP/CV | 2017-01-09 08:00 | 2017-01-12 17:00 | 4d |  | 0 | 2454 | 0 | 0 | 2454 |  | 0 | 0 | 2454 | 4d | 0 | 0 | 0 | 2454 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Leidingen vloerverwarming | 2017-01-13 08:00 | 2017-01-20 17:00 | 6d |  | 0 | 5467 | 0 | 0 | 5467 |  | 0 | 0 | 5467 | 6d | 0 | 0 | 0 | 5467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Afwerken ventilatie | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 1887 | 0 | 0 | 1887 |  | 0 | 0 | 1887 | 2d | 0 | 0 | 0 | 1887 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerken sanitair | 2017-03-27 08:00 | 2017-03-29 17:00 | 3d |  | 0 | 3539 | 0 | 0 | 3539 |  | 0 | 0 | 3539 | 3d | 0 | 0 | 0 | 3539 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afwerken CV/WP | 2017-03-30 08:00 | 2017-04-04 17:00 | 4d |  | 0 | 5752 | 0 | 0 | 5752 |  | 0 | 0 | 5752 | 4d | 0 | 0 | 0 | 5752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Leidingen electro | 2017-01-23 08:00 | 2017-01-26 17:00 | 4d |  | 0 | 2737 | 0 | 0 | 2737 |  | 0 | 0 | 2737 | 4d | 0 | 0 | 0 | 2737 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Afwerken electro | 2017-04-05 08:00 | 2017-04-11 17:00 | 5d |  | 0 | 4986 | 0 | 0 | 4986 |  | 0 | 0 | 4986 | 5d | 0 | 0 | 0 | 4986 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Verlichting | 2017-04-12 08:00 | 2017-04-13 17:00 | 2d |  | 0 | 1500 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Diepsondering, bron en aansluiting | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 4905 | 0 | 0 | 4905 |  | 0 | 0 | 4905 | 5d | 0 | 0 | 0 | 4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Karweien | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Omgevingswerken | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  |  | 2885 |  |  | 2885 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | Opkuis werf (afvoer puin en afval) | 2017-04-19 08:00 | 2017-04-25 17:00 | 5d |  | 0 | 1398 | 0 | 0 | 1398 |  | 0 | 0 | 1398 | 5d | 0 | 0 | 0 | 1398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Grondafvoer | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  | 0 | 1487 | 0 | 0 | 1487 |  | 0 | 0 | 1487 | 6d | 0 | 0 | 0 | 1487 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  |  | 6000 |  |  | 6000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  | 0 | 6000 | 0 | 0 | 6000 |  | 0 | 0 | 6000 | 10d | 0 | 0 | 0 | 6000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Restklasse | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  |  | 45763 |  |  | 45763 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Rest | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  | 0 | 45763 | 0 | 0 | 45763 |  | 0 | 0 | 45763 | 5d | 0 | 0 | 0 | 45763 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-10-12 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (3) | 2016-03-08 08:00 | 2017-05-09 17:00 | 306d |  |  | 367952 |  |  | 367952 |  | 156d | [5 empty] | 134473 |  | 38.11% |  | 140238 | 178889
53 | Voorbereiding | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  |  | 34516 |  |  | 34516 |  | 13d | [5 empty] | 35174 |  | 100% |  | 34516 | 34516
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 29347 | 0 | 0 | 29347 | 2016-03-08 08:00 | 5d | 29347 | 0 | 0 | 7 | 0 | 29354 | 0 | 100% | Finished | 29347 | 29347 | 100 | 100 | 100 | 100 | 100.0239 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 450 | 0 | 0 | 450 | 2016-03-08 08:00 | 3d | 450 | 0 | 0 | 378 | 0 | 828 | 0 | 100% | Finished | 450 | 450 | 100 | 150 | 100 | 100 | 184 | 100
3 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-03-08 08:00 | 13d | 2517 | 0 | 0 | 1675 | 0 | 4192 | 0 | 100% | Finished | 2517 | 2517 | 100 | 144.4444 | 100 | 100 | 166.5475 | 100
4 | Passief | 2016-03-08 08:00 | 2016-03-17 17:00 | 8d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-08 08:00 | 3d | 2202 | 0 | 0 | -1402 | 0 | 800 | 0 | 100% | Finished | 2202 | 2202 | 100 | 37.5 | 100 | 100 | 36.3306 | 100
54 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  |  | 12709 |  |  | 12709 |  | 32d | [5 empty] | 14531 |  | 100% |  | 12709 | 12709
5 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  | 0 | 12709 | 0 | 0 | 12709 | 2016-03-25 08:00 | 32d | 12709 | 0 | 0 | 1822 | 0 | 14531 | 0 | 100% | Finished | 12709 | 12709 | 100 | 118.5185 | 100 | 100 | 114.3363 | 100
55 | Ruwbouw | 2016-04-27 08:00 | 2016-09-28 17:00 | 111d |  |  | 93013 |  |  | 93013 |  | 111d | [5 empty] | 84768 |  | 100% |  | 93013 | 93013
6 | GEWA/Metselwerken | 2016-04-27 08:00 | 2016-05-24 17:00 | 20d |  | 0 | 17864 | 0 | 0 | 17864 | 2016-05-10 08:00 | 17d | 17864 | 0 | 0 | -5192 | 0 | 12672 | 0 | 100% | Finished | 17864 | 17864 | 100 | 85 | 100 | 100 | 70.936 | 100
7 | Gewelven/Structuur | 2016-05-25 08:00 | 2016-06-16 17:00 | 17d |  | 0 | 15388 | 0 | 0 | 15388 | 2016-06-02 08:00 | 16d | 15388 | 0 | 0 | -2976 | 0 | 12412 | 0 | 100% | Finished | 15388 | 15388 | 100 | 94.1176 | 100 | 100 | 80.6603 | 100
8 | Uitbranden GEWA | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 562 | 0 | 0 | 562 | 2016-06-02 08:00 | 2d | 562 | 0 | 0 | -262 | 0 | 300 | 0 | 100% | Finished | 562 | 562 | 100 | 100 | 100 | 100 | 53.3808 | 100
9 | Isolatie | 2016-06-17 08:00 | 2016-07-01 17:00 | 11d |  | 0 | 10384 | 0 | 0 | 10384 | 2016-06-24 08:00 | 9d | 10384 | 0 | 0 | -1829 | 0 | 8555 | 0 | 100% | Finished | 10384 | 10384 | 100 | 81.8182 | 100 | 100 | 82.3864 | 100
10 | Parament | 2016-07-04 08:00 | 2016-08-29 17:00 | 41d |  | 0 | 37120 | 0 | 0 | 37120 | 2016-07-07 08:00 | 49d | 37120 | 0 | 0 | -1023 | 0 | 36097 | 0 | 100% | Finished | 37120 | 37120 | 100 | 119.5122 | 100 | 100 | 97.2441 | 100
11 | Ytong/Gipswanden | 2016-08-30 08:00 | 2016-09-01 17:00 | 3d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-09-14 08:00 | 3d | 2517 | 0 | 0 | -17 | 0 | 2500 | 0 | 100% | Finished | 2517 | 2517 | 100 | 100 | 100 | 100 | 99.3246 | 100
12 | Dorpels | 2016-09-02 08:00 | 2016-09-07 17:00 | 4d |  | 0 | 3081 | 0 | 0 | 3081 | 2016-09-19 08:00 | 6d | 3081 | 0 | 0 | 4237 | 0 | 7318 | 0 | 100% | Finished | 3081 | 3081 | 100 | 150 | 100 | 100 | 237.5203 | 100
13 | Voegwerk | 2016-09-02 08:00 | 2016-09-16 17:00 | 11d |  | 0 | 3082 | 0 | 0 | 3082 | 2016-09-19 08:00 | 11d | 3082 | 0 | 0 | 93 | 0 | 3175 | 0 | 100% | Finished | 3082 | 3082 | 100 | 100 | 100 | 100 | 103.0175 | 100
14 | Stelling | 2016-09-19 08:00 | 2016-09-27 17:00 | 7d |  | 0 | 2815 | 0 | 0 | 2815 | 2016-10-04 08:00 | 5d | 2815 | 0 | 0 | -1621 | 0 | 1194 | 0 | 100% | Finished | 2815 | 2815 | 100 | 71.4286 | 100 | 100 | 42.4156 | 100
15 | Karweien | 2016-09-28 08:00 | 2016-09-28 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-10-11 08:00 | 1d | 200 | 0 | 0 | 345 | 0 | 545 | 0 | 100% | Finished | 200 | 200 | 100 | 100 | 100 | 100 | 272.5 | 100
56 | Dakwerken | 2016-09-29 08:00 | 2016-12-07 17:00 | 50d |  |  | 45039 |  |  | 45039 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 38651
16 | Daktimmer traditioneel/prefabkap | 2016-09-29 08:00 | 2016-11-21 17:00 | 38d |  | 0 | 38651 | 0 | 0 | 38651 |  | 0 | 0 | 38651 | 38d | 0 | 0 | 0 | 38651 | 0% | Not Started | 0 | 38651 | 100 |  | 0 | 100 |  | 0
17 | Dakdekken | 2016-11-22 08:00 | 2016-12-02 17:00 | 9d |  | 0 | 5171 | 0 | 0 | 5171 |  | 0 | 0 | 5171 | 9d | 0 | 0 | 0 | 5171 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Goten & afleiders | 2016-12-05 08:00 | 2016-12-07 17:00 | 3d |  | 0 | 1217 | 0 | 0 | 1217 |  | 0 | 0 | 1217 | 3d | 0 | 0 | 0 | 1217 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Buitenschrijnwerk | 2016-12-08 08:00 | 2016-12-28 17:00 | 15d |  |  | 25604 |  |  | 25604 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Kader buitenschrijnwerk / Wachtbuizen | 2016-12-08 08:00 | 2016-12-09 17:00 | 2d |  | 0 | 1895 | 0 | 0 | 1895 |  | 0 | 0 | 1895 | 2d | 0 | 0 | 0 | 1895 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Buitenschrijnwerk plaatsen | 2016-12-12 08:00 | 2016-12-22 17:00 | 9d |  | 0 | 18502 | 0 | 0 | 18502 |  | 0 | 0 | 18502 | 9d | 0 | 0 | 0 | 18502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Elastische voegen | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 657 | 0 | 0 | 657 |  | 0 | 0 | 657 | 3d | 0 | 0 | 0 | 657 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Poort | 2016-12-23 08:00 | 2016-12-28 17:00 | 4d |  | 0 | 3650 | 0 | 0 | 3650 |  | 0 | 0 | 3650 | 4d | 0 | 0 | 0 | 3650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Karwei buitenschrijnwerk | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 |  | 0 | 0 | 900 | 3d | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Binnenafwerking | 2017-01-27 08:00 | 2017-04-04 17:00 | 48d |  |  | 58308 |  |  | 58308 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | Plakwerken | 2017-01-27 08:00 | 2017-02-13 17:00 | 12d |  | 0 | 10564 | 0 | 0 | 10564 |  | 0 | 0 | 10564 | 12d | 0 | 0 | 0 | 10564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Chapes | 2017-02-14 08:00 | 2017-02-20 17:00 | 5d |  | 0 | 6259 | 0 | 0 | 6259 |  | 0 | 0 | 6259 | 5d | 0 | 0 | 0 | 6259 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Vloerisolatie | 2017-02-22 08:00 | 2017-03-01 17:00 | 6d |  | 0 | 5374 | 0 | 0 | 5374 |  | 0 | 0 | 5374 | 6d | 0 | 0 | 0 | 5374 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Tegelwerken | 2017-03-02 08:00 | 2017-03-22 17:00 | 15d |  | 0 | 17507 | 0 | 0 | 17507 |  | 0 | 0 | 17507 | 15d | 0 | 0 | 0 | 17507 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnendeuren/Uitbekledingen | 2017-03-23 08:00 | 2017-03-29 17:00 | 5d |  | 0 | 8030 | 0 | 0 | 8030 |  | 0 | 0 | 8030 | 5d | 0 | 0 | 0 | 8030 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Trap | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 6700 | 0 | 0 | 6700 |  | 0 | 0 | 6700 | 3d | 0 | 0 | 0 | 6700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-04 17:00 | 9d |  | 0 | 2849 | 0 | 0 | 2849 |  | 0 | 0 | 2849 | 9d | 0 | 0 | 0 | 2849 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Karweiploeg | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 400 | 0 | 0 | 400 |  | 0 | 0 | 400 | 2d | 0 | 0 | 0 | 400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Technieken | 2016-12-23 08:00 | 2017-04-18 17:00 | 83d |  |  | 44115 |  |  | 44115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | UZL | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 846 | 0 | 0 | 846 |  | 0 | 0 | 846 | 3d | 0 | 0 | 0 | 846 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Betonplexplaten | 2016-12-23 08:00 | 2016-12-26 17:00 | 2d |  | 0 | 300 | 0 | 0 | 300 |  | 0 | 0 | 300 | 2d | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Slijpen technieken/boringen | 2016-12-28 08:00 | 2017-01-03 17:00 | 5d |  | 0 | 6473 | 0 | 0 | 6473 |  | 0 | 0 | 6473 | 5d | 0 | 0 | 0 | 6473 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Bad en douche | 2017-02-21 08:00 | 2017-02-21 17:00 | 1d |  | 0 | 342 | 0 | 0 | 342 |  | 0 | 0 | 342 | 1d | 0 | 0 | 0 | 342 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Leidingen ventilatie | 2017-01-04 08:00 | 2017-01-06 17:00 | 3d |  | 0 | 1927 | 0 | 0 | 1927 |  | 0 | 0 | 1927 | 3d | 0 | 0 | 0 | 1927 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Leidingen san/WP/CV | 2017-01-09 08:00 | 2017-01-12 17:00 | 4d |  | 0 | 2454 | 0 | 0 | 2454 |  | 0 | 0 | 2454 | 4d | 0 | 0 | 0 | 2454 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Leidingen vloerverwarming | 2017-01-13 08:00 | 2017-01-20 17:00 | 6d |  | 0 | 5467 | 0 | 0 | 5467 |  | 0 | 0 | 5467 | 6d | 0 | 0 | 0 | 5467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Afwerken ventilatie | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 1887 | 0 | 0 | 1887 |  | 0 | 0 | 1887 | 2d | 0 | 0 | 0 | 1887 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerken sanitair | 2017-03-27 08:00 | 2017-03-29 17:00 | 3d |  | 0 | 3539 | 0 | 0 | 3539 |  | 0 | 0 | 3539 | 3d | 0 | 0 | 0 | 3539 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afwerken CV/WP | 2017-03-30 08:00 | 2017-04-04 17:00 | 4d |  | 0 | 5752 | 0 | 0 | 5752 |  | 0 | 0 | 5752 | 4d | 0 | 0 | 0 | 5752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Leidingen electro | 2017-01-23 08:00 | 2017-01-26 17:00 | 4d |  | 0 | 2737 | 0 | 0 | 2737 |  | 0 | 0 | 2737 | 4d | 0 | 0 | 0 | 2737 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Afwerken electro | 2017-04-05 08:00 | 2017-04-11 17:00 | 5d |  | 0 | 4986 | 0 | 0 | 4986 |  | 0 | 0 | 4986 | 5d | 0 | 0 | 0 | 4986 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Verlichting | 2017-04-12 08:00 | 2017-04-13 17:00 | 2d |  | 0 | 1500 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Diepsondering, bron en aansluiting | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 4905 | 0 | 0 | 4905 |  | 0 | 0 | 4905 | 5d | 0 | 0 | 0 | 4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Karweien | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Omgevingswerken | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  |  | 2885 |  |  | 2885 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | Opkuis werf (afvoer puin en afval) | 2017-04-19 08:00 | 2017-04-25 17:00 | 5d |  | 0 | 1398 | 0 | 0 | 1398 |  | 0 | 0 | 1398 | 5d | 0 | 0 | 0 | 1398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Grondafvoer | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  | 0 | 1487 | 0 | 0 | 1487 |  | 0 | 0 | 1487 | 6d | 0 | 0 | 0 | 1487 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  |  | 6000 |  |  | 6000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  | 0 | 6000 | 0 | 0 | 6000 |  | 0 | 0 | 6000 | 10d | 0 | 0 | 0 | 6000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Restklasse | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  |  | 45763 |  |  | 45763 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Rest | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  | 0 | 45763 | 0 | 0 | 45763 |  | 0 | 0 | 45763 | 5d | 0 | 0 | 0 | 45763 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-12-29 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (3) | 2016-03-08 08:00 | 2017-05-09 17:00 | 306d |  |  | 367952 |  |  | 367952 |  | 212d | [5 empty] | 181871 |  | 50.35% |  | 185277 | 218500
53 | Voorbereiding | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  |  | 34516 |  |  | 34516 |  | 13d | [5 empty] | 35174 |  | 100% |  | 34516 | 34516
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 29347 | 0 | 0 | 29347 | 2016-03-08 08:00 | 5d | 29347 | 0 | 0 | 7 | 0 | 29354 | 0 | 100% | Finished | 29347 | 29347 | 100 | 100 | 100 | 100 | 100.0239 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 450 | 0 | 0 | 450 | 2016-03-08 08:00 | 3d | 450 | 0 | 0 | 378 | 0 | 828 | 0 | 100% | Finished | 450 | 450 | 100 | 150 | 100 | 100 | 184 | 100
3 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-03-08 08:00 | 13d | 2517 | 0 | 0 | 1675 | 0 | 4192 | 0 | 100% | Finished | 2517 | 2517 | 100 | 144.4444 | 100 | 100 | 166.5475 | 100
4 | Passief | 2016-03-08 08:00 | 2016-03-17 17:00 | 8d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-08 08:00 | 3d | 2202 | 0 | 0 | -1402 | 0 | 800 | 0 | 100% | Finished | 2202 | 2202 | 100 | 37.5 | 100 | 100 | 36.3306 | 100
54 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  |  | 12709 |  |  | 12709 |  | 32d | [5 empty] | 14531 |  | 100% |  | 12709 | 12709
5 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  | 0 | 12709 | 0 | 0 | 12709 | 2016-03-25 08:00 | 32d | 12709 | 0 | 0 | 1822 | 0 | 14531 | 0 | 100% | Finished | 12709 | 12709 | 100 | 118.5185 | 100 | 100 | 114.3363 | 100
55 | Ruwbouw | 2016-04-27 08:00 | 2016-09-28 17:00 | 111d |  |  | 93013 |  |  | 93013 |  | 111d | [5 empty] | 84768 |  | 100% |  | 93013 | 93013
6 | GEWA/Metselwerken | 2016-04-27 08:00 | 2016-05-24 17:00 | 20d |  | 0 | 17864 | 0 | 0 | 17864 | 2016-05-10 08:00 | 17d | 17864 | 0 | 0 | -5192 | 0 | 12672 | 0 | 100% | Finished | 17864 | 17864 | 100 | 85 | 100 | 100 | 70.936 | 100
7 | Gewelven/Structuur | 2016-05-25 08:00 | 2016-06-16 17:00 | 17d |  | 0 | 15388 | 0 | 0 | 15388 | 2016-06-02 08:00 | 16d | 15388 | 0 | 0 | -2976 | 0 | 12412 | 0 | 100% | Finished | 15388 | 15388 | 100 | 94.1176 | 100 | 100 | 80.6603 | 100
8 | Uitbranden GEWA | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 562 | 0 | 0 | 562 | 2016-06-02 08:00 | 2d | 562 | 0 | 0 | -262 | 0 | 300 | 0 | 100% | Finished | 562 | 562 | 100 | 100 | 100 | 100 | 53.3808 | 100
9 | Isolatie | 2016-06-17 08:00 | 2016-07-01 17:00 | 11d |  | 0 | 10384 | 0 | 0 | 10384 | 2016-06-24 08:00 | 9d | 10384 | 0 | 0 | -1829 | 0 | 8555 | 0 | 100% | Finished | 10384 | 10384 | 100 | 81.8182 | 100 | 100 | 82.3864 | 100
10 | Parament | 2016-07-04 08:00 | 2016-08-29 17:00 | 41d |  | 0 | 37120 | 0 | 0 | 37120 | 2016-07-07 08:00 | 49d | 37120 | 0 | 0 | -1023 | 0 | 36097 | 0 | 100% | Finished | 37120 | 37120 | 100 | 119.5122 | 100 | 100 | 97.2441 | 100
11 | Ytong/Gipswanden | 2016-08-30 08:00 | 2016-09-01 17:00 | 3d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-09-14 08:00 | 3d | 2517 | 0 | 0 | -17 | 0 | 2500 | 0 | 100% | Finished | 2517 | 2517 | 100 | 100 | 100 | 100 | 99.3246 | 100
12 | Dorpels | 2016-09-02 08:00 | 2016-09-07 17:00 | 4d |  | 0 | 3081 | 0 | 0 | 3081 | 2016-09-19 08:00 | 6d | 3081 | 0 | 0 | 4237 | 0 | 7318 | 0 | 100% | Finished | 3081 | 3081 | 100 | 150 | 100 | 100 | 237.5203 | 100
13 | Voegwerk | 2016-09-02 08:00 | 2016-09-16 17:00 | 11d |  | 0 | 3082 | 0 | 0 | 3082 | 2016-09-19 08:00 | 11d | 3082 | 0 | 0 | 93 | 0 | 3175 | 0 | 100% | Finished | 3082 | 3082 | 100 | 100 | 100 | 100 | 103.0175 | 100
14 | Stelling | 2016-09-19 08:00 | 2016-09-27 17:00 | 7d |  | 0 | 2815 | 0 | 0 | 2815 | 2016-10-04 08:00 | 5d | 2815 | 0 | 0 | -1621 | 0 | 1194 | 0 | 100% | Finished | 2815 | 2815 | 100 | 71.4286 | 100 | 100 | 42.4156 | 100
15 | Karweien | 2016-09-28 08:00 | 2016-09-28 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-10-11 08:00 | 1d | 200 | 0 | 0 | 345 | 0 | 545 | 0 | 100% | Finished | 200 | 200 | 100 | 100 | 100 | 100 | 272.5 | 100
56 | Dakwerken | 2016-09-29 08:00 | 2016-12-07 17:00 | 50d |  |  | 45039 |  |  | 45039 |  | 56d | [5 empty] | 47398 |  | 100% |  | 45039 | 45039
16 | Daktimmer traditioneel/prefabkap | 2016-09-29 08:00 | 2016-11-21 17:00 | 38d |  | 0 | 38651 | 0 | 0 | 38651 | 2016-10-12 08:00 | 35d | 38651 | 0 | 0 | -1663 | 0 | 36988 | 0 | 100% | Finished | 38651 | 38651 | 100 | 92.1053 | 100 | 100 | 95.6974 | 100
17 | Dakdekken | 2016-11-22 08:00 | 2016-12-02 17:00 | 9d |  | 0 | 5171 | 0 | 0 | 5171 | 2016-11-30 08:00 | 14d | 5171 | 0 | 0 | 1815 | 0 | 6986 | 0 | 100% | Finished | 5171 | 5171 | 100 | 155.5556 | 100 | 100 | 135.0996 | 100
18 | Goten & afleiders | 2016-12-05 08:00 | 2016-12-07 17:00 | 3d |  | 0 | 1217 | 0 | 0 | 1217 | 2016-12-20 08:00 | 7d | 1217 | 0 | 0 | 2207 | 0 | 3424 | 0 | 100% | Finished | 1217 | 1217 | 100 | 233.3333 | 100 | 100 | 281.3476 | 100
57 | Buitenschrijnwerk | 2016-12-08 08:00 | 2016-12-28 17:00 | 15d |  |  | 25604 |  |  | 25604 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 25604
19 | Kader buitenschrijnwerk / Wachtbuizen | 2016-12-08 08:00 | 2016-12-09 17:00 | 2d |  | 0 | 1895 | 0 | 0 | 1895 |  | 0 | 0 | 1895 | 2d | 0 | 0 | 0 | 1895 | 0% | Not Started | 0 | 1895 | 100 |  | 0 | 100 |  | 0
20 | Buitenschrijnwerk plaatsen | 2016-12-12 08:00 | 2016-12-22 17:00 | 9d |  | 0 | 18502 | 0 | 0 | 18502 |  | 0 | 0 | 18502 | 9d | 0 | 0 | 0 | 18502 | 0% | Not Started | 0 | 18502 | 100 |  | 0 | 100 |  | 0
21 | Elastische voegen | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 657 | 0 | 0 | 657 |  | 0 | 0 | 657 | 3d | 0 | 0 | 0 | 657 | 0% | Not Started | 0 | 657 | 100 |  | 0 | 100 |  | 0
22 | Poort | 2016-12-23 08:00 | 2016-12-28 17:00 | 4d |  | 0 | 3650 | 0 | 0 | 3650 |  | 0 | 0 | 3650 | 4d | 0 | 0 | 0 | 3650 | 0% | Not Started | 0 | 3650 | 100 |  | 0 | 100 |  | 0
23 | Karwei buitenschrijnwerk | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 |  | 0 | 0 | 900 | 3d | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 900 | 100 |  | 0 | 100 |  | 0
58 | Binnenafwerking | 2017-01-27 08:00 | 2017-04-04 17:00 | 48d |  |  | 58308 |  |  | 58308 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | Plakwerken | 2017-01-27 08:00 | 2017-02-13 17:00 | 12d |  | 0 | 10564 | 0 | 0 | 10564 |  | 0 | 0 | 10564 | 12d | 0 | 0 | 0 | 10564 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Chapes | 2017-02-14 08:00 | 2017-02-20 17:00 | 5d |  | 0 | 6259 | 0 | 0 | 6259 |  | 0 | 0 | 6259 | 5d | 0 | 0 | 0 | 6259 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Vloerisolatie | 2017-02-22 08:00 | 2017-03-01 17:00 | 6d |  | 0 | 5374 | 0 | 0 | 5374 |  | 0 | 0 | 5374 | 6d | 0 | 0 | 0 | 5374 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Tegelwerken | 2017-03-02 08:00 | 2017-03-22 17:00 | 15d |  | 0 | 17507 | 0 | 0 | 17507 |  | 0 | 0 | 17507 | 15d | 0 | 0 | 0 | 17507 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Binnendeuren/Uitbekledingen | 2017-03-23 08:00 | 2017-03-29 17:00 | 5d |  | 0 | 8030 | 0 | 0 | 8030 |  | 0 | 0 | 8030 | 5d | 0 | 0 | 0 | 8030 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Trap | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 6700 | 0 | 0 | 6700 |  | 0 | 0 | 6700 | 3d | 0 | 0 | 0 | 6700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-04 17:00 | 9d |  | 0 | 2849 | 0 | 0 | 2849 |  | 0 | 0 | 2849 | 9d | 0 | 0 | 0 | 2849 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Karweiploeg | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 400 | 0 | 0 | 400 |  | 0 | 0 | 400 | 2d | 0 | 0 | 0 | 400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Technieken | 2016-12-23 08:00 | 2017-04-18 17:00 | 83d |  |  | 44115 |  |  | 44115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 7619
33 | UZL | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 846 | 0 | 0 | 846 |  | 0 | 0 | 846 | 3d | 0 | 0 | 0 | 846 | 0% | Not Started | 0 | 846 | 100 |  | 0 | 100 |  | 0
34 | Betonplexplaten | 2016-12-23 08:00 | 2016-12-26 17:00 | 2d |  | 0 | 300 | 0 | 0 | 300 |  | 0 | 0 | 300 | 2d | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 300 | 100 |  | 0 | 100 |  | 0
35 | Slijpen technieken/boringen | 2016-12-28 08:00 | 2017-01-03 17:00 | 5d |  | 0 | 6473 | 0 | 0 | 6473 |  | 0 | 0 | 6473 | 5d | 0 | 0 | 0 | 6473 | 0% | Not Started | 0 | 6473 | 100 |  | 0 | 100 |  | 0
36 | Bad en douche | 2017-02-21 08:00 | 2017-02-21 17:00 | 1d |  | 0 | 342 | 0 | 0 | 342 |  | 0 | 0 | 342 | 1d | 0 | 0 | 0 | 342 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Leidingen ventilatie | 2017-01-04 08:00 | 2017-01-06 17:00 | 3d |  | 0 | 1927 | 0 | 0 | 1927 |  | 0 | 0 | 1927 | 3d | 0 | 0 | 0 | 1927 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Leidingen san/WP/CV | 2017-01-09 08:00 | 2017-01-12 17:00 | 4d |  | 0 | 2454 | 0 | 0 | 2454 |  | 0 | 0 | 2454 | 4d | 0 | 0 | 0 | 2454 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Leidingen vloerverwarming | 2017-01-13 08:00 | 2017-01-20 17:00 | 6d |  | 0 | 5467 | 0 | 0 | 5467 |  | 0 | 0 | 5467 | 6d | 0 | 0 | 0 | 5467 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Afwerken ventilatie | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 1887 | 0 | 0 | 1887 |  | 0 | 0 | 1887 | 2d | 0 | 0 | 0 | 1887 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Afwerken sanitair | 2017-03-27 08:00 | 2017-03-29 17:00 | 3d |  | 0 | 3539 | 0 | 0 | 3539 |  | 0 | 0 | 3539 | 3d | 0 | 0 | 0 | 3539 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afwerken CV/WP | 2017-03-30 08:00 | 2017-04-04 17:00 | 4d |  | 0 | 5752 | 0 | 0 | 5752 |  | 0 | 0 | 5752 | 4d | 0 | 0 | 0 | 5752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Leidingen electro | 2017-01-23 08:00 | 2017-01-26 17:00 | 4d |  | 0 | 2737 | 0 | 0 | 2737 |  | 0 | 0 | 2737 | 4d | 0 | 0 | 0 | 2737 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Afwerken electro | 2017-04-05 08:00 | 2017-04-11 17:00 | 5d |  | 0 | 4986 | 0 | 0 | 4986 |  | 0 | 0 | 4986 | 5d | 0 | 0 | 0 | 4986 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Verlichting | 2017-04-12 08:00 | 2017-04-13 17:00 | 2d |  | 0 | 1500 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Diepsondering, bron en aansluiting | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 4905 | 0 | 0 | 4905 |  | 0 | 0 | 4905 | 5d | 0 | 0 | 0 | 4905 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Karweien | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 5d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Omgevingswerken | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  |  | 2885 |  |  | 2885 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
48 | Opkuis werf (afvoer puin en afval) | 2017-04-19 08:00 | 2017-04-25 17:00 | 5d |  | 0 | 1398 | 0 | 0 | 1398 |  | 0 | 0 | 1398 | 5d | 0 | 0 | 0 | 1398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Grondafvoer | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  | 0 | 1487 | 0 | 0 | 1487 |  | 0 | 0 | 1487 | 6d | 0 | 0 | 0 | 1487 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  |  | 6000 |  |  | 6000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  | 0 | 6000 | 0 | 0 | 6000 |  | 0 | 0 | 6000 | 10d | 0 | 0 | 0 | 6000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Restklasse | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  |  | 45763 |  |  | 45763 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
52 | Rest | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  | 0 | 45763 | 0 | 0 | 45763 |  | 0 | 0 | 45763 | 5d | 0 | 0 | 0 | 45763 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2017-05-23 08:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (3) | 2016-03-08 08:00 | 2017-05-09 17:00 | 306d |  |  | 367952 |  |  | 367952 |  | 315d | [5 empty] | 324716 |  | 85.15% |  | 313304 | 367952
53 | Voorbereiding | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  |  | 34516 |  |  | 34516 |  | 13d | [5 empty] | 35174 |  | 100% |  | 34516 | 34516
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 29347 | 0 | 0 | 29347 | 2016-03-08 08:00 | 5d | 29347 | 0 | 0 | 7 | 0 | 29354 | 0 | 100% | Finished | 29347 | 29347 | 100 | 100 | 100 | 100 | 100.0239 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 450 | 0 | 0 | 450 | 2016-03-08 08:00 | 3d | 450 | 0 | 0 | 378 | 0 | 828 | 0 | 100% | Finished | 450 | 450 | 100 | 150 | 100 | 100 | 184 | 100
3 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-03-08 08:00 | 13d | 2517 | 0 | 0 | 1675 | 0 | 4192 | 0 | 100% | Finished | 2517 | 2517 | 100 | 144.4444 | 100 | 100 | 166.5475 | 100
4 | Passief | 2016-03-08 08:00 | 2016-03-17 17:00 | 8d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-08 08:00 | 3d | 2202 | 0 | 0 | -1402 | 0 | 800 | 0 | 100% | Finished | 2202 | 2202 | 100 | 37.5 | 100 | 100 | 36.3306 | 100
54 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  |  | 12709 |  |  | 12709 |  | 32d | [5 empty] | 14531 |  | 100% |  | 12709 | 12709
5 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  | 0 | 12709 | 0 | 0 | 12709 | 2016-03-25 08:00 | 32d | 12709 | 0 | 0 | 1822 | 0 | 14531 | 0 | 100% | Finished | 12709 | 12709 | 100 | 118.5185 | 100 | 100 | 114.3363 | 100
55 | Ruwbouw | 2016-04-27 08:00 | 2016-09-28 17:00 | 111d |  |  | 93013 |  |  | 93013 |  | 111d | [5 empty] | 84768 |  | 100% |  | 93013 | 93013
6 | GEWA/Metselwerken | 2016-04-27 08:00 | 2016-05-24 17:00 | 20d |  | 0 | 17864 | 0 | 0 | 17864 | 2016-05-10 08:00 | 17d | 17864 | 0 | 0 | -5192 | 0 | 12672 | 0 | 100% | Finished | 17864 | 17864 | 100 | 85 | 100 | 100 | 70.936 | 100
7 | Gewelven/Structuur | 2016-05-25 08:00 | 2016-06-16 17:00 | 17d |  | 0 | 15388 | 0 | 0 | 15388 | 2016-06-02 08:00 | 16d | 15388 | 0 | 0 | -2976 | 0 | 12412 | 0 | 100% | Finished | 15388 | 15388 | 100 | 94.1176 | 100 | 100 | 80.6603 | 100
8 | Uitbranden GEWA | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 562 | 0 | 0 | 562 | 2016-06-02 08:00 | 2d | 562 | 0 | 0 | -262 | 0 | 300 | 0 | 100% | Finished | 562 | 562 | 100 | 100 | 100 | 100 | 53.3808 | 100
9 | Isolatie | 2016-06-17 08:00 | 2016-07-01 17:00 | 11d |  | 0 | 10384 | 0 | 0 | 10384 | 2016-06-24 08:00 | 9d | 10384 | 0 | 0 | -1829 | 0 | 8555 | 0 | 100% | Finished | 10384 | 10384 | 100 | 81.8182 | 100 | 100 | 82.3864 | 100
10 | Parament | 2016-07-04 08:00 | 2016-08-29 17:00 | 41d |  | 0 | 37120 | 0 | 0 | 37120 | 2016-07-07 08:00 | 49d | 37120 | 0 | 0 | -1023 | 0 | 36097 | 0 | 100% | Finished | 37120 | 37120 | 100 | 119.5122 | 100 | 100 | 97.2441 | 100
11 | Ytong/Gipswanden | 2016-08-30 08:00 | 2016-09-01 17:00 | 3d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-09-14 08:00 | 3d | 2517 | 0 | 0 | -17 | 0 | 2500 | 0 | 100% | Finished | 2517 | 2517 | 100 | 100 | 100 | 100 | 99.3246 | 100
12 | Dorpels | 2016-09-02 08:00 | 2016-09-07 17:00 | 4d |  | 0 | 3081 | 0 | 0 | 3081 | 2016-09-19 08:00 | 6d | 3081 | 0 | 0 | 4237 | 0 | 7318 | 0 | 100% | Finished | 3081 | 3081 | 100 | 150 | 100 | 100 | 237.5203 | 100
13 | Voegwerk | 2016-09-02 08:00 | 2016-09-16 17:00 | 11d |  | 0 | 3082 | 0 | 0 | 3082 | 2016-09-19 08:00 | 11d | 3082 | 0 | 0 | 93 | 0 | 3175 | 0 | 100% | Finished | 3082 | 3082 | 100 | 100 | 100 | 100 | 103.0175 | 100
14 | Stelling | 2016-09-19 08:00 | 2016-09-27 17:00 | 7d |  | 0 | 2815 | 0 | 0 | 2815 | 2016-10-04 08:00 | 5d | 2815 | 0 | 0 | -1621 | 0 | 1194 | 0 | 100% | Finished | 2815 | 2815 | 100 | 71.4286 | 100 | 100 | 42.4156 | 100
15 | Karweien | 2016-09-28 08:00 | 2016-09-28 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-10-11 08:00 | 1d | 200 | 0 | 0 | 345 | 0 | 545 | 0 | 100% | Finished | 200 | 200 | 100 | 100 | 100 | 100 | 272.5 | 100
56 | Dakwerken | 2016-09-29 08:00 | 2016-12-07 17:00 | 50d |  |  | 45039 |  |  | 45039 |  | 56d | [5 empty] | 47398 |  | 100% |  | 45039 | 45039
16 | Daktimmer traditioneel/prefabkap | 2016-09-29 08:00 | 2016-11-21 17:00 | 38d |  | 0 | 38651 | 0 | 0 | 38651 | 2016-10-12 08:00 | 35d | 38651 | 0 | 0 | -1663 | 0 | 36988 | 0 | 100% | Finished | 38651 | 38651 | 100 | 92.1053 | 100 | 100 | 95.6974 | 100
17 | Dakdekken | 2016-11-22 08:00 | 2016-12-02 17:00 | 9d |  | 0 | 5171 | 0 | 0 | 5171 | 2016-11-30 08:00 | 14d | 5171 | 0 | 0 | 1815 | 0 | 6986 | 0 | 100% | Finished | 5171 | 5171 | 100 | 155.5556 | 100 | 100 | 135.0996 | 100
18 | Goten & afleiders | 2016-12-05 08:00 | 2016-12-07 17:00 | 3d |  | 0 | 1217 | 0 | 0 | 1217 | 2016-12-20 08:00 | 7d | 1217 | 0 | 0 | 2207 | 0 | 3424 | 0 | 100% | Finished | 1217 | 1217 | 100 | 233.3333 | 100 | 100 | 281.3476 | 100
57 | Buitenschrijnwerk | 2016-12-08 08:00 | 2016-12-28 17:00 | 15d |  |  | 25604 |  |  | 25604 |  | 18d | [5 empty] | 28044 |  | 100% |  | 25604 | 25604
19 | Kader buitenschrijnwerk / Wachtbuizen | 2016-12-08 08:00 | 2016-12-09 17:00 | 2d |  | 0 | 1895 | 0 | 0 | 1895 | 2016-12-29 08:00 | 1d | 1895 | 0 | 0 | -1651 | 0 | 244 | 0 | 100% | Finished | 1895 | 1895 | 100 | 50 | 100 | 100 | 12.876 | 100
20 | Buitenschrijnwerk plaatsen | 2016-12-12 08:00 | 2016-12-22 17:00 | 9d |  | 0 | 18502 | 0 | 0 | 18502 | 2016-12-30 08:00 | 12d | 18502 | 0 | 0 | 3344 | 0 | 21846 | 0 | 100% | Finished | 18502 | 18502 | 100 | 133.3333 | 100 | 100 | 118.0737 | 100
21 | Elastische voegen | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 657 | 0 | 0 | 657 | 2017-01-17 08:00 | 2d | 657 | 0 | 0 | -190 | 0 | 467 | 0 | 100% | Finished | 657 | 657 | 100 | 66.6667 | 100 | 100 | 71.0807 | 100
22 | Poort | 2016-12-23 08:00 | 2016-12-28 17:00 | 4d |  | 0 | 3650 | 0 | 0 | 3650 | 2017-01-17 08:00 | 5d | 3650 | 0 | 0 | 957 | 0 | 4607 | 0 | 100% | Finished | 3650 | 3650 | 100 | 125 | 100 | 100 | 126.2192 | 100
23 | Karwei buitenschrijnwerk | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 2017-01-17 08:00 | 3d | 900 | 0 | 0 | -20 | 0 | 880 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 97.7778 | 100
58 | Binnenafwerking | 2017-01-27 08:00 | 2017-04-04 17:00 | 48d |  |  | 58308 |  |  | 58308 |  | 49d | [5 empty] | 61856 |  | 100% |  | 58308 | 58308
24 | Plakwerken | 2017-01-27 08:00 | 2017-02-13 17:00 | 12d |  | 0 | 10564 | 0 | 0 | 10564 | 2017-02-20 08:00 | 15d | 10564 | 0 | 0 | 3832 | 0 | 14396 | 0 | 100% | Finished | 10564 | 10564 | 100 | 125 | 100 | 100 | 136.2741 | 100
25 | Chapes | 2017-02-14 08:00 | 2017-02-20 17:00 | 5d |  | 0 | 6259 | 0 | 0 | 6259 | 2017-03-13 08:00 | 10d | 6259 | 0 | 0 | 2067 | 0 | 8326 | 0 | 100% | Finished | 6259 | 6259 | 100 | 200 | 100 | 100 | 133.0244 | 100
26 | Vloerisolatie | 2017-02-22 08:00 | 2017-03-01 17:00 | 6d |  | 0 | 5374 | 0 | 0 | 5374 | 2017-03-22 08:00 | 5d | 5374 | 0 | 0 | -1120 | 0 | 4254 | 0 | 100% | Finished | 5374 | 5374 | 100 | 83.3333 | 100 | 100 | 79.1589 | 100
27 | Tegelwerken | 2017-03-02 08:00 | 2017-03-22 17:00 | 15d |  | 0 | 17507 | 0 | 0 | 17507 | 2017-03-29 08:00 | 15d | 17507 | 0 | 0 | -563 | 0 | 16944 | 0 | 100% | Finished | 17507 | 17507 | 100 | 100 | 100 | 100 | 96.7841 | 100
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2017-04-19 08:00 | 2d | 625 | 0 | 0 | 32 | 0 | 657 | 0 | 100% | Finished | 625 | 625 | 100 | 66.6667 | 100 | 100 | 105.12 | 100
29 | Binnendeuren/Uitbekledingen | 2017-03-23 08:00 | 2017-03-29 17:00 | 5d |  | 0 | 8030 | 0 | 0 | 8030 | 2017-04-19 08:00 | 5d | 8030 | 0 | 0 | 0 | 0 | 8030 | 0 | 100% | Finished | 8030 | 8030 | 100 | 100 | 100 | 100 | 100 | 100
30 | Trap | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 6700 | 0 | 0 | 6700 | 2017-04-19 08:00 | 3d | 6700 | 0 | 0 | -624 | 0 | 6076 | 0 | 100% | Finished | 6700 | 6700 | 100 | 100 | 100 | 100 | 90.6866 | 100
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-04 17:00 | 9d |  | 0 | 2849 | 0 | 0 | 2849 | 2017-04-19 08:00 | 7d | 2849 | 0 | 0 | -55 | 0 | 2794 | 0 | 100% | Finished | 2849 | 2849 | 100 | 77.7778 | 100 | 100 | 98.0695 | 100
32 | Karweiploeg | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 400 | 0 | 0 | 400 | 2017-04-19 08:00 | 2d | 400 | 0 | 0 | -21 | 0 | 379 | 0 | 100% | Finished | 400 | 400 | 100 | 100 | 100 | 100 | 94.75 | 100
59 | Technieken | 2016-12-23 08:00 | 2017-04-18 17:00 | 83d |  |  | 44115 |  |  | 44115 |  | 90d | [5 empty] | 52945 |  | 100% |  | 44115 | 44115
33 | UZL | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 846 | 0 | 0 | 846 | 2017-01-17 08:00 | 4d | 846 | 0 | 0 | 446 | 0 | 1292 | 0 | 100% | Finished | 846 | 846 | 100 | 133.3333 | 100 | 100 | 152.7187 | 100
34 | Betonplexplaten | 2016-12-23 08:00 | 2016-12-26 17:00 | 2d |  | 0 | 300 | 0 | 0 | 300 | 2017-01-17 08:00 | 2d | 300 | 0 | 0 | 1 | 0 | 301 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100.3333 | 100
35 | Slijpen technieken/boringen | 2016-12-28 08:00 | 2017-01-03 17:00 | 5d |  | 0 | 6473 | 0 | 0 | 6473 | 2017-01-23 08:00 | 5d | 6473 | 0 | 0 | 261 | 0 | 6734 | 0 | 100% | Finished | 6473 | 6473 | 100 | 100 | 100 | 100 | 104.0321 | 100
36 | Bad en douche | 2017-02-21 08:00 | 2017-02-21 17:00 | 1d |  | 0 | 342 | 0 | 0 | 342 | 2017-03-20 08:00 | 2d | 342 | 0 | 0 | 52 | 0 | 394 | 0 | 100% | Finished | 342 | 342 | 100 | 200 | 100 | 100 | 115.2047 | 100
37 | Leidingen ventilatie | 2017-01-04 08:00 | 2017-01-06 17:00 | 3d |  | 0 | 1927 | 0 | 0 | 1927 | 2017-01-30 08:00 | 2d | 1927 | 0 | 0 | -114 | 0 | 1813 | 0 | 100% | Finished | 1927 | 1927 | 100 | 66.6667 | 100 | 100 | 94.0841 | 100
38 | Leidingen san/WP/CV | 2017-01-09 08:00 | 2017-01-12 17:00 | 4d |  | 0 | 2454 | 0 | 0 | 2454 | 2017-02-01 08:00 | 4d | 2454 | 0 | 0 | 372 | 0 | 2826 | 0 | 100% | Finished | 2454 | 2454 | 100 | 100 | 100 | 100 | 115.1589 | 100
39 | Leidingen vloerverwarming | 2017-01-13 08:00 | 2017-01-20 17:00 | 6d |  | 0 | 5467 | 0 | 0 | 5467 | 2017-02-07 08:00 | 5d | 5467 | 0 | 0 | -934 | 0 | 4533 | 0 | 100% | Finished | 5467 | 5467 | 100 | 83.3333 | 100 | 100 | 82.9157 | 100
40 | Afwerken ventilatie | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 1887 | 0 | 0 | 1887 | 2017-04-19 08:00 | 1d | 1887 | 0 | 0 | 60 | 0 | 1947 | 0 | 100% | Finished | 1887 | 1887 | 100 | 50 | 100 | 100 | 103.1797 | 100
41 | Afwerken sanitair | 2017-03-27 08:00 | 2017-03-29 17:00 | 3d |  | 0 | 3539 | 0 | 0 | 3539 | 2017-04-20 08:00 | 4d | 3539 | 0 | 0 | 686 | 0 | 4225 | 0 | 100% | Finished | 3539 | 3539 | 100 | 133.3333 | 100 | 100 | 119.384 | 100
42 | Afwerken CV/WP | 2017-03-30 08:00 | 2017-04-04 17:00 | 4d |  | 0 | 5752 | 0 | 0 | 5752 | 2017-04-26 08:00 | 5d | 5752 | 0 | 0 | 3970 | 0 | 9722 | 0 | 100% | Finished | 5752 | 5752 | 100 | 125 | 100 | 100 | 169.0195 | 100
43 | Leidingen electro | 2017-01-23 08:00 | 2017-01-26 17:00 | 4d |  | 0 | 2737 | 0 | 0 | 2737 | 2017-02-14 08:00 | 4d | 2737 | 0 | 0 | -198 | 0 | 2539 | 0 | 100% | Finished | 2737 | 2737 | 100 | 100 | 100 | 100 | 92.7658 | 100
44 | Afwerken electro | 2017-04-05 08:00 | 2017-04-11 17:00 | 5d |  | 0 | 4986 | 0 | 0 | 4986 | 2017-05-03 08:00 | 8d | 4986 | 0 | 0 | 3896 | 0 | 8882 | 0 | 100% | Finished | 4986 | 4986 | 100 | 160 | 100 | 100 | 178.1388 | 100
45 | Verlichting | 2017-04-12 08:00 | 2017-04-13 17:00 | 2d |  | 0 | 1500 | 0 | 0 | 1500 | 2017-05-15 08:00 | 2d | 1500 | 0 | 0 | 16 | 0 | 1516 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 101.0667 | 100
46 | Diepsondering, bron en aansluiting | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 4905 | 0 | 0 | 4905 | 2017-05-15 08:00 | 5d | 4905 | 0 | 0 | -405 | 0 | 4500 | 0 | 100% | Finished | 4905 | 4905 | 100 | 100 | 100 | 100 | 91.7431 | 100
47 | Karweien | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 1000 | 0 | 0 | 1000 | 2017-05-15 08:00 | 6d | 1000 | 0 | 0 | 721 | 0 | 1721 | 0 | 100% | Finished | 1000 | 1000 | 100 | 120 | 100 | 100 | 172.1 | 100
60 | Omgevingswerken | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  |  | 2885 |  |  | 2885 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2885
48 | Opkuis werf (afvoer puin en afval) | 2017-04-19 08:00 | 2017-04-25 17:00 | 5d |  | 0 | 1398 | 0 | 0 | 1398 |  | 0 | 0 | 1398 | 5d | 0 | 0 | 0 | 1398 | 0% | Not Started | 0 | 1398 | 100 |  | 0 | 100 |  | 0
50 | Grondafvoer | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  | 0 | 1487 | 0 | 0 | 1487 |  | 0 | 0 | 1487 | 6d | 0 | 0 | 0 | 1487 | 0% | Not Started | 0 | 1487 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  |  | 6000 |  |  | 6000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6000
51 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  | 0 | 6000 | 0 | 0 | 6000 |  | 0 | 0 | 6000 | 10d | 0 | 0 | 0 | 6000 | 0% | Not Started | 0 | 6000 | 100 |  | 0 | 100 |  | 0
62 | Restklasse | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  |  | 45763 |  |  | 45763 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 45763
52 | Rest | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  | 0 | 45763 | 0 | 0 | 45763 |  | 0 | 0 | 45763 | 5d | 0 | 0 | 0 | 45763 | 0% | Not Started | 0 | 45763 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2017-06-12 17:00 |  | TP Name | Tracking Period 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (3) | 2016-03-08 08:00 | 2017-05-09 17:00 | 306d |  |  | 367952 |  |  | 367952 |  | 330d | [5 empty] | 379300 |  | 100% |  | 367952 | 367952
53 | Voorbereiding | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  |  | 34516 |  |  | 34516 |  | 13d | [5 empty] | 35174 |  | 100% |  | 34516 | 34516
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 29347 | 0 | 0 | 29347 | 2016-03-08 08:00 | 5d | 29347 | 0 | 0 | 7 | 0 | 29354 | 0 | 100% | Finished | 29347 | 29347 | 100 | 100 | 100 | 100 | 100.0239 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 450 | 0 | 0 | 450 | 2016-03-08 08:00 | 3d | 450 | 0 | 0 | 378 | 0 | 828 | 0 | 100% | Finished | 450 | 450 | 100 | 150 | 100 | 100 | 184 | 100
3 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-18 17:00 | 9d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-03-08 08:00 | 13d | 2517 | 0 | 0 | 1675 | 0 | 4192 | 0 | 100% | Finished | 2517 | 2517 | 100 | 144.4444 | 100 | 100 | 166.5475 | 100
4 | Passief | 2016-03-08 08:00 | 2016-03-17 17:00 | 8d |  | 0 | 2202 | 0 | 0 | 2202 | 2016-03-08 08:00 | 3d | 2202 | 0 | 0 | -1402 | 0 | 800 | 0 | 100% | Finished | 2202 | 2202 | 100 | 37.5 | 100 | 100 | 36.3306 | 100
54 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  |  | 12709 |  |  | 12709 |  | 32d | [5 empty] | 14531 |  | 100% |  | 12709 | 12709
5 | Funderingen | 2016-03-21 08:00 | 2016-04-26 17:00 | 27d |  | 0 | 12709 | 0 | 0 | 12709 | 2016-03-25 08:00 | 32d | 12709 | 0 | 0 | 1822 | 0 | 14531 | 0 | 100% | Finished | 12709 | 12709 | 100 | 118.5185 | 100 | 100 | 114.3363 | 100
55 | Ruwbouw | 2016-04-27 08:00 | 2016-09-28 17:00 | 111d |  |  | 93013 |  |  | 93013 |  | 111d | [5 empty] | 84768 |  | 100% |  | 93013 | 93013
6 | GEWA/Metselwerken | 2016-04-27 08:00 | 2016-05-24 17:00 | 20d |  | 0 | 17864 | 0 | 0 | 17864 | 2016-05-10 08:00 | 17d | 17864 | 0 | 0 | -5192 | 0 | 12672 | 0 | 100% | Finished | 17864 | 17864 | 100 | 85 | 100 | 100 | 70.936 | 100
7 | Gewelven/Structuur | 2016-05-25 08:00 | 2016-06-16 17:00 | 17d |  | 0 | 15388 | 0 | 0 | 15388 | 2016-06-02 08:00 | 16d | 15388 | 0 | 0 | -2976 | 0 | 12412 | 0 | 100% | Finished | 15388 | 15388 | 100 | 94.1176 | 100 | 100 | 80.6603 | 100
8 | Uitbranden GEWA | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 562 | 0 | 0 | 562 | 2016-06-02 08:00 | 2d | 562 | 0 | 0 | -262 | 0 | 300 | 0 | 100% | Finished | 562 | 562 | 100 | 100 | 100 | 100 | 53.3808 | 100
9 | Isolatie | 2016-06-17 08:00 | 2016-07-01 17:00 | 11d |  | 0 | 10384 | 0 | 0 | 10384 | 2016-06-24 08:00 | 9d | 10384 | 0 | 0 | -1829 | 0 | 8555 | 0 | 100% | Finished | 10384 | 10384 | 100 | 81.8182 | 100 | 100 | 82.3864 | 100
10 | Parament | 2016-07-04 08:00 | 2016-08-29 17:00 | 41d |  | 0 | 37120 | 0 | 0 | 37120 | 2016-07-07 08:00 | 49d | 37120 | 0 | 0 | -1023 | 0 | 36097 | 0 | 100% | Finished | 37120 | 37120 | 100 | 119.5122 | 100 | 100 | 97.2441 | 100
11 | Ytong/Gipswanden | 2016-08-30 08:00 | 2016-09-01 17:00 | 3d |  | 0 | 2517 | 0 | 0 | 2517 | 2016-09-14 08:00 | 3d | 2517 | 0 | 0 | -17 | 0 | 2500 | 0 | 100% | Finished | 2517 | 2517 | 100 | 100 | 100 | 100 | 99.3246 | 100
12 | Dorpels | 2016-09-02 08:00 | 2016-09-07 17:00 | 4d |  | 0 | 3081 | 0 | 0 | 3081 | 2016-09-19 08:00 | 6d | 3081 | 0 | 0 | 4237 | 0 | 7318 | 0 | 100% | Finished | 3081 | 3081 | 100 | 150 | 100 | 100 | 237.5203 | 100
13 | Voegwerk | 2016-09-02 08:00 | 2016-09-16 17:00 | 11d |  | 0 | 3082 | 0 | 0 | 3082 | 2016-09-19 08:00 | 11d | 3082 | 0 | 0 | 93 | 0 | 3175 | 0 | 100% | Finished | 3082 | 3082 | 100 | 100 | 100 | 100 | 103.0175 | 100
14 | Stelling | 2016-09-19 08:00 | 2016-09-27 17:00 | 7d |  | 0 | 2815 | 0 | 0 | 2815 | 2016-10-04 08:00 | 5d | 2815 | 0 | 0 | -1621 | 0 | 1194 | 0 | 100% | Finished | 2815 | 2815 | 100 | 71.4286 | 100 | 100 | 42.4156 | 100
15 | Karweien | 2016-09-28 08:00 | 2016-09-28 17:00 | 1d |  | 0 | 200 | 0 | 0 | 200 | 2016-10-11 08:00 | 1d | 200 | 0 | 0 | 345 | 0 | 545 | 0 | 100% | Finished | 200 | 200 | 100 | 100 | 100 | 100 | 272.5 | 100
56 | Dakwerken | 2016-09-29 08:00 | 2016-12-07 17:00 | 50d |  |  | 45039 |  |  | 45039 |  | 56d | [5 empty] | 47398 |  | 100% |  | 45039 | 45039
16 | Daktimmer traditioneel/prefabkap | 2016-09-29 08:00 | 2016-11-21 17:00 | 38d |  | 0 | 38651 | 0 | 0 | 38651 | 2016-10-12 08:00 | 35d | 38651 | 0 | 0 | -1663 | 0 | 36988 | 0 | 100% | Finished | 38651 | 38651 | 100 | 92.1053 | 100 | 100 | 95.6974 | 100
17 | Dakdekken | 2016-11-22 08:00 | 2016-12-02 17:00 | 9d |  | 0 | 5171 | 0 | 0 | 5171 | 2016-11-30 08:00 | 14d | 5171 | 0 | 0 | 1815 | 0 | 6986 | 0 | 100% | Finished | 5171 | 5171 | 100 | 155.5556 | 100 | 100 | 135.0996 | 100
18 | Goten & afleiders | 2016-12-05 08:00 | 2016-12-07 17:00 | 3d |  | 0 | 1217 | 0 | 0 | 1217 | 2016-12-20 08:00 | 7d | 1217 | 0 | 0 | 2207 | 0 | 3424 | 0 | 100% | Finished | 1217 | 1217 | 100 | 233.3333 | 100 | 100 | 281.3476 | 100
57 | Buitenschrijnwerk | 2016-12-08 08:00 | 2016-12-28 17:00 | 15d |  |  | 25604 |  |  | 25604 |  | 18d | [5 empty] | 28044 |  | 100% |  | 25604 | 25604
19 | Kader buitenschrijnwerk / Wachtbuizen | 2016-12-08 08:00 | 2016-12-09 17:00 | 2d |  | 0 | 1895 | 0 | 0 | 1895 | 2016-12-29 08:00 | 1d | 1895 | 0 | 0 | -1651 | 0 | 244 | 0 | 100% | Finished | 1895 | 1895 | 100 | 50 | 100 | 100 | 12.876 | 100
20 | Buitenschrijnwerk plaatsen | 2016-12-12 08:00 | 2016-12-22 17:00 | 9d |  | 0 | 18502 | 0 | 0 | 18502 | 2016-12-30 08:00 | 12d | 18502 | 0 | 0 | 3344 | 0 | 21846 | 0 | 100% | Finished | 18502 | 18502 | 100 | 133.3333 | 100 | 100 | 118.0737 | 100
21 | Elastische voegen | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 657 | 0 | 0 | 657 | 2017-01-17 08:00 | 2d | 657 | 0 | 0 | -190 | 0 | 467 | 0 | 100% | Finished | 657 | 657 | 100 | 66.6667 | 100 | 100 | 71.0807 | 100
22 | Poort | 2016-12-23 08:00 | 2016-12-28 17:00 | 4d |  | 0 | 3650 | 0 | 0 | 3650 | 2017-01-17 08:00 | 5d | 3650 | 0 | 0 | 957 | 0 | 4607 | 0 | 100% | Finished | 3650 | 3650 | 100 | 125 | 100 | 100 | 126.2192 | 100
23 | Karwei buitenschrijnwerk | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 2017-01-17 08:00 | 3d | 900 | 0 | 0 | -20 | 0 | 880 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 97.7778 | 100
58 | Binnenafwerking | 2017-01-27 08:00 | 2017-04-04 17:00 | 48d |  |  | 58308 |  |  | 58308 |  | 49d | [5 empty] | 61856 |  | 100% |  | 58308 | 58308
24 | Plakwerken | 2017-01-27 08:00 | 2017-02-13 17:00 | 12d |  | 0 | 10564 | 0 | 0 | 10564 | 2017-02-20 08:00 | 15d | 10564 | 0 | 0 | 3832 | 0 | 14396 | 0 | 100% | Finished | 10564 | 10564 | 100 | 125 | 100 | 100 | 136.2741 | 100
25 | Chapes | 2017-02-14 08:00 | 2017-02-20 17:00 | 5d |  | 0 | 6259 | 0 | 0 | 6259 | 2017-03-13 08:00 | 10d | 6259 | 0 | 0 | 2067 | 0 | 8326 | 0 | 100% | Finished | 6259 | 6259 | 100 | 200 | 100 | 100 | 133.0244 | 100
26 | Vloerisolatie | 2017-02-22 08:00 | 2017-03-01 17:00 | 6d |  | 0 | 5374 | 0 | 0 | 5374 | 2017-03-22 08:00 | 5d | 5374 | 0 | 0 | -1120 | 0 | 4254 | 0 | 100% | Finished | 5374 | 5374 | 100 | 83.3333 | 100 | 100 | 79.1589 | 100
27 | Tegelwerken | 2017-03-02 08:00 | 2017-03-22 17:00 | 15d |  | 0 | 17507 | 0 | 0 | 17507 | 2017-03-29 08:00 | 15d | 17507 | 0 | 0 | -563 | 0 | 16944 | 0 | 100% | Finished | 17507 | 17507 | 100 | 100 | 100 | 100 | 96.7841 | 100
28 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2017-04-19 08:00 | 2d | 625 | 0 | 0 | 32 | 0 | 657 | 0 | 100% | Finished | 625 | 625 | 100 | 66.6667 | 100 | 100 | 105.12 | 100
29 | Binnendeuren/Uitbekledingen | 2017-03-23 08:00 | 2017-03-29 17:00 | 5d |  | 0 | 8030 | 0 | 0 | 8030 | 2017-04-19 08:00 | 5d | 8030 | 0 | 0 | 0 | 0 | 8030 | 0 | 100% | Finished | 8030 | 8030 | 100 | 100 | 100 | 100 | 100 | 100
30 | Trap | 2017-03-23 08:00 | 2017-03-27 17:00 | 3d |  | 0 | 6700 | 0 | 0 | 6700 | 2017-04-19 08:00 | 3d | 6700 | 0 | 0 | -624 | 0 | 6076 | 0 | 100% | Finished | 6700 | 6700 | 100 | 100 | 100 | 100 | 90.6866 | 100
31 | Luchtdichten | 2017-03-23 08:00 | 2017-04-04 17:00 | 9d |  | 0 | 2849 | 0 | 0 | 2849 | 2017-04-19 08:00 | 7d | 2849 | 0 | 0 | -55 | 0 | 2794 | 0 | 100% | Finished | 2849 | 2849 | 100 | 77.7778 | 100 | 100 | 98.0695 | 100
32 | Karweiploeg | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 400 | 0 | 0 | 400 | 2017-04-19 08:00 | 2d | 400 | 0 | 0 | -21 | 0 | 379 | 0 | 100% | Finished | 400 | 400 | 100 | 100 | 100 | 100 | 94.75 | 100
59 | Technieken | 2016-12-23 08:00 | 2017-04-18 17:00 | 83d |  |  | 44115 |  |  | 44115 |  | 90d | [5 empty] | 52945 |  | 100% |  | 44115 | 44115
33 | UZL | 2016-12-23 08:00 | 2016-12-27 17:00 | 3d |  | 0 | 846 | 0 | 0 | 846 | 2017-01-17 08:00 | 4d | 846 | 0 | 0 | 446 | 0 | 1292 | 0 | 100% | Finished | 846 | 846 | 100 | 133.3333 | 100 | 100 | 152.7187 | 100
34 | Betonplexplaten | 2016-12-23 08:00 | 2016-12-26 17:00 | 2d |  | 0 | 300 | 0 | 0 | 300 | 2017-01-17 08:00 | 2d | 300 | 0 | 0 | 1 | 0 | 301 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100.3333 | 100
35 | Slijpen technieken/boringen | 2016-12-28 08:00 | 2017-01-03 17:00 | 5d |  | 0 | 6473 | 0 | 0 | 6473 | 2017-01-23 08:00 | 5d | 6473 | 0 | 0 | 261 | 0 | 6734 | 0 | 100% | Finished | 6473 | 6473 | 100 | 100 | 100 | 100 | 104.0321 | 100
36 | Bad en douche | 2017-02-21 08:00 | 2017-02-21 17:00 | 1d |  | 0 | 342 | 0 | 0 | 342 | 2017-03-20 08:00 | 2d | 342 | 0 | 0 | 52 | 0 | 394 | 0 | 100% | Finished | 342 | 342 | 100 | 200 | 100 | 100 | 115.2047 | 100
37 | Leidingen ventilatie | 2017-01-04 08:00 | 2017-01-06 17:00 | 3d |  | 0 | 1927 | 0 | 0 | 1927 | 2017-01-30 08:00 | 2d | 1927 | 0 | 0 | -114 | 0 | 1813 | 0 | 100% | Finished | 1927 | 1927 | 100 | 66.6667 | 100 | 100 | 94.0841 | 100
38 | Leidingen san/WP/CV | 2017-01-09 08:00 | 2017-01-12 17:00 | 4d |  | 0 | 2454 | 0 | 0 | 2454 | 2017-02-01 08:00 | 4d | 2454 | 0 | 0 | 372 | 0 | 2826 | 0 | 100% | Finished | 2454 | 2454 | 100 | 100 | 100 | 100 | 115.1589 | 100
39 | Leidingen vloerverwarming | 2017-01-13 08:00 | 2017-01-20 17:00 | 6d |  | 0 | 5467 | 0 | 0 | 5467 | 2017-02-07 08:00 | 5d | 5467 | 0 | 0 | -934 | 0 | 4533 | 0 | 100% | Finished | 5467 | 5467 | 100 | 83.3333 | 100 | 100 | 82.9157 | 100
40 | Afwerken ventilatie | 2017-03-23 08:00 | 2017-03-24 17:00 | 2d |  | 0 | 1887 | 0 | 0 | 1887 | 2017-04-19 08:00 | 1d | 1887 | 0 | 0 | 60 | 0 | 1947 | 0 | 100% | Finished | 1887 | 1887 | 100 | 50 | 100 | 100 | 103.1797 | 100
41 | Afwerken sanitair | 2017-03-27 08:00 | 2017-03-29 17:00 | 3d |  | 0 | 3539 | 0 | 0 | 3539 | 2017-04-20 08:00 | 4d | 3539 | 0 | 0 | 686 | 0 | 4225 | 0 | 100% | Finished | 3539 | 3539 | 100 | 133.3333 | 100 | 100 | 119.384 | 100
42 | Afwerken CV/WP | 2017-03-30 08:00 | 2017-04-04 17:00 | 4d |  | 0 | 5752 | 0 | 0 | 5752 | 2017-04-26 08:00 | 5d | 5752 | 0 | 0 | 3970 | 0 | 9722 | 0 | 100% | Finished | 5752 | 5752 | 100 | 125 | 100 | 100 | 169.0195 | 100
43 | Leidingen electro | 2017-01-23 08:00 | 2017-01-26 17:00 | 4d |  | 0 | 2737 | 0 | 0 | 2737 | 2017-02-14 08:00 | 4d | 2737 | 0 | 0 | -198 | 0 | 2539 | 0 | 100% | Finished | 2737 | 2737 | 100 | 100 | 100 | 100 | 92.7658 | 100
44 | Afwerken electro | 2017-04-05 08:00 | 2017-04-11 17:00 | 5d |  | 0 | 4986 | 0 | 0 | 4986 | 2017-05-03 08:00 | 8d | 4986 | 0 | 0 | 3896 | 0 | 8882 | 0 | 100% | Finished | 4986 | 4986 | 100 | 160 | 100 | 100 | 178.1388 | 100
45 | Verlichting | 2017-04-12 08:00 | 2017-04-13 17:00 | 2d |  | 0 | 1500 | 0 | 0 | 1500 | 2017-05-15 08:00 | 2d | 1500 | 0 | 0 | 16 | 0 | 1516 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 101.0667 | 100
46 | Diepsondering, bron en aansluiting | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 4905 | 0 | 0 | 4905 | 2017-05-15 08:00 | 5d | 4905 | 0 | 0 | -405 | 0 | 4500 | 0 | 100% | Finished | 4905 | 4905 | 100 | 100 | 100 | 100 | 91.7431 | 100
47 | Karweien | 2017-04-12 08:00 | 2017-04-18 17:00 | 5d |  | 0 | 1000 | 0 | 0 | 1000 | 2017-05-15 08:00 | 6d | 1000 | 0 | 0 | 721 | 0 | 1721 | 0 | 100% | Finished | 1000 | 1000 | 100 | 120 | 100 | 100 | 172.1 | 100
60 | Omgevingswerken | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  |  | 2885 |  |  | 2885 |  | 6d | [5 empty] | 2700 |  | 100% |  | 2885 | 2885
48 | Opkuis werf (afvoer puin en afval) | 2017-04-19 08:00 | 2017-04-25 17:00 | 5d |  | 0 | 1398 | 0 | 0 | 1398 | 2017-05-23 08:00 | 5d | 1398 | 0 | 0 | -98 | 0 | 1300 | 0 | 100% | Finished | 1398 | 1398 | 100 | 100 | 100 | 100 | 92.99 | 100
50 | Grondafvoer | 2017-04-19 08:00 | 2017-04-26 17:00 | 6d |  | 0 | 1487 | 0 | 0 | 1487 | 2017-05-23 08:00 | 6d | 1487 | 0 | 0 | -87 | 0 | 1400 | 0 | 100% | Finished | 1487 | 1487 | 100 | 100 | 100 | 100 | 94.1493 | 100
61 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  |  | 6000 |  |  | 6000 |  | 10d | [5 empty] | 6121 |  | 100% |  | 6000 | 6000
51 | Schilderwerken | 2017-04-19 08:00 | 2017-05-02 17:00 | 10d |  | 0 | 6000 | 0 | 0 | 6000 | 2017-05-23 08:00 | 10d | 6000 | 0 | 0 | 121 | 0 | 6121 | 0 | 100% | Finished | 6000 | 6000 | 100 | 100 | 100 | 100 | 102.0167 | 100
62 | Restklasse | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  |  | 45763 |  |  | 45763 |  | 5d | [5 empty] | 45763 |  | 100% |  | 45763 | 45763
52 | Rest | 2017-05-03 08:00 | 2017-05-09 17:00 | 5d |  | 0 | 45763 | 0 | 0 | 45763 | 2017-06-06 08:00 | 5d | 45763 | 0 | 0 | 0 | 0 | 45763 | 0 | 100% | Finished | 45763 | 45763 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-08 08:00 | 2016-05-10 08:00 | 65089 | 47225 | 49705 | 2016-04-26 17:00 | -17864 | 72.55% | -2480 | 95.01% | -9d | 80% | 100% | 2017-05-30 16:00 | 2017-10-18 15:00 | 2017-11-17 16:00 | 2017-05-26 11:00 | 2017-10-18 15:00 | 2017-11-15 12:00 | 2017-05-22 17:00 | 2017-08-24 12:00 | 2017-09-19 10:00 | 370432 | 387274.8366 | 491754.7555 | 450613.75 | 514968.803 | 471667.2958 | 404023.7163 | 398289.2882 | 0.8 | 0.95011 | 0.72555 | 1 | -9 | 0.95011 | 1 | 0.8 | 1
Tracking Period 2 | 2016-05-10 08:00 | 2016-10-12 08:00 | 178889 | 140238 | 134473 | 2016-09-28 17:00 | -38651 | 78.39% | 5765 | 104.3% | -9d | 94.23% | 100% | 2017-06-23 09:00 | 2017-09-05 11:00 | 2017-08-14 10:00 | 2017-06-26 15:00 | 2017-09-05 11:00 | 2017-08-22 15:00 | 2017-05-22 17:00 | 2017-06-05 15:00 | 2017-05-25 15:00 | 362187 | 352825.9765 | 424947.2634 | 376128.6735 | 413006.2479 | 366194.5261 | 364235.4294 | 357119.9155 | 0.94231 | 1.0429 | 0.78394 | 1 | -9 | 1.0429 | 1 | 0.94231 | 1
Tracking Period 3 | 2016-10-12 08:00 | 2016-12-29 08:00 | 218500 | 185277 | 181871 | 2016-12-07 17:00 | -33223 | 84.79% | 3406 | 101.9% | -15d | 92.92% | 100% | 2017-06-16 14:00 | 2017-07-25 16:00 | 2017-07-17 10:00 | 2017-06-23 10:00 | 2017-07-25 16:00 | 2017-07-21 09:00 | 2017-05-30 17:00 | 2017-06-12 10:00 | 2017-06-08 09:00 | 364546 | 361187.8333 | 397302.4216 | 378455.264 | 393342.0843 | 374841.3993 | 367408.4761 | 364394.3041 | 0.92925 | 1.0187 | 0.84795 | 1 | -15 | 1.0187 | 1 | 0.92925 | 1
Tracking Period 4 | 2016-12-29 08:00 | 2017-05-23 08:00 | 367952 | 313304 | 324716 | 2017-04-18 17:00 | -54648 | 85.15% | -11412 | 96.49% | -24d | 92.38% | 100% | 2017-07-12 12:00 | 2017-07-24 11:00 | 2017-08-10 12:00 | 2017-07-26 15:00 | 2017-08-07 17:00 | 2017-08-09 17:00 | 2017-06-12 17:00 | 2017-06-14 10:00 | 2017-06-14 16:00 | 379364 | 381354.5363 | 388895.9686 | 383871.0515 | 391233.7039 | 386025.7558 | 382717.6262 | 381840.5635 | 0.92381 | 0.96486 | 0.85148 | 1 | -24 | 0.96486 | 1 | 0.92381 | 1
Tracking Period 5 | 2017-05-23 08:00 | 2017-06-12 17:00 | 367952 | 367952 | 379300 | 2017-05-09 17:00 | 0 | 100% | -11348 | 97.01% | -24d | 92.73% | 100% | 2017-05-09 17:00 | 2017-05-09 17:00 | 2017-05-23 11:00 | 2017-06-12 17:00 | 2017-06-12 17:00 | 2017-06-12 17:00 | 2017-06-12 17:00 | 2017-06-12 17:00 | 2017-06-12 17:00 | 379300 | 379300 | 379300 | 379300 | 379300 | 379300 | 379300 | 379300 | 0.92727 | 0.97008 | 1 | 1 | -24 | 0.97008 | 1 | 0.92727 | 1