## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House Finishing Works (6) | 1 |  |  | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 54324.22 |  |  | 54324.22 | 140.375
27 | Start uitv afwerking | 1.1 |  |  | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8318.5699 |  |  | 8318.5699 | 48.375
1 | F1 ventilatie | 1.1.1 |  | FS2 | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 6.375
2 | F1 san/cv | 1.1.2 | 1FS | FS3 | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 6.375
3 | F1 elektr | 1.1.3 | 2FS | FS4;FS5 | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 841.7 | 0 | 0 | 841.7 | 6.375
4 | Aansluiting water | 1.1.4 | 3FS |  | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 6.375
5 | Dakisolatie | 1.1.5 | 3FS | FS6 | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 13.375
6 | F1 pleister | 1.1.6 | 5FS | FS7;FS25 | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 13.375
28 | Fase 2 | 1.2 |  |  | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13098.23 |  |  | 13098.23 | 28.375
7 | Opm keuken | 1.2.1 | 6FS | FS8;FS9 | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 6.375
25 | F2 san/cv | 1.2.2 | 6FS | FS8;FS9 | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 6.375
8 | F2 ventilatie | 1.2.3 | 7FS;25FS |  | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 6.375
9 | Vloerisolatie | 1.2.4 | 7FS;25FS | FS10 | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3186.51 | 0 | 0 | 3186.51 | 6.375
10 | Chape | 1.2.5 | 9FS | FS11;FS12 | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1951.26 | 0 | 0 | 1951.26 | 6.375
11 | Opm Binnenschr | 1.2.6 | 10FS |  | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 6.375
12 | F2 elektr | 1.2.7 | 10FS | FS13 | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1262.55 | 0 | 0 | 1262.55 | 6.375
13 | openen E/G/W | 1.2.8 | 12FS | FS14 | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 0.375
29 | Fase 3 | 1.3 |  |  | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 14147.79 |  |  | 14147.79 | 32.375
14 | F3 san/cv | 1.3.1 | 13FS | FS15 | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 4.375
15 | Vloerwerken | 1.3.2 | 14FS | FS16 | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2124.3401 | 0 | 0 | 2124.3401 | 4.375
16 | Trappen | 1.3.3 | 15FS | FS17 | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 4.375
17 | Binnenschrijnwerk | 1.3.4 | 16FS | FS18 | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 4.375
18 | Keuken | 1.3.5 | 17FS | FS19;FS20 | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 4.375
30 | Finale afwerking | 1.4 |  |  | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 18759.6301 |  |  | 18759.6301 | 25.375
19 | Afw ventilatie | 1.4.1 | 18FS | FS21;FS24;FS26 | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 11.375
20 | Afw elektr | 1.4.2 | 18FS | FS21;FS24 | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2104.24 | 0 | 0 | 2104.24 | 11.375
21 | Afw san/cv | 1.4.3 | 19FS;20FS |  | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 11.375
26 | Afw vloer | 1.4.4 | 19FS |  | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5310.8501 | 0 | 0 | 5310.8501 | 11.375
24 | Afw pleister | 1.4.5 | 19FS;20FS |  | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 2970.54 | 0 | 0 | 2970.54 | 11.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House Finishing Works (6) | 808h |  |  |  |  | 99 | 100 | 101
27 | Start uitv afwerking | 280h |  |  |  |  | 99 | 100 | 101
1 | F1 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
2 | F1 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | F1 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
4 | Aansluiting water | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Dakisolatie | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
6 | F1 pleister | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
28 | Fase 2 | 168h |  |  |  |  | 99 | 100 | 101
7 | Opm keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | F2 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | F2 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
9 | Vloerisolatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
10 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Opm Binnenschr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | F2 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
13 | openen E/G/W | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | Fase 3 | 200h |  |  |  |  | 99 | 100 | 101
14 | F3 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Vloerwerken | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
16 | Trappen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Binnenschrijnwerk | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | Keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Finale afwerking | 160h |  |  |  |  | 99 | 100 | 101
19 | Afw ventilatie | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Afw elektr | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | Afw san/cv | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Afw vloer | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | Afw pleister | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Project Control - TP1
| TP Status Date | 2016-04-29 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (6) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 54324.22 |  |  | 54324.22 |  | 35d | [5 empty] | 8570.5699 |  | 15.31% |  | 8318.5699 | 8318.5699
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8318.5699 |  |  | 8318.5699 |  | 35d | [5 empty] | 8570.5699 |  | 100% |  | 8318.5699 | 8318.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 99.1463 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 841.7 | 0 | 0 | 841.7 | 2016-03-25 08:00 | 5d | 841.7 | 0 | 0 | 228 | 0 | 1069.7 | 0 | 100% | Finished | 841.7 | 841.7 | 100 | 100 | 100 | 100 | 127.088 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 99.2708 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-01 08:00 | 10d | 2227.9099 | 0 | 0 | -281 | 0 | 1946.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 87.3873 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-15 08:00 | 10d | 2227.9099 | 0 | 0 | 345 | 0 | 2572.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 115.4854 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13098.23 |  |  | 13098.23 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 |  | 0 | 0 | 2231.25 | 5d | 0 | 0 | 0 | 2231.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 |  | 0 | 0 | 1932.83 | 5d | 0 | 0 | 0 | 1932.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 |  | 0 | 0 | 1158.75 | 5d | 0 | 0 | 0 | 1158.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3186.51 | 0 | 0 | 3186.51 |  | 0 | 0 | 3186.51 | 5d | 0 | 0 | 0 | 3186.51 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1951.26 | 0 | 0 | 1951.26 |  | 0 | 0 | 1951.26 | 5d | 0 | 0 | 0 | 1951.26 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 |  | 0 | 0 | 1056.33 | 5d | 0 | 0 | 0 | 1056.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1262.55 | 0 | 0 | 1262.55 |  | 0 | 0 | 1262.55 | 5d | 0 | 0 | 0 | 1262.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 |  | 0 | 0 | 318.75 | 1d | 0 | 0 | 0 | 318.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 14147.79 |  |  | 14147.79 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2124.3401 | 0 | 0 | 2124.3401 |  | 0 | 0 | 2124.3401 | 5d | 0 | 0 | 0 | 2124.3401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 |  | 0 | 0 | 3392.5801 | 5d | 0 | 0 | 0 | 3392.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 |  | 0 | 0 | 1584.49 | 5d | 0 | 0 | 0 | 1584.49 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 18759.6301 |  |  | 18759.6301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 10d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2104.24 | 0 | 0 | 2104.24 |  | 0 | 0 | 2104.24 | 10d | 0 | 0 | 0 | 2104.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 10d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5310.8501 | 0 | 0 | 5310.8501 |  | 0 | 0 | 5310.8501 | 10d | 0 | 0 | 0 | 5310.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 2970.54 | 0 | 0 | 2970.54 |  | 0 | 0 | 2970.54 | 10d | 0 | 0 | 0 | 2970.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-05-30 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (6) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 54324.22 |  |  | 54324.22 |  | 56d | [5 empty] | 20452.7999 |  | 39.42% |  | 21416.7999 | 21416.7999
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8318.5699 |  |  | 8318.5699 |  | 35d | [5 empty] | 8570.5699 |  | 100% |  | 8318.5699 | 8318.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 99.1463 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 841.7 | 0 | 0 | 841.7 | 2016-03-25 08:00 | 5d | 841.7 | 0 | 0 | 228 | 0 | 1069.7 | 0 | 100% | Finished | 841.7 | 841.7 | 100 | 100 | 100 | 100 | 127.088 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 99.2708 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-01 08:00 | 10d | 2227.9099 | 0 | 0 | -281 | 0 | 1946.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 87.3873 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-15 08:00 | 10d | 2227.9099 | 0 | 0 | 345 | 0 | 2572.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 115.4854 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13098.23 |  |  | 13098.23 |  | 21d | [5 empty] | 11882.23 |  | 100% |  | 13098.23 | 13098.23
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 133.7479 | 100
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 99.1205 | 100
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3186.51 | 0 | 0 | 3186.51 | 2016-05-06 08:00 | 5d | 3186.51 | 0 | 0 | -2156 | 0 | 1030.51 | 0 | 100% | Finished | 3186.51 | 3186.51 | 100 | 100 | 100 | 100 | 32.3398 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1951.26 | 0 | 0 | 1951.26 | 2016-05-13 08:00 | 5d | 1951.26 | 0 | 0 | -287 | 0 | 1664.26 | 0 | 100% | Finished | 1951.26 | 1951.26 | 100 | 100 | 100 | 100 | 85.2916 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-20 08:00 | 5d | 1056.33 | 0 | 0 | 184 | 0 | 1240.33 | 0 | 100% | Finished | 1056.33 | 1056.33 | 100 | 100 | 100 | 100 | 117.4188 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1262.55 | 0 | 0 | 1262.55 | 2016-05-20 08:00 | 5d | 1262.55 | 0 | 0 | 342 | 0 | 1604.55 | 0 | 100% | Finished | 1262.55 | 1262.55 | 100 | 100 | 100 | 100 | 127.088 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 99.3725 | 100
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 14147.79 |  |  | 14147.79 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2124.3401 | 0 | 0 | 2124.3401 |  | 0 | 0 | 2124.3401 | 5d | 0 | 0 | 0 | 2124.3401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 |  | 0 | 0 | 3392.5801 | 5d | 0 | 0 | 0 | 3392.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 |  | 0 | 0 | 1584.49 | 5d | 0 | 0 | 0 | 1584.49 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 18759.6301 |  |  | 18759.6301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 10d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2104.24 | 0 | 0 | 2104.24 |  | 0 | 0 | 2104.24 | 10d | 0 | 0 | 0 | 2104.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 10d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5310.8501 | 0 | 0 | 5310.8501 |  | 0 | 0 | 5310.8501 | 10d | 0 | 0 | 0 | 5310.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 2970.54 | 0 | 0 | 2970.54 |  | 0 | 0 | 2970.54 | 10d | 0 | 0 | 0 | 2970.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-04 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (6) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 54324.22 |  |  | 54324.22 |  | 81d | [5 empty] | 36327.5899 |  | 65.47% |  | 35564.5899 | 35564.5899
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8318.5699 |  |  | 8318.5699 |  | 35d | [5 empty] | 8570.5699 |  | 100% |  | 8318.5699 | 8318.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 99.1463 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 841.7 | 0 | 0 | 841.7 | 2016-03-25 08:00 | 5d | 841.7 | 0 | 0 | 228 | 0 | 1069.7 | 0 | 100% | Finished | 841.7 | 841.7 | 100 | 100 | 100 | 100 | 127.088 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 99.2708 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-01 08:00 | 10d | 2227.9099 | 0 | 0 | -281 | 0 | 1946.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 87.3873 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-15 08:00 | 10d | 2227.9099 | 0 | 0 | 345 | 0 | 2572.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 115.4854 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13098.23 |  |  | 13098.23 |  | 21d | [5 empty] | 11882.23 |  | 100% |  | 13098.23 | 13098.23
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 133.7479 | 100
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 99.1205 | 100
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3186.51 | 0 | 0 | 3186.51 | 2016-05-06 08:00 | 5d | 3186.51 | 0 | 0 | -2156 | 0 | 1030.51 | 0 | 100% | Finished | 3186.51 | 3186.51 | 100 | 100 | 100 | 100 | 32.3398 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1951.26 | 0 | 0 | 1951.26 | 2016-05-13 08:00 | 5d | 1951.26 | 0 | 0 | -287 | 0 | 1664.26 | 0 | 100% | Finished | 1951.26 | 1951.26 | 100 | 100 | 100 | 100 | 85.2916 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-20 08:00 | 5d | 1056.33 | 0 | 0 | 184 | 0 | 1240.33 | 0 | 100% | Finished | 1056.33 | 1056.33 | 100 | 100 | 100 | 100 | 117.4188 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1262.55 | 0 | 0 | 1262.55 | 2016-05-20 08:00 | 5d | 1262.55 | 0 | 0 | 342 | 0 | 1604.55 | 0 | 100% | Finished | 1262.55 | 1262.55 | 100 | 100 | 100 | 100 | 127.088 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 99.3725 | 100
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 14147.79 |  |  | 14147.79 |  | 25d | [5 empty] | 15874.79 |  | 100% |  | 14147.79 | 14147.79
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 99.1308 | 100
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2124.3401 | 0 | 0 | 2124.3401 | 2016-06-06 08:00 | 5d | 2124.3401 | 0 | 0 | -403 | 0 | 1721.3401 | 0 | 100% | Finished | 2124.3401 | 2124.3401 | 100 | 100 | 100 | 100 | 81.0294 | 100
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 2016-06-13 08:00 | 5d | 3392.5801 | 0 | 0 | 592 | 0 | 3984.5801 | 0 | 100% | Finished | 3392.5801 | 3392.5801 | 100 | 100 | 100 | 100 | 117.4498 | 100
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 2016-06-20 08:00 | 5d | 1584.49 | 0 | 0 | 276 | 0 | 1860.49 | 0 | 100% | Finished | 1584.49 | 1584.49 | 100 | 100 | 100 | 100 | 117.4189 | 100
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 133.7255 | 100
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 18759.6301 |  |  | 18759.6301 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 10d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2104.24 | 0 | 0 | 2104.24 |  | 0 | 0 | 2104.24 | 10d | 0 | 0 | 0 | 2104.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 10d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5310.8501 | 0 | 0 | 5310.8501 |  | 0 | 0 | 5310.8501 | 10d | 0 | 0 | 0 | 5310.8501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 2970.54 | 0 | 0 | 2970.54 |  | 0 | 0 | 2970.54 | 10d | 0 | 0 | 0 | 2970.54 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-07-29 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (6) | 2016-03-11 08:00 | 2016-07-29 17:00 | 101d |  |  | 54324.22 |  |  | 54324.22 |  | 101d | [5 empty] | 54996.22 |  | 100% |  | 54324.22 | 54324.22
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-28 17:00 | 35d |  |  | 8318.5699 |  |  | 8318.5699 |  | 35d | [5 empty] | 8570.5699 |  | 100% |  | 8318.5699 | 8318.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | -11 | 0 | 1277.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 99.1463 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 841.7 | 0 | 0 | 841.7 | 2016-03-25 08:00 | 5d | 841.7 | 0 | 0 | 228 | 0 | 1069.7 | 0 | 100% | Finished | 841.7 | 841.7 | 100 | 100 | 100 | 100 | 127.088 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | -7 | 0 | 953 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 99.2708 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-01 08:00 | 10d | 2227.9099 | 0 | 0 | -281 | 0 | 1946.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 87.3873 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-28 17:00 | 10d |  | 0 | 2227.9099 | 0 | 0 | 2227.9099 | 2016-04-15 08:00 | 10d | 2227.9099 | 0 | 0 | 345 | 0 | 2572.9099 | 0 | 100% | Finished | 2227.9099 | 2227.9099 | 100 | 100 | 100 | 100 | 115.4854 | 100
28 | Fase 2 | 2016-04-29 08:00 | 2016-05-27 17:00 | 21d |  |  | 13098.23 |  |  | 13098.23 |  | 21d | [5 empty] | 11882.23 |  | 100% |  | 13098.23 | 13098.23
7 | Opm keuken | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-29 08:00 | 5d | 2231.25 | 0 | 0 | 753 | 0 | 2984.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 133.7479 | 100
25 | F2 san/cv | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-29 08:00 | 5d | 1932.83 | 0 | 0 | -17 | 0 | 1915.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 99.1205 | 100
8 | F2 ventilatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-05-06 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 3186.51 | 0 | 0 | 3186.51 | 2016-05-06 08:00 | 5d | 3186.51 | 0 | 0 | -2156 | 0 | 1030.51 | 0 | 100% | Finished | 3186.51 | 3186.51 | 100 | 100 | 100 | 100 | 32.3398 | 100
10 | Chape | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1951.26 | 0 | 0 | 1951.26 | 2016-05-13 08:00 | 5d | 1951.26 | 0 | 0 | -287 | 0 | 1664.26 | 0 | 100% | Finished | 1951.26 | 1951.26 | 100 | 100 | 100 | 100 | 85.2916 | 100
11 | Opm Binnenschr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-20 08:00 | 5d | 1056.33 | 0 | 0 | 184 | 0 | 1240.33 | 0 | 100% | Finished | 1056.33 | 1056.33 | 100 | 100 | 100 | 100 | 117.4188 | 100
12 | F2 elektr | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 1262.55 | 0 | 0 | 1262.55 | 2016-05-20 08:00 | 5d | 1262.55 | 0 | 0 | 342 | 0 | 1604.55 | 0 | 100% | Finished | 1262.55 | 1262.55 | 100 | 100 | 100 | 100 | 127.088 | 100
13 | openen E/G/W | 2016-05-27 08:00 | 2016-05-27 17:00 | 1d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-27 08:00 | 1d | 318.75 | 0 | 0 | -2 | 0 | 316.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 99.3725 | 100
29 | Fase 3 | 2016-05-30 08:00 | 2016-07-01 17:00 | 25d |  |  | 14147.79 |  |  | 14147.79 |  | 25d | [5 empty] | 15874.79 |  | 100% |  | 14147.79 | 14147.79
14 | F3 san/cv | 2016-05-30 08:00 | 2016-06-03 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-30 08:00 | 5d | 3221.3799 | 0 | 0 | -28 | 0 | 3193.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 99.1308 | 100
15 | Vloerwerken | 2016-06-06 08:00 | 2016-06-10 17:00 | 5d |  | 0 | 2124.3401 | 0 | 0 | 2124.3401 | 2016-06-06 08:00 | 5d | 2124.3401 | 0 | 0 | -403 | 0 | 1721.3401 | 0 | 100% | Finished | 2124.3401 | 2124.3401 | 100 | 100 | 100 | 100 | 81.0294 | 100
16 | Trappen | 2016-06-13 08:00 | 2016-06-17 17:00 | 5d |  | 0 | 3392.5801 | 0 | 0 | 3392.5801 | 2016-06-13 08:00 | 5d | 3392.5801 | 0 | 0 | 592 | 0 | 3984.5801 | 0 | 100% | Finished | 3392.5801 | 3392.5801 | 100 | 100 | 100 | 100 | 117.4498 | 100
17 | Binnenschrijnwerk | 2016-06-20 08:00 | 2016-06-24 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 2016-06-20 08:00 | 5d | 1584.49 | 0 | 0 | 276 | 0 | 1860.49 | 0 | 100% | Finished | 1584.49 | 1584.49 | 100 | 100 | 100 | 100 | 117.4189 | 100
18 | Keuken | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-27 08:00 | 5d | 3825 | 0 | 0 | 1290 | 0 | 5115 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 133.7255 | 100
30 | Finale afwerking | 2016-07-04 08:00 | 2016-07-29 17:00 | 20d |  |  | 18759.6301 |  |  | 18759.6301 |  | 20d | [5 empty] | 18668.6301 |  | 100% |  | 18759.6301 | 18759.6301
19 | Afw ventilatie | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-04 08:00 | 10d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 100% | Finished | 1931.25 | 1931.25 | 100 | 100 | 100 | 100 | 97.1003 | 100
20 | Afw elektr | 2016-07-04 08:00 | 2016-07-15 17:00 | 10d |  | 0 | 2104.24 | 0 | 0 | 2104.24 | 2016-07-04 08:00 | 10d | 2104.24 | 0 | 0 | 570 | 0 | 2674.24 | 0 | 100% | Finished | 2104.24 | 2104.24 | 100 | 100 | 100 | 100 | 127.0882 | 100
21 | Afw san/cv | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-18 08:00 | 10d | 6442.75 | 0 | 0 | -57 | 0 | 6385.75 | 0 | 100% | Finished | 6442.75 | 6442.75 | 100 | 100 | 100 | 100 | 99.1153 | 100
26 | Afw vloer | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 5310.8501 | 0 | 0 | 5310.8501 | 2016-07-18 08:00 | 10d | 5310.8501 | 0 | 0 | -1008 | 0 | 4302.8501 | 0 | 100% | Finished | 5310.8501 | 5310.8501 | 100 | 100 | 100 | 100 | 81.02 | 100
24 | Afw pleister | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 2970.54 | 0 | 0 | 2970.54 | 2016-07-18 08:00 | 10d | 2970.54 | 0 | 0 | 460 | 0 | 3430.54 | 0 | 100% | Finished | 2970.54 | 2970.54 | 100 | 100 | 100 | 100 | 115.4854 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-11 08:00 | 2016-04-29 08:00 | 8318.5699 | 8318.5699 | 8570.5699 | 2016-04-28 17:00 | 0 | 100% | -252 | 97.06% | 0 | 100% | 100% | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-08-03 17:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-08-02 17:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-08-02 17:00 | 54576.22 | 55969.9 | 54576.22 | 54576.22 | 55969.9 | 55969.9 | 55684.4495 | 55684.4495 | 1 | 0.9706 | 1 | 1 | 0 | 0.9706 | 1 | 1 | 1
Tracking Period 2 | 2016-04-29 08:00 | 2016-05-30 08:00 | 21416.7999 | 21416.7999 | 20452.7999 | 2016-05-27 17:00 | 0 | 100% | 964 | 104.7% | 0 | 100% | 100% | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-07-25 12:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-07-27 17:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-07-27 17:00 | 53360.22 | 51879.0112 | 53360.22 | 53360.22 | 51879.0112 | 51879.0112 | 52164.4887 | 52164.4887 | 1 | 1.0471 | 1 | 1 | 0 | 1.0471 | 1 | 1 | 1
Tracking Period 3 | 2016-05-30 08:00 | 2016-07-04 08:00 | 35564.5899 | 35564.5899 | 36327.5899 | 2016-07-01 17:00 | 0 | 100% | -763 | 97.9% | 0 | 100% | 100% | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-08-03 09:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-08-01 11:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-08-01 11:00 | 55087.22 | 55489.6877 | 55087.22 | 55087.22 | 55489.6877 | 55489.6877 | 55407.8186 | 55407.8186 | 1 | 0.979 | 1 | 1 | 0 | 0.979 | 1 | 1 | 1
Tracking Period 4 | 2016-07-04 08:00 | 2016-07-29 17:00 | 54324.22 | 54324.22 | 54996.22 | 2016-07-29 17:00 | 0 | 100% | -672 | 98.78% | 0 | 100% | 100% | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-08-02 10:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 2016-07-29 17:00 | 54996.22 | 54996.22 | 54996.22 | 54996.22 | 54996.22 | 54996.22 | 54996.22 | 54996.22 | 1 | 0.98778 | 1 | 1 | 0 | 0.98778 | 1 | 1 | 1