## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building Finishing Works (1) | 1 |  |  | 2016-03-21 08:00 | 2016-08-12 17:00 | 105d |  |  | 488936 |  |  | 488936 | 144.375
24 | gelijkvloers blok A | 1.1 |  |  | 2016-03-21 08:00 | 2016-07-08 17:00 | 80d |  |  | 263062 |  |  | 263062 | 109.375
1 | pleisterwerken wanden 0A | 1.1.1 |  | SS2;FS13 | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 20070 | 0 | 0 | 20070 | 18.375
2 | pleisterwerken plafonds 0A | 1.1.2 | 1SS | FS3-1w | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 25805 | 0 | 0 | 25805 | 4.375
3 | lichte scheidingswanden 0A | 1.1.3 | 2FS-1w | FS4 | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 6594 | 0 | 0 | 6594 | 11.375
4 | gespoten PU isolatie en uitvullingen 0A | 1.1.4 | 3FS | FS5 | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 10035 | 0 | 0 | 10035 | 2.375
5 | chape 0A | 1.1.5 | 4FS | FS6+2w;FS8+1w;FS9+6w | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 4300 | 0 | 0 | 4300 | 6.375
6 | plaatsen keramische tegels 0A | 1.1.6 | 5FS+2w | FS7-1w | 2016-04-28 08:00 | 2016-05-11 17:00 | 10d |  | 0 | 37273 | 0 | 0 | 37273 | 13.375
7 | plaatsen faience 0A | 1.1.7 | 6FS-1w |  | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 15626 | 0 | 0 | 15626 | 13.375
8 | verlaagde plafonds 0A | 1.1.8 | 5FS+1w |  | 2016-04-21 08:00 | 2016-05-18 17:00 | 20d |  | 0 | 14336 | 0 | 0 | 14336 | 27.375
9 | zachte vloerbekleding 0A | 1.1.9 | 5FS+6w | FS10;FS11;FS12 | 2016-05-26 08:00 | 2016-06-10 17:00 | 12d |  | 0 | 11468 | 0 | 0 | 11468 | 15.375
10 | binnenschrijnwerk 0A | 1.1.10 | 9FS |  | 2016-06-13 08:00 | 2016-06-22 17:00 | 8d |  | 0 | 40141 | 0 | 0 | 40141 | 9.375
11 | schilderwerken wanden en plafonds 0A | 1.1.11 | 9FS |  | 2016-06-13 08:00 | 2016-07-08 17:00 | 20d |  | 0 | 34406 | 0 | 0 | 34406 | 25.375
12 | binnenmeubilair 0A | 1.1.12 | 9FS |  | 2016-06-13 08:00 | 2016-06-24 17:00 | 10d |  | 0 | 43008 | 0 | 0 | 43008 | 11.375
25 | nivo +1 blok A | 1.2 |  |  | 2016-04-11 08:00 | 2016-08-12 17:00 | 90d |  |  | 225874 |  |  | 225874 | 123.375
13 | pleisterwerken wanden 1A | 1.2.1 | 1FS | SS14 | 2016-04-11 08:00 | 2016-04-22 17:00 | 10d |  | 0 | 18547 | 0 | 0 | 18547 | 11.375
14 | pleisterwerken plafonds 1A | 1.2.2 | 13SS | FS15-1w | 2016-04-11 08:00 | 2016-04-29 17:00 | 15d |  | 0 | 23846 | 0 | 0 | 23846 | 18.375
15 | lichte scheidingswanden 1A | 1.2.3 | 14FS-1w | FS16 | 2016-04-25 08:00 | 2016-05-06 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 11.375
16 | vloer uitvullingen 1A | 1.2.4 | 15FS | FS17 | 2016-05-09 08:00 | 2016-05-11 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2.375
17 | chape 1A | 1.2.5 | 16FS | FS18+2w;FS20+6w | 2016-05-12 08:00 | 2016-05-18 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 6.375
18 | plaatsen keramische tegels 1A | 1.2.6 | 17FS+2w | FS19-1w | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 13.375
19 | plaatsen faience 1A | 1.2.7 | 18FS-1w |  | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 13.375
20 | zachte vloerbekleding 1A | 1.2.8 | 17FS+6w | FS21;FS22;FS23 | 2016-06-30 08:00 | 2016-07-15 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 15.375
21 | binnenschrijnwerk 1A | 1.2.9 | 20FS |  | 2016-07-18 08:00 | 2016-07-27 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 | 9.375
22 | schilderwerken wanden en plafonds 1A | 1.2.10 | 20FS |  | 2016-07-18 08:00 | 2016-08-12 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 | 25.375
23 | binnenmeubilair 1A | 1.2.11 | 20FS |  | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 31795 | 0 | 0 | 31795 | 11.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building Finishing Works (1) | 840h |  |  |  |  | 99 | 100 | 101
24 | gelijkvloers blok A | 640h |  |  |  |  | 99 | 100 | 101
1 | pleisterwerken wanden 0A | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | pleisterwerken plafonds 0A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | lichte scheidingswanden 0A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | gespoten PU isolatie en uitvullingen 0A | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
5 | chape 0A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | plaatsen keramische tegels 0A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | plaatsen faience 0A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | verlaagde plafonds 0A | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | zachte vloerbekleding 0A | 96h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
10 | binnenschrijnwerk 0A | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | schilderwerken wanden en plafonds 0A | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | binnenmeubilair 0A | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
25 | nivo +1 blok A | 720h |  |  |  |  | 99 | 100 | 101
13 | pleisterwerken wanden 1A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | pleisterwerken plafonds 1A | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | lichte scheidingswanden 1A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | vloer uitvullingen 1A | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
17 | chape 1A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | plaatsen keramische tegels 1A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | plaatsen faience 1A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | zachte vloerbekleding 1A | 96h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | binnenschrijnwerk 1A | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | schilderwerken wanden en plafonds 1A | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
23 | binnenmeubilair 1A | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120

## Project Control - TP1
| TP Status Date | 2016-04-13 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (1) | 2016-03-21 08:00 | 2016-08-12 17:00 | 105d |  |  | 488936 |  |  | 488936 |  | 17d | [5 empty] | 68380 |  | 12.78% |  | 62504 | 109197
24 | gelijkvloers blok A | 2016-03-21 08:00 | 2016-07-08 17:00 | 80d |  |  | 263062 |  |  | 263062 |  | 17d | [5 empty] | 68380 |  | 23.76% |  | 62504 | 66804
1 | pleisterwerken wanden 0A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 20070 | 0 | 0 | 20070 | 2016-03-21 08:00 | 17d | 20070 | 0 | 0 | -351 | 0 | 19719 | 0 | 100% | Finished | 20070 | 20070 | 100 | 113.3333 | 100 | 100 | 98.2511 | 100
2 | pleisterwerken plafonds 0A | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 25805 | 0 | 0 | 25805 | 2016-03-21 08:00 | 7d | 25805 | 0 | 0 | 4770 | 0 | 30575 | 0 | 100% | Finished | 25805 | 25805 | 100 | 140 | 100 | 100 | 118.4848 | 100
3 | lichte scheidingswanden 0A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 6594 | 0 | 0 | 6594 | 2016-03-23 08:00 | 10d | 6594 | 0 | 0 | -632 | 0 | 5962 | 0 | 100% | Finished | 6594 | 6594 | 100 | 100 | 100 | 100 | 90.4155 | 100
4 | gespoten PU isolatie en uitvullingen 0A | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 10035 | 0 | 0 | 10035 | 2016-04-06 08:00 | 5d | 10035 | 0 | 0 | 2089 | 0 | 12124 | 0 | 100% | Finished | 10035 | 10035 | 100 | 166.6667 | 100 | 100 | 120.8171 | 100
5 | chape 0A | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 4300 | 0 | 0 | 4300 |  | 0 | 0 | 4300 | 5d | 0 | 0 | 0 | 4300 | 0% | Not Started | 0 | 4300 | 100 |  | 0 | 100 |  | 0
6 | plaatsen keramische tegels 0A | 2016-04-28 08:00 | 2016-05-11 17:00 | 10d |  | 0 | 37273 | 0 | 0 | 37273 |  | 0 | 0 | 37273 | 10d | 0 | 0 | 0 | 37273 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | plaatsen faience 0A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 15626 | 0 | 0 | 15626 |  | 0 | 0 | 15626 | 10d | 0 | 0 | 0 | 15626 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | verlaagde plafonds 0A | 2016-04-21 08:00 | 2016-05-18 17:00 | 20d |  | 0 | 14336 | 0 | 0 | 14336 |  | 0 | 0 | 14336 | 20d | 0 | 0 | 0 | 14336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | zachte vloerbekleding 0A | 2016-05-26 08:00 | 2016-06-10 17:00 | 12d |  | 0 | 11468 | 0 | 0 | 11468 |  | 0 | 0 | 11468 | 12d | 0 | 0 | 0 | 11468 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | binnenschrijnwerk 0A | 2016-06-13 08:00 | 2016-06-22 17:00 | 8d |  | 0 | 40141 | 0 | 0 | 40141 |  | 0 | 0 | 40141 | 8d | 0 | 0 | 0 | 40141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | schilderwerken wanden en plafonds 0A | 2016-06-13 08:00 | 2016-07-08 17:00 | 20d |  | 0 | 34406 | 0 | 0 | 34406 |  | 0 | 0 | 34406 | 20d | 0 | 0 | 0 | 34406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | binnenmeubilair 0A | 2016-06-13 08:00 | 2016-06-24 17:00 | 10d |  | 0 | 43008 | 0 | 0 | 43008 |  | 0 | 0 | 43008 | 10d | 0 | 0 | 0 | 43008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | nivo +1 blok A | 2016-04-11 08:00 | 2016-08-12 17:00 | 90d |  |  | 225874 |  |  | 225874 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 42393
13 | pleisterwerken wanden 1A | 2016-04-11 08:00 | 2016-04-22 17:00 | 10d |  | 0 | 18547 | 0 | 0 | 18547 |  | 0 | 0 | 18547 | 10d | 0 | 0 | 0 | 18547 | 0% | Not Started | 0 | 18547 | 100 |  | 0 | 100 |  | 0
14 | pleisterwerken plafonds 1A | 2016-04-11 08:00 | 2016-04-29 17:00 | 15d |  | 0 | 23846 | 0 | 0 | 23846 |  | 0 | 0 | 23846 | 15d | 0 | 0 | 0 | 23846 | 0% | Not Started | 0 | 23846 | 100 |  | 0 | 100 |  | 0
15 | lichte scheidingswanden 1A | 2016-04-25 08:00 | 2016-05-06 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 |  | 0 | 0 | 6094 | 10d | 0 | 0 | 0 | 6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | vloer uitvullingen 1A | 2016-05-09 08:00 | 2016-05-11 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 |  | 0 | 0 | 3974 | 3d | 0 | 0 | 0 | 3974 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | chape 1A | 2016-05-12 08:00 | 2016-05-18 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 |  | 0 | 0 | 34444 | 5d | 0 | 0 | 0 | 34444 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | plaatsen keramische tegels 1A | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 |  | 0 | 0 | 14440 | 10d | 0 | 0 | 0 | 14440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | plaatsen faience 1A | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 |  | 0 | 0 | 13247 | 10d | 0 | 0 | 0 | 13247 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | zachte vloerbekleding 1A | 2016-06-30 08:00 | 2016-07-15 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 |  | 0 | 0 | 10598 | 12d | 0 | 0 | 0 | 10598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnenschrijnwerk 1A | 2016-07-18 08:00 | 2016-07-27 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 |  | 0 | 0 | 37094 | 8d | 0 | 0 | 0 | 37094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | schilderwerken wanden en plafonds 1A | 2016-07-18 08:00 | 2016-08-12 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 20d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | binnenmeubilair 1A | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 10d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-06-01 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (1) | 2016-03-21 08:00 | 2016-08-12 17:00 | 105d |  |  | 488936 |  |  | 488936 |  | 52d | [5 empty] | 226645 |  | 45.19% |  | 220944 | 232412
24 | gelijkvloers blok A | 2016-03-21 08:00 | 2016-07-08 17:00 | 80d |  |  | 263062 |  |  | 263062 |  | 52d | [5 empty] | 137581 |  | 50.95% |  | 134039 | 145507
1 | pleisterwerken wanden 0A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 20070 | 0 | 0 | 20070 | 2016-03-21 08:00 | 17d | 20070 | 0 | 0 | -351 | 0 | 19719 | 0 | 100% | Finished | 20070 | 20070 | 100 | 113.3333 | 100 | 100 | 98.2511 | 100
2 | pleisterwerken plafonds 0A | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 25805 | 0 | 0 | 25805 | 2016-03-21 08:00 | 7d | 25805 | 0 | 0 | 4770 | 0 | 30575 | 0 | 100% | Finished | 25805 | 25805 | 100 | 140 | 100 | 100 | 118.4848 | 100
3 | lichte scheidingswanden 0A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 6594 | 0 | 0 | 6594 | 2016-03-23 08:00 | 10d | 6594 | 0 | 0 | -632 | 0 | 5962 | 0 | 100% | Finished | 6594 | 6594 | 100 | 100 | 100 | 100 | 90.4155 | 100
4 | gespoten PU isolatie en uitvullingen 0A | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 10035 | 0 | 0 | 10035 | 2016-04-06 08:00 | 5d | 10035 | 0 | 0 | 2089 | 0 | 12124 | 0 | 100% | Finished | 10035 | 10035 | 100 | 166.6667 | 100 | 100 | 120.8171 | 100
5 | chape 0A | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 4300 | 0 | 0 | 4300 | 2016-04-13 08:00 | 5d | 4300 | 0 | 0 | -48 | 0 | 4252 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 98.8837 | 100
6 | plaatsen keramische tegels 0A | 2016-04-28 08:00 | 2016-05-11 17:00 | 10d |  | 0 | 37273 | 0 | 0 | 37273 | 2016-05-04 08:00 | 10d | 37273 | 0 | 0 | -2668 | 0 | 34605 | 0 | 100% | Finished | 37273 | 37273 | 100 | 100 | 100 | 100 | 92.842 | 100
7 | plaatsen faience 0A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 15626 | 0 | 0 | 15626 | 2016-05-11 08:00 | 10d | 15626 | 0 | 0 | -874 | 0 | 14752 | 0 | 100% | Finished | 15626 | 15626 | 100 | 100 | 100 | 100 | 94.4068 | 100
8 | verlaagde plafonds 0A | 2016-04-21 08:00 | 2016-05-18 17:00 | 20d |  | 0 | 14336 | 0 | 0 | 14336 | 2016-04-27 08:00 | 20d | 14336 | 0 | 0 | 1256 | 0 | 15592 | 0 | 100% | Finished | 14336 | 14336 | 100 | 100 | 100 | 100 | 108.7612 | 100
9 | zachte vloerbekleding 0A | 2016-05-26 08:00 | 2016-06-10 17:00 | 12d |  | 0 | 11468 | 0 | 0 | 11468 |  | 0 | 0 | 11468 | 12d | 0 | 0 | 0 | 11468 | 0% | Not Started | 0 | 11468 | 100 |  | 0 | 100 |  | 0
10 | binnenschrijnwerk 0A | 2016-06-13 08:00 | 2016-06-22 17:00 | 8d |  | 0 | 40141 | 0 | 0 | 40141 |  | 0 | 0 | 40141 | 8d | 0 | 0 | 0 | 40141 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | schilderwerken wanden en plafonds 0A | 2016-06-13 08:00 | 2016-07-08 17:00 | 20d |  | 0 | 34406 | 0 | 0 | 34406 |  | 0 | 0 | 34406 | 20d | 0 | 0 | 0 | 34406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | binnenmeubilair 0A | 2016-06-13 08:00 | 2016-06-24 17:00 | 10d |  | 0 | 43008 | 0 | 0 | 43008 |  | 0 | 0 | 43008 | 10d | 0 | 0 | 0 | 43008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | nivo +1 blok A | 2016-04-11 08:00 | 2016-08-12 17:00 | 90d |  |  | 225874 |  |  | 225874 |  | 35d | [5 empty] | 89064 |  | 38.47% |  | 86905 | 86905
13 | pleisterwerken wanden 1A | 2016-04-11 08:00 | 2016-04-22 17:00 | 10d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-04-13 08:00 | 10d | 18547 | 0 | 0 | 405 | 0 | 18952 | 0 | 100% | Finished | 18547 | 18547 | 100 | 100 | 100 | 100 | 102.1836 | 100
14 | pleisterwerken plafonds 1A | 2016-04-11 08:00 | 2016-04-29 17:00 | 15d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-04-13 08:00 | 15d | 23846 | 0 | 0 | -1160 | 0 | 22686 | 0 | 100% | Finished | 23846 | 23846 | 100 | 100 | 100 | 100 | 95.1355 | 100
15 | lichte scheidingswanden 1A | 2016-04-25 08:00 | 2016-05-06 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-04-27 08:00 | 10d | 6094 | 0 | 0 | -349 | 0 | 5745 | 0 | 100% | Finished | 6094 | 6094 | 100 | 100 | 100 | 100 | 94.2731 | 100
16 | vloer uitvullingen 1A | 2016-05-09 08:00 | 2016-05-11 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-05-11 08:00 | 5d | 3974 | 0 | 0 | 1028 | 0 | 5002 | 0 | 100% | Finished | 3974 | 3974 | 100 | 166.6667 | 100 | 100 | 125.8681 | 100
17 | chape 1A | 2016-05-12 08:00 | 2016-05-18 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-05-18 08:00 | 5d | 34444 | 0 | 0 | 2235 | 0 | 36679 | 0 | 100% | Finished | 34444 | 34444 | 100 | 100 | 100 | 100 | 106.4888 | 100
18 | plaatsen keramische tegels 1A | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 |  | 0 | 0 | 14440 | 10d | 0 | 0 | 0 | 14440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | plaatsen faience 1A | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 |  | 0 | 0 | 13247 | 10d | 0 | 0 | 0 | 13247 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | zachte vloerbekleding 1A | 2016-06-30 08:00 | 2016-07-15 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 |  | 0 | 0 | 10598 | 12d | 0 | 0 | 0 | 10598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | binnenschrijnwerk 1A | 2016-07-18 08:00 | 2016-07-27 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 |  | 0 | 0 | 37094 | 8d | 0 | 0 | 0 | 37094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | schilderwerken wanden en plafonds 1A | 2016-07-18 08:00 | 2016-08-12 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 20d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | binnenmeubilair 1A | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 10d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-27 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (1) | 2016-03-21 08:00 | 2016-08-12 17:00 | 105d |  |  | 488936 |  |  | 488936 |  | 92d | [5 empty] | 393895 |  | 79.41% |  | 388252 | 488936
24 | gelijkvloers blok A | 2016-03-21 08:00 | 2016-07-08 17:00 | 80d |  |  | 263062 |  |  | 263062 |  | 92d | [5 empty] | 267887 |  | 100% |  | 263062 | 263062
1 | pleisterwerken wanden 0A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 20070 | 0 | 0 | 20070 | 2016-03-21 08:00 | 17d | 20070 | 0 | 0 | -351 | 0 | 19719 | 0 | 100% | Finished | 20070 | 20070 | 100 | 113.3333 | 100 | 100 | 98.2511 | 100
2 | pleisterwerken plafonds 0A | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 25805 | 0 | 0 | 25805 | 2016-03-21 08:00 | 7d | 25805 | 0 | 0 | 4770 | 0 | 30575 | 0 | 100% | Finished | 25805 | 25805 | 100 | 140 | 100 | 100 | 118.4848 | 100
3 | lichte scheidingswanden 0A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 6594 | 0 | 0 | 6594 | 2016-03-23 08:00 | 10d | 6594 | 0 | 0 | -632 | 0 | 5962 | 0 | 100% | Finished | 6594 | 6594 | 100 | 100 | 100 | 100 | 90.4155 | 100
4 | gespoten PU isolatie en uitvullingen 0A | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 10035 | 0 | 0 | 10035 | 2016-04-06 08:00 | 5d | 10035 | 0 | 0 | 2089 | 0 | 12124 | 0 | 100% | Finished | 10035 | 10035 | 100 | 166.6667 | 100 | 100 | 120.8171 | 100
5 | chape 0A | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 4300 | 0 | 0 | 4300 | 2016-04-13 08:00 | 5d | 4300 | 0 | 0 | -48 | 0 | 4252 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 98.8837 | 100
6 | plaatsen keramische tegels 0A | 2016-04-28 08:00 | 2016-05-11 17:00 | 10d |  | 0 | 37273 | 0 | 0 | 37273 | 2016-05-04 08:00 | 10d | 37273 | 0 | 0 | -2668 | 0 | 34605 | 0 | 100% | Finished | 37273 | 37273 | 100 | 100 | 100 | 100 | 92.842 | 100
7 | plaatsen faience 0A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 15626 | 0 | 0 | 15626 | 2016-05-11 08:00 | 10d | 15626 | 0 | 0 | -874 | 0 | 14752 | 0 | 100% | Finished | 15626 | 15626 | 100 | 100 | 100 | 100 | 94.4068 | 100
8 | verlaagde plafonds 0A | 2016-04-21 08:00 | 2016-05-18 17:00 | 20d |  | 0 | 14336 | 0 | 0 | 14336 | 2016-04-27 08:00 | 20d | 14336 | 0 | 0 | 1256 | 0 | 15592 | 0 | 100% | Finished | 14336 | 14336 | 100 | 100 | 100 | 100 | 108.7612 | 100
9 | zachte vloerbekleding 0A | 2016-05-26 08:00 | 2016-06-10 17:00 | 12d |  | 0 | 11468 | 0 | 0 | 11468 | 2016-06-01 08:00 | 15d | 11468 | 0 | 0 | 1334 | 0 | 12802 | 0 | 100% | Finished | 11468 | 11468 | 100 | 125 | 100 | 100 | 111.6324 | 100
10 | binnenschrijnwerk 0A | 2016-06-13 08:00 | 2016-06-22 17:00 | 8d |  | 0 | 40141 | 0 | 0 | 40141 | 2016-06-22 08:00 | 10d | 40141 | 0 | 0 | 449 | 0 | 40590 | 0 | 100% | Finished | 40141 | 40141 | 100 | 125 | 100 | 100 | 101.1186 | 100
11 | schilderwerken wanden en plafonds 0A | 2016-06-13 08:00 | 2016-07-08 17:00 | 20d |  | 0 | 34406 | 0 | 0 | 34406 | 2016-06-22 08:00 | 25d | 34406 | 0 | 0 | 2697 | 0 | 37103 | 0 | 100% | Finished | 34406 | 34406 | 100 | 125 | 100 | 100 | 107.8387 | 100
12 | binnenmeubilair 0A | 2016-06-13 08:00 | 2016-06-24 17:00 | 10d |  | 0 | 43008 | 0 | 0 | 43008 | 2016-06-22 08:00 | 10d | 43008 | 0 | 0 | -3197 | 0 | 39811 | 0 | 100% | Finished | 43008 | 43008 | 100 | 100 | 100 | 100 | 92.5665 | 100
25 | nivo +1 blok A | 2016-04-11 08:00 | 2016-08-12 17:00 | 90d |  |  | 225874 |  |  | 225874 |  | 75d | [5 empty] | 126008 |  | 55.42% |  | 125190 | 225874
13 | pleisterwerken wanden 1A | 2016-04-11 08:00 | 2016-04-22 17:00 | 10d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-04-13 08:00 | 10d | 18547 | 0 | 0 | 405 | 0 | 18952 | 0 | 100% | Finished | 18547 | 18547 | 100 | 100 | 100 | 100 | 102.1836 | 100
14 | pleisterwerken plafonds 1A | 2016-04-11 08:00 | 2016-04-29 17:00 | 15d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-04-13 08:00 | 15d | 23846 | 0 | 0 | -1160 | 0 | 22686 | 0 | 100% | Finished | 23846 | 23846 | 100 | 100 | 100 | 100 | 95.1355 | 100
15 | lichte scheidingswanden 1A | 2016-04-25 08:00 | 2016-05-06 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-04-27 08:00 | 10d | 6094 | 0 | 0 | -349 | 0 | 5745 | 0 | 100% | Finished | 6094 | 6094 | 100 | 100 | 100 | 100 | 94.2731 | 100
16 | vloer uitvullingen 1A | 2016-05-09 08:00 | 2016-05-11 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-05-11 08:00 | 5d | 3974 | 0 | 0 | 1028 | 0 | 5002 | 0 | 100% | Finished | 3974 | 3974 | 100 | 166.6667 | 100 | 100 | 125.8681 | 100
17 | chape 1A | 2016-05-12 08:00 | 2016-05-18 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-05-18 08:00 | 5d | 34444 | 0 | 0 | 2235 | 0 | 36679 | 0 | 100% | Finished | 34444 | 34444 | 100 | 100 | 100 | 100 | 106.4888 | 100
18 | plaatsen keramische tegels 1A | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 2016-06-08 08:00 | 10d | 14440 | 0 | 0 | -1302 | 0 | 13138 | 0 | 100% | Finished | 14440 | 14440 | 100 | 100 | 100 | 100 | 90.9834 | 100
19 | plaatsen faience 1A | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 2016-06-15 08:00 | 10d | 13247 | 0 | 0 | -877 | 0 | 12370 | 0 | 100% | Finished | 13247 | 13247 | 100 | 100 | 100 | 100 | 93.3796 | 100
20 | zachte vloerbekleding 1A | 2016-06-30 08:00 | 2016-07-15 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 2016-07-06 08:00 | 15d | 10598 | 0 | 0 | 838 | 0 | 11436 | 0 | 100% | Finished | 10598 | 10598 | 100 | 125 | 100 | 100 | 107.9072 | 100
21 | binnenschrijnwerk 1A | 2016-07-18 08:00 | 2016-07-27 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 |  | 0 | 0 | 37094 | 8d | 0 | 0 | 0 | 37094 | 0% | Not Started | 0 | 37094 | 100 |  | 0 | 100 |  | 0
22 | schilderwerken wanden en plafonds 1A | 2016-07-18 08:00 | 2016-08-12 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 20d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 31795 | 100 |  | 0 | 100 |  | 0
23 | binnenmeubilair 1A | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 10d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 31795 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-08-30 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (1) | 2016-03-21 08:00 | 2016-08-12 17:00 | 105d |  |  | 488936 |  |  | 488936 |  | 117d | [5 empty] | 498473 |  | 100% |  | 488936 | 488936
24 | gelijkvloers blok A | 2016-03-21 08:00 | 2016-07-08 17:00 | 80d |  |  | 263062 |  |  | 263062 |  | 92d | [5 empty] | 267887 |  | 100% |  | 263062 | 263062
1 | pleisterwerken wanden 0A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 20070 | 0 | 0 | 20070 | 2016-03-21 08:00 | 17d | 20070 | 0 | 0 | -351 | 0 | 19719 | 0 | 100% | Finished | 20070 | 20070 | 100 | 113.3333 | 100 | 100 | 98.2511 | 100
2 | pleisterwerken plafonds 0A | 2016-03-21 08:00 | 2016-03-25 17:00 | 5d |  | 0 | 25805 | 0 | 0 | 25805 | 2016-03-21 08:00 | 7d | 25805 | 0 | 0 | 4770 | 0 | 30575 | 0 | 100% | Finished | 25805 | 25805 | 100 | 140 | 100 | 100 | 118.4848 | 100
3 | lichte scheidingswanden 0A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 6594 | 0 | 0 | 6594 | 2016-03-23 08:00 | 10d | 6594 | 0 | 0 | -632 | 0 | 5962 | 0 | 100% | Finished | 6594 | 6594 | 100 | 100 | 100 | 100 | 90.4155 | 100
4 | gespoten PU isolatie en uitvullingen 0A | 2016-04-04 08:00 | 2016-04-06 17:00 | 3d |  | 0 | 10035 | 0 | 0 | 10035 | 2016-04-06 08:00 | 5d | 10035 | 0 | 0 | 2089 | 0 | 12124 | 0 | 100% | Finished | 10035 | 10035 | 100 | 166.6667 | 100 | 100 | 120.8171 | 100
5 | chape 0A | 2016-04-07 08:00 | 2016-04-13 17:00 | 5d |  | 0 | 4300 | 0 | 0 | 4300 | 2016-04-13 08:00 | 5d | 4300 | 0 | 0 | -48 | 0 | 4252 | 0 | 100% | Finished | 4300 | 4300 | 100 | 100 | 100 | 100 | 98.8837 | 100
6 | plaatsen keramische tegels 0A | 2016-04-28 08:00 | 2016-05-11 17:00 | 10d |  | 0 | 37273 | 0 | 0 | 37273 | 2016-05-04 08:00 | 10d | 37273 | 0 | 0 | -2668 | 0 | 34605 | 0 | 100% | Finished | 37273 | 37273 | 100 | 100 | 100 | 100 | 92.842 | 100
7 | plaatsen faience 0A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 15626 | 0 | 0 | 15626 | 2016-05-11 08:00 | 10d | 15626 | 0 | 0 | -874 | 0 | 14752 | 0 | 100% | Finished | 15626 | 15626 | 100 | 100 | 100 | 100 | 94.4068 | 100
8 | verlaagde plafonds 0A | 2016-04-21 08:00 | 2016-05-18 17:00 | 20d |  | 0 | 14336 | 0 | 0 | 14336 | 2016-04-27 08:00 | 20d | 14336 | 0 | 0 | 1256 | 0 | 15592 | 0 | 100% | Finished | 14336 | 14336 | 100 | 100 | 100 | 100 | 108.7612 | 100
9 | zachte vloerbekleding 0A | 2016-05-26 08:00 | 2016-06-10 17:00 | 12d |  | 0 | 11468 | 0 | 0 | 11468 | 2016-06-01 08:00 | 15d | 11468 | 0 | 0 | 1334 | 0 | 12802 | 0 | 100% | Finished | 11468 | 11468 | 100 | 125 | 100 | 100 | 111.6324 | 100
10 | binnenschrijnwerk 0A | 2016-06-13 08:00 | 2016-06-22 17:00 | 8d |  | 0 | 40141 | 0 | 0 | 40141 | 2016-06-22 08:00 | 10d | 40141 | 0 | 0 | 449 | 0 | 40590 | 0 | 100% | Finished | 40141 | 40141 | 100 | 125 | 100 | 100 | 101.1186 | 100
11 | schilderwerken wanden en plafonds 0A | 2016-06-13 08:00 | 2016-07-08 17:00 | 20d |  | 0 | 34406 | 0 | 0 | 34406 | 2016-06-22 08:00 | 25d | 34406 | 0 | 0 | 2697 | 0 | 37103 | 0 | 100% | Finished | 34406 | 34406 | 100 | 125 | 100 | 100 | 107.8387 | 100
12 | binnenmeubilair 0A | 2016-06-13 08:00 | 2016-06-24 17:00 | 10d |  | 0 | 43008 | 0 | 0 | 43008 | 2016-06-22 08:00 | 10d | 43008 | 0 | 0 | -3197 | 0 | 39811 | 0 | 100% | Finished | 43008 | 43008 | 100 | 100 | 100 | 100 | 92.5665 | 100
25 | nivo +1 blok A | 2016-04-11 08:00 | 2016-08-12 17:00 | 90d |  |  | 225874 |  |  | 225874 |  | 100d | [5 empty] | 230586 |  | 100% |  | 225874 | 225874
13 | pleisterwerken wanden 1A | 2016-04-11 08:00 | 2016-04-22 17:00 | 10d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-04-13 08:00 | 10d | 18547 | 0 | 0 | 405 | 0 | 18952 | 0 | 100% | Finished | 18547 | 18547 | 100 | 100 | 100 | 100 | 102.1836 | 100
14 | pleisterwerken plafonds 1A | 2016-04-11 08:00 | 2016-04-29 17:00 | 15d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-04-13 08:00 | 15d | 23846 | 0 | 0 | -1160 | 0 | 22686 | 0 | 100% | Finished | 23846 | 23846 | 100 | 100 | 100 | 100 | 95.1355 | 100
15 | lichte scheidingswanden 1A | 2016-04-25 08:00 | 2016-05-06 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-04-27 08:00 | 10d | 6094 | 0 | 0 | -349 | 0 | 5745 | 0 | 100% | Finished | 6094 | 6094 | 100 | 100 | 100 | 100 | 94.2731 | 100
16 | vloer uitvullingen 1A | 2016-05-09 08:00 | 2016-05-11 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-05-11 08:00 | 5d | 3974 | 0 | 0 | 1028 | 0 | 5002 | 0 | 100% | Finished | 3974 | 3974 | 100 | 166.6667 | 100 | 100 | 125.8681 | 100
17 | chape 1A | 2016-05-12 08:00 | 2016-05-18 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-05-18 08:00 | 5d | 34444 | 0 | 0 | 2235 | 0 | 36679 | 0 | 100% | Finished | 34444 | 34444 | 100 | 100 | 100 | 100 | 106.4888 | 100
18 | plaatsen keramische tegels 1A | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 2016-06-08 08:00 | 10d | 14440 | 0 | 0 | -1302 | 0 | 13138 | 0 | 100% | Finished | 14440 | 14440 | 100 | 100 | 100 | 100 | 90.9834 | 100
19 | plaatsen faience 1A | 2016-06-09 08:00 | 2016-06-22 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 2016-06-15 08:00 | 10d | 13247 | 0 | 0 | -877 | 0 | 12370 | 0 | 100% | Finished | 13247 | 13247 | 100 | 100 | 100 | 100 | 93.3796 | 100
20 | zachte vloerbekleding 1A | 2016-06-30 08:00 | 2016-07-15 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 2016-07-06 08:00 | 15d | 10598 | 0 | 0 | 838 | 0 | 11436 | 0 | 100% | Finished | 10598 | 10598 | 100 | 125 | 100 | 100 | 107.9072 | 100
21 | binnenschrijnwerk 1A | 2016-07-18 08:00 | 2016-07-27 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 | 2016-07-27 08:00 | 10d | 37094 | 0 | 0 | -504 | 0 | 36590 | 0 | 100% | Finished | 37094 | 37094 | 100 | 125 | 100 | 100 | 98.6413 | 100
22 | schilderwerken wanden en plafonds 1A | 2016-07-18 08:00 | 2016-08-12 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 | 2016-07-27 08:00 | 25d | 31795 | 0 | 0 | 4718 | 0 | 36513 | 0 | 100% | Finished | 31795 | 31795 | 100 | 125 | 100 | 100 | 114.8388 | 100
23 | binnenmeubilair 1A | 2016-07-18 08:00 | 2016-07-29 17:00 | 10d |  | 0 | 31795 | 0 | 0 | 31795 | 2016-07-27 08:00 | 10d | 31795 | 0 | 0 | -320 | 0 | 31475 | 0 | 100% | Finished | 31795 | 31795 | 100 | 100 | 100 | 100 | 98.9936 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-21 08:00 | 2016-04-13 08:00 | 109197 | 62504 | 68380 | 2016-04-06 17:00 | -46693 | 57.24% | -5876 | 91.41% | -4d | 76.47% | 100% | 2016-08-26 17:00 | 2016-12-01 12:00 | 2016-12-26 14:00 | 2016-08-24 10:00 | 2016-12-01 12:00 | 2016-12-23 09:00 | 2016-08-18 17:00 | 2016-09-28 10:00 | 2016-10-13 14:00 | 494812 | 534900.8652 | 813373.8421 | 626021.8462 | 883410.7008 | 678445.7468 | 572595.2207 | 550662.2475 | 0.76471 | 0.91407 | 0.5724 | 1 | -4 | 0.91407 | 1 | 0.76471 | 1
Tracking Period 2 | 2016-04-13 08:00 | 2016-06-01 08:00 | 232412 | 220944 | 226645 | 2016-05-25 17:00 | -11468 | 95.07% | -5701 | 97.48% | -4d | 92.31% | 100% | 2016-08-17 12:00 | 2016-08-22 12:00 | 2016-08-25 10:00 | 2016-08-17 14:00 | 2016-08-22 12:00 | 2016-08-23 17:00 | 2016-08-18 17:00 | 2016-08-25 15:00 | 2016-08-29 11:00 | 494637 | 501551.9757 | 508547.0055 | 516969.6667 | 515820.8999 | 524460.8903 | 502923.0716 | 504503.1066 | 0.92308 | 0.97485 | 0.95066 | 1 | -4 | 0.97485 | 1 | 0.92308 | 1
Tracking Period 3 | 2016-06-01 08:00 | 2016-07-27 08:00 | 488936 | 388252 | 393895 | 2016-07-15 17:00 | -100684 | 79.41% | -5643 | 98.57% | -7d | 92.39% | 100% | 2016-09-13 14:00 | 2016-09-21 10:00 | 2016-09-23 09:00 | 2016-09-08 17:00 | 2016-09-21 10:00 | 2016-09-21 16:00 | 2016-08-23 17:00 | 2016-08-25 14:00 | 2016-08-25 17:00 | 494579 | 496042.379 | 520689.021 | 502870.6235 | 522531.8928 | 504454.5161 | 500174.158 | 497338.7036 | 0.92391 | 0.98567 | 0.79408 | 1 | -7 | 0.98567 | 1 | 0.92391 | 1
Tracking Period 4 | 2016-07-27 08:00 | 2016-08-30 17:00 | 488936 | 488936 | 498473 | 2016-08-12 17:00 | 0 | 100% | -9537 | 98.09% | -12d | 89.74% | 100% | 2016-08-12 17:00 | 2016-08-12 17:00 | 2016-08-16 17:00 | 2016-08-30 17:00 | 2016-08-30 17:00 | 2016-08-30 17:00 | 2016-08-30 17:00 | 2016-08-30 17:00 | 2016-08-30 17:00 | 498473 | 498473 | 498473 | 498473 | 498473 | 498473 | 498473 | 498473 | 0.89744 | 0.98087 | 1 | 1 | -12 | 0.98087 | 1 | 0.89744 | 1