## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building Finishing Works (2) | 1 |  |  | 2016-03-21 08:00 | 2016-07-21 17:00 | 89d |  |  | 477381 |  |  | 477381 | 122.375
23 | nivo +2 blok A | 1.1 |  |  | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 233822 |  |  | 233822 | 116.375
1 | pleisterwerken wanden 2A | 1.1.1 |  | SS2 | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 18547 | 0 | 0 | 18547 | 18.375
2 | pleisterwerken plafonds 2A | 1.1.2 | 1SS | FS3-1w | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 23846 | 0 | 0 | 23846 | 11.375
3 | lichte scheidingswanden 2A | 1.1.3 | 2FS-1w | FS4 | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 11.375
4 | vloer uitvullingen 2A | 1.1.4 | 3FS | FS5 | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2.375
5 | chape 2A | 1.1.5 | 4FS | FS6+2w;FS8+6w;FS12 | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 6.375
6 | plaatsen keramische tegels 2A | 1.1.6 | 5FS+2w | FS7-1w | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 13.375
7 | plaatsen faience 2A | 1.1.7 | 6FS-1w |  | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 13.375
8 | zachte vloerbekleding 2A | 1.1.8 | 5FS+6w | FS9;FS10;FS11 | 2016-06-02 08:00 | 2016-06-17 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 15.375
9 | binnenschrijnwerk 2A | 1.1.9 | 8FS |  | 2016-06-20 08:00 | 2016-06-29 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 | 9.375
10 | schilderwerken wanden en plafonds 2A | 1.1.10 | 8FS |  | 2016-06-20 08:00 | 2016-07-15 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 | 25.375
11 | binnenmeubilair 2A | 1.1.11 | 8FS |  | 2016-06-20 08:00 | 2016-07-01 17:00 | 10d |  | 0 | 39743 | 0 | 0 | 39743 | 11.375
24 | nivo +3 blok A | 1.2 |  |  | 2016-04-21 08:00 | 2016-07-21 17:00 | 66d |  |  | 243559 |  |  | 243559 | 91.375
12 | pleisterwerken wanden 3A | 1.2.1 | 5FS | SS13 | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 19319 | 0 | 0 | 19319 | 13.375
13 | pleisterwerken plafonds 3A | 1.2.2 | 12SS | FS14-1w | 2016-04-21 08:00 | 2016-04-27 17:00 | 5d |  | 0 | 24839 | 0 | 0 | 24839 | 6.375
14 | lichte scheidingswanden 3A | 1.2.3 | 13FS-1w | FS15 | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 6347 | 0 | 0 | 6347 | 13.375
15 | vloer uitvullingen 3A | 1.2.4 | 14FS | FS16 | 2016-05-05 08:00 | 2016-05-09 17:00 | 3d |  | 0 | 4139 | 0 | 0 | 4139 | 4.375
16 | chape 3A | 1.2.5 | 15FS | FS17+2w;FS19+6w | 2016-05-10 08:00 | 2016-05-12 17:00 | 3d |  | 0 | 35879 | 0 | 0 | 35879 | 2.375
17 | plaatsen keramische tegels 3A | 1.2.6 | 16FS+2w | FS18-1w | 2016-05-27 08:00 | 2016-06-07 17:00 | 8d |  | 0 | 15041 | 0 | 0 | 15041 | 11.375
18 | plaatsen faience 3A | 1.2.7 | 17FS-1w |  | 2016-06-01 08:00 | 2016-06-10 17:00 | 8d |  | 0 | 13799 | 0 | 0 | 13799 | 9.375
19 | zachte vloerbekleding 3A | 1.2.8 | 16FS+6w | FS20;FS21;FS22 | 2016-06-24 08:00 | 2016-07-07 17:00 | 10d |  | 0 | 11039 | 0 | 0 | 11039 | 13.375
20 | binnenschrijnwerk 3A | 1.2.9 | 19FS |  | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 38639 | 0 | 0 | 38639 | 11.375
21 | schilderwerken wanden en plafonds 3A | 1.2.10 | 19FS |  | 2016-07-08 08:00 | 2016-07-21 17:00 | 10d |  | 0 | 33119 | 0 | 0 | 33119 | 13.375
22 | binnenmeubilair 3A | 1.2.11 | 19FS |  | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 41399 | 0 | 0 | 41399 | 11.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building Finishing Works (2) | 712h |  |  |  |  | 99 | 100 | 101
23 | nivo +2 blok A | 680h |  |  |  |  | 99 | 100 | 101
1 | pleisterwerken wanden 2A | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | pleisterwerken plafonds 2A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | lichte scheidingswanden 2A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | vloer uitvullingen 2A | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
5 | chape 2A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | plaatsen keramische tegels 2A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | plaatsen faience 2A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | zachte vloerbekleding 2A | 96h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | binnenschrijnwerk 2A | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | schilderwerken wanden en plafonds 2A | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
11 | binnenmeubilair 2A | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | nivo +3 blok A | 528h |  |  |  |  | 99 | 100 | 101
12 | pleisterwerken wanden 3A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | pleisterwerken plafonds 3A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | lichte scheidingswanden 3A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | vloer uitvullingen 3A | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
16 | chape 3A | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | plaatsen keramische tegels 3A | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | plaatsen faience 3A | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | zachte vloerbekleding 3A | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
20 | binnenschrijnwerk 3A | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | schilderwerken wanden en plafonds 3A | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
22 | binnenmeubilair 3A | 64h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120

## Project Control - TP1
| TP Status Date | 2016-04-27 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (2) | 2016-03-21 08:00 | 2016-07-21 17:00 | 89d |  |  | 477381 |  |  | 477381 |  | 27d | [5 empty] | 90202 |  | 18.2% |  | 86905 | 137410
23 | nivo +2 blok A | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 233822 |  |  | 233822 |  | 27d | [5 empty] | 90202 |  | 37.17% |  | 86905 | 86905
1 | pleisterwerken wanden 2A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-03-21 08:00 | 17d | 18547 | 0 | 0 | -213 | 0 | 18334 | 0 | 100% | Finished | 18547 | 18547 | 100 | 113.3333 | 100 | 100 | 98.8516 | 100
2 | pleisterwerken plafonds 2A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-03-21 08:00 | 12d | 23846 | 0 | 0 | 3541 | 0 | 27387 | 0 | 100% | Finished | 23846 | 23846 | 100 | 120 | 100 | 100 | 114.8495 | 100
3 | lichte scheidingswanden 2A | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-03-30 08:00 | 10d | 6094 | 0 | 0 | 35 | 0 | 6129 | 0 | 100% | Finished | 6094 | 6094 | 100 | 100 | 100 | 100 | 100.5743 | 100
4 | vloer uitvullingen 2A | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-04-13 08:00 | 5d | 3974 | 0 | 0 | 185 | 0 | 4159 | 0 | 100% | Finished | 3974 | 3974 | 100 | 166.6667 | 100 | 100 | 104.6553 | 100
5 | chape 2A | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-04-20 08:00 | 5d | 34444 | 0 | 0 | -251 | 0 | 34193 | 0 | 100% | Finished | 34444 | 34444 | 100 | 100 | 100 | 100 | 99.2713 | 100
6 | plaatsen keramische tegels 2A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 |  | 0 | 0 | 14440 | 10d | 0 | 0 | 0 | 14440 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | plaatsen faience 2A | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 |  | 0 | 0 | 13247 | 10d | 0 | 0 | 0 | 13247 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | zachte vloerbekleding 2A | 2016-06-02 08:00 | 2016-06-17 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 |  | 0 | 0 | 10598 | 12d | 0 | 0 | 0 | 10598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | binnenschrijnwerk 2A | 2016-06-20 08:00 | 2016-06-29 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 |  | 0 | 0 | 37094 | 8d | 0 | 0 | 0 | 37094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | schilderwerken wanden en plafonds 2A | 2016-06-20 08:00 | 2016-07-15 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 20d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | binnenmeubilair 2A | 2016-06-20 08:00 | 2016-07-01 17:00 | 10d |  | 0 | 39743 | 0 | 0 | 39743 |  | 0 | 0 | 39743 | 10d | 0 | 0 | 0 | 39743 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | nivo +3 blok A | 2016-04-21 08:00 | 2016-07-21 17:00 | 66d |  |  | 243559 |  |  | 243559 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 50505
12 | pleisterwerken wanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 19319 | 0 | 0 | 19319 |  | 0 | 0 | 19319 | 10d | 0 | 0 | 0 | 19319 | 0% | Not Started | 0 | 19319 | 100 |  | 0 | 100 |  | 0
13 | pleisterwerken plafonds 3A | 2016-04-21 08:00 | 2016-04-27 17:00 | 5d |  | 0 | 24839 | 0 | 0 | 24839 |  | 0 | 0 | 24839 | 5d | 0 | 0 | 0 | 24839 | 0% | Not Started | 0 | 24839 | 100 |  | 0 | 100 |  | 0
14 | lichte scheidingswanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 6347 | 0 | 0 | 6347 |  | 0 | 0 | 6347 | 10d | 0 | 0 | 0 | 6347 | 0% | Not Started | 0 | 6347 | 100 |  | 0 | 100 |  | 0
15 | vloer uitvullingen 3A | 2016-05-05 08:00 | 2016-05-09 17:00 | 3d |  | 0 | 4139 | 0 | 0 | 4139 |  | 0 | 0 | 4139 | 3d | 0 | 0 | 0 | 4139 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | chape 3A | 2016-05-10 08:00 | 2016-05-12 17:00 | 3d |  | 0 | 35879 | 0 | 0 | 35879 |  | 0 | 0 | 35879 | 3d | 0 | 0 | 0 | 35879 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | plaatsen keramische tegels 3A | 2016-05-27 08:00 | 2016-06-07 17:00 | 8d |  | 0 | 15041 | 0 | 0 | 15041 |  | 0 | 0 | 15041 | 8d | 0 | 0 | 0 | 15041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | plaatsen faience 3A | 2016-06-01 08:00 | 2016-06-10 17:00 | 8d |  | 0 | 13799 | 0 | 0 | 13799 |  | 0 | 0 | 13799 | 8d | 0 | 0 | 0 | 13799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | zachte vloerbekleding 3A | 2016-06-24 08:00 | 2016-07-07 17:00 | 10d |  | 0 | 11039 | 0 | 0 | 11039 |  | 0 | 0 | 11039 | 10d | 0 | 0 | 0 | 11039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | binnenschrijnwerk 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 38639 | 0 | 0 | 38639 |  | 0 | 0 | 38639 | 8d | 0 | 0 | 0 | 38639 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | schilderwerken wanden en plafonds 3A | 2016-07-08 08:00 | 2016-07-21 17:00 | 10d |  | 0 | 33119 | 0 | 0 | 33119 |  | 0 | 0 | 33119 | 10d | 0 | 0 | 0 | 33119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnenmeubilair 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 41399 | 0 | 0 | 41399 |  | 0 | 0 | 41399 | 8d | 0 | 0 | 0 | 41399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-06-08 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (2) | 2016-03-21 08:00 | 2016-07-21 17:00 | 89d |  |  | 477381 |  |  | 477381 |  | 57d | [5 empty] | 213819 |  | 42.97% |  | 205115 | 244553
23 | nivo +2 blok A | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 233822 |  |  | 233822 |  | 57d | [5 empty] | 118483 |  | 49.01% |  | 114592 | 125190
1 | pleisterwerken wanden 2A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-03-21 08:00 | 17d | 18547 | 0 | 0 | -213 | 0 | 18334 | 0 | 100% | Finished | 18547 | 18547 | 100 | 113.3333 | 100 | 100 | 98.8516 | 100
2 | pleisterwerken plafonds 2A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-03-21 08:00 | 12d | 23846 | 0 | 0 | 3541 | 0 | 27387 | 0 | 100% | Finished | 23846 | 23846 | 100 | 120 | 100 | 100 | 114.8495 | 100
3 | lichte scheidingswanden 2A | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-03-30 08:00 | 10d | 6094 | 0 | 0 | 35 | 0 | 6129 | 0 | 100% | Finished | 6094 | 6094 | 100 | 100 | 100 | 100 | 100.5743 | 100
4 | vloer uitvullingen 2A | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-04-13 08:00 | 5d | 3974 | 0 | 0 | 185 | 0 | 4159 | 0 | 100% | Finished | 3974 | 3974 | 100 | 166.6667 | 100 | 100 | 104.6553 | 100
5 | chape 2A | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-04-20 08:00 | 5d | 34444 | 0 | 0 | -251 | 0 | 34193 | 0 | 100% | Finished | 34444 | 34444 | 100 | 100 | 100 | 100 | 99.2713 | 100
6 | plaatsen keramische tegels 2A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 2016-05-11 08:00 | 10d | 14440 | 0 | 0 | 376 | 0 | 14816 | 0 | 100% | Finished | 14440 | 14440 | 100 | 100 | 100 | 100 | 102.6039 | 100
7 | plaatsen faience 2A | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 2016-05-18 08:00 | 10d | 13247 | 0 | 0 | 218 | 0 | 13465 | 0 | 100% | Finished | 13247 | 13247 | 100 | 100 | 100 | 100 | 101.6457 | 100
8 | zachte vloerbekleding 2A | 2016-06-02 08:00 | 2016-06-17 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 |  | 0 | 0 | 10598 | 12d | 0 | 0 | 0 | 10598 | 0% | Not Started | 0 | 10598 | 100 |  | 0 | 100 |  | 0
9 | binnenschrijnwerk 2A | 2016-06-20 08:00 | 2016-06-29 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 |  | 0 | 0 | 37094 | 8d | 0 | 0 | 0 | 37094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | schilderwerken wanden en plafonds 2A | 2016-06-20 08:00 | 2016-07-15 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 20d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | binnenmeubilair 2A | 2016-06-20 08:00 | 2016-07-01 17:00 | 10d |  | 0 | 39743 | 0 | 0 | 39743 |  | 0 | 0 | 39743 | 10d | 0 | 0 | 0 | 39743 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | nivo +3 blok A | 2016-04-21 08:00 | 2016-07-21 17:00 | 66d |  |  | 243559 |  |  | 243559 |  | 30d | [5 empty] | 95336 |  | 37.17% |  | 90523 | 119363
12 | pleisterwerken wanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 19319 | 0 | 0 | 19319 | 2016-04-27 08:00 | 10d | 19319 | 0 | 0 | 88 | 0 | 19407 | 0 | 100% | Finished | 19319 | 19319 | 100 | 100 | 100 | 100 | 100.4555 | 100
13 | pleisterwerken plafonds 3A | 2016-04-21 08:00 | 2016-04-27 17:00 | 5d |  | 0 | 24839 | 0 | 0 | 24839 | 2016-04-27 08:00 | 5d | 24839 | 0 | 0 | -732 | 0 | 24107 | 0 | 100% | Finished | 24839 | 24839 | 100 | 100 | 100 | 100 | 97.053 | 100
14 | lichte scheidingswanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 6347 | 0 | 0 | 6347 | 2016-04-27 08:00 | 10d | 6347 | 0 | 0 | -159 | 0 | 6188 | 0 | 100% | Finished | 6347 | 6347 | 100 | 100 | 100 | 100 | 97.4949 | 100
15 | vloer uitvullingen 3A | 2016-05-05 08:00 | 2016-05-09 17:00 | 3d |  | 0 | 4139 | 0 | 0 | 4139 | 2016-05-11 08:00 | 5d | 4139 | 0 | 0 | 757 | 0 | 4896 | 0 | 100% | Finished | 4139 | 4139 | 100 | 166.6667 | 100 | 100 | 118.2894 | 100
16 | chape 3A | 2016-05-10 08:00 | 2016-05-12 17:00 | 3d |  | 0 | 35879 | 0 | 0 | 35879 | 2016-05-18 08:00 | 5d | 35879 | 0 | 0 | 4859 | 0 | 40738 | 0 | 100% | Finished | 35879 | 35879 | 100 | 166.6667 | 100 | 100 | 113.5427 | 100
17 | plaatsen keramische tegels 3A | 2016-05-27 08:00 | 2016-06-07 17:00 | 8d |  | 0 | 15041 | 0 | 0 | 15041 |  | 0 | 0 | 15041 | 8d | 0 | 0 | 0 | 15041 | 0% | Not Started | 0 | 15041 | 100 |  | 0 | 100 |  | 0
18 | plaatsen faience 3A | 2016-06-01 08:00 | 2016-06-10 17:00 | 8d |  | 0 | 13799 | 0 | 0 | 13799 |  | 0 | 0 | 13799 | 8d | 0 | 0 | 0 | 13799 | 0% | Not Started | 0 | 13799 | 100 |  | 0 | 100 |  | 0
19 | zachte vloerbekleding 3A | 2016-06-24 08:00 | 2016-07-07 17:00 | 10d |  | 0 | 11039 | 0 | 0 | 11039 |  | 0 | 0 | 11039 | 10d | 0 | 0 | 0 | 11039 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | binnenschrijnwerk 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 38639 | 0 | 0 | 38639 |  | 0 | 0 | 38639 | 8d | 0 | 0 | 0 | 38639 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | schilderwerken wanden en plafonds 3A | 2016-07-08 08:00 | 2016-07-21 17:00 | 10d |  | 0 | 33119 | 0 | 0 | 33119 |  | 0 | 0 | 33119 | 10d | 0 | 0 | 0 | 33119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnenmeubilair 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 41399 | 0 | 0 | 41399 |  | 0 | 0 | 41399 | 8d | 0 | 0 | 0 | 41399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-06-29 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (2) | 2016-03-21 08:00 | 2016-07-21 17:00 | 89d |  |  | 477381 |  |  | 477381 |  | 72d | [5 empty] | 255720 |  | 51.23% |  | 244553 | 364224
23 | nivo +2 blok A | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 233822 |  |  | 233822 |  | 72d | [5 empty] | 129469 |  | 53.54% |  | 125190 | 233822
1 | pleisterwerken wanden 2A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-03-21 08:00 | 17d | 18547 | 0 | 0 | -213 | 0 | 18334 | 0 | 100% | Finished | 18547 | 18547 | 100 | 113.3333 | 100 | 100 | 98.8516 | 100
2 | pleisterwerken plafonds 2A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-03-21 08:00 | 12d | 23846 | 0 | 0 | 3541 | 0 | 27387 | 0 | 100% | Finished | 23846 | 23846 | 100 | 120 | 100 | 100 | 114.8495 | 100
3 | lichte scheidingswanden 2A | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-03-30 08:00 | 10d | 6094 | 0 | 0 | 35 | 0 | 6129 | 0 | 100% | Finished | 6094 | 6094 | 100 | 100 | 100 | 100 | 100.5743 | 100
4 | vloer uitvullingen 2A | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-04-13 08:00 | 5d | 3974 | 0 | 0 | 185 | 0 | 4159 | 0 | 100% | Finished | 3974 | 3974 | 100 | 166.6667 | 100 | 100 | 104.6553 | 100
5 | chape 2A | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-04-20 08:00 | 5d | 34444 | 0 | 0 | -251 | 0 | 34193 | 0 | 100% | Finished | 34444 | 34444 | 100 | 100 | 100 | 100 | 99.2713 | 100
6 | plaatsen keramische tegels 2A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 2016-05-11 08:00 | 10d | 14440 | 0 | 0 | 376 | 0 | 14816 | 0 | 100% | Finished | 14440 | 14440 | 100 | 100 | 100 | 100 | 102.6039 | 100
7 | plaatsen faience 2A | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 2016-05-18 08:00 | 10d | 13247 | 0 | 0 | 218 | 0 | 13465 | 0 | 100% | Finished | 13247 | 13247 | 100 | 100 | 100 | 100 | 101.6457 | 100
8 | zachte vloerbekleding 2A | 2016-06-02 08:00 | 2016-06-17 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 2016-06-08 08:00 | 15d | 10598 | 0 | 0 | 388 | 0 | 10986 | 0 | 100% | Finished | 10598 | 10598 | 100 | 125 | 100 | 100 | 103.6611 | 100
9 | binnenschrijnwerk 2A | 2016-06-20 08:00 | 2016-06-29 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 |  | 0 | 0 | 37094 | 8d | 0 | 0 | 0 | 37094 | 0% | Not Started | 0 | 37094 | 100 |  | 0 | 100 |  | 0
10 | schilderwerken wanden en plafonds 2A | 2016-06-20 08:00 | 2016-07-15 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 |  | 0 | 0 | 31795 | 20d | 0 | 0 | 0 | 31795 | 0% | Not Started | 0 | 31795 | 100 |  | 0 | 100 |  | 0
11 | binnenmeubilair 2A | 2016-06-20 08:00 | 2016-07-01 17:00 | 10d |  | 0 | 39743 | 0 | 0 | 39743 |  | 0 | 0 | 39743 | 10d | 0 | 0 | 0 | 39743 | 0% | Not Started | 0 | 39743 | 100 |  | 0 | 100 |  | 0
24 | nivo +3 blok A | 2016-04-21 08:00 | 2016-07-21 17:00 | 66d |  |  | 243559 |  |  | 243559 |  | 45d | [5 empty] | 126251 |  | 49.01% |  | 119363 | 130402
12 | pleisterwerken wanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 19319 | 0 | 0 | 19319 | 2016-04-27 08:00 | 10d | 19319 | 0 | 0 | 88 | 0 | 19407 | 0 | 100% | Finished | 19319 | 19319 | 100 | 100 | 100 | 100 | 100.4555 | 100
13 | pleisterwerken plafonds 3A | 2016-04-21 08:00 | 2016-04-27 17:00 | 5d |  | 0 | 24839 | 0 | 0 | 24839 | 2016-04-27 08:00 | 5d | 24839 | 0 | 0 | -732 | 0 | 24107 | 0 | 100% | Finished | 24839 | 24839 | 100 | 100 | 100 | 100 | 97.053 | 100
14 | lichte scheidingswanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 6347 | 0 | 0 | 6347 | 2016-04-27 08:00 | 10d | 6347 | 0 | 0 | -159 | 0 | 6188 | 0 | 100% | Finished | 6347 | 6347 | 100 | 100 | 100 | 100 | 97.4949 | 100
15 | vloer uitvullingen 3A | 2016-05-05 08:00 | 2016-05-09 17:00 | 3d |  | 0 | 4139 | 0 | 0 | 4139 | 2016-05-11 08:00 | 5d | 4139 | 0 | 0 | 757 | 0 | 4896 | 0 | 100% | Finished | 4139 | 4139 | 100 | 166.6667 | 100 | 100 | 118.2894 | 100
16 | chape 3A | 2016-05-10 08:00 | 2016-05-12 17:00 | 3d |  | 0 | 35879 | 0 | 0 | 35879 | 2016-05-18 08:00 | 5d | 35879 | 0 | 0 | 4859 | 0 | 40738 | 0 | 100% | Finished | 35879 | 35879 | 100 | 166.6667 | 100 | 100 | 113.5427 | 100
17 | plaatsen keramische tegels 3A | 2016-05-27 08:00 | 2016-06-07 17:00 | 8d |  | 0 | 15041 | 0 | 0 | 15041 | 2016-06-08 08:00 | 10d | 15041 | 0 | 0 | 2053 | 0 | 17094 | 0 | 100% | Finished | 15041 | 15041 | 100 | 125 | 100 | 100 | 113.6494 | 100
18 | plaatsen faience 3A | 2016-06-01 08:00 | 2016-06-10 17:00 | 8d |  | 0 | 13799 | 0 | 0 | 13799 | 2016-06-15 08:00 | 10d | 13799 | 0 | 0 | 22 | 0 | 13821 | 0 | 100% | Finished | 13799 | 13799 | 100 | 125 | 100 | 100 | 100.1594 | 100
19 | zachte vloerbekleding 3A | 2016-06-24 08:00 | 2016-07-07 17:00 | 10d |  | 0 | 11039 | 0 | 0 | 11039 |  | 0 | 0 | 11039 | 10d | 0 | 0 | 0 | 11039 | 0% | Not Started | 0 | 11039 | 100 |  | 0 | 100 |  | 0
20 | binnenschrijnwerk 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 38639 | 0 | 0 | 38639 |  | 0 | 0 | 38639 | 8d | 0 | 0 | 0 | 38639 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | schilderwerken wanden en plafonds 3A | 2016-07-08 08:00 | 2016-07-21 17:00 | 10d |  | 0 | 33119 | 0 | 0 | 33119 |  | 0 | 0 | 33119 | 10d | 0 | 0 | 0 | 33119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnenmeubilair 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 41399 | 0 | 0 | 41399 |  | 0 | 0 | 41399 | 8d | 0 | 0 | 0 | 41399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-08-02 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (2) | 2016-03-21 08:00 | 2016-07-21 17:00 | 89d |  |  | 477381 |  |  | 477381 |  | 97d | [5 empty] | 496991 |  | 100% |  | 477381 | 477381
23 | nivo +2 blok A | 2016-03-21 08:00 | 2016-07-15 17:00 | 85d |  |  | 233822 |  |  | 233822 |  | 97d | [5 empty] | 245743 |  | 100% |  | 233822 | 233822
1 | pleisterwerken wanden 2A | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 18547 | 0 | 0 | 18547 | 2016-03-21 08:00 | 17d | 18547 | 0 | 0 | -213 | 0 | 18334 | 0 | 100% | Finished | 18547 | 18547 | 100 | 113.3333 | 100 | 100 | 98.8516 | 100
2 | pleisterwerken plafonds 2A | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 23846 | 0 | 0 | 23846 | 2016-03-21 08:00 | 12d | 23846 | 0 | 0 | 3541 | 0 | 27387 | 0 | 100% | Finished | 23846 | 23846 | 100 | 120 | 100 | 100 | 114.8495 | 100
3 | lichte scheidingswanden 2A | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 6094 | 0 | 0 | 6094 | 2016-03-30 08:00 | 10d | 6094 | 0 | 0 | 35 | 0 | 6129 | 0 | 100% | Finished | 6094 | 6094 | 100 | 100 | 100 | 100 | 100.5743 | 100
4 | vloer uitvullingen 2A | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3974 | 0 | 0 | 3974 | 2016-04-13 08:00 | 5d | 3974 | 0 | 0 | 185 | 0 | 4159 | 0 | 100% | Finished | 3974 | 3974 | 100 | 166.6667 | 100 | 100 | 104.6553 | 100
5 | chape 2A | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 34444 | 0 | 0 | 34444 | 2016-04-20 08:00 | 5d | 34444 | 0 | 0 | -251 | 0 | 34193 | 0 | 100% | Finished | 34444 | 34444 | 100 | 100 | 100 | 100 | 99.2713 | 100
6 | plaatsen keramische tegels 2A | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 14440 | 0 | 0 | 14440 | 2016-05-11 08:00 | 10d | 14440 | 0 | 0 | 376 | 0 | 14816 | 0 | 100% | Finished | 14440 | 14440 | 100 | 100 | 100 | 100 | 102.6039 | 100
7 | plaatsen faience 2A | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 13247 | 0 | 0 | 13247 | 2016-05-18 08:00 | 10d | 13247 | 0 | 0 | 218 | 0 | 13465 | 0 | 100% | Finished | 13247 | 13247 | 100 | 100 | 100 | 100 | 101.6457 | 100
8 | zachte vloerbekleding 2A | 2016-06-02 08:00 | 2016-06-17 17:00 | 12d |  | 0 | 10598 | 0 | 0 | 10598 | 2016-06-08 08:00 | 15d | 10598 | 0 | 0 | 388 | 0 | 10986 | 0 | 100% | Finished | 10598 | 10598 | 100 | 125 | 100 | 100 | 103.6611 | 100
9 | binnenschrijnwerk 2A | 2016-06-20 08:00 | 2016-06-29 17:00 | 8d |  | 0 | 37094 | 0 | 0 | 37094 | 2016-06-29 08:00 | 10d | 37094 | 0 | 0 | 1257 | 0 | 38351 | 0 | 100% | Finished | 37094 | 37094 | 100 | 125 | 100 | 100 | 103.3887 | 100
10 | schilderwerken wanden en plafonds 2A | 2016-06-20 08:00 | 2016-07-15 17:00 | 20d |  | 0 | 31795 | 0 | 0 | 31795 | 2016-06-29 08:00 | 25d | 31795 | 0 | 0 | 2577 | 0 | 34372 | 0 | 100% | Finished | 31795 | 31795 | 100 | 125 | 100 | 100 | 108.105 | 100
11 | binnenmeubilair 2A | 2016-06-20 08:00 | 2016-07-01 17:00 | 10d |  | 0 | 39743 | 0 | 0 | 39743 | 2016-06-29 08:00 | 10d | 39743 | 0 | 0 | 3808 | 0 | 43551 | 0 | 100% | Finished | 39743 | 39743 | 100 | 100 | 100 | 100 | 109.5816 | 100
24 | nivo +3 blok A | 2016-04-21 08:00 | 2016-07-21 17:00 | 66d |  |  | 243559 |  |  | 243559 |  | 70d | [5 empty] | 251248 |  | 100% |  | 243559 | 243559
12 | pleisterwerken wanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 19319 | 0 | 0 | 19319 | 2016-04-27 08:00 | 10d | 19319 | 0 | 0 | 88 | 0 | 19407 | 0 | 100% | Finished | 19319 | 19319 | 100 | 100 | 100 | 100 | 100.4555 | 100
13 | pleisterwerken plafonds 3A | 2016-04-21 08:00 | 2016-04-27 17:00 | 5d |  | 0 | 24839 | 0 | 0 | 24839 | 2016-04-27 08:00 | 5d | 24839 | 0 | 0 | -732 | 0 | 24107 | 0 | 100% | Finished | 24839 | 24839 | 100 | 100 | 100 | 100 | 97.053 | 100
14 | lichte scheidingswanden 3A | 2016-04-21 08:00 | 2016-05-04 17:00 | 10d |  | 0 | 6347 | 0 | 0 | 6347 | 2016-04-27 08:00 | 10d | 6347 | 0 | 0 | -159 | 0 | 6188 | 0 | 100% | Finished | 6347 | 6347 | 100 | 100 | 100 | 100 | 97.4949 | 100
15 | vloer uitvullingen 3A | 2016-05-05 08:00 | 2016-05-09 17:00 | 3d |  | 0 | 4139 | 0 | 0 | 4139 | 2016-05-11 08:00 | 5d | 4139 | 0 | 0 | 757 | 0 | 4896 | 0 | 100% | Finished | 4139 | 4139 | 100 | 166.6667 | 100 | 100 | 118.2894 | 100
16 | chape 3A | 2016-05-10 08:00 | 2016-05-12 17:00 | 3d |  | 0 | 35879 | 0 | 0 | 35879 | 2016-05-18 08:00 | 5d | 35879 | 0 | 0 | 4859 | 0 | 40738 | 0 | 100% | Finished | 35879 | 35879 | 100 | 166.6667 | 100 | 100 | 113.5427 | 100
17 | plaatsen keramische tegels 3A | 2016-05-27 08:00 | 2016-06-07 17:00 | 8d |  | 0 | 15041 | 0 | 0 | 15041 | 2016-06-08 08:00 | 10d | 15041 | 0 | 0 | 2053 | 0 | 17094 | 0 | 100% | Finished | 15041 | 15041 | 100 | 125 | 100 | 100 | 113.6494 | 100
18 | plaatsen faience 3A | 2016-06-01 08:00 | 2016-06-10 17:00 | 8d |  | 0 | 13799 | 0 | 0 | 13799 | 2016-06-15 08:00 | 10d | 13799 | 0 | 0 | 22 | 0 | 13821 | 0 | 100% | Finished | 13799 | 13799 | 100 | 125 | 100 | 100 | 100.1594 | 100
19 | zachte vloerbekleding 3A | 2016-06-24 08:00 | 2016-07-07 17:00 | 10d |  | 0 | 11039 | 0 | 0 | 11039 | 2016-07-06 08:00 | 10d | 11039 | 0 | 0 | -885 | 0 | 10154 | 0 | 100% | Finished | 11039 | 11039 | 100 | 100 | 100 | 100 | 91.983 | 100
20 | binnenschrijnwerk 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 38639 | 0 | 0 | 38639 | 2016-07-20 08:00 | 10d | 38639 | 0 | 0 | 2721 | 0 | 41360 | 0 | 100% | Finished | 38639 | 38639 | 100 | 125 | 100 | 100 | 107.0421 | 100
21 | schilderwerken wanden en plafonds 3A | 2016-07-08 08:00 | 2016-07-21 17:00 | 10d |  | 0 | 33119 | 0 | 0 | 33119 | 2016-07-20 08:00 | 10d | 33119 | 0 | 0 | -1300 | 0 | 31819 | 0 | 100% | Finished | 33119 | 33119 | 100 | 100 | 100 | 100 | 96.0748 | 100
22 | binnenmeubilair 3A | 2016-07-08 08:00 | 2016-07-19 17:00 | 8d |  | 0 | 41399 | 0 | 0 | 41399 | 2016-07-20 08:00 | 10d | 41399 | 0 | 0 | 265 | 0 | 41664 | 0 | 100% | Finished | 41399 | 41399 | 100 | 125 | 100 | 100 | 100.6401 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-21 08:00 | 2016-04-27 08:00 | 137410 | 86905 | 90202 | 2016-04-20 17:00 | -50505 | 63.25% | -3297 | 96.34% | -4d | 85.19% | 100% | 2016-08-04 11:00 | 2016-10-03 15:00 | 2016-10-10 17:00 | 2016-08-04 16:00 | 2016-10-03 15:00 | 2016-10-07 17:00 | 2016-07-27 17:00 | 2016-08-12 12:00 | 2016-08-17 11:00 | 480678 | 495491.87 | 707603.8429 | 548586.8696 | 731026.8206 | 565977.0648 | 525394.4462 | 505103.5295 | 0.85185 | 0.96345 | 0.63245 | 1 | -4 | 0.96345 | 1 | 0.85185 | 1
Tracking Period 2 | 2016-04-27 08:00 | 2016-06-08 08:00 | 244553 | 205115 | 213819 | 2016-05-26 17:00 | -39438 | 83.87% | -8704 | 95.93% | -8d | 85.96% | 100% | 2016-08-02 11:00 | 2016-08-16 09:00 | 2016-08-22 14:00 | 2016-08-04 10:00 | 2016-08-16 09:00 | 2016-08-18 10:00 | 2016-08-02 17:00 | 2016-08-11 12:00 | 2016-08-15 12:00 | 486085 | 497638.5347 | 538434.2992 | 530536.5918 | 552209.2624 | 543976.4179 | 504956.2215 | 503659.7974 | 0.85965 | 0.95929 | 0.83873 | 1 | -8 | 0.95929 | 1 | 0.85965 | 1
Tracking Period 3 | 2016-06-08 08:00 | 2016-06-29 08:00 | 364224 | 244553 | 255720 | 2016-06-17 17:00 | -119671 | 67.14% | -11167 | 95.63% | -7d | 90.28% | 100% | 2016-08-23 10:00 | 2016-09-21 12:00 | 2016-09-29 14:00 | 2016-08-24 14:00 | 2016-09-21 12:00 | 2016-09-26 11:00 | 2016-08-01 17:00 | 2016-08-04 14:00 | 2016-08-05 15:00 | 488548 | 499179.6025 | 602481.4197 | 513621.7846 | 618315.5529 | 525398.3289 | 514604.1581 | 501937.1741 | 0.90278 | 0.95633 | 0.67144 | 1 | -7 | 0.95633 | 1 | 0.90278 | 1
Tracking Period 4 | 2016-06-29 08:00 | 2016-08-02 17:00 | 477381 | 477381 | 496991 | 2016-07-21 17:00 | 0 | 100% | -19610 | 96.05% | -8d | 91.75% | 100% | 2016-07-21 17:00 | 2016-07-21 17:00 | 2016-07-27 14:00 | 2016-08-02 17:00 | 2016-08-02 17:00 | 2016-08-02 17:00 | 2016-08-02 17:00 | 2016-08-02 17:00 | 2016-08-02 17:00 | 496991 | 496991 | 496991 | 496991 | 496991 | 496991 | 496991 | 496991 | 0.91753 | 0.96054 | 1 | 1 | -8 | 0.96054 | 1 | 0.91753 | 1