## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Young Cattle Barn | 1 |  |  | 2010-09-08 08:00 | 2011-03-07 17:00 | 115d |  |  | 818439.9918 |  |  | 818439.9918 | 180.375
1 | Begin | 1.1 |  | FS2 | 2010-09-08 08:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
2 | Werfinstallatie | 1.2 | 1FS | SS3;SS5;FF6 | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 12659.2598 | 0 | 0 | 12659.2598 | 13.375
3 | Afbraak jongveestal | 1.3 | 2SS | FS7;FS6 | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 6.375
31 | Bijkomende sloopwerken | 1.4 |  |  | 2010-09-08 08:00 | 2010-09-28 17:00 | 15d |  | 0 | 22474.1797 | 0 | 0 | 22474.1797 | 20.375
5 | Omleggen elektrische kabel | 1.5 | 2SS | FS6 | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 26412.5801 | 0 | 0 | 26412.5801 | 0.375
6 | Grondwerken | 1.6 | 2FF;3FS;5FS | SS7 | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 14850.3096 | 0 | 0 | 14850.3096 | 6.375
7 | Aanvulling afbraak jongveestal | 1.7 | 3FS;6SS | FS8 | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 6.375
8 | Plaatfundering-ondergronds | 1.8 | 7FS | FS9 | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 31783.8691 | 0 | 0 | 31783.8691 | 13.375
9 | Funderingswanden | 1.9 | 8FS | FS10 | 2010-10-06 08:00 | 2010-11-03 17:00 | 20d |  | 0 | 118171.1719 | 0 | 0 | 118171.1719 | 28.375
10 | Draagvloeren | 1.10 | 9FS | FS11 | 2010-11-04 08:00 | 2010-11-19 17:00 | 10d |  | 0 | 63201.1914 | 0 | 0 | 63201.1914 | 15.375
11 | Wederaanvulling-binnen | 1.11 | 10FS | FS12 | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 437.87 | 0 | 0 | 437.87 | 1.375
12 | Plaatfundering op volle grond | 1.12 | 11FS | FS14;FS32;FS33 | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 9987.6201 | 0 | 0 | 9987.6201 | 6.375
32 | Betonnen binnenwanden | 1.13 | 12FS |  | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 3145.8401 | 0 | 0 | 3145.8401 | 6.375
14 | Wederaanvulling-buiten | 1.14 | 12FS | FS15 | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 6072.3398 | 0 | 0 | 6072.3398 | 2.375
15 | Structuurelementen-staal | 1.15 | 14FS | FS16 | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 80027.8281 | 0 | 0 | 80027.8281 | 4.375
16 | Structuurelementen-gewapend beton | 1.16 | 15FS | FS18 | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 86174.0078 | 0 | 0 | 86174.0078 | 4.375
33 | Dakstructuur | 1.17 | 12FS |  | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 24820.1094 | 0 | 0 | 24820.1094 | 6.375
18 | Dakwerken | 1.18 | 16FS | FS19-1w | 2010-12-20 08:00 | 2011-01-17 17:00 | 10d |  | 0 | 60579.8086 | 0 | 0 | 60579.8086 | 28.375
19 | Buitenramen, -deuren, -poorten | 1.19 | 18FS-1w | FS20-1w | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 15649.6699 | 0 | 0 | 15649.6699 | 13.375
20 | Gevelbekledingen | 1.20 | 19FS-1w | FS23-1w;FS34;FS35 | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 24598.5195 | 0 | 0 | 24598.5195 | 13.375
34 | Elektrische windzeilen | 1.21 | 20FS |  | 2011-02-01 08:00 | 2011-02-14 17:00 | 10d |  | 0 | 7995.0898 | 0 | 0 | 7995.0898 | 13.375
35 | Poort melkveestal | 1.22 | 20FS |  | 2011-02-01 08:00 | 2011-02-21 17:00 | 15d |  | 0 | 20107.6797 | 0 | 0 | 20107.6797 | 20.375
23 | Rioleringen | 1.23 | 20FS-1w | FS24 | 2011-01-25 08:00 | 2011-02-07 17:00 | 10d |  | 0 | 35762.7383 | 0 | 0 | 35762.7383 | 13.375
24 | Omgevingswerken | 1.24 | 23FS | FS30 | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 30891.0898 | 0 | 0 | 30891.0898 | 27.375
26 | Bedrijfsvloeren | 1.25 |  | FS27 | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 2350.3601 | 0 | 0 | 2350.3601 | 6.375
27 | Hekkens | 1.26 | 26FS | SS28;SS29 | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 58538.5391 | 0 | 0 | 58538.5391 | 20.375
28 | Sanitair | 1.27 | 27SS | FS30 | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 45095.5898 | 0 | 0 | 45095.5898 | 27.375
29 | Brandbestrijding | 1.28 | 27SS | FS30 | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 1669.95 | 0 | 0 | 1669.95 | 27.375
30 | Einde | 1.29 | 24FS;28FS;29FS |  | 2011-03-07 17:00 | 2011-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Criticality Index | Significance Index | Schedule Sensitivity Index | Cruciality Index (CRI-r) | Cruciality Index (CRI-rho) | Cruciality Index (CRI-tau) | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Young Cattle Barn | 920h | [10 empty] | 99 | 100 | 101
1 | Begin | 0 | standard - symmetric | 80 | 100 | 120 | 100% | 0% | 0% | 0% | 50% | 100% | 80 | 100 | 120
2 | Werfinstallatie | 80h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 23% | 13% | 11% | 2% | 80 | 100 | 120
3 | Afbraak jongveestal | 40h | standard - symmetric | 80 | 100 | 120 | 66% | 95% | 8% | 1% | 2% | 12% | 80 | 100 | 120
31 | Bijkomende sloopwerken | 120h | standard - symmetric | 80 | 100 | 120 | 0% | 13% | 0% | 6% | 10% | 2% | 80 | 100 | 120
5 | Omleggen elektrische kabel | 8h | standard - symmetric | 80 | 100 | 120 | 0% | 19% | 0% | 2% | 8% | 39% | 80 | 100 | 120
6 | Grondwerken | 40h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 12% | 9% | 10% | 16% | 80 | 100 | 120
7 | Aanvulling afbraak jongveestal | 40h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 12% | 14% | 6% | 5% | 80 | 100 | 120
8 | Plaatfundering-ondergronds | 80h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 24% | 18% | 14% | 5% | 80 | 100 | 120
9 | Funderingswanden | 160h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 49% | 42% | 39% | 23% | 80 | 100 | 120
10 | Draagvloeren | 80h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 26% | 22% | 26% | 12% | 80 | 100 | 120
11 | Wederaanvulling-binnen | 16h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 4% | 7% | 7% | 22% | 80 | 100 | 120
12 | Plaatfundering op volle grond | 40h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 13% | 24% | 22% | 7% | 80 | 100 | 120
32 | Betonnen binnenwanden | 40h | standard - symmetric | 80 | 100 | 120 | 0% | 9% | 0% | 16% | 18% | 3% | 80 | 100 | 120
14 | Wederaanvulling-buiten | 24h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 8% | 13% | 14% | 4% | 80 | 100 | 120
15 | Structuurelementen-staal | 40h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 11% | 0% | 4% | 13% | 80 | 100 | 120
16 | Structuurelementen-gewapend beton | 40h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 12% | 24% | 27% | 9% | 80 | 100 | 120
33 | Dakstructuur | 40h | standard - symmetric | 80 | 100 | 120 | 0% | 9% | 0% | 23% | 23% | 24% | 80 | 100 | 120
18 | Dakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 28% | 23% | 20% | 9% | 80 | 100 | 120
19 | Buitenramen, -deuren, -poorten | 80h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 24% | 28% | 28% | 14% | 80 | 100 | 120
20 | Gevelbekledingen | 80h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 24% | 28% | 26% | 12% | 80 | 100 | 120
34 | Elektrische windzeilen | 80h | standard - symmetric | 80 | 100 | 120 | 0% | 40% | 0% | 1% | 1% | 5% | 80 | 100 | 120
35 | Poort melkveestal | 120h | standard - symmetric | 80 | 100 | 120 | 0% | 60% | 0% | 10% | 14% | 7% | 80 | 100 | 120
23 | Rioleringen | 80h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 26% | 47% | 46% | 28% | 80 | 100 | 120
24 | Omgevingswerken | 160h | standard - symmetric | 80 | 100 | 120 | 100% | 100% | 49% | 54% | 54% | 34% | 80 | 100 | 120
26 | Bedrijfsvloeren | 40h | standard - symmetric | 80 | 100 | 120 | 0% | 5% | 0% | 23% | 20% | 23% | 80 | 100 | 120
27 | Hekkens | 120h | standard - symmetric | 80 | 100 | 120 | 0% | 14% | 0% | 11% | 7% | 2% | 80 | 100 | 120
28 | Sanitair | 160h | standard - symmetric | 80 | 100 | 120 | 0% | 18% | 0% | 1% | 1% | 2% | 80 | 100 | 120
29 | Brandbestrijding | 160h | standard - symmetric | 80 | 100 | 120 | 0% | 18% | 0% | 15% | 15% | 13% | 80 | 100 | 120
30 | Einde | 0 | standard - symmetric | 80 | 100 | 120 | 100% | 0% | 0% | 0% | 50% | 100% | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2010-09-20 17:00 |  | TP Name | 20/09, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn | 2010-09-08 08:00 | 2011-03-07 17:00 | 115d |  |  | 818439.9918 |  |  | 818439.9918 |  | 9d | [5 empty] | 46883.88 |  | 5.689% |  | 46563.23 | 91379.1094
1 | Begin | 2010-09-08 08:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 12659.2598 | 0 | 0 | 12659.2598 | 2010-09-08 08:00 | 10d | 12659.2598 | 0 | 1d | 0 | 0 | 12659.2598 | 0 | 90.91% | Started | 12659.2598 | 12659.2598 | 100 | 100 | 90.9091 | 100 | 100 | 90.9091
3 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-09-13 08:00 | 10d | 7491.3901 | 0 | 4d | 320.65 | 0 | 7812.0401 | 0 | 71.43% | Started | 7491.3901 | 7491.3901 | 100 | 200 | 71.4286 | 100 | 104.2802 | 71.4286
31 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-28 17:00 | 15d |  | 0 | 22474.1797 | 0 | 0 | 22474.1797 |  | 0 | 0 | 22474.1797 | 15d | 0 | 0 | 0 | 22474.1797 | 0% | Not Started | 0 | 22474.1797 | 100 |  | 0 | 100 |  | 0
5 | Omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 26412.5801 | 0 | 0 | 26412.5801 | 2010-09-13 08:00 | 3d | 26412.5801 | 0 | 0 | 0 | 0 | 26412.5801 | 0 | 100% | Finished | 26412.5801 | 26412.5801 | 100 | 300 | 100 | 100 | 100 | 100
6 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 14850.3096 | 0 | 0 | 14850.3096 |  | 0 | 0 | 14850.3096 | 5d | 0 | 0 | 0 | 14850.3096 | 0% | Not Started | 0 | 14850.3096 | 100 |  | 0 | 100 |  | 0
7 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 |  | 0 | 0 | 7491.3901 | 5d | 0 | 0 | 0 | 7491.3901 | 0% | Not Started | 0 | 7491.3901 | 100 |  | 0 | 100 |  | 0
8 | Plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 31783.8691 | 0 | 0 | 31783.8691 |  | 0 | 0 | 31783.8691 | 10d | 0 | 0 | 0 | 31783.8691 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Funderingswanden | 2010-10-06 08:00 | 2010-11-03 17:00 | 20d |  | 0 | 118171.1719 | 0 | 0 | 118171.1719 |  | 0 | 0 | 118171.1719 | 20d | 0 | 0 | 0 | 118171.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Draagvloeren | 2010-11-04 08:00 | 2010-11-19 17:00 | 10d |  | 0 | 63201.1914 | 0 | 0 | 63201.1914 |  | 0 | 0 | 63201.1914 | 10d | 0 | 0 | 0 | 63201.1914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 437.87 | 0 | 0 | 437.87 |  | 0 | 0 | 437.87 | 2d | 0 | 0 | 0 | 437.87 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 9987.6201 | 0 | 0 | 9987.6201 |  | 0 | 0 | 9987.6201 | 5d | 0 | 0 | 0 | 9987.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Betonnen binnenwanden | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 3145.8401 | 0 | 0 | 3145.8401 |  | 0 | 0 | 3145.8401 | 5d | 0 | 0 | 0 | 3145.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 6072.3398 | 0 | 0 | 6072.3398 |  | 0 | 0 | 6072.3398 | 3d | 0 | 0 | 0 | 6072.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 80027.8281 | 0 | 0 | 80027.8281 |  | 0 | 0 | 80027.8281 | 5d | 0 | 0 | 0 | 80027.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Structuurelementen-gewapend beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 86174.0078 | 0 | 0 | 86174.0078 |  | 0 | 0 | 86174.0078 | 5d | 0 | 0 | 0 | 86174.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakstructuur | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 24820.1094 | 0 | 0 | 24820.1094 |  | 0 | 0 | 24820.1094 | 5d | 0 | 0 | 0 | 24820.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Dakwerken | 2010-12-20 08:00 | 2011-01-17 17:00 | 10d |  | 0 | 60579.8086 | 0 | 0 | 60579.8086 |  | 0 | 0 | 60579.8086 | 10d | 0 | 0 | 0 | 60579.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 15649.6699 | 0 | 0 | 15649.6699 |  | 0 | 0 | 15649.6699 | 10d | 0 | 0 | 0 | 15649.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gevelbekledingen | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 24598.5195 | 0 | 0 | 24598.5195 |  | 0 | 0 | 24598.5195 | 10d | 0 | 0 | 0 | 24598.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Elektrische windzeilen | 2011-02-01 08:00 | 2011-02-14 17:00 | 10d |  | 0 | 7995.0898 | 0 | 0 | 7995.0898 |  | 0 | 0 | 7995.0898 | 10d | 0 | 0 | 0 | 7995.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Poort melkveestal | 2011-02-01 08:00 | 2011-02-21 17:00 | 15d |  | 0 | 20107.6797 | 0 | 0 | 20107.6797 |  | 0 | 0 | 20107.6797 | 15d | 0 | 0 | 0 | 20107.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Rioleringen | 2011-01-25 08:00 | 2011-02-07 17:00 | 10d |  | 0 | 35762.7383 | 0 | 0 | 35762.7383 |  | 0 | 0 | 35762.7383 | 10d | 0 | 0 | 0 | 35762.7383 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Omgevingswerken | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 30891.0898 | 0 | 0 | 30891.0898 |  | 0 | 0 | 30891.0898 | 20d | 0 | 0 | 0 | 30891.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 2350.3601 | 0 | 0 | 2350.3601 |  | 0 | 0 | 2350.3601 | 5d | 0 | 0 | 0 | 2350.3601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 58538.5391 | 0 | 0 | 58538.5391 |  | 0 | 0 | 58538.5391 | 15d | 0 | 0 | 0 | 58538.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 45095.5898 | 0 | 0 | 45095.5898 |  | 0 | 0 | 45095.5898 | 20d | 0 | 0 | 0 | 45095.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 1669.95 | 0 | 0 | 1669.95 |  | 0 | 0 | 1669.95 | 20d | 0 | 0 | 0 | 1669.95 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Einde | 2011-03-07 17:00 | 2011-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2010-11-09 17:00 |  | TP Name | 09/11, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn | 2010-09-08 08:00 | 2011-03-07 17:00 | 115d |  |  | 818439.9918 |  |  | 818439.9918 |  | 44d | [5 empty] | 240403.5014 |  | 25.83% |  | 211368.5806 | 304535.3418
1 | Begin | 2010-09-08 08:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 12659.2598 | 0 | 0 | 12659.2598 | 2010-09-08 08:00 | 10d | 12659.2598 | 0 | 0 | 0 | 0 | 12659.2598 | 0 | 100% | Finished | 12659.2598 | 12659.2598 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-09-13 08:00 | 15d | 7491.3901 | 0 | 0 | 384.78 | 0 | 7876.1701 | 0 | 100% | Finished | 7491.3901 | 7491.3901 | 100 | 300 | 100 | 100 | 105.1363 | 100
31 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-28 17:00 | 15d |  | 0 | 22474.1797 | 0 | 0 | 22474.1797 |  | 0 | 0 | 22474.1797 | 15d | 0 | 0 | 0 | 22474.1797 | 0% | Not Started | 0 | 22474.1797 | 100 |  | 0 | 100 |  | 0
5 | Omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 26412.5801 | 0 | 0 | 26412.5801 | 2010-09-13 08:00 | 3d | 26412.5801 | 0 | 0 | 0 | 0 | 26412.5801 | 0 | 100% | Finished | 26412.5801 | 26412.5801 | 100 | 300 | 100 | 100 | 100 | 100
6 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 14850.3096 | 0 | 0 | 14850.3096 | 2010-09-30 08:00 | 4d | 14850.3096 | 0 | 0 | 1956.22 | 0 | 16806.5295 | 0 | 100% | Finished | 14850.3096 | 14850.3096 | 100 | 80 | 100 | 100 | 113.1729 | 100
7 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 |  | 0 | 0 | 7491.3901 | 5d | 0 | 0 | 0 | 7491.3901 | 0% | Not Started | 0 | 7491.3901 | 100 |  | 0 | 100 |  | 0
8 | Plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 31783.8691 | 0 | 0 | 31783.8691 | 2010-10-14 08:00 | 8d | 31783.8691 | 0 | 0 | 8309.29 | 0 | 40093.1592 | 0 | 100% | Finished | 31783.8691 | 31783.8691 | 100 | 80 | 100 | 100 | 126.1431 | 100
9 | Funderingswanden | 2010-10-06 08:00 | 2010-11-03 17:00 | 20d |  | 0 | 118171.1719 | 0 | 0 | 118171.1719 | 2010-11-02 08:00 | 17d | 118171.1719 | 0 | 11d | 18384.6309 | 0 | 136555.8027 | 0 | 60.71% | Started | 118171.1719 | 118171.1719 | 100 | 85 | 60.7143 | 100 | 115.5576 | 60.7143
10 | Draagvloeren | 2010-11-04 08:00 | 2010-11-19 17:00 | 10d |  | 0 | 63201.1914 | 0 | 0 | 63201.1914 |  | 0 | 0 | 63201.1914 | 10d | 0 | 0 | 0 | 63201.1914 | 0% | Not Started | 0 | 63201.1914 | 100 |  | 0 | 100 |  | 0
11 | Wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 437.87 | 0 | 0 | 437.87 |  | 0 | 0 | 437.87 | 2d | 0 | 0 | 0 | 437.87 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 9987.6201 | 0 | 0 | 9987.6201 |  | 0 | 0 | 9987.6201 | 5d | 0 | 0 | 0 | 9987.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Betonnen binnenwanden | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 3145.8401 | 0 | 0 | 3145.8401 |  | 0 | 0 | 3145.8401 | 5d | 0 | 0 | 0 | 3145.8401 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 6072.3398 | 0 | 0 | 6072.3398 |  | 0 | 0 | 6072.3398 | 3d | 0 | 0 | 0 | 6072.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 80027.8281 | 0 | 0 | 80027.8281 |  | 0 | 0 | 80027.8281 | 5d | 0 | 0 | 0 | 80027.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Structuurelementen-gewapend beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 86174.0078 | 0 | 0 | 86174.0078 |  | 0 | 0 | 86174.0078 | 5d | 0 | 0 | 0 | 86174.0078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Dakstructuur | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 24820.1094 | 0 | 0 | 24820.1094 |  | 0 | 0 | 24820.1094 | 5d | 0 | 0 | 0 | 24820.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Dakwerken | 2010-12-20 08:00 | 2011-01-17 17:00 | 10d |  | 0 | 60579.8086 | 0 | 0 | 60579.8086 |  | 0 | 0 | 60579.8086 | 10d | 0 | 0 | 0 | 60579.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 15649.6699 | 0 | 0 | 15649.6699 |  | 0 | 0 | 15649.6699 | 10d | 0 | 0 | 0 | 15649.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Gevelbekledingen | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 24598.5195 | 0 | 0 | 24598.5195 |  | 0 | 0 | 24598.5195 | 10d | 0 | 0 | 0 | 24598.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Elektrische windzeilen | 2011-02-01 08:00 | 2011-02-14 17:00 | 10d |  | 0 | 7995.0898 | 0 | 0 | 7995.0898 |  | 0 | 0 | 7995.0898 | 10d | 0 | 0 | 0 | 7995.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Poort melkveestal | 2011-02-01 08:00 | 2011-02-21 17:00 | 15d |  | 0 | 20107.6797 | 0 | 0 | 20107.6797 |  | 0 | 0 | 20107.6797 | 15d | 0 | 0 | 0 | 20107.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Rioleringen | 2011-01-25 08:00 | 2011-02-07 17:00 | 10d |  | 0 | 35762.7383 | 0 | 0 | 35762.7383 |  | 0 | 0 | 35762.7383 | 10d | 0 | 0 | 0 | 35762.7383 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Omgevingswerken | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 30891.0898 | 0 | 0 | 30891.0898 |  | 0 | 0 | 30891.0898 | 20d | 0 | 0 | 0 | 30891.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 2350.3601 | 0 | 0 | 2350.3601 |  | 0 | 0 | 2350.3601 | 5d | 0 | 0 | 0 | 2350.3601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 58538.5391 | 0 | 0 | 58538.5391 |  | 0 | 0 | 58538.5391 | 15d | 0 | 0 | 0 | 58538.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 45095.5898 | 0 | 0 | 45095.5898 |  | 0 | 0 | 45095.5898 | 20d | 0 | 0 | 0 | 45095.5898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 1669.95 | 0 | 0 | 1669.95 |  | 0 | 0 | 1669.95 | 20d | 0 | 0 | 0 | 1669.95 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Einde | 2011-03-07 17:00 | 2011-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-03-22 17:00 |  | TP Name | 22/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn | 2010-09-08 08:00 | 2011-03-07 17:00 | 115d |  |  | 818439.9918 |  |  | 818439.9918 |  | 126d | [5 empty] | 548153.8977 |  | 62.95% |  | 515200.9572 | 818439.9918
1 | Begin | 2010-09-08 08:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 12659.2598 | 0 | 0 | 12659.2598 | 2010-09-08 08:00 | 10d | 12659.2598 | 0 | 0 | 0 | 0 | 12659.2598 | 0 | 100% | Finished | 12659.2598 | 12659.2598 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-09-13 08:00 | 15d | 7491.3901 | 0 | 0 | 384.78 | 0 | 7876.1701 | 0 | 100% | Finished | 7491.3901 | 7491.3901 | 100 | 300 | 100 | 100 | 105.1363 | 100
31 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-28 17:00 | 15d |  | 0 | 22474.1797 | 0 | 0 | 22474.1797 | 2010-11-29 09:00 | 15d | 22474.1797 | 0 | 0 | 1154.34 | 0 | 23628.5197 | 0 | 100% | Finished | 22474.1797 | 22474.1797 | 100 | 100 | 100 | 100 | 105.1363 | 100
5 | Omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 26412.5801 | 0 | 0 | 26412.5801 | 2010-09-13 08:00 | 3d | 26412.5801 | 0 | 0 | 0 | 0 | 26412.5801 | 0 | 100% | Finished | 26412.5801 | 26412.5801 | 100 | 300 | 100 | 100 | 100 | 100
6 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 14850.3096 | 0 | 0 | 14850.3096 | 2010-09-30 08:00 | 4d | 14850.3096 | 0 | 0 | 2603.8201 | 0 | 17454.1296 | 0 | 100% | Finished | 14850.3096 | 14850.3096 | 100 | 80 | 100 | 100 | 117.5338 | 100
7 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-12-20 08:00 | 3d | 7491.3901 | 0 | 0 | 384.78 | 0 | 7876.1701 | 0 | 100% | Finished | 7491.3901 | 7491.3901 | 100 | 60 | 100 | 100 | 105.1363 | 100
8 | Plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 31783.8691 | 0 | 0 | 31783.8691 | 2010-10-14 08:00 | 8d | 31783.8691 | 0 | 0 | 8219.2002 | 0 | 40003.0693 | 0 | 100% | Finished | 31783.8691 | 31783.8691 | 100 | 80 | 100 | 100 | 125.8597 | 100
9 | Funderingswanden | 2010-10-06 08:00 | 2010-11-03 17:00 | 20d |  | 0 | 118171.1719 | 0 | 0 | 118171.1719 | 2010-11-02 08:00 | 17d | 118171.1719 | 0 | 11d | 17294.8105 | 0 | 135465.9824 | 0 | 60.71% | Started | 118171.1719 | 118171.1719 | 100 | 85 | 60.7143 | 100 | 114.6354 | 60.7143
10 | Draagvloeren | 2010-11-04 08:00 | 2010-11-19 17:00 | 10d |  | 0 | 63201.1914 | 0 | 0 | 63201.1914 | 2011-01-17 08:00 | 5d | 63201.1914 | 0 | 0 | -7158.0801 | 0 | 56043.1113 | 0 | 100% | Finished | 63201.1914 | 63201.1914 | 100 | 50 | 100 | 100 | 88.6741 | 100
11 | Wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 437.87 | 0 | 0 | 437.87 | 2011-02-14 08:00 | 5d | 437.87 | 0 | 0 | -304.16 | 0 | 133.71 | 0 | 100% | Finished | 437.87 | 437.87 | 100 | 250 | 100 | 100 | 30.5365 | 100
12 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 9987.6201 | 0 | 0 | 9987.6201 | 2011-03-07 08:00 | 10d | 9987.6201 | 0 | 0 | -702.94 | 0 | 9284.6801 | 0 | 100% | Finished | 9987.6201 | 9987.6201 | 100 | 200 | 100 | 100 | 92.9619 | 100
32 | Betonnen binnenwanden | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 3145.8401 | 0 | 0 | 3145.8401 | 2011-03-21 08:00 | 5d | 3145.8401 | 0 | 3d | -313.9 | 0 | 2831.9401 | 0 | 62.5% | Started | 3145.8401 | 3145.8401 | 100 | 100 | 62.5 | 100 | 90.0217 | 62.5
14 | Wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 6072.3398 | 0 | 0 | 6072.3398 | 2011-02-14 08:00 | 5d | 6072.3398 | 0 | 0 | 423.68 | 0 | 6496.0198 | 0 | 100% | Finished | 6072.3398 | 6072.3398 | 100 | 166.6667 | 100 | 100 | 106.9772 | 100
15 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 80027.8281 | 0 | 0 | 80027.8281 | 2011-02-21 08:00 | 10d | 80027.8281 | 0 | 0 | -4731.54 | 0 | 75296.2881 | 0 | 100% | Finished | 80027.8281 | 80027.8281 | 100 | 200 | 100 | 100 | 94.0876 | 100
16 | Structuurelementen-gewapend beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 86174.0078 | 0 | 0 | 86174.0078 | 2011-03-07 08:00 | 5d | 86174.0078 | 0 | 0 | 20274.4199 | 0 | 106448.4277 | 0 | 100% | Finished | 86174.0078 | 86174.0078 | 100 | 100 | 100 | 100 | 123.5273 | 100
33 | Dakstructuur | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 24820.1094 | 0 | 0 | 24820.1094 | 2011-03-21 08:00 | 5d | 24820.1094 | 0 | 3d | -4576.27 | 0 | 20243.8394 | 0 | 62.5% | Started | 24820.1094 | 24820.1094 | 100 | 100 | 62.5 | 100 | 81.5622 | 62.5
18 | Dakwerken | 2010-12-20 08:00 | 2011-01-17 17:00 | 10d |  | 0 | 60579.8086 | 0 | 0 | 60579.8086 |  | 0 | 0 | 60579.8086 | 10d | 0 | 0 | 0 | 60579.8086 | 0% | Not Started | 0 | 60579.8086 | 100 |  | 0 | 100 |  | 0
19 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 15649.6699 | 0 | 0 | 15649.6699 |  | 0 | 0 | 15649.6699 | 10d | 0 | 0 | 0 | 15649.6699 | 0% | Not Started | 0 | 15649.6699 | 100 |  | 0 | 100 |  | 0
20 | Gevelbekledingen | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 24598.5195 | 0 | 0 | 24598.5195 |  | 0 | 0 | 24598.5195 | 10d | 0 | 0 | 0 | 24598.5195 | 0% | Not Started | 0 | 24598.5195 | 100 |  | 0 | 100 |  | 0
34 | Elektrische windzeilen | 2011-02-01 08:00 | 2011-02-14 17:00 | 10d |  | 0 | 7995.0898 | 0 | 0 | 7995.0898 |  | 0 | 0 | 7995.0898 | 10d | 0 | 0 | 0 | 7995.0898 | 0% | Not Started | 0 | 7995.0898 | 100 |  | 0 | 100 |  | 0
35 | Poort melkveestal | 2011-02-01 08:00 | 2011-02-21 17:00 | 15d |  | 0 | 20107.6797 | 0 | 0 | 20107.6797 |  | 0 | 0 | 20107.6797 | 15d | 0 | 0 | 0 | 20107.6797 | 0% | Not Started | 0 | 20107.6797 | 100 |  | 0 | 100 |  | 0
23 | Rioleringen | 2011-01-25 08:00 | 2011-02-07 17:00 | 10d |  | 0 | 35762.7383 | 0 | 0 | 35762.7383 |  | 0 | 0 | 35762.7383 | 10d | 0 | 0 | 0 | 35762.7383 | 0% | Not Started | 0 | 35762.7383 | 100 |  | 0 | 100 |  | 0
24 | Omgevingswerken | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 30891.0898 | 0 | 0 | 30891.0898 |  | 0 | 0 | 30891.0898 | 20d | 0 | 0 | 0 | 30891.0898 | 0% | Not Started | 0 | 30891.0898 | 100 |  | 0 | 100 |  | 0
26 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 2350.3601 | 0 | 0 | 2350.3601 |  | 0 | 0 | 2350.3601 | 5d | 0 | 0 | 0 | 2350.3601 | 0% | Not Started | 0 | 2350.3601 | 100 |  | 0 | 100 |  | 0
27 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 58538.5391 | 0 | 0 | 58538.5391 |  | 0 | 0 | 58538.5391 | 15d | 0 | 0 | 0 | 58538.5391 | 0% | Not Started | 0 | 58538.5391 | 100 |  | 0 | 100 |  | 0
28 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 45095.5898 | 0 | 0 | 45095.5898 |  | 0 | 0 | 45095.5898 | 20d | 0 | 0 | 0 | 45095.5898 | 0% | Not Started | 0 | 45095.5898 | 100 |  | 0 | 100 |  | 0
29 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 1669.95 | 0 | 0 | 1669.95 |  | 0 | 0 | 1669.95 | 20d | 0 | 0 | 0 | 1669.95 | 0% | Not Started | 0 | 1669.95 | 100 |  | 0 | 100 |  | 0
30 | Einde | 2011-03-07 17:00 | 2011-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-05-10 17:00 |  | TP Name | 10/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn | 2010-09-08 08:00 | 2011-03-07 17:00 | 115d |  |  | 818439.9918 |  |  | 818439.9918 |  | 161d | [5 empty] | 702797.5936 |  | 82.42% |  | 674567.4943 | 818439.9918
1 | Begin | 2010-09-08 08:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 12659.2598 | 0 | 0 | 12659.2598 | 2010-09-08 08:00 | 10d | 12659.2598 | 0 | 0 | 0 | 0 | 12659.2598 | 0 | 100% | Finished | 12659.2598 | 12659.2598 | 100 | 100 | 100 | 100 | 100 | 100
3 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-09-13 08:00 | 15d | 7491.3901 | 0 | 0 | 384.78 | 0 | 7876.1701 | 0 | 100% | Finished | 7491.3901 | 7491.3901 | 100 | 300 | 100 | 100 | 105.1363 | 100
31 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-28 17:00 | 15d |  | 0 | 22474.1797 | 0 | 0 | 22474.1797 | 2010-11-29 09:00 | 15d | 22474.1797 | 0 | 0 | 1154.34 | 0 | 23628.5197 | 0 | 100% | Finished | 22474.1797 | 22474.1797 | 100 | 100 | 100 | 100 | 105.1363 | 100
5 | Omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 26412.5801 | 0 | 0 | 26412.5801 | 2010-09-13 08:00 | 3d | 26412.5801 | 0 | 0 | 0 | 0 | 26412.5801 | 0 | 100% | Finished | 26412.5801 | 26412.5801 | 100 | 300 | 100 | 100 | 100 | 100
6 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 14850.3096 | 0 | 0 | 14850.3096 | 2010-09-30 08:00 | 4d | 14850.3096 | 0 | 0 | 2603.8201 | 0 | 17454.1296 | 0 | 100% | Finished | 14850.3096 | 14850.3096 | 100 | 80 | 100 | 100 | 117.5338 | 100
7 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-12-20 08:00 | 3d | 7491.3901 | 0 | 0 | 384.78 | 0 | 7876.1701 | 0 | 100% | Finished | 7491.3901 | 7491.3901 | 100 | 60 | 100 | 100 | 105.1363 | 100
8 | Plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 31783.8691 | 0 | 0 | 31783.8691 | 2010-10-14 08:00 | 8d | 31783.8691 | 0 | 0 | 8219.2002 | 0 | 40003.0693 | 0 | 100% | Finished | 31783.8691 | 31783.8691 | 100 | 80 | 100 | 100 | 125.8597 | 100
9 | Funderingswanden | 2010-10-06 08:00 | 2010-11-03 17:00 | 20d |  | 0 | 118171.1719 | 0 | 0 | 118171.1719 | 2010-11-02 08:00 | 17d | 118171.1719 | 0 | 0 | 16619.2891 | 0 | 134790.4609 | 0 | 100% | Finished | 118171.1719 | 118171.1719 | 100 | 85 | 100 | 100 | 114.0637 | 100
10 | Draagvloeren | 2010-11-04 08:00 | 2010-11-19 17:00 | 10d |  | 0 | 63201.1914 | 0 | 0 | 63201.1914 | 2011-01-17 08:00 | 5d | 63201.1914 | 0 | 0 | -7158.0801 | 0 | 56043.1113 | 0 | 100% | Finished | 63201.1914 | 63201.1914 | 100 | 50 | 100 | 100 | 88.6741 | 100
11 | Wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 437.87 | 0 | 0 | 437.87 | 2011-02-14 08:00 | 5d | 437.87 | 0 | 0 | -304.16 | 0 | 133.71 | 0 | 100% | Finished | 437.87 | 437.87 | 100 | 250 | 100 | 100 | 30.5365 | 100
12 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 9987.6201 | 0 | 0 | 9987.6201 | 2011-03-07 08:00 | 10d | 9987.6201 | 0 | 0 | -702.94 | 0 | 9284.6801 | 0 | 100% | Finished | 9987.6201 | 9987.6201 | 100 | 200 | 100 | 100 | 92.9619 | 100
32 | Betonnen binnenwanden | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 3145.8401 | 0 | 0 | 3145.8401 | 2011-03-21 08:00 | 10d | 3145.8401 | 0 | 0 | -482.78 | 0 | 2663.0601 | 0 | 100% | Finished | 3145.8401 | 3145.8401 | 100 | 200 | 100 | 100 | 84.6534 | 100
14 | Wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 6072.3398 | 0 | 0 | 6072.3398 | 2011-02-14 08:00 | 5d | 6072.3398 | 0 | 0 | 423.68 | 0 | 6496.0198 | 0 | 100% | Finished | 6072.3398 | 6072.3398 | 100 | 166.6667 | 100 | 100 | 106.9772 | 100
15 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 80027.8281 | 0 | 0 | 80027.8281 | 2011-02-21 08:00 | 10d | 80027.8281 | 0 | 0 | -4731.54 | 0 | 75296.2881 | 0 | 100% | Finished | 80027.8281 | 80027.8281 | 100 | 200 | 100 | 100 | 94.0876 | 100
16 | Structuurelementen-gewapend beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 86174.0078 | 0 | 0 | 86174.0078 | 2011-03-07 08:00 | 5d | 86174.0078 | 0 | 0 | 20274.4199 | 0 | 106448.4277 | 0 | 100% | Finished | 86174.0078 | 86174.0078 | 100 | 100 | 100 | 100 | 123.5273 | 100
33 | Dakstructuur | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 24820.1094 | 0 | 0 | 24820.1094 | 2011-03-21 08:00 | 5d | 24820.1094 | 0 | 0 | -4576.27 | 0 | 20243.8394 | 0 | 100% | Finished | 24820.1094 | 24820.1094 | 100 | 100 | 100 | 100 | 81.5622 | 100
18 | Dakwerken | 2010-12-20 08:00 | 2011-01-17 17:00 | 10d |  | 0 | 60579.8086 | 0 | 0 | 60579.8086 | 2011-04-22 08:00 | 6d | 60579.8086 | 0 | 0 | -8154.7798 | 0 | 52425.0288 | 0 | 100% | Finished | 60579.8086 | 60579.8086 | 100 | 60 | 100 | 100 | 86.5388 | 100
19 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 15649.6699 | 0 | 0 | 15649.6699 | 2011-04-14 08:00 | 4d | 15649.6699 | 0 | 0 | -1015 | 0 | 14634.6699 | 0 | 100% | Finished | 15649.6699 | 15649.6699 | 100 | 40 | 100 | 100 | 93.5142 | 100
20 | Gevelbekledingen | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 24598.5195 | 0 | 0 | 24598.5195 | 2011-05-04 08:00 | 9d | 24598.5195 | 0 | 4d | -70.43 | 0 | 24528.0895 | 0 | 69.23% | Started | 24598.5195 | 24598.5195 | 100 | 90 | 69.2308 | 100 | 99.7137 | 69.2308
34 | Elektrische windzeilen | 2011-02-01 08:00 | 2011-02-14 17:00 | 10d |  | 0 | 7995.0898 | 0 | 0 | 7995.0898 |  | 0 | 0 | 7995.0898 | 10d | 0 | 0 | 0 | 7995.0898 | 0% | Not Started | 0 | 7995.0898 | 100 |  | 0 | 100 |  | 0
35 | Poort melkveestal | 2011-02-01 08:00 | 2011-02-21 17:00 | 15d |  | 0 | 20107.6797 | 0 | 0 | 20107.6797 |  | 0 | 0 | 20107.6797 | 15d | 0 | 0 | 0 | 20107.6797 | 0% | Not Started | 0 | 20107.6797 | 100 |  | 0 | 100 |  | 0
23 | Rioleringen | 2011-01-25 08:00 | 2011-02-07 17:00 | 10d |  | 0 | 35762.7383 | 0 | 0 | 35762.7383 |  | 0 | 0 | 35762.7383 | 10d | 0 | 0 | 0 | 35762.7383 | 0% | Not Started | 0 | 35762.7383 | 100 |  | 0 | 100 |  | 0
24 | Omgevingswerken | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 30891.0898 | 0 | 0 | 30891.0898 |  | 0 | 0 | 30891.0898 | 20d | 0 | 0 | 0 | 30891.0898 | 0% | Not Started | 0 | 30891.0898 | 100 |  | 0 | 100 |  | 0
26 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 2350.3601 | 0 | 0 | 2350.3601 |  | 0 | 0 | 2350.3601 | 5d | 0 | 0 | 0 | 2350.3601 | 0% | Not Started | 0 | 2350.3601 | 100 |  | 0 | 100 |  | 0
27 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 58538.5391 | 0 | 0 | 58538.5391 | 2011-05-04 08:00 | 10d | 58538.5391 | 0 | 5d | 5361.77 | 0 | 63900.3091 | 0 | 66.67% | Started | 58538.5391 | 58538.5391 | 100 | 66.6667 | 66.6667 | 100 | 109.1594 | 66.6667
28 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 45095.5898 | 0 | 0 | 45095.5898 |  | 0 | 0 | 45095.5898 | 20d | 0 | 0 | 0 | 45095.5898 | 0% | Not Started | 0 | 45095.5898 | 100 |  | 0 | 100 |  | 0
29 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 1669.95 | 0 | 0 | 1669.95 |  | 0 | 0 | 1669.95 | 20d | 0 | 0 | 0 | 1669.95 | 0% | Not Started | 0 | 1669.95 | 100 |  | 0 | 100 |  | 0
30 | Einde | 2011-03-07 17:00 | 2011-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-06-30 17:00 |  | TP Name | 30/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Young Cattle Barn | 2010-09-08 08:00 | 2011-03-07 17:00 | 115d |  |  | 818439.9918 |  |  | 818439.9918 |  | 188d | [5 empty] | 879853.1711 |  | 100% |  | 818439.9918 | 818439.9918
1 | Begin | 2010-09-08 08:00 | 2010-09-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-09-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Werfinstallatie | 2010-09-08 08:00 | 2010-09-21 17:00 | 10d |  | 0 | 12659.2598 | 0 | 0 | 12659.2598 | 2010-09-08 08:00 | 10d | 12659.2598 | 0 | 0 | 9272.8896 | 0 | 21932.1494 | 0 | 100% | Finished | 12659.2598 | 12659.2598 | 100 | 100 | 100 | 100 | 173.2499 | 100
3 | Afbraak jongveestal | 2010-09-08 08:00 | 2010-09-14 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-09-13 08:00 | 15d | 7491.3901 | 0 | 0 | 486.36 | 0 | 7977.7501 | 0 | 100% | Finished | 7491.3901 | 7491.3901 | 100 | 300 | 100 | 100 | 106.4923 | 100
31 | Bijkomende sloopwerken | 2010-09-08 08:00 | 2010-09-28 17:00 | 15d |  | 0 | 22474.1797 | 0 | 0 | 22474.1797 | 2010-11-29 09:00 | 15d | 22474.1797 | 0 | 0 | 1459.09 | 0 | 23933.2697 | 0 | 100% | Finished | 22474.1797 | 22474.1797 | 100 | 100 | 100 | 100 | 106.4923 | 100
5 | Omleggen elektrische kabel | 2010-09-08 08:00 | 2010-09-08 17:00 | 1d |  | 0 | 26412.5801 | 0 | 0 | 26412.5801 | 2010-09-13 08:00 | 3d | 26412.5801 | 0 | 0 | -383.98 | 0 | 26028.6001 | 0 | 100% | Finished | 26412.5801 | 26412.5801 | 100 | 300 | 100 | 100 | 98.5462 | 100
6 | Grondwerken | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 14850.3096 | 0 | 0 | 14850.3096 | 2010-09-30 08:00 | 4d | 14850.3096 | 0 | 0 | 15026.79 | 0 | 29877.0996 | 0 | 100% | Finished | 14850.3096 | 14850.3096 | 100 | 80 | 100 | 100 | 201.1884 | 100
7 | Aanvulling afbraak jongveestal | 2010-09-15 08:00 | 2010-09-21 17:00 | 5d |  | 0 | 7491.3901 | 0 | 0 | 7491.3901 | 2010-12-20 08:00 | 3d | 7491.3901 | 0 | 0 | 486.36 | 0 | 7977.7501 | 0 | 100% | Finished | 7491.3901 | 7491.3901 | 100 | 60 | 100 | 100 | 106.4923 | 100
8 | Plaatfundering-ondergronds | 2010-09-22 08:00 | 2010-10-05 17:00 | 10d |  | 0 | 31783.8691 | 0 | 0 | 31783.8691 | 2010-10-14 08:00 | 8d | 31783.8691 | 0 | 0 | 8289.5596 | 0 | 40073.4287 | 0 | 100% | Finished | 31783.8691 | 31783.8691 | 100 | 80 | 100 | 100 | 126.081 | 100
9 | Funderingswanden | 2010-10-06 08:00 | 2010-11-03 17:00 | 20d |  | 0 | 118171.1719 | 0 | 0 | 118171.1719 | 2010-11-02 08:00 | 17d | 118171.1719 | 0 | 0 | 19921.3809 | 0 | 138092.5527 | 0 | 100% | Finished | 118171.1719 | 118171.1719 | 100 | 85 | 100 | 100 | 116.8581 | 100
10 | Draagvloeren | 2010-11-04 08:00 | 2010-11-19 17:00 | 10d |  | 0 | 63201.1914 | 0 | 0 | 63201.1914 | 2011-01-17 08:00 | 5d | 63201.1914 | 0 | 0 | 9287.6299 | 0 | 72488.8213 | 0 | 100% | Finished | 63201.1914 | 63201.1914 | 100 | 50 | 100 | 100 | 114.6953 | 100
11 | Wederaanvulling-binnen | 2010-11-22 08:00 | 2010-11-23 17:00 | 2d |  | 0 | 437.87 | 0 | 0 | 437.87 | 2011-02-14 08:00 | 5d | 437.87 | 0 | 0 | 819.02 | 0 | 1256.89 | 0 | 100% | Finished | 437.87 | 437.87 | 100 | 250 | 100 | 100 | 287.0464 | 100
12 | Plaatfundering op volle grond | 2010-11-24 08:00 | 2010-11-30 17:00 | 5d |  | 0 | 9987.6201 | 0 | 0 | 9987.6201 | 2011-03-07 08:00 | 10d | 9987.6201 | 0 | 0 | -667.76 | 0 | 9319.8601 | 0 | 100% | Finished | 9987.6201 | 9987.6201 | 100 | 200 | 100 | 100 | 93.3141 | 100
32 | Betonnen binnenwanden | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 3145.8401 | 0 | 0 | 3145.8401 | 2011-03-21 08:00 | 10d | 3145.8401 | 0 | 0 | 1512.4 | 0 | 4658.2401 | 0 | 100% | Finished | 3145.8401 | 3145.8401 | 100 | 200 | 100 | 100 | 148.0762 | 100
14 | Wederaanvulling-buiten | 2010-12-01 08:00 | 2010-12-03 17:00 | 3d |  | 0 | 6072.3398 | 0 | 0 | 6072.3398 | 2011-02-14 08:00 | 5d | 6072.3398 | 0 | 0 | 3096.29 | 0 | 9168.6299 | 0 | 100% | Finished | 6072.3398 | 6072.3398 | 100 | 166.6667 | 100 | 100 | 150.9901 | 100
15 | Structuurelementen-staal | 2010-12-06 08:00 | 2010-12-10 17:00 | 5d |  | 0 | 80027.8281 | 0 | 0 | 80027.8281 | 2011-02-21 08:00 | 10d | 80027.8281 | 0 | 0 | 1958.91 | 0 | 81986.7382 | 0 | 100% | Finished | 80027.8281 | 80027.8281 | 100 | 200 | 100 | 100 | 102.4478 | 100
16 | Structuurelementen-gewapend beton | 2010-12-13 08:00 | 2010-12-17 17:00 | 5d |  | 0 | 86174.0078 | 0 | 0 | 86174.0078 | 2011-03-07 08:00 | 5d | 86174.0078 | 0 | 0 | 19825.5098 | 0 | 105999.5176 | 0 | 100% | Finished | 86174.0078 | 86174.0078 | 100 | 100 | 100 | 100 | 123.0064 | 100
33 | Dakstructuur | 2010-12-01 08:00 | 2010-12-07 17:00 | 5d |  | 0 | 24820.1094 | 0 | 0 | 24820.1094 | 2011-03-21 08:00 | 5d | 24820.1094 | 0 | 0 | -4538.8599 | 0 | 20281.2495 | 0 | 100% | Finished | 24820.1094 | 24820.1094 | 100 | 100 | 100 | 100 | 81.713 | 100
18 | Dakwerken | 2010-12-20 08:00 | 2011-01-17 17:00 | 10d |  | 0 | 60579.8086 | 0 | 0 | 60579.8086 | 2011-04-22 08:00 | 6d | 60579.8086 | 0 | 0 | -11716.2402 | 0 | 48863.5684 | 0 | 100% | Finished | 60579.8086 | 60579.8086 | 100 | 60 | 100 | 100 | 80.6598 | 100
19 | Buitenramen, -deuren, -poorten | 2011-01-11 08:00 | 2011-01-24 17:00 | 10d |  | 0 | 15649.6699 | 0 | 0 | 15649.6699 | 2011-04-14 08:00 | 4d | 15649.6699 | 0 | 0 | -990.37 | 0 | 14659.2999 | 0 | 100% | Finished | 15649.6699 | 15649.6699 | 100 | 40 | 100 | 100 | 93.6716 | 100
20 | Gevelbekledingen | 2011-01-18 08:00 | 2011-01-31 17:00 | 10d |  | 0 | 24598.5195 | 0 | 0 | 24598.5195 | 2011-05-04 08:00 | 9d | 24598.5195 | 0 | 0 | -4432.9502 | 0 | 20165.5693 | 0 | 100% | Finished | 24598.5195 | 24598.5195 | 100 | 90 | 100 | 100 | 81.9788 | 100
34 | Elektrische windzeilen | 2011-02-01 08:00 | 2011-02-14 17:00 | 10d |  | 0 | 7995.0898 | 0 | 0 | 7995.0898 | 2011-05-16 08:00 | 5d | 7995.0898 | 0 | 0 | -956.18 | 0 | 7038.9099 | 0 | 100% | Finished | 7995.0898 | 7995.0898 | 100 | 50 | 100 | 100 | 88.0404 | 100
35 | Poort melkveestal | 2011-02-01 08:00 | 2011-02-21 17:00 | 15d |  | 0 | 20107.6797 | 0 | 0 | 20107.6797 | 2011-05-16 08:00 | 15d | 20107.6797 | 0 | 0 | -1485.5601 | 0 | 18622.1196 | 0 | 100% | Finished | 20107.6797 | 20107.6797 | 100 | 100 | 100 | 100 | 92.612 | 100
23 | Rioleringen | 2011-01-25 08:00 | 2011-02-07 17:00 | 10d |  | 0 | 35762.7383 | 0 | 0 | 35762.7383 | 2011-05-11 08:00 | 15d | 35762.7383 | 0 | 0 | -1731.51 | 0 | 34031.2283 | 0 | 100% | Finished | 35762.7383 | 35762.7383 | 100 | 150 | 100 | 100 | 95.1583 | 100
24 | Omgevingswerken | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 30891.0898 | 0 | 0 | 30891.0898 | 2011-06-01 08:00 | 10d | 30891.0898 | 0 | 0 | 7693.5698 | 0 | 38584.6597 | 0 | 100% | Finished | 30891.0898 | 30891.0898 | 100 | 50 | 100 | 100 | 124.9055 | 100
26 | Bedrijfsvloeren | 2011-02-01 08:00 | 2011-02-07 17:00 | 5d |  | 0 | 2350.3601 | 0 | 0 | 2350.3601 | 2011-06-01 08:00 | 5d | 2350.3601 | 0 | 0 | -359.45 | 0 | 1990.9101 | 0 | 100% | Finished | 2350.3601 | 2350.3601 | 100 | 100 | 100 | 100 | 84.7066 | 100
27 | Hekkens | 2011-02-08 08:00 | 2011-02-28 17:00 | 15d |  | 0 | 58538.5391 | 0 | 0 | 58538.5391 | 2011-05-04 08:00 | 10d | 58538.5391 | 0 | 0 | 2709.6101 | 0 | 61248.1492 | 0 | 100% | Finished | 58538.5391 | 58538.5391 | 100 | 66.6667 | 100 | 100 | 104.6288 | 100
28 | Sanitair | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 45095.5898 | 0 | 0 | 45095.5898 | 2011-05-11 08:00 | 15d | 45095.5898 | 0 | 0 | -13169.3301 | 0 | 31926.2598 | 0 | 100% | Finished | 45095.5898 | 45095.5898 | 100 | 75 | 100 | 100 | 70.7969 | 100
29 | Brandbestrijding | 2011-02-08 08:00 | 2011-03-07 17:00 | 20d |  | 0 | 1669.95 | 0 | 0 | 1669.95 | 2011-05-11 08:00 | 15d | 1669.95 | 0 | 0 | 0 | 0 | 1669.95 | 0 | 100% | Finished | 1669.95 | 1669.95 | 100 | 75 | 100 | 100 | 100 | 100
30 | Einde | 2011-03-07 17:00 | 2011-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-06-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2010-11-01
1:00 - 2:00 | No | Tuesday | Yes | 2010-11-11
2:00 - 3:00 | No | Wednesday | Yes | 2010-11-12
3:00 - 4:00 | No | Thursday | Yes | 2010-12-24
4:00 - 5:00 | No | Friday | Yes | 2010-12-27
5:00 - 6:00 | No | Saturday | No | 2010-12-28
6:00 - 7:00 | No | Sunday | No | 2010-12-29
7:00 - 8:00 | No |  |  | 2010-12-30
8:00 - 9:00 | Yes |  |  | 2010-12-31
9:00 - 10:00 | Yes |  |  | 2011-01-03
10:00 - 11:00 | Yes |  |  | 2011-01-04
11:00 - 12:00 | Yes |  |  | 2011-01-05
12:00 - 13:00 | No |  |  | 2011-01-06
13:00 - 14:00 | Yes |  |  | 2011-01-07
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
20/09, 2010 | 2010-09-08 08:00 | 2010-09-20 17:00 | 91379.1094 | 46563.23 | 46883.88 | 2010-09-08 08:00 | -44815.8794 | 50.96% | -320.65 | 99.32% | -9d | 0% | 100% | 2011-03-16 10:00 | 2011-08-09 14:00 | 2011-08-11 10:00 | 2011-03-14 11:00 | 2011-08-09 14:00 | 2011-08-11 09:00 | 2011-03-18 17:00 | 2011-03-18 17:00 | 2011-03-18 17:00 | 818760.6418 | 824076.0437 | 1561671.6444 | 818760.6418 | 1572102.9801 | 824076.0437 | 907929.8676 | 823007.1148 | 0 | 0.99316 | 0.50956 | 1 | -9 | 0.99316 | 1 | 0 | 1
09/11, 2010 | 2010-09-20 17:00 | 2010-11-09 17:00 | 304535.3418 | 211368.5806 | 240403.5014 | 2010-10-05 17:00 | -93166.7612 | 69.41% | -29034.9209 | 87.92% | -24d | 45.45% | 75.67% | 2011-03-25 09:00 | 2011-05-17 15:00 | 2011-06-17 12:00 | 2011-03-25 12:00 | 2011-05-17 15:00 | 2011-06-09 11:00 | 2011-04-08 17:00 | 2011-09-15 17:00 | 2011-10-26 15:00 | 847474.9127 | 930866.0692 | 1115059.0402 | 1575960.6062 | 1235207.2396 | 1759421.1506 | 961225.5296 | 1004699.3936 | 0.45455 | 0.87922 | 0.69407 | 0.7567 | -24 | 0.87922 | 1 | 0.45455 | 1
22/03, 2011 | 2010-11-09 17:00 | 2011-03-22 17:00 | 818439.9918 | 515200.9572 | 548153.8977 | 2010-12-17 17:00 | -303239.0347 | 62.95% | -32952.9406 | 93.99% | -56d | 55.56% | 100% | 2011-05-05 14:00 | 2011-06-09 14:00 | 2011-06-27 11:00 | 2011-05-26 14:00 | 2011-07-05 09:00 | 2011-07-11 16:00 | 2011-05-24 17:00 | 2011-07-13 17:00 | 2011-07-21 09:00 | 851392.9324 | 870788.5056 | 1029874.5731 | 1093984.1601 | 1060686.0702 | 1128896.1919 | 893605.2542 | 899524.3063 | 0.55556 | 0.93988 | 0.62949 | 1 | -56 | 0.93988 | 1 | 0.55556 | 1
10/05, 2011 | 2011-03-22 17:00 | 2011-05-10 17:00 | 818439.9918 | 674567.4943 | 702797.5936 | 2011-01-31 17:00 | -143872.4976 | 82.42% | -28230.0993 | 95.98% | -71d | 55.9% | 94.51% | 2011-04-05 10:00 | 2011-04-11 12:00 | 2011-04-19 11:00 | 2011-06-20 10:00 | 2011-06-28 11:00 | 2011-06-29 15:00 | 2011-06-14 17:00 | 2011-07-12 15:00 | 2011-07-14 14:00 | 846670.0911 | 852691.0378 | 877355.3757 | 960169.5059 | 884660.4765 | 970940.3104 | 857050.0938 | 866351.014 | 0.55901 | 0.95983 | 0.82421 | 0.94513 | -71 | 0.95983 | 1 | 0.55901 | 1
30/06, 2011 | 2011-05-10 17:00 | 2011-06-30 17:00 | 818439.9918 | 818439.9918 | 879853.1711 | 2011-03-07 17:00 | 0 | 100% | -61413.1793 | 93.02% | -83d | 58.08% | 100% | 2011-03-07 17:00 | 2011-03-07 17:00 | 2011-03-18 14:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 2011-06-30 17:00 | 879853.1711 | 879853.1711 | 879853.1711 | 879853.1711 | 879853.1711 | 879853.1711 | 879853.1711 | 879853.1711 | 0.58081 | 0.9302 | 1 | 1 | -83 | 0.9302 | 1 | 0.58081 | 1