## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Wiedauwkaai Fenders | 1 |  |  | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 | 211.375
1 | Contractuele uitvoeringstermijn | 1.1 |  |  | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 211.375
2 | Totaal Project | 1.2 |  |  | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 | 211.375
3 | Tijdelijke scheepvaartseinen plaatsen | 1.2.1 | 4SF+1d |  | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2.375
4 | Bestaande scheepvaartseinen wegnemen | 1.2.2 | 7SF | SF3+1d | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2.375
5 | Staketsel, dukdalven, scheepvaartseinen | 1.2.3 |  |  | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 | 210.375
6 | Stalen onderbouw en azobé: prefab | 1.2.3.1 |  |  | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 139.375
7 | Afbraak stak afw kant TL & DD IV | 1.2.3.2 |  | SF4;FS8 | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 4.375
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 1.2.3.3 | 7FS | FS27 | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 4.375
9 | Montage stak afw kant TL & DD IV | 1.2.3.4 | 28FS | FS10 | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 | 5.375
10 | Afbraak stak afw kant WK & DD V | 1.2.3.5 | 9FS | FS11 | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 | 6.375
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 1.2.3.6 | 10FS | FS12 | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 | 6.375
12 | Montage stak afw kant WK met verbindingen, & DD V | 1.2.3.7 | 11FS | FS13 | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 7.375
13 | Heien buispalen stak afw: kop (7 st) | 1.2.3.8 | 12FS | FS14 | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 | 5.375
14 | Montage stak afw kop | 1.2.3.9 | 13FS | FS15 | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 6.375
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 1.2.3.10 | 14FS | FS16 | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 | 11.375
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 1.2.3.11 | 15FS | FS17 | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 6.375
17 | Montage stak opw kant WK & DD II | 1.2.3.12 | 16FS | FS18 | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 7.375
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 1.2.3.13 | 17FS | FS19 | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 | 9.375
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 1.2.3.14 | 18FS | FS20;FS33 | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 6.375
20 | Montage stak opw kant TL met verbindingen, & DD I | 1.2.3.15 | 19FS | FS21 | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 | 11.375
21 | Heien buispalen stak opw: kop (7 st) | 1.2.3.16 | 20FS | FS22 | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 | 5.375
22 | Montage stak opw kop | 1.2.3.17 | 21FS | FS23 | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 6.375
23 | Roosters | 1.2.3.18 | 22FS | FS24 | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 | 6.375
24 | Scheepvaartseinen | 1.2.3.19 | 23FS | FS25 | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 | 5.375
25 | Kabels voedingen | 1.2.3.20 | 24FS |  | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 | 2.375
26 | Gestuurde boring | 1.2.4 |  |  | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 | 11.375
27 | Gestuurde boring | 1.2.4.1 | 8FS | FS28;FS41 | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 | 8.375
28 | Heien buispaal tbv boring | 1.2.4.2 | 27FS | FS9;FS29;FS31;FS37 | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 | 0.375
29 | Trekontlastingen, borden | 1.2.4.3 | 28FS |  | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 | 1.375
30 | Kabelwerken | 1.2.5 |  |  | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 | 13.375
31 | Fase 4: kabels door ingebaggerde buizen | 1.2.5.1 | 28FS |  | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 | 13.375
32 | Dukdalven | 1.2.6 |  |  | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 | 56.375
33 | Stalen brugjes | 1.2.6.1 | 19FS | FS34 | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 | 21.375
34 | Scheepvaartseinen | 1.2.6.2 | 33FS | FS35 | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 | 4.375
35 | Kabels voedingen | 1.2.6.3 | 34FS | FS48 | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 | 3.375
36 | Stabilisatie landhoofd | 1.2.7 |  |  | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 | 50.375
37 | Opzoeken leidingen in vaargeul | 1.2.7.1 | 28FS | FS38 | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 0.375
38 | Peiling 1 | 1.2.7.2 | 37FS | FS39 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 0.375
39 | Onderwater grondbanketten aanbrengen | 1.2.7.3 | 38FS | FS40 | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 | 3.375
40 | Peiling 2 | 1.2.7.4 | 39FS |  | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 0.375
41 | Aanvoer boorinstallatie | 1.2.7.5 | 27FS | FS42 | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 1.375
42 | Groutinjecties | 1.2.7.6 | 41FS | FS46 | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 | 20.375
43 | Buitendienststellingsweekend 1 | 1.2.7.7 |  |  | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
44 | Buitendienststellingsweekend 2 | 1.2.7.8 |  |  | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
45 | Buitendienststellingsweekend 3 | 1.2.7.9 |  |  | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
46 | Peiling 3 | 1.2.7.10 | 42FS | FS47 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 0.375
47 | Afvoer boorinstallatie | 1.2.7.11 | 46FS |  | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 1.375
48 | Opkuis werf | 1.2.8 | 35FS |  | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Wiedauwkaai Fenders | 1216h |  |  |  |  | 99 | 100 | 101
1 | Contractuele uitvoeringstermijn | 1216h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Totaal Project | 1216h |  |  |  |  | 99 | 100 | 101
3 | Tijdelijke scheepvaartseinen plaatsen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Bestaande scheepvaartseinen wegnemen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Staketsel, dukdalven, scheepvaartseinen | 1208h |  |  |  |  | 99 | 100 | 101
6 | Stalen onderbouw en azobé: prefab | 800h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Afbraak stak afw kant TL & DD IV | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Montage stak afw kant TL & DD IV | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Afbraak stak afw kant WK & DD V | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Montage stak afw kant WK met verbindingen, & DD V | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Heien buispalen stak afw: kop (7 st) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Montage stak afw kop | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Montage stak opw kant WK & DD II | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Montage stak opw kant TL met verbindingen, & DD I | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Heien buispalen stak opw: kop (7 st) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Montage stak opw kop | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Roosters | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Scheepvaartseinen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Kabels voedingen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Gestuurde boring | 80h |  |  |  |  | 99 | 100 | 101
27 | Gestuurde boring | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Heien buispaal tbv boring | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Trekontlastingen, borden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Kabelwerken | 80h |  |  |  |  | 99 | 100 | 101
31 | Fase 4: kabels door ingebaggerde buizen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Dukdalven | 328h |  |  |  |  | 99 | 100 | 101
33 | Stalen brugjes | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Scheepvaartseinen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Kabels voedingen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Stabilisatie landhoofd | 296h |  |  |  |  | 99 | 100 | 101
37 | Opzoeken leidingen in vaargeul | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Peiling 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Onderwater grondbanketten aanbrengen | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Peiling 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Aanvoer boorinstallatie | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Groutinjecties | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Buitendienststellingsweekend 1 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Buitendienststellingsweekend 2 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Buitendienststellingsweekend 3 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Peiling 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Afvoer boorinstallatie | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Opkuis werf | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2007-02-28 17:00 |  | TP Name | 28/02, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wiedauwkaai Fenders | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 |  | 20d | [5 empty] | 31927.8793 |  | 3.338% |  | 35702.139 | 50238.899
1 | Contractuele uitvoeringstermijn | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 2007-02-01 08:00 | 20d | 19349.6992 | 0 | 132d | 23 | 0 | 19372.6992 | 0 | 98% | Started | 19349.6992 | 19349.6992 | 100 | 13.1579 | 98 | 100 | 100.1189 | 98
2 | Totaal Project | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 |  | 20d | [5 empty] | 12555.1801 |  | 1.557% |  | 16352.4398 | 30889.1998
3 | Tijdelijke scheepvaartseinen plaatsen | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2007-02-19 08:00 | 3d | 2378.3999 | 0 | 0 | 0 | 0 | 2378.3999 | 0 | 100% | Finished | 2378.3999 | 2378.3999 | 100 | 100 | 100 | 100 | 100 | 100
4 | Bestaande scheepvaartseinen wegnemen | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2007-02-21 08:00 | 3d | 1500.85 | 0 | 0 | 0 | 0 | 1500.85 | 0 | 100% | Finished | 1500.85 | 1500.85 | 100 | 100 | 100 | 100 | 100 | 100
5 | Staketsel, dukdalven, scheepvaartseinen | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 |  | 20d | [5 empty] | 6266.7703 |  | 1.396% |  | 10064.03 | 27009.95
6 | Stalen onderbouw en azobé: prefab | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 2007-02-01 08:00 | 20d | 22599.3801 | 75315.2002 | 80d | -20633.1797 | 20633.1797 | 1966.2004 | 95948.3799 | 2% | Started | 5653.46 | 22599.3801 | 100 | 20 | 2 | 100 | 2.0081 | 2
7 | Afbraak stak afw kant TL & DD IV | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 2007-02-26 08:00 | 3d | 4410.5698 | 2862.8799 | 2d | -110 | 110 | 4300.5698 | 2972.8799 | 60% | Started | 4410.57 | 4410.5698 | 100 | 60 | 60 | 100 | 59.127 | 60
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Montage stak afw kant TL & DD IV | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 |  | 0 | 0 | 35811.5195 | 4d | 0 | 0 | 0 | 35811.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Afbraak stak afw kant WK & DD V | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 |  | 0 | 0 | 7157.1997 | 5d | 0 | 0 | 0 | 7157.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 |  | 0 | 0 | 38295.6006 | 5d | 0 | 0 | 0 | 38295.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage stak afw kant WK met verbindingen, & DD V | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 |  | 0 | 0 | 53717.2793 | 6d | 0 | 0 | 0 | 53717.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Heien buispalen stak afw: kop (7 st) | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 |  | 0 | 0 | 26806.7207 | 4d | 0 | 0 | 0 | 26806.7207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Montage stak afw kop | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 |  | 0 | 0 | 11451.5195 | 8d | 0 | 0 | 0 | 11451.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Montage stak opw kant WK & DD II | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 |  | 0 | 0 | 53717.2793 | 6d | 0 | 0 | 0 | 53717.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 |  | 0 | 0 | 11567.7695 | 8d | 0 | 0 | 0 | 11567.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage stak opw kant TL met verbindingen, & DD I | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 |  | 0 | 0 | 71623.0391 | 8d | 0 | 0 | 0 | 71623.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Heien buispalen stak opw: kop (7 st) | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 |  | 0 | 0 | 28772.9207 | 4d | 0 | 0 | 0 | 28772.9207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Montage stak opw kop | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Roosters | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 |  | 0 | 0 | 31170 | 5d | 0 | 0 | 0 | 31170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Scheepvaartseinen | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 |  | 0 | 0 | 33154.6094 | 4d | 0 | 0 | 0 | 33154.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Kabels voedingen | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 |  | 0 | 0 | 19666.5605 | 3d | 0 | 0 | 0 | 19666.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 |  | 0 | 0 | 46281.7393 | 7d | 0 | 0 | 0 | 46281.7393 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Heien buispaal tbv boring | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 |  | 0 | 0 | 3829.2 | 1d | 0 | 0 | 0 | 3829.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Trekontlastingen, borden | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 |  | 0 | 0 | 4776.1699 | 2d | 0 | 0 | 0 | 4776.1699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Kabelwerken | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Fase 4: kabels door ingebaggerde buizen | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 |  | 0 | 0 | 24123.3999 | 10d | 0 | 0 | 0 | 24123.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Dukdalven | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Stalen brugjes | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 |  | 0 | 0 | 62441.9899 | 16d | 0 | 0 | 0 | 62441.9899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Scheepvaartseinen | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 |  | 0 | 0 | 30008.4395 | 5d | 0 | 0 | 0 | 30008.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Kabels voedingen | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 |  | 0 | 0 | 22002.9297 | 4d | 0 | 0 | 0 | 22002.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Stabilisatie landhoofd | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 |  | 1d | [5 empty] | 2409.1599 |  | 1.882% |  | 2409.1599 | 0
37 | Opzoeken leidingen in vaargeul | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 2007-02-28 08:00 | 1d | 1127.6899 | 0 | 0 | 0 | 0 | 1127.6899 | 0 | 100% | Finished | 1127.6899 | 0 | 100 | 100 | 100 | 100 | 100 | 100
38 | Peiling 1 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-02-28 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 0 | 100 | 100 | 100 | 100 | 100 | 100
39 | Onderwater grondbanketten aanbrengen | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 |  | 0 | 0 | 24908.1602 | 4d | 0 | 0 | 0 | 24908.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Peiling 2 | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 |  | 0 | 0 | 1281.47 | 1d | 0 | 0 | 0 | 1281.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Aanvoer boorinstallatie | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 |  | 0 | 0 | 5125.8599 | 2d | 0 | 0 | 0 | 5125.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Groutinjecties | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 |  | 0 | 0 | 87904.4489 | 15d | 0 | 0 | 0 | 87904.4489 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Buitendienststellingsweekend 1 | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Buitendienststellingsweekend 2 | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Buitendienststellingsweekend 3 | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Peiling 3 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 |  | 0 | 0 | 1281.47 | 1d | 0 | 0 | 0 | 1281.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afvoer boorinstallatie | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 |  | 0 | 0 | 5125.8599 | 2d | 0 | 0 | 0 | 5125.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Opkuis werf | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 |  | 0 | 0 | 3776.3201 | 5d | 0 | 0 | 0 | 3776.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2007-03-31 17:00 |  | TP Name | 31/03, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wiedauwkaai Fenders | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 |  | 42d | [5 empty] | 228566.257 |  | 24.56% |  | 262647.0062 | 250546.5984
1 | Contractuele uitvoeringstermijn | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 2007-02-01 08:00 | 42d | 19349.6992 | 0 | 132d | 110 | 0 | 19459.6992 | 0 | 98% | Started | 19349.6992 | 19349.6992 | 100 | 27.6316 | 98 | 100 | 100.5685 | 98
2 | Totaal Project | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 |  | 42d | [5 empty] | 209106.5577 |  | 23.17% |  | 243297.307 | 231196.8992
3 | Tijdelijke scheepvaartseinen plaatsen | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2007-02-19 08:00 | 3d | 2378.3999 | 0 | 0 | 0 | 0 | 2378.3999 | 0 | 100% | Finished | 2378.3999 | 2378.3999 | 100 | 100 | 100 | 100 | 100 | 100
4 | Bestaande scheepvaartseinen wegnemen | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2007-02-21 08:00 | 3d | 1500.85 | 0 | 0 | 0 | 0 | 1500.85 | 0 | 100% | Finished | 1500.85 | 1500.85 | 100 | 100 | 100 | 100 | 100 | 100
5 | Staketsel, dukdalven, scheepvaartseinen | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 |  | 42d | [5 empty] | 105116.5299 |  | 12.14% |  | 87498.7503 | 125156.3502
6 | Stalen onderbouw en azobé: prefab | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 2007-02-01 08:00 | 42d | 43311.0602 | 75315.2002 | 80d | -40442.7109 | 40442.7109 | 2868.3492 | 115757.9111 | 2% | Started | 5653.46 | 43311.0602 | 100 | 42 | 2 | 100 | 2.9294 | 2
7 | Afbraak stak afw kant TL & DD IV | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 2007-02-26 08:00 | 5d | 7273.4497 | 0 | 0 | -120 | 0 | 7153.4497 | 0 | 100% | Finished | 7273.4497 | 7273.4497 | 100 | 100 | 100 | 100 | 98.3502 | 100
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-03-05 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 148.0122 | 100
9 | Montage stak afw kant TL & DD IV | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 | 2007-03-22 08:00 | 4d | 35811.5195 | 0 | 0 | 3975 | 0 | 39786.5195 | 0 | 100% | Finished | 35811.5195 | 35811.5195 | 100 | 100 | 100 | 100 | 111.0998 | 100
10 | Afbraak stak afw kant WK & DD V | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 | 2007-03-28 08:00 | 3d | 4294.3198 | 2862.8799 | 2d | 0 | 0 | 4294.3198 | 2862.8799 | 60% | Started | 4294.32 | 4294.3198 | 100 | 60 | 60 | 100 | 60 | 60
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 |  | 0 | 0 | 38295.6006 | 5d | 0 | 0 | 0 | 38295.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage stak afw kant WK met verbindingen, & DD V | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 |  | 0 | 0 | 53717.2793 | 6d | 0 | 0 | 0 | 53717.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Heien buispalen stak afw: kop (7 st) | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 |  | 0 | 0 | 26806.7207 | 4d | 0 | 0 | 0 | 26806.7207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Montage stak afw kop | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 |  | 0 | 0 | 11451.5195 | 8d | 0 | 0 | 0 | 11451.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Montage stak opw kant WK & DD II | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 |  | 0 | 0 | 53717.2793 | 6d | 0 | 0 | 0 | 53717.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 |  | 0 | 0 | 11567.7695 | 8d | 0 | 0 | 0 | 11567.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage stak opw kant TL met verbindingen, & DD I | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 |  | 0 | 0 | 71623.0391 | 8d | 0 | 0 | 0 | 71623.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Heien buispalen stak opw: kop (7 st) | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 |  | 0 | 0 | 28772.9207 | 4d | 0 | 0 | 0 | 28772.9207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Montage stak opw kop | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Roosters | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 |  | 0 | 0 | 31170 | 5d | 0 | 0 | 0 | 31170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Scheepvaartseinen | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 |  | 0 | 0 | 33154.6094 | 4d | 0 | 0 | 0 | 33154.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Kabels voedingen | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 |  | 0 | 0 | 19666.5605 | 3d | 0 | 0 | 0 | 19666.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 |  | 10d | [5 empty] | 54887.1091 |  | 100% |  | 54887.1091 | 54887.1091
27 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 | 2007-03-12 08:00 | 7d | 46281.7393 | 0 | 0 | 0 | 0 | 46281.7393 | 0 | 100% | Finished | 46281.7393 | 46281.7393 | 100 | 100 | 100 | 100 | 100 | 100
28 | Heien buispaal tbv boring | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 | 2007-03-21 08:00 | 1d | 3829.2 | 0 | 0 | 0 | 0 | 3829.2 | 0 | 100% | Finished | 3829.2 | 3829.2 | 100 | 100 | 100 | 100 | 100 | 100
29 | Trekontlastingen, borden | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 | 2007-03-22 08:00 | 2d | 4776.1699 | 0 | 0 | 0 | 0 | 4776.1699 | 0 | 100% | Finished | 4776.1699 | 4776.1699 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelwerken | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 |  | 7d | [5 empty] | 24875.3999 |  | 60.85% |  | 14680.1997 | 18675.3999
31 | Fase 4: kabels door ingebaggerde buizen | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 | 2007-03-22 08:00 | 7d | 18675.3999 | 5448 | 3d | 6200 | 0 | 24875.3999 | 5448 | 48% | Started | 14680.1997 | 18675.3999 | 100 | 70 | 48 | 100 | 103.1173 | 48
32 | Dukdalven | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Stalen brugjes | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 |  | 0 | 0 | 62441.9899 | 16d | 0 | 0 | 0 | 62441.9899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Scheepvaartseinen | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 |  | 0 | 0 | 30008.4395 | 5d | 0 | 0 | 0 | 30008.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Kabels voedingen | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 |  | 0 | 0 | 22002.9297 | 4d | 0 | 0 | 0 | 22002.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Stabilisatie landhoofd | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 |  | 23d | [5 empty] | 20348.2689 |  | 64.32% |  | 82351.998 | 28598.79
37 | Opzoeken leidingen in vaargeul | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 2007-02-28 08:00 | 1d | 1127.6899 | 0 | 0 | 0 | 0 | 1127.6899 | 0 | 100% | Finished | 1127.6899 | 1127.6899 | 100 | 100 | 100 | 100 | 100 | 100
38 | Peiling 1 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-02-28 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
39 | Onderwater grondbanketten aanbrengen | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 | 2007-03-26 08:00 | 4d | 24908.1602 | 12454.0801 | 2d | -15672.1602 | 0 | 9236 | 12454.0801 | 43% | Started | 10710.509 | 24908.1602 | 100 | 100 | 43 | 100 | 37.0802 | 43
40 | Peiling 2 | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 |  | 0 | 0 | 1281.47 | 1d | 0 | 0 | 0 | 1281.47 | 0% | Not Started | 0 | 1281.47 | 100 |  | 0 | 100 |  | 0
41 | Aanvoer boorinstallatie | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-03-28 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 0 | 100 | 100 | 100 | 100 | 100 | 100
42 | Groutinjecties | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 | 2007-03-28 08:00 | 3d | 68277.2491 | 22898.3997 | 14d | -64700 | 0 | 3577.2491 | 22898.3997 | 3% | Started | 64106.4692 | 0 | 100 | 20 | 3 | 100 | 4.0695 | 3
43 | Buitendienststellingsweekend 1 | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Buitendienststellingsweekend 2 | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Buitendienststellingsweekend 3 | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Peiling 3 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 |  | 0 | 0 | 1281.47 | 1d | 0 | 0 | 0 | 1281.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afvoer boorinstallatie | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 |  | 0 | 0 | 5125.8599 | 2d | 0 | 0 | 0 | 5125.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Opkuis werf | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 |  | 0 | 0 | 3776.3201 | 5d | 0 | 0 | 0 | 3776.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2007-04-30 17:00 |  | TP Name | 30/04, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wiedauwkaai Fenders | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 |  | 63d | [5 empty] | 524633.1573 |  | 42.09% |  | 450217.6263 | 483775.9474
1 | Contractuele uitvoeringstermijn | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 2007-02-01 08:00 | 63d | 19349.6992 | 0 | 90d | 200 | 0 | 19549.6992 | 0 | 98% | Started | 19349.6992 | 19349.6992 | 100 | 41.4474 | 98 | 100 | 101.0336 | 98
2 | Totaal Project | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 |  | 63d | [5 empty] | 505083.4581 |  | 41.03% |  | 430867.9271 | 464426.2482
3 | Tijdelijke scheepvaartseinen plaatsen | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2007-02-19 08:00 | 3d | 2378.3999 | 0 | 0 | 0 | 0 | 2378.3999 | 0 | 100% | Finished | 2378.3999 | 2378.3999 | 100 | 100 | 100 | 100 | 100 | 100
4 | Bestaande scheepvaartseinen wegnemen | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2007-02-21 08:00 | 3d | 1500.85 | 0 | 0 | 0 | 0 | 1500.85 | 0 | 100% | Finished | 1500.85 | 1500.85 | 100 | 100 | 100 | 100 | 100 | 100
5 | Staketsel, dukdalven, scheepvaartseinen | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 |  | 63d | [5 empty] | 260310.2812 |  | 32.13% |  | 231664.1917 | 259907.3906
6 | Stalen onderbouw en azobé: prefab | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 2007-02-01 08:00 | 63d | 63081.3002 | 54603.5201 | 58d | -20000 | 40442.7109 | 43081.3002 | 95046.2311 | 33% | Started | 34838.1014 | 63081.3002 | 100 | 63 | 33 | 100 | 43.9989 | 33
7 | Afbraak stak afw kant TL & DD IV | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 2007-02-26 08:00 | 5d | 7273.4497 | 0 | 0 | -120 | 0 | 7153.4497 | 0 | 100% | Finished | 7273.4497 | 7273.4497 | 100 | 100 | 100 | 100 | 98.3502 | 100
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-03-05 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 148.0122 | 100
9 | Montage stak afw kant TL & DD IV | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 | 2007-03-22 08:00 | 4d | 35811.5195 | 0 | 0 | 3975 | 0 | 39786.5195 | 0 | 100% | Finished | 35811.5195 | 35811.5195 | 100 | 100 | 100 | 100 | 111.0998 | 100
10 | Afbraak stak afw kant WK & DD V | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 | 2007-03-28 08:00 | 5d | 7157.1997 | 0 | 0 | 0 | 0 | 7157.1997 | 0 | 100% | Finished | 7157.1997 | 7157.1997 | 100 | 100 | 100 | 100 | 100 | 100
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 | 2007-04-04 08:00 | 5d | 38295.6006 | 0 | 0 | 0 | 0 | 38295.6006 | 0 | 100% | Finished | 38295.6006 | 38295.6006 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage stak afw kant WK met verbindingen, & DD V | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-04-18 08:00 | 6d | 53717.2793 | 0 | 0 | 0 | 0 | 53717.2793 | 0 | 100% | Finished | 53717.2793 | 53717.2793 | 100 | 100 | 100 | 100 | 100 | 100
13 | Heien buispalen stak afw: kop (7 st) | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 | 2007-04-26 08:00 | 3d | 20105.0405 | 6701.6802 | 1d | 0 | 0 | 20105.0405 | 6701.6802 | 75% | Started | 20105.0405 | 20105.0405 | 100 | 75 | 75 | 100 | 75 | 75
14 | Montage stak afw kop | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 |  | 0 | 0 | 11451.5195 | 8d | 0 | 0 | 0 | 11451.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Montage stak opw kant WK & DD II | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 |  | 0 | 0 | 53717.2793 | 6d | 0 | 0 | 0 | 53717.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 |  | 0 | 0 | 11567.7695 | 8d | 0 | 0 | 0 | 11567.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage stak opw kant TL met verbindingen, & DD I | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 |  | 0 | 0 | 71623.0391 | 8d | 0 | 0 | 0 | 71623.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Heien buispalen stak opw: kop (7 st) | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 |  | 0 | 0 | 28772.9207 | 4d | 0 | 0 | 0 | 28772.9207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Montage stak opw kop | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Roosters | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 |  | 0 | 0 | 31170 | 5d | 0 | 0 | 0 | 31170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Scheepvaartseinen | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 |  | 0 | 0 | 33154.6094 | 4d | 0 | 0 | 0 | 33154.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Kabels voedingen | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 |  | 0 | 0 | 19666.5605 | 3d | 0 | 0 | 0 | 19666.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 |  | 10d | [5 empty] | 54887.1091 |  | 100% |  | 54887.1091 | 54887.1091
27 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 | 2007-03-12 08:00 | 7d | 46281.7393 | 0 | 0 | 0 | 0 | 46281.7393 | 0 | 100% | Finished | 46281.7393 | 46281.7393 | 100 | 100 | 100 | 100 | 100 | 100
28 | Heien buispaal tbv boring | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 | 2007-03-21 08:00 | 1d | 3829.2 | 0 | 0 | 0 | 0 | 3829.2 | 0 | 100% | Finished | 3829.2 | 3829.2 | 100 | 100 | 100 | 100 | 100 | 100
29 | Trekontlastingen, borden | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 | 2007-03-22 08:00 | 2d | 4776.1699 | 0 | 0 | 0 | 0 | 4776.1699 | 0 | 100% | Finished | 4776.1699 | 4776.1699 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelwerken | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 |  | 28d | [5 empty] | 36627.3999 |  | 77.97% |  | 18808.2776 | 24123.3999
31 | Fase 4: kabels door ingebaggerde buizen | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 | 2007-03-22 08:00 | 29d | 58627.3999 | 21792 | 12d | -22000 | 0 | 36627.3999 | 21792 | 70.73% | Started | 18808.2776 | 24123.3999 | 100 | 290 | 70.7317 | 100 | 151.8335 | 70.7317
32 | Dukdalven | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Stalen brugjes | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 |  | 0 | 0 | 62441.9899 | 16d | 0 | 0 | 0 | 62441.9899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Scheepvaartseinen | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 |  | 0 | 0 | 30008.4395 | 5d | 0 | 0 | 0 | 30008.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Kabels voedingen | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 |  | 0 | 0 | 22002.9297 | 4d | 0 | 0 | 0 | 22002.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Stabilisatie landhoofd | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 |  | 44d | [5 empty] | 149379.418 |  | 95% |  | 121629.0988 | 121629.0988
37 | Opzoeken leidingen in vaargeul | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 2007-02-28 08:00 | 1d | 1127.6899 | 0 | 0 | 0 | 0 | 1127.6899 | 0 | 100% | Finished | 1127.6899 | 1127.6899 | 100 | 100 | 100 | 100 | 100 | 100
38 | Peiling 1 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-02-28 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
39 | Onderwater grondbanketten aanbrengen | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 | 2007-03-26 08:00 | 6d | 37362.2402 | 0 | 0 | -16004.9404 | 0 | 21357.2998 | 0 | 100% | Finished | 24908.1602 | 24908.1602 | 100 | 150 | 100 | 100 | 85.7442 | 100
40 | Peiling 2 | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-04-02 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
41 | Aanvoer boorinstallatie | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-03-28 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 5125.8599 | 100 | 100 | 100 | 100 | 100 | 100
42 | Groutinjecties | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 | 2007-03-28 08:00 | 20d | 96082.4487 | 0 | 0 | 23123.1797 | 0 | 119205.6284 | 0 | 100% | Finished | 87904.4489 | 87904.4489 | 100 | 133.3333 | 100 | 100 | 135.6082 | 100
43 | Buitendienststellingsweekend 1 | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
44 | Buitendienststellingsweekend 2 | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Buitendienststellingsweekend 3 | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Peiling 3 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 |  | 0 | 0 | 1281.47 | 1d | 0 | 0 | 0 | 1281.47 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afvoer boorinstallatie | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 |  | 0 | 0 | 5125.8599 | 2d | 0 | 0 | 0 | 5125.8599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Opkuis werf | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 |  | 0 | 0 | 3776.3201 | 5d | 0 | 0 | 0 | 3776.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2007-05-31 17:00 |  | TP Name | 31/05, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wiedauwkaai Fenders | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 |  | 86d | [5 empty] | 764311.585 |  | 56.33% |  | 602515.1974 | 609219.9974
1 | Contractuele uitvoeringstermijn | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 2007-02-01 08:00 | 86d | 19349.6992 | 0 | 64d | 300 | 0 | 19649.6992 | 0 | 99% | Started | 19349.6992 | 19349.6992 | 100 | 56.5789 | 99 | 100 | 101.5504 | 99
2 | Totaal Project | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 |  | 86d | [5 empty] | 744661.8858 |  | 55.53% |  | 583165.4982 | 589870.2982
3 | Tijdelijke scheepvaartseinen plaatsen | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2007-02-19 08:00 | 3d | 2378.3999 | 0 | 0 | 0 | 0 | 2378.3999 | 0 | 100% | Finished | 2378.3999 | 2378.3999 | 100 | 100 | 100 | 100 | 100 | 100
4 | Bestaande scheepvaartseinen wegnemen | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2007-02-21 08:00 | 3d | 1500.85 | 0 | 0 | 0 | 0 | 1500.85 | 0 | 100% | Finished | 1500.85 | 1500.85 | 100 | 100 | 100 | 100 | 100 | 100
5 | Staketsel, dukdalven, scheepvaartseinen | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 |  | 86d | [5 empty] | 485148.4299 |  | 51.9% |  | 374236.9109 | 378944.1107
6 | Stalen onderbouw en azobé: prefab | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 2007-02-01 08:00 | 83d | 81910.1003 | 32950.4001 | 35d | 23000 | 0 | 104910.1003 | 32950.4001 | 81% | Started | 80027.2205 | 84734.4203 | 100 | 83 | 81 | 100 | 107.1445 | 81
7 | Afbraak stak afw kant TL & DD IV | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 2007-02-26 08:00 | 5d | 7273.4497 | 0 | 0 | -120 | 0 | 7153.4497 | 0 | 100% | Finished | 7273.4497 | 7273.4497 | 100 | 100 | 100 | 100 | 98.3502 | 100
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-03-05 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 148.0122 | 100
9 | Montage stak afw kant TL & DD IV | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 | 2007-03-22 08:00 | 4d | 35811.5195 | 0 | 0 | 3975 | 0 | 39786.5195 | 0 | 100% | Finished | 35811.5195 | 35811.5195 | 100 | 100 | 100 | 100 | 111.0998 | 100
10 | Afbraak stak afw kant WK & DD V | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 | 2007-03-28 08:00 | 5d | 7157.1997 | 0 | 0 | 0 | 0 | 7157.1997 | 0 | 100% | Finished | 7157.1997 | 7157.1997 | 100 | 100 | 100 | 100 | 100 | 100
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 | 2007-04-04 08:00 | 5d | 38295.6006 | 0 | 0 | 18386.5391 | 0 | 56682.1396 | 0 | 100% | Finished | 38295.6006 | 38295.6006 | 100 | 100 | 100 | 100 | 148.0121 | 100
12 | Montage stak afw kant WK met verbindingen, & DD V | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-04-18 08:00 | 6d | 53717.2793 | 0 | 0 | 5960.3799 | 0 | 59677.6592 | 0 | 100% | Finished | 53717.2793 | 53717.2793 | 100 | 100 | 100 | 100 | 111.0958 | 100
13 | Heien buispalen stak afw: kop (7 st) | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 | 2007-04-26 08:00 | 3d | 20105.0405 | 0 | 0 | 19572.4297 | 0 | 39677.4702 | 0 | 100% | Finished | 26806.7207 | 26806.7207 | 100 | 75 | 100 | 100 | 148.0131 | 100
14 | Montage stak afw kop | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 2007-05-04 08:00 | 5d | 44764.3994 | 0 | 0 | 4966.9902 | 0 | 49731.3896 | 0 | 100% | Finished | 44764.3994 | 44764.3994 | 100 | 100 | 100 | 100 | 111.0958 | 100
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 | 2007-05-11 08:00 | 8d | 11451.5195 | 0 | 0 | 0 | 0 | 11451.5195 | 0 | 100% | Finished | 11451.5195 | 11451.5195 | 100 | 100 | 100 | 100 | 100 | 100
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-05-25 08:00 | 5d | 34466.001 | 0 | 0 | 23441.0898 | 0 | 57907.0908 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 168.0122 | 100
17 | Montage stak opw kant WK & DD II | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 |  | 0 | 0 | 53717.2793 | 6d | 0 | 0 | 0 | 53717.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 |  | 0 | 0 | 11567.7695 | 8d | 0 | 0 | 0 | 11567.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 |  | 0 | 0 | 34466.001 | 5d | 0 | 0 | 0 | 34466.001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage stak opw kant TL met verbindingen, & DD I | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 |  | 0 | 0 | 71623.0391 | 8d | 0 | 0 | 0 | 71623.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Heien buispalen stak opw: kop (7 st) | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 |  | 0 | 0 | 28772.9207 | 4d | 0 | 0 | 0 | 28772.9207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Montage stak opw kop | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Roosters | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 |  | 0 | 0 | 31170 | 5d | 0 | 0 | 0 | 31170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Scheepvaartseinen | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 |  | 0 | 0 | 33154.6094 | 4d | 0 | 0 | 0 | 33154.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Kabels voedingen | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 |  | 0 | 0 | 19666.5605 | 3d | 0 | 0 | 0 | 19666.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 |  | 10d | [5 empty] | 54887.1091 |  | 100% |  | 54887.1091 | 54887.1091
27 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 | 2007-03-12 08:00 | 7d | 46281.7393 | 0 | 0 | 0 | 0 | 46281.7393 | 0 | 100% | Finished | 46281.7393 | 46281.7393 | 100 | 100 | 100 | 100 | 100 | 100
28 | Heien buispaal tbv boring | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 | 2007-03-21 08:00 | 1d | 3829.2 | 0 | 0 | 0 | 0 | 3829.2 | 0 | 100% | Finished | 3829.2 | 3829.2 | 100 | 100 | 100 | 100 | 100 | 100
29 | Trekontlastingen, borden | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 | 2007-03-22 08:00 | 2d | 4776.1699 | 0 | 0 | 0 | 0 | 4776.1699 | 0 | 100% | Finished | 4776.1699 | 4776.1699 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelwerken | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 |  | 51d | [5 empty] | 44960.3491 |  | 91.72% |  | 22125.7996 | 24123.3999
31 | Fase 4: kabels door ingebaggerde buizen | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 | 2007-03-22 08:00 | 51d | 98579.3999 | 5448 | 3d | -53619.0508 | 0 | 44960.3491 | 5448 | 89% | Started | 22125.7996 | 24123.3999 | 100 | 510 | 89 | 100 | 186.3765 | 89
32 | Dukdalven | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
33 | Stalen brugjes | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 |  | 0 | 0 | 62441.9899 | 16d | 0 | 0 | 0 | 62441.9899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Scheepvaartseinen | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 |  | 0 | 0 | 30008.4395 | 5d | 0 | 0 | 0 | 30008.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Kabels voedingen | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 |  | 0 | 0 | 22002.9297 | 4d | 0 | 0 | 0 | 22002.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Stabilisatie landhoofd | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 |  | 53d | [5 empty] | 155786.7478 |  | 100% |  | 128036.4286 | 128036.4286
37 | Opzoeken leidingen in vaargeul | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 2007-02-28 08:00 | 1d | 1127.6899 | 0 | 0 | 0 | 0 | 1127.6899 | 0 | 100% | Finished | 1127.6899 | 1127.6899 | 100 | 100 | 100 | 100 | 100 | 100
38 | Peiling 1 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-02-28 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
39 | Onderwater grondbanketten aanbrengen | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 | 2007-03-26 08:00 | 6d | 37362.2402 | 0 | 0 | -16004.9404 | 0 | 21357.2998 | 0 | 100% | Finished | 24908.1602 | 24908.1602 | 100 | 150 | 100 | 100 | 85.7442 | 100
40 | Peiling 2 | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-04-02 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
41 | Aanvoer boorinstallatie | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-03-28 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 5125.8599 | 100 | 100 | 100 | 100 | 100 | 100
42 | Groutinjecties | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 | 2007-03-28 08:00 | 20d | 96082.4487 | 0 | 0 | 23123.1797 | 0 | 119205.6284 | 0 | 100% | Finished | 87904.4489 | 87904.4489 | 100 | 133.3333 | 100 | 100 | 135.6082 | 100
43 | Buitendienststellingsweekend 1 | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
44 | Buitendienststellingsweekend 2 | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
45 | Buitendienststellingsweekend 3 | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
46 | Peiling 3 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-05-04 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afvoer boorinstallatie | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-05-07 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 5125.8599 | 100 | 100 | 100 | 100 | 100 | 100
48 | Opkuis werf | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 |  | 0 | 0 | 3776.3201 | 5d | 0 | 0 | 0 | 3776.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2007-06-30 17:00 |  | TP Name | 30/06, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wiedauwkaai Fenders | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 |  | 107d | [5 empty] | 918901.8244 |  | 67.66% |  | 723668.7557 | 735852.4772
1 | Contractuele uitvoeringstermijn | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 2007-02-01 08:00 | 107d | 19349.6992 | 0 | 48d | 414.95 | 0 | 19764.6492 | 0 | 99% | Started | 19349.6992 | 19349.6992 | 100 | 70.3947 | 99 | 100 | 102.1445 | 99
2 | Totaal Project | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 |  | 107d | [5 empty] | 899137.1752 |  | 67.07% |  | 704319.0565 | 716502.778
3 | Tijdelijke scheepvaartseinen plaatsen | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2007-02-19 08:00 | 3d | 2378.3999 | 0 | 0 | 0 | 0 | 2378.3999 | 0 | 100% | Finished | 2378.3999 | 2378.3999 | 100 | 100 | 100 | 100 | 100 | 100
4 | Bestaande scheepvaartseinen wegnemen | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2007-02-21 08:00 | 3d | 1500.85 | 0 | 0 | 0 | 0 | 1500.85 | 0 | 100% | Finished | 1500.85 | 1500.85 | 100 | 100 | 100 | 100 | 100 | 100
5 | Staketsel, dukdalven, scheepvaartseinen | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 |  | 107d | [5 empty] | 633036.88 |  | 68.22% |  | 491875.3206 | 500828.2004
6 | Stalen onderbouw en azobé: prefab | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 2007-02-01 08:00 | 104d | 101680.3403 | 0 | 0 | 28975.2598 | 0 | 130655.6001 | 0 | 100% | Finished | 97914.5803 | 97914.5803 | 100 | 104 | 100 | 100 | 133.4383 | 100
7 | Afbraak stak afw kant TL & DD IV | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 2007-02-26 08:00 | 5d | 7273.4497 | 0 | 0 | -120 | 0 | 7153.4497 | 0 | 100% | Finished | 7273.4497 | 7273.4497 | 100 | 100 | 100 | 100 | 98.3502 | 100
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-03-05 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 148.0122 | 100
9 | Montage stak afw kant TL & DD IV | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 | 2007-03-22 08:00 | 4d | 35811.5195 | 0 | 0 | 3975 | 0 | 39786.5195 | 0 | 100% | Finished | 35811.5195 | 35811.5195 | 100 | 100 | 100 | 100 | 111.0998 | 100
10 | Afbraak stak afw kant WK & DD V | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 | 2007-03-28 08:00 | 5d | 7157.1997 | 0 | 0 | 0 | 0 | 7157.1997 | 0 | 100% | Finished | 7157.1997 | 7157.1997 | 100 | 100 | 100 | 100 | 100 | 100
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 | 2007-04-04 08:00 | 5d | 38295.6006 | 0 | 0 | 18386.5391 | 0 | 56682.1396 | 0 | 100% | Finished | 38295.6006 | 38295.6006 | 100 | 100 | 100 | 100 | 148.0121 | 100
12 | Montage stak afw kant WK met verbindingen, & DD V | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-04-18 08:00 | 6d | 53717.2793 | 0 | 0 | 5960.3799 | 0 | 59677.6592 | 0 | 100% | Finished | 53717.2793 | 53717.2793 | 100 | 100 | 100 | 100 | 111.0958 | 100
13 | Heien buispalen stak afw: kop (7 st) | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 | 2007-04-26 08:00 | 3d | 20105.0405 | 0 | 0 | 19572.4297 | 0 | 39677.4702 | 0 | 100% | Finished | 26806.7207 | 26806.7207 | 100 | 75 | 100 | 100 | 148.0131 | 100
14 | Montage stak afw kop | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 2007-05-04 08:00 | 5d | 44764.3994 | 0 | 0 | 4966.9902 | 0 | 49731.3896 | 0 | 100% | Finished | 44764.3994 | 44764.3994 | 100 | 100 | 100 | 100 | 111.0958 | 100
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 | 2007-05-11 08:00 | 8d | 11451.5195 | 0 | 0 | 0 | 0 | 11451.5195 | 0 | 100% | Finished | 11451.5195 | 11451.5195 | 100 | 100 | 100 | 100 | 100 | 100
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-05-25 08:00 | 5d | 34466.001 | 0 | 0 | 23441.0898 | 0 | 57907.0908 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 168.0122 | 100
17 | Montage stak opw kant WK & DD II | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-06-04 08:00 | 6d | 53717.2793 | 0 | 0 | 5960.3799 | 0 | 59677.6592 | 0 | 100% | Finished | 53717.2793 | 53717.2793 | 100 | 100 | 100 | 100 | 111.0958 | 100
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 | 2007-06-12 08:00 | 8d | 11567.7695 | 0 | 0 | -116.37 | 0 | 11451.3995 | 0 | 100% | Finished | 11567.7695 | 11567.7695 | 100 | 100 | 100 | 100 | 98.994 | 100
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-06-22 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 148.0122 | 100
20 | Montage stak opw kant TL met verbindingen, & DD I | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 |  | 0 | 0 | 71623.0391 | 8d | 0 | 0 | 0 | 71623.0391 | 0% | Not Started | 0 | 8952.8799 | 100 |  | 0 | 100 |  | 0
21 | Heien buispalen stak opw: kop (7 st) | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 |  | 0 | 0 | 28772.9207 | 4d | 0 | 0 | 0 | 28772.9207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Montage stak opw kop | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 |  | 0 | 0 | 44764.3994 | 5d | 0 | 0 | 0 | 44764.3994 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Roosters | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 |  | 0 | 0 | 31170 | 5d | 0 | 0 | 0 | 31170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Scheepvaartseinen | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 |  | 0 | 0 | 33154.6094 | 4d | 0 | 0 | 0 | 33154.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Kabels voedingen | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 |  | 0 | 0 | 19666.5605 | 3d | 0 | 0 | 0 | 19666.5605 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 |  | 10d | [5 empty] | 54887.1091 |  | 100% |  | 54887.1091 | 54887.1091
27 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 | 2007-03-12 08:00 | 7d | 46281.7393 | 0 | 0 | 0 | 0 | 46281.7393 | 0 | 100% | Finished | 46281.7393 | 46281.7393 | 100 | 100 | 100 | 100 | 100 | 100
28 | Heien buispaal tbv boring | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 | 2007-03-21 08:00 | 1d | 3829.2 | 0 | 0 | 0 | 0 | 3829.2 | 0 | 100% | Finished | 3829.2 | 3829.2 | 100 | 100 | 100 | 100 | 100 | 100
29 | Trekontlastingen, borden | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 | 2007-03-22 08:00 | 2d | 4776.1699 | 0 | 0 | 0 | 0 | 4776.1699 | 0 | 100% | Finished | 4776.1699 | 4776.1699 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelwerken | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 |  | 54d | [5 empty] | 50598.7983 |  | 100% |  | 24123.3999 | 24123.3999
31 | Fase 4: kabels door ingebaggerde buizen | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 | 2007-03-22 08:00 | 54d | 104027.3999 | 0 | 0 | -53428.6016 | 0 | 50598.7983 | 0 | 100% | Finished | 24123.3999 | 24123.3999 | 100 | 540 | 100 | 100 | 209.7499 | 100
32 | Dukdalven | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 |  | 1d | [5 empty] | 948.39 |  | 1.326% |  | 1517.5484 | 4748.39
33 | Stalen brugjes | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 | 2007-06-29 08:00 | 1d | 4748.39 | 57693.5999 | 15d | -3800 | 0 | 948.39 | 57693.5999 | 1% | Started | 1517.5484 | 4748.39 | 100 | 6.25 | 1 | 100 | 1.5188 | 1
34 | Scheepvaartseinen | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 |  | 0 | 0 | 30008.4395 | 5d | 0 | 0 | 0 | 30008.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Kabels voedingen | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 |  | 0 | 0 | 22002.9297 | 4d | 0 | 0 | 0 | 22002.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Stabilisatie landhoofd | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 |  | 53d | [5 empty] | 155786.7478 |  | 100% |  | 128036.4286 | 128036.4286
37 | Opzoeken leidingen in vaargeul | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 2007-02-28 08:00 | 1d | 1127.6899 | 0 | 0 | 0 | 0 | 1127.6899 | 0 | 100% | Finished | 1127.6899 | 1127.6899 | 100 | 100 | 100 | 100 | 100 | 100
38 | Peiling 1 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-02-28 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
39 | Onderwater grondbanketten aanbrengen | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 | 2007-03-26 08:00 | 6d | 37362.2402 | 0 | 0 | -16004.9404 | 0 | 21357.2998 | 0 | 100% | Finished | 24908.1602 | 24908.1602 | 100 | 150 | 100 | 100 | 85.7442 | 100
40 | Peiling 2 | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-04-02 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
41 | Aanvoer boorinstallatie | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-03-28 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 5125.8599 | 100 | 100 | 100 | 100 | 100 | 100
42 | Groutinjecties | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 | 2007-03-28 08:00 | 20d | 96082.4487 | 0 | 0 | 23123.1797 | 0 | 119205.6284 | 0 | 100% | Finished | 87904.4489 | 87904.4489 | 100 | 133.3333 | 100 | 100 | 135.6082 | 100
43 | Buitendienststellingsweekend 1 | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
44 | Buitendienststellingsweekend 2 | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
45 | Buitendienststellingsweekend 3 | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
46 | Peiling 3 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-05-04 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afvoer boorinstallatie | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-05-07 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 5125.8599 | 100 | 100 | 100 | 100 | 100 | 100
48 | Opkuis werf | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 |  | 0 | 0 | 3776.3201 | 5d | 0 | 0 | 0 | 3776.3201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2007-08-31 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Wiedauwkaai Fenders | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 253122.0964 |  |  | 1069532.4154 |  | 152d | [5 empty] | 1314584.5815 |  | 100% |  | 1069532.4154 | 1069532.4154
1 | Contractuele uitvoeringstermijn | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  | 0 | 19349.6992 | 0 | 0 | 19349.6992 | 2007-02-01 08:00 | 150d | 19349.6992 | 0 | 0 | 492.45 | 0 | 19842.1492 | 0 | 100% | Finished | 19349.6992 | 19349.6992 | 100 | 98.6842 | 100 | 100 | 102.545 | 100
2 | Totaal Project | 2007-02-01 08:00 | 2007-08-31 17:00 | 152d |  |  | 233772.3972 |  |  | 1050182.7162 |  | 152d | [5 empty] | 1294742.4322 |  | 100% |  | 1050182.7162 | 1050182.7162
3 | Tijdelijke scheepvaartseinen plaatsen | 2007-02-19 08:00 | 2007-02-21 17:00 | 3d |  | 0 | 2378.3999 | 0 | 0 | 2378.3999 | 2007-02-19 08:00 | 3d | 2378.3999 | 0 | 0 | 0 | 0 | 2378.3999 | 0 | 100% | Finished | 2378.3999 | 2378.3999 | 100 | 100 | 100 | 100 | 100 | 100
4 | Bestaande scheepvaartseinen wegnemen | 2007-02-21 08:00 | 2007-02-23 17:00 | 3d |  | 0 | 1500.85 | 0 | 0 | 1500.85 | 2007-02-21 08:00 | 3d | 1500.85 | 0 | 0 | 0 | 0 | 1500.85 | 0 | 100% | Finished | 1500.85 | 1500.85 | 100 | 100 | 100 | 100 | 100 | 100
5 | Staketsel, dukdalven, scheepvaartseinen | 2007-02-01 08:00 | 2007-08-30 17:00 | 151d |  |  | 58790.45 |  |  | 721026.8496 |  | 151d | [5 empty] | 879483.8495 |  | 100% |  | 721026.8496 | 721026.8496
6 | Stalen onderbouw en azobé: prefab | 2007-02-01 08:00 | 2007-06-20 17:00 | 100d |  | 0 | 3770.5801 | 117.68 | 94144.0002 | 97914.5803 | 2007-02-01 08:00 | 104d | 101680.3403 | 0 | 0 | 28975.2598 | 0 | 130655.6001 | 0 | 100% | Finished | 97914.5803 | 97914.5803 | 100 | 104 | 100 | 100 | 133.4383 | 100
7 | Afbraak stak afw kant TL & DD IV | 2007-02-26 08:00 | 2007-03-02 17:00 | 5d |  | 0 | 116.25 | 178.93 | 7157.1997 | 7273.4497 | 2007-02-26 08:00 | 5d | 7273.4497 | 0 | 0 | -120 | 0 | 7153.4497 | 0 | 100% | Finished | 7273.4497 | 7273.4497 | 100 | 100 | 100 | 100 | 98.3502 | 100
8 | Heien buispalen stak afw kant TL, DD IV & SS A1 (9 st) | 2007-03-05 08:00 | 2007-03-09 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-03-05 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 148.0122 | 100
9 | Montage stak afw kant TL & DD IV | 2007-03-22 08:00 | 2007-03-27 17:00 | 4d |  | 0 | 0 | 1119.11 | 35811.5195 | 35811.5195 | 2007-03-22 08:00 | 4d | 35811.5195 | 0 | 0 | 3975 | 0 | 39786.5195 | 0 | 100% | Finished | 35811.5195 | 35811.5195 | 100 | 100 | 100 | 100 | 111.0998 | 100
10 | Afbraak stak afw kant WK & DD V | 2007-03-28 08:00 | 2007-04-03 17:00 | 5d |  | 0 | 0 | 178.93 | 7157.1997 | 7157.1997 | 2007-03-28 08:00 | 5d | 7157.1997 | 0 | 0 | 0 | 0 | 7157.1997 | 0 | 100% | Finished | 7157.1997 | 7157.1997 | 100 | 100 | 100 | 100 | 100 | 100
11 | Heien buispalen stak afw kant WK, DD V & SS A4 (10 st) | 2007-04-04 08:00 | 2007-04-10 17:00 | 5d |  | 0 | 0 | 957.39 | 38295.6006 | 38295.6006 | 2007-04-04 08:00 | 5d | 38295.6006 | 0 | 0 | 18386.5391 | 0 | 56682.1396 | 0 | 100% | Finished | 38295.6006 | 38295.6006 | 100 | 100 | 100 | 100 | 148.0121 | 100
12 | Montage stak afw kant WK met verbindingen, & DD V | 2007-04-18 08:00 | 2007-04-25 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-04-18 08:00 | 6d | 53717.2793 | 0 | 0 | 5960.3799 | 0 | 59677.6592 | 0 | 100% | Finished | 53717.2793 | 53717.2793 | 100 | 100 | 100 | 100 | 111.0958 | 100
13 | Heien buispalen stak afw: kop (7 st) | 2007-04-26 08:00 | 2007-05-01 17:00 | 4d |  | 0 | 0 | 837.71 | 26806.7207 | 26806.7207 | 2007-04-26 08:00 | 3d | 20105.0405 | 0 | 0 | 19572.4297 | 0 | 39677.4702 | 0 | 100% | Finished | 26806.7207 | 26806.7207 | 100 | 75 | 100 | 100 | 148.0131 | 100
14 | Montage stak afw kop | 2007-05-04 08:00 | 2007-05-10 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 2007-05-04 08:00 | 5d | 44764.3994 | 0 | 0 | 4966.9902 | 0 | 49731.3896 | 0 | 100% | Finished | 44764.3994 | 44764.3994 | 100 | 100 | 100 | 100 | 111.0958 | 100
15 | Afbraak stak opw kant WK, DD II + III & helft gasleiding | 2007-05-11 08:00 | 2007-05-22 17:00 | 8d |  | 0 | 0 | 178.93 | 11451.5195 | 11451.5195 | 2007-05-11 08:00 | 8d | 11451.5195 | 0 | 0 | 0 | 0 | 11451.5195 | 0 | 100% | Finished | 11451.5195 | 11451.5195 | 100 | 100 | 100 | 100 | 100 | 100
16 | Heien buispalen stak opw kant WK, DD II & SS O4 (9 st) | 2007-05-25 08:00 | 2007-05-31 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-05-25 08:00 | 5d | 34466.001 | 0 | 0 | 23441.0898 | 0 | 57907.0908 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 168.0122 | 100
17 | Montage stak opw kant WK & DD II | 2007-06-04 08:00 | 2007-06-11 17:00 | 6d |  | 0 | 0 | 1119.11 | 53717.2793 | 53717.2793 | 2007-06-04 08:00 | 6d | 53717.2793 | 0 | 0 | 5960.3799 | 0 | 59677.6592 | 0 | 100% | Finished | 53717.2793 | 53717.2793 | 100 | 100 | 100 | 100 | 111.0958 | 100
18 | Afbraak stak opw kant TL, DD I & helft gasleiding | 2007-06-12 08:00 | 2007-06-21 17:00 | 8d |  | 0 | 116.25 | 178.93 | 11451.5195 | 11567.7695 | 2007-06-12 08:00 | 8d | 11567.7695 | 0 | 0 | -116.37 | 0 | 11451.3995 | 0 | 100% | Finished | 11567.7695 | 11567.7695 | 100 | 100 | 100 | 100 | 98.994 | 100
19 | Heien buispalen stak opw kant TL, DD I & SS O1(9 st) | 2007-06-22 08:00 | 2007-06-28 17:00 | 5d |  | 0 | 0 | 861.65 | 34466.001 | 34466.001 | 2007-06-22 08:00 | 5d | 34466.001 | 0 | 0 | 16547.8906 | 0 | 51013.8916 | 0 | 100% | Finished | 34466.001 | 34466.001 | 100 | 100 | 100 | 100 | 148.0122 | 100
20 | Montage stak opw kant TL met verbindingen, & DD I | 2007-06-29 08:00 | 2007-07-10 17:00 | 8d |  | 0 | 0 | 1119.11 | 71623.0391 | 71623.0391 | 2007-08-01 08:00 | 8d | 71623.0391 | 0 | 0 | 7947.1802 | 0 | 79570.2192 | 0 | 100% | Finished | 71623.0391 | 71623.0391 | 100 | 100 | 100 | 100 | 111.0958 | 100
21 | Heien buispalen stak opw: kop (7 st) | 2007-07-11 08:00 | 2007-07-16 17:00 | 4d |  | 0 | 1966.2 | 837.71 | 26806.7207 | 28772.9207 | 2007-07-11 08:00 | 4d | 28772.9207 | 0 | 0 | 12870.8301 | 0 | 41643.7507 | 0 | 100% | Finished | 28772.9207 | 28772.9207 | 100 | 100 | 100 | 100 | 144.7324 | 100
22 | Montage stak opw kop | 2007-08-07 08:00 | 2007-08-13 17:00 | 5d |  | 0 | 0 | 1119.11 | 44764.3994 | 44764.3994 | 2007-08-07 08:00 | 5d | 44764.3994 | 0 | 0 | 4966.9902 | 0 | 49731.3896 | 0 | 100% | Finished | 44764.3994 | 44764.3994 | 100 | 100 | 100 | 100 | 111.0958 | 100
23 | Roosters | 2007-08-14 08:00 | 2007-08-20 17:00 | 5d |  | 0 | 0 | 779.25 | 31170 | 31170 | 2007-08-14 08:00 | 5d | 31170 | 0 | 0 | -21705.4805 | 0 | 9464.5195 | 0 | 100% | Finished | 31170 | 31170 | 100 | 100 | 100 | 100 | 30.3642 | 100
24 | Scheepvaartseinen | 2007-08-22 08:00 | 2007-08-27 17:00 | 4d |  | 0 | 33154.6094 | 0 | 0 | 33154.6094 | 2007-08-22 08:00 | 4d | 33154.6094 | 0 | 0 | -1586.98 | 0 | 31567.6294 | 0 | 100% | Finished | 33154.6094 | 33154.6094 | 100 | 100 | 100 | 100 | 95.2134 | 100
25 | Kabels voedingen | 2007-08-28 08:00 | 2007-08-30 17:00 | 3d |  | 0 | 19666.5605 | 0 | 0 | 19666.5605 | 2007-08-28 08:00 | 3d | 19666.5605 | 0 | 0 | 14802.9004 | 0 | 34469.4609 | 0 | 100% | Finished | 19666.5605 | 19666.5605 | 100 | 100 | 100 | 100 | 175.2694 | 100
26 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-23 17:00 | 10d |  |  | 29855.1895 |  |  | 54887.1091 |  | 10d | [5 empty] | 54887.1091 |  | 100% |  | 54887.1091 | 54887.1091
27 | Gestuurde boring | 2007-03-12 08:00 | 2007-03-20 17:00 | 7d |  | 0 | 25079.0195 | 378.62 | 21202.7197 | 46281.7393 | 2007-03-12 08:00 | 7d | 46281.7393 | 0 | 0 | 0 | 0 | 46281.7393 | 0 | 100% | Finished | 46281.7393 | 46281.7393 | 100 | 100 | 100 | 100 | 100 | 100
28 | Heien buispaal tbv boring | 2007-03-21 08:00 | 2007-03-21 17:00 | 1d |  | 0 | 0 | 478.65 | 3829.2 | 3829.2 | 2007-03-21 08:00 | 1d | 3829.2 | 0 | 0 | 0 | 0 | 3829.2 | 0 | 100% | Finished | 3829.2 | 3829.2 | 100 | 100 | 100 | 100 | 100 | 100
29 | Trekontlastingen, borden | 2007-03-22 08:00 | 2007-03-23 17:00 | 2d |  | 0 | 4776.1699 | 0 | 0 | 4776.1699 | 2007-03-22 08:00 | 2d | 4776.1699 | 0 | 0 | 0 | 0 | 4776.1699 | 0 | 100% | Finished | 4776.1699 | 4776.1699 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelwerken | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  |  | 5963.3999 |  |  | 24123.3999 |  | 54d | [5 empty] | 50598.7983 |  | 100% |  | 24123.3999 | 24123.3999
31 | Fase 4: kabels door ingebaggerde buizen | 2007-03-22 08:00 | 2007-04-04 17:00 | 10d |  | 0 | 5963.3999 | 227 | 18160 | 24123.3999 | 2007-03-22 08:00 | 54d | 104027.3999 | 0 | 0 | -53428.6016 | 0 | 50598.7983 | 0 | 100% | Finished | 24123.3999 | 24123.3999 | 100 | 540 | 100 | 100 | 209.7499 | 100
32 | Dukdalven | 2007-06-29 08:00 | 2007-08-24 17:00 | 41d |  |  | 52913.5192 |  |  | 114453.359 |  | 46d | [5 empty] | 146330.3575 |  | 100% |  | 114453.359 | 114453.359
33 | Stalen brugjes | 2007-06-29 08:00 | 2007-07-20 17:00 | 16d |  | 0 | 902.15 | 480.78 | 61539.8398 | 62441.9899 | 2007-06-29 08:00 | 46d | 177829.1896 | 0 | 0 | -98313.1016 | 0 | 79516.088 | 0 | 100% | Finished | 62441.9899 | 62441.9899 | 100 | 287.5 | 100 | 100 | 127.3439 | 100
34 | Scheepvaartseinen | 2007-08-13 08:00 | 2007-08-17 17:00 | 5d |  | 0 | 30008.4395 | 0 | 0 | 30008.4395 | 2007-08-13 08:00 | 5d | 30008.4395 | 0 | 0 | 0 | 0 | 30008.4395 | 0 | 100% | Finished | 30008.4395 | 30008.4395 | 100 | 100 | 100 | 100 | 100 | 100
35 | Kabels voedingen | 2007-08-21 08:00 | 2007-08-24 17:00 | 4d |  | 0 | 22002.9297 | 0 | 0 | 22002.9297 | 2007-08-21 08:00 | 4d | 22002.9297 | 0 | 0 | 14802.9004 | 0 | 36805.8301 | 0 | 100% | Finished | 22002.9297 | 22002.9297 | 100 | 100 | 100 | 100 | 167.277 | 100
36 | Stabilisatie landhoofd | 2007-03-22 08:00 | 2007-05-11 17:00 | 37d |  |  | 78594.2688 |  |  | 128036.4286 |  | 53d | [5 empty] | 155786.7478 |  | 100% |  | 128036.4286 | 128036.4286
37 | Opzoeken leidingen in vaargeul | 2007-03-22 08:00 | 2007-03-22 17:00 | 1d |  | 0 | 1127.6899 | 0 | 0 | 1127.6899 | 2007-02-28 08:00 | 1d | 1127.6899 | 0 | 0 | 0 | 0 | 1127.6899 | 0 | 100% | Finished | 1127.6899 | 1127.6899 | 100 | 100 | 100 | 100 | 100 | 100
38 | Peiling 1 | 2007-03-23 08:00 | 2007-03-23 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-02-28 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
39 | Onderwater grondbanketten aanbrengen | 2007-03-26 08:00 | 2007-03-29 17:00 | 4d |  | 0 | 0 | 778.38 | 24908.1602 | 24908.1602 | 2007-03-26 08:00 | 6d | 37362.2402 | 0 | 0 | -16004.9404 | 0 | 21357.2998 | 0 | 100% | Finished | 24908.1602 | 24908.1602 | 100 | 150 | 100 | 100 | 85.7442 | 100
40 | Peiling 2 | 2007-03-30 08:00 | 2007-03-30 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-04-02 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
41 | Aanvoer boorinstallatie | 2007-04-02 08:00 | 2007-04-03 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-03-28 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 5125.8599 | 100 | 100 | 100 | 100 | 100 | 100
42 | Groutinjecties | 2007-04-04 08:00 | 2007-04-24 17:00 | 15d |  | 0 | 63370.4492 | 204.45 | 24533.9996 | 87904.4489 | 2007-03-28 08:00 | 20d | 96082.4487 | 0 | 0 | 23123.1797 | 0 | 119205.6284 | 0 | 100% | Finished | 87904.4489 | 87904.4489 | 100 | 133.3333 | 100 | 100 | 135.6082 | 100
43 | Buitendienststellingsweekend 1 | 2007-04-27 17:00 | 2007-04-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-04-27 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
44 | Buitendienststellingsweekend 2 | 2007-05-04 17:00 | 2007-05-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
45 | Buitendienststellingsweekend 3 | 2007-05-11 17:00 | 2007-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2007-05-14 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
46 | Peiling 3 | 2007-05-04 08:00 | 2007-05-04 17:00 | 1d |  | 0 | 1281.47 | 0 | 0 | 1281.47 | 2007-05-04 08:00 | 1d | 1281.47 | 0 | 0 | 0 | 0 | 1281.47 | 0 | 100% | Finished | 1281.47 | 1281.47 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afvoer boorinstallatie | 2007-05-07 08:00 | 2007-05-08 17:00 | 2d |  | 0 | 5125.8599 | 0 | 0 | 5125.8599 | 2007-05-07 08:00 | 2d | 5125.8599 | 0 | 0 | 0 | 0 | 5125.8599 | 0 | 100% | Finished | 5125.8599 | 5125.8599 | 100 | 100 | 100 | 100 | 100 | 100
48 | Opkuis werf | 2007-08-27 08:00 | 2007-08-31 17:00 | 5d |  | 0 | 3776.3201 | 0 | 0 | 3776.3201 | 2007-08-27 08:00 | 5d | 3776.3201 | 0 | 0 | 0 | 0 | 3776.3201 | 0 | 100% | Finished | 3776.3201 | 3776.3201 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
28/02, 2007 | 2007-02-01 08:00 | 2007-02-28 17:00 | 50238.899 | 35702.139 | 31927.8793 | 2007-02-16 17:00 | -14536.76 | 71.06% | 3774.2598 | 111.8% | -8d | 60% | 72.65% | 2007-09-05 09:00 | 2007-11-27 16:00 | 2007-10-26 10:00 | 2007-09-10 15:00 | 2007-11-27 16:00 | 2007-10-30 11:00 | 2007-09-12 17:00 | 2008-01-22 11:00 | 2007-12-18 14:00 | 1065758.1556 | 956466.5522 | 1486700.5141 | 1754978.3399 | 1332908.8932 | 1572825.6674 | 1029160.6147 | 1050911.9322 | 0.6 | 1.1182 | 0.71065 | 0.72647 | -8 | 1.1182 | 1 | 0.6 | 1
31/03, 2007 | 2007-02-28 17:00 | 2007-03-31 17:00 | 250546.5984 | 262647.0062 | 228566.257 | 2007-04-03 15:00 | 12100.4078 | 104.8% | 34080.7492 | 114.9% | 1d 6h | 104.2% | 75.49% | 2007-08-30 10:00 | 2007-08-22 17:00 | 2007-07-27 09:00 | 2007-08-29 17:00 | 2007-08-22 17:00 | 2007-08-03 14:00 | 2007-08-30 10:00 | 2007-08-23 16:00 | 2007-08-06 11:00 | 1035451.6662 | 930751.2179 | 998277.6559 | 1003176.2498 | 898400.861 | 902663.8194 | 943291.7273 | 944132.1142 | 1.0417 | 1.1491 | 1.0483 | 0.7549 | 1.75 | 1.1491 | 1 | 1.0417 | 1
30/04, 2007 | 2007-03-31 17:00 | 2007-04-30 17:00 | 483775.9474 | 450217.6263 | 524633.1573 | 2007-04-24 16:00 | -33558.3211 | 93.06% | -74415.531 | 85.82% | -4d 1h | 93.45% | 93.4% | 2007-09-07 15:00 | 2007-09-18 11:00 | 2007-10-25 11:00 | 2007-09-07 11:00 | 2007-09-18 11:00 | 2007-10-10 16:00 | 2007-09-07 09:00 | 2007-09-17 14:00 | 2007-10-10 09:00 | 1143947.9464 | 1246313.1941 | 1190110.4317 | 1187339.4284 | 1300105.7803 | 1296876.7636 | 1234325.8015 | 1233693.4388 | 0.93452 | 0.85816 | 0.93063 | 0.93398 | -4.125 | 0.85816 | 1 | 0.93452 | 1
31/05, 2007 | 2007-04-30 17:00 | 2007-05-31 17:00 | 609219.9974 | 602515.1974 | 764311.585 | 2007-05-31 09:00 | -6704.8 | 98.9% | -161796.3876 | 78.83% | -7h | 98.98% | 99.02% | 2007-09-03 17:00 | 2007-09-04 15:00 | 2007-10-31 17:00 | 2007-09-03 17:00 | 2007-09-04 15:00 | 2007-09-28 16:00 | 2007-09-03 16:00 | 2007-09-04 12:00 | 2007-09-28 15:00 | 1231328.803 | 1356739.2477 | 1236525.7791 | 1236129.2737 | 1363331.7935 | 1362828.8125 | 1328037.2645 | 1327924.1771 | 0.98983 | 0.78831 | 0.98899 | 0.99024 | -0.875 | 0.78831 | 1 | 0.98983 | 1
30/06, 2007 | 2007-05-31 17:00 | 2007-06-30 17:00 | 735852.4772 | 723668.7557 | 918901.8244 | 2007-06-28 17:00 | -12183.7215 | 98.34% | -195233.0687 | 78.75% | -1d | 99.07% | 100% | 2007-09-04 15:00 | 2007-09-05 12:00 | 2007-11-02 10:00 | 2007-09-04 15:00 | 2007-09-05 12:00 | 2007-09-24 11:00 | 2007-09-03 17:00 | 2007-09-04 11:00 | 2007-09-20 17:00 | 1264765.4841 | 1358073.4004 | 1270588.4611 | 1268028.3488 | 1365467.3138 | 1362216.5284 | 1337259.4227 | 1336530.8236 | 0.99065 | 0.78754 | 0.98344 | 1 | -1 | 0.78754 | 1 | 0.99065 | 1
Actual Schedule | 2007-06-30 17:00 | 2007-08-31 17:00 | 1069532.4154 | 1069532.4154 | 1314584.5815 | 2007-08-31 17:00 | 0 | 100% | -245052.1661 | 81.36% | 0 | 100% | 100% | 2007-08-31 17:00 | 2007-08-31 17:00 | 2007-10-19 16:00 | 2007-08-31 17:00 | 2007-08-31 17:00 | 2007-08-31 17:00 | 2007-08-31 17:00 | 2007-08-31 17:00 | 2007-08-31 17:00 | 1314584.5815 | 1314584.5815 | 1314584.5815 | 1314584.5815 | 1314584.5815 | 1314584.5815 | 1314584.5815 | 1314584.5815 | 1 | 0.81359 | 1 | 1 | 0 | 0.81359 | 1 | 1 | 1