## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Tanglewood 4 | 1 |  |  | 2020-01-01 08:00 | 2022-07-27 18:00 | 671d |  |  | 0 |  |  | 13812918.75 | 938.4167
32 | ActivityGroup | 1.1 |  |  | 2020-01-01 08:00 | 2020-01-15 18:00 | 11d |  |  | 0 |  |  | 6187.5 | 14.4167
1 | Geotechnical site investigation | 1.1.1 |  | FS3 | 2020-01-01 08:00 | 2020-01-15 18:00 | 11d | Engineers[2.00 #8] | 6187.5 | 0 | 0 | 0 | 6187.5 | 14.4167
33 | ActivityGroup | 1.2 |  |  | 2020-01-16 08:00 | 2020-07-16 18:00 | 131d |  |  | 0 |  |  | 701718.75 | 182.4167
3 | Stormwater pollution prevention plan design | 1.2.1 | 1FS;2FS | FS4;FS5;FS6;FS7;FS8 | 2020-01-16 08:00 | 2020-04-01 18:00 | 55d | Engineers[2.00 #8] | 30937.5 | 0 | 0 | 0 | 30937.5 | 76.4167
4 | Civil engineering | 1.2.2 | 3FS | FS9;FS10;FS11;FS12;FS13;FS14;FS15;FS16 | 2020-04-02 08:00 | 2020-05-13 18:00 | 30d | Engineers[4.00 #8] | 33750 | 0 | 0 | 0 | 33750 | 41.4167
5 | Pile foundation engineering | 1.2.3 | 3FS | FS9;FS10;FS11;FS12;FS13;FS14;FS15;FS16 | 2020-05-14 08:00 | 2020-05-27 18:00 | 10d | Engineers[3.00 #8] | 8437.5 | 0 | 0 | 0 | 8437.5 | 13.4167
6 | AC/DC system engineering | 1.2.4 | 3FS | FS9;FS10;FS11;FS12;FS13;FS14;FS15;FS16 | 2020-04-02 08:00 | 2020-07-16 18:00 | 76d | Engineers[2.00 #8] | 42750 | 0 | 0 | 0 | 42750 | 105.4167
8 | SCADA engineering | 1.2.5 | 3FS | FS9;FS10;FS11;FS12;FS13;FS14;FS15;FS16 | 2020-04-02 08:00 | 2020-06-09 18:00 | 49d | Engineers[2.00 #8];Workers[10.00 #58] | 578812.5 | 0 | 0 | 0 | 578812.5 | 68.4167
7 | BLA & CAB system - shoals | 1.2.6 | 3FS | FS9;FS10;FS11;FS12;FS13;FS14;FS15;FS16 | 2020-05-14 08:00 | 2020-06-17 18:00 | 25d | Engineers | 7031.25 | 0 | 0 | 0 | 7031.25 | 34.4167
2 | Electrical site investigation | 1.3 |  | FS3 | 2020-01-01 08:00 | 2020-01-15 18:00 | 11d | Engineers[3.00 #8] | 9281.25 | 0 | 0 | 0 | 9281.25 | 14.4167
34 | ActivityGroup | 1.4 |  |  | 2020-07-17 08:00 | 2021-01-14 18:00 | 130d |  |  | 0 |  |  | 826200 | 181.4167
9 | AC cable & fiber procurement | 1.4.1 | 4FS;5FS;6FS;7FS;8FS | FS17;FS27 | 2020-07-17 08:00 | 2020-10-21 18:00 | 69d | Purchasepeople | 93150 | 0 | 0 | 0 | 93150 | 96.4167
10 | DC cable - procurement | 1.4.2 | 4FS;5FS;6FS;7FS;8FS | FS17;FS27 | 2020-07-17 08:00 | 2020-09-09 18:00 | 39d | Purchasepeople | 52650 | 0 | 0 | 0 | 52650 | 54.4167
11 | Piles - procurement | 1.4.3 | 4FS;5FS;6FS;7FS;8FS | FS17;FS27 | 2020-07-17 08:00 | 2020-10-15 18:00 | 65d | Purchasepeople | 87750 | 0 | 0 | 0 | 87750 | 90.4167
12 | Racking - procurement | 1.4.4 | 4FS;5FS;6FS;7FS;8FS | FS17;FS27 | 2020-07-17 08:00 | 2020-11-27 18:00 | 96d | Purchasepeople | 129600 | 0 | 0 | 0 | 129600 | 133.4167
13 | PV modules - procurement | 1.4.5 | 4FS;5FS;6FS;7FS;8FS | FS17;FS27 | 2020-07-17 08:00 | 2021-01-08 18:00 | 126d | Purchasepeople | 170100 | 0 | 0 | 0 | 170100 | 175.4167
14 | Inverters - procurement | 1.4.6 | 4FS;5FS;6FS;7FS;8FS | FS17;FS27 | 2020-07-17 08:00 | 2021-01-14 18:00 | 130d | Purchasepeople | 175500 | 0 | 0 | 0 | 175500 | 181.4167
15 | BLA - procurement | 1.4.7 | 4FS;5FS;6FS;7FS;8FS | FS17 | 2020-10-16 08:00 | 2020-12-22 18:00 | 48d | Purchasepeople | 64800 | 0 | 0 | 0 | 64800 | 67.4167
16 | CAB - procurement | 1.4.8 | 4FS;5FS;6FS;7FS;8FS | FS17;FS27 | 2020-09-10 08:00 | 2020-11-03 18:00 | 39d | Purchasepeople | 52650 | 0 | 0 | 0 | 52650 | 54.4167
17 | Mobilization | 1.5 | 9FS;10FS;11FS;12FS;13FS;14FS;15FS;16FS | FS18 | 2021-01-15 08:00 | 2021-03-29 18:00 | 52d | Workers[15.00 #58] | 877500 | 0 | 0 | 0 | 877500 | 73.4167
35 | construction | 1.6 |  |  | 2021-03-30 08:00 | 2022-06-14 18:00 | 316d |  |  | 0 |  |  | 8248781.25 | 441.4167
18 | Clearing & grading | 1.6.1 | 17FS | FS19 | 2021-03-30 08:00 | 2021-10-19 18:00 | 146d | Engineers[2.00 #8];Workers[25.00 #58] | 4188375 | 0 | 0 | 0 | 4188375 | 203.4167
19 | sub array works | 1.6.2 | 18FS | FS20;FS21;FS22;FS23 | 2021-10-20 08:00 | 2022-01-10 18:00 | 59d | Engineers[4.00 #8];Workers[35.00 #58] | 2389500 | 0 | 0 | 0 | 2389500 | 82.4167
20 | AC electrical | 1.6.3 | 19FS | FS25;FS24 | 2022-01-11 08:00 | 2022-03-25 18:00 | 54d | Workers[5.00 #58] | 303750 | 0 | 0 | 0 | 303750 | 73.4167
21 | DC electrical | 1.6.4 | 19FS | FS25;FS24 | 2022-01-11 08:00 | 2022-04-12 18:00 | 66d | Workers[5.00 #58] | 371250 | 0 | 0 | 0 | 371250 | 91.4167
22 | Roads | 1.6.5 | 19FS | FS25;FS24 | 2022-01-11 08:00 | 2022-01-28 18:00 | 14d | Engineers;Workers[7.00 #58] | 114187.5 | 0 | 0 | 0 | 114187.5 | 17.4167
23 | Met station | 1.6.6 | 19FS | FS25;FS24 | 2022-01-11 08:00 | 2022-01-17 18:00 | 5d | Engineers[2.00 #8];Workers[13.00 #58] | 75937.5 | 0 | 0 | 0 | 75937.5 | 6.4167
25 | Mechanical completion circuits | 1.6.7 | 20FS;21FS;22FS;23FS | FS26 | 2022-04-18 08:00 | 2022-04-19 18:00 | 2d | Workers[15.00 #58] | 33750 | 0 | 0 | 0 | 33750 | 1.4167
24 | Electrical testing | 1.6.8 | 20FS;21FS;22FS;23FS | FS26 | 2022-04-13 08:00 | 2022-06-14 18:00 | 45d | Engineers;Workers[15.00 #58] | 772031.25 | 0 | 0 | 0 | 772031.25 | 62.4167
26 | Energization circuits | 1.7 | 25FS;24FS | FS29 | 2022-06-15 08:00 | 2022-06-16 18:00 | 2d | Engineers[5.00 #8];Workers[15.00 #58] | 36562.5 | 0 | 0 | 0 | 36562.5 | 1.4167
36 | Substation | 1.8 |  |  | 2022-01-31 08:00 | 2022-04-15 18:00 | 55d |  |  | 0 |  |  | 2676093.75 | 74.4167
27 | Construction substation | 1.8.1 | 9FS;10FS;11FS;12FS;13FS;14FS;16FS | FS28 | 2022-01-31 08:00 | 2022-04-15 18:00 | 55d | Engineers[5.00 #8];Workers[42.00 #58] | 2676093.75 | 0 | 0 | 0 | 2676093.75 | 74.4167
37 | Commisioning | 1.9 |  |  | 2022-06-17 08:00 | 2022-07-27 18:00 | 29d |  |  | 0 |  |  | 380531.25 | 40.4167
29 | Inverter commissioning | 1.9.1 | 26FS;28FS | FS30 | 2022-06-17 08:00 | 2022-06-24 18:00 | 6d | Engineers[2.00 #8];Workers[10.00 #58] | 70875 | 0 | 0 | 0 | 70875 | 7.4167
30 | Commissioning sub arrays | 1.9.2 | 29FS | FS31 | 2022-06-27 08:00 | 2022-07-06 18:00 | 8d | Engineers[2.00 #8];Workers[10.00 #58] | 94500 | 0 | 0 | 0 | 94500 | 9.4167
31 | IV curve testing | 1.9.3 | 30FS |  | 2022-07-07 08:00 | 2022-07-27 18:00 | 15d | Engineers[3.00 #8];Workers[12.00 #58] | 215156.25 | 0 | 0 | 0 | 215156.25 | 20.4167
28 | Energization | 1.10 | 27FS | FS29 | 2022-04-18 08:00 | 2022-04-19 18:00 | 2d | Engineers;Workers[22.00 #58] | 50062.5 | 0 | 0 | 0 | 50062.5 | 1.4167

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Workers | Renewable | 58 W | 0 | 125 | 8[10.00 Workers];17[15.00 Workers];18[25.00 Workers];19[35.00 Workers];20[5.00 Workers];21[5.00 Workers];22[7.00 Workers];23[13.00 Workers];25[15.00 Workers];24[15.00 Workers];26[15.00 Workers];27[42.00 Workers];29[10.00 Workers];30[10.00 Workers];31[12.00 Workers];28[22.00 Workers]; | 12551625
2 | Engineers | Renewable | 8 E | 0 | 31.25 | 1[2.00 Engineers];3[2.00 Engineers];4[4.00 Engineers];5[3.00 Engineers];6[2.00 Engineers];8[2.00 Engineers];7;2[3.00 Engineers];18[2.00 Engineers];19[4.00 Engineers];22;23[2.00 Engineers];24;26[5.00 Engineers];27[5.00 Engineers];29[2.00 Engineers];30[2.00 Engineers];31[3.00 Engineers];28; | 435093.75
3 | Purchasepeople | Renewable | 6 P | 0 | 150 | 9;10;11;12;13;14;15;16; | 826200

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Tanglewood 4 | 6039h |  |  |  |  | 99 | 100 | 101
32 | ActivityGroup | 99h |  |  |  |  | 99 | 100 | 101
1 | Geotechnical site investigation | 99h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | ActivityGroup | 1179h |  |  |  |  | 99 | 100 | 101
3 | Stormwater pollution prevention plan design | 495h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Civil engineering | 270h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Pile foundation engineering | 90h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | AC/DC system engineering | 684h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | SCADA engineering | 441h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | BLA & CAB system - shoals | 225h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Electrical site investigation | 99h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | ActivityGroup | 1170h |  |  |  |  | 99 | 100 | 101
9 | AC cable & fiber procurement | 621h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | DC cable - procurement | 351h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Piles - procurement | 585h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Racking - procurement | 864h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | PV modules - procurement | 1134h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Inverters - procurement | 1170h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | BLA - procurement | 432h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | CAB - procurement | 351h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Mobilization | 468h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | construction | 2844h |  |  |  |  | 99 | 100 | 101
18 | Clearing & grading | 1314h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | sub array works | 531h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | AC electrical | 486h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | DC electrical | 594h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Roads | 126h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Met station | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Mechanical completion circuits | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Electrical testing | 405h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Energization circuits | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Substation | 495h |  |  |  |  | 99 | 100 | 101
27 | Construction substation | 495h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Commisioning | 261h |  |  |  |  | 99 | 100 | 101
29 | Inverter commissioning | 54h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Commissioning sub arrays | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | IV curve testing | 135h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Energization | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | Yes
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))