## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Defense Building | 1 |  |  | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 | 389.375
1 | Plaatsbeschrijving | 1.1 |  | FS3 | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 0.375
2 | Opstellen URS | 1.2 |  | FS4;FS5 | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 6.375
3 | Werfinrichting / stofwanden | 1.3 | 1FS | FS7;FS8;FS9;FS10;FS12+3d | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 13.375
4 | Risk Assessment | 1.4 | 2FS |  | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 6.375
5 | Uitzetten van de werf | 1.5 | 2FS | FS7;FS8;FS9;FS10;FS19 | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 7.375
6 | Validation Master Plan | 1.6 |  |  | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 112.375
7 | Metselwerken / Betonwerken | 1.7 | 3FS;5FS | FS14-2w;FS18;FS17 | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 26.375
8 | Voorbereiding technieken | 1.8 | 3FS;5FS |  | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 36.375
9 | Voeding werfzone | 1.9 | 3FS;5FS | FS11 | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 0.375
10 | Plaatsen afvoeren | 1.10 | 3FS;5FS |  | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 6.375
11 | Afbraak en/of omleggen bestaand bord | 1.11 | 9FS |  | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 1.375
12 | Groepen plaatsen | 1.12 | 3FS+3d | FS48 | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 13.375
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 1.13 |  |  | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 6.375
14 | Kanalen | 1.14 | 7FS-2w |  | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 27.375
15 | Plaatsen waterinstallatie in Techn Ruimte | 1.15 | 17FS |  | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 27.375
17 | Pleisterwerken | 1.16 | 7FS | FS27;FS15 | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 21.375
18 | Plaatsen nieuwe centrale op niv -2 | 1.17 | 7FS |  | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 6.375
16 | plaatsen stalen poutrellen ter versteviging | 1.18 | 46SS |  | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 1.375
19 | demonteren plafonds niv 0 | 1.19 | 5FS;27SF-1w |  | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 4.375
20 | maken doorvoeren niv +1 -> gvl | 1.20 |  | FS25;FS24 | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 6.375
21 | Kabels naar bord verd -2 | 1.21 |  |  | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 5.375
22 | Plaatsen toevoerleidingen + isolatie | 1.22 |  | FS37 | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 42.375
23 | Plaatsen leidingen | 1.23 |  |  | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 43.375
24 | plaatsen afvoeren en aansluiten op niv 0 | 1.24 | 20FS | FS33 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 28.375
25 | Maken doorvoeren dak -> niv +1 | 1.25 | 20FS | FS26 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 1.375
26 | Aanpassingswerken dak | 1.26 | 25FS |  | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 7.375
27 | Chape | 1.27 | 17FS | FS36;FS28;SF19-1w | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 6.375
28 | Piping | 1.28 | 27FS | FS29 | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 41.375
29 | Bekabeling | 1.29 | 28FS |  | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 42.375
30 | Kabelgoten | 1.30 |  |  | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 14.375
31 | Plaatsen leidingen | 1.31 |  |  | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 14.375
32 | gipskartonwanden 1e zijde | 1.32 |  | FS51-2d;FS42+1d;FF38;FS35-1w | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 18.375
33 | dichtleggen plafond niv 0 | 1.33 | 24FS |  | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 0.375
34 | Alu buitenramen / roosters | 1.34 |  | FS40-1d | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 8.375
35 | Technieken in gipswanden | 1.35 | 32FS-1w | FS44 | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 19.375
36 | Leidingen trekken + inbouwbakjes | 1.36 | 27FS |  | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 26.375
37 | Plaatsen brandleiding + koppelingen | 1.37 | 22FS |  | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 11.375
38 | structuur voorzetwanden | 1.38 | 32FF | FS43;FS41 | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 5.375
39 | Beglaasde binnenramen | 1.39 | 41FF |  | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 6.375
40 | Buitenzonnewering | 1.40 | 34FS-1d |  | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 5.375
41 | gipskartonwanden 2e zijde, incl plamuren | 1.41 | 38FS | FS45-1w;FF39 | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 20.375
42 | Afmonteren data aansluitingen | 1.42 | 32FS+1d |  | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 15.375
43 | Plaatsen leidingen branddetectie | 1.43 | 38FS |  | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 10.375
44 | Technieken boven valse plafonds | 1.44 | 35FS |  | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 27.375
45 | Dichtzetten voorzetwanden | 1.45 | 41FS-1w | FS47 | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 3.375
46 | Laufervloer | 1.46 |  | SS16 | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 1.375
47 | Afwerken dagkanten ramen | 1.47 | 45FS | FS49 | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 6.375
48 | Hygienische coating Technische Ruimte | 1.48 | 12FS |  | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 6.375
49 | Wandbekleding binnenzijde gevel | 1.49 | 50FF;47FS |  | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 5.375
50 | Bekleden cleanroomwanden | 1.50 |  | FS65+4d;FS63;FS61;FS60;FS59-2d;FS58-2d;FS55-3d;FS56-3d;FS53-3d;FF49 | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 21.375
51 | Plaatsen metalen deuromlijstingen | 1.51 | 32FS-2d |  | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 5.375
52 | Beloopbaar verlaagd plafond Cleanroom | 1.52 |  |  | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 21.375
53 | Plaatsen schakelaars, stopcontacten | 1.53 | 50FS-3d |  | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 26.375
54 | Verlaagde plafonds | 1.54 |  |  | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 | 5.375
55 | Plaatsen verlichtingsarmaturen | 1.55 | 50FS-3d |  | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 58.375
56 | Plaatsen elektr borden | 1.56 | 50FS-3d | FS57-2d | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2.375
57 | Aansluiten elektr bord | 1.57 | 56FS-2d |  | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 20.375
58 | Plaatsen kranenwerk, toestellen | 1.58 | 50FS-2d |  | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 20.375
59 | Afwerking | 1.59 | 50FS-2d | FS64 | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 13.375
60 | Afgewerkte cleanroomwanden | 1.60 | 50FS |  | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
61 | Schilderwerken | 1.61 | 50FS | FS82 | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 | 18.375
62 | Plaatsen sokkels meubilair | 1.62 |  |  | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 4.375
63 | Elektronische borden | 1.63 | 50FS |  | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2.375
64 | Testen deel 1 | 1.64 | 59FS |  | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 6.375
65 | Harsgebonden bedrijfsvloer | 1.65 | 50FS+4d | FS69;FS68;FS67;FS66 | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 13.375
66 | Synthetische vinyl vloerbekleding, incl plinten | 1.66 | 65FS |  | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 | 1.375
67 | Meubilair | 1.67 | 65FS | SS91;SF87-1w;FS75;FF74 | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 | 19.375
68 | Plaatsen toestellen | 1.68 | 65FS | FS71-3w | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 | 33.375
69 | Data rack | 1.69 | 65FS | FS70 | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 | 1.375
70 | Aansluiten data rack | 1.70 | 69FS | FS73;FS72-1d | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 | 10.375
71 | Aansluiten toestellen | 1.71 | 68FS-3w | FS80 | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 | 20.375
72 | plaatsen sirenes, bord, brandmelders, … | 1.72 | 70FS-1d |  | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 | 33.375
73 | Verbinding data en telefonie | 1.73 | 70FS | FS77 | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 | 4.375
74 | Spiegel | 1.74 | 67FF |  | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 | 0.375
75 | Wand-en hoekbescherming | 1.75 | 67FS | FS76-4d | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 | 6.375
76 | Algemene afwerkingen | 1.76 | 75FS-4d | FS82 | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 | 13.375
77 | Testen deel 2 | 1.77 | 73FS | SS78 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 | 1.375
78 | Testen deel 3 | 1.78 | 77SS |  | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 | 0.375
79 | Keuringen en testen installatie | 1.79 | 82SS-1w |  | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 | 19.375
80 | Testen deel 4 | 1.80 | 71FS |  | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 | 6.375
81 | Plaatsen tabletten | 1.81 |  |  | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 6.375
82 | Signalisatie | 1.82 | 76FS;61FS | FF84;SS79-1w | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 | 6.375
83 | Eerste Rondgang der werken | 1.83 | 84SS | FS85 | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 | 6.375
84 | Eindschoonmaak | 1.84 | 82FF | SS83 | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 | 6.375
85 | Wegwerken eventuele opmerkingen | 1.85 | 83FS | FS90;FS88;FS86 | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 | 11.375
86 | Filters plaatsen + afwerking | 1.86 | 85FS |  | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 | 13.375
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 1.87 | 67SF-1w |  | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 | 13.375
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 1.88 | 85FS | FS92;SS89 | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 6.375
89 | Start validation | 1.89 | 88SS |  | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
90 | Verwijderen werfinrichting | 1.90 | 85FS |  | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 | 6.375
91 | Plaatsen deurbladen | 1.91 | 67SS |  | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 | 0.375
92 | Certificatietesten Cleanroom & HVAC | 1.92 | 88FS | FS95;FS93 | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 6.375
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 1.93 | 92FS |  | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 | 13.375
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 1.94 |  | FS95 | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 6.375
95 | Nakijken van uitgevoerde testen door uitvoerders | 1.95 | 92FS;94FS | FS96 | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 6.375
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 1.96 | 95FS | FS97 | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 4.375
97 | Ondersteuning ontwikkeling SOP's | 1.97 | 96FS | FS98 | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 | 39.375
98 | Verwijderen werfburelen | 1.98 | 97FS |  | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Defense Building | 2016h |  |  |  |  | 99 | 100 | 101
1 | Plaatsbeschrijving | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Opstellen URS | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
3 | Werfinrichting / stofwanden | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
4 | Risk Assessment | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Uitzetten van de werf | 48h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
6 | Validation Master Plan | 640h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Metselwerken / Betonwerken | 152h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
8 | Voorbereiding technieken | 216h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
9 | Voeding werfzone | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Plaatsen afvoeren | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Afbraak en/of omleggen bestaand bord | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
12 | Groepen plaatsen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Kanalen | 160h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
15 | Plaatsen waterinstallatie in Techn Ruimte | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Pleisterwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Plaatsen nieuwe centrale op niv -2 | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
16 | plaatsen stalen poutrellen ter versteviging | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
19 | demonteren plafonds niv 0 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | maken doorvoeren niv +1 -> gvl | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
21 | Kabels naar bord verd -2 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Plaatsen toevoerleidingen + isolatie | 240h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
23 | Plaatsen leidingen | 248h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
24 | plaatsen afvoeren en aansluiten op niv 0 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Maken doorvoeren dak -> niv +1 | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
26 | Aanpassingswerken dak | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
27 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Piping | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Bekabeling | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Kabelgoten | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Plaatsen leidingen | 88h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
32 | gipskartonwanden 1e zijde | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | dichtleggen plafond niv 0 | 8h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
34 | Alu buitenramen / roosters | 56h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
35 | Technieken in gipswanden | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Leidingen trekken + inbouwbakjes | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Plaatsen brandleiding + koppelingen | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
38 | structuur voorzetwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Beglaasde binnenramen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Buitenzonnewering | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | gipskartonwanden 2e zijde, incl plamuren | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Afmonteren data aansluitingen | 96h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
43 | Plaatsen leidingen branddetectie | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Technieken boven valse plafonds | 160h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
45 | Dichtzetten voorzetwanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Laufervloer | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
47 | Afwerken dagkanten ramen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Hygienische coating Technische Ruimte | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Wandbekleding binnenzijde gevel | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Bekleden cleanroomwanden | 120h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
51 | Plaatsen metalen deuromlijstingen | 32h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
52 | Beloopbaar verlaagd plafond Cleanroom | 120h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
53 | Plaatsen schakelaars, stopcontacten | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Verlaagde plafonds | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Plaatsen verlichtingsarmaturen | 216h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
56 | Plaatsen elektr borden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Aansluiten elektr bord | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Plaatsen kranenwerk, toestellen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Afwerking | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Afgewerkte cleanroomwanden | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Schilderwerken | 104h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
62 | Plaatsen sokkels meubilair | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Elektronische borden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Testen deel 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Harsgebonden bedrijfsvloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Synthetische vinyl vloerbekleding, incl plinten | 16h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
67 | Meubilair | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Plaatsen toestellen | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Data rack | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Aansluiten data rack | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Aansluiten toestellen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | plaatsen sirenes, bord, brandmelders, … | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Verbinding data en telefonie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Spiegel | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | Wand-en hoekbescherming | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | Algemene afwerkingen | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
77 | Testen deel 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Testen deel 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | Keuringen en testen installatie | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | Testen deel 4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | Plaatsen tabletten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | Signalisatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Eerste Rondgang der werken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | Eindschoonmaak | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | Wegwerken eventuele opmerkingen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Filters plaatsen + afwerking | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | Start validation | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | Verwijderen werfinrichting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Plaatsen deurbladen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Certificatietesten Cleanroom & HVAC | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Nakijken van uitgevoerde testen door uitvoerders | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Ondersteuning ontwikkeling SOP's | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | Verwijderen werfburelen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-02-03 08:00 |  | TP Name | T1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 688368.5344
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 |  | 0 | 0 | 935 | 1d | 0 | 0 | 0 | 935 | 0% | Not Started | 0 | 935 | 100 |  | 0 | 100 |  | 0
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 |  | 0 | 0 | 2937 | 5d | 0 | 0 | 0 | 2937 | 0% | Not Started | 0 | 2937 | 100 |  | 0 | 100 |  | 0
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 |  | 0 | 0 | 2435.05 | 10d | 0 | 0 | 0 | 2435.05 | 0% | Not Started | 0 | 2435.05 | 100 |  | 0 | 100 |  | 0
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 |  | 0 | 0 | 4928 | 5d | 0 | 0 | 0 | 4928 | 0% | Not Started | 0 | 4928 | 100 |  | 0 | 100 |  | 0
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 |  | 0 | 0 | 8937 | 6d | 0 | 0 | 0 | 8937 | 0% | Not Started | 0 | 8937 | 100 |  | 0 | 100 |  | 0
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 |  | 0 | 0 | 199353.2734 | 80d | 0 | 0 | 0 | 199353.2734 | 0% | Not Started | 0 | 87353.2734 | 100 |  | 0 | 100 |  | 0
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 |  | 0 | 0 | 51444.7695 | 19d | 0 | 0 | 0 | 51444.7695 | 0% | Not Started | 0 | 44404.7695 | 100 |  | 0 | 100 |  | 0
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 |  | 0 | 0 | 18357 | 27d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 6197 | 100 |  | 0 | 100 |  | 0
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 |  | 0 | 0 | 10000 | 1d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 |  | 0 | 0 | 31746.2207 | 5d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 31746.2207 | 100 |  | 0 | 100 |  | 0
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 |  | 0 | 0 | 10000 | 2d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 |  | 0 | 0 | 455069 | 10d | 0 | 0 | 0 | 455069 | 0% | Not Started | 0 | 447389 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 |  | 0 | 0 | 31746.2207 | 5d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 31106.2207 | 100 |  | 0 | 100 |  | 0
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 |  | 0 | 0 | 285454.1875 | 20d | 0 | 0 | 0 | 285454.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 |  | 0 | 0 | 32234.1797 | 20d | 0 | 0 | 0 | 32234.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 |  | 0 | 0 | 18854.4697 | 15d | 0 | 0 | 0 | 18854.4697 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 |  | 0 | 0 | 12002.4004 | 5d | 0 | 0 | 0 | 12002.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 |  | 0 | 0 | 21629.5098 | 2d | 0 | 0 | 0 | 21629.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 |  | 0 | 0 | 3008 | 3d | 0 | 0 | 0 | 3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 |  | 0 | 0 | 6670.9399 | 5d | 0 | 0 | 0 | 6670.9399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 |  | 0 | 0 | 7207 | 4d | 0 | 0 | 0 | 7207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 |  | 0 | 0 | 31746.2197 | 30d | 0 | 0 | 0 | 31746.2197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 |  | 0 | 0 | 17246.05 | 31d | 0 | 0 | 0 | 17246.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 |  | 0 | 0 | 5540.9199 | 20d | 0 | 0 | 0 | 5540.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 |  | 0 | 0 | 11485.7998 | 2d | 0 | 0 | 0 | 11485.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 |  | 0 | 0 | 1885.11 | 5d | 0 | 0 | 0 | 1885.11 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 |  | 0 | 0 | 30266.6895 | 5d | 0 | 0 | 0 | 30266.6895 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 |  | 0 | 0 | 92974.5781 | 30d | 0 | 0 | 0 | 92974.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 |  | 0 | 0 | 20000 | 30d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 |  | 0 | 0 | 8577.6101 | 11d | 0 | 0 | 0 | 8577.6101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 |  | 0 | 0 | 27983.5 | 11d | 0 | 0 | 0 | 27983.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 |  | 0 | 0 | 48507.7617 | 13d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 |  | 0 | 0 | 2876 | 1d | 0 | 0 | 0 | 2876 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 |  | 0 | 0 | 40211.3281 | 7d | 0 | 0 | 0 | 40211.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 |  | 0 | 0 | 34640 | 14d | 0 | 0 | 0 | 34640 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 |  | 0 | 0 | 44692.6992 | 19d | 0 | 0 | 0 | 44692.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 |  | 0 | 0 | 31746.2207 | 10d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 |  | 0 | 0 | 18409.8799 | 4d | 0 | 0 | 0 | 18409.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 |  | 0 | 0 | 30766.0508 | 5d | 0 | 0 | 0 | 30766.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 |  | 0 | 0 | 14837 | 12d | 0 | 0 | 0 | 14837 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 |  | 0 | 0 | 2908.17 | 9d | 0 | 0 | 0 | 2908.17 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 |  | 0 | 0 | 14283 | 20d | 0 | 0 | 0 | 14283 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 |  | 0 | 0 | 18409.8809 | 2d | 0 | 0 | 0 | 18409.8809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 |  | 0 | 0 | 1839.76 | 2d | 0 | 0 | 0 | 1839.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 |  | 0 | 0 | 17304 | 5d | 0 | 0 | 0 | 17304 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 |  | 0 | 0 | 5938 | 5d | 0 | 0 | 0 | 5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 |  | 0 | 0 | 254308.8125 | 4d | 0 | 0 | 0 | 254308.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 |  | 0 | 0 | 6840 | 15d | 0 | 0 | 0 | 6840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 |  | 0 | 0 | 2843 | 3d | 0 | 0 | 0 | 2843 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-03-03 08:00 |  | TP Name | T2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 10d | [5 empty] | 29372.05 |  | 0.6781% |  | 29372.0499 | 1111104.5214
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 9d | 2275.05 | 160 | 1d | 0 | 0 | 2275.05 | 160 | 90% | Started | 2275.0499 | 2435.05 | 100 | 90 | 90 | 100 | 93.4293 | 90
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 5d | 8297 | 640 | 1d | 0 | 0 | 8297 | 640 | 83.33% | Started | 8296.9999 | 8937 | 100 | 83.3333 | 83.3333 | 100 | 92.8388 | 83.3333
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 |  | 0 | 0 | 199353.2734 | 80d | 0 | 0 | 0 | 199353.2734 | 0% | Not Started | 0 | 119353.2734 | 100 |  | 0 | 100 |  | 0
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 |  | 0 | 0 | 51444.7695 | 19d | 0 | 0 | 0 | 51444.7695 | 0% | Not Started | 0 | 51444.7695 | 100 |  | 0 | 100 |  | 0
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 |  | 0 | 0 | 18357 | 27d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 |  | 0 | 0 | 31746.2207 | 5d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 31746.2207 | 100 |  | 0 | 100 |  | 0
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 |  | 0 | 0 | 10000 | 2d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 |  | 0 | 0 | 455069 | 10d | 0 | 0 | 0 | 455069 | 0% | Not Started | 0 | 455069 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 |  | 0 | 0 | 31746.2207 | 5d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 31746.2207 | 100 |  | 0 | 100 |  | 0
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 |  | 0 | 0 | 285454.1875 | 20d | 0 | 0 | 0 | 285454.1875 | 0% | Not Started | 0 | 284654.1875 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 |  | 0 | 0 | 32234.1797 | 20d | 0 | 0 | 0 | 32234.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 |  | 0 | 0 | 18854.4697 | 15d | 0 | 0 | 0 | 18854.4697 | 0% | Not Started | 0 | 15014.4697 | 100 |  | 0 | 100 |  | 0
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 |  | 0 | 0 | 12002.4004 | 5d | 0 | 0 | 0 | 12002.4004 | 0% | Not Started | 0 | 12002.4004 | 100 |  | 0 | 100 |  | 0
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 |  | 0 | 0 | 21629.5098 | 2d | 0 | 0 | 0 | 21629.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 |  | 0 | 0 | 3008 | 3d | 0 | 0 | 0 | 3008 | 0% | Not Started | 0 | 2368 | 100 |  | 0 | 100 |  | 0
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 |  | 0 | 0 | 6670.9399 | 5d | 0 | 0 | 0 | 6670.9399 | 0% | Not Started | 0 | 6670.9399 | 100 |  | 0 | 100 |  | 0
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 |  | 0 | 0 | 7207 | 4d | 0 | 0 | 0 | 7207 | 0% | Not Started | 0 | 7207 | 100 |  | 0 | 100 |  | 0
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 |  | 0 | 0 | 31746.2197 | 30d | 0 | 0 | 0 | 31746.2197 | 0% | Not Started | 0 | 16386.2197 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 |  | 0 | 0 | 17246.05 | 31d | 0 | 0 | 0 | 17246.05 | 0% | Not Started | 0 | 4766.05 | 100 |  | 0 | 100 |  | 0
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 |  | 0 | 0 | 5540.9199 | 20d | 0 | 0 | 0 | 5540.9199 | 0% | Not Started | 0 | 2660.9199 | 100 |  | 0 | 100 |  | 0
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 |  | 0 | 0 | 11485.7998 | 2d | 0 | 0 | 0 | 11485.7998 | 0% | Not Started | 0 | 11485.7998 | 100 |  | 0 | 100 |  | 0
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 |  | 0 | 0 | 1885.11 | 5d | 0 | 0 | 0 | 1885.11 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 |  | 0 | 0 | 30266.6895 | 5d | 0 | 0 | 0 | 30266.6895 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 |  | 0 | 0 | 92974.5781 | 30d | 0 | 0 | 0 | 92974.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 |  | 0 | 0 | 20000 | 30d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 |  | 0 | 0 | 8577.6101 | 11d | 0 | 0 | 0 | 8577.6101 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 |  | 0 | 0 | 27983.5 | 11d | 0 | 0 | 0 | 27983.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 |  | 0 | 0 | 48507.7617 | 13d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 |  | 0 | 0 | 2876 | 1d | 0 | 0 | 0 | 2876 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 |  | 0 | 0 | 40211.3281 | 7d | 0 | 0 | 0 | 40211.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 |  | 0 | 0 | 34640 | 14d | 0 | 0 | 0 | 34640 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 |  | 0 | 0 | 44692.6992 | 19d | 0 | 0 | 0 | 44692.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 |  | 0 | 0 | 31746.2207 | 10d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 |  | 0 | 0 | 18409.8799 | 4d | 0 | 0 | 0 | 18409.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 |  | 0 | 0 | 30766.0508 | 5d | 0 | 0 | 0 | 30766.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 |  | 0 | 0 | 14837 | 12d | 0 | 0 | 0 | 14837 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 |  | 0 | 0 | 2908.17 | 9d | 0 | 0 | 0 | 2908.17 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 |  | 0 | 0 | 14283 | 20d | 0 | 0 | 0 | 14283 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 |  | 0 | 0 | 18409.8809 | 2d | 0 | 0 | 0 | 18409.8809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 |  | 0 | 0 | 1839.76 | 2d | 0 | 0 | 0 | 1839.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 |  | 0 | 0 | 17304 | 5d | 0 | 0 | 0 | 17304 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 |  | 0 | 0 | 5938 | 5d | 0 | 0 | 0 | 5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 |  | 0 | 0 | 254308.8125 | 4d | 0 | 0 | 0 | 254308.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 |  | 0 | 0 | 6840 | 15d | 0 | 0 | 0 | 6840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 |  | 0 | 0 | 2843 | 3d | 0 | 0 | 0 | 2843 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-04-07 08:00 |  | TP Name | T3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 34d | [5 empty] | 628109.4609 |  | 14.51% |  | 628473.5992 | 1516753.9778
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 25d | 111353.2734 | 88000 | 55d | 0 | 0 | 111353.2734 | 88000 | 31.25% | Started | 111353.2734 | 157753.2734 | 100 | 31.25 | 31.25 | 100 | 55.8573 | 31.25
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 24d | 16437 | 1920 | 3d | 0 | 0 | 16437 | 1920 | 88.89% | Started | 16437.0001 | 18357 | 100 | 88.8889 | 88.8889 | 100 | 89.5408 | 88.8889
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 |  | 0 | 0 | 31746.2207 | 5d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 31746.2207 | 100 |  | 0 | 100 |  | 0
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 |  | 0 | 0 | 455069 | 10d | 0 | 0 | 0 | 455069 | 0% | Not Started | 0 | 455069 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 11d | 278254.1875 | 7200 | 9d | 0 | 0 | 278254.1875 | 7200 | 55% | Started | 278254.1877 | 285454.1875 | 100 | 55 | 55 | 100 | 97.4777 | 55
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 |  | 0 | 0 | 32234.1797 | 20d | 0 | 0 | 0 | 32234.1797 | 0% | Not Started | 0 | 30954.1797 | 100 |  | 0 | 100 |  | 0
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 4d | 11814.4697 | 7040 | 11d | 0 | 0 | 11814.4697 | 7040 | 26.67% | Started | 11814.4699 | 18854.4697 | 100 | 26.6667 | 26.6667 | 100 | 62.6614 | 26.6667
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 0 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 2d | 4750.9399 | 1920 | 3d | 0 | 0 | 4750.9399 | 1920 | 40% | Started | 4750.94 | 6670.9399 | 100 | 40 | 40 | 100 | 71.2184 | 40
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 2d | 5927 | 1280 | 2d | 0 | 0 | 5927 | 1280 | 50% | Started | 5927 | 7207 | 100 | 50 | 50 | 100 | 82.2395 | 50
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 14d | 21506.2197 | 10240 | 16d | 0 | 0 | 21506.2197 | 10240 | 46.67% | Started | 21506.2198 | 31746.2197 | 100 | 46.6667 | 46.6667 | 100 | 67.7442 | 46.6667
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 11d | 7646.05 | 8640 | 18d | 0 | 0 | 7646.05 | 8640 | 37.93% | Started | 8010.1879 | 16286.05 | 100 | 35.4839 | 37.931 | 100 | 44.3351 | 37.931
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 |  | 0 | 0 | 5540.9199 | 20d | 0 | 0 | 0 | 5540.9199 | 0% | Not Started | 0 | 5540.9199 | 100 |  | 0 | 100 |  | 0
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 |  | 0 | 0 | 11485.7998 | 2d | 0 | 0 | 0 | 11485.7998 | 0% | Not Started | 0 | 11485.7998 | 100 |  | 0 | 100 |  | 0
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 |  | 0 | 0 | 1885.11 | 5d | 0 | 0 | 0 | 1885.11 | 0% | Not Started | 0 | 1885.11 | 100 |  | 0 | 100 |  | 0
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 |  | 0 | 0 | 30266.6895 | 5d | 0 | 0 | 0 | 30266.6895 | 0% | Not Started | 0 | 30266.6895 | 100 |  | 0 | 100 |  | 0
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 |  | 0 | 0 | 92974.5781 | 30d | 0 | 0 | 0 | 92974.5781 | 0% | Not Started | 0 | 82094.5781 | 100 |  | 0 | 100 |  | 0
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 |  | 0 | 0 | 20000 | 30d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 |  | 0 | 0 | 27983.5 | 11d | 0 | 0 | 0 | 27983.5 | 0% | Not Started | 0 | 27983.5 | 100 |  | 0 | 100 |  | 0
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 |  | 0 | 0 | 48507.7617 | 13d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 47227.7617 | 100 |  | 0 | 100 |  | 0
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 |  | 0 | 0 | 2876 | 1d | 0 | 0 | 0 | 2876 | 0% | Not Started | 0 | 2876 | 100 |  | 0 | 100 |  | 0
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 |  | 0 | 0 | 40211.3281 | 7d | 0 | 0 | 0 | 40211.3281 | 0% | Not Started | 0 | 38291.3281 | 100 |  | 0 | 100 |  | 0
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 |  | 0 | 0 | 34640 | 14d | 0 | 0 | 0 | 34640 | 0% | Not Started | 0 | 27600 | 100 |  | 0 | 100 |  | 0
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 |  | 0 | 0 | 44692.6992 | 19d | 0 | 0 | 0 | 44692.6992 | 0% | Not Started | 0 | 34452.6992 | 100 |  | 0 | 100 |  | 0
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 |  | 0 | 0 | 31746.2207 | 10d | 0 | 0 | 0 | 31746.2207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 |  | 0 | 0 | 18409.8799 | 4d | 0 | 0 | 0 | 18409.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 |  | 0 | 0 | 30766.0508 | 5d | 0 | 0 | 0 | 30766.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 |  | 0 | 0 | 14837 | 12d | 0 | 0 | 0 | 14837 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 |  | 0 | 0 | 2908.17 | 9d | 0 | 0 | 0 | 2908.17 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 |  | 0 | 0 | 14283 | 20d | 0 | 0 | 0 | 14283 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 |  | 0 | 0 | 18409.8809 | 2d | 0 | 0 | 0 | 18409.8809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 0 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 |  | 0 | 0 | 17304 | 5d | 0 | 0 | 0 | 17304 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 |  | 0 | 0 | 5938 | 5d | 0 | 0 | 0 | 5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 |  | 0 | 0 | 254308.8125 | 4d | 0 | 0 | 0 | 254308.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 |  | 0 | 0 | 6840 | 15d | 0 | 0 | 0 | 6840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 |  | 0 | 0 | 2843 | 3d | 0 | 0 | 0 | 2843 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-05-05 08:00 |  | TP Name | T4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 54d | [5 empty] | 818934.6011 |  | 18.91% |  | 818934.6014 | 1705206.0101
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 40d | 135353.2734 | 64000 | 40d | 0 | 0 | 135353.2734 | 64000 | 50% | Started | 135353.2734 | 189753.2734 | 100 | 50 | 50 | 100 | 67.8962 | 50
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 |  | 0 | 0 | 455069 | 10d | 0 | 0 | 0 | 455069 | 0% | Not Started | 0 | 455069 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 4d | 21994.1797 | 10240 | 16d | 0 | 0 | 21994.1797 | 10240 | 20% | Started | 21994.1797 | 32234.1797 | 100 | 20 | 20 | 100 | 68.2325 | 20
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 0 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 12d | 4260.9199 | 1280 | 8d | 0 | 0 | 4260.9199 | 1280 | 60% | Started | 4260.92 | 5540.9199 | 100 | 60 | 60 | 100 | 76.8991 | 60
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 3d | 28986.6895 | 1280 | 2d | 0 | 0 | 28986.6895 | 1280 | 60% | Started | 28986.6895 | 30266.6895 | 100 | 60 | 60 | 100 | 95.7709 | 60
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 |  | 0 | 0 | 92974.5781 | 30d | 0 | 0 | 0 | 92974.5781 | 0% | Not Started | 0 | 92974.5781 | 100 |  | 0 | 100 |  | 0
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 |  | 0 | 0 | 20000 | 30d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 7040 | 100 |  | 0 | 100 |  | 0
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 |  | 0 | 0 | 27983.5 | 11d | 0 | 0 | 0 | 27983.5 | 0% | Not Started | 0 | 27983.5 | 100 |  | 0 | 100 |  | 0
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 |  | 0 | 0 | 48507.7617 | 13d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 48507.7617 | 100 |  | 0 | 100 |  | 0
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 |  | 0 | 0 | 2876 | 1d | 0 | 0 | 0 | 2876 | 0% | Not Started | 0 | 2876 | 100 |  | 0 | 100 |  | 0
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 |  | 0 | 0 | 40211.3281 | 7d | 0 | 0 | 0 | 40211.3281 | 0% | Not Started | 0 | 40211.3281 | 100 |  | 0 | 100 |  | 0
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 |  | 0 | 0 | 34640 | 14d | 0 | 0 | 0 | 34640 | 0% | Not Started | 0 | 34640 | 100 |  | 0 | 100 |  | 0
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 |  | 0 | 0 | 44692.6992 | 19d | 0 | 0 | 0 | 44692.6992 | 0% | Not Started | 0 | 44692.6992 | 100 |  | 0 | 100 |  | 0
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 3d | 27266.2207 | 4480 | 7d | 0 | 0 | 27266.2207 | 4480 | 30% | Started | 27266.2208 | 31746.2207 | 100 | 30 | 30 | 100 | 85.8881 | 30
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 |  | 0 | 0 | 18409.8799 | 4d | 0 | 0 | 0 | 18409.8799 | 0% | Not Started | 0 | 18409.8799 | 100 |  | 0 | 100 |  | 0
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 |  | 0 | 0 | 30766.0508 | 5d | 0 | 0 | 0 | 30766.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 4000 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 44027.7617 | 100 |  | 0 | 100 |  | 0
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 |  | 0 | 0 | 14837 | 12d | 0 | 0 | 0 | 14837 | 0% | Not Started | 0 | 12277 | 100 |  | 0 | 100 |  | 0
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 |  | 0 | 0 | 2908.17 | 9d | 0 | 0 | 0 | 2908.17 | 0% | Not Started | 0 | 1948.17 | 100 |  | 0 | 100 |  | 0
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 |  | 0 | 0 | 14283 | 20d | 0 | 0 | 0 | 14283 | 0% | Not Started | 0 | 3403 | 100 |  | 0 | 100 |  | 0
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 |  | 0 | 0 | 18409.8809 | 2d | 0 | 0 | 0 | 18409.8809 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 0 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 |  | 0 | 0 | 17304 | 5d | 0 | 0 | 0 | 17304 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 |  | 0 | 0 | 5938 | 5d | 0 | 0 | 0 | 5938 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 |  | 0 | 0 | 254308.8125 | 4d | 0 | 0 | 0 | 254308.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 |  | 0 | 0 | 6840 | 15d | 0 | 0 | 0 | 6840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 |  | 0 | 0 | 2843 | 3d | 0 | 0 | 0 | 2843 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-06-02 08:00 |  | TP Name | T5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 74d | [5 empty] | 1491348.3785 |  | 34.43% |  | 1491348.3803 | 2134949.7858
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 59d | 165753.2734 | 33600 | 21d | 0 | 0 | 165753.2734 | 33600 | 73.75% | Started | 165753.275 | 199353.2734 | 100 | 73.75 | 73.75 | 100 | 83.1455 | 73.75
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 4d | 447389 | 7680 | 6d | 0 | 0 | 447389 | 7680 | 40% | Started | 447389.0001 | 455069 | 100 | 40 | 40 | 100 | 98.3123 | 40
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 17d | 84654.5781 | 8320 | 13d | 0 | 0 | 84654.5781 | 8320 | 56.67% | Started | 84654.578 | 92974.5781 | 100 | 56.6667 | 56.6667 | 100 | 91.0513 | 56.6667
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 17d | 13760 | 6240 | 13d | 0 | 0 | 13760 | 6240 | 56.67% | Started | 13759.9999 | 16640 | 100 | 56.6667 | 56.6667 | 100 | 68.8 | 56.6667
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 |  | 0 | 0 | 48507.7617 | 13d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 48507.7617 | 100 |  | 0 | 100 |  | 0
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 |  | 0 | 0 | 40211.3281 | 7d | 0 | 0 | 0 | 40211.3281 | 0% | Not Started | 0 | 40211.3281 | 100 |  | 0 | 100 |  | 0
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 |  | 0 | 0 | 34640 | 14d | 0 | 0 | 0 | 34640 | 0% | Not Started | 0 | 34640 | 100 |  | 0 | 100 |  | 0
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 15d | 42132.6992 | 2560 | 4d | 0 | 0 | 42132.6992 | 2560 | 78.95% | Started | 42132.6996 | 44692.6992 | 100 | 78.9474 | 78.9474 | 100 | 94.272 | 78.9474
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 |  | 0 | 0 | 18409.8799 | 4d | 0 | 0 | 0 | 18409.8799 | 0% | Not Started | 0 | 18409.8799 | 100 |  | 0 | 100 |  | 0
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 |  | 0 | 0 | 30766.0508 | 5d | 0 | 0 | 0 | 30766.0508 | 0% | Not Started | 0 | 30766.0508 | 100 |  | 0 | 100 |  | 0
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 4000 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 48507.7617 | 100 |  | 0 | 100 |  | 0
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 |  | 0 | 0 | 14837 | 12d | 0 | 0 | 0 | 14837 | 0% | Not Started | 0 | 14837 | 100 |  | 0 | 100 |  | 0
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 |  | 0 | 0 | 2908.17 | 9d | 0 | 0 | 0 | 2908.17 | 0% | Not Started | 0 | 2908.17 | 100 |  | 0 | 100 |  | 0
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 |  | 0 | 0 | 14283 | 20d | 0 | 0 | 0 | 14283 | 0% | Not Started | 0 | 14283 | 100 |  | 0 | 100 |  | 0
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 |  | 0 | 0 | 18409.8809 | 2d | 0 | 0 | 0 | 18409.8809 | 0% | Not Started | 0 | 18409.8809 | 100 |  | 0 | 100 |  | 0
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 |  | 0 | 0 | 17304 | 5d | 0 | 0 | 0 | 17304 | 0% | Not Started | 0 | 17304 | 100 |  | 0 | 100 |  | 0
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 42107.7617 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 |  | 0 | 0 | 254308.8125 | 4d | 0 | 0 | 0 | 254308.8125 | 0% | Not Started | 0 | 253668.8125 | 100 |  | 0 | 100 |  | 0
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 |  | 0 | 0 | 6840 | 15d | 0 | 0 | 0 | 6840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 |  | 0 | 0 | 2843 | 3d | 0 | 0 | 0 | 2843 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2014-07-07 08:00 |  | TP Name | T6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 98d | [5 empty] | 1660837.3482 |  | 38.35% |  | 1660837.3498 | 2808357.5721
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 79d | 197753.2734 | 1600 | 1d | 0 | 0 | 197753.2734 | 1600 | 98.75% | Started | 197753.275 | 199353.2734 | 100 | 98.75 | 98.75 | 100 | 99.1974 | 98.75
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 5d | 38931.3281 | 1280 | 2d | 0 | 0 | 38931.3281 | 1280 | 71.43% | Started | 38931.3282 | 40211.3281 | 100 | 71.4286 | 71.4286 | 100 | 96.8168 | 71.4286
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 |  | 0 | 0 | 34640 | 14d | 0 | 0 | 0 | 34640 | 0% | Not Started | 0 | 34640 | 100 |  | 0 | 100 |  | 0
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 |  | 0 | 0 | 30766.0508 | 5d | 0 | 0 | 0 | 30766.0508 | 0% | Not Started | 0 | 30766.0508 | 100 |  | 0 | 100 |  | 0
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 4000 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 48507.7617 | 100 |  | 0 | 100 |  | 0
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 |  | 0 | 0 | 14837 | 12d | 0 | 0 | 0 | 14837 | 0% | Not Started | 0 | 14837 | 100 |  | 0 | 100 |  | 0
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 |  | 0 | 0 | 2908.17 | 9d | 0 | 0 | 0 | 2908.17 | 0% | Not Started | 0 | 2908.17 | 100 |  | 0 | 100 |  | 0
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 |  | 0 | 0 | 14283 | 20d | 0 | 0 | 0 | 14283 | 0% | Not Started | 0 | 14283 | 100 |  | 0 | 100 |  | 0
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 |  | 0 | 0 | 18409.8809 | 2d | 0 | 0 | 0 | 18409.8809 | 0% | Not Started | 0 | 18409.8809 | 100 |  | 0 | 100 |  | 0
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 |  | 0 | 0 | 17304 | 5d | 0 | 0 | 0 | 17304 | 0% | Not Started | 0 | 17304 | 100 |  | 0 | 100 |  | 0
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 31558.2598 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 48507.7617 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 |  | 0 | 0 | 254308.8125 | 4d | 0 | 0 | 0 | 254308.8125 | 0% | Not Started | 0 | 254308.8125 | 100 |  | 0 | 100 |  | 0
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 94632.8516 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 224091.6562 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 3892.36 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 15887.0703 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 8080 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 14625.8198 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 3924.88 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 30699.1992 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 |  | 0 | 0 | 2843 | 3d | 0 | 0 | 0 | 2843 | 0% | Not Started | 0 | 2843 | 100 |  | 0 | 100 |  | 0
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 218919.3594 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 7013.3301 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2014-08-05 08:00 |  | TP Name | T7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 103d | [5 empty] | 1747010.2799 |  | 40.33% |  | 1747010.2801 | 2816197.5721
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 5d | 28880 | 5760 | 9d | 0 | 0 | 28880 | 5760 | 35.71% | Started | 28880.0001 | 34640 | 100 | 35.7143 | 35.7143 | 100 | 83.3718 | 35.7143
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 |  | 0 | 0 | 30766.0508 | 5d | 0 | 0 | 0 | 30766.0508 | 0% | Not Started | 0 | 30766.0508 | 100 |  | 0 | 100 |  | 0
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 4000 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 5d | 42107.7617 | 6400 | 10d | 0 | 0 | 42107.7617 | 6400 | 33.33% | Started | 42107.7618 | 48507.7617 | 100 | 33.3333 | 33.3333 | 100 | 86.8062 | 33.3333
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 5d | 10357 | 4480 | 7d | 0 | 0 | 10357 | 4480 | 41.67% | Started | 10356.9999 | 14837 | 100 | 41.6667 | 41.6667 | 100 | 69.8052 | 41.6667
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 5d | 1948.17 | 960 | 4d | 0 | 0 | 1948.17 | 960 | 55.56% | Started | 1948.17 | 2908.17 | 100 | 55.5556 | 55.5556 | 100 | 66.9895 | 55.5556
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 |  | 0 | 0 | 14283 | 20d | 0 | 0 | 0 | 14283 | 0% | Not Started | 0 | 14283 | 100 |  | 0 | 100 |  | 0
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 |  | 0 | 0 | 18409.8809 | 2d | 0 | 0 | 0 | 18409.8809 | 0% | Not Started | 0 | 18409.8809 | 100 |  | 0 | 100 |  | 0
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 |  | 0 | 0 | 17304 | 5d | 0 | 0 | 0 | 17304 | 0% | Not Started | 0 | 17304 | 100 |  | 0 | 100 |  | 0
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 31558.2598 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 |  | 0 | 0 | 48507.7617 | 15d | 0 | 0 | 0 | 48507.7617 | 0% | Not Started | 0 | 48507.7617 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 |  | 0 | 0 | 254308.8125 | 4d | 0 | 0 | 0 | 254308.8125 | 0% | Not Started | 0 | 254308.8125 | 100 |  | 0 | 100 |  | 0
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 95912.8516 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 224091.6562 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 4692.36 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 15887.0703 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 15905.8198 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 3924.88 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 31979.1992 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 |  | 0 | 0 | 2843 | 3d | 0 | 0 | 0 | 2843 | 0% | Not Started | 0 | 2843 | 100 |  | 0 | 100 |  | 0
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 218919.3594 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 8293.3301 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2014-09-01 08:00 |  | TP Name | T8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 122d | [5 empty] | 2141432.7858 |  | 49.44% |  | 2141432.7861 | 2914767.0721
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 100% | Finished | 34640 | 34640 | 100 | 100 | 100 | 100 | 100 | 100
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 100% | Finished | 30766.0508 | 30766.0508 | 100 | 100 | 100 | 100 | 100 | 100
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 |  | 0 | 0 | 4000 | 4d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 4000 | 100 |  | 0 | 100 |  | 0
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 100% | Finished | 14837 | 14837 | 100 | 100 | 100 | 100 | 100 | 100
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 100% | Finished | 2908.17 | 2908.17 | 100 | 100 | 100 | 100 | 100 | 100
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 16d | 11723 | 2560 | 4d | 0 | 0 | 11723 | 2560 | 80% | Started | 11723.0002 | 14283 | 100 | 80 | 80 | 100 | 82.0766 | 80
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 100% | Finished | 18409.8809 | 18409.8809 | 100 | 100 | 100 | 100 | 100 | 100
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 100% | Finished | 17304 | 17304 | 100 | 100 | 100 | 100 | 100 | 100
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 |  | 0 | 0 | 31558.2598 | 4d | 0 | 0 | 0 | 31558.2598 | 0% | Not Started | 0 | 31558.2598 | 100 |  | 0 | 100 |  | 0
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 4d | 41467.7617 | 7040 | 11d | 0 | 0 | 41467.7617 | 7040 | 26.67% | Started | 41467.7619 | 48507.7617 | 100 | 26.6667 | 26.6667 | 100 | 85.4869 | 26.6667
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 100% | Finished | 254308.8125 | 254308.8125 | 100 | 100 | 100 | 100 | 100 | 100
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 |  | 0 | 0 | 95912.8516 | 19d | 0 | 0 | 0 | 95912.8516 | 0% | Not Started | 0 | 95912.8516 | 100 |  | 0 | 100 |  | 0
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 224091.6562 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 |  | 0 | 0 | 5972.36 | 27d | 0 | 0 | 0 | 5972.36 | 0% | Not Started | 0 | 5972.36 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 |  | 0 | 0 | 15887.0703 | 3d | 0 | 0 | 0 | 15887.0703 | 0% | Not Started | 0 | 15887.0703 | 100 |  | 0 | 100 |  | 0
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 |  | 0 | 0 | 10000 | 15d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 10000 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 |  | 0 | 0 | 15905.8198 | 15d | 0 | 0 | 0 | 15905.8198 | 0% | Not Started | 0 | 15905.8198 | 100 |  | 0 | 100 |  | 0
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 |  | 0 | 0 | 3924.88 | 10d | 0 | 0 | 0 | 3924.88 | 0% | Not Started | 0 | 3924.88 | 100 |  | 0 | 100 |  | 0
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 31979.1992 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 100% | Finished | 2843 | 2843 | 100 | 100 | 100 | 100 | 100 | 100
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 |  | 0 | 0 | 218919.3594 | 3d | 0 | 0 | 0 | 218919.3594 | 0% | Not Started | 0 | 218919.3594 | 100 |  | 0 | 100 |  | 0
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 |  | 0 | 0 | 8293.3301 | 5d | 0 | 0 | 0 | 8293.3301 | 0% | Not Started | 0 | 8293.3301 | 100 |  | 0 | 100 |  | 0
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 |  | 0 | 0 | 99209.5 | 10d | 0 | 0 | 0 | 99209.5 | 0% | Not Started | 0 | 97289.5 | 100 |  | 0 | 100 |  | 0
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 |  | 0 | 0 | 9484 | 5d | 0 | 0 | 0 | 9484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2014-10-06 08:00 |  | TP Name | T9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 147d | [5 empty] | 2668020.2167 |  | 61.6% |  | 2668020.2166 | 3878941.3062
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 100% | Finished | 34640 | 34640 | 100 | 100 | 100 | 100 | 100 | 100
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 100% | Finished | 30766.0508 | 30766.0508 | 100 | 100 | 100 | 100 | 100 | 100
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 2014-09-08 08:00 | 4d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 100% | Finished | 14837 | 14837 | 100 | 100 | 100 | 100 | 100 | 100
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 100% | Finished | 2908.17 | 2908.17 | 100 | 100 | 100 | 100 | 100 | 100
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 20d | 14283 | 0 | 0 | 0 | 0 | 14283 | 0 | 100% | Finished | 14283 | 14283 | 100 | 100 | 100 | 100 | 100 | 100
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 100% | Finished | 18409.8809 | 18409.8809 | 100 | 100 | 100 | 100 | 100 | 100
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 100% | Finished | 17304 | 17304 | 100 | 100 | 100 | 100 | 100 | 100
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 2014-09-10 08:00 | 4d | 31558.2598 | 0 | 0 | 0 | 0 | 31558.2598 | 0 | 100% | Finished | 31558.2598 | 31558.2598 | 100 | 100 | 100 | 100 | 100 | 100
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 100% | Finished | 254308.8125 | 254308.8125 | 100 | 100 | 100 | 100 | 100 | 100
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 2014-09-05 08:00 | 19d | 95912.8516 | 0 | 0 | 0 | 0 | 95912.8516 | 0 | 100% | Finished | 95912.8516 | 95912.8516 | 100 | 100 | 100 | 100 | 100 | 100
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 |  | 0 | 0 | 224091.6562 | 4d | 0 | 0 | 0 | 224091.6562 | 0% | Not Started | 0 | 224091.6562 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 2014-09-11 08:00 | 14d | 3892.36 | 2080 | 13d | 0 | 0 | 3892.36 | 2080 | 51.85% | Started | 3892.3599 | 5972.36 | 100 | 51.8519 | 51.8519 | 100 | 65.1729 | 51.8519
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2014-09-11 08:00 | 3d | 15887.0703 | 0 | 0 | 0 | 0 | 15887.0703 | 0 | 100% | Finished | 15887.0703 | 15887.0703 | 100 | 100 | 100 | 100 | 100 | 100
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 2014-09-12 08:00 | 15d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 2014-09-12 08:00 | 15d | 15905.8198 | 0 | 0 | 0 | 0 | 15905.8198 | 0 | 100% | Finished | 15905.8198 | 15905.8198 | 100 | 100 | 100 | 100 | 100 | 100
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 2014-09-12 08:00 | 10d | 3924.88 | 0 | 0 | 0 | 0 | 3924.88 | 0 | 100% | Finished | 3924.88 | 3924.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 31979.1992 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 100% | Finished | 2843 | 2843 | 100 | 100 | 100 | 100 | 100 | 100
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2014-09-16 08:00 | 3d | 218919.3594 | 0 | 0 | 0 | 0 | 218919.3594 | 0 | 100% | Finished | 218919.3594 | 218919.3594 | 100 | 100 | 100 | 100 | 100 | 100
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 2014-09-26 08:00 | 5d | 8293.3301 | 0 | 0 | 0 | 0 | 8293.3301 | 0 | 100% | Finished | 8293.3301 | 8293.3301 | 100 | 100 | 100 | 100 | 100 | 100
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 2014-09-22 08:00 | 10d | 99209.5 | 0 | 0 | 0 | 0 | 99209.5 | 0 | 100% | Finished | 99209.5 | 99209.5 | 100 | 100 | 100 | 100 | 100 | 100
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 |  | 0 | 0 | 11064.3398 | 2d | 0 | 0 | 0 | 11064.3398 | 0% | Not Started | 0 | 11064.3398 | 100 |  | 0 | 100 |  | 0
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 |  | 0 | 0 | 63322.1602 | 14d | 0 | 0 | 0 | 63322.1602 | 0% | Not Started | 0 | 63322.1602 | 100 |  | 0 | 100 |  | 0
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 |  | 0 | 0 | 588141.5 | 24d | 0 | 0 | 0 | 588141.5 | 0% | Not Started | 0 | 586861.5 | 100 |  | 0 | 100 |  | 0
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 |  | 0 | 0 | 1717.6899 | 2d | 0 | 0 | 0 | 1717.6899 | 0% | Not Started | 0 | 1717.6899 | 100 |  | 0 | 100 |  | 0
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 |  | 0 | 0 | 1717.69 | 9d | 0 | 0 | 0 | 1717.69 | 0% | Not Started | 0 | 1717.69 | 100 |  | 0 | 100 |  | 0
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 |  | 0 | 0 | 196047.1719 | 15d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 194127.1719 | 100 |  | 0 | 100 |  | 0
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 |  | 0 | 0 | 8716.96 | 24d | 0 | 0 | 0 | 8716.96 | 0% | Not Started | 0 | 6636.96 | 100 |  | 0 | 100 |  | 0
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 |  | 0 | 0 | 5206.42 | 5d | 0 | 0 | 0 | 5206.42 | 0% | Not Started | 0 | 5206.42 | 100 |  | 0 | 100 |  | 0
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 |  | 0 | 0 | 103.27 | 1d | 0 | 0 | 0 | 103.27 | 0% | Not Started | 0 | 103.27 | 100 |  | 0 | 100 |  | 0
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 |  | 0 | 0 | 12152.29 | 5d | 0 | 0 | 0 | 12152.29 | 0% | Not Started | 0 | 12152.29 | 100 |  | 0 | 100 |  | 0
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 |  | 0 | 0 | 31206 | 10d | 0 | 0 | 0 | 31206 | 0% | Not Started | 0 | 28646 | 100 |  | 0 | 100 |  | 0
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 |  | 0 | 0 | 10312.7305 | 2d | 0 | 0 | 0 | 10312.7305 | 0% | Not Started | 0 | 10312.7305 | 100 |  | 0 | 100 |  | 0
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 |  | 0 | 0 | 37786.0117 | 1d | 0 | 0 | 0 | 37786.0117 | 0% | Not Started | 0 | 37786.0117 | 100 |  | 0 | 100 |  | 0
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 2600 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 2014-09-15 08:00 | 5d | 9484 | 0 | 0 | 0 | 0 | 9484 | 0 | 100% | Finished | 9484 | 0 | 100 | 100 | 100 | 100 | 100 | 100
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 |  | 0 | 0 | 4000 | 10d | 0 | 0 | 0 | 4000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 |  | 0 | 0 | 593 | 1d | 0 | 0 | 0 | 593 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2014-11-03 08:00 |  | TP Name | T10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 167d | [5 empty] | 3855079.107 |  | 89.01% |  | 3855079.1068 | 4237830.4859
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 100% | Finished | 34640 | 34640 | 100 | 100 | 100 | 100 | 100 | 100
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 100% | Finished | 30766.0508 | 30766.0508 | 100 | 100 | 100 | 100 | 100 | 100
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 2014-09-08 08:00 | 4d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 100% | Finished | 14837 | 14837 | 100 | 100 | 100 | 100 | 100 | 100
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 100% | Finished | 2908.17 | 2908.17 | 100 | 100 | 100 | 100 | 100 | 100
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 20d | 14283 | 0 | 0 | 0 | 0 | 14283 | 0 | 100% | Finished | 14283 | 14283 | 100 | 100 | 100 | 100 | 100 | 100
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 100% | Finished | 18409.8809 | 18409.8809 | 100 | 100 | 100 | 100 | 100 | 100
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 100% | Finished | 17304 | 17304 | 100 | 100 | 100 | 100 | 100 | 100
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 2014-09-10 08:00 | 4d | 31558.2598 | 0 | 0 | 0 | 0 | 31558.2598 | 0 | 100% | Finished | 31558.2598 | 31558.2598 | 100 | 100 | 100 | 100 | 100 | 100
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 100% | Finished | 254308.8125 | 254308.8125 | 100 | 100 | 100 | 100 | 100 | 100
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 2014-09-05 08:00 | 19d | 95912.8516 | 0 | 0 | 0 | 0 | 95912.8516 | 0 | 100% | Finished | 95912.8516 | 95912.8516 | 100 | 100 | 100 | 100 | 100 | 100
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 | 2014-10-28 08:00 | 4d | 224091.6562 | 0 | 0 | 0 | 0 | 224091.6562 | 0 | 100% | Finished | 224091.6562 | 224091.6562 | 100 | 100 | 100 | 100 | 100 | 100
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 2014-09-11 08:00 | 27d | 5972.36 | 0 | 0 | 0 | 0 | 5972.36 | 0 | 100% | Finished | 5972.36 | 5972.36 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2014-09-11 08:00 | 3d | 15887.0703 | 0 | 0 | 0 | 0 | 15887.0703 | 0 | 100% | Finished | 15887.0703 | 15887.0703 | 100 | 100 | 100 | 100 | 100 | 100
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 2014-09-12 08:00 | 15d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 2014-09-12 08:00 | 15d | 15905.8198 | 0 | 0 | 0 | 0 | 15905.8198 | 0 | 100% | Finished | 15905.8198 | 15905.8198 | 100 | 100 | 100 | 100 | 100 | 100
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 2014-09-12 08:00 | 10d | 3924.88 | 0 | 0 | 0 | 0 | 3924.88 | 0 | 100% | Finished | 3924.88 | 3924.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 |  | 0 | 0 | 31979.1992 | 13d | 0 | 0 | 0 | 31979.1992 | 0% | Not Started | 0 | 31979.1992 | 100 |  | 0 | 100 |  | 0
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 100% | Finished | 2843 | 2843 | 100 | 100 | 100 | 100 | 100 | 100
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2014-09-16 08:00 | 3d | 218919.3594 | 0 | 0 | 0 | 0 | 218919.3594 | 0 | 100% | Finished | 218919.3594 | 218919.3594 | 100 | 100 | 100 | 100 | 100 | 100
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 2014-09-26 08:00 | 5d | 8293.3301 | 0 | 0 | 0 | 0 | 8293.3301 | 0 | 100% | Finished | 8293.3301 | 8293.3301 | 100 | 100 | 100 | 100 | 100 | 100
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 2014-09-22 08:00 | 10d | 99209.5 | 0 | 0 | 0 | 0 | 99209.5 | 0 | 100% | Finished | 99209.5 | 99209.5 | 100 | 100 | 100 | 100 | 100 | 100
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 | 2014-10-31 08:00 | 1d | 10424.3398 | 640 | 1d | 0 | 0 | 10424.3398 | 640 | 50% | Started | 10424.3398 | 11064.3398 | 100 | 50 | 50 | 100 | 94.2157 | 50
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 | 2014-10-06 08:00 | 14d | 63322.1602 | 0 | 0 | 0 | 0 | 63322.1602 | 0 | 100% | Finished | 63322.1602 | 63322.1602 | 100 | 100 | 100 | 100 | 100 | 100
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 | 2014-10-06 08:00 | 20d | 585581.5 | 2560 | 4d | 0 | 0 | 585581.5 | 2560 | 83.33% | Started | 585581.4997 | 588141.5 | 100 | 83.3333 | 83.3333 | 100 | 99.5647 | 83.3333
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 | 2014-10-06 08:00 | 2d | 1717.6899 | 0 | 0 | 0 | 0 | 1717.6899 | 0 | 100% | Finished | 1717.6899 | 1717.6899 | 100 | 100 | 100 | 100 | 100 | 100
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 | 2014-10-08 08:00 | 9d | 1717.69 | 0 | 0 | 0 | 0 | 1717.69 | 0 | 100% | Finished | 1717.69 | 1717.69 | 100 | 100 | 100 | 100 | 100 | 100
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 | 2014-10-17 08:00 | 11d | 193487.1719 | 2560 | 4d | 0 | 0 | 193487.1719 | 2560 | 73.33% | Started | 193487.172 | 196047.1719 | 100 | 73.3333 | 73.3333 | 100 | 98.6942 | 73.3333
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 | 2014-10-20 08:00 | 10d | 6476.96 | 2240 | 14d | 0 | 0 | 6476.96 | 2240 | 41.67% | Started | 6476.9599 | 8716.96 | 100 | 41.6667 | 41.6667 | 100 | 74.303 | 41.6667
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 | 2014-10-21 08:00 | 5d | 5206.42 | 0 | 0 | 0 | 0 | 5206.42 | 0 | 100% | Finished | 5206.42 | 5206.42 | 100 | 100 | 100 | 100 | 100 | 100
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 | 2014-10-23 08:00 | 1d | 103.27 | 0 | 0 | 0 | 0 | 103.27 | 0 | 100% | Finished | 103.27 | 103.27 | 100 | 100 | 100 | 100 | 100 | 100
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 | 2014-10-24 08:00 | 5d | 12152.29 | 0 | 0 | 0 | 0 | 12152.29 | 0 | 100% | Finished | 12152.29 | 12152.29 | 100 | 100 | 100 | 100 | 100 | 100
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 | 2014-10-27 08:00 | 5d | 28006 | 3200 | 5d | 0 | 0 | 28006 | 3200 | 50% | Started | 28006 | 31206 | 100 | 50 | 50 | 100 | 89.7456 | 50
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 | 2014-10-28 08:00 | 2d | 10312.7305 | 0 | 0 | 0 | 0 | 10312.7305 | 0 | 100% | Finished | 10312.7305 | 10312.7305 | 100 | 100 | 100 | 100 | 100 | 100
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 | 2014-10-28 08:00 | 1d | 37786.0117 | 0 | 0 | 0 | 0 | 37786.0117 | 0 | 100% | Finished | 37786.0117 | 37786.0117 | 100 | 100 | 100 | 100 | 100 | 100
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 |  | 0 | 0 | 8840 | 14d | 0 | 0 | 0 | 8840 | 0% | Not Started | 0 | 8840 | 100 |  | 0 | 100 |  | 0
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 |  | 0 | 0 | 196047.1719 | 5d | 0 | 0 | 0 | 196047.1719 | 0% | Not Started | 0 | 196047.1719 | 100 |  | 0 | 100 |  | 0
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 2014-09-15 08:00 | 5d | 9484 | 0 | 0 | 0 | 0 | 9484 | 0 | 100% | Finished | 9484 | 9484 | 100 | 100 | 100 | 100 | 100 | 100
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 |  | 0 | 0 | 63074.5391 | 5d | 0 | 0 | 0 | 63074.5391 | 0% | Not Started | 0 | 63074.5391 | 100 |  | 0 | 100 |  | 0
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 |  | 0 | 0 | 2954 | 5d | 0 | 0 | 0 | 2954 | 0% | Not Started | 0 | 2954 | 100 |  | 0 | 100 |  | 0
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 |  | 0 | 0 | 3948 | 5d | 0 | 0 | 0 | 3948 | 0% | Not Started | 0 | 3948 | 100 |  | 0 | 100 |  | 0
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 4207 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 44973.4688 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 | 2014-10-17 08:00 | 10d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 3840 | 100 | 100 | 100 | 100 | 100 | 100
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 12960 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 2728 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 | 2014-10-06 08:00 | 1d | 593 | 0 | 0 | 0 | 0 | 593 | 0 | 100% | Finished | 593 | 593 | 100 | 100 | 100 | 100 | 100 | 100
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2014-12-01 08:00 |  | TP Name | T11
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 187d | [5 empty] | 4171202.0171 |  | 96.3% |  | 4171202.0172 | 4299110.4859
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 100% | Finished | 34640 | 34640 | 100 | 100 | 100 | 100 | 100 | 100
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 100% | Finished | 30766.0508 | 30766.0508 | 100 | 100 | 100 | 100 | 100 | 100
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 2014-09-08 08:00 | 4d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 100% | Finished | 14837 | 14837 | 100 | 100 | 100 | 100 | 100 | 100
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 100% | Finished | 2908.17 | 2908.17 | 100 | 100 | 100 | 100 | 100 | 100
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 20d | 14283 | 0 | 0 | 0 | 0 | 14283 | 0 | 100% | Finished | 14283 | 14283 | 100 | 100 | 100 | 100 | 100 | 100
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 100% | Finished | 18409.8809 | 18409.8809 | 100 | 100 | 100 | 100 | 100 | 100
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 100% | Finished | 17304 | 17304 | 100 | 100 | 100 | 100 | 100 | 100
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 2014-09-10 08:00 | 4d | 31558.2598 | 0 | 0 | 0 | 0 | 31558.2598 | 0 | 100% | Finished | 31558.2598 | 31558.2598 | 100 | 100 | 100 | 100 | 100 | 100
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 100% | Finished | 254308.8125 | 254308.8125 | 100 | 100 | 100 | 100 | 100 | 100
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 2014-09-05 08:00 | 19d | 95912.8516 | 0 | 0 | 0 | 0 | 95912.8516 | 0 | 100% | Finished | 95912.8516 | 95912.8516 | 100 | 100 | 100 | 100 | 100 | 100
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 | 2014-10-28 08:00 | 4d | 224091.6562 | 0 | 0 | 0 | 0 | 224091.6562 | 0 | 100% | Finished | 224091.6562 | 224091.6562 | 100 | 100 | 100 | 100 | 100 | 100
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 2014-09-11 08:00 | 27d | 5972.36 | 0 | 0 | 0 | 0 | 5972.36 | 0 | 100% | Finished | 5972.36 | 5972.36 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2014-09-11 08:00 | 3d | 15887.0703 | 0 | 0 | 0 | 0 | 15887.0703 | 0 | 100% | Finished | 15887.0703 | 15887.0703 | 100 | 100 | 100 | 100 | 100 | 100
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 2014-09-12 08:00 | 15d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 2014-09-12 08:00 | 15d | 15905.8198 | 0 | 0 | 0 | 0 | 15905.8198 | 0 | 100% | Finished | 15905.8198 | 15905.8198 | 100 | 100 | 100 | 100 | 100 | 100
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 2014-09-12 08:00 | 10d | 3924.88 | 0 | 0 | 0 | 0 | 3924.88 | 0 | 100% | Finished | 3924.88 | 3924.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 | 2014-11-03 08:00 | 13d | 31979.1992 | 0 | 0 | 0 | 0 | 31979.1992 | 0 | 100% | Finished | 31979.1992 | 31979.1992 | 100 | 100 | 100 | 100 | 100 | 100
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 100% | Finished | 2843 | 2843 | 100 | 100 | 100 | 100 | 100 | 100
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2014-09-16 08:00 | 3d | 218919.3594 | 0 | 0 | 0 | 0 | 218919.3594 | 0 | 100% | Finished | 218919.3594 | 218919.3594 | 100 | 100 | 100 | 100 | 100 | 100
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 2014-09-26 08:00 | 5d | 8293.3301 | 0 | 0 | 0 | 0 | 8293.3301 | 0 | 100% | Finished | 8293.3301 | 8293.3301 | 100 | 100 | 100 | 100 | 100 | 100
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 2014-09-22 08:00 | 10d | 99209.5 | 0 | 0 | 0 | 0 | 99209.5 | 0 | 100% | Finished | 99209.5 | 99209.5 | 100 | 100 | 100 | 100 | 100 | 100
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 | 2014-10-31 08:00 | 2d | 11064.3398 | 0 | 0 | 0 | 0 | 11064.3398 | 0 | 100% | Finished | 11064.3398 | 11064.3398 | 100 | 100 | 100 | 100 | 100 | 100
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 | 2014-10-06 08:00 | 14d | 63322.1602 | 0 | 0 | 0 | 0 | 63322.1602 | 0 | 100% | Finished | 63322.1602 | 63322.1602 | 100 | 100 | 100 | 100 | 100 | 100
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 | 2014-10-06 08:00 | 24d | 588141.5 | 0 | 0 | 0 | 0 | 588141.5 | 0 | 100% | Finished | 588141.5 | 588141.5 | 100 | 100 | 100 | 100 | 100 | 100
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 | 2014-10-06 08:00 | 2d | 1717.6899 | 0 | 0 | 0 | 0 | 1717.6899 | 0 | 100% | Finished | 1717.6899 | 1717.6899 | 100 | 100 | 100 | 100 | 100 | 100
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 | 2014-10-08 08:00 | 9d | 1717.69 | 0 | 0 | 0 | 0 | 1717.69 | 0 | 100% | Finished | 1717.69 | 1717.69 | 100 | 100 | 100 | 100 | 100 | 100
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 | 2014-10-17 08:00 | 15d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 | 2014-10-20 08:00 | 24d | 8716.96 | 0 | 0 | 0 | 0 | 8716.96 | 0 | 100% | Finished | 8716.96 | 8716.96 | 100 | 100 | 100 | 100 | 100 | 100
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 | 2014-10-21 08:00 | 5d | 5206.42 | 0 | 0 | 0 | 0 | 5206.42 | 0 | 100% | Finished | 5206.42 | 5206.42 | 100 | 100 | 100 | 100 | 100 | 100
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 | 2014-10-23 08:00 | 1d | 103.27 | 0 | 0 | 0 | 0 | 103.27 | 0 | 100% | Finished | 103.27 | 103.27 | 100 | 100 | 100 | 100 | 100 | 100
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 | 2014-10-24 08:00 | 5d | 12152.29 | 0 | 0 | 0 | 0 | 12152.29 | 0 | 100% | Finished | 12152.29 | 12152.29 | 100 | 100 | 100 | 100 | 100 | 100
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 | 2014-10-27 08:00 | 10d | 31206 | 0 | 0 | 0 | 0 | 31206 | 0 | 100% | Finished | 31206 | 31206 | 100 | 100 | 100 | 100 | 100 | 100
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 | 2014-10-28 08:00 | 2d | 10312.7305 | 0 | 0 | 0 | 0 | 10312.7305 | 0 | 100% | Finished | 10312.7305 | 10312.7305 | 100 | 100 | 100 | 100 | 100 | 100
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 | 2014-10-28 08:00 | 1d | 37786.0117 | 0 | 0 | 0 | 0 | 37786.0117 | 0 | 100% | Finished | 37786.0117 | 37786.0117 | 100 | 100 | 100 | 100 | 100 | 100
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 | 2014-11-17 08:00 | 10d | 6920 | 1920 | 4d | 0 | 0 | 6920 | 1920 | 71.43% | Started | 6920.0001 | 8840 | 100 | 71.4286 | 71.4286 | 100 | 78.2805 | 71.4286
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 | 2014-11-07 08:00 | 5d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 2014-09-15 08:00 | 5d | 9484 | 0 | 0 | 0 | 0 | 9484 | 0 | 100% | Finished | 9484 | 9484 | 100 | 100 | 100 | 100 | 100 | 100
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 | 2014-11-24 08:00 | 5d | 63074.5391 | 0 | 0 | 0 | 0 | 63074.5391 | 0 | 100% | Finished | 63074.5391 | 63074.5391 | 100 | 100 | 100 | 100 | 100 | 100
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 | 2014-11-24 08:00 | 5d | 2954 | 0 | 0 | 0 | 0 | 2954 | 0 | 100% | Finished | 2954 | 2954 | 100 | 100 | 100 | 100 | 100 | 100
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 | 2014-11-24 08:00 | 5d | 3948 | 0 | 0 | 0 | 0 | 3948 | 0 | 100% | Finished | 3948 | 3948 | 100 | 100 | 100 | 100 | 100 | 100
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 |  | 0 | 0 | 4207 | 8d | 0 | 0 | 0 | 4207 | 0% | Not Started | 0 | 4207 | 100 |  | 0 | 100 |  | 0
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 49453.4688 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 | 2014-10-17 08:00 | 10d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 14240 | 100 |  | 0 | 100 |  | 0
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 |  | 0 | 0 | 3048 | 5d | 0 | 0 | 0 | 3048 | 0% | Not Started | 0 | 3048 | 100 |  | 0 | 100 |  | 0
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 | 2014-10-06 08:00 | 1d | 593 | 0 | 0 | 0 | 0 | 593 | 0 | 100% | Finished | 593 | 593 | 100 | 100 | 100 | 100 | 100 | 100
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 14240 | 100 |  | 0 | 100 |  | 0
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 14240 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 14240 | 100 |  | 0 | 100 |  | 0
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 12320 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2015-01-05 08:00 |  | TP Name | T12
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 202d | [5 empty] | 4235417.0171 |  | 97.79% |  | 4235417.0172 | 4319910.4859
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 100% | Finished | 34640 | 34640 | 100 | 100 | 100 | 100 | 100 | 100
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 100% | Finished | 30766.0508 | 30766.0508 | 100 | 100 | 100 | 100 | 100 | 100
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 2014-09-08 08:00 | 4d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 100% | Finished | 14837 | 14837 | 100 | 100 | 100 | 100 | 100 | 100
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 100% | Finished | 2908.17 | 2908.17 | 100 | 100 | 100 | 100 | 100 | 100
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 20d | 14283 | 0 | 0 | 0 | 0 | 14283 | 0 | 100% | Finished | 14283 | 14283 | 100 | 100 | 100 | 100 | 100 | 100
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 100% | Finished | 18409.8809 | 18409.8809 | 100 | 100 | 100 | 100 | 100 | 100
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 100% | Finished | 17304 | 17304 | 100 | 100 | 100 | 100 | 100 | 100
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 2014-09-10 08:00 | 4d | 31558.2598 | 0 | 0 | 0 | 0 | 31558.2598 | 0 | 100% | Finished | 31558.2598 | 31558.2598 | 100 | 100 | 100 | 100 | 100 | 100
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 100% | Finished | 254308.8125 | 254308.8125 | 100 | 100 | 100 | 100 | 100 | 100
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 2014-09-05 08:00 | 19d | 95912.8516 | 0 | 0 | 0 | 0 | 95912.8516 | 0 | 100% | Finished | 95912.8516 | 95912.8516 | 100 | 100 | 100 | 100 | 100 | 100
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 | 2014-10-28 08:00 | 4d | 224091.6562 | 0 | 0 | 0 | 0 | 224091.6562 | 0 | 100% | Finished | 224091.6562 | 224091.6562 | 100 | 100 | 100 | 100 | 100 | 100
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 2014-09-11 08:00 | 27d | 5972.36 | 0 | 0 | 0 | 0 | 5972.36 | 0 | 100% | Finished | 5972.36 | 5972.36 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2014-09-11 08:00 | 3d | 15887.0703 | 0 | 0 | 0 | 0 | 15887.0703 | 0 | 100% | Finished | 15887.0703 | 15887.0703 | 100 | 100 | 100 | 100 | 100 | 100
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 2014-09-12 08:00 | 15d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 2014-09-12 08:00 | 15d | 15905.8198 | 0 | 0 | 0 | 0 | 15905.8198 | 0 | 100% | Finished | 15905.8198 | 15905.8198 | 100 | 100 | 100 | 100 | 100 | 100
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 2014-09-12 08:00 | 10d | 3924.88 | 0 | 0 | 0 | 0 | 3924.88 | 0 | 100% | Finished | 3924.88 | 3924.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 | 2014-11-03 08:00 | 13d | 31979.1992 | 0 | 0 | 0 | 0 | 31979.1992 | 0 | 100% | Finished | 31979.1992 | 31979.1992 | 100 | 100 | 100 | 100 | 100 | 100
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 100% | Finished | 2843 | 2843 | 100 | 100 | 100 | 100 | 100 | 100
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2014-09-16 08:00 | 3d | 218919.3594 | 0 | 0 | 0 | 0 | 218919.3594 | 0 | 100% | Finished | 218919.3594 | 218919.3594 | 100 | 100 | 100 | 100 | 100 | 100
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 2014-09-26 08:00 | 5d | 8293.3301 | 0 | 0 | 0 | 0 | 8293.3301 | 0 | 100% | Finished | 8293.3301 | 8293.3301 | 100 | 100 | 100 | 100 | 100 | 100
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 2014-09-22 08:00 | 10d | 99209.5 | 0 | 0 | 0 | 0 | 99209.5 | 0 | 100% | Finished | 99209.5 | 99209.5 | 100 | 100 | 100 | 100 | 100 | 100
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 | 2014-10-31 08:00 | 2d | 11064.3398 | 0 | 0 | 0 | 0 | 11064.3398 | 0 | 100% | Finished | 11064.3398 | 11064.3398 | 100 | 100 | 100 | 100 | 100 | 100
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 | 2014-10-06 08:00 | 14d | 63322.1602 | 0 | 0 | 0 | 0 | 63322.1602 | 0 | 100% | Finished | 63322.1602 | 63322.1602 | 100 | 100 | 100 | 100 | 100 | 100
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 | 2014-10-06 08:00 | 24d | 588141.5 | 0 | 0 | 0 | 0 | 588141.5 | 0 | 100% | Finished | 588141.5 | 588141.5 | 100 | 100 | 100 | 100 | 100 | 100
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 | 2014-10-06 08:00 | 2d | 1717.6899 | 0 | 0 | 0 | 0 | 1717.6899 | 0 | 100% | Finished | 1717.6899 | 1717.6899 | 100 | 100 | 100 | 100 | 100 | 100
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 | 2014-10-08 08:00 | 9d | 1717.69 | 0 | 0 | 0 | 0 | 1717.69 | 0 | 100% | Finished | 1717.69 | 1717.69 | 100 | 100 | 100 | 100 | 100 | 100
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 | 2014-10-17 08:00 | 15d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 | 2014-10-20 08:00 | 24d | 8716.96 | 0 | 0 | 0 | 0 | 8716.96 | 0 | 100% | Finished | 8716.96 | 8716.96 | 100 | 100 | 100 | 100 | 100 | 100
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 | 2014-10-21 08:00 | 5d | 5206.42 | 0 | 0 | 0 | 0 | 5206.42 | 0 | 100% | Finished | 5206.42 | 5206.42 | 100 | 100 | 100 | 100 | 100 | 100
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 | 2014-10-23 08:00 | 1d | 103.27 | 0 | 0 | 0 | 0 | 103.27 | 0 | 100% | Finished | 103.27 | 103.27 | 100 | 100 | 100 | 100 | 100 | 100
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 | 2014-10-24 08:00 | 5d | 12152.29 | 0 | 0 | 0 | 0 | 12152.29 | 0 | 100% | Finished | 12152.29 | 12152.29 | 100 | 100 | 100 | 100 | 100 | 100
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 | 2014-10-27 08:00 | 10d | 31206 | 0 | 0 | 0 | 0 | 31206 | 0 | 100% | Finished | 31206 | 31206 | 100 | 100 | 100 | 100 | 100 | 100
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 | 2014-10-28 08:00 | 2d | 10312.7305 | 0 | 0 | 0 | 0 | 10312.7305 | 0 | 100% | Finished | 10312.7305 | 10312.7305 | 100 | 100 | 100 | 100 | 100 | 100
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 | 2014-10-28 08:00 | 1d | 37786.0117 | 0 | 0 | 0 | 0 | 37786.0117 | 0 | 100% | Finished | 37786.0117 | 37786.0117 | 100 | 100 | 100 | 100 | 100 | 100
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 | 2014-11-17 08:00 | 14d | 8840 | 0 | 0 | 0 | 0 | 8840 | 0 | 100% | Finished | 8840 | 8840 | 100 | 100 | 100 | 100 | 100 | 100
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 | 2014-11-07 08:00 | 5d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 2014-09-15 08:00 | 5d | 9484 | 0 | 0 | 0 | 0 | 9484 | 0 | 100% | Finished | 9484 | 9484 | 100 | 100 | 100 | 100 | 100 | 100
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 | 2014-11-24 08:00 | 5d | 63074.5391 | 0 | 0 | 0 | 0 | 63074.5391 | 0 | 100% | Finished | 63074.5391 | 63074.5391 | 100 | 100 | 100 | 100 | 100 | 100
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 | 2014-11-24 08:00 | 5d | 2954 | 0 | 0 | 0 | 0 | 2954 | 0 | 100% | Finished | 2954 | 2954 | 100 | 100 | 100 | 100 | 100 | 100
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 | 2014-11-24 08:00 | 5d | 3948 | 0 | 0 | 0 | 0 | 3948 | 0 | 100% | Finished | 3948 | 3948 | 100 | 100 | 100 | 100 | 100 | 100
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 | 2014-12-01 08:00 | 8d | 4207 | 0 | 0 | 0 | 0 | 4207 | 0 | 100% | Finished | 4207 | 4207 | 100 | 100 | 100 | 100 | 100 | 100
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 |  | 0 | 0 | 49453.4688 | 10d | 0 | 0 | 0 | 49453.4688 | 0% | Not Started | 0 | 49453.4688 | 100 |  | 0 | 100 |  | 0
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 | 2014-10-17 08:00 | 10d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-12-11 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 | 2014-12-11 08:00 | 5d | 3048 | 0 | 0 | 0 | 0 | 3048 | 0 | 100% | Finished | 3048 | 3048 | 100 | 100 | 100 | 100 | 100 | 100
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 | 2014-10-06 08:00 | 1d | 593 | 0 | 0 | 0 | 0 | 593 | 0 | 100% | Finished | 593 | 593 | 100 | 100 | 100 | 100 | 100 | 100
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-18 08:00 | 2d | 12320 | 1920 | 3d | 0 | 0 | 12320 | 1920 | 40% | Started | 12320 | 14240 | 100 | 40 | 40 | 100 | 86.5169 | 40
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 |  | 0 | 0 | 14240 | 10d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 14240 | 100 |  | 0 | 100 |  | 0
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 |  | 0 | 0 | 14240 | 5d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 14240 | 100 |  | 0 | 100 |  | 0
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-01 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 |  | 0 | 0 | 14240 | 20d | 0 | 0 | 0 | 14240 | 0% | Not Started | 0 | 4640 | 100 |  | 0 | 100 |  | 0
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2015-02-02 08:00 |  | TP Name | T13
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 222d | [5 empty] | 4326310.4859 |  | 99.89% |  | 4326310.4859 | 4331260.4859
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 100% | Finished | 34640 | 34640 | 100 | 100 | 100 | 100 | 100 | 100
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 100% | Finished | 30766.0508 | 30766.0508 | 100 | 100 | 100 | 100 | 100 | 100
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 2014-09-08 08:00 | 4d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 100% | Finished | 14837 | 14837 | 100 | 100 | 100 | 100 | 100 | 100
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 100% | Finished | 2908.17 | 2908.17 | 100 | 100 | 100 | 100 | 100 | 100
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 20d | 14283 | 0 | 0 | 0 | 0 | 14283 | 0 | 100% | Finished | 14283 | 14283 | 100 | 100 | 100 | 100 | 100 | 100
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 100% | Finished | 18409.8809 | 18409.8809 | 100 | 100 | 100 | 100 | 100 | 100
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 100% | Finished | 17304 | 17304 | 100 | 100 | 100 | 100 | 100 | 100
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 2014-09-10 08:00 | 4d | 31558.2598 | 0 | 0 | 0 | 0 | 31558.2598 | 0 | 100% | Finished | 31558.2598 | 31558.2598 | 100 | 100 | 100 | 100 | 100 | 100
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 100% | Finished | 254308.8125 | 254308.8125 | 100 | 100 | 100 | 100 | 100 | 100
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 2014-09-05 08:00 | 19d | 95912.8516 | 0 | 0 | 0 | 0 | 95912.8516 | 0 | 100% | Finished | 95912.8516 | 95912.8516 | 100 | 100 | 100 | 100 | 100 | 100
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 | 2014-10-28 08:00 | 4d | 224091.6562 | 0 | 0 | 0 | 0 | 224091.6562 | 0 | 100% | Finished | 224091.6562 | 224091.6562 | 100 | 100 | 100 | 100 | 100 | 100
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 2014-09-11 08:00 | 27d | 5972.36 | 0 | 0 | 0 | 0 | 5972.36 | 0 | 100% | Finished | 5972.36 | 5972.36 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2014-09-11 08:00 | 3d | 15887.0703 | 0 | 0 | 0 | 0 | 15887.0703 | 0 | 100% | Finished | 15887.0703 | 15887.0703 | 100 | 100 | 100 | 100 | 100 | 100
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 2014-09-12 08:00 | 15d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 2014-09-12 08:00 | 15d | 15905.8198 | 0 | 0 | 0 | 0 | 15905.8198 | 0 | 100% | Finished | 15905.8198 | 15905.8198 | 100 | 100 | 100 | 100 | 100 | 100
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 2014-09-12 08:00 | 10d | 3924.88 | 0 | 0 | 0 | 0 | 3924.88 | 0 | 100% | Finished | 3924.88 | 3924.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 | 2014-11-03 08:00 | 13d | 31979.1992 | 0 | 0 | 0 | 0 | 31979.1992 | 0 | 100% | Finished | 31979.1992 | 31979.1992 | 100 | 100 | 100 | 100 | 100 | 100
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 100% | Finished | 2843 | 2843 | 100 | 100 | 100 | 100 | 100 | 100
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2014-09-16 08:00 | 3d | 218919.3594 | 0 | 0 | 0 | 0 | 218919.3594 | 0 | 100% | Finished | 218919.3594 | 218919.3594 | 100 | 100 | 100 | 100 | 100 | 100
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 2014-09-26 08:00 | 5d | 8293.3301 | 0 | 0 | 0 | 0 | 8293.3301 | 0 | 100% | Finished | 8293.3301 | 8293.3301 | 100 | 100 | 100 | 100 | 100 | 100
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 2014-09-22 08:00 | 10d | 99209.5 | 0 | 0 | 0 | 0 | 99209.5 | 0 | 100% | Finished | 99209.5 | 99209.5 | 100 | 100 | 100 | 100 | 100 | 100
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 | 2014-10-31 08:00 | 2d | 11064.3398 | 0 | 0 | 0 | 0 | 11064.3398 | 0 | 100% | Finished | 11064.3398 | 11064.3398 | 100 | 100 | 100 | 100 | 100 | 100
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 | 2014-10-06 08:00 | 14d | 63322.1602 | 0 | 0 | 0 | 0 | 63322.1602 | 0 | 100% | Finished | 63322.1602 | 63322.1602 | 100 | 100 | 100 | 100 | 100 | 100
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 | 2014-10-06 08:00 | 24d | 588141.5 | 0 | 0 | 0 | 0 | 588141.5 | 0 | 100% | Finished | 588141.5 | 588141.5 | 100 | 100 | 100 | 100 | 100 | 100
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 | 2014-10-06 08:00 | 2d | 1717.6899 | 0 | 0 | 0 | 0 | 1717.6899 | 0 | 100% | Finished | 1717.6899 | 1717.6899 | 100 | 100 | 100 | 100 | 100 | 100
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 | 2014-10-08 08:00 | 9d | 1717.69 | 0 | 0 | 0 | 0 | 1717.69 | 0 | 100% | Finished | 1717.69 | 1717.69 | 100 | 100 | 100 | 100 | 100 | 100
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 | 2014-10-17 08:00 | 15d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 | 2014-10-20 08:00 | 24d | 8716.96 | 0 | 0 | 0 | 0 | 8716.96 | 0 | 100% | Finished | 8716.96 | 8716.96 | 100 | 100 | 100 | 100 | 100 | 100
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 | 2014-10-21 08:00 | 5d | 5206.42 | 0 | 0 | 0 | 0 | 5206.42 | 0 | 100% | Finished | 5206.42 | 5206.42 | 100 | 100 | 100 | 100 | 100 | 100
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 | 2014-10-23 08:00 | 1d | 103.27 | 0 | 0 | 0 | 0 | 103.27 | 0 | 100% | Finished | 103.27 | 103.27 | 100 | 100 | 100 | 100 | 100 | 100
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 | 2014-10-24 08:00 | 5d | 12152.29 | 0 | 0 | 0 | 0 | 12152.29 | 0 | 100% | Finished | 12152.29 | 12152.29 | 100 | 100 | 100 | 100 | 100 | 100
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 | 2014-10-27 08:00 | 10d | 31206 | 0 | 0 | 0 | 0 | 31206 | 0 | 100% | Finished | 31206 | 31206 | 100 | 100 | 100 | 100 | 100 | 100
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 | 2014-10-28 08:00 | 2d | 10312.7305 | 0 | 0 | 0 | 0 | 10312.7305 | 0 | 100% | Finished | 10312.7305 | 10312.7305 | 100 | 100 | 100 | 100 | 100 | 100
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 | 2014-10-28 08:00 | 1d | 37786.0117 | 0 | 0 | 0 | 0 | 37786.0117 | 0 | 100% | Finished | 37786.0117 | 37786.0117 | 100 | 100 | 100 | 100 | 100 | 100
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 | 2014-11-17 08:00 | 14d | 8840 | 0 | 0 | 0 | 0 | 8840 | 0 | 100% | Finished | 8840 | 8840 | 100 | 100 | 100 | 100 | 100 | 100
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 | 2014-11-07 08:00 | 5d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 2014-09-15 08:00 | 5d | 9484 | 0 | 0 | 0 | 0 | 9484 | 0 | 100% | Finished | 9484 | 9484 | 100 | 100 | 100 | 100 | 100 | 100
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 | 2014-11-24 08:00 | 5d | 63074.5391 | 0 | 0 | 0 | 0 | 63074.5391 | 0 | 100% | Finished | 63074.5391 | 63074.5391 | 100 | 100 | 100 | 100 | 100 | 100
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 | 2014-11-24 08:00 | 5d | 2954 | 0 | 0 | 0 | 0 | 2954 | 0 | 100% | Finished | 2954 | 2954 | 100 | 100 | 100 | 100 | 100 | 100
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 | 2014-11-24 08:00 | 5d | 3948 | 0 | 0 | 0 | 0 | 3948 | 0 | 100% | Finished | 3948 | 3948 | 100 | 100 | 100 | 100 | 100 | 100
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 | 2014-12-01 08:00 | 8d | 4207 | 0 | 0 | 0 | 0 | 4207 | 0 | 100% | Finished | 4207 | 4207 | 100 | 100 | 100 | 100 | 100 | 100
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 | 2015-01-12 08:00 | 10d | 49453.4688 | 0 | 0 | 0 | 0 | 49453.4688 | 0 | 100% | Finished | 49453.4688 | 49453.4688 | 100 | 100 | 100 | 100 | 100 | 100
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 | 2014-10-17 08:00 | 10d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-12-11 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 | 2014-12-11 08:00 | 5d | 3048 | 0 | 0 | 0 | 0 | 3048 | 0 | 100% | Finished | 3048 | 3048 | 100 | 100 | 100 | 100 | 100 | 100
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 | 2014-10-06 08:00 | 1d | 593 | 0 | 0 | 0 | 0 | 593 | 0 | 100% | Finished | 593 | 593 | 100 | 100 | 100 | 100 | 100 | 100
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-18 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 | 2015-01-08 08:00 | 10d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2015-01-08 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-01 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 | 2015-01-12 08:00 | 15d | 11040 | 3200 | 5d | 0 | 0 | 11040 | 3200 | 75% | Started | 11040 | 14240 | 100 | 75 | 75 | 100 | 77.5281 | 75
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 |  | 0 | 0 | 1750 | 5d | 0 | 0 | 0 | 1750 | 0% | Not Started | 0 | 1750 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2015-03-02 08:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Defense Building | 2014-01-06 08:00 | 2015-01-30 17:00 | 252d |  |  | 3697980.4859 |  |  | 4331260.4859 |  | 232d | [5 empty] | 4331260.4859 |  | 100% |  | 4331260.4859 | 4331260.4859
1 | Plaatsbeschrijving | 2014-01-06 08:00 | 2014-01-06 17:00 | 1d |  | 0 | 135 | 100 | 800 | 935 | 2014-02-17 08:00 | 1d | 935 | 0 | 0 | 0 | 0 | 935 | 0 | 100% | Finished | 935 | 935 | 100 | 100 | 100 | 100 | 100 | 100
2 | Opstellen URS | 2014-01-07 08:00 | 2014-01-13 17:00 | 5d |  | 0 | 537 | 60 | 2400 | 2937 | 2014-02-17 08:00 | 5d | 2937 | 0 | 0 | 0 | 0 | 2937 | 0 | 100% | Finished | 2937 | 2937 | 100 | 100 | 100 | 100 | 100 | 100
3 | Werfinrichting / stofwanden | 2014-01-07 08:00 | 2014-01-20 17:00 | 10d |  | 0 | 835.05 | 20 | 1600 | 2435.05 | 2014-02-18 08:00 | 10d | 2435.05 | 0 | 0 | 0 | 0 | 2435.05 | 0 | 100% | Finished | 2435.05 | 2435.05 | 100 | 100 | 100 | 100 | 100 | 100
4 | Risk Assessment | 2014-01-14 08:00 | 2014-01-20 17:00 | 5d |  | 0 | 928 | 100 | 4000 | 4928 | 2014-02-24 08:00 | 5d | 4928 | 0 | 0 | 0 | 0 | 4928 | 0 | 100% | Finished | 4928 | 4928 | 100 | 100 | 100 | 100 | 100 | 100
5 | Uitzetten van de werf | 2014-01-14 08:00 | 2014-01-21 17:00 | 6d |  | 0 | 5097 | 80 | 3840 | 8937 | 2014-02-24 08:00 | 6d | 8937 | 0 | 0 | 0 | 0 | 8937 | 0 | 100% | Finished | 8937 | 8937 | 100 | 100 | 100 | 100 | 100 | 100
6 | Validation Master Plan | 2014-01-20 08:00 | 2014-05-12 17:00 | 80d |  | 0 | 71353.2734 | 200 | 128000 | 199353.2734 | 2014-03-03 08:00 | 80d | 199353.2734 | 0 | 0 | 0 | 0 | 199353.2734 | 0 | 100% | Finished | 199353.2734 | 199353.2734 | 100 | 100 | 100 | 100 | 100 | 100
7 | Metselwerken / Betonwerken | 2014-01-22 08:00 | 2014-02-17 17:00 | 19d |  | 0 | 39284.7695 | 80 | 12160 | 51444.7695 | 2014-03-04 08:00 | 19d | 51444.7695 | 0 | 0 | 0 | 0 | 51444.7695 | 0 | 100% | Finished | 51444.7695 | 51444.7695 | 100 | 100 | 100 | 100 | 100 | 100
8 | Voorbereiding technieken | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d |  | 0 | 1077 | 80 | 17280 | 18357 | 2014-03-04 08:00 | 27d | 18357 | 0 | 0 | 0 | 0 | 18357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 100 | 100
9 | Voeding werfzone | 2014-01-22 08:00 | 2014-01-22 17:00 | 1d |  | 0 | 9360 | 80 | 640 | 10000 | 2014-02-17 08:00 | 1d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
10 | Plaatsen afvoeren | 2014-01-22 08:00 | 2014-01-28 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-04-07 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
11 | Afbraak en/of omleggen bestaand bord | 2014-01-23 08:00 | 2014-01-24 17:00 | 2d |  | 0 | 8720 | 80 | 1280 | 10000 | 2014-03-06 08:00 | 2d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
12 | Groepen plaatsen | 2014-01-28 08:00 | 2014-02-10 17:00 | 10d |  | 0 | 442269 | 160 | 12800 | 455069 | 2014-05-20 08:00 | 10d | 455069 | 0 | 0 | 0 | 0 | 455069 | 0 | 100% | Finished | 455069 | 455069 | 100 | 100 | 100 | 100 | 100 | 100
13 | Plaatsen toevoerleiding vanuit verd -1 naar verd +1 | 2014-01-28 08:00 | 2014-02-03 17:00 | 5d |  | 0 | 28546.2207 | 80 | 3200 | 31746.2207 | 2014-03-19 08:00 | 5d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
14 | Kanalen | 2014-02-04 08:00 | 2014-03-03 17:00 | 20d |  | 0 | 269454.1875 | 100 | 16000 | 285454.1875 | 2014-03-17 08:00 | 20d | 285454.1875 | 0 | 0 | 0 | 0 | 285454.1875 | 0 | 100% | Finished | 285454.1875 | 285454.1875 | 100 | 100 | 100 | 100 | 100 | 100
15 | Plaatsen waterinstallatie in Techn Ruimte | 2014-03-12 08:00 | 2014-04-08 17:00 | 20d |  | 0 | 19434.1797 | 80 | 12800 | 32234.1797 | 2014-04-29 08:00 | 20d | 32234.1797 | 0 | 0 | 0 | 0 | 32234.1797 | 0 | 100% | Finished | 32234.1797 | 32234.1797 | 100 | 100 | 100 | 100 | 100 | 100
17 | Pleisterwerken | 2014-02-18 08:00 | 2014-03-11 17:00 | 15d |  | 0 | 9254.4697 | 80 | 9600 | 18854.4697 | 2014-03-31 08:00 | 15d | 18854.4697 | 0 | 0 | 0 | 0 | 18854.4697 | 0 | 100% | Finished | 18854.4697 | 18854.4697 | 100 | 100 | 100 | 100 | 100 | 100
18 | Plaatsen nieuwe centrale op niv -2 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d |  | 0 | 8802.4004 | 80 | 3200 | 12002.4004 | 2014-03-31 08:00 | 5d | 12002.4004 | 0 | 0 | 0 | 0 | 12002.4004 | 0 | 100% | Finished | 12002.4004 | 12002.4004 | 100 | 100 | 100 | 100 | 100 | 100
16 | plaatsen stalen poutrellen ter versteviging | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 20029.5098 | 100 | 1600 | 21629.5098 | 2014-03-17 08:00 | 2d | 21629.5098 | 0 | 0 | 0 | 0 | 21629.5098 | 0 | 100% | Finished | 21629.5098 | 21629.5098 | 100 | 100 | 100 | 100 | 100 | 100
19 | demonteren plafonds niv 0 | 2014-02-27 08:00 | 2014-03-03 17:00 | 3d |  | 0 | 1088 | 80 | 1920 | 3008 | 2014-03-31 08:00 | 3d | 3008 | 0 | 0 | 0 | 0 | 3008 | 0 | 100% | Finished | 3008 | 3008 | 100 | 100 | 100 | 100 | 100 | 100
20 | maken doorvoeren niv +1 -> gvl | 2014-02-20 08:00 | 2014-02-26 17:00 | 5d |  | 0 | 3470.9399 | 80 | 3200 | 6670.9399 | 2014-04-03 08:00 | 5d | 6670.9399 | 0 | 0 | 0 | 0 | 6670.9399 | 0 | 100% | Finished | 6670.9399 | 6670.9399 | 100 | 100 | 100 | 100 | 100 | 100
21 | Kabels naar bord verd -2 | 2014-02-20 08:00 | 2014-02-25 17:00 | 4d |  | 0 | 4647 | 80 | 2560 | 7207 | 2014-04-03 08:00 | 4d | 7207 | 0 | 0 | 0 | 0 | 7207 | 0 | 100% | Finished | 7207 | 7207 | 100 | 100 | 100 | 100 | 100 | 100
22 | Plaatsen toevoerleidingen + isolatie | 2014-02-21 08:00 | 2014-04-04 17:00 | 30d |  | 0 | 12546.2197 | 80 | 19200 | 31746.2197 | 2014-03-11 08:00 | 30d | 31746.2197 | 0 | 0 | 0 | 0 | 31746.2197 | 0 | 100% | Finished | 31746.2197 | 31746.2197 | 100 | 100 | 100 | 100 | 100 | 100
23 | Plaatsen leidingen | 2014-02-24 08:00 | 2014-04-08 17:00 | 31d |  | 0 | 2366.05 | 60 | 14880 | 17246.05 | 2014-03-11 08:00 | 31d | 17246.05 | 0 | 0 | 0 | 0 | 17246.05 | 0 | 100% | Finished | 17246.05 | 17246.05 | 100 | 100 | 100 | 100 | 100 | 100
24 | plaatsen afvoeren en aansluiten op niv 0 | 2014-02-27 08:00 | 2014-03-27 17:00 | 20d |  | 0 | 2340.9199 | 20 | 3200 | 5540.9199 | 2014-04-10 08:00 | 20d | 5540.9199 | 0 | 0 | 0 | 0 | 5540.9199 | 0 | 100% | Finished | 5540.9199 | 5540.9199 | 100 | 100 | 100 | 100 | 100 | 100
25 | Maken doorvoeren dak -> niv +1 | 2014-02-27 08:00 | 2014-02-28 17:00 | 2d |  | 0 | 10205.7998 | 80 | 1280 | 11485.7998 | 2014-04-10 08:00 | 2d | 11485.7998 | 0 | 0 | 0 | 0 | 11485.7998 | 0 | 100% | Finished | 11485.7998 | 11485.7998 | 100 | 100 | 100 | 100 | 100 | 100
26 | Aanpassingswerken dak | 2014-03-03 08:00 | 2014-03-10 17:00 | 5d |  | 0 | 285.11 | 40 | 1600 | 1885.11 | 2014-04-22 08:00 | 5d | 1885.11 | 0 | 0 | 0 | 0 | 1885.11 | 0 | 100% | Finished | 1885.11 | 1885.11 | 100 | 100 | 100 | 100 | 100 | 100
27 | Chape | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d |  | 0 | 27066.6895 | 80 | 3200 | 30266.6895 | 2014-04-29 08:00 | 5d | 30266.6895 | 0 | 0 | 0 | 0 | 30266.6895 | 0 | 100% | Finished | 30266.6895 | 30266.6895 | 100 | 100 | 100 | 100 | 100 | 100
28 | Piping | 2014-03-19 08:00 | 2014-04-29 17:00 | 30d |  | 0 | 73774.5781 | 80 | 19200 | 92974.5781 | 2014-05-08 08:00 | 30d | 92974.5781 | 0 | 0 | 0 | 0 | 92974.5781 | 0 | 100% | Finished | 92974.5781 | 92974.5781 | 100 | 100 | 100 | 100 | 100 | 100
29 | Bekabeling | 2014-04-30 08:00 | 2014-06-11 17:00 | 30d |  | 0 | 5600 | 60 | 14400 | 20000 | 2014-05-08 08:00 | 30d | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 100% | Finished | 20000 | 20000 | 100 | 100 | 100 | 100 | 100 | 100
30 | Kabelgoten | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 3297.6101 | 60 | 5280 | 8577.6101 | 2014-03-10 08:00 | 11d | 8577.6101 | 0 | 0 | 0 | 0 | 8577.6101 | 0 | 100% | Finished | 8577.6101 | 8577.6101 | 100 | 100 | 100 | 100 | 100 | 100
31 | Plaatsen leidingen | 2014-03-18 08:00 | 2014-04-01 17:00 | 11d |  | 0 | 20943.5 | 80 | 7040 | 27983.5 | 2014-05-08 08:00 | 11d | 27983.5 | 0 | 0 | 0 | 0 | 27983.5 | 0 | 100% | Finished | 27983.5 | 27983.5 | 100 | 100 | 100 | 100 | 100 | 100
32 | gipskartonwanden 1e zijde | 2014-03-21 08:00 | 2014-04-08 17:00 | 13d |  | 0 | 40187.7617 | 80 | 8320 | 48507.7617 | 2014-06-16 08:00 | 13d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
33 | dichtleggen plafond niv 0 | 2014-03-28 08:00 | 2014-03-28 17:00 | 1d |  | 0 | 2236 | 80 | 640 | 2876 | 2014-05-20 08:00 | 1d | 2876 | 0 | 0 | 0 | 0 | 2876 | 0 | 100% | Finished | 2876 | 2876 | 100 | 100 | 100 | 100 | 100 | 100
34 | Alu buitenramen / roosters | 2014-04-01 08:00 | 2014-04-09 17:00 | 7d |  | 0 | 35731.3281 | 80 | 4480 | 40211.3281 | 2014-06-30 08:00 | 7d | 40211.3281 | 0 | 0 | 0 | 0 | 40211.3281 | 0 | 100% | Finished | 40211.3281 | 40211.3281 | 100 | 100 | 100 | 100 | 100 | 100
35 | Technieken in gipswanden | 2014-04-02 08:00 | 2014-04-21 17:00 | 14d |  | 0 | 25680 | 80 | 8960 | 34640 | 2014-07-07 08:00 | 14d | 34640 | 0 | 0 | 0 | 0 | 34640 | 0 | 100% | Finished | 34640 | 34640 | 100 | 100 | 100 | 100 | 100 | 100
36 | Leidingen trekken + inbouwbakjes | 2014-04-02 08:00 | 2014-04-28 17:00 | 19d |  | 0 | 32532.6992 | 80 | 12160 | 44692.6992 | 2014-05-08 08:00 | 19d | 44692.6992 | 0 | 0 | 0 | 0 | 44692.6992 | 0 | 100% | Finished | 44692.6992 | 44692.6992 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plaatsen brandleiding + koppelingen | 2014-04-07 08:00 | 2014-04-18 17:00 | 10d |  | 0 | 25346.2207 | 80 | 6400 | 31746.2207 | 2014-04-30 08:00 | 10d | 31746.2207 | 0 | 0 | 0 | 0 | 31746.2207 | 0 | 100% | Finished | 31746.2207 | 31746.2207 | 100 | 100 | 100 | 100 | 100 | 100
38 | structuur voorzetwanden | 2014-04-09 08:00 | 2014-04-14 17:00 | 4d |  | 0 | 15849.8799 | 80 | 2560 | 18409.8799 | 2014-06-27 08:00 | 4d | 18409.8799 | 0 | 0 | 0 | 0 | 18409.8799 | 0 | 100% | Finished | 18409.8799 | 18409.8799 | 100 | 100 | 100 | 100 | 100 | 100
39 | Beglaasde binnenramen | 2014-05-07 08:00 | 2014-05-13 17:00 | 5d |  | 0 | 27566.0508 | 80 | 3200 | 30766.0508 | 2014-08-08 08:00 | 5d | 30766.0508 | 0 | 0 | 0 | 0 | 30766.0508 | 0 | 100% | Finished | 30766.0508 | 30766.0508 | 100 | 100 | 100 | 100 | 100 | 100
40 | Buitenzonnewering | 2014-04-10 08:00 | 2014-04-15 17:00 | 4d |  | 0 | 1440 | 80 | 2560 | 4000 | 2014-09-08 08:00 | 4d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
41 | gipskartonwanden 2e zijde, incl plamuren | 2014-04-23 08:00 | 2014-05-13 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-07-07 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
42 | Afmonteren data aansluitingen | 2014-04-23 08:00 | 2014-05-08 17:00 | 12d |  | 0 | 7157 | 80 | 7680 | 14837 | 2014-07-07 08:00 | 12d | 14837 | 0 | 0 | 0 | 0 | 14837 | 0 | 100% | Finished | 14837 | 14837 | 100 | 100 | 100 | 100 | 100 | 100
43 | Plaatsen leidingen branddetectie | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d |  | 0 | 748.17 | 30 | 2160 | 2908.17 | 2014-07-07 08:00 | 9d | 2908.17 | 0 | 0 | 0 | 0 | 2908.17 | 0 | 100% | Finished | 2908.17 | 2908.17 | 100 | 100 | 100 | 100 | 100 | 100
44 | Technieken boven valse plafonds | 2014-04-30 08:00 | 2014-05-27 17:00 | 20d |  | 0 | 1483 | 80 | 12800 | 14283 | 2014-08-07 08:00 | 20d | 14283 | 0 | 0 | 0 | 0 | 14283 | 0 | 100% | Finished | 14283 | 14283 | 100 | 100 | 100 | 100 | 100 | 100
45 | Dichtzetten voorzetwanden | 2014-05-09 08:00 | 2014-05-12 17:00 | 2d |  | 0 | 17129.8809 | 80 | 1280 | 18409.8809 | 2014-08-08 08:00 | 2d | 18409.8809 | 0 | 0 | 0 | 0 | 18409.8809 | 0 | 100% | Finished | 18409.8809 | 18409.8809 | 100 | 100 | 100 | 100 | 100 | 100
46 | Laufervloer | 2014-05-13 08:00 | 2014-05-14 17:00 | 2d |  | 0 | 559.76 | 80 | 1280 | 1839.76 | 2014-03-17 08:00 | 2d | 1839.76 | 0 | 0 | 0 | 0 | 1839.76 | 0 | 100% | Finished | 1839.76 | 1839.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | Afwerken dagkanten ramen | 2014-05-13 08:00 | 2014-05-19 17:00 | 5d |  | 0 | 14104 | 80 | 3200 | 17304 | 2014-08-12 08:00 | 5d | 17304 | 0 | 0 | 0 | 0 | 17304 | 0 | 100% | Finished | 17304 | 17304 | 100 | 100 | 100 | 100 | 100 | 100
48 | Hygienische coating Technische Ruimte | 2014-05-14 08:00 | 2014-05-20 17:00 | 5d |  | 0 | 2738 | 80 | 3200 | 5938 | 2014-05-13 08:00 | 5d | 5938 | 0 | 0 | 0 | 0 | 5938 | 0 | 100% | Finished | 5938 | 5938 | 100 | 100 | 100 | 100 | 100 | 100
49 | Wandbekleding binnenzijde gevel | 2014-06-11 08:00 | 2014-06-16 17:00 | 4d |  | 0 | 28998.2598 | 80 | 2560 | 31558.2598 | 2014-09-10 08:00 | 4d | 31558.2598 | 0 | 0 | 0 | 0 | 31558.2598 | 0 | 100% | Finished | 31558.2598 | 31558.2598 | 100 | 100 | 100 | 100 | 100 | 100
50 | Bekleden cleanroomwanden | 2014-05-26 08:00 | 2014-06-16 17:00 | 15d |  | 0 | 38907.7617 | 80 | 9600 | 48507.7617 | 2014-08-26 08:00 | 15d | 48507.7617 | 0 | 0 | 0 | 0 | 48507.7617 | 0 | 100% | Finished | 48507.7617 | 48507.7617 | 100 | 100 | 100 | 100 | 100 | 100
51 | Plaatsen metalen deuromlijstingen | 2014-05-28 08:00 | 2014-06-02 17:00 | 4d |  | 0 | 251748.8125 | 80 | 2560 | 254308.8125 | 2014-08-25 08:00 | 4d | 254308.8125 | 0 | 0 | 0 | 0 | 254308.8125 | 0 | 100% | Finished | 254308.8125 | 254308.8125 | 100 | 100 | 100 | 100 | 100 | 100
52 | Beloopbaar verlaagd plafond Cleanroom | 2014-06-03 08:00 | 2014-06-24 17:00 | 15d |  | 0 | 2040 | 40 | 4800 | 6840 | 2014-06-02 08:00 | 15d | 6840 | 0 | 0 | 0 | 0 | 6840 | 0 | 100% | Finished | 6840 | 6840 | 100 | 100 | 100 | 100 | 100 | 100
53 | Plaatsen schakelaars, stopcontacten | 2014-06-12 08:00 | 2014-07-08 17:00 | 19d |  | 0 | 83752.8516 | 80 | 12160 | 95912.8516 | 2014-09-05 08:00 | 19d | 95912.8516 | 0 | 0 | 0 | 0 | 95912.8516 | 0 | 100% | Finished | 95912.8516 | 95912.8516 | 100 | 100 | 100 | 100 | 100 | 100
54 | Verlaagde plafonds | 2014-06-13 08:00 | 2014-06-18 17:00 | 4d |  | 0 | 221531.6562 | 80 | 2560 | 224091.6562 | 2014-10-28 08:00 | 4d | 224091.6562 | 0 | 0 | 0 | 0 | 224091.6562 | 0 | 100% | Finished | 224091.6562 | 224091.6562 | 100 | 100 | 100 | 100 | 100 | 100
55 | Plaatsen verlichtingsarmaturen | 2014-06-17 08:00 | 2014-08-14 17:00 | 27d |  | 0 | 1652.36 | 20 | 4320 | 5972.36 | 2014-09-11 08:00 | 27d | 5972.36 | 0 | 0 | 0 | 0 | 5972.36 | 0 | 100% | Finished | 5972.36 | 5972.36 | 100 | 100 | 100 | 100 | 100 | 100
56 | Plaatsen elektr borden | 2014-06-18 08:00 | 2014-06-20 17:00 | 3d |  | 0 | 13967.0703 | 80 | 1920 | 15887.0703 | 2014-09-11 08:00 | 3d | 15887.0703 | 0 | 0 | 0 | 0 | 15887.0703 | 0 | 100% | Finished | 15887.0703 | 15887.0703 | 100 | 100 | 100 | 100 | 100 | 100
57 | Aansluiten elektr bord | 2014-06-19 08:00 | 2014-07-09 17:00 | 15d |  | 0 | 400 | 80 | 9600 | 10000 | 2014-09-12 08:00 | 15d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 100 | 100 | 100 | 100 | 100
58 | Plaatsen kranenwerk, toestellen | 2014-06-18 08:00 | 2014-07-08 17:00 | 15d |  | 0 | 6305.8198 | 80 | 9600 | 15905.8198 | 2014-09-12 08:00 | 15d | 15905.8198 | 0 | 0 | 0 | 0 | 15905.8198 | 0 | 100% | Finished | 15905.8198 | 15905.8198 | 100 | 100 | 100 | 100 | 100 | 100
59 | Afwerking | 2014-06-18 08:00 | 2014-07-01 17:00 | 10d |  | 0 | 724.88 | 40 | 3200 | 3924.88 | 2014-09-12 08:00 | 10d | 3924.88 | 0 | 0 | 0 | 0 | 3924.88 | 0 | 100% | Finished | 3924.88 | 3924.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | Afgewerkte cleanroomwanden | 2014-06-18 17:00 | 2014-06-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
61 | Schilderwerken | 2014-06-20 08:00 | 2014-07-08 17:00 | 13d |  | 0 | 23659.1992 | 80 | 8320 | 31979.1992 | 2014-11-03 08:00 | 13d | 31979.1992 | 0 | 0 | 0 | 0 | 31979.1992 | 0 | 100% | Finished | 31979.1992 | 31979.1992 | 100 | 100 | 100 | 100 | 100 | 100
62 | Plaatsen sokkels meubilair | 2014-06-20 08:00 | 2014-06-24 17:00 | 3d |  | 0 | 923 | 80 | 1920 | 2843 | 2014-08-25 08:00 | 3d | 2843 | 0 | 0 | 0 | 0 | 2843 | 0 | 100% | Finished | 2843 | 2843 | 100 | 100 | 100 | 100 | 100 | 100
63 | Elektronische borden | 2014-06-23 08:00 | 2014-06-25 17:00 | 3d |  | 0 | 216999.3594 | 80 | 1920 | 218919.3594 | 2014-09-16 08:00 | 3d | 218919.3594 | 0 | 0 | 0 | 0 | 218919.3594 | 0 | 100% | Finished | 218919.3594 | 218919.3594 | 100 | 100 | 100 | 100 | 100 | 100
64 | Testen deel 1 | 2014-07-02 08:00 | 2014-07-08 17:00 | 5d |  | 0 | 5093.3301 | 80 | 3200 | 8293.3301 | 2014-09-26 08:00 | 5d | 8293.3301 | 0 | 0 | 0 | 0 | 8293.3301 | 0 | 100% | Finished | 8293.3301 | 8293.3301 | 100 | 100 | 100 | 100 | 100 | 100
65 | Harsgebonden bedrijfsvloer | 2014-08-21 08:00 | 2014-09-03 17:00 | 10d |  | 0 | 92809.5 | 80 | 6400 | 99209.5 | 2014-09-22 08:00 | 10d | 99209.5 | 0 | 0 | 0 | 0 | 99209.5 | 0 | 100% | Finished | 99209.5 | 99209.5 | 100 | 100 | 100 | 100 | 100 | 100
66 | Synthetische vinyl vloerbekleding, incl plinten | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 9784.3398 | 80 | 1280 | 11064.3398 | 2014-10-31 08:00 | 2d | 11064.3398 | 0 | 0 | 0 | 0 | 11064.3398 | 0 | 100% | Finished | 11064.3398 | 11064.3398 | 100 | 100 | 100 | 100 | 100 | 100
67 | Meubilair | 2014-09-04 08:00 | 2014-09-23 17:00 | 14d |  | 0 | 54362.1602 | 80 | 8960 | 63322.1602 | 2014-10-06 08:00 | 14d | 63322.1602 | 0 | 0 | 0 | 0 | 63322.1602 | 0 | 100% | Finished | 63322.1602 | 63322.1602 | 100 | 100 | 100 | 100 | 100 | 100
68 | Plaatsen toestellen | 2014-09-04 08:00 | 2014-10-07 17:00 | 24d |  | 0 | 572781.5 | 80 | 15360 | 588141.5 | 2014-10-06 08:00 | 24d | 588141.5 | 0 | 0 | 0 | 0 | 588141.5 | 0 | 100% | Finished | 588141.5 | 588141.5 | 100 | 100 | 100 | 100 | 100 | 100
69 | Data rack | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 1077.6899 | 40 | 640 | 1717.6899 | 2014-10-06 08:00 | 2d | 1717.6899 | 0 | 0 | 0 | 0 | 1717.6899 | 0 | 100% | Finished | 1717.6899 | 1717.6899 | 100 | 100 | 100 | 100 | 100 | 100
70 | Aansluiten data rack | 2014-09-09 08:00 | 2014-09-19 17:00 | 9d |  | 0 | 277.69 | 20 | 1440 | 1717.69 | 2014-10-08 08:00 | 9d | 1717.69 | 0 | 0 | 0 | 0 | 1717.69 | 0 | 100% | Finished | 1717.69 | 1717.69 | 100 | 100 | 100 | 100 | 100 | 100
71 | Aansluiten toestellen | 2014-09-18 08:00 | 2014-10-08 17:00 | 15d |  | 0 | 186447.1719 | 80 | 9600 | 196047.1719 | 2014-10-17 08:00 | 15d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
72 | plaatsen sirenes, bord, brandmelders, … | 2014-09-19 08:00 | 2014-10-22 17:00 | 24d |  | 0 | 4876.96 | 20 | 3840 | 8716.96 | 2014-10-20 08:00 | 24d | 8716.96 | 0 | 0 | 0 | 0 | 8716.96 | 0 | 100% | Finished | 8716.96 | 8716.96 | 100 | 100 | 100 | 100 | 100 | 100
73 | Verbinding data en telefonie | 2014-09-22 08:00 | 2014-09-26 17:00 | 5d |  | 0 | 2006.42 | 80 | 3200 | 5206.42 | 2014-10-21 08:00 | 5d | 5206.42 | 0 | 0 | 0 | 0 | 5206.42 | 0 | 100% | Finished | 5206.42 | 5206.42 | 100 | 100 | 100 | 100 | 100 | 100
74 | Spiegel | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 23.27 | 10 | 80 | 103.27 | 2014-10-23 08:00 | 1d | 103.27 | 0 | 0 | 0 | 0 | 103.27 | 0 | 100% | Finished | 103.27 | 103.27 | 100 | 100 | 100 | 100 | 100 | 100
75 | Wand-en hoekbescherming | 2014-09-25 08:00 | 2014-10-01 17:00 | 5d |  | 0 | 8952.29 | 80 | 3200 | 12152.29 | 2014-10-24 08:00 | 5d | 12152.29 | 0 | 0 | 0 | 0 | 12152.29 | 0 | 100% | Finished | 12152.29 | 12152.29 | 100 | 100 | 100 | 100 | 100 | 100
76 | Algemene afwerkingen | 2014-09-26 08:00 | 2014-10-09 17:00 | 10d |  | 0 | 24806 | 80 | 6400 | 31206 | 2014-10-27 08:00 | 10d | 31206 | 0 | 0 | 0 | 0 | 31206 | 0 | 100% | Finished | 31206 | 31206 | 100 | 100 | 100 | 100 | 100 | 100
77 | Testen deel 2 | 2014-09-29 08:00 | 2014-09-30 17:00 | 2d |  | 0 | 9032.7305 | 80 | 1280 | 10312.7305 | 2014-10-28 08:00 | 2d | 10312.7305 | 0 | 0 | 0 | 0 | 10312.7305 | 0 | 100% | Finished | 10312.7305 | 10312.7305 | 100 | 100 | 100 | 100 | 100 | 100
78 | Testen deel 3 | 2014-09-29 08:00 | 2014-09-29 17:00 | 1d |  | 0 | 37146.0117 | 80 | 640 | 37786.0117 | 2014-10-28 08:00 | 1d | 37786.0117 | 0 | 0 | 0 | 0 | 37786.0117 | 0 | 100% | Finished | 37786.0117 | 37786.0117 | 100 | 100 | 100 | 100 | 100 | 100
79 | Keuringen en testen installatie | 2014-10-03 08:00 | 2014-10-22 17:00 | 14d |  | 0 | 2120 | 60 | 6720 | 8840 | 2014-11-17 08:00 | 14d | 8840 | 0 | 0 | 0 | 0 | 8840 | 0 | 100% | Finished | 8840 | 8840 | 100 | 100 | 100 | 100 | 100 | 100
80 | Testen deel 4 | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 192847.1719 | 80 | 3200 | 196047.1719 | 2014-11-07 08:00 | 5d | 196047.1719 | 0 | 0 | 0 | 0 | 196047.1719 | 0 | 100% | Finished | 196047.1719 | 196047.1719 | 100 | 100 | 100 | 100 | 100 | 100
81 | Plaatsen tabletten | 2014-10-09 08:00 | 2014-10-15 17:00 | 5d |  | 0 | 6284 | 80 | 3200 | 9484 | 2014-09-15 08:00 | 5d | 9484 | 0 | 0 | 0 | 0 | 9484 | 0 | 100% | Finished | 9484 | 9484 | 100 | 100 | 100 | 100 | 100 | 100
82 | Signalisatie | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 59874.5391 | 80 | 3200 | 63074.5391 | 2014-11-24 08:00 | 5d | 63074.5391 | 0 | 0 | 0 | 0 | 63074.5391 | 0 | 100% | Finished | 63074.5391 | 63074.5391 | 100 | 100 | 100 | 100 | 100 | 100
83 | Eerste Rondgang der werken | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 554 | 60 | 2400 | 2954 | 2014-11-24 08:00 | 5d | 2954 | 0 | 0 | 0 | 0 | 2954 | 0 | 100% | Finished | 2954 | 2954 | 100 | 100 | 100 | 100 | 100 | 100
84 | Eindschoonmaak | 2014-10-10 08:00 | 2014-10-16 17:00 | 5d |  | 0 | 748 | 80 | 3200 | 3948 | 2014-11-24 08:00 | 5d | 3948 | 0 | 0 | 0 | 0 | 3948 | 0 | 100% | Finished | 3948 | 3948 | 100 | 100 | 100 | 100 | 100 | 100
85 | Wegwerken eventuele opmerkingen | 2014-10-17 08:00 | 2014-10-28 17:00 | 8d |  | 0 | 367 | 60 | 3840 | 4207 | 2014-12-01 08:00 | 8d | 4207 | 0 | 0 | 0 | 0 | 4207 | 0 | 100% | Finished | 4207 | 4207 | 100 | 100 | 100 | 100 | 100 | 100
86 | Filters plaatsen + afwerking | 2014-10-29 08:00 | 2014-11-11 17:00 | 10d |  | 0 | 43053.4688 | 80 | 6400 | 49453.4688 | 2015-01-12 08:00 | 10d | 49453.4688 | 0 | 0 | 0 | 0 | 49453.4688 | 0 | 100% | Finished | 49453.4688 | 49453.4688 | 100 | 100 | 100 | 100 | 100 | 100
87 | Plaatsen toebehoren (zeepdispensers, handdoekdispensers,…) | 2014-10-21 08:00 | 2014-11-03 17:00 | 10d |  | 0 | 2400 | 20 | 1600 | 4000 | 2014-10-17 08:00 | 10d | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 100% | Finished | 4000 | 4000 | 100 | 100 | 100 | 100 | 100 | 100
88 | Opstellen systeem validatie IQ/OQ protocol templates Cleanroom & HVAC | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
89 | Start validation | 2014-10-28 17:00 | 2014-10-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-12-11 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
90 | Verwijderen werfinrichting | 2014-10-29 08:00 | 2014-11-04 17:00 | 5d |  | 0 | 2248 | 20 | 800 | 3048 | 2014-12-11 08:00 | 5d | 3048 | 0 | 0 | 0 | 0 | 3048 | 0 | 100% | Finished | 3048 | 3048 | 100 | 100 | 100 | 100 | 100 | 100
91 | Plaatsen deurbladen | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 273 | 40 | 320 | 593 | 2014-10-06 08:00 | 1d | 593 | 0 | 0 | 0 | 0 | 593 | 0 | 100% | Finished | 593 | 593 | 100 | 100 | 100 | 100 | 100 | 100
92 | Certificatietesten Cleanroom & HVAC | 2014-11-05 08:00 | 2014-11-11 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-18 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
93 | Nazicht uitvoering IQ/OQ + rapport Cleanroom & HVAC | 2014-11-12 08:00 | 2014-11-25 17:00 | 10d |  | 0 | 7840 | 80 | 6400 | 14240 | 2015-01-08 08:00 | 10d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
94 | Opstellen systeem validatie templates IQ/OQ/PQ protocol | 2014-11-20 08:00 | 2014-11-26 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-11 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
95 | Nakijken van uitgevoerde testen door uitvoerders | 2014-11-27 08:00 | 2014-12-03 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2015-01-08 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
96 | Opstellen systeemvalidatierapporten IQ/OQ/PQ | 2014-12-08 08:00 | 2014-12-12 17:00 | 5d |  | 0 | 11040 | 80 | 3200 | 14240 | 2014-12-01 08:00 | 5d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
97 | Ondersteuning ontwikkeling SOP's | 2014-12-15 08:00 | 2015-01-23 17:00 | 20d |  | 0 | 1440 | 80 | 12800 | 14240 | 2015-01-12 08:00 | 20d | 14240 | 0 | 0 | 0 | 0 | 14240 | 0 | 100% | Finished | 14240 | 14240 | 100 | 100 | 100 | 100 | 100 | 100
98 | Verwijderen werfburelen | 2015-01-26 08:00 | 2015-01-30 17:00 | 5d |  | 0 | 950 | 20 | 800 | 1750 | 2015-02-09 08:00 | 5d | 1750 | 0 | 0 | 0 | 0 | 1750 | 0 | 100% | Finished | 1750 | 1750 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2014-08-01
1:00 - 2:00 | No | Tuesday | Yes | 2014-06-04
2:00 - 3:00 | No | Wednesday | Yes | 2014-03-05
3:00 - 4:00 | No | Thursday | Yes | 2014-07-14
4:00 - 5:00 | No | Friday | Yes | 2014-07-15
5:00 - 6:00 | No | Saturday | No | 2014-07-16
6:00 - 7:00 | No | Sunday | No | 2014-07-17
7:00 - 8:00 | No |  |  | 2014-07-18
8:00 - 9:00 | Yes |  |  | 2014-07-21
9:00 - 10:00 | Yes |  |  | 2014-07-22
10:00 - 11:00 | Yes |  |  | 2014-07-23
11:00 - 12:00 | Yes |  |  | 2014-07-24
12:00 - 13:00 | No |  |  | 2014-07-25
13:00 - 14:00 | Yes |  |  | 2014-07-28
14:00 - 15:00 | Yes |  |  | 2014-07-29
15:00 - 16:00 | Yes |  |  | 2014-07-30
16:00 - 17:00 | Yes |  |  | 2014-07-31
17:00 - 18:00 | No |  |  | 2014-08-04
18:00 - 19:00 | No |  |  | 2014-12-22
19:00 - 20:00 | No |  |  | 2014-12-23
20:00 - 21:00 | No |  |  | 2014-12-24
21:00 - 22:00 | No |  |  | 2014-12-25
22:00 - 23:00 | No |  |  | 2014-12-26
23:00 - 0:00 | No |  |  | 2014-12-29
2014-12-30
2014-12-31
Generated by PMConverter v1.1.3 |  |  |  | 2015-01-01
2015-01-02

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
T1 | 2014-01-06 08:00 | 2014-02-03 08:00 | 688368.5344 | 0 | 0 | 2014-01-06 08:00 | -688368.5344 | 0% | 0 | 0% | -20d | 0% | 100% | 2015-03-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 0 | 0 | 0 | 1 | -20 | 0 | 1 | 0 | 1
T2 | 2014-02-03 08:00 | 2014-03-03 08:00 | 1111104.5214 | 29372.0499 | 29372.05 | 2014-01-17 17:00 | -1081732.4715 | 2.644% | -0.00011444 | 100% | -30d | 25% | 100% | 2015-04-29 16:00 | 2050-08-29 16:00 | 2050-08-29 16:00 | 2015-03-26 17:00 | 2050-08-29 16:00 | 2050-08-29 16:00 | 2015-03-13 17:00 | 2017-12-25 17:00 | 2017-12-25 17:00 | 4331260.486 | 4331260.5028 | 162763934.7556 | 17236925.794 | 162763935.3897 | 17236925.8611 | 5371428.2994 | 5090417.2874 | 0.25 | 1 | 0.026435 | 1 | -30 | 1 | 1 | 0.25 | 1
T3 | 2014-03-03 08:00 | 2014-04-07 08:00 | 1516753.9778 | 628473.5992 | 628109.4609 | 2014-01-27 17:00 | -888280.3786 | 41.44% | 364.1384 | 100.1% | -48d | 25% | 84.27% | 2015-04-14 14:00 | 2016-06-14 09:00 | 2016-06-13 16:00 | 2015-03-25 12:00 | 2016-06-14 09:00 | 2016-06-13 16:00 | 2015-04-08 17:00 | 2017-12-25 17:00 | 2017-12-25 12:00 | 4330896.3475 | 4328750.9484 | 9564390.5495 | 15439257.0075 | 9559212.8576 | 15430675.411 | 4819937.384 | 4981953.7181 | 0.25 | 1.0006 | 0.41435 | 0.84267 | -48 | 1.0006 | 1 | 0.25 | 1
T4 | 2014-04-07 08:00 | 2014-05-05 08:00 | 1705206.0101 | 818934.6014 | 818934.6011 | 2014-02-03 17:00 | -886271.4087 | 48.03% | 0.00026703 | 100% | -63d | 25% | 35.27% | 2015-04-14 14:00 | 2016-02-17 15:00 | 2016-02-17 15:00 | 2015-04-02 14:00 | 2016-02-17 15:00 | 2016-02-17 15:00 | 2015-04-29 17:00 | 2017-12-25 17:00 | 2017-12-25 17:00 | 4331260.4856 | 4331260.4845 | 8132386.9788 | 14868238.1391 | 8132386.9764 | 14868238.1345 | 4738717.5987 | 4951082.6993 | 0.25 | 1 | 0.48026 | 0.35273 | -63 | 1 | 1 | 0.25 | 1
T5 | 2014-05-05 08:00 | 2014-06-02 08:00 | 2134949.7858 | 1491348.3803 | 1491348.3785 | 2014-04-01 17:00 | -643601.4055 | 69.85% | 0.001812 | 100% | -43d | 58.65% | 93.79% | 2015-03-25 12:00 | 2015-07-02 15:00 | 2015-07-02 15:00 | 2015-03-17 11:00 | 2015-07-02 15:00 | 2015-07-02 15:00 | 2015-04-01 17:00 | 2015-10-07 14:00 | 2015-10-07 14:00 | 4331260.4841 | 4331260.4806 | 5556843.6186 | 6333165.7388 | 5556843.6137 | 6333165.7329 | 4513470.0854 | 4587269.3289 | 0.58654 | 1 | 0.69854 | 0.9379 | -43 | 1 | 1 | 0.58654 | 1
T6 | 2014-06-02 08:00 | 2014-07-07 08:00 | 2808357.5721 | 1660837.3498 | 1660837.3482 | 2014-04-22 17:00 | -1147520.2223 | 59.14% | 0.0016022 | 100% | -52d | 59.38% | 97.53% | 2015-05-05 15:00 | 2015-10-02 09:00 | 2015-10-02 09:00 | 2015-04-15 10:00 | 2015-10-02 09:00 | 2015-10-02 09:00 | 2015-04-14 17:00 | 2015-09-30 11:00 | 2015-09-30 11:00 | 4331260.4843 | 4331260.4817 | 6176332.5205 | 6158392.1037 | 6176332.5161 | 6158392.0994 | 4568913.7272 | 4567420.351 | 0.59375 | 1 | 0.59139 | 0.97533 | -52 | 1 | 1 | 0.59375 | 1
T7 | 2014-07-07 08:00 | 2014-08-05 08:00 | 2816197.5721 | 1747010.2801 | 1747010.2799 | 2014-05-08 09:00 | -1069187.2921 | 62.03% | 0.00015259 | 100% | -45d 7h | 65.51% | 97.02% | 2015-04-29 10:00 | 2015-09-04 10:00 | 2015-09-04 10:00 | 2015-04-13 12:00 | 2015-09-04 10:00 | 2015-09-04 10:00 | 2015-04-06 16:00 | 2015-08-05 15:00 | 2015-08-05 15:00 | 4331260.4857 | 4331260.4855 | 5912846.7598 | 5691977.5955 | 5912846.7595 | 5691977.5952 | 4543609.8422 | 4522744.3994 | 0.65508 | 1 | 0.62034 | 0.97021 | -45.875 | 1 | 1 | 0.65508 | 1
T8 | 2014-08-05 08:00 | 2014-09-01 08:00 | 2914767.0721 | 2141432.7861 | 2141432.7858 | 2014-06-05 15:00 | -773334.2861 | 73.47% | 0.0002861 | 100% | -45d 2h | 70.23% | 99.58% | 2015-04-03 17:00 | 2015-06-08 17:00 | 2015-06-08 17:00 | 2015-03-30 11:00 | 2015-06-08 17:00 | 2015-06-08 17:00 | 2015-04-06 10:00 | 2015-06-30 16:00 | 2015-06-30 16:00 | 4331260.4856 | 4331260.4853 | 5122071.5967 | 5259501.267 | 5122071.5963 | 5259501.2666 | 4453971.1631 | 4469895.9571 | 0.7023 | 1 | 0.73468 | 0.99582 | -45.25 | 1 | 1 | 0.7023 | 1
T9 | 2014-09-01 08:00 | 2014-10-06 08:00 | 3878941.3062 | 2668020.2166 | 2668020.2167 | 2014-06-20 17:00 | -1210921.0896 | 68.78% | -4.7684e-05 | 100% | -59d | 66.67% | 90.26% | 2015-05-11 12:00 | 2015-07-10 11:00 | 2015-07-10 11:00 | 2015-04-20 10:00 | 2015-07-10 11:00 | 2015-07-10 11:00 | 2015-04-23 17:00 | 2015-07-27 17:00 | 2015-07-27 17:00 | 4331260.4859 | 4331260.486 | 5086147.0893 | 5162880.6206 | 5086147.0893 | 5162880.6206 | 4442021.4013 | 4450063.3623 | 0.66667 | 1 | 0.68782 | 0.90263 | -59 | 1 | 1 | 0.66667 | 1
T10 | 2014-10-06 08:00 | 2014-11-03 08:00 | 4237830.4859 | 3855079.1068 | 3855079.107 | 2014-09-26 17:00 | -382751.3791 | 90.97% | -0.00019073 | 100% | -25d | 87.31% | 99.15% | 2015-03-04 10:00 | 2015-03-06 17:00 | 2015-03-06 17:00 | 2015-02-25 15:00 | 2015-03-06 17:00 | 2015-03-06 17:00 | 2015-03-06 17:00 | 2015-03-24 14:00 | 2015-03-24 14:00 | 4331260.4861 | 4331260.4861 | 4378538.1358 | 4400472.8958 | 4378538.1358 | 4400472.8959 | 4340020.2461 | 4343661.0428 | 0.8731 | 1 | 0.90968 | 0.99145 | -25 | 1 | 1 | 0.8731 | 1
T11 | 2014-11-03 08:00 | 2014-12-01 08:00 | 4299110.4859 | 4171202.0172 | 4171202.0171 | 2014-10-21 09:00 | -127908.4686 | 97.02% | 0.00011444 | 100% | -28d 7h | 86.69% | 99.94% | 2015-02-11 12:00 | 2015-02-11 15:00 | 2015-02-11 15:00 | 2015-02-10 12:00 | 2015-02-11 15:00 | 2015-02-11 15:00 | 2015-03-12 16:00 | 2015-03-26 14:00 | 2015-03-26 14:00 | 4331260.4858 | 4331260.4858 | 4336168.6234 | 4355827.5996 | 4336168.6234 | 4355827.5996 | 4332218.6089 | 4335636.5665 | 0.86694 | 1 | 0.97025 | 0.99942 | -28.875 | 1 | 1 | 0.86694 | 1
T12 | 2014-12-01 08:00 | 2015-01-05 08:00 | 4319910.4859 | 4235417.0172 | 4235417.0171 | 2014-10-30 12:00 | -84493.4687 | 98.04% | 1.9073e-05 | 100% | -36d 4h | 84.27% | 98.96% | 2015-02-06 16:00 | 2015-02-06 17:00 | 2015-02-06 17:00 | 2015-02-06 12:00 | 2015-02-06 17:00 | 2015-02-06 17:00 | 2015-03-24 12:00 | 2015-04-07 17:00 | 2015-04-07 17:00 | 4331260.4859 | 4331260.4859 | 4333172.4929 | 4349154.535 | 4333172.4929 | 4349154.535 | 4331636.8802 | 4334374.2256 | 0.84267 | 1 | 0.98044 | 0.98961 | -36.5 | 1 | 1 | 0.84267 | 1
T13 | 2015-01-05 08:00 | 2015-02-02 08:00 | 4331260.4859 | 4326310.4859 | 4326310.4859 | 2015-01-16 17:00 | -4950 | 99.89% | 0 | 100% | -10d | 96.03% | 100% | 2015-02-02 10:00 | 2015-02-02 10:00 | 2015-02-02 10:00 | 2015-02-02 10:00 | 2015-02-02 10:00 | 2015-02-02 10:00 | 2015-02-13 17:00 | 2015-02-16 11:00 | 2015-02-16 11:00 | 4331260.4859 | 4331260.4859 | 4331266.1495 | 4331465.0313 | 4331266.1495 | 4331465.0313 | 4331261.6176 | 4331300.0859 | 0.96032 | 1 | 0.99886 | 1 | -10 | 1 | 1 | 0.96032 | 1
Actual Schedule | 2015-02-02 08:00 | 2015-03-02 08:00 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 2015-01-30 17:00 | 0 | 100% | 0 | 100% | -20d | 92.65% | 100% | 2015-01-30 17:00 | 2015-01-30 17:00 | 2015-01-30 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 2015-02-27 17:00 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 4331260.4859 | 0.92647 | 1 | 1 | 1 | -20 | 1 | 1 | 0.92647 | 1