## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Recy-Call | 1 |  |  | 2018-02-01 12:00 | 2018-08-28 14:00 | 148d 2h |  |  | 78350 |  |  | 78350 | 208.0833
49 | Market research | 1.1 |  | FS26 | 2018-02-01 12:00 | 2018-02-12 17:00 | 8d | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 11.2083
26 | Proof of knowledge | 1.2 | 49FS | FS27 | 2018-02-12 17:00 | 2018-02-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
27 | Opening a banking account | 1.3 | 26FS | FS28 | 2018-02-13 12:00 | 2018-02-14 15:00 | 1d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 1.125
28 | Raise €6000 | 1.4 | 27FS | FS4;FS5;FS29 | 2018-02-14 15:00 | 2018-02-14 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
29 | Writing the statutes | 1.5 | 28FS | FS6 | 2018-02-14 15:00 | 2018-02-21 14:00 | 4d 4h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 6.9583
4 | Document of bank deposit | 1.6 | 28FS | FS6 | 2018-02-14 15:00 | 2018-02-16 15:00 | 2d | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 2
5 | Financial and business plan | 1.7 | 28FS | FS6 | 2018-02-21 14:00 | 2018-03-07 16:00 | 10d 2h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 14.0833
6 | Writing the deed | 1.8 | 4FS;5FS;29FS | FS7;FS8;FS9 | 2018-03-07 16:00 | 2018-03-14 15:00 | 4d 4h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 6.9583
7 | Making the deed public | 1.9 | 6FS | FS10 | 2018-03-14 15:00 | 2018-03-30 16:00 | 12d 1h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 16.0417
8 | E-depot | 1.10 | 6FS | FS10 | 2018-03-30 16:00 | 2018-04-05 14:00 | 3d 3h | Laura & Domien | 0 | 350 | 0 | 0 | 350 | 5.9167
9 | Registering the company | 1.11 | 6FS | FS10 | 2018-04-05 14:00 | 2018-04-10 14:00 | 3d | Laura & Domien | 0 | 6000 | 0 | 0 | 6000 | 5
10 | Enterprise number | 1.12 | 9FS;8FS;7FS | FS11;FS19;FS25 | 2018-04-10 14:00 | 2018-04-12 13:00 | 1d 4h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 1.9583
11 | Contacting the schools | 1.13 | 10FS | FS12 | 2018-04-12 13:00 | 2018-04-17 13:00 | 3d | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 5
12 | Preparing the pitch | 1.14 | 11FS | FS13 | 2018-04-17 13:00 | 2018-04-23 17:00 | 4d 4h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 6.1667
13 | First school meeting | 1.15 | 12FS | FS14 | 2018-05-08 14:00 | 2018-05-11 17:00 | 3d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 3.125
14 | Delivering boxes | 1.16 | 13FS | FS15 | 2018-05-29 13:00 | 2018-05-30 16:00 | 1d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 1.125
15 | Intermediate feedback session | 1.17 | 14FS | FS16 | 2018-06-01 14:00 | 2018-06-04 17:00 | 1d 3h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 3.125
16 | Picking up boxes | 1.18 | 15FS | FS17;FS18 | 2018-06-06 15:00 | 2018-06-08 13:00 | 1d 3h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 1.9167
17 | Delivering the cell-phones | 1.19 | 16FS | FS32;FS46 | 2018-06-08 13:00 | 2018-06-11 16:00 | 1d 3h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 3.125
18 | Follow up and analyze | 1.20 | 16FS | FS31 | 2018-07-24 14:00 | 2018-08-03 14:00 | 8d | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 10
19 | Contacting logistic companies | 1.21 | 10FS | SF20 | 2018-04-24 16:00 | 2018-04-27 13:00 | 2d 2h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 2.875
20 | Cost analysis | 1.22 | 19SF | FS21;FS22 | 2018-04-24 16:00 | 2018-05-01 14:00 | 4d 3h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 6.9167
21 | Hire a driver | 1.23 | 20FS | FS23 | 2018-05-01 14:00 | 2018-05-02 13:00 | 4h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 0.95833
22 | Buying a van | 1.24 | 20FS | FS24 | 2018-05-01 14:00 | 2018-05-02 16:00 | 1d 2h | Laura & Domien[0.50 #1] | 0 | 15000 | 0 | 0 | 15000 | 1.0833
23 | Signing the contract | 1.25 | 21FS |  | 2018-05-08 12:00 | 2018-05-08 14:00 | 2h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 0.083333
24 | Van administration | 1.26 | 22FS |  | 2018-05-04 14:00 | 2018-05-07 15:00 | 1d 1h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 3.0417
25 | Research on regulations | 1.27 | 10FS | FS30 | 2018-05-02 16:00 | 2018-05-04 14:00 | 1d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 1.9167
30 | OVAM registration | 1.28 | 25FS |  | 2018-05-04 14:00 | 2018-05-07 17:00 | 1d 3h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 3.125
31 | Raising money from FFF's | 1.29 | 18FS | FS33 | 2018-08-03 14:00 | 2018-08-08 16:00 | 3d 2h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 5.0833
32 | Talking to business angels | 1.30 | 17FS | FS34 | 2018-06-11 16:00 | 2018-06-13 15:00 | 1d 4h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 1.9583
33 | Taking a loan | 1.31 | 31FS | FS34 | 2018-08-08 16:00 | 2018-08-16 17:00 | 6d 1h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 8.0417
34 | First face to face dialogue | 1.32 | 33FS;32FS | FS35 | 2018-08-17 12:00 | 2018-08-17 17:00 | 1d | Laura & Domien | 0 | 2000 | 0 | 0 | 2000 | 0.20833
35 | Second face to face dialogue | 1.33 | 34FS | FS36 | 2018-08-20 12:00 | 2018-08-20 17:00 | 1d | Laura & Domien | 0 | 2000 | 0 | 0 | 2000 | 0.20833
36 | Customize proposals | 1.34 | 35FS | FS37 | 2018-08-21 12:00 | 2018-08-22 15:00 | 1d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 1.125
37 | Final face to face dialogue | 1.35 | 36FS | FS38;FS39 | 2018-08-22 15:00 | 2018-08-23 14:00 | 4h | Laura & Domien | 0 | 6000 | 0 | 0 | 6000 | 0.95833
38 | Create social media accounts | 1.36 | 37FS |  | 2018-08-27 12:00 | 2018-08-27 16:00 | 4h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 0.16667
39 | Intellectual property protection | 1.37 | 37FS |  | 2018-08-23 14:00 | 2018-08-24 17:00 | 1d 3h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 1.125
40 | Face to face dialogue with school teachers | 1.38 | 48FS | FS41 | 2018-06-21 13:00 | 2018-06-26 16:00 | 3d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 5.125
41 | Create didactic material | 1.39 | 40FS | FS42 | 2018-06-26 16:00 | 2018-07-09 13:00 | 8d 2h | Laura & Domien | 0 | 47000 | 0 | 0 | 47000 | 12.875
42 | Contacting schools | 1.40 | 41FS | FS43 | 2018-07-09 13:00 | 2018-07-12 13:00 | 3d | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 3
43 | Meetings preparation | 1.41 | 42FS | FS44 | 2018-07-12 13:00 | 2018-07-18 16:00 | 4d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 6.125
44 | Meetings | 1.42 | 43FS | FS45 | 2018-07-18 16:00 | 2018-07-24 14:00 | 3d 3h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 5.9167
45 | Deliver didactic material | 1.43 | 44FS |  | 2018-08-23 14:00 | 2018-08-28 14:00 | 3d | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 5
46 | Contacting government | 1.44 | 17FS | FS47 | 2018-06-13 15:00 | 2018-06-15 13:00 | 1d 3h | Laura & Domien[0.50 #1] | 0 | 0 | 0 | 0 | 0 | 1.9167
47 | Government meeting | 1.45 | 46FS | FS48 | 2018-06-15 13:00 | 2018-06-15 17:00 | 4h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 0.16667
48 | Government follow-up | 1.46 | 47FS | FS40 | 2018-06-18 12:00 | 2018-06-21 13:00 | 3d 1h | Laura & Domien | 0 | 0 | 0 | 0 | 0 | 3.0417

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Laura & Domien | Renewable | 1 | 0 | 0 | 49;27;29[0.50 Laura & Domien];4[0.50 Laura & Domien];5;6;7;8;9;10;11;12;13;14;15[0.50 Laura & Domien];16[0.50 Laura & Domien];17[0.50 Laura & Domien];18;19[0.50 Laura & Domien];20[0.50 Laura & Domien];21[0.50 Laura & Domien];22[0.50 Laura & Domien];23;24[0.50 Laura & Domien];25;30[0.50 Laura & Domien];31;32;33;34;35;36;37;38[0.50 Laura & Domien];39[0.50 Laura & Domien];40;41;42[0.50 Laura & Domien];43;44;45[0.50 Laura & Domien];46[0.50 Laura & Domien];47;48; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Recy-Call | 742h |  |  |  |  | 99 | 100 | 101
49 | Market research | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Proof of knowledge | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
27 | Opening a banking account | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Raise €6000 | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
29 | Writing the statutes | 24h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
4 | Document of bank deposit | 10h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
5 | Financial and business plan | 52h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
6 | Writing the deed | 24h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
7 | Making the deed public | 61h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | E-depot | 18h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | Registering the company | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Enterprise number | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Contacting the schools | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Preparing the pitch | 24h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
13 | First school meeting | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Delivering boxes | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Intermediate feedback session | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Picking up boxes | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Delivering the cell-phones | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Follow up and analyze | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
19 | Contacting logistic companies | 12h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Cost analysis | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Hire a driver | 4h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
22 | Buying a van | 7h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
23 | Signing the contract | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Van administration | 6h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | Research on regulations | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | OVAM registration | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Raising money from FFF's | 17h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
32 | Talking to business angels | 9h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
33 | Taking a loan | 31h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | First face to face dialogue | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Second face to face dialogue | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Customize proposals | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Final face to face dialogue | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Create social media accounts | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Intellectual property protection | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Face to face dialogue with school teachers | 18h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
41 | Create didactic material | 42h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
42 | Contacting schools | 15h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
43 | Meetings preparation | 23h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
44 | Meetings | 18h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
45 | Deliver didactic material | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Contacting government | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Government meeting | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Government follow-up | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | No
9:00 - 10:00 | No
10:00 - 11:00 | No
11:00 - 12:00 | No
12:00 - 13:00 | Yes
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))