## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Project | 1 |  |  | 2023-09-22 08:00 | 2023-09-27 15:00 | 3d 6h |  |  | 0 |  |  | 0
1 | Placing outer heras fences | 1.1 |  | FS2 | 2023-09-22 08:00 | 2023-09-22 10:00 | 2h |  | 0 | 0 | 0 | 0 | 0
2 | Placing inner heras fences | 1.2 | 1FS | FS3;FS9;FS15;FS21;FS27;FS30;FS32;FS35;FS38;FS39;FS42;FS46;FS49;FS52;FS55;FS58;FS61;FS67;FS69;FS72;FS75;FS78;FS83;FS86;FS89;FS92;FS95;FS98;FS101;FS104;FS107;FS110;FS113;FS116;FS119;FS120;FS123;FS124;FS126;FS127;FS128;FS129;FS130;FS131;FS133;FS135;FS137;FS149;FS150;FS151 | 2023-09-22 10:00 | 2023-09-22 12:00 | 2h |  | 0 | 0 | 0 | 0 | 0
3 | Setting up the tent (bar B1) | 1.3 | 2FS | FS4 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
4 | Tent equipping with utilities (bar B1) | 1.4 | 3FS | FS5 | 2023-09-22 15:00 | 2023-09-22 17:00 | 2h |  | 0 | 0 | 0 | 0 | 0
5 | Installing the bar (bar B1) | 1.5 | 4FS | FS6 | 2023-09-25 08:00 | 2023-09-25 09:00 | 1h |  | 0 | 0 | 0 | 0 | 0
6 | Connecting barrels (bar B1) | 1.6 | 5FS | FS7 | 2023-09-25 09:00 | 2023-09-25 10:00 | 1h |  | 0 | 0 | 0 | 0 | 0
7 | Positioning fridges (bar B1) | 1.7 | 6FS | FS8 | 2023-09-25 10:00 | 2023-09-25 11:00 | 1h |  | 0 | 0 | 0 | 0 | 0
8 | Filling fridges (bar B1) | 1.8 | 7FS | FS139;FS146 | 2023-09-25 11:00 | 2023-09-25 12:00 | 1h |  | 0 | 0 | 0 | 0 | 0
9 | Setting up the tent (bar B2) | 1.9 | 2FS | FS10 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
10 | Tent equipping with utilities (bar B2) | 1.10 | 9FS | FS11 | 2023-09-22 15:00 | 2023-09-22 17:00 | 2h |  | 0 | 0 | 0 | 0 | 0
11 | Installing the bar (bar B2) | 1.11 | 10FS | FS12 | 2023-09-25 08:00 | 2023-09-25 09:00 | 1h |  | 0 | 0 | 0 | 0 | 0
12 | Connecting barrels (bar B2) | 1.12 | 11FS | FS13 | 2023-09-25 09:00 | 2023-09-25 10:00 | 1h |  | 0 | 0 | 0 | 0 | 0
13 | Positioning fridges (bar B2) | 1.13 | 12FS | FS14 | 2023-09-25 10:00 | 2023-09-25 11:00 | 1h |  | 0 | 0 | 0 | 0 | 0
14 | Filling fridges (bar B2) | 1.14 | 13FS | FS141;FS144 | 2023-09-25 11:00 | 2023-09-25 12:00 | 1h |  | 0 | 0 | 0 | 0 | 0
15 | Setting up the tent (bar B5) | 1.15 | 2FS | FS16 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
16 | Tent equipping with utilities (bar B5) | 1.16 | 15FS | FS17 | 2023-09-22 15:00 | 2023-09-22 17:00 | 2h |  | 0 | 0 | 0 | 0 | 0
17 | Installing the bar (bar B5) | 1.17 | 16FS | FS18 | 2023-09-25 08:00 | 2023-09-25 09:00 | 1h |  | 0 | 0 | 0 | 0 | 0
18 | Connecting barrels (bar B5) | 1.18 | 17FS | FS19 | 2023-09-25 09:00 | 2023-09-25 10:00 | 1h |  | 0 | 0 | 0 | 0 | 0
19 | Positioning fridges (bar B5) | 1.19 | 18FS | FS20 | 2023-09-25 10:00 | 2023-09-25 11:00 | 1h |  | 0 | 0 | 0 | 0 | 0
20 | Filling fridges (bar B5) | 1.20 | 19FS | FS147;FS155 | 2023-09-25 11:00 | 2023-09-25 12:00 | 1h |  | 0 | 0 | 0 | 0 | 0
21 | Setting up the tent (bar B8) | 1.21 | 2FS | FS22 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
22 | Tent equipping with utilities (bar B8) | 1.22 | 21FS | FS23 | 2023-09-22 15:00 | 2023-09-22 17:00 | 2h |  | 0 | 0 | 0 | 0 | 0
23 | Installing the bar (bar B8) | 1.23 | 22FS | FS24 | 2023-09-25 08:00 | 2023-09-25 09:00 | 1h |  | 0 | 0 | 0 | 0 | 0
24 | Connecting barrels (bar B8) | 1.24 | 23FS | FS25 | 2023-09-25 09:00 | 2023-09-25 10:00 | 1h |  | 0 | 0 | 0 | 0 | 0
25 | Positioning fridges (bar B8) | 1.25 | 24FS | FS26 | 2023-09-25 10:00 | 2023-09-25 11:00 | 1h |  | 0 | 0 | 0 | 0 | 0
26 | Filling fridges (bar B8) | 1.26 | 25FS | FS142;FS145 | 2023-09-25 11:00 | 2023-09-25 12:00 | 1h |  | 0 | 0 | 0 | 0 | 0
27 | Setting up the tent (backstagetent) | 1.27 | 2FS | FS28 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
28 | Tent equipping with utilities (backstagetent) | 1.28 | 27FS | FS29 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | Furnishing interior tent (backstagetent) | 1.29 | 28FS | FS155 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
30 | Setting up the tent (first-aid tent) | 1.30 | 2FS | FS31 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
31 | Tent equipping with utilities (first-aid tent) | 1.31 | 30FS | FS155 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
32 | Setting up the tent (employees frame tent) | 1.32 | 2FS | FS33 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
33 | Tent equipping with utilities (employees frame tent) | 1.33 | 32FS | FS34 | 2023-09-22 15:00 | 2023-09-22 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
34 | Furnishing interior tent (employees frame tent) | 1.34 | 33FS | FS155 | 2023-09-22 15:00 | 2023-09-22 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0
35 | Setting up the tent (Eristoff tent) | 1.35 | 2FS | FS36 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
36 | Tent equipping with utilities (Eristoff tent) | 1.36 | 35FS | FS37 | 2023-09-22 16:00 | 2023-09-22 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0
37 | Furnishing interior tent (Eristoff tent) | 1.37 | 36FS | FS155 | 2023-09-22 16:00 | 2023-09-25 11:00 | 4h |  | 0 | 0 | 0 | 0 | 0
38 | Setting up 53 tents (association tents) | 1.38 | 2FS | FS158 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
39 | Setting up the tent (VIP catering) | 1.39 | 2FS | FS40 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
40 | Tent equipping with utilities (VIP catering) | 1.40 | 39FS | FS41 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
41 | Furnishing interior tent (VIP catering) | 1.41 | 40FS | FS155 | 2023-09-22 13:00 | 2023-09-22 14:00 | 1h |  | 0 | 0 | 0 | 0 | 0
42 | Setting up the deck (VIP deck) | 1.42 | 2FS | FS43 | 2023-09-22 13:00 | 2023-09-22 16:00 | 3h |  | 0 | 0 | 0 | 0 | 0
43 | Setting up the tent (VIP deck) | 1.43 | 42FS | FS44 | 2023-09-22 16:00 | 2023-09-25 10:00 | 3h |  | 0 | 0 | 0 | 0 | 0
44 | Tent equipping with utilities (VIP deck) | 1.44 | 43FS | FS45 | 2023-09-25 10:00 | 2023-09-25 12:00 | 2h |  | 0 | 0 | 0 | 0 | 0
45 | Furnishing interior tent (VIP deck) | 1.45 | 44FS | FS155 | 2023-09-25 13:00 | 2023-09-25 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
46 | Setting up the tent (recycling area 1) | 1.46 | 2FS | FS47 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
47 | Tent equipping with utilities (recycling area 1) | 1.47 | 46FS | FS48 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
48 | Furnishing interior tent (recycling area 1) | 1.48 | 47FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
49 | Setting up the tent (recycling area 2) | 1.49 | 2FS | FS50 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
50 | Tent equipping with utilities (recycling area 2) | 1.50 | 49FS | FS51 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
51 | Furnishing interior tent (recycling area 2) | 1.51 | 50FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
52 | Setting up the tent (recycling area 3) | 1.52 | 2FS | FS53 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
53 | Tent equipping with utilities (recycling area 3) | 1.53 | 52FS | FS54 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
54 | Furnishing interior tent (recycling area 3) | 1.54 | 53FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
55 | Setting up the tent (direction 1) | 1.55 | 2FS | FS56 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
56 | Tent equipping with utilities (direction 1) | 1.56 | 55FS | FS57 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
57 | Furnishing interior tent (direction 1) | 1.57 | 56FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
58 | Setting up the tent (direction 2) | 1.58 | 2FS | FS59 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
59 | Tent equipping with utilities (direction 2) | 1.59 | 58FS | FS60 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
60 | Furnishing interior tent (direction 2) | 1.60 | 59FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
61 | Placing bottom container (bar 3) | 1.61 | 2FS | FS62 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
62 | Placing top container (bar3) | 1.62 | 61FS | FS63 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
63 | Installing the stairs (bar3) | 1.63 | 62FS | FS64 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
64 | Equipping both containers with utilities (bar3) | 1.64 | 63FS | FS65 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
65 | Filling the fridges in the bottom container (bar 3) | 1.65 | 64FS | FS66 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
66 | Furnishing interior of upper container (bar 3) | 1.66 | 65FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
67 | Placing fully equipped container (bar 4) | 1.67 | 2FS | FS68 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
68 | Equipping container with utilities (bar 4) | 1.68 | 67FS | FS140;FS148 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
69 | Placing container (desk container boxoffices) | 1.69 | 2FS | FS70 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
70 | Equipping container with utilities (desk container boxoffices) | 1.70 | 69FS | FS71 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
71 | Furnishing interior of container (desk container boxoffices) | 1.71 | 70FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
72 | Placing container (desk container coordinators) | 1.72 | 2FS | FS73 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
73 | Equipping container with utilities (desk container coordinators) | 1.73 | 72FS | FS74 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
74 | Furnishing interior of container (desk container coordinators) | 1.74 | 73FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
75 | Placing container (first-aid) | 1.75 | 2FS | FS76 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
76 | Equipping container with utilities (first-aid) | 1.76 | 75FS | FS77 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
77 | Furnishing interior of container (first-aid) | 1.77 | 76FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
78 | Placing bottom container (warehouse + SS) | 1.78 | 2FS | FS79 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
79 | Placing top container (warehouse + SS) | 1.79 | 78FS | FS80 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
80 | Installing the stairs (warehouse + SS) | 1.80 | 79FS | FS81 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
81 | Equipping both containers with utilities (warehouse + SS) | 1.81 | 80FS | FS82 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
82 | Furnishing interior of both containers (warehouse + SS) | 1.82 | 81FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
83 | Placing container (press) | 1.83 | 2FS | FS84 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
84 | Equipping container with utilities (press) | 1.84 | 83FS | FS85 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
85 | Furnishing interior of container (press) | 1.85 | 84FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
86 | Placing container (production x IT x bitstream) | 1.86 | 2FS | FS87 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
87 | Equipping container with utilities (production x IT x bitstream) | 1.87 | 86FS | FS88 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
88 | Furnishing interior of container (production x IT x bitstream) | 1.88 | 87FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
89 | Placing container (checkout Petermans) | 1.89 | 2FS | FS90 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
90 | Equipping container with utilities (checkout Petermans) | 1.90 | 89FS | FS91 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
91 | Furnishing interior of container (checkout Petermans) | 1.91 | 90FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
92 | Placing container (checkout 1 main toilet) | 1.92 | 2FS | FS93 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
93 | Equipping container with utilities (checkout 1 main toilet) | 1.93 | 92FS | FS94 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
94 | Furnishing interior of container (checkout 1 main toilet) | 1.94 | 93FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
95 | Placing container (checkout 2 main toilet) | 1.95 | 2FS | FS96 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
96 | Equipping container with utilities (checkout 2 main toilet) | 1.96 | 95FS | FS97 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
97 | Furnishing interior of container (checkout 2 main toilet) | 1.97 | 96FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
98 | Placing container (checkout container K1) | 1.98 | 2FS | FS99 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
99 | Equipping container with utilities (checkout container K1) | 1.99 | 98FS | FS100 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
100 | Furnishing interior of container (checkout container K1) | 1.100 | 99FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
101 | Placing container (checkout container K2) | 1.101 | 2FS | FS102 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
102 | Equipping container with utilities (checkout container K2) | 1.102 | 101FS | FS103 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
103 | Furnishing interior of container (checkout container K2) | 1.103 | 102FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
104 | Placing container (checkout container K3) | 1.104 | 2FS | FS105 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
105 | Equipping container with utilities (checkout container K3) | 1.105 | 104FS | FS106 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
106 | Furnishing interior of container (checkout container K3) | 1.106 | 105FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
107 | Placing container (checkout container K4) | 1.107 | 2FS | FS108 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
108 | Equipping container with utilities (checkout container K4) | 1.108 | 107FS | FS109 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
109 | Furnishing interior of container (checkout container K4) | 1.109 | 108FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
110 | Placing container (checkout container K5) | 1.110 | 2FS | FS111 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
111 | Equipping container with utilities (checkout container K5) | 1.111 | 110FS | FS112 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
112 | Furnishing interior of container (checkout container K5) | 1.112 | 111FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
113 | Placing container (core container) | 1.113 | 2FS | FS114 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
114 | Equipping container with utilities (core container) | 1.114 | 113FS | FS115 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
115 | Furnishing interior of container (core container) | 1.115 | 114FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
116 | Placing container (toilet container VIP) | 1.116 | 2FS | FS117 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
117 | Equipping container with utilities (toilet container VIP) | 1.117 | 116FS | FS118 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
118 | Equipping container with supplies (toilet container VIP) | 1.118 | 117FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
119 | Placing piscines (toilet 1) | 1.119 | 2FS | FS121 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
120 | Placing toilets (toilet 1) | 1.120 | 2FS | FS121 | 2023-09-22 13:00 | 2023-09-22 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0
121 | Equipping with utilities (toilet 1) | 1.121 | 119FS;120FS | FS122 | 2023-09-22 15:00 | 2023-09-22 17:00 | 2h |  | 0 | 0 | 0 | 0 | 0
122 | Building up toilet exit (toilet 1) | 1.122 | 121FS | FS155 | 2023-09-25 08:00 | 2023-09-25 09:00 | 1h |  | 0 | 0 | 0 | 0 | 0
123 | Placing piscines (toilet 2) | 1.123 | 2FS | FS125 | 2023-09-22 13:00 | 2023-09-22 14:00 | 1h |  | 0 | 0 | 0 | 0 | 0
124 | Placing toilets (toilet 2) | 1.124 | 2FS | FS125 | 2023-09-22 13:00 | 2023-09-22 14:00 | 1h |  | 0 | 0 | 0 | 0 | 0
125 | Equipping with utilities (toilet 2) | 1.125 | 123FS;124FS | FS155 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
126 | Helping with set-up (mainstage) | 1.126 | 2FS | FS152 | 2023-09-22 13:00 | 2023-09-26 15:00 | 2d 2h |  | 0 | 0 | 0 | 0 | 0
127 | Helping with set-up (delay 1) | 1.127 | 2FS | FS158 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
128 | Helping with set-up (delay 2) | 1.128 | 2FS | FS158 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
129 | Helping with set-up (petermans 1) | 1.129 | 2FS | FS154 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
130 | Helping with set-up (petermans 2) | 1.130 | 2FS | FS154 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
131 | Placing container (DJ booth) | 1.131 | 2FS | FS132 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
132 | Equipping container with utilities (DJ booth) | 1.132 | 131FS | FS153 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
133 | Positioning container fridge | 1.133 | 2FS | FS134 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
134 | Equipping with utilities (container fridge) | 1.134 | 133FS | FS155 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
135 | Positioning Icelander | 1.135 | 2FS | FS136 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
136 | Equipping with utilities (icelander) | 1.136 | 135FS | FS155 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
137 | Positioning tap water site | 1.137 | 2FS | FS138 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
138 | Equipping with utilities (tap water site) | 1.138 | 137FS | FS155 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
139 | Placing cold store (x2) (bar B1) | 1.139 | 8FS | FS143 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
140 | Placing cold store (bar 4) | 1.140 | 68FS | FS143 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
141 | Placing cold store (bar B2) | 1.141 | 14FS | FS143 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
142 | Placing cold store (x2) (bar B8) | 1.142 | 26FS | FS143 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
143 | Equipping cold store with utilities | 1.143 | 139FS;140FS;141FS;142FS | FS155 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
144 | Placing Maes barrels (x2) (bar B2) | 1.144 | 14FS | FS158 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
145 | Placing barrels (x5) (bar B8) | 1.145 | 26FS | FS158 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
146 | Placing Maes barrels (x3) (bar B1) | 1.146 | 8FS | FS158 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
147 | Placing barrels (x3) (bar B5) | 1.147 | 20FS | FS158 | 2023-09-25 12:00 | 2023-09-25 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
148 | Placing Maes barrels (x2) (bar 4) | 1.148 | 68FS | FS158 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
149 | Equipping with utilities (storage Buysse) | 1.149 | 2FS | FS155 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
150 | Positioning stock (bar B1) | 1.150 | 2FS | FS158 | 2023-09-22 13:00 | 2023-09-22 14:00 | 1h |  | 0 | 0 | 0 | 0 | 0
151 | Positioning stock (bar B8) | 1.151 | 2FS | FS158 | 2023-09-22 13:00 | 2023-09-22 14:00 | 1h |  | 0 | 0 | 0 | 0 | 0
152 | Placing crashbarriers (mainstage) | 1.152 | 126FS | FS158 | 2023-09-26 15:00 | 2023-09-26 17:00 | 2h |  | 0 | 0 | 0 | 0 | 0
153 | Placing crashbarriers (Eristoff stage) | 1.153 | 132FS | FS158 | 2023-09-22 14:00 | 2023-09-22 14:00 | 0 |  | 0 | 0 | 0 | 0 | 0
154 | Placing crashbarriers (Petermanstage) | 1.154 | 129FS;130FS | FS158 | 2023-09-22 12:00 | 2023-09-22 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0
155 | Placing constructions | 1.155 | 20FS;29FS;31FS;34FS;37FS;41FS;45FS;48FS;51FS;54FS;57FS;60FS;66FS;74FS;71FS;77FS;82FS;85FS;88FS;91FS;94FS;97FS;100FS;103FS;106FS;109FS;112FS;115FS;118FS;122FS;125FS;134FS;136FS;138FS;149FS;143FS | FS156 | 2023-09-25 15:00 | 2023-09-26 12:00 | 6h |  | 0 | 0 | 0 | 0 | 0
156 | Wire management | 1.156 | 155FS | FS157 | 2023-09-26 13:00 | 2023-09-27 10:00 | 6h |  | 0 | 0 | 0 | 0 | 0
157 | Making connections | 1.157 | 156FS | FS158 | 2023-09-27 10:00 | 2023-09-27 12:00 | 2h |  | 0 | 0 | 0 | 0 | 0
158 | Final check | 1.158 | 157FS;144FS;145FS;146FS;147FS;148FS;38FS;152FS;153FS;154FS;150FS;151FS;127FS;128FS |  | 2023-09-27 13:00 | 2023-09-27 15:00 | 2h |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Project | 30h
1 | Placing outer heras fences | 2h | standard - symmetric | 80 | 100 | 120
2 | Placing inner heras fences | 2h | standard - symmetric | 80 | 100 | 120
3 | Setting up the tent (bar B1) | 2h | standard - symmetric | 80 | 100 | 120
4 | Tent equipping with utilities (bar B1) | 2h | standard - symmetric | 80 | 100 | 120
5 | Installing the bar (bar B1) | 1h | standard - symmetric | 80 | 100 | 120
6 | Connecting barrels (bar B1) | 1h | standard - symmetric | 80 | 100 | 120
7 | Positioning fridges (bar B1) | 1h | standard - symmetric | 80 | 100 | 120
8 | Filling fridges (bar B1) | 1h | standard - symmetric | 80 | 100 | 120
9 | Setting up the tent (bar B2) | 2h | standard - symmetric | 80 | 100 | 120
10 | Tent equipping with utilities (bar B2) | 2h | standard - symmetric | 80 | 100 | 120
11 | Installing the bar (bar B2) | 1h | standard - symmetric | 80 | 100 | 120
12 | Connecting barrels (bar B2) | 1h | standard - symmetric | 80 | 100 | 120
13 | Positioning fridges (bar B2) | 1h | standard - symmetric | 80 | 100 | 120
14 | Filling fridges (bar B2) | 1h | standard - symmetric | 80 | 100 | 120
15 | Setting up the tent (bar B5) | 2h | standard - symmetric | 80 | 100 | 120
16 | Tent equipping with utilities (bar B5) | 2h | standard - symmetric | 80 | 100 | 120
17 | Installing the bar (bar B5) | 1h | standard - symmetric | 80 | 100 | 120
18 | Connecting barrels (bar B5) | 1h | standard - symmetric | 80 | 100 | 120
19 | Positioning fridges (bar B5) | 1h | standard - symmetric | 80 | 100 | 120
20 | Filling fridges (bar B5) | 1h | standard - symmetric | 80 | 100 | 120
21 | Setting up the tent (bar B8) | 2h | standard - symmetric | 80 | 100 | 120
22 | Tent equipping with utilities (bar B8) | 2h | standard - symmetric | 80 | 100 | 120
23 | Installing the bar (bar B8) | 1h | standard - symmetric | 80 | 100 | 120
24 | Connecting barrels (bar B8) | 1h | standard - symmetric | 80 | 100 | 120
25 | Positioning fridges (bar B8) | 1h | standard - symmetric | 80 | 100 | 120
26 | Filling fridges (bar B8) | 1h | standard - symmetric | 80 | 100 | 120
27 | Setting up the tent (backstagetent) | 0 | standard - symmetric | 80 | 100 | 120
28 | Tent equipping with utilities (backstagetent) | 0 | standard - symmetric | 80 | 100 | 120
29 | Furnishing interior tent (backstagetent) | 0 | standard - symmetric | 80 | 100 | 120
30 | Setting up the tent (first-aid tent) | 0 | standard - symmetric | 80 | 100 | 120
31 | Tent equipping with utilities (first-aid tent) | 0 | standard - symmetric | 80 | 100 | 120
32 | Setting up the tent (employees frame tent) | 2h | standard - symmetric | 80 | 100 | 120
33 | Tent equipping with utilities (employees frame tent) | 0 | standard - symmetric | 80 | 100 | 120
34 | Furnishing interior tent (employees frame tent) | 0 | standard - symmetric | 80 | 100 | 120
35 | Setting up the tent (Eristoff tent) | 2h | standard - symmetric | 80 | 100 | 120
36 | Tent equipping with utilities (Eristoff tent) | 0 | standard - symmetric | 80 | 100 | 120
37 | Furnishing interior tent (Eristoff tent) | 4h | standard - symmetric | 80 | 100 | 120
38 | Setting up 53 tents (association tents) | 2h | standard - symmetric | 80 | 100 | 120
39 | Setting up the tent (VIP catering) | 0 | standard - symmetric | 80 | 100 | 120
40 | Tent equipping with utilities (VIP catering) | 0 | standard - symmetric | 80 | 100 | 120
41 | Furnishing interior tent (VIP catering) | 1h | standard - symmetric | 80 | 100 | 120
42 | Setting up the deck (VIP deck) | 3h | standard - symmetric | 80 | 100 | 120
43 | Setting up the tent (VIP deck) | 3h | standard - symmetric | 80 | 100 | 120
44 | Tent equipping with utilities (VIP deck) | 2h | standard - symmetric | 80 | 100 | 120
45 | Furnishing interior tent (VIP deck) | 2h | standard - symmetric | 80 | 100 | 120
46 | Setting up the tent (recycling area 1) | 0 | standard - symmetric | 80 | 100 | 120
47 | Tent equipping with utilities (recycling area 1) | 0 | standard - symmetric | 80 | 100 | 120
48 | Furnishing interior tent (recycling area 1) | 0 | standard - symmetric | 80 | 100 | 120
49 | Setting up the tent (recycling area 2) | 0 | standard - symmetric | 80 | 100 | 120
50 | Tent equipping with utilities (recycling area 2) | 0 | standard - symmetric | 80 | 100 | 120
51 | Furnishing interior tent (recycling area 2) | 0 | standard - symmetric | 80 | 100 | 120
52 | Setting up the tent (recycling area 3) | 0 | standard - symmetric | 80 | 100 | 120
53 | Tent equipping with utilities (recycling area 3) | 0 | standard - symmetric | 80 | 100 | 120
54 | Furnishing interior tent (recycling area 3) | 0 | standard - symmetric | 80 | 100 | 120
55 | Setting up the tent (direction 1) | 0 | standard - symmetric | 80 | 100 | 120
56 | Tent equipping with utilities (direction 1) | 0 | standard - symmetric | 80 | 100 | 120
57 | Furnishing interior tent (direction 1) | 0 | standard - symmetric | 80 | 100 | 120
58 | Setting up the tent (direction 2) | 0 | standard - symmetric | 80 | 100 | 120
59 | Tent equipping with utilities (direction 2) | 0 | standard - symmetric | 80 | 100 | 120
60 | Furnishing interior tent (direction 2) | 0 | standard - symmetric | 80 | 100 | 120
61 | Placing bottom container (bar 3) | 0 | standard - symmetric | 80 | 100 | 120
62 | Placing top container (bar3) | 0 | standard - symmetric | 80 | 100 | 120
63 | Installing the stairs (bar3) | 0 | standard - symmetric | 80 | 100 | 120
64 | Equipping both containers with utilities (bar3) | 0 | standard - symmetric | 80 | 100 | 120
65 | Filling the fridges in the bottom container (bar 3) | 0 | standard - symmetric | 80 | 100 | 120
66 | Furnishing interior of upper container (bar 3) | 0 | standard - symmetric | 80 | 100 | 120
67 | Placing fully equipped container (bar 4) | 0 | standard - symmetric | 80 | 100 | 120
68 | Equipping container with utilities (bar 4) | 0 | standard - symmetric | 80 | 100 | 120
69 | Placing container (desk container boxoffices) | 0 | standard - symmetric | 80 | 100 | 120
70 | Equipping container with utilities (desk container boxoffices) | 0 | standard - symmetric | 80 | 100 | 120
71 | Furnishing interior of container (desk container boxoffices) | 0 | standard - symmetric | 80 | 100 | 120
72 | Placing container (desk container coordinators) | 0 | standard - symmetric | 80 | 100 | 120
73 | Equipping container with utilities (desk container coordinators) | 0 | standard - symmetric | 80 | 100 | 120
74 | Furnishing interior of container (desk container coordinators) | 0 | standard - symmetric | 80 | 100 | 120
75 | Placing container (first-aid) | 0 | standard - symmetric | 80 | 100 | 120
76 | Equipping container with utilities (first-aid) | 0 | standard - symmetric | 80 | 100 | 120
77 | Furnishing interior of container (first-aid) | 0 | standard - symmetric | 80 | 100 | 120
78 | Placing bottom container (warehouse + SS) | 0 | standard - symmetric | 80 | 100 | 120
79 | Placing top container (warehouse + SS) | 0 | standard - symmetric | 80 | 100 | 120
80 | Installing the stairs (warehouse + SS) | 0 | standard - symmetric | 80 | 100 | 120
81 | Equipping both containers with utilities (warehouse + SS) | 0 | standard - symmetric | 80 | 100 | 120
82 | Furnishing interior of both containers (warehouse + SS) | 0 | standard - symmetric | 80 | 100 | 120
83 | Placing container (press) | 0 | standard - symmetric | 80 | 100 | 120
84 | Equipping container with utilities (press) | 0 | standard - symmetric | 80 | 100 | 120
85 | Furnishing interior of container (press) | 0 | standard - symmetric | 80 | 100 | 120
86 | Placing container (production x IT x bitstream) | 0 | standard - symmetric | 80 | 100 | 120
87 | Equipping container with utilities (production x IT x bitstream) | 0 | standard - symmetric | 80 | 100 | 120
88 | Furnishing interior of container (production x IT x bitstream) | 0 | standard - symmetric | 80 | 100 | 120
89 | Placing container (checkout Petermans) | 0 | standard - symmetric | 80 | 100 | 120
90 | Equipping container with utilities (checkout Petermans) | 0 | standard - symmetric | 80 | 100 | 120
91 | Furnishing interior of container (checkout Petermans) | 0 | standard - symmetric | 80 | 100 | 120
92 | Placing container (checkout 1 main toilet) | 0 | standard - symmetric | 80 | 100 | 120
93 | Equipping container with utilities (checkout 1 main toilet) | 0 | standard - symmetric | 80 | 100 | 120
94 | Furnishing interior of container (checkout 1 main toilet) | 0 | standard - symmetric | 80 | 100 | 120
95 | Placing container (checkout 2 main toilet) | 0 | standard - symmetric | 80 | 100 | 120
96 | Equipping container with utilities (checkout 2 main toilet) | 0 | standard - symmetric | 80 | 100 | 120
97 | Furnishing interior of container (checkout 2 main toilet) | 0 | standard - symmetric | 80 | 100 | 120
98 | Placing container (checkout container K1) | 0 | standard - symmetric | 80 | 100 | 120
99 | Equipping container with utilities (checkout container K1) | 0 | standard - symmetric | 80 | 100 | 120
100 | Furnishing interior of container (checkout container K1) | 0 | standard - symmetric | 80 | 100 | 120
101 | Placing container (checkout container K2) | 0 | standard - symmetric | 80 | 100 | 120
102 | Equipping container with utilities (checkout container K2) | 0 | standard - symmetric | 80 | 100 | 120
103 | Furnishing interior of container (checkout container K2) | 0 | standard - symmetric | 80 | 100 | 120
104 | Placing container (checkout container K3) | 0 | standard - symmetric | 80 | 100 | 120
105 | Equipping container with utilities (checkout container K3) | 0 | standard - symmetric | 80 | 100 | 120
106 | Furnishing interior of container (checkout container K3) | 0 | standard - symmetric | 80 | 100 | 120
107 | Placing container (checkout container K4) | 0 | standard - symmetric | 80 | 100 | 120
108 | Equipping container with utilities (checkout container K4) | 0 | standard - symmetric | 80 | 100 | 120
109 | Furnishing interior of container (checkout container K4) | 0 | standard - symmetric | 80 | 100 | 120
110 | Placing container (checkout container K5) | 0 | standard - symmetric | 80 | 100 | 120
111 | Equipping container with utilities (checkout container K5) | 0 | standard - symmetric | 80 | 100 | 120
112 | Furnishing interior of container (checkout container K5) | 0 | standard - symmetric | 80 | 100 | 120
113 | Placing container (core container) | 0 | standard - symmetric | 80 | 100 | 120
114 | Equipping container with utilities (core container) | 0 | standard - symmetric | 80 | 100 | 120
115 | Furnishing interior of container (core container) | 0 | standard - symmetric | 80 | 100 | 120
116 | Placing container (toilet container VIP) | 0 | standard - symmetric | 80 | 100 | 120
117 | Equipping container with utilities (toilet container VIP) | 0 | standard - symmetric | 80 | 100 | 120
118 | Equipping container with supplies (toilet container VIP) | 0 | standard - symmetric | 80 | 100 | 120
119 | Placing piscines (toilet 1) | 2h | standard - symmetric | 80 | 100 | 120
120 | Placing toilets (toilet 1) | 2h | standard - symmetric | 80 | 100 | 120
121 | Equipping with utilities (toilet 1) | 2h | standard - symmetric | 80 | 100 | 120
122 | Building up toilet exit (toilet 1) | 1h | standard - symmetric | 80 | 100 | 120
123 | Placing piscines (toilet 2) | 1h | standard - symmetric | 80 | 100 | 120
124 | Placing toilets (toilet 2) | 1h | standard - symmetric | 80 | 100 | 120
125 | Equipping with utilities (toilet 2) | 0 | standard - symmetric | 80 | 100 | 120
126 | Helping with set-up (mainstage) | 18h | standard - symmetric | 80 | 100 | 120
127 | Helping with set-up (delay 1) | 0 | standard - symmetric | 80 | 100 | 120
128 | Helping with set-up (delay 2) | 0 | standard - symmetric | 80 | 100 | 120
129 | Helping with set-up (petermans 1) | 0 | standard - symmetric | 80 | 100 | 120
130 | Helping with set-up (petermans 2) | 0 | standard - symmetric | 80 | 100 | 120
131 | Placing container (DJ booth) | 0 | standard - symmetric | 80 | 100 | 120
132 | Equipping container with utilities (DJ booth) | 0 | standard - symmetric | 80 | 100 | 120
133 | Positioning container fridge | 0 | standard - symmetric | 80 | 100 | 120
134 | Equipping with utilities (container fridge) | 0 | standard - symmetric | 80 | 100 | 120
135 | Positioning Icelander | 0 | standard - symmetric | 80 | 100 | 120
136 | Equipping with utilities (icelander) | 0 | standard - symmetric | 80 | 100 | 120
137 | Positioning tap water site | 0 | standard - symmetric | 80 | 100 | 120
138 | Equipping with utilities (tap water site) | 0 | standard - symmetric | 80 | 100 | 120
139 | Placing cold store (x2) (bar B1) | 0 | standard - symmetric | 80 | 100 | 120
140 | Placing cold store (bar 4) | 0 | standard - symmetric | 80 | 100 | 120
141 | Placing cold store (bar B2) | 0 | standard - symmetric | 80 | 100 | 120
142 | Placing cold store (x2) (bar B8) | 0 | standard - symmetric | 80 | 100 | 120
143 | Equipping cold store with utilities | 0 | standard - symmetric | 80 | 100 | 120
144 | Placing Maes barrels (x2) (bar B2) | 0 | standard - symmetric | 80 | 100 | 120
145 | Placing barrels (x5) (bar B8) | 0 | standard - symmetric | 80 | 100 | 120
146 | Placing Maes barrels (x3) (bar B1) | 0 | standard - symmetric | 80 | 100 | 120
147 | Placing barrels (x3) (bar B5) | 0 | standard - symmetric | 80 | 100 | 120
148 | Placing Maes barrels (x2) (bar 4) | 0 | standard - symmetric | 80 | 100 | 120
149 | Equipping with utilities (storage Buysse) | 0 | standard - symmetric | 80 | 100 | 120
150 | Positioning stock (bar B1) | 1h | standard - symmetric | 80 | 100 | 120
151 | Positioning stock (bar B8) | 1h | standard - symmetric | 80 | 100 | 120
152 | Placing crashbarriers (mainstage) | 2h | standard - symmetric | 80 | 100 | 120
153 | Placing crashbarriers (Eristoff stage) | 0 | standard - symmetric | 80 | 100 | 120
154 | Placing crashbarriers (Petermanstage) | 0 | standard - symmetric | 80 | 100 | 120
155 | Placing constructions | 6h | standard - symmetric | 80 | 100 | 120
156 | Wire management | 6h | standard - symmetric | 80 | 100 | 120
157 | Making connections | 2h | standard - symmetric | 80 | 100 | 120
158 | Final check | 2h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))