## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Family Day | 1 |  |  | 2012-06-01 08:00 | 2012-10-16 10:00 | 97d 2h |  |  | 23131 |  |  | 31675 | 137.0833
1 | first appointment | 1.1 |  | FS2 | 2012-06-01 08:00 | 2012-06-01 17:00 | 1d | Full-Time[2.00 #2] | 192 | 0 | 0 | 0 | 192 | 0.375
2 | register location | 1.2 | 1FS | FS3;FS9;FS5;FS18;FS8 | 2012-06-04 10:00 | 2012-07-02 10:00 | 20d | Employees[2.00 #3] | 1280 | 5000 | 0 | 0 | 6280 | 28
3 | discuss invitation | 1.3 | 2FS | FS4 | 2012-07-23 10:00 | 2012-08-06 10:00 | 10d | Employees | 320 | 0 | 0 | 0 | 320 | 14
4 | print and send invitation | 1.4 | 3FS | FS16 | 2012-08-06 10:00 | 2012-08-13 10:00 | 5d | Employees | 160 | 220 | 0 | 0 | 380 | 7
5 | order bar | 1.5 | 2FS | FS17;FS6 | 2012-07-02 10:00 | 2012-07-16 10:00 | 10d | Employees | 320 | 1000 | 0 | 0 | 1320 | 14
6 | order bouncy castle | 1.6 | 5FS | FS21;FS22 | 2012-07-16 10:00 | 2012-07-23 10:00 | 5d | Employees | 160 | 220 | 0 | 0 | 380 | 7
7 | map out the route | 1.7 | 9FS | FS10 | 2012-07-30 10:00 | 2012-08-13 10:00 | 10d | Employees[2.00 #3] | 640 | 0 | 0 | 0 | 640 | 14
8 | search and hire fotographer | 1.8 | 2FS | FS21 | 2012-07-23 10:00 | 2012-07-30 10:00 | 5d | Employees | 160 | 800 | 0 | 0 | 960 | 7
9 | find stations | 1.9 | 2FS | FS7 | 2012-07-02 10:00 | 2012-07-23 10:00 | 15d | Employees[2.00 #3] | 960 | 300 | 0 | 0 | 1260 | 21
10 | find suitable activities for stations | 1.10 | 7FS | FS11 | 2012-08-13 10:00 | 2012-08-27 10:00 | 10d | Employees[2.00 #3] | 640 | 0 | 0 | 0 | 640 | 14
11 | plan activities | 1.11 | 10FS | FS17;FS13;FS12 | 2012-08-27 10:00 | 2012-09-10 10:00 | 10d | Employees | 320 | 0 | 0 | 0 | 320 | 14
12 | make route description | 1.12 | 11FS | FS21 | 2012-09-10 10:00 | 2012-09-17 10:00 | 5d | Employees | 160 | 100 | 0 | 0 | 260 | 7
13 | find volunteers/helpers | 1.13 | 11FS | FS21 | 2012-09-17 10:00 | 2012-10-08 10:00 | 15d | Employees | 480 | 368 | 0 | 0 | 848 | 21
14 | discuss decoration | 1.14 | 18FS | FS19 | 2012-09-10 10:00 | 2012-09-17 10:00 | 5d | Employees | 160 | 0 | 0 | 0 | 160 | 7
15 | discuss and order menu | 1.15 | 20FS | FS21 | 2012-09-24 10:00 | 2012-10-01 10:00 | 5d | Employees | 160 | 12000 | 0 | 0 | 12160 | 7
16 | receiving rsvp's | 1.16 | 4FS | FS20;FS17 | 2012-08-13 10:00 | 2012-09-10 10:00 | 20d | Employees | 640 | 0 | 0 | 0 | 640 | 28
17 | buy supplies afternoon | 1.17 | 16FS;5FS;11FS | FS21 | 2012-10-01 10:00 | 2012-10-15 10:00 | 10d | Employees[2.00 #3] | 640 | 850 | 0 | 0 | 1490 | 14
18 | search for dj and stereo | 1.18 | 2FS | FS14 | 2012-08-27 10:00 | 2012-09-10 10:00 | 10d | Employees | 320 | 600 | 0 | 0 | 920 | 14
19 | buy decorations | 1.19 | 14FS | FS21 | 2012-10-08 10:00 | 2012-10-15 10:00 | 5d | Employees | 160 | 200 | 0 | 0 | 360 | 7
20 | book caterer | 1.20 | 16FS | FS15 | 2012-09-10 10:00 | 2012-09-24 10:00 | 10d | Employees | 320 | 0 | 0 | 0 | 320 | 14
22 | hire rain supplies | 1.21 | 6FS | FS21 | 2012-09-19 08:00 | 2012-09-25 17:00 | 5d | Employees | 160 | 1473 | 0 | 0 | 1633 | 6.375
21 | family day | 1.22 | 15FS;17FS;12FS;13FS;8FS;19FS;6FS;22FS |  | 2012-10-15 10:00 | 2012-10-16 10:00 | 1d | Full-Time[2.00 #2] | 192 | 0 | 0 | 0 | 192 | 1

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employees | Renewable | 3 | 0 | 4 | 2[2.00 Employees];3;4;5;6;7[2.00 Employees];8;9[2.00 Employees];10[2.00 Employees];11;12;13;14;15;16;17[2.00 Employees];18;19;20;22; | 8160
2 | Full-Time | Renewable | 2 | 0 | 12 | 1[2.00 Full-Time];21[2.00 Full-Time]; | 384

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Family Day | 778h |  |  |  |  | 99 | 100 | 101
1 | first appointment | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | register location | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | discuss invitation | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | print and send invitation | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | order bar | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | order bouncy castle | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | map out the route | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | search and hire fotographer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | find stations | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | find suitable activities for stations | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | plan activities | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | make route description | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | find volunteers/helpers | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | discuss decoration | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | discuss and order menu | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | receiving rsvp's | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | buy supplies afternoon | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | search for dj and stereo | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | buy decorations | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | book caterer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | hire rain supplies | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | family day | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold