## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Debt Collection System | 1 |  |  | 2013-10-24 08:00 | 2014-05-20 12:00 | 148d 4h |  |  | 0 |  |  | 458112.3684 | 208.1667
9 | define | 1.1 |  |  | 2013-10-24 08:00 | 2013-12-18 17:00 | 40d |  |  | 0 |  |  | 41864.71 | 55.375
1 | kick-off meeting | 1.1.1 |  | FS2;FS3;FS4;FS5 | 2013-10-24 08:00 | 2013-10-24 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 0.375
266 | project charter set | 1.1.2 |  |  | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  |  | 0 |  |  | 37495.44 | 31.375
2 | project charter (scope definition) | 1.1.2.1 | 1FS | FS7;FS6 | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d | Employee A;Employee B | 36531.84 | 0 | 0 | 0 | 36531.84 | 31.375
3 | project security risks | 1.1.2.2 | 1FS | FS7;FS6 | 2013-11-13 08:00 | 2013-11-13 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
267 | project charter - communication and validation | 1.1.3 |  |  | 2013-11-25 08:00 | 2013-12-18 17:00 | 18d |  |  | 0 |  |  | 3810.71 | 23.375
4 | inform IT governance | 1.1.3.1 | 1FS | FS7;FS6 | 2013-11-25 08:00 | 2013-11-25 09:00 | 1h | Employee B;Employee C | 240.9 | 0 | 0 | 0 | 240.9 | 0.041667
5 | send info | 1.1.3.2 | 1FS | FS7;FS6 | 2013-11-28 08:00 | 2013-11-28 17:00 | 1d | Employee B;Employee D | 1927.2 | 0 | 0 | 0 | 1927.2 | 0.375
6 | send project charter for validation + delivery board validation | 1.1.3.3 | 2FS;3FS;4FS;5FS | FS8 | 2013-12-13 08:00 | 2013-12-16 09:00 | 1d 1h | Employee B | 1084.05 | 0 | 0 | 0 | 1084.05 | 3.0417
7 | business validation | 1.1.3.4 | 2FS;3FS;4FS;5FS | FS8 | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 0.375
8 | end of define | 1.1.3.5 | 6FS;7FS | FS14 | 2013-12-18 17:00 | 2013-12-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
22 | design | 1.2 |  |  | 2013-11-25 08:00 | 2014-02-10 17:00 | 56d |  |  | 0 |  |  | 107215.84 | 77.375
15 | blueprint set | 1.2.1 |  |  | 2013-11-25 08:00 | 2014-01-23 17:00 | 44d |  |  | 0 |  |  | 103826.72 | 59.375
10 | functional analysis List/file creation | 1.2.1.1 |  |  | 2013-12-02 08:00 | 2014-01-03 17:00 | 25d | Employee G | 15056 | 0 | 0 | 0 | 15056 | 32.375
11 | functional analysis Monitoring | 1.2.1.2 |  |  | 2013-11-25 08:00 | 2014-01-08 17:00 | 33d | Employee H | 19873.92 | 0 | 0 | 0 | 19873.92 | 44.375
12 | functional analysis Interfacing | 1.2.1.3 |  |  | 2013-11-25 08:00 | 2014-01-03 17:00 | 30d | Employee F;Employee I | 36134.4 | 0 | 0 | 0 | 36134.4 | 39.375
13 | architecture analysis | 1.2.1.4 |  |  | 2013-11-25 08:00 | 2013-12-27 17:00 | 25d | Employee E | 24090 | 0 | 0 | 0 | 24090 | 32.375
14 | budget &amp; planning for development + master test chapter | 1.2.1.5 | 8FS |  | 2014-01-13 08:00 | 2014-01-23 17:00 | 9d | Employee B | 8672.4 | 0 | 0 | 0 | 8672.4 | 10.375
21 | design phase - validations | 1.2.2 |  |  | 2014-01-21 08:00 | 2014-02-10 17:00 | 15d |  |  | 0 |  |  | 3389.12 | 20.375
16 | presentation to Business part 1 | 1.2.2.1 |  | FS17 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G;Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.16667
17 | presentation to Business part 2 | 1.2.2.2 | 16FS | FS18 | 2014-01-31 08:00 | 2014-01-31 12:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 0.16667
18 | send to delivery board + IT governance validation | 1.2.2.3 | 17FS | FS20 | 2014-02-07 08:00 | 2014-02-10 17:00 | 2d | Employee B | 1927.2 | 0 | 0 | 0 | 1927.2 | 3.375
19 | business validation | 1.2.2.4 |  |  | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 0.375
20 | end of design | 1.2.2.5 | 18FS |  | 2014-02-10 17:00 | 2014-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
184 | build | 1.3 |  |  | 2013-12-27 15:00 | 2014-05-14 17:00 | 98d 2h |  |  | 0 |  |  | 178453.6384 | 138.0833
32 | weekly file | 1.3.1 |  |  | 2014-01-02 15:00 | 2014-03-11 17:00 | 48d 2h |  |  | 0 |  |  | 19499.28 | 68.0833
23 | build/technical design | 1.3.1.1 | 33FS | FS24 | 2014-01-02 15:00 | 2014-01-09 15:00 | 5d | Employee G[0.60 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 7
24 | ABAP | 1.3.1.2 | 23FS | FS31 | 2014-01-09 15:00 | 2014-01-22 15:00 | 9d | ABAP | 6750 | 0 | 0 | 0 | 6750 | 13
25 | UT program in general | 1.3.1.3 | 31FS | FS26;FS27;FS30;FS191 | 2014-01-23 15:00 | 2014-01-27 10:00 | 1d 4h | Employee G | 903.36 | 0 | 0 | 0 | 903.36 | 3.7917
26 | UT submission file | 1.3.1.4 | 25FS | FS30;FS29;FS191 | 2014-01-31 15:00 | 2014-02-06 10:00 | 3d 4h | Employee G | 2107.84 | 0 | 0 | 0 | 2107.84 | 5.7917
27 | UT clearing file | 1.3.1.5 | 25FS | FS28;FS30;FS29;FS191 | 2014-01-27 10:00 | 2014-01-31 10:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 4
28 | UT other treatment file | 1.3.1.6 | 27FS | FS29;FS191 | 2014-01-31 10:00 | 2014-02-06 10:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 6
29 | business UT submission | 1.3.1.7 | 26FS;27FS;28FS |  | 2014-03-05 13:00 | 2014-03-10 12:00 | 3d | Employee M | 1908.96 | 0 | 0 | 0 | 1908.96 | 4.9583
30 | UT sending via e-mail | 1.3.1.8 | 25FS;26FS;27FS |  | 2014-03-11 08:00 | 2014-03-11 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
31 | build/technical design | 1.3.1.9 | 24FS | FS25 | 2014-01-22 15:00 | 2014-01-23 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 1
82 | monthly file | 1.3.2 |  |  | 2013-12-27 15:00 | 2014-02-14 17:00 | 35d 2h |  |  | 0 |  |  | 6713.344 | 49.0833
33 | build/technical design | 1.3.2.1 |  | FS34;FS23 | 2013-12-27 15:00 | 2014-01-02 15:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 6
34 | ABAP | 1.3.2.2 | 33FS | FS35 | 2014-01-30 08:00 | 2014-02-03 12:00 | 2d 4h | ABAP[0.80 #1] | 1500 | 0 | 0 | 0 | 1500 | 4.1667
35 | UT | 1.3.2.3 | 34FS | FS36;FS192 | 2014-02-03 13:00 | 2014-02-11 17:00 | 6d 4h | Employee G[0.40 #1] | 1565.824 | 0 | 0 | 0 | 1565.824 | 8.1667
36 | business UT | 1.3.2.4 | 35FS | FS37 | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee M | 636.32 | 0 | 0 | 0 | 636.32 | 0.375
37 | UT sending via e-mail | 1.3.2.5 | 36FS |  | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
83 | authorization check | 1.3.3 |  |  | 2014-01-24 08:00 | 2014-03-24 12:00 | 41d 4h |  |  | 0 |  |  | 15386.2 | 59.1667
38 | IRIS-SC | 1.3.3.1 | 196FS | FS43;FS45;FS61;FS71 | 2014-03-13 08:00 | 2014-03-18 17:00 | 4d | Java | 3000 | 0 | 0 | 0 | 3000 | 5.375
39 | build/technical design | 1.3.3.2 |  | FS40;FS42 | 2014-01-24 08:00 | 2014-01-24 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
40 | ABAP | 1.3.3.3 | 39FS | FS41-1d | 2014-01-27 08:00 | 2014-02-10 17:00 | 11d | ABAP | 8250 | 0 | 0 | 0 | 8250 | 14.375
41 | UT | 1.3.3.4 | 40FS-1d | FS44 | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
42 | build/technical design | 1.3.3.5 | 39FS | FS43 | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
43 | ABAP | 1.3.3.6 | 38FS;42FS;45FS | FS44 | 2014-03-19 13:00 | 2014-03-20 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 0.95833
44 | UT | 1.3.3.7 | 41FS;43FS | FS46;FS71 | 2014-03-20 13:00 | 2014-03-21 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.95833
45 | import WSDL | 1.3.3.8 | 38FS | FS43 | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 0.16667
46 | ESB (pass BP to basic) | 1.3.3.9 | 44FS |  | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2.9583
84 | send DMS file via e-mail | 1.3.4 |  |  | 2014-02-05 15:00 | 2014-03-10 17:00 | 23d 2h |  |  | 0 |  |  | 13548.8944 | 33.0833
47 | build/technical design | 1.3.4.1 |  | FS67 | 2014-02-17 08:00 | 2014-03-07 10:00 | 14d 2h | Employee I[0.07 #1] | 600.7344 | 0 | 0 | 0 | 600.7344 | 18.0833
48 | import WSDL | 1.3.4.2 |  | FS49;FS62;FS191;FS192;FS193;FS195 | 2014-02-05 15:00 | 2014-02-06 10:00 | 4h | EAI | 301.12 | 0 | 0 | 0 | 301.12 | 0.79167
49 | build/technical design | 1.3.4.3 | 48FS | FS50;FS52;FS55 | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
50 | EAI | 1.3.4.4 | 49FS | FS51 | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
51 | UT | 1.3.4.5 | 50FS | FS70 | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.375
52 | build/technical design | 1.3.4.6 | 49FS | FS53;FS55 | 2014-02-18 08:00 | 2014-02-18 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
53 | EAI | 1.3.4.7 | 52FS | FS54 | 2014-02-19 08:00 | 2014-02-19 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
54 | UT | 1.3.4.8 | 53FS |  | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
55 | design | 1.3.4.9 | 49FS;52FS | FS56 | 2014-02-19 08:00 | 2014-02-20 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.375
56 | build | 1.3.4.10 | 55FS | FS57 | 2014-02-21 08:00 | 2014-02-25 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 4.375
57 | queue handling | 1.3.4.11 | 56FS | FS58 | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2.375
58 | UT | 1.3.4.12 | 57FS | FS59 | 2014-03-03 08:00 | 2014-03-06 17:00 | 4d | EAI | 2408.96 | 0 | 0 | 0 | 2408.96 | 3.375
59 | deployment | 1.3.4.13 | 58FS |  | 2014-03-07 08:00 | 2014-03-10 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 3.375
85 | duplicates | 1.3.5 |  |  | 2014-02-12 13:00 | 2014-03-26 17:00 | 30d 4h |  |  | 0 |  |  | 5261.2 | 42.1667
60 | build/technical design | 1.3.5.1 | 63FS | FS61 | 2014-02-12 13:00 | 2014-02-14 12:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.9583
61 | java | 1.3.5.2 | 38FS;60FS;64FS | FS62 | 2014-03-19 08:00 | 2014-03-21 17:00 | 3d | Java | 2250 | 0 | 0 | 0 | 2250 | 2.375
62 | UT | 1.3.5.3 | 48FS;61FS |  | 2014-03-24 08:00 | 2014-03-26 17:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2.375
86 | current saldo | 1.3.6 |  |  | 2014-02-11 08:00 | 2014-02-20 17:00 | 8d |  |  | 0 |  |  | 3943.04 | 9.375
63 | build/technical design | 1.3.6.1 |  | FS60;FS64 | 2014-02-11 08:00 | 2014-02-12 12:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 1.1667
64 | java | 1.3.6.2 | 63FS | FS61;FS65 | 2014-02-14 13:00 | 2014-02-18 12:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 3.9583
65 | UT | 1.3.6.3 | 64FS | FS66 | 2014-02-18 13:00 | 2014-02-19 17:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 1.1667
66 | business UT | 1.3.6.4 | 65FS |  | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 0.375
88 | BRM | 1.3.7 |  |  | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d |  |  | 0 |  |  | 3613.44 | 10
67 | BRM | 1.3.7.1 | 47FS | FS136;FS155 | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d | Employee I | 3613.44 | 0 | 0 | 0 | 3613.44 | 10
87 | account statement | 1.3.8 |  |  | 2014-01-24 15:00 | 2014-03-31 12:00 | 45d 6h |  |  | 0 |  |  | 15044.8 | 65.875
68 | build/technical design | 1.3.8.1 |  | FS69;FS81-1d;FS195 | 2014-01-24 15:00 | 2014-02-07 15:00 | 10d | Employee F[0.50 #1];Employee L[0.50 #1] | 6022.4 | 0 | 0 | 0 | 6022.4 | 14
69 | ABAP | 1.3.8.2 | 68FS | FS72;FS70 | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 1.375
70 | UT | 1.3.8.3 | 51FS;69FS | FS73;FS76;FS194 | 2014-02-13 08:00 | 2014-02-14 17:00 | 2d | Employee F;Employee L | 2408.96 | 0 | 0 | 0 | 2408.96 | 1.375
71 | spec proxy | 1.3.8.4 | 38FS;44FS | FS74 | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2.9583
72 | ABAP proxy | 1.3.8.5 | 69FS | FS73 | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 0.375
73 | UT proxy | 1.3.8.6 | 70FS;72FS | FS76 | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
74 | spec wrapper core | 1.3.8.7 | 71FS | FS75 | 2014-03-24 13:00 | 2014-03-26 12:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.9583
75 | ABAP wrapper core | 1.3.8.8 | 74FS | FS76 | 2014-03-26 13:00 | 2014-03-27 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 0.95833
76 | UT wrapper core | 1.3.8.9 | 70FS;73FS;75FS | FS77 | 2014-03-27 13:00 | 2014-03-28 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.95833
77 | email functionality | 1.3.8.10 | 76FS |  | 2014-03-28 13:00 | 2014-03-31 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2.9583
173 | monitoring and reporting | 1.3.9 |  |  | 2014-01-29 08:00 | 2014-03-05 15:00 | 25d 6h |  |  | 0 |  |  | 31228.56 | 35.2917
78 | build/technical design | 1.3.9.1 |  | FS79;FS187 | 2014-01-29 08:00 | 2014-02-03 17:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 5.375
79 | ABAP | 1.3.9.2 | 78FS | FS80 | 2014-02-06 08:00 | 2014-02-12 17:00 | 5d | ABAP | 3750 | 0 | 0 | 0 | 3750 | 6.375
80 | UT | 1.3.9.3 | 79FS | FS96 | 2014-02-13 08:00 | 2014-02-19 17:00 | 5d | Employee H;ABAP | 6761.2 | 0 | 0 | 0 | 6761.2 | 6.375
81 | BI reports | 1.3.9.4 | 68FS-1d | FS188;FS190 | 2014-02-06 15:00 | 2014-03-05 15:00 | 19d | Employee K | 18308.4 | 0 | 0 | 0 | 18308.4 | 27
174 | weekly file | 1.3.10 |  |  | 2014-03-21 08:00 | 2014-04-01 15:00 | 7d 6h |  |  | 0 |  |  | 3219.2 | 11.2917
89 | build/technical design | 1.3.10.1 |  | FS90 | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
90 | ABAP | 1.3.10.2 | 89FS | FS91 | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 0.375
91 | UT | 1.3.10.3 | 90FS | FS96 | 2014-03-25 08:00 | 2014-03-25 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
92 | build/technical design | 1.3.10.4 | 98FS | FS93;FS94 | 2014-03-28 15:00 | 2014-03-31 10:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2.7917
93 | setup autosys | 1.3.10.5 | 92FS | FS203 | 2014-03-31 15:00 | 2014-04-01 15:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 1
175 | monthly file | 1.3.11 |  |  | 2014-03-31 10:00 | 2014-04-01 17:00 | 1d 6h |  |  | 0 |  |  | 1505.62 | 1.2917
94 | build/technical design | 1.3.11.1 | 92FS | FS95 | 2014-03-31 10:00 | 2014-03-31 15:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 0.20833
95 | setup autosys | 1.3.11.2 | 94FS | FS203 | 2014-03-31 15:00 | 2014-04-01 17:00 | 1d 2h | Employee D | 1204.5 | 0 | 0 | 0 | 1204.5 | 1.0833
176 | list | 1.3.12 |  |  | 2014-03-26 08:00 | 2014-03-28 15:00 | 2d 6h |  |  | 0 |  |  | 1579.48 | 2.2917
96 | build/technical design | 1.3.12.1 | 80FS;91FS | FS97 | 2014-03-26 08:00 | 2014-03-26 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
97 | ABAP | 1.3.12.2 | 96FS | FS98 | 2014-03-27 08:00 | 2014-03-27 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 0.16667
98 | UT | 1.3.12.3 | 97FS | FS92;FS204 | 2014-03-27 15:00 | 2014-03-28 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 1
177 | migration program | 1.3.13 |  |  | 2014-03-21 08:00 | 2014-04-07 17:00 | 12d |  |  | 0 |  |  | 7522.4 | 17.375
99 | build/technical design | 1.3.13.1 | 135FS | FS100 | 2014-03-21 08:00 | 2014-04-01 17:00 | 8d | Employee H | 4817.92 | 0 | 0 | 0 | 4817.92 | 11.375
100 | ABAP | 1.3.13.2 | 99FS | FS101 | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 1.375
101 | UT | 1.3.13.3 | 100FS | FS202 | 2014-04-04 08:00 | 2014-04-07 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 3.375
178 | send DMS file via e-mail | 1.3.14 |  |  | 2014-03-14 08:00 | 2014-03-27 15:00 | 9d 6h |  |  | 0 |  |  | 7463.06 | 13.2917
102 | WSDL update | 1.3.14.1 | 198FS | FS103 | 2014-03-14 08:00 | 2014-03-14 10:00 | 2h | Java;Employee I | 338.06 | 0 | 0 | 0 | 338.06 | 0.083333
103 | get cert / encrypt | 1.3.14.2 | 102FS | FS104 | 2014-03-14 10:00 | 2014-03-21 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 7
104 | error handling | 1.3.14.3 | 103FS | FS105 | 2014-03-21 10:00 | 2014-03-25 10:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 4
105 | UT java team | 1.3.14.4 | 104FS | FS205 | 2014-03-25 10:00 | 2014-03-27 15:00 | 2d 4h | Java | 1875 | 0 | 0 | 0 | 1875 | 2.2083
179 | feedback | 1.3.15 |  |  | 2014-03-11 15:00 | 2014-04-04 10:00 | 17d 4h |  |  | 0 |  |  | 29314.4 | 23.7917
106 | build/technical design | 1.3.15.1 |  | FS107;FS112;FS201 | 2014-03-13 08:00 | 2014-03-13 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
107 | ABAP | 1.3.15.2 | 106FS | FS108 | 2014-03-14 08:00 | 2014-03-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 0.375
108 | UT | 1.3.15.3 | 107FS |  | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
109 | build/technical design | 1.3.15.4 | 199FS | FS110;FS115 | 2014-03-11 15:00 | 2014-03-12 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 0.79167
110 | ABAP | 1.3.15.5 | 109FS | FS111 | 2014-03-21 15:00 | 2014-03-24 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2.7917
111 | UT | 1.3.15.6 | 110FS |  | 2014-03-24 10:00 | 2014-03-24 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
112 | build/technical design | 1.3.15.7 | 106FS | FS113;FS118;FS215 | 2014-03-14 08:00 | 2014-03-14 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 0.16667
113 | ABAP | 1.3.15.8 | 112FS | FS114 | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 0.16667
114 | UT | 1.3.15.9 | 113FS |  | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
115 | build/technical design | 1.3.15.10 | 109FS | FS116 | 2014-03-12 10:00 | 2014-03-13 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 1
116 | ABAP | 1.3.15.11 | 115FS | FS117 | 2014-03-13 10:00 | 2014-03-14 10:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 1
117 | UT | 1.3.15.12 | 116FS | FS121 | 2014-03-14 10:00 | 2014-03-17 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 3
118 | build/technical design | 1.3.15.13 | 112FS | FS119 | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 0.16667
119 | ABAP | 1.3.15.14 | 118FS | FS120 | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 0.16667
120 | UT | 1.3.15.15 | 119FS | FS124 | 2014-03-17 13:00 | 2014-03-17 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
121 | build/technical design | 1.3.15.16 | 117FS | FS122 | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 0.20833
122 | ABAP | 1.3.15.17 | 121FS | FS123 | 2014-03-17 15:00 | 2014-03-18 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 0.79167
123 | UT | 1.3.15.18 | 122FS | FS127 | 2014-03-18 10:00 | 2014-03-18 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
124 | build/technical design | 1.3.15.19 | 120FS | FS125;FS130 | 2014-03-18 08:00 | 2014-03-18 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
125 | ABAP | 1.3.15.20 | 124FS | FS126 | 2014-03-19 08:00 | 2014-03-19 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 0.375
126 | UT | 1.3.15.21 | 125FS |  | 2014-03-20 08:00 | 2014-03-20 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
127 | build/technical design | 1.3.15.22 | 123FS | FS128 | 2014-03-18 13:00 | 2014-03-18 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 0.16667
128 | ABAP | 1.3.15.23 | 127FS | FS129 | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 0.16667
129 | UT | 1.3.15.24 | 128FS | FS133 | 2014-03-19 13:00 | 2014-03-19 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
130 | build/technical design | 1.3.15.25 | 124FS | FS131 | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 0.16667
131 | ABAP | 1.3.15.26 | 130FS | FS132 | 2014-03-19 13:00 | 2014-03-19 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 0.16667
132 | UT | 1.3.15.27 | 131FS | FS149 | 2014-03-20 08:00 | 2014-03-20 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
133 | build/technical design | 1.3.15.28 | 129FS | FS134 | 2014-03-19 15:00 | 2014-03-20 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 0.79167
134 | ABAP | 1.3.15.29 | 133FS | FS135 | 2014-03-20 10:00 | 2014-03-20 15:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 0.20833
135 | UT | 1.3.15.30 | 134FS | FS99 | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
136 | import WSDL | 1.3.15.31 | 67FS | FS138 | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 0.20833
137 | spec proxy | 1.3.15.32 | 198FS | FS138;FS140;FS143 | 2014-03-14 08:00 | 2014-03-17 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 3.375
138 | ABAP proxy | 1.3.15.33 | 136FS;137FS | FS139;FS141 | 2014-03-18 08:00 | 2014-03-18 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 0.29167
139 | UT proxy | 1.3.15.34 | 138FS | FS142 | 2014-03-18 15:00 | 2014-03-20 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 1.7917
140 | spec wrapper core | 1.3.15.35 | 137FS | FS141 | 2014-03-18 08:00 | 2014-03-19 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 1.375
141 | ABAP wrapper core | 1.3.15.36 | 138FS;140FS | FS142;FS144 | 2014-03-20 08:00 | 2014-03-20 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 0.29167
142 | UT wrapper core | 1.3.15.37 | 139FS;141FS | FS145 | 2014-03-20 15:00 | 2014-03-24 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 3.7917
143 | spec proxy | 1.3.15.38 | 137FS | FS144;FS146 | 2014-03-18 08:00 | 2014-03-20 17:00 | 3d | Employee F[0.50 #1] | 903.36 | 0 | 0 | 0 | 903.36 | 2.375
144 | ABAP proxy | 1.3.15.39 | 141FS;143FS | FS145;FS147 | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 0.375
145 | UT proxy | 1.3.15.40 | 142FS;144FS | FS148 | 2014-03-24 10:00 | 2014-03-26 10:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2
146 | spec wrapper core | 1.3.15.41 | 143FS | FS147 | 2014-03-21 08:00 | 2014-03-26 17:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 5.375
147 | ABAP wrapper core | 1.3.15.42 | 144FS;146FS | FS148 | 2014-03-27 08:00 | 2014-03-28 12:00 | 1d 4h | ABAP | 1125 | 0 | 0 | 0 | 1125 | 1.1667
148 | UT wrapper core | 1.3.15.43 | 145FS;147FS |  | 2014-03-28 13:00 | 2014-04-03 12:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 5.9583
149 | content | 1.3.15.44 | 132FS | FS150 | 2014-03-20 10:00 | 2014-03-20 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
150 | UT | 1.3.15.45 | 149FS | FS151 | 2014-03-20 13:00 | 2014-03-20 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
151 | content | 1.3.15.46 | 150FS | FS152 | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
152 | UT | 1.3.15.47 | 151FS | FS153 | 2014-03-21 08:00 | 2014-03-21 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
153 | content | 1.3.15.48 | 152FS | FS154 | 2014-03-21 10:00 | 2014-03-21 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
154 | UT | 1.3.15.49 | 153FS | FS204 | 2014-03-21 13:00 | 2014-03-21 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 0.083333
155 | build/technical design | 1.3.15.50 | 67FS | FS156 | 2014-03-17 10:00 | 2014-03-20 10:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 3
156 | java | 1.3.15.51 | 155FS | FS157 | 2014-03-20 10:00 | 2014-03-27 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 7
157 | UT | 1.3.15.52 | 156FS |  | 2014-03-27 10:00 | 2014-04-04 10:00 | 6d | Employee F[0.50 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 8
180 | performance report | 1.3.16 |  |  | 2014-05-05 08:00 | 2014-05-14 17:00 | 8d |  |  | 0 |  |  | 4817.92 | 9.375
158 | build/technical design | 1.3.16.1 |  | FS159 | 2014-05-05 08:00 | 2014-05-06 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.375
159 | EAI | 1.3.16.2 | 158FS | FS160 | 2014-05-07 08:00 | 2014-05-09 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2.375
160 | UT | 1.3.16.3 | 159FS |  | 2014-05-12 08:00 | 2014-05-14 17:00 | 3d | Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 | 2.375
181 | preparation IT test strategy | 1.3.17 |  |  | 2014-02-04 08:00 | 2014-02-17 17:00 | 10d |  |  | 0 |  |  | 3011.2 | 13.375
161 | preparation core | 1.3.17.1 |  |  | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
162 | preparation migration | 1.3.17.2 |  |  | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
163 | preparation interfacing | 1.3.17.3 |  |  | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
164 | preparation reporting | 1.3.17.4 |  |  | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
165 | preparation interfacing | 1.3.17.5 |  |  | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
182 | service preparation | 1.3.18 |  |  | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d |  |  | 0 |  |  | 2890.8 | 0.375
166 | service manual draft | 1.3.18.1 |  |  | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
167 | SDM validation | 1.3.18.2 |  |  | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
168 | TCS validation | 1.3.18.3 |  |  | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
183 | build phase - validation | 1.3.19 |  |  | 2014-04-08 08:00 | 2014-04-09 17:00 | 2d |  |  | 0 |  |  | 2890.8 | 1.375
169 | program manager validation | 1.3.19.1 |  | FS172 | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
170 | SCM validation | 1.3.19.2 |  |  | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
171 | information security validation | 1.3.19.3 |  |  | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
172 | end of build | 1.3.19.4 | 169FS |  | 2014-04-09 17:00 | 2014-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
260 | implement | 1.4 |  |  | 2013-10-25 08:00 | 2014-05-19 17:00 | 147d |  |  | 0 |  |  | 120846.38 | 206.375
250 | certificates | 1.4.1 |  |  | 2014-04-02 10:00 | 2014-05-08 17:00 | 26d 6h |  |  | 0 |  |  | 17344.8 | 36.2917
185 | certificates on acceptance | 1.4.1.1 | 205FS |  | 2014-04-02 10:00 | 2014-04-15 10:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 13
186 | certificates on production | 1.4.1.2 |  |  | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 10.375
251 | integration testing release 1 | 1.4.2 |  |  | 2014-02-06 10:00 | 2014-03-20 17:00 | 30d 6h |  |  | 0 |  |  | 26287.92 | 42.2917
187 | backend | 1.4.2.1 | 78FS | FS188;FS189 | 2014-03-03 15:00 | 2014-03-05 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2
188 | backend and extract | 1.4.2.2 | 81FS;187FS | FS199 | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H;Employee K | 3131.68 | 0 | 0 | 0 | 3131.68 | 2
189 | performance testing monitoring backend | 1.4.2.3 | 187FS | FS199 | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2
190 | monitoring BI | 1.4.2.4 | 81FS | FS200 | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d | Employee K | 4818 | 0 | 0 | 0 | 4818 | 6.375
191 | weekly files | 1.4.2.5 | 25FS;26FS;27FS;28FS;48FS | FS196 | 2014-02-06 10:00 | 2014-02-11 17:00 | 3d 6h | Employee G | 2258.4 | 0 | 0 | 0 | 2258.4 | 5.2917
192 | monthly files | 1.4.2.6 | 35FS;48FS | FS197 | 2014-02-21 08:00 | 2014-02-25 12:00 | 2d 4h | Employee G | 1505.6 | 0 | 0 | 0 | 1505.6 | 4.1667
193 | duplicate documents | 1.4.2.7 | 48FS;194FS | FS198;FS195 | 2014-03-05 08:00 | 2014-03-06 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.375
194 | current saldo | 1.4.2.8 | 70FS | FS193 | 2014-03-03 08:00 | 2014-03-04 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.375
195 | account statement | 1.4.2.9 | 48FS;68FS;193FS | FS198 | 2014-03-07 08:00 | 2014-03-11 17:00 | 3d | Employee F | 1806.72 | 0 | 0 | 0 | 1806.72 | 4.375
196 | defect core weekly | 1.4.2.10 | 191FS | FS38;FS216 | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2.375
197 | defect core monthly | 1.4.2.11 | 192FS |  | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2.375
198 | defect interfacing | 1.4.2.12 | 193FS;195FS | FS137;FS102 | 2014-03-12 08:00 | 2014-03-13 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.375
199 | defect monitoring | 1.4.2.13 | 188FS;189FS | FS109 | 2014-03-07 15:00 | 2014-03-11 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 4
200 | defect BI reporting | 1.4.2.14 | 190FS |  | 2014-03-19 08:00 | 2014-03-20 17:00 | 2d | Employee K | 1927.2 | 0 | 0 | 0 | 1927.2 | 1.375
252 | integration testing release 2 | 1.4.3 |  |  | 2014-04-01 08:00 | 2014-04-23 17:00 | 17d |  |  | 0 |  |  | 15056 | 22.375
201 | feedback | 1.4.3.1 | 106FS | FS207 | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee F[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 13.375
202 | migration | 1.4.3.2 | 101FS | FS208 | 2014-04-08 08:00 | 2014-04-21 17:00 | 10d | Employee H[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 13.375
203 | list batch testing | 1.4.3.3 | 93FS;95FS | FS204 | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | Employee G[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 1.375
204 | core | 1.4.3.4 | 98FS;154FS;203FS | FS206 | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee G[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 13.375
205 | mail encryption | 1.4.3.5 | 105FS | FS185;FS209 | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee I | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
206 | defect core | 1.4.3.6 | 204FS | FS211;FS210 | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee G | 1204.48 | 0 | 0 | 0 | 1204.48 | 3.375
207 | defect interfacing | 1.4.3.7 | 201FS | FS221 | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 3.375
208 | defect migration | 1.4.3.8 | 202FS |  | 2014-04-22 08:00 | 2014-04-23 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 1.375
209 | defect mail encryption | 1.4.3.9 | 205FS | FS211 | 2014-04-02 10:00 | 2014-04-04 10:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2
253 | p2p testing | 1.4.4 |  |  | 2014-04-15 08:00 | 2014-04-22 17:00 | 6d |  |  | 0 |  |  | 6022.4 | 7.375
210 | p2p weekly files | 1.4.4.1 | 206FS |  | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
211 | p2p monthly files | 1.4.4.2 | 206FS;209FS |  | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 0.375
212 | p2p current saldo | 1.4.4.3 |  | FS213 | 2014-04-15 08:00 | 2014-04-15 17:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 0.375
213 | p2p duplicate documents | 1.4.4.4 | 212FS | FS214 | 2014-04-16 10:00 | 2014-04-17 10:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 1
214 | p2p account statement | 1.4.4.5 | 213FS | FS215 | 2014-04-17 13:00 | 2014-04-18 12:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 0.95833
215 | p2p feedback | 1.4.4.6 | 112FS;214FS |  | 2014-04-18 15:00 | 2014-04-21 15:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 3
254 | business acceptance testing release 1 | 1.4.5 |  |  | 2013-10-25 08:00 | 2014-04-04 12:00 | 115d 4h |  |  | 0 |  |  | 45815.04 | 161.1667
216 | part 1 - information lists | 1.4.5.1 | 196FS |  | 2014-02-17 08:00 | 2014-03-28 12:00 | 29d 4h | Employee M | 18771.44 | 0 | 0 | 0 | 18771.44 | 39.1667
217 | part 2 - interface | 1.4.5.2 |  |  | 2013-10-25 08:00 | 2013-10-29 17:00 | 3d | Employee N | 1908.96 | 0 | 0 | 0 | 1908.96 | 4.375
218 | part 3 - reporting | 1.4.5.3 |  |  | 2014-02-10 08:00 | 2014-04-04 12:00 | 39d 4h | Employee P | 25134.64 | 0 | 0 | 0 | 25134.64 | 53.1667
255 | business acceptance testing release 2 | 1.4.6 |  |  | 2014-04-21 08:00 | 2014-04-22 17:00 | 2d |  |  | 0 |  |  | 2545.28 | 1.375
219 | test definition | 1.4.6.1 |  | FS221 | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 0.375
220 | test data | 1.4.6.2 |  | FS221 | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 0.375
221 | test execution | 1.4.6.3 | 207FS;219FS;220FS |  | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee N;Employee O | 1272.64 | 0 | 0 | 0 | 1272.64 | 0.375
256 | service preparation | 1.4.7 |  |  | 2014-03-24 08:00 | 2014-04-23 17:00 | 23d |  |  | 0 |  |  | 3208.46 | 30.375
227 | SLA review | 1.4.7.1 |  |  | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 0.083333
228 | service budget agreement | 1.4.7.2 |  |  | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 0.083333
229 | production handbook | 1.4.7.3 |  |  | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
230 | service manual | 1.4.7.4 |  |  | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 0.083333
231 | SCM validation | 1.4.7.5 |  |  | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 0.083333
232 | CIO validation | 1.4.7.6 |  |  | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 0.375
257 | go-no go meeting | 1.4.8 |  |  | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d |  |  | 0 |  |  | 1522.16 | 0.375
233 | formal validation | 1.4.8.1 |  |  | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 | 0.375
258 | deploy on production | 1.4.9 |  |  | 2013-10-25 08:00 | 2014-05-16 17:00 | 146d |  |  | 0 |  |  | 1522.16 | 203.375
234 | go live | 1.4.9.1 |  |  | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
235 | PIN testing IT | 1.4.9.2 |  |  | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
236 | PIN testing business | 1.4.9.3 |  |  | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 0.375
259 | validation | 1.4.10 |  |  | 2014-05-16 17:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1522.16 | 3
237 | steerco validation | 1.4.10.1 |  |  | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 | 0.375
238 | end of implement | 1.4.10.2 |  | FS239 | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
265 | close | 1.5 |  |  | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 9731.8 | 1.1667
261 | hand-over preparation | 1.5.1 |  |  | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 6841 | 1.1667
239 | project charter as built | 1.5.1.1 | 238FS |  | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h | Employee A;Employee B | 2283.24 | 0 | 0 | 0 | 2283.24 | 1.1667
240 | blueprint as built | 1.5.1.2 |  |  | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee J;Employee M;Employee N | 2751.04 | 0 | 0 | 0 | 2751.04 | 0.375
241 | technical design as built | 1.5.1.3 |  |  | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee F;Employee G;Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 | 0.375
262 | hand-over | 1.5.2 |  |  | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1927.2 | 0.375
242 | service manual | 1.5.2.1 |  |  | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 | 0.16667
243 | CMDB check | 1.5.2.2 |  |  | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee C | 963.6 | 0 | 0 | 0 | 963.6 | 0.375
244 | SCM validation | 1.5.2.3 |  |  | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 | 0.16667
263 | project evaluation | 1.5.3 |  |  | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h |  |  | 0 |  |  | 722.7 | 0.083333
245 | customer satisfaction survey | 1.5.3.1 |  |  | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 0.083333
246 | project team briefing | 1.5.3.2 |  |  | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 0.083333
247 | suppliers evaluation | 1.5.3.3 |  |  | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 0.083333
264 | close phase | 1.5.4 |  |  | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 240.9 | 0.375
248 | program manager validation | 1.5.4.1 |  |  | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 0.083333
249 | end of project | 1.5.4.2 |  |  | 2014-05-19 17:00 | 2014-05-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 69.82 | 1;2;7;19;232;233;236;237;239;240; | 18711.76
2 | Employee B | Renewable | 1 | 0 | 120.45 | 2;3;4;5;6;14;18;166;167;168;169;170;171;227;228;230;231;233;235;237;239;242;244;245;246;247;248; | 49866.3
3 | Employee C | Renewable | 1 | 0 | 120.45 | 4;227;228;230;243; | 1806.75
4 | Employee D | Renewable | 1 | 0 | 120.45 | 5;93;95;185;186;229; | 21440.1
5 | Employee E | Renewable | 1 | 0 | 120.45 | 13; | 24090
6 | Employee F | Renewable | 1 | 0 | 75.28 | 12;16;39;41;42;44;68[0.50 Employee F];70;71;73;74;76;77;137[0.50 Employee F];139[0.50 Employee F];140[0.50 Employee F];142[0.50 Employee F];143[0.50 Employee F];145[0.50 Employee F];146[0.50 Employee F];148[0.50 Employee F];157[0.50 Employee F];163;165;193;194;195;198;201[0.50 Employee F];207;212;213;214;215;241; | 50287.04
7 | Employee G | Renewable | 1 | 0 | 75.28 | 10;16;23[0.60 Employee G];25;26;28;31;33;35[0.40 Employee G];37;89;91;92;94;96;98;106;108;112;114;118;120;124;126;127;129;130;132;149;150;151;152;153;154;161;191;192;196;197;203[0.50 Employee G];204[0.50 Employee G];206;210;211;241; | 50497.824
8 | Employee H | Renewable | 1 | 0 | 75.28 | 11;17;27;30;78;80;99;101;109;111;115;117;121;123;133;135;158;160;162;164;187;188;189;199;202[0.50 Employee H];208;241; | 51039.84
9 | Employee I | Renewable | 1 | 0 | 75.28 | 12;47[0.07 Employee I];60;62;63;65;67;102;155;205;209; | 30863.2944
10 | Employee J | Renewable | 1 | 0 | 114.98 | 240; | 919.84
11 | ABAP | Renewable | 1 | 0 | 93.75 | 24;34[0.80 ABAP];40;43;69;72;75;79;80;90;97;100;107;110;113;116;119;122;125;128;131;134;138;141;144;147; | 38250
12 | Employee K | Renewable | 1 | 0 | 120.45 | 81;188;190;200; | 26980.8
13 | Java | Renewable | 1 | 0 | 93.75 | 38;45;61;64;102;103;104;105;136;156; | 18562.5
14 | EAI | Renewable | 1 | 0 | 75.28 | 46;48;49;50;51;52;53;54;55;56;57;58;59;159;212;213;214;215; | 17766.08
15 | Employee L | Renewable | 1 | 0 | 75.28 | 68[0.50 Employee L];70; | 4215.68
16 | Employee M | Renewable | 1 | 0 | 79.54 | 29;36;216;240; | 21953.04
17 | Employee N | Renewable | 1 | 0 | 79.54 | 66;217;219;220;221;240; | 5090.56
18 | Employee O | Renewable | 1 | 0 | 79.54 | 221; | 636.32
19 | Employee P | Renewable | 1 | 0 | 79.54 | 218; | 25134.64

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Debt Collection System | 1188h |  |  |  |  | 99 | 100 | 101
9 | define | 320h |  |  |  |  | 99 | 100 | 101
1 | kick-off meeting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
266 | project charter set | 192h |  |  |  |  | 99 | 100 | 101
2 | project charter (scope definition) | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | project security risks | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
267 | project charter - communication and validation | 144h |  |  |  |  | 99 | 100 | 101
4 | inform IT governance | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | send info | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | send project charter for validation + delivery board validation | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | business validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | end of define | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | design | 448h |  |  |  |  | 99 | 100 | 101
15 | blueprint set | 352h |  |  |  |  | 99 | 100 | 101
10 | functional analysis List/file creation | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | functional analysis Monitoring | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | functional analysis Interfacing | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | architecture analysis | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | budget &amp; planning for development + master test chapter | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | design phase - validations | 120h |  |  |  |  | 99 | 100 | 101
16 | presentation to Business part 1 | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | presentation to Business part 2 | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | send to delivery board + IT governance validation | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | business validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | end of design | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | build | 786h |  |  |  |  | 99 | 100 | 101
32 | weekly file | 386h |  |  |  |  | 99 | 100 | 101
23 | build/technical design | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | ABAP | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | UT program in general | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | UT submission file | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | UT clearing file | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | UT other treatment file | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | business UT submission | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | UT sending via e-mail | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | monthly file | 282h |  |  |  |  | 99 | 100 | 101
33 | build/technical design | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | ABAP | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | UT | 52h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | business UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | UT sending via e-mail | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | authorization check | 332h |  |  |  |  | 99 | 100 | 101
38 | IRIS-SC | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | ABAP | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | ABAP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | import WSDL | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | ESB (pass BP to basic) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | send DMS file via e-mail | 186h |  |  |  |  | 99 | 100 | 101
47 | build/technical design | 114h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | import WSDL | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | EAI | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | UT | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | EAI | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | design | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | build | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | queue handling | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | UT | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | deployment | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | duplicates | 244h |  |  |  |  | 99 | 100 | 101
60 | build/technical design | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | java | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | UT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | current saldo | 64h |  |  |  |  | 99 | 100 | 101
63 | build/technical design | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | java | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | UT | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | business UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | BRM | 48h |  |  |  |  | 99 | 100 | 101
67 | BRM | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | account statement | 366h |  |  |  |  | 99 | 100 | 101
68 | build/technical design | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | ABAP | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | UT | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | spec proxy | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | ABAP proxy | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | UT proxy | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | spec wrapper core | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | ABAP wrapper core | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | UT wrapper core | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | email functionality | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
173 | monitoring and reporting | 206h |  |  |  |  | 99 | 100 | 101
78 | build/technical design | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | ABAP | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | UT | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | BI reports | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
174 | weekly file | 62h |  |  |  |  | 99 | 100 | 101
89 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | ABAP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | setup autosys | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | monthly file | 14h |  |  |  |  | 99 | 100 | 101
94 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | setup autosys | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | list | 22h |  |  |  |  | 99 | 100 | 101
96 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
177 | migration program | 96h |  |  |  |  | 99 | 100 | 101
99 | build/technical design | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | ABAP | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | UT | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
178 | send DMS file via e-mail | 78h |  |  |  |  | 99 | 100 | 101
102 | WSDL update | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | get cert / encrypt | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | error handling | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | UT java team | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
179 | feedback | 140h |  |  |  |  | 99 | 100 | 101
106 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | ABAP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | ABAP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | build/technical design | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | ABAP | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | UT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | build/technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | ABAP | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | import WSDL | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | spec proxy | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | ABAP proxy | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | UT proxy | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | spec wrapper core | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | ABAP wrapper core | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | UT wrapper core | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | spec proxy | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | ABAP proxy | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | UT proxy | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | spec wrapper core | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | ABAP wrapper core | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | UT wrapper core | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | content | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | content | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | content | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | UT | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | build/technical design | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | java | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | UT | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
180 | performance report | 64h |  |  |  |  | 99 | 100 | 101
158 | build/technical design | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | EAI | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | UT | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
181 | preparation IT test strategy | 80h |  |  |  |  | 99 | 100 | 101
161 | preparation core | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | preparation migration | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | preparation interfacing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | preparation reporting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | preparation interfacing | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
182 | service preparation | 8h |  |  |  |  | 99 | 100 | 101
166 | service manual draft | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | SDM validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
168 | TCS validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | build phase - validation | 16h |  |  |  |  | 99 | 100 | 101
169 | program manager validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | SCM validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | information security validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
172 | end of build | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
260 | implement | 1176h |  |  |  |  | 99 | 100 | 101
250 | certificates | 214h |  |  |  |  | 99 | 100 | 101
185 | certificates on acceptance | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
186 | certificates on production | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
251 | integration testing release 1 | 246h |  |  |  |  | 99 | 100 | 101
187 | backend | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
188 | backend and extract | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
189 | performance testing monitoring backend | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
190 | monitoring BI | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
191 | weekly files | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | monthly files | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
193 | duplicate documents | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
194 | current saldo | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | account statement | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
196 | defect core weekly | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
197 | defect core monthly | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
198 | defect interfacing | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
199 | defect monitoring | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
200 | defect BI reporting | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
252 | integration testing release 2 | 136h |  |  |  |  | 99 | 100 | 101
201 | feedback | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
202 | migration | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
203 | list batch testing | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
204 | core | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
205 | mail encryption | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
206 | defect core | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
207 | defect interfacing | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
208 | defect migration | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
209 | defect mail encryption | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
253 | p2p testing | 48h |  |  |  |  | 99 | 100 | 101
210 | p2p weekly files | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
211 | p2p monthly files | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
212 | p2p current saldo | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
213 | p2p duplicate documents | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
214 | p2p account statement | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
215 | p2p feedback | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
254 | business acceptance testing release 1 | 924h |  |  |  |  | 99 | 100 | 101
216 | part 1 - information lists | 236h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
217 | part 2 - interface | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | part 3 - reporting | 316h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
255 | business acceptance testing release 2 | 16h |  |  |  |  | 99 | 100 | 101
219 | test definition | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
220 | test data | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
221 | test execution | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
256 | service preparation | 184h |  |  |  |  | 99 | 100 | 101
227 | SLA review | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
228 | service budget agreement | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
229 | production handbook | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
230 | service manual | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
231 | SCM validation | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
232 | CIO validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
257 | go-no go meeting | 8h |  |  |  |  | 99 | 100 | 101
233 | formal validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
258 | deploy on production | 1168h |  |  |  |  | 99 | 100 | 101
234 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
235 | PIN testing IT | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
236 | PIN testing business | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
259 | validation | 8h |  |  |  |  | 99 | 100 | 101
237 | steerco validation | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
238 | end of implement | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
265 | close | 12h |  |  |  |  | 99 | 100 | 101
261 | hand-over preparation | 12h |  |  |  |  | 99 | 100 | 101
239 | project charter as built | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
240 | blueprint as built | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
241 | technical design as built | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
262 | hand-over | 8h |  |  |  |  | 99 | 100 | 101
242 | service manual | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
243 | CMDB check | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
244 | SCM validation | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
263 | project evaluation | 2h |  |  |  |  | 99 | 100 | 101
245 | customer satisfaction survey | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
246 | project team briefing | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
247 | suppliers evaluation | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
264 | close phase | 8h |  |  |  |  | 99 | 100 | 101
248 | program manager validation | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
249 | end of project | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-03-20 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Debt Collection System | 2013-10-24 08:00 | 2014-05-20 12:00 | 148d 4h |  |  | 0 |  |  | 458112.3684 |  | 110d | [5 empty] | 300587.0561 |  | 56.46% |  | 258667.0548 | 344534.1284
9 | define | 2013-10-24 08:00 | 2013-12-18 17:00 | 40d |  |  | 0 |  |  | 41864.71 |  | 39d 7h | [5 empty] | 41864.71 |  | 100% |  | 41864.71 | 41864.71
1 | kick-off meeting | 2013-10-24 08:00 | 2013-10-24 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-10-24 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
266 | project charter set | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  |  | 0 |  |  | 37495.44 |  | 24d | [5 empty] | 37495.44 |  | 100% |  | 37495.44 | 37495.44
2 | project charter (scope definition) | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d | Employee A;Employee B | 36531.84 | 0 | 0 | 0 | 36531.84 | 2013-11-04 08:00 | 24d | 36531.84 | 0 | 0 | 0 | 0 | 36531.84 | 0 | 100% | Finished | 36531.84 | 36531.84 | 100 | 100 | 100 | 100 | 100 | 100
3 | project security risks | 2013-11-13 08:00 | 2013-11-13 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2013-11-13 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
267 | project charter - communication and validation | 2013-11-25 08:00 | 2013-12-18 17:00 | 18d |  |  | 0 |  |  | 3810.71 |  | 17d 7h | [5 empty] | 3810.71 |  | 100% |  | 3810.71 | 3810.71
4 | inform IT governance | 2013-11-25 08:00 | 2013-11-25 09:00 | 1h | Employee B;Employee C | 240.9 | 0 | 0 | 0 | 240.9 | 2013-11-25 08:00 | 1h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
5 | send info | 2013-11-28 08:00 | 2013-11-28 17:00 | 1d | Employee B;Employee D | 1927.2 | 0 | 0 | 0 | 1927.2 | 2013-11-28 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 100 | 100 | 100 | 100 | 100
6 | send project charter for validation + delivery board validation | 2013-12-13 08:00 | 2013-12-16 09:00 | 1d 1h | Employee B | 1084.05 | 0 | 0 | 0 | 1084.05 | 2013-12-13 08:00 | 1d 1h | 1084.05 | 0 | 0 | 0 | 0 | 1084.05 | 0 | 100% | Finished | 1084.05 | 1084.05 | 100 | 100 | 100 | 100 | 100 | 100
7 | business validation | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-12-17 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
8 | end of define | 2013-12-18 17:00 | 2013-12-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
22 | design | 2013-11-25 08:00 | 2014-02-10 17:00 | 56d |  |  | 0 |  |  | 107215.84 |  | 84d | [5 empty] | 64208.83 |  | 64.56% |  | 69222.7776 | 107215.84
15 | blueprint set | 2013-11-25 08:00 | 2014-01-23 17:00 | 44d |  |  | 0 |  |  | 103826.72 |  | 84d | [5 empty] | 63115.2 |  | 65.78% |  | 68294.56 | 103826.72
10 | functional analysis List/file creation | 2013-12-02 08:00 | 2014-01-03 17:00 | 25d | Employee G | 15056 | 0 | 0 | 0 | 15056 | 2013-12-02 08:00 | 13d | 7829.12 | 7829.12 | 13d | 0 | 0 | 7829.12 | 7829.12 | 50% | Started | 7528 | 15056 | 100 | 52 | 50 | 100 | 52 | 50
11 | functional analysis Monitoring | 2013-11-25 08:00 | 2014-01-08 17:00 | 33d | Employee H | 19873.92 | 0 | 0 | 0 | 19873.92 | 2013-11-25 08:00 | 17d | 10238.08 | 10238.08 | 17d | 0 | 0 | 10238.08 | 10238.08 | 50% | Started | 9936.96 | 19873.92 | 100 | 51.5152 | 50 | 100 | 51.5152 | 50
12 | functional analysis Interfacing | 2013-11-25 08:00 | 2014-01-03 17:00 | 30d | Employee F;Employee I | 36134.4 | 0 | 0 | 0 | 36134.4 | 2013-11-25 08:00 | 15d | 18067.2 | 18067.2 | 15d | 0 | 0 | 18067.2 | 18067.2 | 50% | Started | 18067.2 | 36134.4 | 100 | 50 | 50 | 100 | 50 | 50
13 | architecture analysis | 2013-11-25 08:00 | 2013-12-27 17:00 | 25d | Employee E | 24090 | 0 | 0 | 0 | 24090 | 2013-11-25 08:00 | 25d | 24090 | 0 | 0 | 0 | 0 | 24090 | 0 | 100% | Finished | 24090 | 24090 | 100 | 100 | 100 | 100 | 100 | 100
14 | budget &amp; planning for development + master test chapter | 2014-01-13 08:00 | 2014-01-23 17:00 | 9d | Employee B | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-01-30 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 100% | Finished | 8672.4 | 8672.4 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
21 | design phase - validations | 2014-01-21 08:00 | 2014-02-10 17:00 | 15d |  |  | 0 |  |  | 3389.12 |  | 43d | [5 empty] | 1093.63 |  | 27.39% |  | 928.2176 | 3389.12
16 | presentation to Business part 1 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G;Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-21 08:00 | 4h | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
17 | presentation to Business part 2 | 2014-01-31 08:00 | 2014-01-31 12:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-01-31 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
18 | send to delivery board + IT governance validation | 2014-02-07 08:00 | 2014-02-10 17:00 | 2d | Employee B | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-02-07 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 19.272 | 1927.2 | 100 | 6.25 | 1 | 100 | 6.25 | 1
19 | business validation | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-02-07 08:00 | 1h | 69.82 | 6912.18 | 12d 3h | 0 | 0 | 69.82 | 6912.18 | 1% | Started | 5.5856 | 558.56 | 100 | 12.5 | 1 | 100 | 12.5 | 1
20 | end of design | 2014-02-10 17:00 | 2014-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | build | 2013-12-27 15:00 | 2014-05-14 17:00 | 98d 2h |  |  | 0 |  |  | 178453.6384 |  | 44d | [5 empty] | 105628.4661 |  | 58.33% |  | 104084.9387 | 132009.5784
32 | weekly file | 2014-01-02 15:00 | 2014-03-11 17:00 | 48d 2h |  |  | 0 |  |  | 19499.28 |  | 36d | [5 empty] | 18084.892 |  | 96.94% |  | 18903.0624 | 19499.28
23 | build/technical design | 2014-01-02 15:00 | 2014-01-09 15:00 | 5d | Employee G[0.60 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-01-30 08:00 | 5d 4h | 1987.392 | 0 | 0 | 0 | 0 | 1987.392 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 110 | 100 | 100 | 110 | 100
24 | ABAP | 2014-01-09 15:00 | 2014-01-22 15:00 | 9d | ABAP | 6750 | 0 | 0 | 0 | 6750 | 2014-02-06 08:00 | 9d | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 100% | Finished | 6750 | 6750 | 100 | 100 | 100 | 100 | 100 | 100
25 | UT program in general | 2014-01-23 15:00 | 2014-01-27 10:00 | 1d 4h | Employee G | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
26 | UT submission file | 2014-01-31 15:00 | 2014-02-06 10:00 | 3d 4h | Employee G | 2107.84 | 0 | 0 | 0 | 2107.84 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2107.84 | 2107.84 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | UT clearing file | 2014-01-27 10:00 | 2014-01-31 10:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
28 | UT other treatment file | 2014-01-31 10:00 | 2014-02-06 10:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-26 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
29 | business UT submission | 2014-03-05 13:00 | 2014-03-10 12:00 | 3d | Employee M | 1908.96 | 0 | 0 | 0 | 1908.96 | 2014-02-25 08:00 | 3h | 238.62 | 0 | 0 | 0 | 0 | 238.62 | 0 | 100% | Finished | 1908.96 | 1908.96 | 100 | 12.5 | 100 | 100 | 12.5 | 100
30 | UT sending via e-mail | 2014-03-11 08:00 | 2014-03-11 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
31 | build/technical design | 2014-01-22 15:00 | 2014-01-23 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
82 | monthly file | 2013-12-27 15:00 | 2014-02-14 17:00 | 35d 2h |  |  | 0 |  |  | 6713.344 |  | 40d | [5 empty] | 5750.052 |  | 91.12% |  | 6117.1264 | 6713.344
33 | build/technical design | 2013-12-27 15:00 | 2014-01-02 15:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-24 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
34 | ABAP | 2014-01-30 08:00 | 2014-02-03 12:00 | 2d 4h | ABAP[0.80 #1] | 1500 | 0 | 0 | 0 | 1500 | 2014-01-30 08:00 | 2d 4h | 1500 | 0 | 0 | 2.2352e-05 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
35 | UT | 2014-02-03 13:00 | 2014-02-11 17:00 | 6d 4h | Employee G[0.40 #1] | 1565.824 | 0 | 0 | 0 | 1565.824 | 2014-02-03 08:00 | 7d | 1686.272 | 0 | 0 | 2.5127e-05 | 0 | 1686.272 | 0 | 100% | Finished | 1565.824 | 1565.824 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
36 | business UT | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee M | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-18 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
37 | UT sending via e-mail | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
83 | authorization check | 2014-01-24 08:00 | 2014-03-24 12:00 | 41d 4h |  |  | 0 |  |  | 15386.2 |  | 40d | [5 empty] | 14859.24 |  | 96.12% |  | 14789.9824 | 14482.84
38 | IRIS-SC | 2014-03-13 08:00 | 2014-03-18 17:00 | 4d | Java | 3000 | 0 | 0 | 0 | 3000 | 2014-03-13 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
39 | build/technical design | 2014-01-24 08:00 | 2014-01-24 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-24 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
40 | ABAP | 2014-01-27 08:00 | 2014-02-10 17:00 | 11d | ABAP | 8250 | 0 | 0 | 0 | 8250 | 2014-01-27 08:00 | 11d | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 100% | Finished | 8250 | 8250 | 100 | 100 | 100 | 100 | 100 | 100
41 | UT | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
42 | build/technical design | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
43 | ABAP | 2014-03-19 13:00 | 2014-03-20 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
44 | UT | 2014-03-20 13:00 | 2014-03-21 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
45 | import WSDL | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-02-13 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
46 | ESB (pass BP to basic) | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 0 | 100 | 12.5 | 1 | 100 | 12.5 | 1
84 | send DMS file via e-mail | 2014-02-05 15:00 | 2014-03-10 17:00 | 23d 2h |  |  | 0 |  |  | 13548.8944 |  | 24d | [5 empty] | 5299.712 |  | 36.53% |  | 4948.9072 | 13548.8944
47 | build/technical design | 2014-02-17 08:00 | 2014-03-07 10:00 | 14d 2h | Employee I[0.07 #1] | 600.7344 | 0 | 0 | 0 | 600.7344 | 2014-02-17 08:00 | 15d | 632.352 | 0 | 0 | 2.6922e-06 | 0 | 632.352 | 0 | 100% | Finished | 600.7344 | 600.7344 | 100 | 105.2632 | 100 | 100 | 105.2632 | 100
48 | import WSDL | 2014-02-05 15:00 | 2014-02-06 10:00 | 4h | EAI | 301.12 | 0 | 0 | 0 | 301.12 | 2014-02-17 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
49 | build/technical design | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
50 | EAI | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | UT | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
52 | build/technical design | 2014-02-18 08:00 | 2014-02-18 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
53 | EAI | 2014-02-19 08:00 | 2014-02-19 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
54 | UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-20 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
55 | design | 2014-02-19 08:00 | 2014-02-20 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | build | 2014-02-21 08:00 | 2014-02-25 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-21 08:00 | 4h | 301.12 | 1204.48 | 2d | 0 | 0 | 301.12 | 1204.48 | 20% | Started | 361.344 | 1806.72 | 100 | 16.6667 | 20 | 100 | 16.6667 | 20
57 | queue handling | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 18.0672 | 1806.72 | 100 | 4.1667 | 1 | 100 | 4.1667 | 1
58 | UT | 2014-03-03 08:00 | 2014-03-06 17:00 | 4d | EAI | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-03-03 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 24.0896 | 2408.96 | 100 | 3.125 | 1 | 100 | 3.125 | 1
59 | deployment | 2014-03-07 08:00 | 2014-03-10 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-07 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
85 | duplicates | 2014-02-12 13:00 | 2014-03-26 17:00 | 30d 4h |  |  | 0 |  |  | 5261.2 |  | 11d | [5 empty] | 5261.2 |  | 100% |  | 5261.2 | 2704.48
60 | build/technical design | 2014-02-12 13:00 | 2014-02-14 12:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-12 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
61 | java | 2014-03-19 08:00 | 2014-03-21 17:00 | 3d | Java | 2250 | 0 | 0 | 0 | 2250 | 2014-02-19 08:00 | 3d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 2250 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
62 | UT | 2014-03-24 08:00 | 2014-03-26 17:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-24 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 0 | 100 | 100 | 100 | 100 | 100 | 100
86 | current saldo | 2014-02-11 08:00 | 2014-02-20 17:00 | 8d |  |  | 0 |  |  | 3943.04 |  | 7d 4h | [5 empty] | 3386.26 |  | 100% |  | 3943.04 | 3943.04
63 | build/technical design | 2014-02-11 08:00 | 2014-02-12 12:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-11 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
64 | java | 2014-02-14 13:00 | 2014-02-18 12:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-02-17 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
65 | UT | 2014-02-18 13:00 | 2014-02-19 17:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
66 | business UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-20 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
88 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d |  |  | 0 |  |  | 3613.44 |  | 6d | [5 empty] | 3613.44 |  | 100% |  | 3613.44 | 3613.44
67 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d | Employee I | 3613.44 | 0 | 0 | 0 | 3613.44 | 2014-03-07 10:00 | 6d | 3613.44 | 0 | 0 | 0 | 0 | 3613.44 | 0 | 100% | Finished | 3613.44 | 3613.44 | 100 | 100 | 100 | 100 | 100 | 100
87 | account statement | 2014-01-24 15:00 | 2014-03-31 12:00 | 45d 6h |  |  | 0 |  |  | 15044.8 |  | 29d | [5 empty] | 11431.36 |  | 75.98% |  | 11431.36 | 11283.6
68 | build/technical design | 2014-01-24 15:00 | 2014-02-07 15:00 | 10d | Employee F[0.50 #1];Employee L[0.50 #1] | 6022.4 | 0 | 0 | 0 | 6022.4 | 2014-02-10 08:00 | 10d | 6022.4 | 0 | 0 | 0 | 0 | 6022.4 | 0 | 100% | Finished | 6022.4 | 6022.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | ABAP | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-02-20 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
70 | UT | 2014-02-13 08:00 | 2014-02-14 17:00 | 2d | Employee F;Employee L | 2408.96 | 0 | 0 | 0 | 2408.96 |  | 0 | 0 | 2408.96 | 2d | 0 | 0 | 0 | 2408.96 | 0% | Not Started | 0 | 2408.96 | 100 |  | 0 | 100 |  | 0
71 | spec proxy | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 0 | 100 | 100 | 100 | 100 | 100 | 100
72 | ABAP proxy | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
73 | UT proxy | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 602.24 | 100 |  | 0 | 100 |  | 0
74 | spec wrapper core | 2014-03-24 13:00 | 2014-03-26 12:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-20 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 0 | 100 | 100 | 100 | 100 | 100 | 100
75 | ABAP wrapper core | 2014-03-26 13:00 | 2014-03-27 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 0 | 100 | 100 | 100 | 100 | 100 | 100
76 | UT wrapper core | 2014-03-27 13:00 | 2014-03-28 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | email functionality | 2014-03-28 13:00 | 2014-03-31 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 0 | 100 | 100 | 100 | 100 | 100 | 100
173 | monitoring and reporting | 2014-01-29 08:00 | 2014-03-05 15:00 | 25d 6h |  |  | 0 |  |  | 31228.56 |  | 37d | [5 empty] | 25446.96 |  | 78.31% |  | 24454.4519 | 31228.56
78 | build/technical design | 2014-01-29 08:00 | 2014-02-03 17:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-29 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
79 | ABAP | 2014-02-06 08:00 | 2014-02-12 17:00 | 5d | ABAP | 3750 | 0 | 0 | 0 | 3750 | 2014-02-06 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
80 | UT | 2014-02-13 08:00 | 2014-02-19 17:00 | 5d | Employee H;ABAP | 6761.2 | 0 | 0 | 0 | 6761.2 | 2014-02-13 08:00 | 5d | 6761.2 | 0 | 0 | 0 | 0 | 6761.2 | 0 | 100% | Finished | 6761.2 | 6761.2 | 100 | 100 | 100 | 100 | 100 | 100
81 | BI reports | 2014-02-06 15:00 | 2014-03-05 15:00 | 19d | Employee K | 18308.4 | 0 | 0 | 0 | 18308.4 | 2014-02-06 15:00 | 13d | 12526.8 | 7347.45 | 7d 5h | -1.819e-12 | 0 | 12526.8 | 7347.45 | 63% | Started | 11534.2919 | 18308.4 | 100 | 68.4211 | 63 | 100 | 68.4211 | 63
174 | weekly file | 2014-03-21 08:00 | 2014-04-01 15:00 | 7d 6h |  |  | 0 |  |  | 3219.2 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
89 | build/technical design | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | ABAP | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | UT | 2014-03-25 08:00 | 2014-03-25 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | build/technical design | 2014-03-28 15:00 | 2014-03-31 10:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 |  | 0 | 0 | 301.12 | 4h | 0 | 0 | 0 | 301.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | setup autosys | 2014-03-31 15:00 | 2014-04-01 15:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | monthly file | 2014-03-31 10:00 | 2014-04-01 17:00 | 1d 6h |  |  | 0 |  |  | 1505.62 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
94 | build/technical design | 2014-03-31 10:00 | 2014-03-31 15:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 |  | 0 | 0 | 301.12 | 4h | 0 | 0 | 0 | 301.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | setup autosys | 2014-03-31 15:00 | 2014-04-01 17:00 | 1d 2h | Employee D | 1204.5 | 0 | 0 | 0 | 1204.5 |  | 0 | 0 | 1204.5 | 1d 2h | 0 | 0 | 0 | 1204.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | list | 2014-03-26 08:00 | 2014-03-28 15:00 | 2d 6h |  |  | 0 |  |  | 1579.48 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
96 | build/technical design | 2014-03-26 08:00 | 2014-03-26 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | ABAP | 2014-03-27 08:00 | 2014-03-27 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 4h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | UT | 2014-03-27 15:00 | 2014-03-28 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | migration program | 2014-03-21 08:00 | 2014-04-07 17:00 | 12d |  |  | 0 |  |  | 7522.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
99 | build/technical design | 2014-03-21 08:00 | 2014-04-01 17:00 | 8d | Employee H | 4817.92 | 0 | 0 | 0 | 4817.92 |  | 0 | 0 | 4817.92 | 8d | 0 | 0 | 0 | 4817.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | ABAP | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | UT | 2014-04-04 08:00 | 2014-04-07 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | send DMS file via e-mail | 2014-03-14 08:00 | 2014-03-27 15:00 | 9d 6h |  |  | 0 |  |  | 7463.06 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3900.56
102 | WSDL update | 2014-03-14 08:00 | 2014-03-14 10:00 | 2h | Java;Employee I | 338.06 | 0 | 0 | 0 | 338.06 |  | 0 | 0 | 338.06 | 2h | 0 | 0 | 0 | 338.06 | 0% | Not Started | 0 | 338.06 | 100 |  | 0 | 100 |  | 0
103 | get cert / encrypt | 2014-03-14 10:00 | 2014-03-21 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 |  | 0 | 0 | 3750 | 5d | 0 | 0 | 0 | 3750 | 0% | Not Started | 0 | 3562.5 | 100 |  | 0 | 100 |  | 0
104 | error handling | 2014-03-21 10:00 | 2014-03-25 10:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | UT java team | 2014-03-25 10:00 | 2014-03-27 15:00 | 2d 4h | Java | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 2d 4h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | feedback | 2014-03-11 15:00 | 2014-04-04 10:00 | 17d 4h |  |  | 0 |  |  | 29314.4 |  | 11d | [5 empty] | 12118.95 |  | 36.13% |  | 10592.2564 | 18080.34
106 | build/technical design | 2014-03-13 08:00 | 2014-03-13 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
107 | ABAP | 2014-03-14 08:00 | 2014-03-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
108 | UT | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
109 | build/technical design | 2014-03-11 15:00 | 2014-03-12 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-12 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
110 | ABAP | 2014-03-21 15:00 | 2014-03-24 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-13 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 0 | 100 | 25 | 1 | 100 | 25 | 1
111 | UT | 2014-03-24 10:00 | 2014-03-24 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-13 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 1.5056 | 0 | 100 | 50 | 1 | 100 | 50 | 1
112 | build/technical design | 2014-03-14 08:00 | 2014-03-14 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
113 | ABAP | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-14 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
114 | UT | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 1.5056 | 150.56 | 100 | 50 | 1 | 100 | 50 | 1
115 | build/technical design | 2014-03-12 10:00 | 2014-03-13 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
116 | ABAP | 2014-03-13 10:00 | 2014-03-14 10:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 7.5 | 750 | 100 | 12.5 | 1 | 100 | 12.5 | 1
117 | UT | 2014-03-14 10:00 | 2014-03-17 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
118 | build/technical design | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
119 | ABAP | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
120 | UT | 2014-03-17 13:00 | 2014-03-17 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 1.5056 | 150.56 | 100 | 50 | 1 | 100 | 50 | 1
121 | build/technical design | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-18 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
122 | ABAP | 2014-03-17 15:00 | 2014-03-18 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-18 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
123 | UT | 2014-03-18 10:00 | 2014-03-18 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-19 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 1.5056 | 150.56 | 100 | 50 | 1 | 100 | 50 | 1
124 | build/technical design | 2014-03-18 08:00 | 2014-03-18 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
125 | ABAP | 2014-03-19 08:00 | 2014-03-19 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-19 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 7.5 | 750 | 100 | 12.5 | 1 | 100 | 12.5 | 1
126 | UT | 2014-03-20 08:00 | 2014-03-20 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-20 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
127 | build/technical design | 2014-03-18 13:00 | 2014-03-18 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
128 | ABAP | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
129 | UT | 2014-03-19 13:00 | 2014-03-19 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 1.5056 | 150.56 | 100 | 50 | 1 | 100 | 50 | 1
130 | build/technical design | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
131 | ABAP | 2014-03-19 13:00 | 2014-03-19 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
132 | UT | 2014-03-20 08:00 | 2014-03-20 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 1.5056 | 150.56 | 100 | 50 | 1 | 100 | 50 | 1
133 | build/technical design | 2014-03-19 15:00 | 2014-03-20 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-20 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
134 | ABAP | 2014-03-20 10:00 | 2014-03-20 15:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 4h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 375 | 100 |  | 0 | 100 |  | 0
135 | UT | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 |  | 0 | 0 | 150.56 | 2h | 0 | 0 | 0 | 150.56 | 0% | Not Started | 0 | 150.56 | 100 |  | 0 | 100 |  | 0
136 | import WSDL | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
137 | spec proxy | 2014-03-14 08:00 | 2014-03-17 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 2d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 602.24 | 100 |  | 0 | 100 |  | 0
138 | ABAP proxy | 2014-03-18 08:00 | 2014-03-18 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 |  | 0 | 0 | 562.5 | 6h | 0 | 0 | 0 | 562.5 | 0% | Not Started | 0 | 562.5 | 100 |  | 0 | 100 |  | 0
139 | UT proxy | 2014-03-18 15:00 | 2014-03-20 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 |  | 0 | 0 | 451.68 | 1d 4h | 0 | 0 | 0 | 451.68 | 0% | Not Started | 0 | 451.68 | 100 |  | 0 | 100 |  | 0
140 | spec wrapper core | 2014-03-18 08:00 | 2014-03-19 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 2d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 602.24 | 100 |  | 0 | 100 |  | 0
141 | ABAP wrapper core | 2014-03-20 08:00 | 2014-03-20 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 |  | 0 | 0 | 562.5 | 6h | 0 | 0 | 0 | 562.5 | 0% | Not Started | 0 | 562.5 | 100 |  | 0 | 100 |  | 0
142 | UT wrapper core | 2014-03-20 15:00 | 2014-03-24 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 |  | 0 | 0 | 451.68 | 1d 4h | 0 | 0 | 0 | 451.68 | 0% | Not Started | 0 | 75.28 | 100 |  | 0 | 100 |  | 0
143 | spec proxy | 2014-03-18 08:00 | 2014-03-20 17:00 | 3d | Employee F[0.50 #1] | 903.36 | 0 | 0 | 0 | 903.36 |  | 0 | 0 | 903.36 | 3d | 0 | 0 | 0 | 903.36 | 0% | Not Started | 0 | 903.36 | 100 |  | 0 | 100 |  | 0
144 | ABAP proxy | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | UT proxy | 2014-03-24 10:00 | 2014-03-26 10:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 2d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | spec wrapper core | 2014-03-21 08:00 | 2014-03-26 17:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 4d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | ABAP wrapper core | 2014-03-27 08:00 | 2014-03-28 12:00 | 1d 4h | ABAP | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 4h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | UT wrapper core | 2014-03-28 13:00 | 2014-04-03 12:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 4d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | content | 2014-03-20 10:00 | 2014-03-20 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
150 | UT | 2014-03-20 13:00 | 2014-03-20 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 1.5056 | 150.56 | 100 | 50 | 1 | 100 | 50 | 1
151 | content | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
152 | UT | 2014-03-21 08:00 | 2014-03-21 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 |  | 0 | 0 | 150.56 | 2h | 0 | 0 | 0 | 150.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | content | 2014-03-21 10:00 | 2014-03-21 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 |  | 0 | 0 | 150.56 | 2h | 0 | 0 | 0 | 150.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | UT | 2014-03-21 13:00 | 2014-03-21 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 |  | 0 | 0 | 150.56 | 2h | 0 | 0 | 0 | 150.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | build/technical design | 2014-03-17 10:00 | 2014-03-20 10:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-17 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
156 | java | 2014-03-20 10:00 | 2014-03-27 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-03-20 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
157 | UT | 2014-03-27 10:00 | 2014-04-04 10:00 | 6d | Employee F[0.50 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 6d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | performance report | 2014-05-05 08:00 | 2014-05-14 17:00 | 8d |  |  | 0 |  |  | 4817.92 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
158 | build/technical design | 2014-05-05 08:00 | 2014-05-06 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | EAI | 2014-05-07 08:00 | 2014-05-09 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 3d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | UT | 2014-05-12 08:00 | 2014-05-14 17:00 | 3d | Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 3d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | preparation IT test strategy | 2014-02-04 08:00 | 2014-02-17 17:00 | 10d |  |  | 0 |  |  | 3011.2 |  | 33d | [5 empty] | 376.4 |  | 1% |  | 30.112 | 3011.2
161 | preparation core | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
162 | preparation migration | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
163 | preparation interfacing | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
164 | preparation reporting | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
165 | preparation interfacing | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
182 | service preparation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d |  |  | 0 |  |  | 2890.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
166 | service manual draft | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | SDM validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | TCS validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | build phase - validation | 2014-04-08 08:00 | 2014-04-09 17:00 | 2d |  |  | 0 |  |  | 2890.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
169 | program manager validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | SCM validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | information security validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | end of build | 2014-04-09 17:00 | 2014-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | implement | 2013-10-25 08:00 | 2014-05-19 17:00 | 147d |  |  | 0 |  |  | 120846.38 |  | 105d | [5 empty] | 88885.05 |  | 35.99% |  | 43494.6284 | 63444
250 | certificates | 2014-04-02 10:00 | 2014-05-08 17:00 | 26d 6h |  |  | 0 |  |  | 17344.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
185 | certificates on acceptance | 2014-04-02 10:00 | 2014-04-15 10:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 |  | 0 | 0 | 8672.4 | 9d | 0 | 0 | 0 | 8672.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | certificates on production | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 |  | 0 | 0 | 8672.4 | 9d | 0 | 0 | 0 | 8672.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | integration testing release 1 | 2014-02-06 10:00 | 2014-03-20 17:00 | 30d 6h |  |  | 0 |  |  | 26287.92 |  | 20d | [5 empty] | 12526.65 |  | 44% |  | 11567.272 | 26287.92
187 | backend | 2014-03-03 15:00 | 2014-03-05 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-04 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
188 | backend and extract | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H;Employee K | 3131.68 | 0 | 0 | 0 | 3131.68 | 2014-03-06 15:00 | 4h | 782.92 | 2348.76 | 1d 4h | -1.1369e-13 | 0 | 782.92 | 2348.76 | 25% | Started | 782.92 | 3131.68 | 100 | 25 | 25 | 100 | 25 | 25
189 | performance testing monitoring backend | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-06 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
190 | monitoring BI | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d | Employee K | 4818 | 0 | 0 | 0 | 4818 | 2014-03-12 08:00 | 3d | 2890.8 | 2890.8 | 3d | 0 | 0 | 2890.8 | 2890.8 | 50% | Started | 2409 | 4818 | 100 | 60 | 50 | 100 | 60 | 50
191 | weekly files | 2014-02-06 10:00 | 2014-02-11 17:00 | 3d 6h | Employee G | 2258.4 | 0 | 0 | 0 | 2258.4 | 2014-03-04 08:00 | 2d | 1204.48 | 1204.48 | 2d | 0 | 0 | 1204.48 | 1204.48 | 50% | Started | 1129.2 | 2258.4 | 100 | 53.3333 | 50 | 100 | 53.3333 | 50
192 | monthly files | 2014-02-21 08:00 | 2014-02-25 12:00 | 2d 4h | Employee G | 1505.6 | 0 | 0 | 0 | 1505.6 | 2014-02-21 08:00 | 2d | 1204.48 | 301.12 | 4h | 0 | 0 | 1204.48 | 301.12 | 80% | Started | 1204.48 | 1505.6 | 100 | 80 | 80 | 100 | 80 | 80
193 | duplicate documents | 2014-03-05 08:00 | 2014-03-06 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 1204.48 | 100 |  | 0 | 100 |  | 0
194 | current saldo | 2014-03-03 08:00 | 2014-03-04 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 1204.48 | 100 |  | 0 | 100 |  | 0
195 | account statement | 2014-03-07 08:00 | 2014-03-11 17:00 | 3d | Employee F | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 3d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 1806.72 | 100 |  | 0 | 100 |  | 0
196 | defect core weekly | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-10 08:00 | 2d 4h | 1505.6 | 526.96 | 7h | 0 | 0 | 1505.6 | 526.96 | 75% | Started | 1355.04 | 1806.72 | 100 | 83.3333 | 75 | 100 | 83.3333 | 75
197 | defect core monthly | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 2d 4h | 1505.6 | 526.96 | 7h | 0 | 0 | 1505.6 | 526.96 | 75% | Started | 1355.04 | 1806.72 | 100 | 83.3333 | 75 | 100 | 83.3333 | 75
198 | defect interfacing | 2014-03-12 08:00 | 2014-03-13 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 1204.48 | 100 |  | 0 | 100 |  | 0
199 | defect monitoring | 2014-03-07 15:00 | 2014-03-11 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-10 15:00 | 1d 4h | 903.36 | 301.12 | 4h | 0 | 0 | 903.36 | 301.12 | 75% | Started | 903.36 | 1204.48 | 100 | 75 | 75 | 100 | 75 | 75
200 | defect BI reporting | 2014-03-19 08:00 | 2014-03-20 17:00 | 2d | Employee K | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-03-19 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 19.272 | 1927.2 | 100 | 6.25 | 1 | 100 | 6.25 | 1
252 | integration testing release 2 | 2014-04-01 08:00 | 2014-04-23 17:00 | 17d |  |  | 0 |  |  | 15056 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
201 | feedback | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee F[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 |  | 0 | 0 | 3011.2 | 10d | 0 | 0 | 0 | 3011.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | migration | 2014-04-08 08:00 | 2014-04-21 17:00 | 10d | Employee H[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 |  | 0 | 0 | 3011.2 | 10d | 0 | 0 | 0 | 3011.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | list batch testing | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | Employee G[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 2d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | core | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee G[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 |  | 0 | 0 | 3011.2 | 10d | 0 | 0 | 0 | 3011.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | mail encryption | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee I | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | defect core | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee G | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | defect interfacing | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | defect migration | 2014-04-22 08:00 | 2014-04-23 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | defect mail encryption | 2014-04-02 10:00 | 2014-04-04 10:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | p2p testing | 2014-04-15 08:00 | 2014-04-22 17:00 | 6d |  |  | 0 |  |  | 6022.4 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | p2p weekly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | p2p monthly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | p2p current saldo | 2014-04-15 08:00 | 2014-04-15 17:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 1d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | p2p duplicate documents | 2014-04-16 10:00 | 2014-04-17 10:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 1d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | p2p account statement | 2014-04-17 13:00 | 2014-04-18 12:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 1d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | p2p feedback | 2014-04-18 15:00 | 2014-04-21 15:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 1d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | business acceptance testing release 1 | 2013-10-25 08:00 | 2014-04-04 12:00 | 115d 4h |  |  | 0 |  |  | 45815.04 |  | 105d | [5 empty] | 54723.52 |  | 67.19% |  | 30781.9804 | 35633.92
216 | part 1 - information lists | 2014-02-17 08:00 | 2014-03-28 12:00 | 29d 4h | Employee M | 18771.44 | 0 | 0 | 0 | 18771.44 | 2014-02-17 08:00 | 22d | 13999.04 | 5408.72 | 8d 4h | 0 | 0 | 13999.04 | 5408.72 | 72% | Started | 13515.4373 | 15271.68 | 100 | 74.5763 | 72 | 100 | 74.5763 | 72
217 | part 2 - interface | 2013-10-25 08:00 | 2013-10-29 17:00 | 3d | Employee N | 1908.96 | 0 | 0 | 0 | 1908.96 | 2013-10-25 08:00 | 40d | 25452.8 | 8510.78 | 13d 3h | -3.638e-12 | 0 | 25452.8 | 8510.78 | 75% | Started | 1431.72 | 1908.96 | 100 | 1333.3333 | 75 | 100 | 1333.3333 | 75
218 | part 3 - reporting | 2014-02-10 08:00 | 2014-04-04 12:00 | 39d 4h | Employee P | 25134.64 | 0 | 0 | 0 | 25134.64 | 2014-02-10 08:00 | 24d | 15271.68 | 8988.02 | 14d 1h | 0 | 0 | 15271.68 | 8988.02 | 63% | Started | 15834.8231 | 18453.28 | 100 | 60.7595 | 63 | 100 | 60.7595 | 63
255 | business acceptance testing release 2 | 2014-04-21 08:00 | 2014-04-22 17:00 | 2d |  |  | 0 |  |  | 2545.28 |  | 24d | [5 empty] | 21634.88 |  | 45% |  | 1145.376 | 0
219 | test definition | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 0 | 100 | 1900 | 100 | 100 | 1900 | 100
220 | test data | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 15d | 9544.8 | 2386.2 | 3d 6h | -1.819e-12 | 0 | 9544.8 | 2386.2 | 80% | Started | 509.056 | 0 | 100 | 1500 | 80 | 100 | 1500 | 80
221 | test execution | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee N;Employee O | 1272.64 | 0 | 0 | 0 | 1272.64 |  | 0 | 0 | 1272.64 | 1d | 0 | 0 | 0 | 1272.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | service preparation | 2014-03-24 08:00 | 2014-04-23 17:00 | 23d |  |  | 0 |  |  | 3208.46 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
227 | SLA review | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | service budget agreement | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | production handbook | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | service manual | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | SCM validation | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | CIO validation | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 |  | 0 | 0 | 558.56 | 1d | 0 | 0 | 0 | 558.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | go-no go meeting | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
233 | formal validation | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | deploy on production | 2013-10-25 08:00 | 2014-05-16 17:00 | 146d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1522.16
234 | go live | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | PIN testing IT | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
236 | PIN testing business | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 |  | 0 | 0 | 558.56 | 1d | 0 | 0 | 0 | 558.56 | 0% | Not Started | 0 | 558.56 | 100 |  | 0 | 100 |  | 0
259 | validation | 2014-05-16 17:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
237 | steerco validation | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | end of implement | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | close | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 9731.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | hand-over preparation | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | project charter as built | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h | Employee A;Employee B | 2283.24 | 0 | 0 | 0 | 2283.24 |  | 0 | 0 | 2283.24 | 1d 4h | 0 | 0 | 0 | 2283.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | blueprint as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee J;Employee M;Employee N | 2751.04 | 0 | 0 | 0 | 2751.04 |  | 0 | 0 | 2751.04 | 1d | 0 | 0 | 0 | 2751.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | technical design as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee F;Employee G;Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 1d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | hand-over | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1927.2 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | service manual | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | CMDB check | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee C | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | SCM validation | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | project evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h |  |  | 0 |  |  | 722.7 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
245 | customer satisfaction survey | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | project team briefing | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | suppliers evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | close phase | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 240.9 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | program manager validation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | end of project | 2014-05-19 17:00 | 2014-05-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-05-01 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Debt Collection System | 2013-10-24 08:00 | 2014-05-20 12:00 | 148d 4h |  |  | 0 |  |  | 458112.3684 |  | 139d | [5 empty] | 411441.6761 |  | 77.69% |  | 355893.5123 | 435700.3284
9 | define | 2013-10-24 08:00 | 2013-12-18 17:00 | 40d |  |  | 0 |  |  | 41864.71 |  | 39d 7h | [5 empty] | 41864.71 |  | 100% |  | 41864.71 | 41864.71
1 | kick-off meeting | 2013-10-24 08:00 | 2013-10-24 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-10-24 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
266 | project charter set | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  |  | 0 |  |  | 37495.44 |  | 24d | [5 empty] | 37495.44 |  | 100% |  | 37495.44 | 37495.44
2 | project charter (scope definition) | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d | Employee A;Employee B | 36531.84 | 0 | 0 | 0 | 36531.84 | 2013-11-04 08:00 | 24d | 36531.84 | 0 | 0 | 0 | 0 | 36531.84 | 0 | 100% | Finished | 36531.84 | 36531.84 | 100 | 100 | 100 | 100 | 100 | 100
3 | project security risks | 2013-11-13 08:00 | 2013-11-13 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2013-11-13 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
267 | project charter - communication and validation | 2013-11-25 08:00 | 2013-12-18 17:00 | 18d |  |  | 0 |  |  | 3810.71 |  | 17d 7h | [5 empty] | 3810.71 |  | 100% |  | 3810.71 | 3810.71
4 | inform IT governance | 2013-11-25 08:00 | 2013-11-25 09:00 | 1h | Employee B;Employee C | 240.9 | 0 | 0 | 0 | 240.9 | 2013-11-25 08:00 | 1h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
5 | send info | 2013-11-28 08:00 | 2013-11-28 17:00 | 1d | Employee B;Employee D | 1927.2 | 0 | 0 | 0 | 1927.2 | 2013-11-28 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 100 | 100 | 100 | 100 | 100
6 | send project charter for validation + delivery board validation | 2013-12-13 08:00 | 2013-12-16 09:00 | 1d 1h | Employee B | 1084.05 | 0 | 0 | 0 | 1084.05 | 2013-12-13 08:00 | 1d 1h | 1084.05 | 0 | 0 | 0 | 0 | 1084.05 | 0 | 100% | Finished | 1084.05 | 1084.05 | 100 | 100 | 100 | 100 | 100 | 100
7 | business validation | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-12-17 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
8 | end of define | 2013-12-18 17:00 | 2013-12-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
22 | design | 2013-11-25 08:00 | 2014-02-10 17:00 | 56d |  |  | 0 |  |  | 107215.84 |  | 55d 7h | [5 empty] | 100711.54 |  | 100% |  | 107215.84 | 107215.84
15 | blueprint set | 2013-11-25 08:00 | 2014-01-23 17:00 | 44d |  |  | 0 |  |  | 103826.72 |  | 51d | [5 empty] | 98045.12 |  | 100% |  | 103826.72 | 103826.72
10 | functional analysis List/file creation | 2013-12-02 08:00 | 2014-01-03 17:00 | 25d | Employee G | 15056 | 0 | 0 | 0 | 15056 | 2013-12-02 08:00 | 25d | 15056 | 0 | 0 | 0 | 0 | 15056 | 0 | 100% | Finished | 15056 | 15056 | 100 | 100 | 100 | 100 | 100 | 100
11 | functional analysis Monitoring | 2013-11-25 08:00 | 2014-01-08 17:00 | 33d | Employee H | 19873.92 | 0 | 0 | 0 | 19873.92 | 2013-11-25 08:00 | 33d | 19873.92 | 0 | 0 | -3.638e-12 | 0 | 19873.92 | 0 | 100% | Finished | 19873.92 | 19873.92 | 100 | 100 | 100 | 100 | 100 | 100
12 | functional analysis Interfacing | 2013-11-25 08:00 | 2014-01-03 17:00 | 30d | Employee F;Employee I | 36134.4 | 0 | 0 | 0 | 36134.4 | 2013-11-25 08:00 | 30d | 36134.4 | 0 | 0 | 0 | 0 | 36134.4 | 0 | 100% | Finished | 36134.4 | 36134.4 | 100 | 100 | 100 | 100 | 100 | 100
13 | architecture analysis | 2013-11-25 08:00 | 2013-12-27 17:00 | 25d | Employee E | 24090 | 0 | 0 | 0 | 24090 | 2013-11-25 08:00 | 25d | 24090 | 0 | 0 | 0 | 0 | 24090 | 0 | 100% | Finished | 24090 | 24090 | 100 | 100 | 100 | 100 | 100 | 100
14 | budget &amp; planning for development + master test chapter | 2014-01-13 08:00 | 2014-01-23 17:00 | 9d | Employee B | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-01-30 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 100% | Finished | 8672.4 | 8672.4 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
21 | design phase - validations | 2014-01-21 08:00 | 2014-02-10 17:00 | 15d |  |  | 0 |  |  | 3389.12 |  | 14d 7h | [5 empty] | 2666.42 |  | 100% |  | 3389.12 | 3389.12
16 | presentation to Business part 1 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G;Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-21 08:00 | 4h | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
17 | presentation to Business part 2 | 2014-01-31 08:00 | 2014-01-31 12:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-01-31 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
18 | send to delivery board + IT governance validation | 2014-02-07 08:00 | 2014-02-10 17:00 | 2d | Employee B | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-02-07 08:00 | 1d 2h | 1204.5 | 0 | 0 | 0 | 0 | 1204.5 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 62.5 | 100 | 100 | 62.5 | 100
19 | business validation | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-02-07 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
20 | end of design | 2014-02-10 17:00 | 2014-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | build | 2013-12-27 15:00 | 2014-05-14 17:00 | 98d 2h |  |  | 0 |  |  | 178453.6384 |  | 70d | [5 empty] | 143043.7461 |  | 80.18% |  | 143091.3943 | 173635.7184
32 | weekly file | 2014-01-02 15:00 | 2014-03-11 17:00 | 48d 2h |  |  | 0 |  |  | 19499.28 |  | 66d | [5 empty] | 18084.892 |  | 96.94% |  | 18903.0624 | 19499.28
23 | build/technical design | 2014-01-02 15:00 | 2014-01-09 15:00 | 5d | Employee G[0.60 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-01-30 08:00 | 5d 4h | 1987.392 | 0 | 0 | 0 | 0 | 1987.392 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 110 | 100 | 100 | 110 | 100
24 | ABAP | 2014-01-09 15:00 | 2014-01-22 15:00 | 9d | ABAP | 6750 | 0 | 0 | 0 | 6750 | 2014-02-06 08:00 | 9d | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 100% | Finished | 6750 | 6750 | 100 | 100 | 100 | 100 | 100 | 100
25 | UT program in general | 2014-01-23 15:00 | 2014-01-27 10:00 | 1d 4h | Employee G | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
26 | UT submission file | 2014-01-31 15:00 | 2014-02-06 10:00 | 3d 4h | Employee G | 2107.84 | 0 | 0 | 0 | 2107.84 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2107.84 | 2107.84 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | UT clearing file | 2014-01-27 10:00 | 2014-01-31 10:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
28 | UT other treatment file | 2014-01-31 10:00 | 2014-02-06 10:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-26 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
29 | business UT submission | 2014-03-05 13:00 | 2014-03-10 12:00 | 3d | Employee M | 1908.96 | 0 | 0 | 0 | 1908.96 | 2014-02-25 08:00 | 3h | 238.62 | 0 | 0 | 0 | 0 | 238.62 | 0 | 100% | Finished | 1908.96 | 1908.96 | 100 | 12.5 | 100 | 100 | 12.5 | 100
30 | UT sending via e-mail | 2014-03-11 08:00 | 2014-03-11 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
31 | build/technical design | 2014-01-22 15:00 | 2014-01-23 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
82 | monthly file | 2013-12-27 15:00 | 2014-02-14 17:00 | 35d 2h |  |  | 0 |  |  | 6713.344 |  | 70d | [5 empty] | 5750.052 |  | 91.12% |  | 6117.1264 | 6713.344
33 | build/technical design | 2013-12-27 15:00 | 2014-01-02 15:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-24 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
34 | ABAP | 2014-01-30 08:00 | 2014-02-03 12:00 | 2d 4h | ABAP[0.80 #1] | 1500 | 0 | 0 | 0 | 1500 | 2014-01-30 08:00 | 2d 4h | 1500 | 0 | 0 | 2.2352e-05 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
35 | UT | 2014-02-03 13:00 | 2014-02-11 17:00 | 6d 4h | Employee G[0.40 #1] | 1565.824 | 0 | 0 | 0 | 1565.824 | 2014-02-03 08:00 | 7d | 1686.272 | 0 | 0 | 2.5127e-05 | 0 | 1686.272 | 0 | 100% | Finished | 1565.824 | 1565.824 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
36 | business UT | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee M | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-18 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
37 | UT sending via e-mail | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
83 | authorization check | 2014-01-24 08:00 | 2014-03-24 12:00 | 41d 4h |  |  | 0 |  |  | 15386.2 |  | 38d | [5 empty] | 15386.2 |  | 100% |  | 15386.2 | 15386.2
38 | IRIS-SC | 2014-03-13 08:00 | 2014-03-18 17:00 | 4d | Java | 3000 | 0 | 0 | 0 | 3000 | 2014-03-13 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
39 | build/technical design | 2014-01-24 08:00 | 2014-01-24 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-24 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
40 | ABAP | 2014-01-27 08:00 | 2014-02-10 17:00 | 11d | ABAP | 8250 | 0 | 0 | 0 | 8250 | 2014-01-27 08:00 | 11d | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 100% | Finished | 8250 | 8250 | 100 | 100 | 100 | 100 | 100 | 100
41 | UT | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
42 | build/technical design | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
43 | ABAP | 2014-03-19 13:00 | 2014-03-20 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
44 | UT | 2014-03-20 13:00 | 2014-03-21 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | import WSDL | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-02-13 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
46 | ESB (pass BP to basic) | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
84 | send DMS file via e-mail | 2014-02-05 15:00 | 2014-03-10 17:00 | 23d 2h |  |  | 0 |  |  | 13548.8944 |  | 54d | [5 empty] | 8612.032 |  | 61.6% |  | 8345.5408 | 13548.8944
47 | build/technical design | 2014-02-17 08:00 | 2014-03-07 10:00 | 14d 2h | Employee I[0.07 #1] | 600.7344 | 0 | 0 | 0 | 600.7344 | 2014-02-17 08:00 | 15d | 632.352 | 0 | 0 | 2.6922e-06 | 0 | 632.352 | 0 | 100% | Finished | 600.7344 | 600.7344 | 100 | 105.2632 | 100 | 100 | 105.2632 | 100
48 | import WSDL | 2014-02-05 15:00 | 2014-02-06 10:00 | 4h | EAI | 301.12 | 0 | 0 | 0 | 301.12 | 2014-02-17 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
49 | build/technical design | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
50 | EAI | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | UT | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
52 | build/technical design | 2014-02-18 08:00 | 2014-02-18 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
53 | EAI | 2014-02-19 08:00 | 2014-02-19 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
54 | UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
55 | design | 2014-02-19 08:00 | 2014-02-20 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | build | 2014-02-21 08:00 | 2014-02-25 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-21 08:00 | 2d 4h | 1505.6 | 677.52 | 1d 1h | 0 | 0 | 1505.6 | 677.52 | 70% | Started | 1264.704 | 1806.72 | 100 | 83.3333 | 70 | 100 | 83.3333 | 70
57 | queue handling | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 1d | 602.24 | 903.36 | 1d 4h | 0 | 0 | 602.24 | 903.36 | 40% | Started | 722.688 | 1806.72 | 100 | 33.3333 | 40 | 100 | 33.3333 | 40
58 | UT | 2014-03-03 08:00 | 2014-03-06 17:00 | 4d | EAI | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-03-03 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 24.0896 | 2408.96 | 100 | 3.125 | 1 | 100 | 3.125 | 1
59 | deployment | 2014-03-07 08:00 | 2014-03-10 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-07 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
85 | duplicates | 2014-02-12 13:00 | 2014-03-26 17:00 | 30d 4h |  |  | 0 |  |  | 5261.2 |  | 11d | [5 empty] | 5261.2 |  | 100% |  | 5261.2 | 5261.2
60 | build/technical design | 2014-02-12 13:00 | 2014-02-14 12:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-12 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
61 | java | 2014-03-19 08:00 | 2014-03-21 17:00 | 3d | Java | 2250 | 0 | 0 | 0 | 2250 | 2014-02-19 08:00 | 3d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 2250 | 2250 | 100 | 100 | 100 | 100 | 100 | 100
62 | UT | 2014-03-24 08:00 | 2014-03-26 17:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-24 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
86 | current saldo | 2014-02-11 08:00 | 2014-02-20 17:00 | 8d |  |  | 0 |  |  | 3943.04 |  | 7d 4h | [5 empty] | 3386.26 |  | 100% |  | 3943.04 | 3943.04
63 | build/technical design | 2014-02-11 08:00 | 2014-02-12 12:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-11 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
64 | java | 2014-02-14 13:00 | 2014-02-18 12:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-02-17 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
65 | UT | 2014-02-18 13:00 | 2014-02-19 17:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
66 | business UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-20 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
88 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d |  |  | 0 |  |  | 3613.44 |  | 6d | [5 empty] | 3613.44 |  | 100% |  | 3613.44 | 3613.44
67 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d | Employee I | 3613.44 | 0 | 0 | 0 | 3613.44 | 2014-03-07 10:00 | 6d | 3613.44 | 0 | 0 | 0 | 0 | 3613.44 | 0 | 100% | Finished | 3613.44 | 3613.44 | 100 | 100 | 100 | 100 | 100 | 100
87 | account statement | 2014-01-24 15:00 | 2014-03-31 12:00 | 45d 6h |  |  | 0 |  |  | 15044.8 |  | 59d | [5 empty] | 12936.96 |  | 85.99% |  | 12936.96 | 15044.8
68 | build/technical design | 2014-01-24 15:00 | 2014-02-07 15:00 | 10d | Employee F[0.50 #1];Employee L[0.50 #1] | 6022.4 | 0 | 0 | 0 | 6022.4 | 2014-02-10 08:00 | 10d | 6022.4 | 0 | 0 | 0 | 0 | 6022.4 | 0 | 100% | Finished | 6022.4 | 6022.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | ABAP | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-02-20 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
70 | UT | 2014-02-13 08:00 | 2014-02-14 17:00 | 2d | Employee F;Employee L | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-04-02 08:00 | 1d | 1204.48 | 1204.48 | 1d | 0 | 0 | 1204.48 | 1204.48 | 50% | Started | 1204.48 | 2408.96 | 100 | 50 | 50 | 100 | 50 | 50
71 | spec proxy | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
72 | ABAP proxy | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
73 | UT proxy | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-04 08:00 | 2h | 150.56 | 451.68 | 6h | 0 | 0 | 150.56 | 451.68 | 25% | Started | 150.56 | 602.24 | 100 | 25 | 25 | 100 | 25 | 25
74 | spec wrapper core | 2014-03-24 13:00 | 2014-03-26 12:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-20 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
75 | ABAP wrapper core | 2014-03-26 13:00 | 2014-03-27 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
76 | UT wrapper core | 2014-03-27 13:00 | 2014-03-28 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-07 08:00 | 2h | 150.56 | 451.68 | 6h | 0 | 0 | 150.56 | 451.68 | 25% | Started | 150.56 | 602.24 | 100 | 25 | 25 | 100 | 25 | 25
77 | email functionality | 2014-03-28 13:00 | 2014-03-31 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
173 | monitoring and reporting | 2014-01-29 08:00 | 2014-03-05 15:00 | 25d 6h |  |  | 0 |  |  | 31228.56 |  | 67d | [5 empty] | 25446.96 |  | 78.31% |  | 24454.4519 | 31228.56
78 | build/technical design | 2014-01-29 08:00 | 2014-02-03 17:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-29 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
79 | ABAP | 2014-02-06 08:00 | 2014-02-12 17:00 | 5d | ABAP | 3750 | 0 | 0 | 0 | 3750 | 2014-02-06 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
80 | UT | 2014-02-13 08:00 | 2014-02-19 17:00 | 5d | Employee H;ABAP | 6761.2 | 0 | 0 | 0 | 6761.2 | 2014-02-13 08:00 | 5d | 6761.2 | 0 | 0 | 0 | 0 | 6761.2 | 0 | 100% | Finished | 6761.2 | 6761.2 | 100 | 100 | 100 | 100 | 100 | 100
81 | BI reports | 2014-02-06 15:00 | 2014-03-05 15:00 | 19d | Employee K | 18308.4 | 0 | 0 | 0 | 18308.4 | 2014-02-06 15:00 | 13d | 12526.8 | 7347.45 | 7d 5h | -1.819e-12 | 0 | 12526.8 | 7347.45 | 63% | Started | 11534.2919 | 18308.4 | 100 | 68.4211 | 63 | 100 | 68.4211 | 63
174 | weekly file | 2014-03-21 08:00 | 2014-04-01 15:00 | 7d 6h |  |  | 0 |  |  | 3219.2 |  | 30d | [5 empty] | 1623.25 |  | 42.59% |  | 1370.9096 | 3219.2
89 | build/technical design | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-21 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
90 | ABAP | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
91 | UT | 2014-03-25 08:00 | 2014-03-25 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-25 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
92 | build/technical design | 2014-03-28 15:00 | 2014-03-31 10:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 15:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 3.0112 | 301.12 | 100 | 25 | 1 | 100 | 25 | 1
93 | setup autosys | 2014-03-31 15:00 | 2014-04-01 15:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-03-31 15:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
175 | monthly file | 2014-03-31 10:00 | 2014-04-01 17:00 | 1d 6h |  |  | 0 |  |  | 1505.62 |  | 23d 6h | [5 empty] | 195.73 |  | 1% |  | 15.0562 | 1505.62
94 | build/technical design | 2014-03-31 10:00 | 2014-03-31 15:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 10:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 3.0112 | 301.12 | 100 | 25 | 1 | 100 | 25 | 1
95 | setup autosys | 2014-03-31 15:00 | 2014-04-01 17:00 | 1d 2h | Employee D | 1204.5 | 0 | 0 | 0 | 1204.5 | 2014-04-01 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 12.045 | 1204.5 | 100 | 10 | 1 | 100 | 10 | 1
176 | list | 2014-03-26 08:00 | 2014-03-28 15:00 | 2d 6h |  |  | 0 |  |  | 1579.48 |  | 27d | [5 empty] | 620.71 |  | 31.12% |  | 491.5644 | 1579.48
96 | build/technical design | 2014-03-26 08:00 | 2014-03-26 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-26 08:00 | 6h | 451.68 | 75.28 | 1h | 0 | 0 | 451.68 | 75.28 | 80% | Started | 481.792 | 602.24 | 100 | 75 | 80 | 100 | 75 | 80
97 | ABAP | 2014-03-27 08:00 | 2014-03-27 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-27 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
98 | UT | 2014-03-27 15:00 | 2014-03-28 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-28 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
177 | migration program | 2014-03-21 08:00 | 2014-04-07 17:00 | 12d |  |  | 0 |  |  | 7522.4 |  | 29d | [5 empty] | 4685.83 |  | 61.2% |  | 4604.0687 | 7522.4
99 | build/technical design | 2014-03-21 08:00 | 2014-04-01 17:00 | 8d | Employee H | 4817.92 | 0 | 0 | 0 | 4817.92 | 2014-03-24 08:00 | 7d 4h | 4516.8 | 225.84 | 3h | 0 | 0 | 4516.8 | 225.84 | 95% | Started | 4577.0239 | 4817.92 | 100 | 93.75 | 95 | 100 | 93.75 | 95
100 | ABAP | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-04-03 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 15 | 1500 | 100 | 6.25 | 1 | 100 | 6.25 | 1
101 | UT | 2014-04-04 08:00 | 2014-04-07 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-07 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
178 | send DMS file via e-mail | 2014-03-14 08:00 | 2014-03-27 15:00 | 9d 6h |  |  | 0 |  |  | 7463.06 |  | 11d | [5 empty] | 5025.56 |  | 80.4% |  | 6000.5599 | 7463.06
102 | WSDL update | 2014-03-14 08:00 | 2014-03-14 10:00 | 2h | Java;Employee I | 338.06 | 0 | 0 | 0 | 338.06 | 2014-04-17 08:00 | 2h | 338.06 | 0 | 0 | 0 | 0 | 338.06 | 0 | 100% | Finished | 338.06 | 338.06 | 100 | 100 | 100 | 100 | 100 | 100
103 | get cert / encrypt | 2014-03-14 10:00 | 2014-03-21 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-04-17 08:00 | 4d 2h | 3187.5 | 375 | 4h | 0 | 0 | 3187.5 | 375 | 90% | Started | 3374.9999 | 3750 | 100 | 85 | 90 | 100 | 85 | 90
104 | error handling | 2014-03-21 10:00 | 2014-03-25 10:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-04-24 08:00 | 1d | 750 | 93.75 | 1h | 0 | 0 | 750 | 93.75 | 90% | Started | 1350 | 1500 | 100 | 50 | 90 | 100 | 50 | 90
105 | UT java team | 2014-03-25 10:00 | 2014-03-27 15:00 | 2d 4h | Java | 1875 | 0 | 0 | 0 | 1875 | 2014-04-28 08:00 | 1d | 750 | 750 | 1d | 0 | 0 | 750 | 750 | 50% | Started | 937.5 | 1875 | 100 | 40 | 50 | 100 | 40 | 50
179 | feedback | 2014-03-11 15:00 | 2014-04-04 10:00 | 17d 4h |  |  | 0 |  |  | 29314.4 |  | 37d | [5 empty] | 26512.67 |  | 87.83% |  | 25746.214 | 29314.4
106 | build/technical design | 2014-03-13 08:00 | 2014-03-13 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
107 | ABAP | 2014-03-14 08:00 | 2014-03-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
108 | UT | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
109 | build/technical design | 2014-03-11 15:00 | 2014-03-12 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-12 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
110 | ABAP | 2014-03-21 15:00 | 2014-03-24 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-13 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 375 | 375 | 100 | 200 | 100 | 100 | 200 | 100
111 | UT | 2014-03-24 10:00 | 2014-03-24 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 400 | 100 | 100 | 400 | 100
112 | build/technical design | 2014-03-14 08:00 | 2014-03-14 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
113 | ABAP | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-14 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
114 | UT | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
115 | build/technical design | 2014-03-12 10:00 | 2014-03-13 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
116 | ABAP | 2014-03-13 10:00 | 2014-03-14 10:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
117 | UT | 2014-03-14 10:00 | 2014-03-17 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
118 | build/technical design | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
119 | ABAP | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
120 | UT | 2014-03-17 13:00 | 2014-03-17 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
121 | build/technical design | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-18 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
122 | ABAP | 2014-03-17 15:00 | 2014-03-18 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-18 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
123 | UT | 2014-03-18 10:00 | 2014-03-18 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-19 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
124 | build/technical design | 2014-03-18 08:00 | 2014-03-18 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
125 | ABAP | 2014-03-19 08:00 | 2014-03-19 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-19 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
126 | UT | 2014-03-20 08:00 | 2014-03-20 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
127 | build/technical design | 2014-03-18 13:00 | 2014-03-18 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
128 | ABAP | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
129 | UT | 2014-03-19 13:00 | 2014-03-19 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
130 | build/technical design | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
131 | ABAP | 2014-03-19 13:00 | 2014-03-19 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
132 | UT | 2014-03-20 08:00 | 2014-03-20 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
133 | build/technical design | 2014-03-19 15:00 | 2014-03-20 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-20 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
134 | ABAP | 2014-03-20 10:00 | 2014-03-20 15:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-21 10:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
135 | UT | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-24 15:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
136 | import WSDL | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
137 | spec proxy | 2014-03-14 08:00 | 2014-03-17 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-17 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
138 | ABAP proxy | 2014-03-18 08:00 | 2014-03-18 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-21 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
139 | UT proxy | 2014-03-18 15:00 | 2014-03-20 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-21 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
140 | spec wrapper core | 2014-03-18 08:00 | 2014-03-19 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-21 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
141 | ABAP wrapper core | 2014-03-20 08:00 | 2014-03-20 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-23 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
142 | UT wrapper core | 2014-03-20 15:00 | 2014-03-24 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-23 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
143 | spec proxy | 2014-03-18 08:00 | 2014-03-20 17:00 | 3d | Employee F[0.50 #1] | 903.36 | 0 | 0 | 0 | 903.36 | 2014-04-21 08:00 | 3d | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
144 | ABAP proxy | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-04-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
145 | UT proxy | 2014-03-24 10:00 | 2014-03-26 10:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-25 10:00 | 1d 1h | 338.76 | 263.48 | 7h | 0 | 0 | 338.76 | 263.48 | 56.25% | Started | 338.76 | 602.24 | 100 | 56.25 | 56.25 | 100 | 56.25 | 56.25
146 | spec wrapper core | 2014-03-21 08:00 | 2014-03-26 17:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-24 08:00 | 2d 1h | 639.88 | 564.6 | 1d 7h | 0 | 0 | 639.88 | 564.6 | 53.12% | Started | 639.88 | 1204.48 | 100 | 53.125 | 53.125 | 100 | 53.125 | 53.125
147 | ABAP wrapper core | 2014-03-27 08:00 | 2014-03-28 12:00 | 1d 4h | ABAP | 1125 | 0 | 0 | 0 | 1125 | 2014-04-30 08:00 | 1h | 93.75 | 1031.25 | 1d 3h | 0 | 0 | 93.75 | 1031.25 | 8.333% | Started | 93.75 | 1125 | 100 | 8.3333 | 8.3333 | 100 | 8.3333 | 8.3333
148 | UT wrapper core | 2014-03-28 13:00 | 2014-04-03 12:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 1h | 37.64 | 1166.84 | 3d 7h | 0 | 0 | 37.64 | 1166.84 | 3.125% | Started | 37.64 | 1204.48 | 100 | 3.125 | 3.125 | 100 | 3.125 | 3.125
149 | content | 2014-03-20 10:00 | 2014-03-20 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
150 | UT | 2014-03-20 13:00 | 2014-03-20 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
151 | content | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
152 | UT | 2014-03-21 08:00 | 2014-03-21 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
153 | content | 2014-03-21 10:00 | 2014-03-21 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 10:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
154 | UT | 2014-03-21 13:00 | 2014-03-21 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 13:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
155 | build/technical design | 2014-03-17 10:00 | 2014-03-20 10:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-17 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
156 | java | 2014-03-20 10:00 | 2014-03-27 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-03-20 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
157 | UT | 2014-03-27 10:00 | 2014-04-04 10:00 | 6d | Employee F[0.50 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-27 10:00 | 4d | 1204.48 | 526.96 | 1d 6h | 0 | 0 | 1204.48 | 526.96 | 70% | Started | 1264.704 | 1806.72 | 100 | 66.6667 | 70 | 100 | 66.6667 | 70
180 | performance report | 2014-05-05 08:00 | 2014-05-14 17:00 | 8d |  |  | 0 |  |  | 4817.92 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
158 | build/technical design | 2014-05-05 08:00 | 2014-05-06 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | EAI | 2014-05-07 08:00 | 2014-05-09 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 3d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | UT | 2014-05-12 08:00 | 2014-05-14 17:00 | 3d | Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 3d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | preparation IT test strategy | 2014-02-04 08:00 | 2014-02-17 17:00 | 10d |  |  | 0 |  |  | 3011.2 |  | 10d | [5 empty] | 3011.2 |  | 100% |  | 3011.2 | 3011.2
161 | preparation core | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
162 | preparation migration | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
163 | preparation interfacing | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
164 | preparation reporting | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
165 | preparation interfacing | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
182 | service preparation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 2890.8 |  | 100% |  | 2890.8 | 2890.8
166 | service manual draft | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
167 | SDM validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
168 | TCS validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
183 | build phase - validation | 2014-04-08 08:00 | 2014-04-09 17:00 | 2d |  |  | 0 |  |  | 2890.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2890.8
169 | program manager validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
170 | SCM validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
171 | information security validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
172 | end of build | 2014-04-09 17:00 | 2014-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | implement | 2013-10-25 08:00 | 2014-05-19 17:00 | 147d |  |  | 0 |  |  | 120846.38 |  | 138d | [5 empty] | 125821.68 |  | 52.73% |  | 63721.568 | 112984.06
250 | certificates | 2014-04-02 10:00 | 2014-05-08 17:00 | 26d 6h |  |  | 0 |  |  | 17344.8 |  | 5d | [5 empty] | 1927.2 |  | 35% |  | 6070.6799 | 12526.8
185 | certificates on acceptance | 2014-04-02 10:00 | 2014-04-15 10:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-04-25 08:00 | 2d | 1927.2 | 843.15 | 7h | 0 | 0 | 1927.2 | 843.15 | 70% | Started | 6070.6799 | 8672.4 | 100 | 22.2222 | 70 | 100 | 22.2222 | 70
186 | certificates on production | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 |  | 0 | 0 | 8672.4 | 9d | 0 | 0 | 0 | 8672.4 | 0% | Not Started | 0 | 3854.4 | 100 |  | 0 | 100 |  | 0
251 | integration testing release 1 | 2014-02-06 10:00 | 2014-03-20 17:00 | 30d 6h |  |  | 0 |  |  | 26287.92 |  | 50d | [5 empty] | 19557.84 |  | 69.46% |  | 18260.0047 | 26287.92
187 | backend | 2014-03-03 15:00 | 2014-03-05 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-04 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
188 | backend and extract | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H;Employee K | 3131.68 | 0 | 0 | 0 | 3131.68 | 2014-03-06 15:00 | 2d | 3131.68 | 0 | 0 | -4.5475e-13 | 0 | 3131.68 | 0 | 100% | Finished | 3131.68 | 3131.68 | 100 | 100 | 100 | 100 | 100 | 100
189 | performance testing monitoring backend | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-06 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
190 | monitoring BI | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d | Employee K | 4818 | 0 | 0 | 0 | 4818 | 2014-03-12 08:00 | 3d | 2890.8 | 2890.8 | 3d | 0 | 0 | 2890.8 | 2890.8 | 50% | Started | 2409 | 4818 | 100 | 60 | 50 | 100 | 60 | 50
191 | weekly files | 2014-02-06 10:00 | 2014-02-11 17:00 | 3d 6h | Employee G | 2258.4 | 0 | 0 | 0 | 2258.4 | 2014-03-04 08:00 | 3d 6h | 2258.4 | 0 | 0 | 0 | 0 | 2258.4 | 0 | 100% | Finished | 2258.4 | 2258.4 | 100 | 100 | 100 | 100 | 100 | 100
192 | monthly files | 2014-02-21 08:00 | 2014-02-25 12:00 | 2d 4h | Employee G | 1505.6 | 0 | 0 | 0 | 1505.6 | 2014-02-21 08:00 | 2d 4h | 1505.6 | 0 | 0 | 0 | 0 | 1505.6 | 0 | 100% | Finished | 1505.6 | 1505.6 | 100 | 100 | 100 | 100 | 100 | 100
193 | duplicate documents | 2014-03-05 08:00 | 2014-03-06 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-08 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
194 | current saldo | 2014-03-03 08:00 | 2014-03-04 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-04 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
195 | account statement | 2014-03-07 08:00 | 2014-03-11 17:00 | 3d | Employee F | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-04-10 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 18.0672 | 1806.72 | 100 | 4.1667 | 1 | 100 | 4.1667 | 1
196 | defect core weekly | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-10 08:00 | 2d 6h | 1656.16 | 150.56 | 2h | 0 | 0 | 1656.16 | 150.56 | 90% | Started | 1626.048 | 1806.72 | 100 | 91.6667 | 90 | 100 | 91.6667 | 90
197 | defect core monthly | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 2d 6h | 1656.16 | 150.56 | 2h | 0 | 0 | 1656.16 | 150.56 | 90% | Started | 1626.048 | 1806.72 | 100 | 91.6667 | 90 | 100 | 91.6667 | 90
198 | defect interfacing | 2014-03-12 08:00 | 2014-03-13 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
199 | defect monitoring | 2014-03-07 15:00 | 2014-03-11 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-10 15:00 | 2d 6h | 1656.16 | 150.56 | 2h | 0 | 0 | 1656.16 | 150.56 | 90% | Started | 1084.032 | 1204.48 | 100 | 137.5 | 90 | 100 | 137.5 | 90
200 | defect BI reporting | 2014-03-19 08:00 | 2014-03-20 17:00 | 2d | Employee K | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-03-19 08:00 | 1d | 963.6 | 963.6 | 1d | 0 | 0 | 963.6 | 963.6 | 50% | Started | 963.6 | 1927.2 | 100 | 50 | 50 | 100 | 50 | 50
252 | integration testing release 2 | 2014-04-01 08:00 | 2014-04-23 17:00 | 17d |  |  | 0 |  |  | 15056 |  | 22d | [5 empty] | 2484.24 |  | 15.57% |  | 2344.2192 | 15056
201 | feedback | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee F[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 |  | 0 | 0 | 3011.2 | 10d | 0 | 0 | 0 | 3011.2 | 0% | Not Started | 0 | 3011.2 | 100 |  | 0 | 100 |  | 0
202 | migration | 2014-04-08 08:00 | 2014-04-21 17:00 | 10d | Employee H[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-09 08:00 | 1h | 37.64 | 2973.56 | 9d 7h | 0 | 0 | 37.64 | 2973.56 | 1.25% | Started | 37.64 | 3011.2 | 100 | 1.25 | 1.25 | 100 | 1.25 | 1.25
203 | list batch testing | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | Employee G[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-02 08:00 | 1h | 37.64 | 3726.36 | 12d 3h | 0 | 0 | 37.64 | 3726.36 | 1% | Started | 6.0224 | 602.24 | 100 | 6.25 | 1 | 100 | 6.25 | 1
204 | core | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee G[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-04 08:00 | 7d | 2107.84 | 715.16 | 2d 3h | 0 | 0 | 2107.84 | 715.16 | 75% | Started | 2258.4 | 3011.2 | 100 | 70 | 75 | 100 | 70 | 75
205 | mail encryption | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee I | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-30 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
206 | defect core | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee G | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
207 | defect interfacing | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 1204.48 | 100 |  | 0 | 100 |  | 0
208 | defect migration | 2014-04-22 08:00 | 2014-04-23 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-23 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
209 | defect mail encryption | 2014-04-02 10:00 | 2014-04-04 10:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
253 | p2p testing | 2014-04-15 08:00 | 2014-04-22 17:00 | 6d |  |  | 0 |  |  | 6022.4 |  | 13d | [5 empty] | 677.52 |  | 0.9% |  | 54.2016 | 6022.4
210 | p2p weekly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-22 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
211 | p2p monthly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 |  | 0 | 0 | 602.24 | 1d | 0 | 0 | 0 | 602.24 | 0% | Not Started | 0 | 602.24 | 100 |  | 0 | 100 |  | 0
212 | p2p current saldo | 2014-04-15 08:00 | 2014-04-15 17:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
213 | p2p duplicate documents | 2014-04-16 10:00 | 2014-04-17 10:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-16 08:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
214 | p2p account statement | 2014-04-17 13:00 | 2014-04-18 12:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-17 13:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
215 | p2p feedback | 2014-04-18 15:00 | 2014-04-21 15:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 15:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
254 | business acceptance testing release 1 | 2013-10-25 08:00 | 2014-04-04 12:00 | 115d 4h |  |  | 0 |  |  | 45815.04 |  | 135d | [5 empty] | 62995.68 |  | 75.19% |  | 34447.1826 | 45815.04
216 | part 1 - information lists | 2014-02-17 08:00 | 2014-03-28 12:00 | 29d 4h | Employee M | 18771.44 | 0 | 0 | 0 | 18771.44 | 2014-02-17 08:00 | 27d | 17180.64 | 1908.96 | 3d | -3.638e-12 | 0 | 17180.64 | 1908.96 | 90% | Started | 16894.2956 | 18771.44 | 100 | 91.5254 | 90 | 100 | 91.5254 | 90
217 | part 2 - interface | 2013-10-25 08:00 | 2013-10-29 17:00 | 3d | Employee N | 1908.96 | 0 | 0 | 0 | 1908.96 | 2013-10-25 08:00 | 48d | 30543.36 | 3420.22 | 5d 3h | 0 | 0 | 30543.36 | 3420.22 | 90% | Started | 1718.064 | 1908.96 | 100 | 1600 | 90 | 100 | 1600 | 90
218 | part 3 - reporting | 2014-02-10 08:00 | 2014-04-04 12:00 | 39d 4h | Employee P | 25134.64 | 0 | 0 | 0 | 25134.64 | 2014-02-10 08:00 | 24d | 15271.68 | 8988.02 | 14d 1h | 0 | 0 | 15271.68 | 8988.02 | 63% | Started | 15834.8231 | 25134.64 | 100 | 60.7595 | 63 | 100 | 60.7595 | 63
255 | business acceptance testing release 2 | 2014-04-21 08:00 | 2014-04-22 17:00 | 2d |  |  | 0 |  |  | 2545.28 |  | 57d | [5 empty] | 38179.2 |  | 100% |  | 2545.28 | 2545.28
219 | test definition | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
220 | test data | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
221 | test execution | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee N;Employee O | 1272.64 | 0 | 0 | 0 | 1272.64 | 2014-04-22 08:00 | 11d | 13999.04 | 0 | 0 | 0 | 0 | 13999.04 | 0 | 100% | Finished | 1272.64 | 1272.64 | 100 | 1100 | 100 | 100 | 1100 | 100
256 | service preparation | 2014-03-24 08:00 | 2014-04-23 17:00 | 23d |  |  | 0 |  |  | 3208.46 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3208.46
227 | SLA review | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
228 | service budget agreement | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
229 | production handbook | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
230 | service manual | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
231 | SCM validation | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 240.9 | 100 |  | 0 | 100 |  | 0
232 | CIO validation | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 |  | 0 | 0 | 558.56 | 1d | 0 | 0 | 0 | 558.56 | 0% | Not Started | 0 | 558.56 | 100 |  | 0 | 100 |  | 0
257 | go-no go meeting | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
233 | formal validation | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | deploy on production | 2013-10-25 08:00 | 2014-05-16 17:00 | 146d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1522.16
234 | go live | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | PIN testing IT | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
236 | PIN testing business | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 |  | 0 | 0 | 558.56 | 1d | 0 | 0 | 0 | 558.56 | 0% | Not Started | 0 | 558.56 | 100 |  | 0 | 100 |  | 0
259 | validation | 2014-05-16 17:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
237 | steerco validation | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | end of implement | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | close | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 9731.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | hand-over preparation | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | project charter as built | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h | Employee A;Employee B | 2283.24 | 0 | 0 | 0 | 2283.24 |  | 0 | 0 | 2283.24 | 1d 4h | 0 | 0 | 0 | 2283.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | blueprint as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee J;Employee M;Employee N | 2751.04 | 0 | 0 | 0 | 2751.04 |  | 0 | 0 | 2751.04 | 1d | 0 | 0 | 0 | 2751.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | technical design as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee F;Employee G;Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 1d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | hand-over | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1927.2 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | service manual | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | CMDB check | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee C | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | SCM validation | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | project evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h |  |  | 0 |  |  | 722.7 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
245 | customer satisfaction survey | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | project team briefing | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | suppliers evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | close phase | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 240.9 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | program manager validation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | end of project | 2014-05-19 17:00 | 2014-05-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-05-07 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Debt Collection System | 2013-10-24 08:00 | 2014-05-20 12:00 | 148d 4h |  |  | 0 |  |  | 458112.3684 |  | 140d | [5 empty] | 426824.6661 |  | 82.27% |  | 376902.1018 | 441361.4484
9 | define | 2013-10-24 08:00 | 2013-12-18 17:00 | 40d |  |  | 0 |  |  | 41864.71 |  | 39d 7h | [5 empty] | 41864.71 |  | 100% |  | 41864.71 | 41864.71
1 | kick-off meeting | 2013-10-24 08:00 | 2013-10-24 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-10-24 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
266 | project charter set | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  |  | 0 |  |  | 37495.44 |  | 24d | [5 empty] | 37495.44 |  | 100% |  | 37495.44 | 37495.44
2 | project charter (scope definition) | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d | Employee A;Employee B | 36531.84 | 0 | 0 | 0 | 36531.84 | 2013-11-04 08:00 | 24d | 36531.84 | 0 | 0 | 0 | 0 | 36531.84 | 0 | 100% | Finished | 36531.84 | 36531.84 | 100 | 100 | 100 | 100 | 100 | 100
3 | project security risks | 2013-11-13 08:00 | 2013-11-13 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2013-11-13 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
267 | project charter - communication and validation | 2013-11-25 08:00 | 2013-12-18 17:00 | 18d |  |  | 0 |  |  | 3810.71 |  | 17d 7h | [5 empty] | 3810.71 |  | 100% |  | 3810.71 | 3810.71
4 | inform IT governance | 2013-11-25 08:00 | 2013-11-25 09:00 | 1h | Employee B;Employee C | 240.9 | 0 | 0 | 0 | 240.9 | 2013-11-25 08:00 | 1h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
5 | send info | 2013-11-28 08:00 | 2013-11-28 17:00 | 1d | Employee B;Employee D | 1927.2 | 0 | 0 | 0 | 1927.2 | 2013-11-28 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 100 | 100 | 100 | 100 | 100
6 | send project charter for validation + delivery board validation | 2013-12-13 08:00 | 2013-12-16 09:00 | 1d 1h | Employee B | 1084.05 | 0 | 0 | 0 | 1084.05 | 2013-12-13 08:00 | 1d 1h | 1084.05 | 0 | 0 | 0 | 0 | 1084.05 | 0 | 100% | Finished | 1084.05 | 1084.05 | 100 | 100 | 100 | 100 | 100 | 100
7 | business validation | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-12-17 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
8 | end of define | 2013-12-18 17:00 | 2013-12-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
22 | design | 2013-11-25 08:00 | 2014-02-10 17:00 | 56d |  |  | 0 |  |  | 107215.84 |  | 55d 7h | [5 empty] | 100711.54 |  | 100% |  | 107215.84 | 107215.84
15 | blueprint set | 2013-11-25 08:00 | 2014-01-23 17:00 | 44d |  |  | 0 |  |  | 103826.72 |  | 51d | [5 empty] | 98045.12 |  | 100% |  | 103826.72 | 103826.72
10 | functional analysis List/file creation | 2013-12-02 08:00 | 2014-01-03 17:00 | 25d | Employee G | 15056 | 0 | 0 | 0 | 15056 | 2013-12-02 08:00 | 25d | 15056 | 0 | 0 | 0 | 0 | 15056 | 0 | 100% | Finished | 15056 | 15056 | 100 | 100 | 100 | 100 | 100 | 100
11 | functional analysis Monitoring | 2013-11-25 08:00 | 2014-01-08 17:00 | 33d | Employee H | 19873.92 | 0 | 0 | 0 | 19873.92 | 2013-11-25 08:00 | 33d | 19873.92 | 0 | 0 | -3.638e-12 | 0 | 19873.92 | 0 | 100% | Finished | 19873.92 | 19873.92 | 100 | 100 | 100 | 100 | 100 | 100
12 | functional analysis Interfacing | 2013-11-25 08:00 | 2014-01-03 17:00 | 30d | Employee F;Employee I | 36134.4 | 0 | 0 | 0 | 36134.4 | 2013-11-25 08:00 | 30d | 36134.4 | 0 | 0 | 0 | 0 | 36134.4 | 0 | 100% | Finished | 36134.4 | 36134.4 | 100 | 100 | 100 | 100 | 100 | 100
13 | architecture analysis | 2013-11-25 08:00 | 2013-12-27 17:00 | 25d | Employee E | 24090 | 0 | 0 | 0 | 24090 | 2013-11-25 08:00 | 25d | 24090 | 0 | 0 | 0 | 0 | 24090 | 0 | 100% | Finished | 24090 | 24090 | 100 | 100 | 100 | 100 | 100 | 100
14 | budget &amp; planning for development + master test chapter | 2014-01-13 08:00 | 2014-01-23 17:00 | 9d | Employee B | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-01-30 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 100% | Finished | 8672.4 | 8672.4 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
21 | design phase - validations | 2014-01-21 08:00 | 2014-02-10 17:00 | 15d |  |  | 0 |  |  | 3389.12 |  | 14d 7h | [5 empty] | 2666.42 |  | 100% |  | 3389.12 | 3389.12
16 | presentation to Business part 1 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G;Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-21 08:00 | 4h | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
17 | presentation to Business part 2 | 2014-01-31 08:00 | 2014-01-31 12:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-01-31 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
18 | send to delivery board + IT governance validation | 2014-02-07 08:00 | 2014-02-10 17:00 | 2d | Employee B | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-02-07 08:00 | 1d 2h | 1204.5 | 0 | 0 | 0 | 0 | 1204.5 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 62.5 | 100 | 100 | 62.5 | 100
19 | business validation | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-02-07 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
20 | end of design | 2014-02-10 17:00 | 2014-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | build | 2013-12-27 15:00 | 2014-05-14 17:00 | 98d 2h |  |  | 0 |  |  | 178453.6384 |  | 74d | [5 empty] | 150893.9161 |  | 85.16% |  | 151971.2715 | 175442.4384
32 | weekly file | 2014-01-02 15:00 | 2014-03-11 17:00 | 48d 2h |  |  | 0 |  |  | 19499.28 |  | 70d | [5 empty] | 18084.892 |  | 96.94% |  | 18903.0624 | 19499.28
23 | build/technical design | 2014-01-02 15:00 | 2014-01-09 15:00 | 5d | Employee G[0.60 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-01-30 08:00 | 5d 4h | 1987.392 | 0 | 0 | 0 | 0 | 1987.392 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 110 | 100 | 100 | 110 | 100
24 | ABAP | 2014-01-09 15:00 | 2014-01-22 15:00 | 9d | ABAP | 6750 | 0 | 0 | 0 | 6750 | 2014-02-06 08:00 | 9d | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 100% | Finished | 6750 | 6750 | 100 | 100 | 100 | 100 | 100 | 100
25 | UT program in general | 2014-01-23 15:00 | 2014-01-27 10:00 | 1d 4h | Employee G | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
26 | UT submission file | 2014-01-31 15:00 | 2014-02-06 10:00 | 3d 4h | Employee G | 2107.84 | 0 | 0 | 0 | 2107.84 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2107.84 | 2107.84 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | UT clearing file | 2014-01-27 10:00 | 2014-01-31 10:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
28 | UT other treatment file | 2014-01-31 10:00 | 2014-02-06 10:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-26 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
29 | business UT submission | 2014-03-05 13:00 | 2014-03-10 12:00 | 3d | Employee M | 1908.96 | 0 | 0 | 0 | 1908.96 | 2014-02-25 08:00 | 3h | 238.62 | 0 | 0 | 0 | 0 | 238.62 | 0 | 100% | Finished | 1908.96 | 1908.96 | 100 | 12.5 | 100 | 100 | 12.5 | 100
30 | UT sending via e-mail | 2014-03-11 08:00 | 2014-03-11 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
31 | build/technical design | 2014-01-22 15:00 | 2014-01-23 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
82 | monthly file | 2013-12-27 15:00 | 2014-02-14 17:00 | 35d 2h |  |  | 0 |  |  | 6713.344 |  | 74d | [5 empty] | 5750.052 |  | 91.12% |  | 6117.1264 | 6713.344
33 | build/technical design | 2013-12-27 15:00 | 2014-01-02 15:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-24 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
34 | ABAP | 2014-01-30 08:00 | 2014-02-03 12:00 | 2d 4h | ABAP[0.80 #1] | 1500 | 0 | 0 | 0 | 1500 | 2014-01-30 08:00 | 2d 4h | 1500 | 0 | 0 | 2.2352e-05 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
35 | UT | 2014-02-03 13:00 | 2014-02-11 17:00 | 6d 4h | Employee G[0.40 #1] | 1565.824 | 0 | 0 | 0 | 1565.824 | 2014-02-03 08:00 | 7d | 1686.272 | 0 | 0 | 2.5127e-05 | 0 | 1686.272 | 0 | 100% | Finished | 1565.824 | 1565.824 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
36 | business UT | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee M | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-18 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
37 | UT sending via e-mail | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
83 | authorization check | 2014-01-24 08:00 | 2014-03-24 12:00 | 41d 4h |  |  | 0 |  |  | 15386.2 |  | 38d | [5 empty] | 15386.2 |  | 100% |  | 15386.2 | 15386.2
38 | IRIS-SC | 2014-03-13 08:00 | 2014-03-18 17:00 | 4d | Java | 3000 | 0 | 0 | 0 | 3000 | 2014-03-13 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
39 | build/technical design | 2014-01-24 08:00 | 2014-01-24 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-24 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
40 | ABAP | 2014-01-27 08:00 | 2014-02-10 17:00 | 11d | ABAP | 8250 | 0 | 0 | 0 | 8250 | 2014-01-27 08:00 | 11d | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 100% | Finished | 8250 | 8250 | 100 | 100 | 100 | 100 | 100 | 100
41 | UT | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
42 | build/technical design | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
43 | ABAP | 2014-03-19 13:00 | 2014-03-20 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
44 | UT | 2014-03-20 13:00 | 2014-03-21 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | import WSDL | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-02-13 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
46 | ESB (pass BP to basic) | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
84 | send DMS file via e-mail | 2014-02-05 15:00 | 2014-03-10 17:00 | 23d 2h |  |  | 0 |  |  | 13548.8944 |  | 58d | [5 empty] | 8612.032 |  | 61.6% |  | 8345.5408 | 13548.8944
47 | build/technical design | 2014-02-17 08:00 | 2014-03-07 10:00 | 14d 2h | Employee I[0.07 #1] | 600.7344 | 0 | 0 | 0 | 600.7344 | 2014-02-17 08:00 | 15d | 632.352 | 0 | 0 | 2.6922e-06 | 0 | 632.352 | 0 | 100% | Finished | 600.7344 | 600.7344 | 100 | 105.2632 | 100 | 100 | 105.2632 | 100
48 | import WSDL | 2014-02-05 15:00 | 2014-02-06 10:00 | 4h | EAI | 301.12 | 0 | 0 | 0 | 301.12 | 2014-02-17 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
49 | build/technical design | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
50 | EAI | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | UT | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
52 | build/technical design | 2014-02-18 08:00 | 2014-02-18 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
53 | EAI | 2014-02-19 08:00 | 2014-02-19 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
54 | UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
55 | design | 2014-02-19 08:00 | 2014-02-20 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | build | 2014-02-21 08:00 | 2014-02-25 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-21 08:00 | 2d 4h | 1505.6 | 677.52 | 1d 1h | 0 | 0 | 1505.6 | 677.52 | 70% | Started | 1264.704 | 1806.72 | 100 | 83.3333 | 70 | 100 | 83.3333 | 70
57 | queue handling | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 1d | 602.24 | 903.36 | 1d 4h | 0 | 0 | 602.24 | 903.36 | 40% | Started | 722.688 | 1806.72 | 100 | 33.3333 | 40 | 100 | 33.3333 | 40
58 | UT | 2014-03-03 08:00 | 2014-03-06 17:00 | 4d | EAI | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-03-03 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 24.0896 | 2408.96 | 100 | 3.125 | 1 | 100 | 3.125 | 1
59 | deployment | 2014-03-07 08:00 | 2014-03-10 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-07 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
85 | duplicates | 2014-02-12 13:00 | 2014-03-26 17:00 | 30d 4h |  |  | 0 |  |  | 5261.2 |  | 11d | [5 empty] | 5261.2 |  | 100% |  | 5261.2 | 5261.2
60 | build/technical design | 2014-02-12 13:00 | 2014-02-14 12:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-12 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
61 | java | 2014-03-19 08:00 | 2014-03-21 17:00 | 3d | Java | 2250 | 0 | 0 | 0 | 2250 | 2014-02-19 08:00 | 3d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 2250 | 2250 | 100 | 100 | 100 | 100 | 100 | 100
62 | UT | 2014-03-24 08:00 | 2014-03-26 17:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-24 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
86 | current saldo | 2014-02-11 08:00 | 2014-02-20 17:00 | 8d |  |  | 0 |  |  | 3943.04 |  | 7d 4h | [5 empty] | 3386.26 |  | 100% |  | 3943.04 | 3943.04
63 | build/technical design | 2014-02-11 08:00 | 2014-02-12 12:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-11 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
64 | java | 2014-02-14 13:00 | 2014-02-18 12:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-02-17 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
65 | UT | 2014-02-18 13:00 | 2014-02-19 17:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
66 | business UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-20 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
88 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d |  |  | 0 |  |  | 3613.44 |  | 6d | [5 empty] | 3613.44 |  | 100% |  | 3613.44 | 3613.44
67 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d | Employee I | 3613.44 | 0 | 0 | 0 | 3613.44 | 2014-03-07 10:00 | 6d | 3613.44 | 0 | 0 | 0 | 0 | 3613.44 | 0 | 100% | Finished | 3613.44 | 3613.44 | 100 | 100 | 100 | 100 | 100 | 100
87 | account statement | 2014-01-24 15:00 | 2014-03-31 12:00 | 45d 6h |  |  | 0 |  |  | 15044.8 |  | 63d | [5 empty] | 12936.96 |  | 85.99% |  | 12936.96 | 15044.8
68 | build/technical design | 2014-01-24 15:00 | 2014-02-07 15:00 | 10d | Employee F[0.50 #1];Employee L[0.50 #1] | 6022.4 | 0 | 0 | 0 | 6022.4 | 2014-02-10 08:00 | 10d | 6022.4 | 0 | 0 | 0 | 0 | 6022.4 | 0 | 100% | Finished | 6022.4 | 6022.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | ABAP | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-02-20 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
70 | UT | 2014-02-13 08:00 | 2014-02-14 17:00 | 2d | Employee F;Employee L | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-04-02 08:00 | 1d | 1204.48 | 1204.48 | 1d | 0 | 0 | 1204.48 | 1204.48 | 50% | Started | 1204.48 | 2408.96 | 100 | 50 | 50 | 100 | 50 | 50
71 | spec proxy | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
72 | ABAP proxy | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
73 | UT proxy | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-04 08:00 | 2h | 150.56 | 451.68 | 6h | 0 | 0 | 150.56 | 451.68 | 25% | Started | 150.56 | 602.24 | 100 | 25 | 25 | 100 | 25 | 25
74 | spec wrapper core | 2014-03-24 13:00 | 2014-03-26 12:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-20 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
75 | ABAP wrapper core | 2014-03-26 13:00 | 2014-03-27 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
76 | UT wrapper core | 2014-03-27 13:00 | 2014-03-28 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-07 08:00 | 2h | 150.56 | 451.68 | 6h | 0 | 0 | 150.56 | 451.68 | 25% | Started | 150.56 | 602.24 | 100 | 25 | 25 | 100 | 25 | 25
77 | email functionality | 2014-03-28 13:00 | 2014-03-31 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
173 | monitoring and reporting | 2014-01-29 08:00 | 2014-03-05 15:00 | 25d 6h |  |  | 0 |  |  | 31228.56 |  | 71d | [5 empty] | 27374.16 |  | 89.45% |  | 27933.0479 | 31228.56
78 | build/technical design | 2014-01-29 08:00 | 2014-02-03 17:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-29 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
79 | ABAP | 2014-02-06 08:00 | 2014-02-12 17:00 | 5d | ABAP | 3750 | 0 | 0 | 0 | 3750 | 2014-02-06 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
80 | UT | 2014-02-13 08:00 | 2014-02-19 17:00 | 5d | Employee H;ABAP | 6761.2 | 0 | 0 | 0 | 6761.2 | 2014-02-13 08:00 | 5d | 6761.2 | 0 | 0 | 0 | 0 | 6761.2 | 0 | 100% | Finished | 6761.2 | 6761.2 | 100 | 100 | 100 | 100 | 100 | 100
81 | BI reports | 2014-02-06 15:00 | 2014-03-05 15:00 | 19d | Employee K | 18308.4 | 0 | 0 | 0 | 18308.4 | 2014-02-06 15:00 | 15d | 14454 | 3131.7 | 3d 2h | 0 | 0 | 14454 | 3131.7 | 82% | Started | 15012.8879 | 18308.4 | 100 | 78.9474 | 82 | 100 | 78.9474 | 82
174 | weekly file | 2014-03-21 08:00 | 2014-04-01 15:00 | 7d 6h |  |  | 0 |  |  | 3219.2 |  | 34d | [5 empty] | 1623.25 |  | 42.59% |  | 1370.9096 | 3219.2
89 | build/technical design | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-21 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
90 | ABAP | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
91 | UT | 2014-03-25 08:00 | 2014-03-25 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-25 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
92 | build/technical design | 2014-03-28 15:00 | 2014-03-31 10:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 15:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 3.0112 | 301.12 | 100 | 25 | 1 | 100 | 25 | 1
93 | setup autosys | 2014-03-31 15:00 | 2014-04-01 15:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-03-31 15:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
175 | monthly file | 2014-03-31 10:00 | 2014-04-01 17:00 | 1d 6h |  |  | 0 |  |  | 1505.62 |  | 27d 6h | [5 empty] | 195.73 |  | 1% |  | 15.0562 | 1505.62
94 | build/technical design | 2014-03-31 10:00 | 2014-03-31 15:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 10:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 3.0112 | 301.12 | 100 | 25 | 1 | 100 | 25 | 1
95 | setup autosys | 2014-03-31 15:00 | 2014-04-01 17:00 | 1d 2h | Employee D | 1204.5 | 0 | 0 | 0 | 1204.5 | 2014-04-01 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 12.045 | 1204.5 | 100 | 10 | 1 | 100 | 10 | 1
176 | list | 2014-03-26 08:00 | 2014-03-28 15:00 | 2d 6h |  |  | 0 |  |  | 1579.48 |  | 31d | [5 empty] | 620.71 |  | 31.12% |  | 491.5644 | 1579.48
96 | build/technical design | 2014-03-26 08:00 | 2014-03-26 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-26 08:00 | 6h | 451.68 | 75.28 | 1h | 0 | 0 | 451.68 | 75.28 | 80% | Started | 481.792 | 602.24 | 100 | 75 | 80 | 100 | 75 | 80
97 | ABAP | 2014-03-27 08:00 | 2014-03-27 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-27 08:00 | 1h | 93.75 | 9281.25 | 12d 3h | 0 | 0 | 93.75 | 9281.25 | 1% | Started | 3.75 | 375 | 100 | 25 | 1 | 100 | 25 | 1
98 | UT | 2014-03-27 15:00 | 2014-03-28 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-28 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
177 | migration program | 2014-03-21 08:00 | 2014-04-07 17:00 | 12d |  |  | 0 |  |  | 7522.4 |  | 33d | [5 empty] | 6468.48 |  | 84.79% |  | 6378.144 | 7522.4
99 | build/technical design | 2014-03-21 08:00 | 2014-04-01 17:00 | 8d | Employee H | 4817.92 | 0 | 0 | 0 | 4817.92 | 2014-03-24 08:00 | 8d | 4817.92 | 0 | 0 | 0 | 0 | 4817.92 | 0 | 100% | Finished | 4817.92 | 4817.92 | 100 | 100 | 100 | 100 | 100 | 100
100 | ABAP | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-04-03 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
101 | UT | 2014-04-04 08:00 | 2014-04-07 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-07 08:00 | 2h | 150.56 | 2860.64 | 4d 6h | 0 | 0 | 150.56 | 2860.64 | 5% | Started | 60.224 | 1204.48 | 100 | 12.5 | 5 | 100 | 12.5 | 5
178 | send DMS file via e-mail | 2014-03-14 08:00 | 2014-03-27 15:00 | 9d 6h |  |  | 0 |  |  | 7463.06 |  | 15d | [5 empty] | 5025.56 |  | 80.4% |  | 6000.5599 | 7463.06
102 | WSDL update | 2014-03-14 08:00 | 2014-03-14 10:00 | 2h | Java;Employee I | 338.06 | 0 | 0 | 0 | 338.06 | 2014-04-17 08:00 | 2h | 338.06 | 0 | 0 | 0 | 0 | 338.06 | 0 | 100% | Finished | 338.06 | 338.06 | 100 | 100 | 100 | 100 | 100 | 100
103 | get cert / encrypt | 2014-03-14 10:00 | 2014-03-21 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-04-17 08:00 | 4d 2h | 3187.5 | 375 | 4h | 0 | 0 | 3187.5 | 375 | 90% | Started | 3374.9999 | 3750 | 100 | 85 | 90 | 100 | 85 | 90
104 | error handling | 2014-03-21 10:00 | 2014-03-25 10:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-04-24 08:00 | 1d | 750 | 93.75 | 1h | 0 | 0 | 750 | 93.75 | 90% | Started | 1350 | 1500 | 100 | 50 | 90 | 100 | 50 | 90
105 | UT java team | 2014-03-25 10:00 | 2014-03-27 15:00 | 2d 4h | Java | 1875 | 0 | 0 | 0 | 1875 | 2014-04-28 08:00 | 1d | 750 | 750 | 1d | 0 | 0 | 750 | 750 | 50% | Started | 937.5 | 1875 | 100 | 40 | 50 | 100 | 40 | 50
179 | feedback | 2014-03-11 15:00 | 2014-04-04 10:00 | 17d 4h |  |  | 0 |  |  | 29314.4 |  | 40d | [5 empty] | 30141.08 |  | 100% |  | 29314.4 | 29314.4
106 | build/technical design | 2014-03-13 08:00 | 2014-03-13 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
107 | ABAP | 2014-03-14 08:00 | 2014-03-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
108 | UT | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
109 | build/technical design | 2014-03-11 15:00 | 2014-03-12 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-12 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
110 | ABAP | 2014-03-21 15:00 | 2014-03-24 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-13 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 375 | 375 | 100 | 200 | 100 | 100 | 200 | 100
111 | UT | 2014-03-24 10:00 | 2014-03-24 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 400 | 100 | 100 | 400 | 100
112 | build/technical design | 2014-03-14 08:00 | 2014-03-14 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
113 | ABAP | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-14 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
114 | UT | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
115 | build/technical design | 2014-03-12 10:00 | 2014-03-13 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
116 | ABAP | 2014-03-13 10:00 | 2014-03-14 10:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
117 | UT | 2014-03-14 10:00 | 2014-03-17 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
118 | build/technical design | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
119 | ABAP | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
120 | UT | 2014-03-17 13:00 | 2014-03-17 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
121 | build/technical design | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-18 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
122 | ABAP | 2014-03-17 15:00 | 2014-03-18 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-18 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
123 | UT | 2014-03-18 10:00 | 2014-03-18 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-19 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
124 | build/technical design | 2014-03-18 08:00 | 2014-03-18 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
125 | ABAP | 2014-03-19 08:00 | 2014-03-19 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-19 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
126 | UT | 2014-03-20 08:00 | 2014-03-20 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
127 | build/technical design | 2014-03-18 13:00 | 2014-03-18 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
128 | ABAP | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
129 | UT | 2014-03-19 13:00 | 2014-03-19 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
130 | build/technical design | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
131 | ABAP | 2014-03-19 13:00 | 2014-03-19 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
132 | UT | 2014-03-20 08:00 | 2014-03-20 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
133 | build/technical design | 2014-03-19 15:00 | 2014-03-20 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-20 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
134 | ABAP | 2014-03-20 10:00 | 2014-03-20 15:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-21 10:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
135 | UT | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-24 15:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
136 | import WSDL | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
137 | spec proxy | 2014-03-14 08:00 | 2014-03-17 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-17 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
138 | ABAP proxy | 2014-03-18 08:00 | 2014-03-18 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-21 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
139 | UT proxy | 2014-03-18 15:00 | 2014-03-20 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-21 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
140 | spec wrapper core | 2014-03-18 08:00 | 2014-03-19 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-21 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
141 | ABAP wrapper core | 2014-03-20 08:00 | 2014-03-20 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-23 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
142 | UT wrapper core | 2014-03-20 15:00 | 2014-03-24 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-23 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
143 | spec proxy | 2014-03-18 08:00 | 2014-03-20 17:00 | 3d | Employee F[0.50 #1] | 903.36 | 0 | 0 | 0 | 903.36 | 2014-04-21 08:00 | 3d | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
144 | ABAP proxy | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-04-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
145 | UT proxy | 2014-03-24 10:00 | 2014-03-26 10:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-25 10:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
146 | spec wrapper core | 2014-03-21 08:00 | 2014-03-26 17:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-24 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
147 | ABAP wrapper core | 2014-03-27 08:00 | 2014-03-28 12:00 | 1d 4h | ABAP | 1125 | 0 | 0 | 0 | 1125 | 2014-04-30 08:00 | 1d 4h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
148 | UT wrapper core | 2014-03-28 13:00 | 2014-04-03 12:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
149 | content | 2014-03-20 10:00 | 2014-03-20 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
150 | UT | 2014-03-20 13:00 | 2014-03-20 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
151 | content | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
152 | UT | 2014-03-21 08:00 | 2014-03-21 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
153 | content | 2014-03-21 10:00 | 2014-03-21 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 10:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
154 | UT | 2014-03-21 13:00 | 2014-03-21 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 13:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
155 | build/technical design | 2014-03-17 10:00 | 2014-03-20 10:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-17 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
156 | java | 2014-03-20 10:00 | 2014-03-27 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-03-20 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
157 | UT | 2014-03-27 10:00 | 2014-04-04 10:00 | 6d | Employee F[0.50 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-27 10:00 | 6d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
180 | performance report | 2014-05-05 08:00 | 2014-05-14 17:00 | 8d |  |  | 0 |  |  | 4817.92 |  | 3d | [5 empty] | 150.56 |  | 0.625% |  | 30.112 | 1806.72
158 | build/technical design | 2014-05-05 08:00 | 2014-05-06 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-05 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
159 | EAI | 2014-05-07 08:00 | 2014-05-09 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-07 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 18.0672 | 602.24 | 100 | 4.1667 | 1 | 100 | 4.1667 | 1
160 | UT | 2014-05-12 08:00 | 2014-05-14 17:00 | 3d | Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 3d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | preparation IT test strategy | 2014-02-04 08:00 | 2014-02-17 17:00 | 10d |  |  | 0 |  |  | 3011.2 |  | 10d | [5 empty] | 3011.2 |  | 100% |  | 3011.2 | 3011.2
161 | preparation core | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
162 | preparation migration | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
163 | preparation interfacing | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
164 | preparation reporting | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
165 | preparation interfacing | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
182 | service preparation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 2890.8 |  | 100% |  | 2890.8 | 2890.8
166 | service manual draft | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
167 | SDM validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
168 | TCS validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
183 | build phase - validation | 2014-04-08 08:00 | 2014-04-09 17:00 | 2d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 361.35 |  | 1% |  | 28.908 | 2890.8
169 | program manager validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
170 | SCM validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
171 | information security validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
172 | end of build | 2014-04-09 17:00 | 2014-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | implement | 2013-10-25 08:00 | 2014-05-19 17:00 | 147d |  |  | 0 |  |  | 120846.38 |  | 139d | [5 empty] | 133354.5 |  | 62.77% |  | 75850.2803 | 116838.46
250 | certificates | 2014-04-02 10:00 | 2014-05-08 17:00 | 26d 6h |  |  | 0 |  |  | 17344.8 |  | 9d | [5 empty] | 4095.3 |  | 70% |  | 12141.3598 | 16381.2
185 | certificates on acceptance | 2014-04-02 10:00 | 2014-04-15 10:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-04-25 08:00 | 2d | 1927.2 | 843.15 | 7h | 0 | 0 | 1927.2 | 843.15 | 70% | Started | 6070.6799 | 8672.4 | 100 | 22.2222 | 70 | 100 | 22.2222 | 70
186 | certificates on production | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-05-06 08:00 | 2d 2h | 2168.1 | 963.6 | 1d | 0 | 0 | 2168.1 | 963.6 | 70% | Started | 6070.6799 | 7708.8 | 100 | 25 | 70 | 100 | 25 | 70
251 | integration testing release 1 | 2014-02-06 10:00 | 2014-03-20 17:00 | 30d 6h |  |  | 0 |  |  | 26287.92 |  | 54d | [5 empty] | 19557.84 |  | 69.46% |  | 18260.0047 | 26287.92
187 | backend | 2014-03-03 15:00 | 2014-03-05 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-04 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
188 | backend and extract | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H;Employee K | 3131.68 | 0 | 0 | 0 | 3131.68 | 2014-03-06 15:00 | 2d | 3131.68 | 0 | 0 | -4.5475e-13 | 0 | 3131.68 | 0 | 100% | Finished | 3131.68 | 3131.68 | 100 | 100 | 100 | 100 | 100 | 100
189 | performance testing monitoring backend | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-06 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
190 | monitoring BI | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d | Employee K | 4818 | 0 | 0 | 0 | 4818 | 2014-03-12 08:00 | 3d | 2890.8 | 2890.8 | 3d | 0 | 0 | 2890.8 | 2890.8 | 50% | Started | 2409 | 4818 | 100 | 60 | 50 | 100 | 60 | 50
191 | weekly files | 2014-02-06 10:00 | 2014-02-11 17:00 | 3d 6h | Employee G | 2258.4 | 0 | 0 | 0 | 2258.4 | 2014-03-04 08:00 | 3d 6h | 2258.4 | 0 | 0 | 0 | 0 | 2258.4 | 0 | 100% | Finished | 2258.4 | 2258.4 | 100 | 100 | 100 | 100 | 100 | 100
192 | monthly files | 2014-02-21 08:00 | 2014-02-25 12:00 | 2d 4h | Employee G | 1505.6 | 0 | 0 | 0 | 1505.6 | 2014-02-21 08:00 | 2d 4h | 1505.6 | 0 | 0 | 0 | 0 | 1505.6 | 0 | 100% | Finished | 1505.6 | 1505.6 | 100 | 100 | 100 | 100 | 100 | 100
193 | duplicate documents | 2014-03-05 08:00 | 2014-03-06 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-08 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
194 | current saldo | 2014-03-03 08:00 | 2014-03-04 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-04 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
195 | account statement | 2014-03-07 08:00 | 2014-03-11 17:00 | 3d | Employee F | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-04-10 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 18.0672 | 1806.72 | 100 | 4.1667 | 1 | 100 | 4.1667 | 1
196 | defect core weekly | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-10 08:00 | 2d 6h | 1656.16 | 150.56 | 2h | 0 | 0 | 1656.16 | 150.56 | 90% | Started | 1626.048 | 1806.72 | 100 | 91.6667 | 90 | 100 | 91.6667 | 90
197 | defect core monthly | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 2d 6h | 1656.16 | 150.56 | 2h | 0 | 0 | 1656.16 | 150.56 | 90% | Started | 1626.048 | 1806.72 | 100 | 91.6667 | 90 | 100 | 91.6667 | 90
198 | defect interfacing | 2014-03-12 08:00 | 2014-03-13 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
199 | defect monitoring | 2014-03-07 15:00 | 2014-03-11 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-10 15:00 | 2d 6h | 1656.16 | 150.56 | 2h | 0 | 0 | 1656.16 | 150.56 | 90% | Started | 1084.032 | 1204.48 | 100 | 137.5 | 90 | 100 | 137.5 | 90
200 | defect BI reporting | 2014-03-19 08:00 | 2014-03-20 17:00 | 2d | Employee K | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-03-19 08:00 | 1d | 963.6 | 963.6 | 1d | 0 | 0 | 963.6 | 963.6 | 50% | Started | 963.6 | 1927.2 | 100 | 50 | 50 | 100 | 50 | 50
252 | integration testing release 2 | 2014-04-01 08:00 | 2014-04-23 17:00 | 17d |  |  | 0 |  |  | 15056 |  | 26d | [5 empty] | 4592.08 |  | 30.57% |  | 4602.6192 | 15056
201 | feedback | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee F[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-05-07 08:00 | 7d | 2107.84 | 715.16 | 2d 3h | 0 | 0 | 2107.84 | 715.16 | 75% | Started | 2258.4 | 3011.2 | 100 | 70 | 75 | 100 | 70 | 75
202 | migration | 2014-04-08 08:00 | 2014-04-21 17:00 | 10d | Employee H[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-09 08:00 | 1h | 37.64 | 2973.56 | 9d 7h | 0 | 0 | 37.64 | 2973.56 | 1.25% | Started | 37.64 | 3011.2 | 100 | 1.25 | 1.25 | 100 | 1.25 | 1.25
203 | list batch testing | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | Employee G[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-02 08:00 | 1h | 37.64 | 3726.36 | 12d 3h | 0 | 0 | 37.64 | 3726.36 | 1% | Started | 6.0224 | 602.24 | 100 | 6.25 | 1 | 100 | 6.25 | 1
204 | core | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee G[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-04 08:00 | 7d | 2107.84 | 715.16 | 2d 3h | 0 | 0 | 2107.84 | 715.16 | 75% | Started | 2258.4 | 3011.2 | 100 | 70 | 75 | 100 | 70 | 75
205 | mail encryption | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee I | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-30 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
206 | defect core | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee G | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
207 | defect interfacing | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 |  | 0 | 0 | 1204.48 | 2d | 0 | 0 | 0 | 1204.48 | 0% | Not Started | 0 | 1204.48 | 100 |  | 0 | 100 |  | 0
208 | defect migration | 2014-04-22 08:00 | 2014-04-23 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-23 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
209 | defect mail encryption | 2014-04-02 10:00 | 2014-04-04 10:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
253 | p2p testing | 2014-04-15 08:00 | 2014-04-22 17:00 | 6d |  |  | 0 |  |  | 6022.4 |  | 17d | [5 empty] | 752.8 |  | 1% |  | 60.224 | 6022.4
210 | p2p weekly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-22 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
211 | p2p monthly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-05-05 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
212 | p2p current saldo | 2014-04-15 08:00 | 2014-04-15 17:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
213 | p2p duplicate documents | 2014-04-16 10:00 | 2014-04-17 10:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-16 08:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
214 | p2p account statement | 2014-04-17 13:00 | 2014-04-18 12:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-17 13:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
215 | p2p feedback | 2014-04-18 15:00 | 2014-04-21 15:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 15:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
254 | business acceptance testing release 1 | 2013-10-25 08:00 | 2014-04-04 12:00 | 115d 4h |  |  | 0 |  |  | 45815.04 |  | 139d | [5 empty] | 66177.28 |  | 83.47% |  | 38240.7926 | 45815.04
216 | part 1 - information lists | 2014-02-17 08:00 | 2014-03-28 12:00 | 29d 4h | Employee M | 18771.44 | 0 | 0 | 0 | 18771.44 | 2014-02-17 08:00 | 27d | 17180.64 | 874.94 | 1d 3h | -3.638e-12 | 0 | 17180.64 | 874.94 | 95% | Started | 17832.8678 | 18771.44 | 100 | 91.5254 | 95 | 100 | 91.5254 | 95
217 | part 2 - interface | 2013-10-25 08:00 | 2013-10-29 17:00 | 3d | Employee N | 1908.96 | 0 | 0 | 0 | 1908.96 | 2013-10-25 08:00 | 48d | 30543.36 | 3420.22 | 5d 3h | 0 | 0 | 30543.36 | 3420.22 | 90% | Started | 1718.064 | 1908.96 | 100 | 1600 | 90 | 100 | 1600 | 90
218 | part 3 - reporting | 2014-02-10 08:00 | 2014-04-04 12:00 | 39d 4h | Employee P | 25134.64 | 0 | 0 | 0 | 25134.64 | 2014-02-10 08:00 | 29d | 18453.28 | 6363.2 | 10d | -3.638e-12 | 0 | 18453.28 | 6363.2 | 74.36% | Started | 18689.8609 | 25134.64 | 100 | 73.4177 | 74.359 | 100 | 73.4177 | 74.359
255 | business acceptance testing release 2 | 2014-04-21 08:00 | 2014-04-22 17:00 | 2d |  |  | 0 |  |  | 2545.28 |  | 57d | [5 empty] | 38179.2 |  | 100% |  | 2545.28 | 2545.28
219 | test definition | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
220 | test data | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
221 | test execution | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee N;Employee O | 1272.64 | 0 | 0 | 0 | 1272.64 | 2014-04-22 08:00 | 11d | 13999.04 | 0 | 0 | 0 | 0 | 13999.04 | 0 | 100% | Finished | 1272.64 | 1272.64 | 100 | 1100 | 100 | 100 | 1100 | 100
256 | service preparation | 2014-03-24 08:00 | 2014-04-23 17:00 | 23d |  |  | 0 |  |  | 3208.46 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3208.46
227 | SLA review | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
228 | service budget agreement | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
229 | production handbook | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
230 | service manual | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 2h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
231 | SCM validation | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 240.9 | 100 |  | 0 | 100 |  | 0
232 | CIO validation | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 |  | 0 | 0 | 558.56 | 1d | 0 | 0 | 0 | 558.56 | 0% | Not Started | 0 | 558.56 | 100 |  | 0 | 100 |  | 0
257 | go-no go meeting | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
233 | formal validation | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | deploy on production | 2013-10-25 08:00 | 2014-05-16 17:00 | 146d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1522.16
234 | go live | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | PIN testing IT | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
236 | PIN testing business | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 |  | 0 | 0 | 558.56 | 1d | 0 | 0 | 0 | 558.56 | 0% | Not Started | 0 | 558.56 | 100 |  | 0 | 100 |  | 0
259 | validation | 2014-05-16 17:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
237 | steerco validation | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | end of implement | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | close | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 9731.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
261 | hand-over preparation | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
239 | project charter as built | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h | Employee A;Employee B | 2283.24 | 0 | 0 | 0 | 2283.24 |  | 0 | 0 | 2283.24 | 1d 4h | 0 | 0 | 0 | 2283.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | blueprint as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee J;Employee M;Employee N | 2751.04 | 0 | 0 | 0 | 2751.04 |  | 0 | 0 | 2751.04 | 1d | 0 | 0 | 0 | 2751.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | technical design as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee F;Employee G;Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 1d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | hand-over | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1927.2 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | service manual | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | CMDB check | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee C | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | SCM validation | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | project evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h |  |  | 0 |  |  | 722.7 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
245 | customer satisfaction survey | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | project team briefing | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | suppliers evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | close phase | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 240.9 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
248 | program manager validation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | end of project | 2014-05-19 17:00 | 2014-05-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-05-21 22:00 |  | TP Name | Tracking 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Debt Collection System | 2013-10-24 08:00 | 2014-05-20 12:00 | 148d 4h |  |  | 0 |  |  | 458112.3684 |  | 151d | [5 empty] | 475424.1361 |  | 92.43% |  | 423433.7021 | 458112.3684
9 | define | 2013-10-24 08:00 | 2013-12-18 17:00 | 40d |  |  | 0 |  |  | 41864.71 |  | 39d 7h | [5 empty] | 41864.71 |  | 100% |  | 41864.71 | 41864.71
1 | kick-off meeting | 2013-10-24 08:00 | 2013-10-24 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-10-24 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
266 | project charter set | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  |  | 0 |  |  | 37495.44 |  | 24d | [5 empty] | 37495.44 |  | 100% |  | 37495.44 | 37495.44
2 | project charter (scope definition) | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d | Employee A;Employee B | 36531.84 | 0 | 0 | 0 | 36531.84 | 2013-11-04 08:00 | 24d | 36531.84 | 0 | 0 | 0 | 0 | 36531.84 | 0 | 100% | Finished | 36531.84 | 36531.84 | 100 | 100 | 100 | 100 | 100 | 100
3 | project security risks | 2013-11-13 08:00 | 2013-11-13 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2013-11-13 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
267 | project charter - communication and validation | 2013-11-25 08:00 | 2013-12-18 17:00 | 18d |  |  | 0 |  |  | 3810.71 |  | 17d 7h | [5 empty] | 3810.71 |  | 100% |  | 3810.71 | 3810.71
4 | inform IT governance | 2013-11-25 08:00 | 2013-11-25 09:00 | 1h | Employee B;Employee C | 240.9 | 0 | 0 | 0 | 240.9 | 2013-11-25 08:00 | 1h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
5 | send info | 2013-11-28 08:00 | 2013-11-28 17:00 | 1d | Employee B;Employee D | 1927.2 | 0 | 0 | 0 | 1927.2 | 2013-11-28 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 100 | 100 | 100 | 100 | 100
6 | send project charter for validation + delivery board validation | 2013-12-13 08:00 | 2013-12-16 09:00 | 1d 1h | Employee B | 1084.05 | 0 | 0 | 0 | 1084.05 | 2013-12-13 08:00 | 1d 1h | 1084.05 | 0 | 0 | 0 | 0 | 1084.05 | 0 | 100% | Finished | 1084.05 | 1084.05 | 100 | 100 | 100 | 100 | 100 | 100
7 | business validation | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-12-17 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
8 | end of define | 2013-12-18 17:00 | 2013-12-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
22 | design | 2013-11-25 08:00 | 2014-02-10 17:00 | 56d |  |  | 0 |  |  | 107215.84 |  | 55d 7h | [5 empty] | 100711.54 |  | 100% |  | 107215.84 | 107215.84
15 | blueprint set | 2013-11-25 08:00 | 2014-01-23 17:00 | 44d |  |  | 0 |  |  | 103826.72 |  | 51d | [5 empty] | 98045.12 |  | 100% |  | 103826.72 | 103826.72
10 | functional analysis List/file creation | 2013-12-02 08:00 | 2014-01-03 17:00 | 25d | Employee G | 15056 | 0 | 0 | 0 | 15056 | 2013-12-02 08:00 | 25d | 15056 | 0 | 0 | 0 | 0 | 15056 | 0 | 100% | Finished | 15056 | 15056 | 100 | 100 | 100 | 100 | 100 | 100
11 | functional analysis Monitoring | 2013-11-25 08:00 | 2014-01-08 17:00 | 33d | Employee H | 19873.92 | 0 | 0 | 0 | 19873.92 | 2013-11-25 08:00 | 33d | 19873.92 | 0 | 0 | -3.638e-12 | 0 | 19873.92 | 0 | 100% | Finished | 19873.92 | 19873.92 | 100 | 100 | 100 | 100 | 100 | 100
12 | functional analysis Interfacing | 2013-11-25 08:00 | 2014-01-03 17:00 | 30d | Employee F;Employee I | 36134.4 | 0 | 0 | 0 | 36134.4 | 2013-11-25 08:00 | 30d | 36134.4 | 0 | 0 | 0 | 0 | 36134.4 | 0 | 100% | Finished | 36134.4 | 36134.4 | 100 | 100 | 100 | 100 | 100 | 100
13 | architecture analysis | 2013-11-25 08:00 | 2013-12-27 17:00 | 25d | Employee E | 24090 | 0 | 0 | 0 | 24090 | 2013-11-25 08:00 | 25d | 24090 | 0 | 0 | 0 | 0 | 24090 | 0 | 100% | Finished | 24090 | 24090 | 100 | 100 | 100 | 100 | 100 | 100
14 | budget &amp; planning for development + master test chapter | 2014-01-13 08:00 | 2014-01-23 17:00 | 9d | Employee B | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-01-30 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 100% | Finished | 8672.4 | 8672.4 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
21 | design phase - validations | 2014-01-21 08:00 | 2014-02-10 17:00 | 15d |  |  | 0 |  |  | 3389.12 |  | 14d 7h | [5 empty] | 2666.42 |  | 100% |  | 3389.12 | 3389.12
16 | presentation to Business part 1 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G;Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-21 08:00 | 4h | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
17 | presentation to Business part 2 | 2014-01-31 08:00 | 2014-01-31 12:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-01-31 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
18 | send to delivery board + IT governance validation | 2014-02-07 08:00 | 2014-02-10 17:00 | 2d | Employee B | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-02-07 08:00 | 1d 2h | 1204.5 | 0 | 0 | 0 | 0 | 1204.5 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 62.5 | 100 | 100 | 62.5 | 100
19 | business validation | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-02-07 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
20 | end of design | 2014-02-10 17:00 | 2014-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | build | 2013-12-27 15:00 | 2014-05-14 17:00 | 98d 2h |  |  | 0 |  |  | 178453.6384 |  | 84d | [5 empty] | 170068.9661 |  | 95.72% |  | 170822.0056 | 178453.6384
32 | weekly file | 2014-01-02 15:00 | 2014-03-11 17:00 | 48d 2h |  |  | 0 |  |  | 19499.28 |  | 29d | [5 empty] | 18611.852 |  | 100% |  | 19499.28 | 19499.28
23 | build/technical design | 2014-01-02 15:00 | 2014-01-09 15:00 | 5d | Employee G[0.60 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-01-30 08:00 | 5d 4h | 1987.392 | 0 | 0 | 0 | 0 | 1987.392 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 110 | 100 | 100 | 110 | 100
24 | ABAP | 2014-01-09 15:00 | 2014-01-22 15:00 | 9d | ABAP | 6750 | 0 | 0 | 0 | 6750 | 2014-02-06 08:00 | 9d | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 100% | Finished | 6750 | 6750 | 100 | 100 | 100 | 100 | 100 | 100
25 | UT program in general | 2014-01-23 15:00 | 2014-01-27 10:00 | 1d 4h | Employee G | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
26 | UT submission file | 2014-01-31 15:00 | 2014-02-06 10:00 | 3d 4h | Employee G | 2107.84 | 0 | 0 | 0 | 2107.84 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2107.84 | 2107.84 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | UT clearing file | 2014-01-27 10:00 | 2014-01-31 10:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
28 | UT other treatment file | 2014-01-31 10:00 | 2014-02-06 10:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-26 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
29 | business UT submission | 2014-03-05 13:00 | 2014-03-10 12:00 | 3d | Employee M | 1908.96 | 0 | 0 | 0 | 1908.96 | 2014-02-25 08:00 | 3h | 238.62 | 0 | 0 | 0 | 0 | 238.62 | 0 | 100% | Finished | 1908.96 | 1908.96 | 100 | 12.5 | 100 | 100 | 12.5 | 100
30 | UT sending via e-mail | 2014-03-11 08:00 | 2014-03-11 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
31 | build/technical design | 2014-01-22 15:00 | 2014-01-23 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
82 | monthly file | 2013-12-27 15:00 | 2014-02-14 17:00 | 35d 2h |  |  | 0 |  |  | 6713.344 |  | 33d | [5 empty] | 6277.012 |  | 100% |  | 6713.344 | 6713.344
33 | build/technical design | 2013-12-27 15:00 | 2014-01-02 15:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-24 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
34 | ABAP | 2014-01-30 08:00 | 2014-02-03 12:00 | 2d 4h | ABAP[0.80 #1] | 1500 | 0 | 0 | 0 | 1500 | 2014-01-30 08:00 | 2d 4h | 1500 | 0 | 0 | 2.2352e-05 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
35 | UT | 2014-02-03 13:00 | 2014-02-11 17:00 | 6d 4h | Employee G[0.40 #1] | 1565.824 | 0 | 0 | 0 | 1565.824 | 2014-02-03 08:00 | 7d | 1686.272 | 0 | 0 | 2.5127e-05 | 0 | 1686.272 | 0 | 100% | Finished | 1565.824 | 1565.824 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
36 | business UT | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee M | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-18 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
37 | UT sending via e-mail | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
83 | authorization check | 2014-01-24 08:00 | 2014-03-24 12:00 | 41d 4h |  |  | 0 |  |  | 15386.2 |  | 38d | [5 empty] | 15386.2 |  | 100% |  | 15386.2 | 15386.2
38 | IRIS-SC | 2014-03-13 08:00 | 2014-03-18 17:00 | 4d | Java | 3000 | 0 | 0 | 0 | 3000 | 2014-03-13 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
39 | build/technical design | 2014-01-24 08:00 | 2014-01-24 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-24 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
40 | ABAP | 2014-01-27 08:00 | 2014-02-10 17:00 | 11d | ABAP | 8250 | 0 | 0 | 0 | 8250 | 2014-01-27 08:00 | 11d | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 100% | Finished | 8250 | 8250 | 100 | 100 | 100 | 100 | 100 | 100
41 | UT | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
42 | build/technical design | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
43 | ABAP | 2014-03-19 13:00 | 2014-03-20 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
44 | UT | 2014-03-20 13:00 | 2014-03-21 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | import WSDL | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-02-13 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
46 | ESB (pass BP to basic) | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
84 | send DMS file via e-mail | 2014-02-05 15:00 | 2014-03-10 17:00 | 23d 2h |  |  | 0 |  |  | 13548.8944 |  | 16d | [5 empty] | 13580.512 |  | 100% |  | 13548.8944 | 13548.8944
47 | build/technical design | 2014-02-17 08:00 | 2014-03-07 10:00 | 14d 2h | Employee I[0.07 #1] | 600.7344 | 0 | 0 | 0 | 600.7344 | 2014-02-17 08:00 | 15d | 632.352 | 0 | 0 | 2.6922e-06 | 0 | 632.352 | 0 | 100% | Finished | 600.7344 | 600.7344 | 100 | 105.2632 | 100 | 100 | 105.2632 | 100
48 | import WSDL | 2014-02-05 15:00 | 2014-02-06 10:00 | 4h | EAI | 301.12 | 0 | 0 | 0 | 301.12 | 2014-02-17 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
49 | build/technical design | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
50 | EAI | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | UT | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
52 | build/technical design | 2014-02-18 08:00 | 2014-02-18 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
53 | EAI | 2014-02-19 08:00 | 2014-02-19 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
54 | UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
55 | design | 2014-02-19 08:00 | 2014-02-20 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | build | 2014-02-21 08:00 | 2014-02-25 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-21 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
57 | queue handling | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | UT | 2014-03-03 08:00 | 2014-03-06 17:00 | 4d | EAI | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-03-03 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
59 | deployment | 2014-03-07 08:00 | 2014-03-10 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-07 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
85 | duplicates | 2014-02-12 13:00 | 2014-03-26 17:00 | 30d 4h |  |  | 0 |  |  | 5261.2 |  | 11d | [5 empty] | 5261.2 |  | 100% |  | 5261.2 | 5261.2
60 | build/technical design | 2014-02-12 13:00 | 2014-02-14 12:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-12 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
61 | java | 2014-03-19 08:00 | 2014-03-21 17:00 | 3d | Java | 2250 | 0 | 0 | 0 | 2250 | 2014-02-19 08:00 | 3d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 2250 | 2250 | 100 | 100 | 100 | 100 | 100 | 100
62 | UT | 2014-03-24 08:00 | 2014-03-26 17:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-24 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
86 | current saldo | 2014-02-11 08:00 | 2014-02-20 17:00 | 8d |  |  | 0 |  |  | 3943.04 |  | 7d 4h | [5 empty] | 3386.26 |  | 100% |  | 3943.04 | 3943.04
63 | build/technical design | 2014-02-11 08:00 | 2014-02-12 12:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-11 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
64 | java | 2014-02-14 13:00 | 2014-02-18 12:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-02-17 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
65 | UT | 2014-02-18 13:00 | 2014-02-19 17:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
66 | business UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-20 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
88 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d |  |  | 0 |  |  | 3613.44 |  | 6d | [5 empty] | 3613.44 |  | 100% |  | 3613.44 | 3613.44
67 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d | Employee I | 3613.44 | 0 | 0 | 0 | 3613.44 | 2014-03-07 10:00 | 6d | 3613.44 | 0 | 0 | 0 | 0 | 3613.44 | 0 | 100% | Finished | 3613.44 | 3613.44 | 100 | 100 | 100 | 100 | 100 | 100
87 | account statement | 2014-01-24 15:00 | 2014-03-31 12:00 | 45d 6h |  |  | 0 |  |  | 15044.8 |  | 41d | [5 empty] | 15044.8 |  | 100% |  | 15044.8 | 15044.8
68 | build/technical design | 2014-01-24 15:00 | 2014-02-07 15:00 | 10d | Employee F[0.50 #1];Employee L[0.50 #1] | 6022.4 | 0 | 0 | 0 | 6022.4 | 2014-02-10 08:00 | 10d | 6022.4 | 0 | 0 | 0 | 0 | 6022.4 | 0 | 100% | Finished | 6022.4 | 6022.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | ABAP | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-02-20 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
70 | UT | 2014-02-13 08:00 | 2014-02-14 17:00 | 2d | Employee F;Employee L | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-04-02 08:00 | 2d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
71 | spec proxy | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
72 | ABAP proxy | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
73 | UT proxy | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
74 | spec wrapper core | 2014-03-24 13:00 | 2014-03-26 12:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-20 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
75 | ABAP wrapper core | 2014-03-26 13:00 | 2014-03-27 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
76 | UT wrapper core | 2014-03-27 13:00 | 2014-03-28 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-07 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
77 | email functionality | 2014-03-28 13:00 | 2014-03-31 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
173 | monitoring and reporting | 2014-01-29 08:00 | 2014-03-05 15:00 | 25d 6h |  |  | 0 |  |  | 31228.56 |  | 25d 6h | [5 empty] | 31228.56 |  | 100% |  | 31228.56 | 31228.56
78 | build/technical design | 2014-01-29 08:00 | 2014-02-03 17:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-29 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
79 | ABAP | 2014-02-06 08:00 | 2014-02-12 17:00 | 5d | ABAP | 3750 | 0 | 0 | 0 | 3750 | 2014-02-06 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
80 | UT | 2014-02-13 08:00 | 2014-02-19 17:00 | 5d | Employee H;ABAP | 6761.2 | 0 | 0 | 0 | 6761.2 | 2014-02-13 08:00 | 5d | 6761.2 | 0 | 0 | 0 | 0 | 6761.2 | 0 | 100% | Finished | 6761.2 | 6761.2 | 100 | 100 | 100 | 100 | 100 | 100
81 | BI reports | 2014-02-06 15:00 | 2014-03-05 15:00 | 19d | Employee K | 18308.4 | 0 | 0 | 0 | 18308.4 | 2014-02-06 15:00 | 19d | 18308.4 | 0 | 0 | 0 | 0 | 18308.4 | 0 | 100% | Finished | 18308.4 | 18308.4 | 100 | 100 | 100 | 100 | 100 | 100
174 | weekly file | 2014-03-21 08:00 | 2014-04-01 15:00 | 7d 6h |  |  | 0 |  |  | 3219.2 |  | 7d 6h | [5 empty] | 3219.2 |  | 100% |  | 3219.2 | 3219.2
89 | build/technical design | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-21 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
90 | ABAP | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
91 | UT | 2014-03-25 08:00 | 2014-03-25 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-25 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
92 | build/technical design | 2014-03-28 15:00 | 2014-03-31 10:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 15:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
93 | setup autosys | 2014-03-31 15:00 | 2014-04-01 15:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-03-31 15:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
175 | monthly file | 2014-03-31 10:00 | 2014-04-01 17:00 | 1d 6h |  |  | 0 |  |  | 1505.62 |  | 1d 6h | [5 empty] | 1264.72 |  | 100% |  | 1505.62 | 1505.62
94 | build/technical design | 2014-03-31 10:00 | 2014-03-31 15:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 10:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
95 | setup autosys | 2014-03-31 15:00 | 2014-04-01 17:00 | 1d 2h | Employee D | 1204.5 | 0 | 0 | 0 | 1204.5 | 2014-04-01 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 1204.5 | 1204.5 | 100 | 80 | 100 | 100 | 80 | 100
176 | list | 2014-03-26 08:00 | 2014-03-28 15:00 | 2d 6h |  |  | 0 |  |  | 1579.48 |  | 3d | [5 empty] | 1579.48 |  | 100% |  | 1579.48 | 1579.48
96 | build/technical design | 2014-03-26 08:00 | 2014-03-26 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-26 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
97 | ABAP | 2014-03-27 08:00 | 2014-03-27 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-27 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
98 | UT | 2014-03-27 15:00 | 2014-03-28 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
177 | migration program | 2014-03-21 08:00 | 2014-04-07 17:00 | 12d |  |  | 0 |  |  | 7522.4 |  | 12d | [5 empty] | 7522.4 |  | 100% |  | 7522.4 | 7522.4
99 | build/technical design | 2014-03-21 08:00 | 2014-04-01 17:00 | 8d | Employee H | 4817.92 | 0 | 0 | 0 | 4817.92 | 2014-03-24 08:00 | 8d | 4817.92 | 0 | 0 | 0 | 0 | 4817.92 | 0 | 100% | Finished | 4817.92 | 4817.92 | 100 | 100 | 100 | 100 | 100 | 100
100 | ABAP | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-04-03 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
101 | UT | 2014-04-04 08:00 | 2014-04-07 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-07 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
178 | send DMS file via e-mail | 2014-03-14 08:00 | 2014-03-27 15:00 | 9d 6h |  |  | 0 |  |  | 7463.06 |  | 9d 4h | [5 empty] | 7463.06 |  | 100% |  | 7463.06 | 7463.06
102 | WSDL update | 2014-03-14 08:00 | 2014-03-14 10:00 | 2h | Java;Employee I | 338.06 | 0 | 0 | 0 | 338.06 | 2014-04-17 08:00 | 2h | 338.06 | 0 | 0 | 0 | 0 | 338.06 | 0 | 100% | Finished | 338.06 | 338.06 | 100 | 100 | 100 | 100 | 100 | 100
103 | get cert / encrypt | 2014-03-14 10:00 | 2014-03-21 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-04-17 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
104 | error handling | 2014-03-21 10:00 | 2014-03-25 10:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-04-24 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
105 | UT java team | 2014-03-25 10:00 | 2014-03-27 15:00 | 2d 4h | Java | 1875 | 0 | 0 | 0 | 1875 | 2014-04-28 08:00 | 2d 4h | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 1875 | 1875 | 100 | 100 | 100 | 100 | 100 | 100
179 | feedback | 2014-03-11 15:00 | 2014-04-04 10:00 | 17d 4h |  |  | 0 |  |  | 29314.4 |  | 40d | [5 empty] | 30141.08 |  | 100% |  | 29314.4 | 29314.4
106 | build/technical design | 2014-03-13 08:00 | 2014-03-13 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
107 | ABAP | 2014-03-14 08:00 | 2014-03-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
108 | UT | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
109 | build/technical design | 2014-03-11 15:00 | 2014-03-12 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-12 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
110 | ABAP | 2014-03-21 15:00 | 2014-03-24 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-13 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 375 | 375 | 100 | 200 | 100 | 100 | 200 | 100
111 | UT | 2014-03-24 10:00 | 2014-03-24 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 400 | 100 | 100 | 400 | 100
112 | build/technical design | 2014-03-14 08:00 | 2014-03-14 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
113 | ABAP | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-14 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
114 | UT | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
115 | build/technical design | 2014-03-12 10:00 | 2014-03-13 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
116 | ABAP | 2014-03-13 10:00 | 2014-03-14 10:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
117 | UT | 2014-03-14 10:00 | 2014-03-17 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
118 | build/technical design | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
119 | ABAP | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
120 | UT | 2014-03-17 13:00 | 2014-03-17 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
121 | build/technical design | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-18 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
122 | ABAP | 2014-03-17 15:00 | 2014-03-18 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-18 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
123 | UT | 2014-03-18 10:00 | 2014-03-18 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-19 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
124 | build/technical design | 2014-03-18 08:00 | 2014-03-18 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
125 | ABAP | 2014-03-19 08:00 | 2014-03-19 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-19 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
126 | UT | 2014-03-20 08:00 | 2014-03-20 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
127 | build/technical design | 2014-03-18 13:00 | 2014-03-18 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
128 | ABAP | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
129 | UT | 2014-03-19 13:00 | 2014-03-19 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
130 | build/technical design | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
131 | ABAP | 2014-03-19 13:00 | 2014-03-19 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
132 | UT | 2014-03-20 08:00 | 2014-03-20 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
133 | build/technical design | 2014-03-19 15:00 | 2014-03-20 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-20 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
134 | ABAP | 2014-03-20 10:00 | 2014-03-20 15:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-21 10:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
135 | UT | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-24 15:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
136 | import WSDL | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
137 | spec proxy | 2014-03-14 08:00 | 2014-03-17 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-17 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
138 | ABAP proxy | 2014-03-18 08:00 | 2014-03-18 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-21 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
139 | UT proxy | 2014-03-18 15:00 | 2014-03-20 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-21 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
140 | spec wrapper core | 2014-03-18 08:00 | 2014-03-19 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-21 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
141 | ABAP wrapper core | 2014-03-20 08:00 | 2014-03-20 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-23 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
142 | UT wrapper core | 2014-03-20 15:00 | 2014-03-24 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-23 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
143 | spec proxy | 2014-03-18 08:00 | 2014-03-20 17:00 | 3d | Employee F[0.50 #1] | 903.36 | 0 | 0 | 0 | 903.36 | 2014-04-21 08:00 | 3d | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
144 | ABAP proxy | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-04-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
145 | UT proxy | 2014-03-24 10:00 | 2014-03-26 10:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-25 10:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
146 | spec wrapper core | 2014-03-21 08:00 | 2014-03-26 17:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-24 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
147 | ABAP wrapper core | 2014-03-27 08:00 | 2014-03-28 12:00 | 1d 4h | ABAP | 1125 | 0 | 0 | 0 | 1125 | 2014-04-30 08:00 | 1d 4h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
148 | UT wrapper core | 2014-03-28 13:00 | 2014-04-03 12:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
149 | content | 2014-03-20 10:00 | 2014-03-20 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
150 | UT | 2014-03-20 13:00 | 2014-03-20 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
151 | content | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
152 | UT | 2014-03-21 08:00 | 2014-03-21 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
153 | content | 2014-03-21 10:00 | 2014-03-21 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 10:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
154 | UT | 2014-03-21 13:00 | 2014-03-21 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 13:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
155 | build/technical design | 2014-03-17 10:00 | 2014-03-20 10:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-17 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
156 | java | 2014-03-20 10:00 | 2014-03-27 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-03-20 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
157 | UT | 2014-03-27 10:00 | 2014-04-04 10:00 | 6d | Employee F[0.50 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-27 10:00 | 6d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
180 | performance report | 2014-05-05 08:00 | 2014-05-14 17:00 | 8d |  |  | 0 |  |  | 4817.92 |  | 13d | [5 empty] | 225.84 |  | 1% |  | 48.1792 | 4817.92
158 | build/technical design | 2014-05-05 08:00 | 2014-05-06 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-05 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
159 | EAI | 2014-05-07 08:00 | 2014-05-09 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-07 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 18.0672 | 1806.72 | 100 | 4.1667 | 1 | 100 | 4.1667 | 1
160 | UT | 2014-05-12 08:00 | 2014-05-14 17:00 | 3d | Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-12 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 18.0672 | 1806.72 | 100 | 4.1667 | 1 | 100 | 4.1667 | 1
181 | preparation IT test strategy | 2014-02-04 08:00 | 2014-02-17 17:00 | 10d |  |  | 0 |  |  | 3011.2 |  | 10d | [5 empty] | 3011.2 |  | 100% |  | 3011.2 | 3011.2
161 | preparation core | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
162 | preparation migration | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
163 | preparation interfacing | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
164 | preparation reporting | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
165 | preparation interfacing | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
182 | service preparation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 2890.8 |  | 100% |  | 2890.8 | 2890.8
166 | service manual draft | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
167 | SDM validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
168 | TCS validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
183 | build phase - validation | 2014-04-08 08:00 | 2014-04-09 17:00 | 2d |  |  | 0 |  |  | 2890.8 |  | 11d | [5 empty] | 361.35 |  | 1% |  | 28.908 | 2890.8
169 | program manager validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
170 | SCM validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
171 | information security validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
172 | end of build | 2014-04-09 17:00 | 2014-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
260 | implement | 2013-10-25 08:00 | 2014-05-19 17:00 | 147d |  |  | 0 |  |  | 120846.38 |  | 150d | [5 empty] | 162778.92 |  | 85.67% |  | 103531.1465 | 120846.38
250 | certificates | 2014-04-02 10:00 | 2014-05-08 17:00 | 26d 6h |  |  | 0 |  |  | 17344.8 |  | 19d | [5 empty] | 4577.1 |  | 75% |  | 13008.6 | 17344.8
185 | certificates on acceptance | 2014-04-02 10:00 | 2014-04-15 10:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-04-25 08:00 | 2d 4h | 2409 | 602.25 | 5h | 0 | 0 | 2409 | 602.25 | 80% | Started | 6937.9201 | 8672.4 | 100 | 27.7778 | 80 | 100 | 27.7778 | 80
186 | certificates on production | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-05-06 08:00 | 2d 2h | 2168.1 | 963.6 | 1d | 0 | 0 | 2168.1 | 963.6 | 70% | Started | 6070.6799 | 8672.4 | 100 | 25 | 70 | 100 | 25 | 70
251 | integration testing release 1 | 2014-02-06 10:00 | 2014-03-20 17:00 | 30d 6h |  |  | 0 |  |  | 26287.92 |  | 39d | [5 empty] | 26890.16 |  | 100% |  | 26287.92 | 26287.92
187 | backend | 2014-03-03 15:00 | 2014-03-05 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-04 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
188 | backend and extract | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H;Employee K | 3131.68 | 0 | 0 | 0 | 3131.68 | 2014-03-06 15:00 | 2d | 3131.68 | 0 | 0 | -4.5475e-13 | 0 | 3131.68 | 0 | 100% | Finished | 3131.68 | 3131.68 | 100 | 100 | 100 | 100 | 100 | 100
189 | performance testing monitoring backend | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-06 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
190 | monitoring BI | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d | Employee K | 4818 | 0 | 0 | 0 | 4818 | 2014-03-12 08:00 | 5d | 4818 | 0 | 0 | 0 | 0 | 4818 | 0 | 100% | Finished | 4818 | 4818 | 100 | 100 | 100 | 100 | 100 | 100
191 | weekly files | 2014-02-06 10:00 | 2014-02-11 17:00 | 3d 6h | Employee G | 2258.4 | 0 | 0 | 0 | 2258.4 | 2014-03-04 08:00 | 3d 6h | 2258.4 | 0 | 0 | 0 | 0 | 2258.4 | 0 | 100% | Finished | 2258.4 | 2258.4 | 100 | 100 | 100 | 100 | 100 | 100
192 | monthly files | 2014-02-21 08:00 | 2014-02-25 12:00 | 2d 4h | Employee G | 1505.6 | 0 | 0 | 0 | 1505.6 | 2014-02-21 08:00 | 2d 4h | 1505.6 | 0 | 0 | 0 | 0 | 1505.6 | 0 | 100% | Finished | 1505.6 | 1505.6 | 100 | 100 | 100 | 100 | 100 | 100
193 | duplicate documents | 2014-03-05 08:00 | 2014-03-06 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-08 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
194 | current saldo | 2014-03-03 08:00 | 2014-03-04 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-04 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
195 | account statement | 2014-03-07 08:00 | 2014-03-11 17:00 | 3d | Employee F | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-04-10 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
196 | defect core weekly | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-10 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
197 | defect core monthly | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
198 | defect interfacing | 2014-03-12 08:00 | 2014-03-13 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
199 | defect monitoring | 2014-03-07 15:00 | 2014-03-11 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-10 15:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 150 | 100 | 100 | 150 | 100
200 | defect BI reporting | 2014-03-19 08:00 | 2014-03-20 17:00 | 2d | Employee K | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-03-19 08:00 | 2d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 100 | 100 | 100 | 100 | 100
252 | integration testing release 2 | 2014-04-01 08:00 | 2014-04-23 17:00 | 17d |  |  | 0 |  |  | 15056 |  | 37d | [5 empty] | 13399.84 |  | 88.12% |  | 13267.3472 | 15056
201 | feedback | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee F[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-05-07 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 100% | Finished | 3011.2 | 3011.2 | 100 | 100 | 100 | 100 | 100 | 100
202 | migration | 2014-04-08 08:00 | 2014-04-21 17:00 | 10d | Employee H[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-09 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 100% | Finished | 3011.2 | 3011.2 | 100 | 100 | 100 | 100 | 100 | 100
203 | list batch testing | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | Employee G[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-02 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
204 | core | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee G[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-04 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 100% | Finished | 3011.2 | 3011.2 | 100 | 100 | 100 | 100 | 100 | 100
205 | mail encryption | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee I | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-30 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 6.0224 | 602.24 | 100 | 12.5 | 1 | 100 | 12.5 | 1
206 | defect core | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee G | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
207 | defect interfacing | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-21 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
208 | defect migration | 2014-04-22 08:00 | 2014-04-23 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-23 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
209 | defect mail encryption | 2014-04-02 10:00 | 2014-04-04 10:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 1h | 75.28 | 7452.72 | 12d 3h | 0 | 0 | 75.28 | 7452.72 | 1% | Started | 12.0448 | 1204.48 | 100 | 6.25 | 1 | 100 | 6.25 | 1
253 | p2p testing | 2014-04-15 08:00 | 2014-04-22 17:00 | 6d |  |  | 0 |  |  | 6022.4 |  | 27d | [5 empty] | 3613.44 |  | 60.4% |  | 3637.5296 | 6022.4
210 | p2p weekly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-22 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
211 | p2p monthly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-05-05 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 50 | 100 | 100 | 50 | 100
212 | p2p current saldo | 2014-04-15 08:00 | 2014-04-15 17:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
213 | p2p duplicate documents | 2014-04-16 10:00 | 2014-04-17 10:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-16 08:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
214 | p2p account statement | 2014-04-17 13:00 | 2014-04-18 12:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-17 13:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
215 | p2p feedback | 2014-04-18 15:00 | 2014-04-21 15:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 15:00 | 1h | 150.56 | 14905.44 | 12d 3h | 0 | 0 | 150.56 | 14905.44 | 1% | Started | 12.0448 | 1204.48 | 100 | 12.5 | 1 | 100 | 12.5 | 1
254 | business acceptance testing release 1 | 2013-10-25 08:00 | 2014-04-04 12:00 | 115d 4h |  |  | 0 |  |  | 45815.04 |  | 149d | [5 empty] | 75085.76 |  | 97.68% |  | 44752.3851 | 45815.04
216 | part 1 - information lists | 2014-02-17 08:00 | 2014-03-28 12:00 | 29d 4h | Employee M | 18771.44 | 0 | 0 | 0 | 18771.44 | 2014-02-17 08:00 | 30d | 19089.6 | 0 | 0 | -3.638e-12 | 0 | 19089.6 | 0 | 100% | Finished | 18771.44 | 18771.44 | 100 | 101.6949 | 100 | 100 | 101.6949 | 100
217 | part 2 - interface | 2013-10-25 08:00 | 2013-10-29 17:00 | 3d | Employee N | 1908.96 | 0 | 0 | 0 | 1908.96 | 2013-10-25 08:00 | 51d | 32452.32 | 1034.02 | 1d 5h | -3.638e-12 | 0 | 32452.32 | 1034.02 | 97% | Started | 1851.6913 | 1908.96 | 100 | 1700 | 97 | 100 | 1700 | 97
218 | part 3 - reporting | 2014-02-10 08:00 | 2014-04-04 12:00 | 39d 4h | Employee P | 25134.64 | 0 | 0 | 0 | 25134.64 | 2014-02-10 08:00 | 37d | 23543.84 | 954.48 | 1d 4h | 0 | 0 | 23543.84 | 954.48 | 96% | Started | 24129.2539 | 25134.64 | 100 | 93.6709 | 96 | 100 | 93.6709 | 96
255 | business acceptance testing release 2 | 2014-04-21 08:00 | 2014-04-22 17:00 | 2d |  |  | 0 |  |  | 2545.28 |  | 57d | [5 empty] | 38179.2 |  | 100% |  | 2545.28 | 2545.28
219 | test definition | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
220 | test data | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
221 | test execution | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee N;Employee O | 1272.64 | 0 | 0 | 0 | 1272.64 | 2014-04-22 08:00 | 11d | 13999.04 | 0 | 0 | 0 | 0 | 13999.04 | 0 | 100% | Finished | 1272.64 | 1272.64 | 100 | 1100 | 100 | 100 | 1100 | 100
256 | service preparation | 2014-03-24 08:00 | 2014-04-23 17:00 | 23d |  |  | 0 |  |  | 3208.46 |  | 10d | [5 empty] | 1033.42 |  | 1% |  | 32.0846 | 3208.46
227 | SLA review | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1h | 240.9 | 23849.1 | 12d 3h | 0 | 0 | 240.9 | 23849.1 | 1% | Started | 4.818 | 481.8 | 100 | 50 | 1 | 100 | 50 | 1
228 | service budget agreement | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1h | 240.9 | 23849.1 | 12d 3h | 0 | 0 | 240.9 | 23849.1 | 1% | Started | 4.818 | 481.8 | 100 | 50 | 1 | 100 | 50 | 1
229 | production handbook | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-08 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 9.636 | 963.6 | 100 | 12.5 | 1 | 100 | 12.5 | 1
230 | service manual | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1h | 240.9 | 23849.1 | 12d 3h | 0 | 0 | 240.9 | 23849.1 | 1% | Started | 4.818 | 481.8 | 100 | 50 | 1 | 100 | 50 | 1
231 | SCM validation | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-08 08:00 | 1h | 120.45 | 11924.55 | 12d 3h | 0 | 0 | 120.45 | 11924.55 | 1% | Started | 2.409 | 240.9 | 100 | 50 | 1 | 100 | 50 | 1
232 | CIO validation | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-05-08 08:00 | 1h | 69.82 | 6912.18 | 12d 3h | 0 | 0 | 69.82 | 6912.18 | 1% | Started | 5.5856 | 558.56 | 100 | 12.5 | 1 | 100 | 12.5 | 1
257 | go-no go meeting | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1522.16
233 | formal validation | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 1522.16 | 100 |  | 0 | 100 |  | 0
258 | deploy on production | 2013-10-25 08:00 | 2014-05-16 17:00 | 146d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1522.16
234 | go live | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | PIN testing IT | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
236 | PIN testing business | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 |  | 0 | 0 | 558.56 | 1d | 0 | 0 | 0 | 558.56 | 0% | Not Started | 0 | 558.56 | 100 |  | 0 | 100 |  | 0
259 | validation | 2014-05-16 17:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1522.16
237 | steerco validation | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 |  | 0 | 0 | 1522.16 | 1d | 0 | 0 | 0 | 1522.16 | 0% | Not Started | 0 | 1522.16 | 100 |  | 0 | 100 |  | 0
238 | end of implement | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | close | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 9731.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 9731.8
261 | hand-over preparation | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 6841 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6841
239 | project charter as built | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h | Employee A;Employee B | 2283.24 | 0 | 0 | 0 | 2283.24 |  | 0 | 0 | 2283.24 | 1d 4h | 0 | 0 | 0 | 2283.24 | 0% | Not Started | 0 | 2283.24 | 100 |  | 0 | 100 |  | 0
240 | blueprint as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee J;Employee M;Employee N | 2751.04 | 0 | 0 | 0 | 2751.04 |  | 0 | 0 | 2751.04 | 1d | 0 | 0 | 0 | 2751.04 | 0% | Not Started | 0 | 2751.04 | 100 |  | 0 | 100 |  | 0
241 | technical design as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee F;Employee G;Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 |  | 0 | 0 | 1806.72 | 1d | 0 | 0 | 0 | 1806.72 | 0% | Not Started | 0 | 1806.72 | 100 |  | 0 | 100 |  | 0
262 | hand-over | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1927.2 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1927.2
242 | service manual | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
243 | CMDB check | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee C | 963.6 | 0 | 0 | 0 | 963.6 |  | 0 | 0 | 963.6 | 1d | 0 | 0 | 0 | 963.6 | 0% | Not Started | 0 | 963.6 | 100 |  | 0 | 100 |  | 0
244 | SCM validation | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 |  | 0 | 0 | 481.8 | 4h | 0 | 0 | 0 | 481.8 | 0% | Not Started | 0 | 481.8 | 100 |  | 0 | 100 |  | 0
263 | project evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h |  |  | 0 |  |  | 722.7 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 722.7
245 | customer satisfaction survey | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 240.9 | 100 |  | 0 | 100 |  | 0
246 | project team briefing | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 240.9 | 100 |  | 0 | 100 |  | 0
247 | suppliers evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 240.9 | 100 |  | 0 | 100 |  | 0
264 | close phase | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 240.9 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 240.9
248 | program manager validation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 |  | 0 | 0 | 240.9 | 2h | 0 | 0 | 0 | 240.9 | 0% | Not Started | 0 | 240.9 | 100 |  | 0 | 100 |  | 0
249 | end of project | 2014-05-19 17:00 | 2014-05-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-05-30 22:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Debt Collection System | 2013-10-24 08:00 | 2014-05-20 12:00 | 148d 4h |  |  | 0 |  |  | 458112.3684 |  | 153d 4h | [5 empty] | 512546.1461 |  | 100% |  | 458112.3684 | 458112.3684
9 | define | 2013-10-24 08:00 | 2013-12-18 17:00 | 40d |  |  | 0 |  |  | 41864.71 |  | 39d 7h | [5 empty] | 41864.71 |  | 100% |  | 41864.71 | 41864.71
1 | kick-off meeting | 2013-10-24 08:00 | 2013-10-24 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-10-24 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
266 | project charter set | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d |  |  | 0 |  |  | 37495.44 |  | 24d | [5 empty] | 37495.44 |  | 100% |  | 37495.44 | 37495.44
2 | project charter (scope definition) | 2013-11-04 08:00 | 2013-12-05 17:00 | 24d | Employee A;Employee B | 36531.84 | 0 | 0 | 0 | 36531.84 | 2013-11-04 08:00 | 24d | 36531.84 | 0 | 0 | 0 | 0 | 36531.84 | 0 | 100% | Finished | 36531.84 | 36531.84 | 100 | 100 | 100 | 100 | 100 | 100
3 | project security risks | 2013-11-13 08:00 | 2013-11-13 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2013-11-13 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
267 | project charter - communication and validation | 2013-11-25 08:00 | 2013-12-18 17:00 | 18d |  |  | 0 |  |  | 3810.71 |  | 17d 7h | [5 empty] | 3810.71 |  | 100% |  | 3810.71 | 3810.71
4 | inform IT governance | 2013-11-25 08:00 | 2013-11-25 09:00 | 1h | Employee B;Employee C | 240.9 | 0 | 0 | 0 | 240.9 | 2013-11-25 08:00 | 1h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
5 | send info | 2013-11-28 08:00 | 2013-11-28 17:00 | 1d | Employee B;Employee D | 1927.2 | 0 | 0 | 0 | 1927.2 | 2013-11-28 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 100 | 100 | 100 | 100 | 100
6 | send project charter for validation + delivery board validation | 2013-12-13 08:00 | 2013-12-16 09:00 | 1d 1h | Employee B | 1084.05 | 0 | 0 | 0 | 1084.05 | 2013-12-13 08:00 | 1d 1h | 1084.05 | 0 | 0 | 0 | 0 | 1084.05 | 0 | 100% | Finished | 1084.05 | 1084.05 | 100 | 100 | 100 | 100 | 100 | 100
7 | business validation | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2013-12-17 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
8 | end of define | 2013-12-18 17:00 | 2013-12-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
22 | design | 2013-11-25 08:00 | 2014-02-10 17:00 | 56d |  |  | 0 |  |  | 107215.84 |  | 55d 7h | [5 empty] | 100711.54 |  | 100% |  | 107215.84 | 107215.84
15 | blueprint set | 2013-11-25 08:00 | 2014-01-23 17:00 | 44d |  |  | 0 |  |  | 103826.72 |  | 51d | [5 empty] | 98045.12 |  | 100% |  | 103826.72 | 103826.72
10 | functional analysis List/file creation | 2013-12-02 08:00 | 2014-01-03 17:00 | 25d | Employee G | 15056 | 0 | 0 | 0 | 15056 | 2013-12-02 08:00 | 25d | 15056 | 0 | 0 | 0 | 0 | 15056 | 0 | 100% | Finished | 15056 | 15056 | 100 | 100 | 100 | 100 | 100 | 100
11 | functional analysis Monitoring | 2013-11-25 08:00 | 2014-01-08 17:00 | 33d | Employee H | 19873.92 | 0 | 0 | 0 | 19873.92 | 2013-11-25 08:00 | 33d | 19873.92 | 0 | 0 | -3.638e-12 | 0 | 19873.92 | 0 | 100% | Finished | 19873.92 | 19873.92 | 100 | 100 | 100 | 100 | 100 | 100
12 | functional analysis Interfacing | 2013-11-25 08:00 | 2014-01-03 17:00 | 30d | Employee F;Employee I | 36134.4 | 0 | 0 | 0 | 36134.4 | 2013-11-25 08:00 | 30d | 36134.4 | 0 | 0 | 0 | 0 | 36134.4 | 0 | 100% | Finished | 36134.4 | 36134.4 | 100 | 100 | 100 | 100 | 100 | 100
13 | architecture analysis | 2013-11-25 08:00 | 2013-12-27 17:00 | 25d | Employee E | 24090 | 0 | 0 | 0 | 24090 | 2013-11-25 08:00 | 25d | 24090 | 0 | 0 | 0 | 0 | 24090 | 0 | 100% | Finished | 24090 | 24090 | 100 | 100 | 100 | 100 | 100 | 100
14 | budget &amp; planning for development + master test chapter | 2014-01-13 08:00 | 2014-01-23 17:00 | 9d | Employee B | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-01-30 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 100% | Finished | 8672.4 | 8672.4 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
21 | design phase - validations | 2014-01-21 08:00 | 2014-02-10 17:00 | 15d |  |  | 0 |  |  | 3389.12 |  | 14d 7h | [5 empty] | 2666.42 |  | 100% |  | 3389.12 | 3389.12
16 | presentation to Business part 1 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G;Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-21 08:00 | 4h | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
17 | presentation to Business part 2 | 2014-01-31 08:00 | 2014-01-31 12:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-01-31 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
18 | send to delivery board + IT governance validation | 2014-02-07 08:00 | 2014-02-10 17:00 | 2d | Employee B | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-02-07 08:00 | 1d 2h | 1204.5 | 0 | 0 | 0 | 0 | 1204.5 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 62.5 | 100 | 100 | 62.5 | 100
19 | business validation | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-02-07 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
20 | end of design | 2014-02-10 17:00 | 2014-02-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | build | 2013-12-27 15:00 | 2014-05-14 17:00 | 98d 2h |  |  | 0 |  |  | 178453.6384 |  | 79d | [5 empty] | 177190.4961 |  | 100% |  | 178453.6384 | 178453.6384
32 | weekly file | 2014-01-02 15:00 | 2014-03-11 17:00 | 48d 2h |  |  | 0 |  |  | 19499.28 |  | 29d | [5 empty] | 18611.852 |  | 100% |  | 19499.28 | 19499.28
23 | build/technical design | 2014-01-02 15:00 | 2014-01-09 15:00 | 5d | Employee G[0.60 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-01-30 08:00 | 5d 4h | 1987.392 | 0 | 0 | 0 | 0 | 1987.392 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 110 | 100 | 100 | 110 | 100
24 | ABAP | 2014-01-09 15:00 | 2014-01-22 15:00 | 9d | ABAP | 6750 | 0 | 0 | 0 | 6750 | 2014-02-06 08:00 | 9d | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 100% | Finished | 6750 | 6750 | 100 | 100 | 100 | 100 | 100 | 100
25 | UT program in general | 2014-01-23 15:00 | 2014-01-27 10:00 | 1d 4h | Employee G | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
26 | UT submission file | 2014-01-31 15:00 | 2014-02-06 10:00 | 3d 4h | Employee G | 2107.84 | 0 | 0 | 0 | 2107.84 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2107.84 | 2107.84 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | UT clearing file | 2014-01-27 10:00 | 2014-01-31 10:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-20 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
28 | UT other treatment file | 2014-01-31 10:00 | 2014-02-06 10:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-02-26 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
29 | business UT submission | 2014-03-05 13:00 | 2014-03-10 12:00 | 3d | Employee M | 1908.96 | 0 | 0 | 0 | 1908.96 | 2014-02-25 08:00 | 3h | 238.62 | 0 | 0 | 0 | 0 | 238.62 | 0 | 100% | Finished | 1908.96 | 1908.96 | 100 | 12.5 | 100 | 100 | 12.5 | 100
30 | UT sending via e-mail | 2014-03-11 08:00 | 2014-03-11 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
31 | build/technical design | 2014-01-22 15:00 | 2014-01-23 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
82 | monthly file | 2013-12-27 15:00 | 2014-02-14 17:00 | 35d 2h |  |  | 0 |  |  | 6713.344 |  | 33d | [5 empty] | 6277.012 |  | 100% |  | 6713.344 | 6713.344
33 | build/technical design | 2013-12-27 15:00 | 2014-01-02 15:00 | 4d | Employee G | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-24 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
34 | ABAP | 2014-01-30 08:00 | 2014-02-03 12:00 | 2d 4h | ABAP[0.80 #1] | 1500 | 0 | 0 | 0 | 1500 | 2014-01-30 08:00 | 2d 4h | 1500 | 0 | 0 | 2.2352e-05 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
35 | UT | 2014-02-03 13:00 | 2014-02-11 17:00 | 6d 4h | Employee G[0.40 #1] | 1565.824 | 0 | 0 | 0 | 1565.824 | 2014-02-03 08:00 | 7d | 1686.272 | 0 | 0 | 2.5127e-05 | 0 | 1686.272 | 0 | 100% | Finished | 1565.824 | 1565.824 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
36 | business UT | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee M | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-18 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
37 | UT sending via e-mail | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-11 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
83 | authorization check | 2014-01-24 08:00 | 2014-03-24 12:00 | 41d 4h |  |  | 0 |  |  | 15386.2 |  | 38d | [5 empty] | 15386.2 |  | 100% |  | 15386.2 | 15386.2
38 | IRIS-SC | 2014-03-13 08:00 | 2014-03-18 17:00 | 4d | Java | 3000 | 0 | 0 | 0 | 3000 | 2014-03-13 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
39 | build/technical design | 2014-01-24 08:00 | 2014-01-24 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-01-24 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
40 | ABAP | 2014-01-27 08:00 | 2014-02-10 17:00 | 11d | ABAP | 8250 | 0 | 0 | 0 | 8250 | 2014-01-27 08:00 | 11d | 8250 | 0 | 0 | 0 | 0 | 8250 | 0 | 100% | Finished | 8250 | 8250 | 100 | 100 | 100 | 100 | 100 | 100
41 | UT | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
42 | build/technical design | 2014-02-13 08:00 | 2014-02-13 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
43 | ABAP | 2014-03-19 13:00 | 2014-03-20 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
44 | UT | 2014-03-20 13:00 | 2014-03-21 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
45 | import WSDL | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-02-13 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
46 | ESB (pass BP to basic) | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
84 | send DMS file via e-mail | 2014-02-05 15:00 | 2014-03-10 17:00 | 23d 2h |  |  | 0 |  |  | 13548.8944 |  | 16d | [5 empty] | 13580.512 |  | 100% |  | 13548.8944 | 13548.8944
47 | build/technical design | 2014-02-17 08:00 | 2014-03-07 10:00 | 14d 2h | Employee I[0.07 #1] | 600.7344 | 0 | 0 | 0 | 600.7344 | 2014-02-17 08:00 | 15d | 632.352 | 0 | 0 | 2.6922e-06 | 0 | 632.352 | 0 | 100% | Finished | 600.7344 | 600.7344 | 100 | 105.2632 | 100 | 100 | 105.2632 | 100
48 | import WSDL | 2014-02-05 15:00 | 2014-02-06 10:00 | 4h | EAI | 301.12 | 0 | 0 | 0 | 301.12 | 2014-02-17 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
49 | build/technical design | 2014-02-07 08:00 | 2014-02-07 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
50 | EAI | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
51 | UT | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
52 | build/technical design | 2014-02-18 08:00 | 2014-02-18 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
53 | EAI | 2014-02-19 08:00 | 2014-02-19 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
54 | UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | EAI | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
55 | design | 2014-02-19 08:00 | 2014-02-20 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-19 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
56 | build | 2014-02-21 08:00 | 2014-02-25 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-21 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
57 | queue handling | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
58 | UT | 2014-03-03 08:00 | 2014-03-06 17:00 | 4d | EAI | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-03-03 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
59 | deployment | 2014-03-07 08:00 | 2014-03-10 17:00 | 2d | EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-07 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
85 | duplicates | 2014-02-12 13:00 | 2014-03-26 17:00 | 30d 4h |  |  | 0 |  |  | 5261.2 |  | 11d | [5 empty] | 5261.2 |  | 100% |  | 5261.2 | 5261.2
60 | build/technical design | 2014-02-12 13:00 | 2014-02-14 12:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-12 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
61 | java | 2014-03-19 08:00 | 2014-03-21 17:00 | 3d | Java | 2250 | 0 | 0 | 0 | 2250 | 2014-02-19 08:00 | 3d | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 2250 | 2250 | 100 | 100 | 100 | 100 | 100 | 100
62 | UT | 2014-03-24 08:00 | 2014-03-26 17:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-24 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
86 | current saldo | 2014-02-11 08:00 | 2014-02-20 17:00 | 8d |  |  | 0 |  |  | 3943.04 |  | 7d 4h | [5 empty] | 3386.26 |  | 100% |  | 3943.04 | 3943.04
63 | build/technical design | 2014-02-11 08:00 | 2014-02-12 12:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-11 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
64 | java | 2014-02-14 13:00 | 2014-02-18 12:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-02-17 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
65 | UT | 2014-02-18 13:00 | 2014-02-19 17:00 | 1d 4h | Employee I | 903.36 | 0 | 0 | 0 | 903.36 | 2014-02-19 08:00 | 1d 4h | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
66 | business UT | 2014-02-20 08:00 | 2014-02-20 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-20 08:00 | 1h | 79.54 | 0 | 0 | 0 | 0 | 79.54 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 12.5 | 100 | 100 | 12.5 | 100
88 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d |  |  | 0 |  |  | 3613.44 |  | 6d | [5 empty] | 3613.44 |  | 100% |  | 3613.44 | 3613.44
67 | BRM | 2014-03-07 10:00 | 2014-03-17 10:00 | 6d | Employee I | 3613.44 | 0 | 0 | 0 | 3613.44 | 2014-03-07 10:00 | 6d | 3613.44 | 0 | 0 | 0 | 0 | 3613.44 | 0 | 100% | Finished | 3613.44 | 3613.44 | 100 | 100 | 100 | 100 | 100 | 100
87 | account statement | 2014-01-24 15:00 | 2014-03-31 12:00 | 45d 6h |  |  | 0 |  |  | 15044.8 |  | 41d | [5 empty] | 15044.8 |  | 100% |  | 15044.8 | 15044.8
68 | build/technical design | 2014-01-24 15:00 | 2014-02-07 15:00 | 10d | Employee F[0.50 #1];Employee L[0.50 #1] | 6022.4 | 0 | 0 | 0 | 6022.4 | 2014-02-10 08:00 | 10d | 6022.4 | 0 | 0 | 0 | 0 | 6022.4 | 0 | 100% | Finished | 6022.4 | 6022.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | ABAP | 2014-02-11 08:00 | 2014-02-12 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-02-20 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
70 | UT | 2014-02-13 08:00 | 2014-02-14 17:00 | 2d | Employee F;Employee L | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-04-02 08:00 | 2d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
71 | spec proxy | 2014-03-21 13:00 | 2014-03-24 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-19 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
72 | ABAP proxy | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
73 | UT proxy | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
74 | spec wrapper core | 2014-03-24 13:00 | 2014-03-26 12:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-02-20 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
75 | ABAP wrapper core | 2014-03-26 13:00 | 2014-03-27 12:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-02-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
76 | UT wrapper core | 2014-03-27 13:00 | 2014-03-28 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-07 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
77 | email functionality | 2014-03-28 13:00 | 2014-03-31 12:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
173 | monitoring and reporting | 2014-01-29 08:00 | 2014-03-05 15:00 | 25d 6h |  |  | 0 |  |  | 31228.56 |  | 25d 6h | [5 empty] | 31228.56 |  | 100% |  | 31228.56 | 31228.56
78 | build/technical design | 2014-01-29 08:00 | 2014-02-03 17:00 | 4d | Employee H | 2408.96 | 0 | 0 | 0 | 2408.96 | 2014-01-29 08:00 | 4d | 2408.96 | 0 | 0 | 0 | 0 | 2408.96 | 0 | 100% | Finished | 2408.96 | 2408.96 | 100 | 100 | 100 | 100 | 100 | 100
79 | ABAP | 2014-02-06 08:00 | 2014-02-12 17:00 | 5d | ABAP | 3750 | 0 | 0 | 0 | 3750 | 2014-02-06 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
80 | UT | 2014-02-13 08:00 | 2014-02-19 17:00 | 5d | Employee H;ABAP | 6761.2 | 0 | 0 | 0 | 6761.2 | 2014-02-13 08:00 | 5d | 6761.2 | 0 | 0 | 0 | 0 | 6761.2 | 0 | 100% | Finished | 6761.2 | 6761.2 | 100 | 100 | 100 | 100 | 100 | 100
81 | BI reports | 2014-02-06 15:00 | 2014-03-05 15:00 | 19d | Employee K | 18308.4 | 0 | 0 | 0 | 18308.4 | 2014-02-06 15:00 | 19d | 18308.4 | 0 | 0 | 0 | 0 | 18308.4 | 0 | 100% | Finished | 18308.4 | 18308.4 | 100 | 100 | 100 | 100 | 100 | 100
174 | weekly file | 2014-03-21 08:00 | 2014-04-01 15:00 | 7d 6h |  |  | 0 |  |  | 3219.2 |  | 7d 6h | [5 empty] | 3219.2 |  | 100% |  | 3219.2 | 3219.2
89 | build/technical design | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-21 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
90 | ABAP | 2014-03-24 08:00 | 2014-03-24 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
91 | UT | 2014-03-25 08:00 | 2014-03-25 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-25 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
92 | build/technical design | 2014-03-28 15:00 | 2014-03-31 10:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 15:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
93 | setup autosys | 2014-03-31 15:00 | 2014-04-01 15:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-03-31 15:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
175 | monthly file | 2014-03-31 10:00 | 2014-04-01 17:00 | 1d 6h |  |  | 0 |  |  | 1505.62 |  | 1d 6h | [5 empty] | 1264.72 |  | 100% |  | 1505.62 | 1505.62
94 | build/technical design | 2014-03-31 10:00 | 2014-03-31 15:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-31 10:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
95 | setup autosys | 2014-03-31 15:00 | 2014-04-01 17:00 | 1d 2h | Employee D | 1204.5 | 0 | 0 | 0 | 1204.5 | 2014-04-01 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 1204.5 | 1204.5 | 100 | 80 | 100 | 100 | 80 | 100
176 | list | 2014-03-26 08:00 | 2014-03-28 15:00 | 2d 6h |  |  | 0 |  |  | 1579.48 |  | 3d | [5 empty] | 1579.48 |  | 100% |  | 1579.48 | 1579.48
96 | build/technical design | 2014-03-26 08:00 | 2014-03-26 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-26 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
97 | ABAP | 2014-03-27 08:00 | 2014-03-27 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-27 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
98 | UT | 2014-03-27 15:00 | 2014-03-28 15:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-28 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
177 | migration program | 2014-03-21 08:00 | 2014-04-07 17:00 | 12d |  |  | 0 |  |  | 7522.4 |  | 12d | [5 empty] | 7522.4 |  | 100% |  | 7522.4 | 7522.4
99 | build/technical design | 2014-03-21 08:00 | 2014-04-01 17:00 | 8d | Employee H | 4817.92 | 0 | 0 | 0 | 4817.92 | 2014-03-24 08:00 | 8d | 4817.92 | 0 | 0 | 0 | 0 | 4817.92 | 0 | 100% | Finished | 4817.92 | 4817.92 | 100 | 100 | 100 | 100 | 100 | 100
100 | ABAP | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | ABAP | 1500 | 0 | 0 | 0 | 1500 | 2014-04-03 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
101 | UT | 2014-04-04 08:00 | 2014-04-07 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-07 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
178 | send DMS file via e-mail | 2014-03-14 08:00 | 2014-03-27 15:00 | 9d 6h |  |  | 0 |  |  | 7463.06 |  | 9d 4h | [5 empty] | 7463.06 |  | 100% |  | 7463.06 | 7463.06
102 | WSDL update | 2014-03-14 08:00 | 2014-03-14 10:00 | 2h | Java;Employee I | 338.06 | 0 | 0 | 0 | 338.06 | 2014-04-17 08:00 | 2h | 338.06 | 0 | 0 | 0 | 0 | 338.06 | 0 | 100% | Finished | 338.06 | 338.06 | 100 | 100 | 100 | 100 | 100 | 100
103 | get cert / encrypt | 2014-03-14 10:00 | 2014-03-21 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-04-17 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
104 | error handling | 2014-03-21 10:00 | 2014-03-25 10:00 | 2d | Java | 1500 | 0 | 0 | 0 | 1500 | 2014-04-24 08:00 | 2d | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 100% | Finished | 1500 | 1500 | 100 | 100 | 100 | 100 | 100 | 100
105 | UT java team | 2014-03-25 10:00 | 2014-03-27 15:00 | 2d 4h | Java | 1875 | 0 | 0 | 0 | 1875 | 2014-04-28 08:00 | 2d 4h | 1875 | 0 | 0 | 0 | 0 | 1875 | 0 | 100% | Finished | 1875 | 1875 | 100 | 100 | 100 | 100 | 100 | 100
179 | feedback | 2014-03-11 15:00 | 2014-04-04 10:00 | 17d 4h |  |  | 0 |  |  | 29314.4 |  | 40d | [5 empty] | 30141.08 |  | 100% |  | 29314.4 | 29314.4
106 | build/technical design | 2014-03-13 08:00 | 2014-03-13 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
107 | ABAP | 2014-03-14 08:00 | 2014-03-14 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
108 | UT | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
109 | build/technical design | 2014-03-11 15:00 | 2014-03-12 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-12 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
110 | ABAP | 2014-03-21 15:00 | 2014-03-24 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-13 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 375 | 375 | 100 | 200 | 100 | 100 | 200 | 100
111 | UT | 2014-03-24 10:00 | 2014-03-24 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 400 | 100 | 100 | 400 | 100
112 | build/technical design | 2014-03-14 08:00 | 2014-03-14 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
113 | ABAP | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-14 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
114 | UT | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
115 | build/technical design | 2014-03-12 10:00 | 2014-03-13 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-13 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
116 | ABAP | 2014-03-13 10:00 | 2014-03-14 10:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-14 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
117 | UT | 2014-03-14 10:00 | 2014-03-17 10:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
118 | build/technical design | 2014-03-14 13:00 | 2014-03-14 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-14 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
119 | ABAP | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
120 | UT | 2014-03-17 13:00 | 2014-03-17 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-17 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
121 | build/technical design | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-18 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
122 | ABAP | 2014-03-17 15:00 | 2014-03-18 10:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-18 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
123 | UT | 2014-03-18 10:00 | 2014-03-18 12:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-19 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
124 | build/technical design | 2014-03-18 08:00 | 2014-03-18 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-18 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
125 | ABAP | 2014-03-19 08:00 | 2014-03-19 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-03-19 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
126 | UT | 2014-03-20 08:00 | 2014-03-20 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-03-20 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
127 | build/technical design | 2014-03-18 13:00 | 2014-03-18 17:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
128 | ABAP | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
129 | UT | 2014-03-19 13:00 | 2014-03-19 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
130 | build/technical design | 2014-03-19 08:00 | 2014-03-19 12:00 | 4h | Employee G | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-19 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
131 | ABAP | 2014-03-19 13:00 | 2014-03-19 17:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-19 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
132 | UT | 2014-03-20 08:00 | 2014-03-20 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
133 | build/technical design | 2014-03-19 15:00 | 2014-03-20 10:00 | 4h | Employee H | 301.12 | 0 | 0 | 0 | 301.12 | 2014-03-20 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 301.12 | 301.12 | 100 | 100 | 100 | 100 | 100 | 100
134 | ABAP | 2014-03-20 10:00 | 2014-03-20 15:00 | 4h | ABAP | 375 | 0 | 0 | 0 | 375 | 2014-03-21 10:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
135 | UT | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee H | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-24 15:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
136 | import WSDL | 2014-03-17 10:00 | 2014-03-17 15:00 | 4h | Java | 375 | 0 | 0 | 0 | 375 | 2014-03-17 08:00 | 4h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
137 | spec proxy | 2014-03-14 08:00 | 2014-03-17 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-17 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
138 | ABAP proxy | 2014-03-18 08:00 | 2014-03-18 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-21 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
139 | UT proxy | 2014-03-18 15:00 | 2014-03-20 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-21 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
140 | spec wrapper core | 2014-03-18 08:00 | 2014-03-19 17:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-21 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
141 | ABAP wrapper core | 2014-03-20 08:00 | 2014-03-20 15:00 | 6h | ABAP | 562.5 | 0 | 0 | 0 | 562.5 | 2014-04-23 08:00 | 6h | 562.5 | 0 | 0 | 0 | 0 | 562.5 | 0 | 100% | Finished | 562.5 | 562.5 | 100 | 100 | 100 | 100 | 100 | 100
142 | UT wrapper core | 2014-03-20 15:00 | 2014-03-24 10:00 | 1d 4h | Employee F[0.50 #1] | 451.68 | 0 | 0 | 0 | 451.68 | 2014-04-23 15:00 | 1d 4h | 451.68 | 0 | 0 | 0 | 0 | 451.68 | 0 | 100% | Finished | 451.68 | 451.68 | 100 | 100 | 100 | 100 | 100 | 100
143 | spec proxy | 2014-03-18 08:00 | 2014-03-20 17:00 | 3d | Employee F[0.50 #1] | 903.36 | 0 | 0 | 0 | 903.36 | 2014-04-21 08:00 | 3d | 903.36 | 0 | 0 | 0 | 0 | 903.36 | 0 | 100% | Finished | 903.36 | 903.36 | 100 | 100 | 100 | 100 | 100 | 100
144 | ABAP proxy | 2014-03-21 08:00 | 2014-03-21 17:00 | 1d | ABAP | 750 | 0 | 0 | 0 | 750 | 2014-04-24 08:00 | 1d | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
145 | UT proxy | 2014-03-24 10:00 | 2014-03-26 10:00 | 2d | Employee F[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-25 10:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
146 | spec wrapper core | 2014-03-21 08:00 | 2014-03-26 17:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-24 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
147 | ABAP wrapper core | 2014-03-27 08:00 | 2014-03-28 12:00 | 1d 4h | ABAP | 1125 | 0 | 0 | 0 | 1125 | 2014-04-30 08:00 | 1d 4h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
148 | UT wrapper core | 2014-03-28 13:00 | 2014-04-03 12:00 | 4d | Employee F[0.50 #1] | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 4d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
149 | content | 2014-03-20 10:00 | 2014-03-20 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
150 | UT | 2014-03-20 13:00 | 2014-03-20 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
151 | content | 2014-03-20 15:00 | 2014-03-20 17:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-20 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
152 | UT | 2014-03-21 08:00 | 2014-03-21 10:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 08:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
153 | content | 2014-03-21 10:00 | 2014-03-21 12:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 10:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
154 | UT | 2014-03-21 13:00 | 2014-03-21 15:00 | 2h | Employee G | 150.56 | 0 | 0 | 0 | 150.56 | 2014-03-21 13:00 | 2h | 150.56 | 0 | 0 | 0 | 0 | 150.56 | 0 | 100% | Finished | 150.56 | 150.56 | 100 | 100 | 100 | 100 | 100 | 100
155 | build/technical design | 2014-03-17 10:00 | 2014-03-20 10:00 | 3d | Employee I | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-17 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
156 | java | 2014-03-20 10:00 | 2014-03-27 10:00 | 5d | Java | 3750 | 0 | 0 | 0 | 3750 | 2014-03-20 08:00 | 5d | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 3750 | 3750 | 100 | 100 | 100 | 100 | 100 | 100
157 | UT | 2014-03-27 10:00 | 2014-04-04 10:00 | 6d | Employee F[0.50 #1] | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-27 10:00 | 6d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
180 | performance report | 2014-05-05 08:00 | 2014-05-14 17:00 | 8d |  |  | 0 |  |  | 4817.92 |  | 8d | [5 empty] | 4817.92 |  | 100% |  | 4817.92 | 4817.92
158 | build/technical design | 2014-05-05 08:00 | 2014-05-06 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-05 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
159 | EAI | 2014-05-07 08:00 | 2014-05-09 17:00 | 3d | EAI | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-07 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
160 | UT | 2014-05-12 08:00 | 2014-05-14 17:00 | 3d | Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-12 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
181 | preparation IT test strategy | 2014-02-04 08:00 | 2014-02-17 17:00 | 10d |  |  | 0 |  |  | 3011.2 |  | 10d | [5 empty] | 3011.2 |  | 100% |  | 3011.2 | 3011.2
161 | preparation core | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
162 | preparation migration | 2014-02-17 08:00 | 2014-02-17 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-17 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
163 | preparation interfacing | 2014-02-10 08:00 | 2014-02-10 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
164 | preparation reporting | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee H | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-04 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
165 | preparation interfacing | 2014-02-04 08:00 | 2014-02-04 17:00 | 1d | Employee F | 602.24 | 0 | 0 | 0 | 602.24 | 2014-02-10 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
182 | service preparation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 2890.8 |  | 100% |  | 2890.8 | 2890.8
166 | service manual draft | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
167 | SDM validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
168 | TCS validation | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-04-30 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
183 | build phase - validation | 2014-04-08 08:00 | 2014-04-09 17:00 | 2d |  |  | 0 |  |  | 2890.8 |  | 1d | [5 empty] | 2890.8 |  | 100% |  | 2890.8 | 2890.8
169 | program manager validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
170 | SCM validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
171 | information security validation | 2014-04-08 08:00 | 2014-04-08 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-07 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
172 | end of build | 2014-04-09 17:00 | 2014-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
260 | implement | 2013-10-25 08:00 | 2014-05-19 17:00 | 147d |  |  | 0 |  |  | 120846.38 |  | 152d | [5 empty] | 183047.6 |  | 100% |  | 120846.38 | 120846.38
250 | certificates | 2014-04-02 10:00 | 2014-05-08 17:00 | 26d 6h |  |  | 0 |  |  | 17344.8 |  | 10d | [5 empty] | 5781.6 |  | 100% |  | 17344.8 | 17344.8
185 | certificates on acceptance | 2014-04-02 10:00 | 2014-04-15 10:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-04-25 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 100% | Finished | 8672.4 | 8672.4 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
186 | certificates on production | 2014-04-28 08:00 | 2014-05-08 17:00 | 9d | Employee D | 8672.4 | 0 | 0 | 0 | 8672.4 | 2014-05-06 08:00 | 3d | 2890.8 | 0 | 0 | 0 | 0 | 2890.8 | 0 | 100% | Finished | 8672.4 | 8672.4 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
251 | integration testing release 1 | 2014-02-06 10:00 | 2014-03-20 17:00 | 30d 6h |  |  | 0 |  |  | 26287.92 |  | 39d | [5 empty] | 26890.16 |  | 100% |  | 26287.92 | 26287.92
187 | backend | 2014-03-03 15:00 | 2014-03-05 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-04 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
188 | backend and extract | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H;Employee K | 3131.68 | 0 | 0 | 0 | 3131.68 | 2014-03-06 15:00 | 2d | 3131.68 | 0 | 0 | -4.5475e-13 | 0 | 3131.68 | 0 | 100% | Finished | 3131.68 | 3131.68 | 100 | 100 | 100 | 100 | 100 | 100
189 | performance testing monitoring backend | 2014-03-05 15:00 | 2014-03-07 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-06 15:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
190 | monitoring BI | 2014-03-12 08:00 | 2014-03-18 17:00 | 5d | Employee K | 4818 | 0 | 0 | 0 | 4818 | 2014-03-12 08:00 | 5d | 4818 | 0 | 0 | 0 | 0 | 4818 | 0 | 100% | Finished | 4818 | 4818 | 100 | 100 | 100 | 100 | 100 | 100
191 | weekly files | 2014-02-06 10:00 | 2014-02-11 17:00 | 3d 6h | Employee G | 2258.4 | 0 | 0 | 0 | 2258.4 | 2014-03-04 08:00 | 3d 6h | 2258.4 | 0 | 0 | 0 | 0 | 2258.4 | 0 | 100% | Finished | 2258.4 | 2258.4 | 100 | 100 | 100 | 100 | 100 | 100
192 | monthly files | 2014-02-21 08:00 | 2014-02-25 12:00 | 2d 4h | Employee G | 1505.6 | 0 | 0 | 0 | 1505.6 | 2014-02-21 08:00 | 2d 4h | 1505.6 | 0 | 0 | 0 | 0 | 1505.6 | 0 | 100% | Finished | 1505.6 | 1505.6 | 100 | 100 | 100 | 100 | 100 | 100
193 | duplicate documents | 2014-03-05 08:00 | 2014-03-06 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-08 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
194 | current saldo | 2014-03-03 08:00 | 2014-03-04 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-04 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
195 | account statement | 2014-03-07 08:00 | 2014-03-11 17:00 | 3d | Employee F | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-04-10 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
196 | defect core weekly | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-03-10 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
197 | defect core monthly | 2014-02-26 08:00 | 2014-02-28 17:00 | 3d | Employee G | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-02-26 08:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
198 | defect interfacing | 2014-03-12 08:00 | 2014-03-13 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
199 | defect monitoring | 2014-03-07 15:00 | 2014-03-11 15:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-03-10 15:00 | 3d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 150 | 100 | 100 | 150 | 100
200 | defect BI reporting | 2014-03-19 08:00 | 2014-03-20 17:00 | 2d | Employee K | 1927.2 | 0 | 0 | 0 | 1927.2 | 2014-03-19 08:00 | 2d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 1927.2 | 1927.2 | 100 | 100 | 100 | 100 | 100 | 100
252 | integration testing release 2 | 2014-04-01 08:00 | 2014-04-23 17:00 | 17d |  |  | 0 |  |  | 15056 |  | 37d | [5 empty] | 15056 |  | 100% |  | 15056 | 15056
201 | feedback | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee F[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-05-07 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 100% | Finished | 3011.2 | 3011.2 | 100 | 100 | 100 | 100 | 100 | 100
202 | migration | 2014-04-08 08:00 | 2014-04-21 17:00 | 10d | Employee H[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-09 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 100% | Finished | 3011.2 | 3011.2 | 100 | 100 | 100 | 100 | 100 | 100
203 | list batch testing | 2014-04-02 08:00 | 2014-04-03 17:00 | 2d | Employee G[0.50 #1] | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-02 08:00 | 2d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
204 | core | 2014-04-04 08:00 | 2014-04-17 17:00 | 10d | Employee G[0.50 #1] | 3011.2 | 0 | 0 | 0 | 3011.2 | 2014-04-04 08:00 | 10d | 3011.2 | 0 | 0 | 0 | 0 | 3011.2 | 0 | 100% | Finished | 3011.2 | 3011.2 | 100 | 100 | 100 | 100 | 100 | 100
205 | mail encryption | 2014-04-01 08:00 | 2014-04-01 17:00 | 1d | Employee I | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-30 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
206 | defect core | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee G | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
207 | defect interfacing | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee F | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-21 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
208 | defect migration | 2014-04-22 08:00 | 2014-04-23 17:00 | 2d | Employee H | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-23 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
209 | defect mail encryption | 2014-04-02 10:00 | 2014-04-04 10:00 | 2d | Employee I | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-05-01 08:00 | 2d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
253 | p2p testing | 2014-04-15 08:00 | 2014-04-22 17:00 | 6d |  |  | 0 |  |  | 6022.4 |  | 14d 4h | [5 empty] | 5721.28 |  | 100% |  | 6022.4 | 6022.4
210 | p2p weekly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-04-22 08:00 | 1d | 602.24 | 0 | 0 | 0 | 0 | 602.24 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 100 | 100 | 100 | 100 | 100
211 | p2p monthly files | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee G | 602.24 | 0 | 0 | 0 | 602.24 | 2014-05-05 08:00 | 4h | 301.12 | 0 | 0 | 0 | 0 | 301.12 | 0 | 100% | Finished | 602.24 | 602.24 | 100 | 50 | 100 | 100 | 50 | 100
212 | p2p current saldo | 2014-04-15 08:00 | 2014-04-15 17:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-15 08:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
213 | p2p duplicate documents | 2014-04-16 10:00 | 2014-04-17 10:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-16 08:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
214 | p2p account statement | 2014-04-17 13:00 | 2014-04-18 12:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-17 13:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
215 | p2p feedback | 2014-04-18 15:00 | 2014-04-21 15:00 | 1d | Employee F;EAI | 1204.48 | 0 | 0 | 0 | 1204.48 | 2014-04-18 15:00 | 1d | 1204.48 | 0 | 0 | 0 | 0 | 1204.48 | 0 | 100% | Finished | 1204.48 | 1204.48 | 100 | 100 | 100 | 100 | 100 | 100
254 | business acceptance testing release 1 | 2013-10-25 08:00 | 2014-04-04 12:00 | 115d 4h |  |  | 0 |  |  | 45815.04 |  | 115d 4h | [5 empty] | 78585.52 |  | 100% |  | 45815.04 | 45815.04
216 | part 1 - information lists | 2014-02-17 08:00 | 2014-03-28 12:00 | 29d 4h | Employee M | 18771.44 | 0 | 0 | 0 | 18771.44 | 2014-02-17 08:00 | 30d | 19089.6 | 0 | 0 | -3.638e-12 | 0 | 19089.6 | 0 | 100% | Finished | 18771.44 | 18771.44 | 100 | 101.6949 | 100 | 100 | 101.6949 | 100
217 | part 2 - interface | 2013-10-25 08:00 | 2013-10-29 17:00 | 3d | Employee N | 1908.96 | 0 | 0 | 0 | 1908.96 | 2013-10-25 08:00 | 54d | 34361.28 | 0 | 0 | -7.276e-12 | 0 | 34361.28 | 0 | 100% | Finished | 1908.96 | 1908.96 | 100 | 1800 | 100 | 100 | 1800 | 100
218 | part 3 - reporting | 2014-02-10 08:00 | 2014-04-04 12:00 | 39d 4h | Employee P | 25134.64 | 0 | 0 | 0 | 25134.64 | 2014-02-10 08:00 | 39d 4h | 25134.64 | 0 | 0 | -3.638e-12 | 0 | 25134.64 | 0 | 100% | Finished | 25134.64 | 25134.64 | 100 | 100 | 100 | 100 | 100 | 100
255 | business acceptance testing release 2 | 2014-04-21 08:00 | 2014-04-22 17:00 | 2d |  |  | 0 |  |  | 2545.28 |  | 57d | [5 empty] | 38179.2 |  | 100% |  | 2545.28 | 2545.28
219 | test definition | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
220 | test data | 2014-04-21 08:00 | 2014-04-21 17:00 | 1d | Employee N | 636.32 | 0 | 0 | 0 | 636.32 | 2014-02-17 08:00 | 19d | 12090.08 | 0 | 0 | -1.819e-12 | 0 | 12090.08 | 0 | 100% | Finished | 636.32 | 636.32 | 100 | 1900 | 100 | 100 | 1900 | 100
221 | test execution | 2014-04-22 08:00 | 2014-04-22 17:00 | 1d | Employee N;Employee O | 1272.64 | 0 | 0 | 0 | 1272.64 | 2014-04-22 08:00 | 11d | 13999.04 | 0 | 0 | 0 | 0 | 13999.04 | 0 | 100% | Finished | 1272.64 | 1272.64 | 100 | 1100 | 100 | 100 | 1100 | 100
256 | service preparation | 2014-03-24 08:00 | 2014-04-23 17:00 | 23d |  |  | 0 |  |  | 3208.46 |  | 1d | [5 empty] | 8267.36 |  | 100% |  | 3208.46 | 3208.46
227 | SLA review | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 481.8 | 481.8 | 100 | 400 | 100 | 100 | 400 | 100
228 | service budget agreement | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 481.8 | 481.8 | 100 | 400 | 100 | 100 | 400 | 100
229 | production handbook | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee D | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-08 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
230 | service manual | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B;Employee C | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-08 08:00 | 1d | 1927.2 | 0 | 0 | 0 | 0 | 1927.2 | 0 | 100% | Finished | 481.8 | 481.8 | 100 | 400 | 100 | 100 | 400 | 100
231 | SCM validation | 2014-04-23 08:00 | 2014-04-23 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-08 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 400 | 100 | 100 | 400 | 100
232 | CIO validation | 2014-04-23 08:00 | 2014-04-23 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-05-08 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
257 | go-no go meeting | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 1d | [5 empty] | 1522.16 |  | 100% |  | 1522.16 | 1522.16
233 | formal validation | 2014-05-14 08:00 | 2014-05-14 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 | 2014-05-22 08:00 | 1d | 1522.16 | 0 | 0 | 2.2737e-13 | 0 | 1522.16 | 0 | 100% | Finished | 1522.16 | 1522.16 | 100 | 100 | 100 | 100 | 100 | 100
258 | deploy on production | 2013-10-25 08:00 | 2014-05-16 17:00 | 146d |  |  | 0 |  |  | 1522.16 |  | 1d | [5 empty] | 1522.16 |  | 100% |  | 1522.16 | 1522.16
234 | go live | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
235 | PIN testing IT | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee B | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-23 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
236 | PIN testing business | 2013-10-25 08:00 | 2013-10-25 17:00 | 1d | Employee A | 558.56 | 0 | 0 | 0 | 558.56 | 2014-05-23 08:00 | 1d | 558.56 | 0 | 0 | 0 | 0 | 558.56 | 0 | 100% | Finished | 558.56 | 558.56 | 100 | 100 | 100 | 100 | 100 | 100
259 | validation | 2014-05-16 17:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1522.16 |  | 1d 1h | [5 empty] | 1522.16 |  | 100% |  | 1522.16 | 1522.16
237 | steerco validation | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee B | 1522.16 | 0 | 0 | 0 | 1522.16 | 2014-05-26 08:00 | 1d | 1522.16 | 0 | 0 | 2.2737e-13 | 0 | 1522.16 | 0 | 100% | Finished | 1522.16 | 1522.16 | 100 | 100 | 100 | 100 | 100 | 100
238 | end of implement | 2014-05-16 17:00 | 2014-05-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-23 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
265 | close | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 9731.8 |  | 1d 4h | [5 empty] | 9731.8 |  | 100% |  | 9731.8 | 9731.8
261 | hand-over preparation | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h |  |  | 0 |  |  | 6841 |  | 1d 4h | [5 empty] | 6841 |  | 100% |  | 6841 | 6841
239 | project charter as built | 2014-05-19 08:00 | 2014-05-20 12:00 | 1d 4h | Employee A;Employee B | 2283.24 | 0 | 0 | 0 | 2283.24 | 2014-05-26 08:00 | 1d 4h | 2283.24 | 0 | 0 | 0 | 0 | 2283.24 | 0 | 100% | Finished | 2283.24 | 2283.24 | 100 | 100 | 100 | 100 | 100 | 100
240 | blueprint as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee A;Employee J;Employee M;Employee N | 2751.04 | 0 | 0 | 0 | 2751.04 | 2014-05-26 08:00 | 1d | 2751.04 | 0 | 0 | -4.5475e-13 | 0 | 2751.04 | 0 | 100% | Finished | 2751.04 | 2751.04 | 100 | 100 | 100 | 100 | 100 | 100
241 | technical design as built | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee F;Employee G;Employee H | 1806.72 | 0 | 0 | 0 | 1806.72 | 2014-05-26 08:00 | 1d | 1806.72 | 0 | 0 | 0 | 0 | 1806.72 | 0 | 100% | Finished | 1806.72 | 1806.72 | 100 | 100 | 100 | 100 | 100 | 100
262 | hand-over | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 1927.2 |  | 1d | [5 empty] | 1927.2 |  | 100% |  | 1927.2 | 1927.2
242 | service manual | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-26 08:00 | 4h | 481.8 | 0 | 0 | 0 | 0 | 481.8 | 0 | 100% | Finished | 481.8 | 481.8 | 100 | 100 | 100 | 100 | 100 | 100
243 | CMDB check | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d | Employee C | 963.6 | 0 | 0 | 0 | 963.6 | 2014-05-26 08:00 | 1d | 963.6 | 0 | 0 | 0 | 0 | 963.6 | 0 | 100% | Finished | 963.6 | 963.6 | 100 | 100 | 100 | 100 | 100 | 100
244 | SCM validation | 2014-05-19 08:00 | 2014-05-19 12:00 | 4h | Employee B | 481.8 | 0 | 0 | 0 | 481.8 | 2014-05-26 08:00 | 4h | 481.8 | 0 | 0 | 0 | 0 | 481.8 | 0 | 100% | Finished | 481.8 | 481.8 | 100 | 100 | 100 | 100 | 100 | 100
263 | project evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h |  |  | 0 |  |  | 722.7 |  | 2h | [5 empty] | 722.7 |  | 100% |  | 722.7 | 722.7
245 | customer satisfaction survey | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
246 | project team briefing | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
247 | suppliers evaluation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
264 | close phase | 2014-05-19 08:00 | 2014-05-19 17:00 | 1d |  |  | 0 |  |  | 240.9 |  | 7h | [5 empty] | 240.9 |  | 100% |  | 240.9 | 240.9
248 | program manager validation | 2014-05-19 08:00 | 2014-05-19 10:00 | 2h | Employee B | 240.9 | 0 | 0 | 0 | 240.9 | 2014-05-26 08:00 | 2h | 240.9 | 0 | 0 | 0 | 0 | 240.9 | 0 | 100% | Finished | 240.9 | 240.9 | 100 | 100 | 100 | 100 | 100 | 100
249 | end of project | 2014-05-19 17:00 | 2014-05-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-26 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-10-24 08:00 | 2014-03-20 22:00 | 344534.1284 | 258667.0548 | 300587.0561 | 2014-02-26 12:00 | -85867.0736 | 75.08% | -41920.0013 | 86.05% | -16d 4h | 84.43% | 79.24% | 2014-06-27 11:00 | 2014-07-28 15:00 | 2014-09-10 16:00 | 2014-06-25 16:00 | 2014-07-28 15:00 | 2014-08-18 14:00 | 2014-06-11 17:00 | 2014-06-26 16:00 | 2014-07-14 10:00 | 500032.3697 | 532354.7998 | 566240.2037 | 536801.6175 | 609292.3826 | 575082.9314 | 538422.2156 | 533230.7187 | 0.84434 | 0.86054 | 0.75077 | 0.79238 | -16.5 | 0.86054 | 1 | 0.84434 | 1
Tracking 2 | 2014-03-20 22:00 | 2014-05-01 22:00 | 435700.3284 | 355893.5123 | 411441.6761 | 2014-03-24 11:00 | -79806.8161 | 81.68% | -55548.1638 | 86.5% | -28d 5h | 78.95% | 91.86% | 2014-06-25 11:00 | 2014-07-04 15:00 | 2014-08-14 09:00 | 2014-06-24 11:00 | 2014-07-04 15:00 | 2014-07-15 17:00 | 2014-06-30 09:00 | 2014-07-15 09:00 | 2014-07-25 10:00 | 513660.5322 | 529614.9387 | 536582.4489 | 540910.9606 | 556114.5278 | 561118.6373 | 530945.6725 | 531713.6525 | 0.78952 | 0.86499 | 0.81683 | 0.91862 | -28.625 | 0.86499 | 1 | 0.78952 | 1
Tracking 3 | 2014-05-01 22:00 | 2014-05-07 22:00 | 441361.4484 | 376902.1018 | 426824.6661 | 2014-03-28 10:00 | -64459.3466 | 85.4% | -49922.5642 | 88.3% | -28d 6h | 79.46% | 92.4% | 2014-06-18 11:00 | 2014-06-24 16:00 | 2014-07-25 16:00 | 2014-06-17 17:00 | 2014-06-24 16:00 | 2014-07-01 11:00 | 2014-06-30 10:00 | 2014-07-11 16:00 | 2014-07-22 09:00 | 508034.9326 | 518791.6377 | 521923.8462 | 529021.8554 | 534520.2072 | 542558.3831 | 519401.4638 | 520670.4822 | 0.79464 | 0.88304 | 0.85395 | 0.92403 | -28.75 | 0.88304 | 1 | 0.79464 | 1
Tracking 4 | 2014-05-07 22:00 | 2014-05-21 22:00 | 458112.3684 | 423433.7021 | 475424.1361 | 2014-04-21 11:00 | -34678.6663 | 92.43% | -51990.4339 | 89.06% | -22d 5h | 84.92% | 97.31% | 2014-06-04 15:00 | 2014-06-05 14:00 | 2014-07-03 11:00 | 2014-06-06 11:00 | 2014-06-09 10:00 | 2014-06-10 15:00 | 2014-06-20 09:00 | 2014-06-25 16:00 | 2014-06-30 16:00 | 510102.8023 | 514360.7509 | 512942.9397 | 516262.6047 | 517549.6087 | 521276.8718 | 514068.6804 | 514726.8173 | 0.84917 | 0.89064 | 0.9243 | 0.97311 | -22.625 | 0.89064 | 1 | 0.84917 | 1
Closure | 2014-05-21 22:00 | 2014-05-30 22:00 | 458112.3684 | 458112.3684 | 512546.1461 | 2014-05-20 12:00 | 0 | 100% | -54433.7777 | 89.38% | -8d 4h | 94.59% | 100% | 2014-05-20 12:00 | 2014-05-20 12:00 | 2014-06-13 09:00 | 2014-05-30 17:00 | 2014-05-30 17:00 | 2014-05-30 17:00 | 2014-05-30 17:00 | 2014-05-30 17:00 | 2014-05-30 17:00 | 512546.1461 | 512546.1461 | 512546.1461 | 512546.1461 | 512546.1461 | 512546.1461 | 512546.1461 | 512546.1461 | 0.94586 | 0.8938 | 1 | 1 | -8.5 | 0.8938 | 1 | 0.94586 | 1