## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Day Care | 1 |  |  | 2011-11-28 08:00 | 2012-05-23 17:00 | 128d |  |  | 0 |  |  | 0 | 177.375
1 | Werfinrichting | 1.1 |  |  | 2011-11-28 08:00 | 2011-12-02 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 4.375
2 | Eerste fase dak + ontmanteling | 1.2 |  | FS4 | 2011-11-28 08:00 | 2011-12-09 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
3 | Tweede fase metselwerk en vloer | 1.3 | 4FS | FS5 | 2011-12-19 08:00 | 2011-12-30 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 11.375
4 | Plaatsen stalen ligger | 1.4 | 2FS | FS3 | 2011-12-12 08:00 | 2011-12-16 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 4.375
5 | Ruwbouw + rioleringswerken | 1.5 | 3FS | FS7 | 2012-01-02 08:00 | 2012-01-27 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 25.375
6 | Dakwerken | 1.6 | 7SS+2w | FS9;FS10;FS11 | 2012-02-13 08:00 | 2012-03-09 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 25.375
7 | Gevelrenovatie | 1.7 | 5FS | FS8;SS6+2w | 2012-01-30 08:00 | 2012-02-17 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 18.375
8 | Buitenschrijnwerk | 1.8 | 7FS |  | 2012-02-20 08:00 | 2012-02-21 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
9 | Elektriciteit | 1.9 | 6FS | FS14 | 2012-03-12 08:00 | 2012-03-14 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2.375
10 | Sanitair | 1.10 | 6FS | FS14 | 2012-03-12 08:00 | 2012-03-13 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
11 | Verluchting | 1.11 | 6FS | FS14 | 2012-03-12 08:00 | 2012-03-16 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 4.375
12 | Vloerverwarming | 1.12 | 16FS | FS17 | 2012-04-09 08:00 | 2012-04-10 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
13 | Toestellen en aansluitingen | 1.13 | 18SS+1w |  | 2012-04-25 08:00 | 2012-05-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
14 | Pleisterwerken | 1.14 | 9FS;10FS;11FS | FS15 | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 4.375
15 | Uitvulchape | 1.15 | 14FS | FS16+1w;FS19 | 2012-03-26 08:00 | 2012-03-28 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2.375
16 | Vloerisolatie | 1.16 | 15FS+1w | FS12;FS19 | 2012-04-05 08:00 | 2012-04-06 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
17 | Chape | 1.17 | 12FS | FS18+3d;FS19 | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
18 | Gyprowerken | 1.18 | 17FS+3d | SS13+1w | 2012-04-18 08:00 | 2012-05-08 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 20.375
19 | Vals plafond | 1.19 | 15FS;16FS;17FS | FS20 | 2012-04-13 08:00 | 2012-04-19 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 6.375
20 | Binnenschrijnwerk | 1.20 | 19FS | FS22 | 2012-04-20 08:00 | 2012-04-25 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0 | 5.375
21 | Linoleum | 1.21 | 22FS | FS23 | 2012-05-14 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 4.375
22 | Schilderwerken | 1.22 | 20FS | FS21 | 2012-04-26 08:00 | 2012-05-11 17:00 | 12d |  | 0 | 0 | 0 | 0 | 0 | 15.375
23 | Meubilair | 1.23 | 21FS | FS24 | 2012-05-21 08:00 | 2012-05-22 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0 | 1.375
24 | Opkuis | 1.24 | 23FS |  | 2012-05-23 08:00 | 2012-05-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Day Care | 1024h |  |  |  |  | 99 | 100 | 101
1 | Werfinrichting | 40h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
2 | Eerste fase dak + ontmanteling | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
3 | Tweede fase metselwerk en vloer | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
4 | Plaatsen stalen ligger | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Ruwbouw + rioleringswerken | 160h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
6 | Dakwerken | 160h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
7 | Gevelrenovatie | 120h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
8 | Buitenschrijnwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Elektriciteit | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Sanitair | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Verluchting | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
12 | Vloerverwarming | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Toestellen en aansluitingen | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
14 | Pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Uitvulchape | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Vloerisolatie | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Chape | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Gyprowerken | 120h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
19 | Vals plafond | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Linoleum | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Schilderwerken | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Meubilair | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Opkuis | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold