## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Bridge (3) | 1 |  |  | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 | 282.375
1 | Werfinrichting | 1.1 |  |  | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 4.375
2 | Uitgraving bouwputten + aanvullingen | 1.2 |  |  | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 36.375
3 | Paalfundering kant spoor B | 1.3 |  | FS5 | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 13.375
4 | Paalfundering kant spoor A | 1.4 |  |  | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 13.375
5 | Plaatsen grachtelementen B | 1.5 | 3FS | FS6 | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 8.375
6 | Plaatsen schanskorven B | 1.6 | 5FS |  | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 6.375
7 | Funderingszool B | 1.7 |  | FS8 | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 9.375
8 | Grachtelementen A | 1.8 | 7FS | FS9 | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 10.375
9 | Schanskorven A | 1.9 | 8FS |  | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 6.375
10 | Funderingszool A | 1.10 |  |  | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 11.375
11 | Aanvoer en monteren boogbrug | 1.11 |  |  | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 6.375
26 | 1e fase brug | 1.12 |  |  | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 | 23.375
12 | Wapenen | 1.12.1 |  | FS13;FS15 | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 9.375
13 | Betonneren | 1.12.2 | 12FS | FS14+2d | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 0.375
14 | Plaatsen metalen uitkraging | 1.12.3 | 13FS+2d |  | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 0.375
15 | Uitharden | 1.12.4 | 12FS | FS16 | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 9.375
27 | 2e fase brug | 1.13 |  |  | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 | 43.0833
16 | Verplaatsen bekisting + opkuis | 1.13.1 | 15FS |  | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 | 1.375
17 | Wapenen | 1.13.2 |  | FS18;FS21 | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 | 7.375
18 | Betonneren | 1.13.3 | 17FS | FS19+2h | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 | 0.375
19 | Plaatsen metalen uitkraging | 1.13.4 | 18FS+2h | FS20 | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 | 1
20 | Uitharden | 1.13.5 | 19FS |  | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 14
21 | Verbindingsbalken brug | 1.14 | 17FS | FS22+1w | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 | 6.375
22 | Aanbrengen waterdichte rok | 1.15 | 21FS+1w | FS23 | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 | 6.375
23 | Aanvullingen en wegeniswerken | 1.16 | 22FS | FS24;FS25 | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 | 28.375
24 | Plaatsen leuningen | 1.17 | 23FS |  | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 | 34.375
25 | Afwerkingen | 1.18 | 23FS |  | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 | 69.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Bridge (3) | 1624h |  |  |  |  | 99 | 100 | 101
1 | Werfinrichting | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
2 | Uitgraving bouwputten + aanvullingen | 216h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
3 | Paalfundering kant spoor B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Paalfundering kant spoor A | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Plaatsen grachtelementen B | 56h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
6 | Plaatsen schanskorven B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Funderingszool B | 64h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
8 | Grachtelementen A | 56h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
9 | Schanskorven A | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Funderingszool A | 64h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
11 | Aanvoer en monteren boogbrug | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
26 | 1e fase brug | 144h |  |  |  |  | 99 | 100 | 101
12 | Wapenen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
14 | Plaatsen metalen uitkraging | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Uitharden | 64h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
27 | 2e fase brug | 250h |  |  |  |  | 99 | 100 | 101
16 | Verplaatsen bekisting + opkuis | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
17 | Wapenen | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Betonneren | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
19 | Plaatsen metalen uitkraging | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Uitharden | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
21 | Verbindingsbalken brug | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
22 | Aanbrengen waterdichte rok | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
23 | Aanvullingen en wegeniswerken | 168h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
24 | Plaatsen leuningen | 200h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
25 | Afwerkingen | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-09-02 07:00 |  | TP Name | T1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 10d | [5 empty] | 177458.7793 |  | 19.15% |  | 177458.779 | 177458.7793
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 10d | 144294.3594 | 16320 | 17d | 0 | 0 | 144294.3594 | 16320 | 37.04% | Started | 144294.3591 | 144294.3594 | 100 | 37.037 | 37.037 | 100 | 89.839 | 37.037
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 |  | 0 | 0 | 116188.6172 | 10d | 0 | 0 | 0 | 116188.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 |  | 0 | 0 | 124162.3516 | 10d | 0 | 0 | 0 | 124162.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 |  | 0 | 0 | 5169.91 | 7d | 0 | 0 | 0 | 5169.91 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 |  | 0 | 0 | 35864.6992 | 5d | 0 | 0 | 0 | 35864.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 |  | 0 | 0 | 30168.5703 | 8d | 0 | 0 | 0 | 30168.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 |  | 0 | 0 | 5017.85 | 7d | 0 | 0 | 0 | 5017.85 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 |  | 0 | 0 | 34820.0996 | 5d | 0 | 0 | 0 | 34820.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 |  | 0 | 0 | 24957.6309 | 8d | 0 | 0 | 0 | 24957.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 |  | 0 | 0 | 106637.5234 | 5d | 0 | 0 | 0 | 106637.5234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 |  | 0 | 0 | 4494.6 | 8d | 0 | 0 | 0 | 4494.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 |  | 0 | 0 | 6523.0498 | 1d | 0 | 0 | 0 | 6523.0498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 |  | 0 | 0 | 10825.1299 | 1d | 0 | 0 | 0 | 10825.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 8d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 |  | 0 | 0 | 29002.3008 | 2d | 0 | 0 | 0 | 29002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 |  | 0 | 0 | 4967.72 | 6d | 0 | 0 | 0 | 4967.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 |  | 0 | 0 | 6595.5298 | 1d | 0 | 0 | 0 | 6595.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 |  | 0 | 0 | 11538.8799 | 1d | 0 | 0 | 0 | 11538.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 |  | 0 | 0 | 7691.5698 | 5d | 0 | 0 | 0 | 7691.5698 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 |  | 0 | 0 | 50379.3594 | 5d | 0 | 0 | 0 | 50379.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 |  | 0 | 0 | 68251.2305 | 21d | 0 | 0 | 0 | 68251.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-10-07 07:00 |  | TP Name | T2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 35d | [5 empty] | 429779.6581 |  | 46.37% |  | 429779.6582 | 429779.6581
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 3d | 116882.3516 | 7280 | 7d | 0 | 0 | 116882.3516 | 7280 | 30% | Started | 116882.3517 | 116882.3516 | 100 | 30 | 30 | 100 | 94.1367 | 30
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 3d | 2929.91 | 2240 | 4d | 0 | 0 | 2929.91 | 2240 | 42.86% | Started | 2929.9101 | 2929.91 | 100 | 42.8571 | 42.8571 | 100 | 56.6724 | 42.8571
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 |  | 0 | 0 | 35864.6992 | 5d | 0 | 0 | 0 | 35864.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 |  | 0 | 0 | 30168.5703 | 8d | 0 | 0 | 0 | 30168.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 |  | 0 | 0 | 5017.85 | 7d | 0 | 0 | 0 | 5017.85 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 |  | 0 | 0 | 34820.0996 | 5d | 0 | 0 | 0 | 34820.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 |  | 0 | 0 | 24957.6309 | 8d | 0 | 0 | 0 | 24957.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 |  | 0 | 0 | 106637.5234 | 5d | 0 | 0 | 0 | 106637.5234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 |  | 0 | 0 | 4494.6 | 8d | 0 | 0 | 0 | 4494.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 |  | 0 | 0 | 6523.0498 | 1d | 0 | 0 | 0 | 6523.0498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 |  | 0 | 0 | 10825.1299 | 1d | 0 | 0 | 0 | 10825.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 8d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 |  | 0 | 0 | 29002.3008 | 2d | 0 | 0 | 0 | 29002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 |  | 0 | 0 | 4967.72 | 6d | 0 | 0 | 0 | 4967.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 |  | 0 | 0 | 6595.5298 | 1d | 0 | 0 | 0 | 6595.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 |  | 0 | 0 | 11538.8799 | 1d | 0 | 0 | 0 | 11538.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 |  | 0 | 0 | 7691.5698 | 5d | 0 | 0 | 0 | 7691.5698 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 |  | 0 | 0 | 50379.3594 | 5d | 0 | 0 | 0 | 50379.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 |  | 0 | 0 | 68251.2305 | 21d | 0 | 0 | 0 | 68251.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-11-04 07:00 |  | TP Name | T3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 55d | [5 empty] | 512242.3069 |  | 55.26% |  | 512242.3069 | 544250.8772
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 |  | 0 | 0 | 30168.5703 | 8d | 0 | 0 | 0 | 30168.5703 | 0% | Not Started | 0 | 30168.5703 | 100 |  | 0 | 100 |  | 0
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 2d | 32060.0996 | 2760 | 3d | 0 | 0 | 32060.0996 | 2760 | 40% | Started | 32060.0996 | 33900.0996 | 100 | 40 | 40 | 100 | 92.0735 | 40
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 |  | 0 | 0 | 24957.6309 | 8d | 0 | 0 | 0 | 24957.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 |  | 0 | 0 | 106637.5234 | 5d | 0 | 0 | 0 | 106637.5234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 |  | 0 | 0 | 4494.6 | 8d | 0 | 0 | 0 | 4494.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 |  | 0 | 0 | 6523.0498 | 1d | 0 | 0 | 0 | 6523.0498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 |  | 0 | 0 | 10825.1299 | 1d | 0 | 0 | 0 | 10825.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 8d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 |  | 0 | 0 | 29002.3008 | 2d | 0 | 0 | 0 | 29002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 |  | 0 | 0 | 4967.72 | 6d | 0 | 0 | 0 | 4967.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 |  | 0 | 0 | 6595.5298 | 1d | 0 | 0 | 0 | 6595.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 |  | 0 | 0 | 11538.8799 | 1d | 0 | 0 | 0 | 11538.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 |  | 0 | 0 | 7691.5698 | 5d | 0 | 0 | 0 | 7691.5698 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 |  | 0 | 0 | 50379.3594 | 5d | 0 | 0 | 0 | 50379.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 |  | 0 | 0 | 68251.2305 | 21d | 0 | 0 | 0 | 68251.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-12-02 07:00 |  | TP Name | T4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 75d | [5 empty] | 562968.5081 |  | 61.21% |  | 567312.5082 | 679060.6315
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 3d | 20557.6309 | 1760 | 2d | 0 | 0 | 20557.6309 | 1760 | 60% | Started | 22141.631 | 24957.6309 | 100 | 37.5 | 60 | 100 | 82.3701 | 60
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 |  | 0 | 0 | 106637.5234 | 5d | 0 | 0 | 0 | 106637.5234 | 0% | Not Started | 0 | 106637.5234 | 100 |  | 0 | 100 |  | 0
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2294.6
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 |  | 0 | 0 | 4494.6 | 8d | 0 | 0 | 0 | 4494.6 | 0% | Not Started | 0 | 2294.6 | 100 |  | 0 | 100 |  | 0
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 |  | 0 | 0 | 6523.0498 | 1d | 0 | 0 | 0 | 6523.0498 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 |  | 0 | 0 | 10825.1299 | 1d | 0 | 0 | 0 | 10825.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 8d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 |  | 0 | 0 | 29002.3008 | 2d | 0 | 0 | 0 | 29002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 |  | 0 | 0 | 4967.72 | 6d | 0 | 0 | 0 | 4967.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 |  | 0 | 0 | 6595.5298 | 1d | 0 | 0 | 0 | 6595.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 |  | 0 | 0 | 11538.8799 | 1d | 0 | 0 | 0 | 11538.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 |  | 0 | 0 | 7691.5698 | 5d | 0 | 0 | 0 | 7691.5698 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 |  | 0 | 0 | 50379.3594 | 5d | 0 | 0 | 0 | 50379.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 |  | 0 | 0 | 68251.2305 | 21d | 0 | 0 | 0 | 68251.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-01-06 07:00 |  | TP Name | T5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 100d | [5 empty] | 671366.0315 |  | 73.01% |  | 676766.0315 | 703577.5311
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 100% | Finished | 24957.6309 | 24957.6309 | 100 | 62.5 | 100 | 100 | 89.4221 | 100
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 100% | Finished | 106637.5234 | 106637.5234 | 100 | 100 | 100 | 100 | 100 | 100
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 21843.7797
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 |  | 0 | 0 | 4494.6 | 8d | 0 | 0 | 0 | 4494.6 | 0% | Not Started | 0 | 4494.6 | 100 |  | 0 | 100 |  | 0
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 |  | 0 | 0 | 6523.0498 | 1d | 0 | 0 | 0 | 6523.0498 | 0% | Not Started | 0 | 6523.0498 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 |  | 0 | 0 | 10825.1299 | 1d | 0 | 0 | 0 | 10825.1299 | 0% | Not Started | 0 | 10825.1299 | 100 |  | 0 | 100 |  | 0
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 8d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4967.72
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 |  | 0 | 0 | 29002.3008 | 2d | 0 | 0 | 0 | 29002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 |  | 0 | 0 | 4967.72 | 6d | 0 | 0 | 0 | 4967.72 | 0% | Not Started | 0 | 4967.72 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 |  | 0 | 0 | 6595.5298 | 1d | 0 | 0 | 0 | 6595.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 |  | 0 | 0 | 11538.8799 | 1d | 0 | 0 | 0 | 11538.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 |  | 0 | 0 | 7691.5698 | 5d | 0 | 0 | 0 | 7691.5698 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 |  | 0 | 0 | 50379.3594 | 5d | 0 | 0 | 0 | 50379.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 |  | 0 | 0 | 68251.2305 | 21d | 0 | 0 | 0 | 68251.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2014-02-03 07:00 |  | TP Name | T6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 120d | [5 empty] | 691889.8112 |  | 75.37% |  | 698609.8112 | 757126.8114
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 100% | Finished | 24957.6309 | 24957.6309 | 100 | 62.5 | 100 | 100 | 89.4221 | 100
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 100% | Finished | 106637.5234 | 106637.5234 | 100 | 100 | 100 | 100 | 100 | 100
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 12d | [5 empty] | 20523.7797 |  | 100% |  | 21843.7797 | 21843.7797
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 2014-01-16 07:00 | 5d | 3174.6 | 0 | 0 | 0 | 0 | 3174.6 | 0 | 100% | Finished | 4494.6 | 4494.6 | 100 | 62.5 | 100 | 100 | 70.6314 | 100
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 2014-01-23 07:00 | 1d | 6523.0498 | 0 | 0 | 0 | 0 | 6523.0498 | 0 | 100% | Finished | 6523.0498 | 6523.0498 | 100 | 100 | 100 | 100 | 100 | 100
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 2014-01-29 07:00 | 1d | 10825.1299 | 0 | 0 | 0 | 0 | 10825.1299 | 0 | 100% | Finished | 10825.1299 | 10825.1299 | 100 | 100 | 100 | 100 | 100 | 100
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 2014-01-27 07:00 | 5d | 1 | 0 | 5d | 0 | 0 | 1 | 0 | 50% | Started | 1 | 1 | 100 | 62.5 | 50 | 100 | 100 | 50
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 52105.4304
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 |  | 0 | 0 | 29002.3008 | 2d | 0 | 0 | 0 | 29002.3008 | 0% | Not Started | 0 | 29002.3008 | 100 |  | 0 | 100 |  | 0
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 |  | 0 | 0 | 4967.72 | 6d | 0 | 0 | 0 | 4967.72 | 0% | Not Started | 0 | 4967.72 | 100 |  | 0 | 100 |  | 0
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 |  | 0 | 0 | 6595.5298 | 1d | 0 | 0 | 0 | 6595.5298 | 0% | Not Started | 0 | 6595.5298 | 100 |  | 0 | 100 |  | 0
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 |  | 0 | 0 | 11538.8799 | 1d | 0 | 0 | 0 | 11538.8799 | 0% | Not Started | 0 | 11538.8799 | 100 |  | 0 | 100 |  | 0
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 |  | 0 | 0 | 7691.5698 | 5d | 0 | 0 | 0 | 7691.5698 | 0% | Not Started | 0 | 6411.5698 | 100 |  | 0 | 100 |  | 0
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 |  | 0 | 0 | 50379.3594 | 5d | 0 | 0 | 0 | 50379.3594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 |  | 0 | 0 | 68251.2305 | 21d | 0 | 0 | 0 | 68251.2305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2014-03-03 07:00 |  | TP Name | T7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 140d | [5 empty] | 751246.8114 |  | 81.82% |  | 758406.8114 | 864037.4012
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 100% | Finished | 24957.6309 | 24957.6309 | 100 | 62.5 | 100 | 100 | 89.4221 | 100
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 100% | Finished | 106637.5234 | 106637.5234 | 100 | 100 | 100 | 100 | 100 | 100
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 17d | [5 empty] | 20523.7797 |  | 100% |  | 21843.7797 | 21843.7797
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 2014-01-16 07:00 | 5d | 3174.6 | 0 | 0 | 0 | 0 | 3174.6 | 0 | 100% | Finished | 4494.6 | 4494.6 | 100 | 62.5 | 100 | 100 | 70.6314 | 100
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 2014-01-23 07:00 | 1d | 6523.0498 | 0 | 0 | 0 | 0 | 6523.0498 | 0 | 100% | Finished | 6523.0498 | 6523.0498 | 100 | 100 | 100 | 100 | 100 | 100
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 2014-01-29 07:00 | 1d | 10825.1299 | 0 | 0 | 0 | 0 | 10825.1299 | 0 | 100% | Finished | 10825.1299 | 10825.1299 | 100 | 100 | 100 | 100 | 100 | 100
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 2014-01-27 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 125 | 100 | 100 | 100 | 100
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 15d | [5 empty] | 51665.4304 |  | 100% |  | 52105.4304 | 52105.4304
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 | 2014-02-10 07:00 | 2d | 29002.3008 | 0 | 0 | 0 | 0 | 29002.3008 | 0 | 100% | Finished | 29002.3008 | 29002.3008 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 | 2014-02-10 07:00 | 5d | 4527.72 | 0 | 0 | 0 | 0 | 4527.72 | 0 | 100% | Finished | 4967.72 | 4967.72 | 100 | 83.3333 | 100 | 100 | 91.1428 | 100
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 | 2014-02-17 07:00 | 1d | 6595.5298 | 0 | 0 | 0 | 0 | 6595.5298 | 0 | 100% | Finished | 6595.5298 | 6595.5298 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 | 2014-02-20 07:00 | 1d | 11538.8799 | 0 | 0 | 0 | 0 | 11538.8799 | 0 | 100% | Finished | 11538.8799 | 11538.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-02-21 07:00 | 6d | 1 | 0 | 4d | 0 | 0 | 1 | 0 | 60% | Started | 1 | 1 | 100 | 60 | 60 | 100 | 100 | 60
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 | 2014-02-17 07:00 | 5d | 7691.5698 | 0 | 0 | 0 | 0 | 7691.5698 | 0 | 100% | Finished | 7691.5698 | 7691.5698 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 |  | 0 | 0 | 50379.3594 | 5d | 0 | 0 | 0 | 50379.3594 | 0% | Not Started | 0 | 50379.3594 | 100 |  | 0 | 100 |  | 0
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 |  | 0 | 0 | 68251.2305 | 21d | 0 | 0 | 0 | 68251.2305 | 0% | Not Started | 0 | 55251.2305 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2014-04-07 07:00 |  | TP Name | T8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 165d | [5 empty] | 868877.4012 |  | 93.87% |  | 870037.4017 | 897928.0109
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 100% | Finished | 24957.6309 | 24957.6309 | 100 | 62.5 | 100 | 100 | 89.4221 | 100
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 100% | Finished | 106637.5234 | 106637.5234 | 100 | 100 | 100 | 100 | 100 | 100
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 17d | [5 empty] | 20523.7797 |  | 100% |  | 21843.7797 | 21843.7797
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 2014-01-16 07:00 | 5d | 3174.6 | 0 | 0 | 0 | 0 | 3174.6 | 0 | 100% | Finished | 4494.6 | 4494.6 | 100 | 62.5 | 100 | 100 | 70.6314 | 100
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 2014-01-23 07:00 | 1d | 6523.0498 | 0 | 0 | 0 | 0 | 6523.0498 | 0 | 100% | Finished | 6523.0498 | 6523.0498 | 100 | 100 | 100 | 100 | 100 | 100
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 2014-01-29 07:00 | 1d | 10825.1299 | 0 | 0 | 0 | 0 | 10825.1299 | 0 | 100% | Finished | 10825.1299 | 10825.1299 | 100 | 100 | 100 | 100 | 100 | 100
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 2014-01-27 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 125 | 100 | 100 | 100 | 100
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 19d | [5 empty] | 51665.4304 |  | 100% |  | 52105.4304 | 52105.4304
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 | 2014-02-10 07:00 | 2d | 29002.3008 | 0 | 0 | 0 | 0 | 29002.3008 | 0 | 100% | Finished | 29002.3008 | 29002.3008 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 | 2014-02-10 07:00 | 5d | 4527.72 | 0 | 0 | 0 | 0 | 4527.72 | 0 | 100% | Finished | 4967.72 | 4967.72 | 100 | 83.3333 | 100 | 100 | 91.1428 | 100
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 | 2014-02-17 07:00 | 1d | 6595.5298 | 0 | 0 | 0 | 0 | 6595.5298 | 0 | 100% | Finished | 6595.5298 | 6595.5298 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 | 2014-02-20 07:00 | 1d | 11538.8799 | 0 | 0 | 0 | 0 | 11538.8799 | 0 | 100% | Finished | 11538.8799 | 11538.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-02-21 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 | 2014-02-17 07:00 | 5d | 7691.5698 | 0 | 0 | 0 | 0 | 7691.5698 | 0 | 100% | Finished | 7691.5698 | 7691.5698 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 | 2014-03-03 07:00 | 5d | 50379.3594 | 0 | 0 | 0 | 0 | 50379.3594 | 0 | 100% | Finished | 50379.3594 | 50379.3594 | 100 | 100 | 100 | 100 | 100 | 100
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 | 2014-03-10 07:00 | 20d | 67251.2305 | 10000 | 10d | 0 | 0 | 67251.2305 | 10000 | 66.67% | Started | 61251.2309 | 68251.2305 | 100 | 95.2381 | 66.6667 | 100 | 98.5348 | 66.6667
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 |  | 0 | 0 | 26990.5996 | 25d | 0 | 0 | 0 | 26990.5996 | 0% | Not Started | 0 | 14750.5996 | 100 |  | 0 | 100 |  | 0
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 |  | 0 | 0 | 22860.01 | 50d | 0 | 0 | 0 | 22860.01 | 0% | Not Started | 0 | 6140.01 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2014-05-05 07:00 |  | TP Name | T9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 185d | [5 empty] | 895328.0109 |  | 97.92% |  | 907638.0109 | 918968.0109
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 100% | Finished | 24957.6309 | 24957.6309 | 100 | 62.5 | 100 | 100 | 89.4221 | 100
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 100% | Finished | 106637.5234 | 106637.5234 | 100 | 100 | 100 | 100 | 100 | 100
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 17d | [5 empty] | 20523.7797 |  | 100% |  | 21843.7797 | 21843.7797
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 2014-01-16 07:00 | 5d | 3174.6 | 0 | 0 | 0 | 0 | 3174.6 | 0 | 100% | Finished | 4494.6 | 4494.6 | 100 | 62.5 | 100 | 100 | 70.6314 | 100
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 2014-01-23 07:00 | 1d | 6523.0498 | 0 | 0 | 0 | 0 | 6523.0498 | 0 | 100% | Finished | 6523.0498 | 6523.0498 | 100 | 100 | 100 | 100 | 100 | 100
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 2014-01-29 07:00 | 1d | 10825.1299 | 0 | 0 | 0 | 0 | 10825.1299 | 0 | 100% | Finished | 10825.1299 | 10825.1299 | 100 | 100 | 100 | 100 | 100 | 100
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 2014-01-27 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 125 | 100 | 100 | 100 | 100
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 19d | [5 empty] | 51665.4304 |  | 100% |  | 52105.4304 | 52105.4304
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 | 2014-02-10 07:00 | 2d | 29002.3008 | 0 | 0 | 0 | 0 | 29002.3008 | 0 | 100% | Finished | 29002.3008 | 29002.3008 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 | 2014-02-10 07:00 | 5d | 4527.72 | 0 | 0 | 0 | 0 | 4527.72 | 0 | 100% | Finished | 4967.72 | 4967.72 | 100 | 83.3333 | 100 | 100 | 91.1428 | 100
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 | 2014-02-17 07:00 | 1d | 6595.5298 | 0 | 0 | 0 | 0 | 6595.5298 | 0 | 100% | Finished | 6595.5298 | 6595.5298 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 | 2014-02-20 07:00 | 1d | 11538.8799 | 0 | 0 | 0 | 0 | 11538.8799 | 0 | 100% | Finished | 11538.8799 | 11538.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-02-21 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 | 2014-02-17 07:00 | 5d | 7691.5698 | 0 | 0 | 0 | 0 | 7691.5698 | 0 | 100% | Finished | 7691.5698 | 7691.5698 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 | 2014-03-03 07:00 | 5d | 50379.3594 | 0 | 0 | 0 | 0 | 50379.3594 | 0 | 100% | Finished | 50379.3594 | 50379.3594 | 100 | 100 | 100 | 100 | 100 | 100
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 | 2014-03-10 07:00 | 30d | 77251.2305 | 0 | 0 | 0 | 0 | 77251.2305 | 0 | 100% | Finished | 68251.2305 | 68251.2305 | 100 | 142.8571 | 100 | 100 | 113.1866 | 100
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 | 2014-04-21 07:00 | 5d | 13390.5996 | 0 | 0 | 0 | 0 | 13390.5996 | 0 | 100% | Finished | 26990.5996 | 26990.5996 | 100 | 20 | 100 | 100 | 49.6121 | 100
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 | 2014-04-28 07:00 | 5d | 3060.01 | 15400 | 35d | 0 | 0 | 3060.01 | 15400 | 12.5% | Started | 3610.01 | 14940.01 | 100 | 10 | 12.5 | 100 | 13.3859 | 12.5

## TP10
| TP Status Date | 2014-06-02 07:00 |  | TP Name | T10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 205d | [5 empty] | 904128.0109 |  | 99.11% |  | 918638.0109 | 926888.0109
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 100% | Finished | 24957.6309 | 24957.6309 | 100 | 62.5 | 100 | 100 | 89.4221 | 100
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 100% | Finished | 106637.5234 | 106637.5234 | 100 | 100 | 100 | 100 | 100 | 100
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 17d | [5 empty] | 20523.7797 |  | 100% |  | 21843.7797 | 21843.7797
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 2014-01-16 07:00 | 5d | 3174.6 | 0 | 0 | 0 | 0 | 3174.6 | 0 | 100% | Finished | 4494.6 | 4494.6 | 100 | 62.5 | 100 | 100 | 70.6314 | 100
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 2014-01-23 07:00 | 1d | 6523.0498 | 0 | 0 | 0 | 0 | 6523.0498 | 0 | 100% | Finished | 6523.0498 | 6523.0498 | 100 | 100 | 100 | 100 | 100 | 100
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 2014-01-29 07:00 | 1d | 10825.1299 | 0 | 0 | 0 | 0 | 10825.1299 | 0 | 100% | Finished | 10825.1299 | 10825.1299 | 100 | 100 | 100 | 100 | 100 | 100
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 2014-01-27 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 125 | 100 | 100 | 100 | 100
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 19d | [5 empty] | 51665.4304 |  | 100% |  | 52105.4304 | 52105.4304
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 | 2014-02-10 07:00 | 2d | 29002.3008 | 0 | 0 | 0 | 0 | 29002.3008 | 0 | 100% | Finished | 29002.3008 | 29002.3008 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 | 2014-02-10 07:00 | 5d | 4527.72 | 0 | 0 | 0 | 0 | 4527.72 | 0 | 100% | Finished | 4967.72 | 4967.72 | 100 | 83.3333 | 100 | 100 | 91.1428 | 100
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 | 2014-02-17 07:00 | 1d | 6595.5298 | 0 | 0 | 0 | 0 | 6595.5298 | 0 | 100% | Finished | 6595.5298 | 6595.5298 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 | 2014-02-20 07:00 | 1d | 11538.8799 | 0 | 0 | 0 | 0 | 11538.8799 | 0 | 100% | Finished | 11538.8799 | 11538.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-02-21 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 | 2014-02-17 07:00 | 5d | 7691.5698 | 0 | 0 | 0 | 0 | 7691.5698 | 0 | 100% | Finished | 7691.5698 | 7691.5698 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 | 2014-03-03 07:00 | 5d | 50379.3594 | 0 | 0 | 0 | 0 | 50379.3594 | 0 | 100% | Finished | 50379.3594 | 50379.3594 | 100 | 100 | 100 | 100 | 100 | 100
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 | 2014-03-10 07:00 | 30d | 77251.2305 | 0 | 0 | 0 | 0 | 77251.2305 | 0 | 100% | Finished | 68251.2305 | 68251.2305 | 100 | 142.8571 | 100 | 100 | 113.1866 | 100
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 | 2014-04-21 07:00 | 5d | 13390.5996 | 0 | 0 | 0 | 0 | 13390.5996 | 0 | 100% | Finished | 26990.5996 | 26990.5996 | 100 | 20 | 100 | 100 | 49.6121 | 100
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 | 2014-04-28 07:00 | 25d | 11860.01 | 6600 | 15d | 0 | 0 | 11860.01 | 6600 | 62.5% | Started | 14610.01 | 22860.01 | 100 | 50 | 62.5 | 100 | 51.881 | 62.5

## TP11
| TP Status Date | 2014-07-07 07:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (3) | 2013-08-19 07:00 | 2014-05-28 16:00 | 203d |  |  | 753448.0109 |  |  | 926888.0109 |  | 220d | [5 empty] | 910728.0109 |  | 100% |  | 926888.0109 | 926888.0109
1 | Werfinrichting | 2013-08-19 07:00 | 2013-08-23 16:00 | 5d |  | 0 | 27564.4199 | 140 | 5600 | 33164.4199 | 2013-08-19 07:00 | 5d | 33164.4199 | 0 | 0 | 0 | 0 | 33164.4199 | 0 | 100% | Finished | 33164.4199 | 33164.4199 | 100 | 100 | 100 | 100 | 100 | 100
2 | Uitgraving bouwputten + aanvullingen | 2013-08-19 07:00 | 2013-09-24 16:00 | 27d |  | 0 | 134694.3594 | 120 | 25920 | 160614.3594 | 2013-08-19 07:00 | 27d | 160614.3594 | 0 | 0 | 0 | 0 | 160614.3594 | 0 | 100% | Finished | 160614.3594 | 160614.3594 | 100 | 100 | 100 | 100 | 100 | 100
3 | Paalfundering kant spoor B | 2013-09-18 07:00 | 2013-10-01 16:00 | 10d |  | 0 | 105788.6172 | 130 | 10400 | 116188.6172 | 2013-09-18 07:00 | 10d | 116188.6172 | 0 | 0 | 0 | 0 | 116188.6172 | 0 | 100% | Finished | 116188.6172 | 116188.6172 | 100 | 100 | 100 | 100 | 100 | 100
4 | Paalfundering kant spoor A | 2013-10-02 07:00 | 2013-10-15 16:00 | 10d |  | 0 | 113762.3516 | 130 | 10400 | 124162.3516 | 2013-10-02 07:00 | 10d | 124162.3516 | 0 | 0 | 0 | 0 | 124162.3516 | 0 | 100% | Finished | 124162.3516 | 124162.3516 | 100 | 100 | 100 | 100 | 100 | 100
5 | Plaatsen grachtelementen B | 2013-10-02 07:00 | 2013-10-10 16:00 | 7d |  | 0 | 1249.91 | 70 | 3920 | 5169.91 | 2013-10-02 07:00 | 7d | 5169.91 | 0 | 0 | 0 | 0 | 5169.91 | 0 | 100% | Finished | 5169.91 | 5169.91 | 100 | 100 | 100 | 100 | 100 | 100
6 | Plaatsen schanskorven B | 2013-10-11 07:00 | 2013-10-17 16:00 | 5d |  | 0 | 31464.6992 | 110 | 4400 | 35864.6992 | 2013-10-11 07:00 | 5d | 35864.6992 | 0 | 0 | 0 | 0 | 35864.6992 | 0 | 100% | Finished | 35864.6992 | 35864.6992 | 100 | 100 | 100 | 100 | 100 | 100
7 | Funderingszool B | 2013-10-08 07:00 | 2013-10-17 16:00 | 8d |  | 0 | 22808.5703 | 115 | 7360 | 30168.5703 | 2013-11-20 07:00 | 5d | 27408.5703 | 0 | 0 | 0 | 0 | 27408.5703 | 0 | 100% | Finished | 30168.5703 | 30168.5703 | 100 | 62.5 | 100 | 100 | 90.8514 | 100
8 | Grachtelementen A | 2013-10-18 07:00 | 2013-10-28 16:00 | 7d |  | 0 | 817.85 | 75 | 4200 | 5017.85 | 2013-10-18 07:00 | 7d | 5017.85 | 0 | 0 | 0 | 0 | 5017.85 | 0 | 100% | Finished | 5017.85 | 5017.85 | 100 | 100 | 100 | 100 | 100 | 100
9 | Schanskorven A | 2013-10-29 07:00 | 2013-11-04 16:00 | 5d |  | 0 | 30220.0996 | 115 | 4600 | 34820.0996 | 2013-10-29 07:00 | 5d | 34820.0996 | 0 | 0 | 0 | 0 | 34820.0996 | 0 | 100% | Finished | 34820.0996 | 34820.0996 | 100 | 100 | 100 | 100 | 100 | 100
10 | Funderingszool A | 2013-11-07 07:00 | 2013-11-18 16:00 | 8d |  | 0 | 17917.6309 | 110 | 7040 | 24957.6309 | 2013-11-27 07:00 | 5d | 22317.6309 | 0 | 0 | 0 | 0 | 22317.6309 | 0 | 100% | Finished | 24957.6309 | 24957.6309 | 100 | 62.5 | 100 | 100 | 89.4221 | 100
11 | Aanvoer en monteren boogbrug | 2013-11-20 07:00 | 2013-11-26 16:00 | 5d |  | 0 | 101037.5234 | 140 | 5600 | 106637.5234 | 2013-12-04 07:00 | 5d | 106637.5234 | 0 | 0 | 0 | 0 | 106637.5234 | 0 | 100% | Finished | 106637.5234 | 106637.5234 | 100 | 100 | 100 | 100 | 100 | 100
26 | 1e fase brug | 2013-11-27 07:00 | 2013-12-20 16:00 | 18d |  |  | 16483.7797 |  |  | 21843.7797 |  | 17d | [5 empty] | 20523.7797 |  | 100% |  | 21843.7797 | 21843.7797
12 | Wapenen | 2013-11-27 07:00 | 2013-12-06 16:00 | 8d |  | 0 | 974.6 | 55 | 3520 | 4494.6 | 2014-01-16 07:00 | 5d | 3174.6 | 0 | 0 | 0 | 0 | 3174.6 | 0 | 100% | Finished | 4494.6 | 4494.6 | 100 | 62.5 | 100 | 100 | 70.6314 | 100
13 | Betonneren | 2013-12-09 07:00 | 2013-12-09 16:00 | 1d |  | 0 | 5563.0498 | 120 | 960 | 6523.0498 | 2014-01-23 07:00 | 1d | 6523.0498 | 0 | 0 | 0 | 0 | 6523.0498 | 0 | 100% | Finished | 6523.0498 | 6523.0498 | 100 | 100 | 100 | 100 | 100 | 100
14 | Plaatsen metalen uitkraging | 2013-12-12 07:00 | 2013-12-12 16:00 | 1d |  | 0 | 9945.1299 | 110 | 880 | 10825.1299 | 2014-01-29 07:00 | 1d | 10825.1299 | 0 | 0 | 0 | 0 | 10825.1299 | 0 | 100% | Finished | 10825.1299 | 10825.1299 | 100 | 100 | 100 | 100 | 100 | 100
15 | Uitharden | 2013-12-11 07:00 | 2013-12-20 16:00 | 8d |  | 0 | 1 | 0 | 0 | 1 | 2014-01-27 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 125 | 100 | 100 | 100 | 100
27 | 2e fase brug | 2013-12-17 07:00 | 2014-01-29 09:00 | 31d 2h |  |  | 41465.4304 |  |  | 52105.4304 |  | 19d | [5 empty] | 51665.4304 |  | 100% |  | 52105.4304 | 52105.4304
16 | Verplaatsen bekisting + opkuis | 2014-01-08 07:00 | 2014-01-09 16:00 | 2d |  | 0 | 23882.3008 | 320 | 5120 | 29002.3008 | 2014-02-10 07:00 | 2d | 29002.3008 | 0 | 0 | 0 | 0 | 29002.3008 | 0 | 100% | Finished | 29002.3008 | 29002.3008 | 100 | 100 | 100 | 100 | 100 | 100
17 | Wapenen | 2013-12-17 07:00 | 2013-12-24 16:00 | 6d |  | 0 | 2327.72 | 55 | 2640 | 4967.72 | 2014-02-10 07:00 | 5d | 4527.72 | 0 | 0 | 0 | 0 | 4527.72 | 0 | 100% | Finished | 4967.72 | 4967.72 | 100 | 83.3333 | 100 | 100 | 91.1428 | 100
18 | Betonneren | 2014-01-13 07:00 | 2014-01-13 16:00 | 1d |  | 0 | 5635.5298 | 120 | 960 | 6595.5298 | 2014-02-17 07:00 | 1d | 6595.5298 | 0 | 0 | 0 | 0 | 6595.5298 | 0 | 100% | Finished | 6595.5298 | 6595.5298 | 100 | 100 | 100 | 100 | 100 | 100
19 | Plaatsen metalen uitkraging | 2014-01-14 09:00 | 2014-01-15 09:00 | 1d |  | 0 | 9618.8799 | 240 | 1920 | 11538.8799 | 2014-02-20 07:00 | 1d | 11538.8799 | 0 | 0 | 0 | 0 | 11538.8799 | 0 | 100% | Finished | 11538.8799 | 11538.8799 | 100 | 100 | 100 | 100 | 100 | 100
20 | Uitharden | 2014-01-15 09:00 | 2014-01-29 09:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2014-02-21 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
21 | Verbindingsbalken brug | 2014-01-29 07:00 | 2014-02-04 16:00 | 5d |  | 0 | 4491.5698 | 80 | 3200 | 7691.5698 | 2014-02-17 07:00 | 5d | 7691.5698 | 0 | 0 | 0 | 0 | 7691.5698 | 0 | 100% | Finished | 7691.5698 | 7691.5698 | 100 | 100 | 100 | 100 | 100 | 100
22 | Aanbrengen waterdichte rok | 2014-02-12 07:00 | 2014-02-18 16:00 | 5d |  | 0 | 45579.3594 | 120 | 4800 | 50379.3594 | 2014-03-03 07:00 | 5d | 50379.3594 | 0 | 0 | 0 | 0 | 50379.3594 | 0 | 100% | Finished | 50379.3594 | 50379.3594 | 100 | 100 | 100 | 100 | 100 | 100
23 | Aanvullingen en wegeniswerken | 2014-02-19 07:00 | 2014-03-19 16:00 | 21d |  | 0 | 47251.2305 | 125 | 21000 | 68251.2305 | 2014-03-10 07:00 | 30d | 77251.2305 | 0 | 0 | 0 | 0 | 77251.2305 | 0 | 100% | Finished | 68251.2305 | 68251.2305 | 100 | 142.8571 | 100 | 100 | 113.1866 | 100
24 | Plaatsen leuningen | 2014-03-27 07:00 | 2014-04-30 16:00 | 25d |  | 0 | 9990.5996 | 85 | 17000 | 26990.5996 | 2014-04-21 07:00 | 5d | 13390.5996 | 0 | 0 | 0 | 0 | 13390.5996 | 0 | 100% | Finished | 26990.5996 | 26990.5996 | 100 | 20 | 100 | 100 | 49.6121 | 100
25 | Afwerkingen | 2014-03-20 07:00 | 2014-05-28 16:00 | 50d |  | 0 | 860.01 | 55 | 22000 | 22860.01 | 2014-04-28 07:00 | 40d | 18460.01 | 0 | 0 | 0 | 0 | 18460.01 | 0 | 100% | Finished | 22860.01 | 22860.01 | 100 | 80 | 100 | 100 | 80.7524 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | Yes
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | No
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
T1 | 2013-08-19 07:00 | 2013-09-02 07:00 | 177458.7793 | 177458.779 | 177458.7793 | 2013-08-30 16:00 | -0.00031471 | 100% | -0.00031471 | 100% | 0 | 100% | 100% | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 926888.0112 | 926888.0125 | 926888.0125 | 926888.0112 | 926888.0138 | 926888.0125 | 926888.0125 | 926888.0122 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T2 | 2013-09-02 07:00 | 2013-10-07 07:00 | 429779.6581 | 429779.6582 | 429779.6581 | 2013-10-04 16:00 | 0.00014067 | 100% | 0.00014067 | 100% | 0 | 100% | 100% | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-28 16:00 | 926888.0107 | 926888.0106 | 926888.0106 | 926888.0107 | 926888.0104 | 926888.0106 | 926888.0106 | 926888.0106 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
T3 | 2013-10-07 07:00 | 2013-11-04 07:00 | 544250.8772 | 512242.3069 | 512242.3069 | 2013-10-28 16:00 | -32008.5703 | 94.12% | 2.7418e-05 | 100% | -4d | 92.73% | 94.09% | 2014-06-06 16:00 | 2014-06-16 12:00 | 2014-06-16 12:00 | 2014-06-03 09:00 | 2014-06-16 12:00 | 2014-06-16 12:00 | 2014-06-03 16:00 | 2014-06-19 15:00 | 2014-06-19 15:00 | 926888.0108 | 926888.0108 | 952798.0459 | 959409.2425 | 952798.0459 | 959409.2425 | 931823.3039 | 933008.2426 | 0.92727 | 1 | 0.94119 | 0.94089 | -4 | 1 | 1 | 0.92727 | 1
T4 | 2013-11-04 07:00 | 2013-12-02 07:00 | 679060.6315 | 567312.5082 | 562968.5081 | 2013-11-13 14:00 | -111748.1232 | 83.54% | 4344.0002 | 100.8% | -12d 2h | 83.67% | 100% | 2014-07-02 11:00 | 2014-07-23 16:00 | 2014-07-22 08:00 | 2014-06-16 10:00 | 2014-07-23 16:00 | 2014-07-22 14:00 | 2014-06-16 09:00 | 2014-07-23 12:00 | 2014-07-22 10:00 | 922544.0107 | 919790.6851 | 993372.4994 | 992740.0252 | 990076.8291 | 989449.1978 | 932423.0664 | 932329.7472 | 0.83667 | 1.0077 | 0.83544 | 1 | -12.25 | 1.0077 | 1 | 0.83667 | 1
T5 | 2013-12-02 07:00 | 2014-01-06 07:00 | 703577.5311 | 676766.0315 | 671366.0315 | 2013-11-26 16:00 | -26811.4996 | 96.19% | 5400 | 100.8% | -28d | 72% | 100% | 2014-06-05 15:00 | 2014-06-09 16:00 | 2014-06-06 10:00 | 2014-06-03 14:00 | 2014-06-09 16:00 | 2014-06-09 08:00 | 2014-07-07 16:00 | 2014-09-16 16:00 | 2014-09-15 11:00 | 921488.0109 | 919492.2566 | 931397.1154 | 1018757.6695 | 929322.2952 | 1015985.7886 | 921785.2171 | 934531.9225 | 0.72 | 1.008 | 0.96189 | 1 | -28 | 1.008 | 1 | 0.72 | 1
T6 | 2014-01-06 07:00 | 2014-02-03 07:00 | 757126.8114 | 698609.8112 | 691889.8112 | 2013-12-16 16:00 | -58517.0002 | 92.27% | 6720 | 101% | -34d | 71.67% | 100% | 2014-06-16 15:00 | 2014-06-20 16:00 | 2014-06-18 15:00 | 2014-06-11 09:00 | 2014-06-20 16:00 | 2014-06-19 16:00 | 2014-07-15 16:00 | 2014-09-18 09:00 | 2014-09-16 12:00 | 920168.0109 | 917972.1793 | 939289.0642 | 1010417.5317 | 936909.3052 | 1007353.5806 | 921936.5237 | 931903.8939 | 0.71667 | 1.0097 | 0.92271 | 1 | -34 | 1.0097 | 1 | 0.71667 | 1
T7 | 2014-02-03 07:00 | 2014-03-03 07:00 | 864037.4012 | 758406.8114 | 751246.8114 | 2014-02-11 16:00 | -105630.5898 | 87.77% | 7160 | 101% | -13d | 90.71% | 100% | 2014-07-01 08:00 | 2014-07-08 09:00 | 2014-07-04 08:00 | 2014-06-23 08:00 | 2014-07-08 09:00 | 2014-07-07 10:00 | 2014-06-16 16:00 | 2014-06-26 14:00 | 2014-06-25 16:00 | 919728.0109 | 918137.4062 | 943194.0033 | 936974.1179 | 941381.8599 | 935220.6955 | 922611.358 | 921592.7488 | 0.90714 | 1.0095 | 0.87775 | 1 | -13 | 1.0095 | 1 | 0.90714 | 1
T8 | 2014-03-03 07:00 | 2014-04-07 07:00 | 897928.0109 | 870037.4017 | 868877.4012 | 2014-03-10 16:00 | -27890.6092 | 96.89% | 1160.0004 | 100.1% | -19d | 88.48% | 100% | 2014-06-06 08:00 | 2014-06-06 11:00 | 2014-06-06 09:00 | 2014-06-05 08:00 | 2014-06-06 11:00 | 2014-06-06 11:00 | 2014-06-24 16:00 | 2014-07-04 10:00 | 2014-07-04 10:00 | 925728.0104 | 925652.2129 | 927550.4587 | 933126.3774 | 927472.2313 | 933040.7157 | 926021.9718 | 927004.6153 | 0.88485 | 1.0013 | 0.96894 | 1 | -19 | 1.0013 | 1 | 0.88485 | 1
T9 | 2014-04-07 07:00 | 2014-05-05 07:00 | 918968.0109 | 907638.0109 | 895328.0109 | 2014-04-17 12:00 | -11330 | 98.77% | 12310 | 101.4% | -11d 3h | 93.85% | 99.3% | 2014-06-02 11:00 | 2014-06-02 11:00 | 2014-05-28 14:00 | 2014-06-02 09:00 | 2014-06-02 11:00 | 2014-06-02 09:00 | 2014-06-13 10:00 | 2014-06-17 09:00 | 2014-06-16 15:00 | 914578.0109 | 914316.9294 | 914818.3077 | 915839.17 | 914553.9671 | 915560.9838 | 914415.1307 | 914603.0294 | 0.93851 | 1.0137 | 0.98767 | 0.99303 | -11.375 | 1.0137 | 1 | 0.93851 | 1
T10 | 2014-05-05 07:00 | 2014-06-02 07:00 | 926888.0109 | 918638.0109 | 904128.0109 | 2014-05-02 09:00 | -8250 | 99.11% | 14510 | 101.6% | -20d 6h | 89.88% | 100% | 2014-05-30 14:00 | 2014-05-30 15:00 | 2014-05-27 12:00 | 2014-06-03 15:00 | 2014-06-03 15:00 | 2014-06-03 14:00 | 2014-06-26 14:00 | 2014-06-30 15:00 | 2014-06-30 11:00 | 912378.0109 | 912247.7011 | 912452.1015 | 913307.1153 | 912320.6215 | 913162.1303 | 912287.7742 | 912439.558 | 0.89878 | 1.016 | 0.9911 | 1 | -20.75 | 1.016 | 1 | 0.89878 | 1
Actual Schedule | 2014-06-02 07:00 | 2014-07-07 07:00 | 926888.0109 | 926888.0109 | 910728.0109 | 2014-05-28 16:00 | 0 | 100% | 16160 | 101.8% | -27d | 88.26% | 100% | 2014-05-28 16:00 | 2014-05-28 16:00 | 2014-05-23 11:00 | 2014-07-04 16:00 | 2014-07-04 16:00 | 2014-07-04 16:00 | 2014-07-04 16:00 | 2014-07-04 16:00 | 2014-07-04 16:00 | 910728.0109 | 910728.0109 | 910728.0109 | 910728.0109 | 910728.0109 | 910728.0109 | 910728.0109 | 910728.0109 | 0.88261 | 1.0177 | 1 | 1 | -27 | 1.0177 | 1 | 0.88261 | 1