## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Office Finishing Works (1) | 1 |  |  | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 | 329.375
3 | Diversen | 1.1 |  | SS2;SS1;SS5 | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 120.375
10 | Regiewerken | 1.2 |  | SS2;SS1;SS5 | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 | 120.375
11 | Zuivere OA (1) | 1.3 |  | SS2;SS1;SS5 | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 | 120.375
4 | Zuivere OA (2) | 1.4 |  | SS2;SS1;SS5 | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 151.375
1 | Verplaatsbare wanden (1) | 1.5 | 3SS;10SS;11SS;4SS | FS6;FS8;FS9 | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 142.375
5 | Coördinatie OA | 1.6 | 3SS;10SS;11SS;4SS |  | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 | 111.375
2 | Verplaatsbare wanden (2) | 1.7 | 3SS;10SS;11SS;4SS |  | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 0.375
6 | Coördinatie opmerkingen | 1.8 | 1FS | FS7 | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 | 65.375
8 | Systeemwanden | 1.9 | 1FS | FS7 | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 | 65.375
9 | Opmerkingen | 1.10 | 1FS | FS7 | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 | 2.375
7 | Verplaatsbare wanden (3) | 1.11 | 6FS;8FS;9FS |  | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 | 34.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Office Finishing Works (1) | 1888h |  |  |  |  | 99 | 100 | 101
3 | Diversen | 696h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Regiewerken | 696h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Zuivere OA (1) | 696h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Zuivere OA (2) | 880h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Verplaatsbare wanden (1) | 824h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Coördinatie OA | 640h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Verplaatsbare wanden (2) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Coördinatie opmerkingen | 384h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Systeemwanden | 384h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Opmerkingen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Verplaatsbare wanden (3) | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2010-08-31 09:00 |  | TP Name | periode 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 21d 1h | [5 empty] | 143782.3451 |  | 19.35% |  | 216475.2251 | 11738.7402
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 22d | 3849.1201 | 11372.4004 | 65d | -1858.38 | 0 | 1990.7401 | 11372.4004 | 25.29% | Started | 3849.1202 | 3696.0301 | 100 | 25.2874 | 25.2874 | 100 | 13.0785 | 25.2874
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 |  | 0 | 0 | 1127.52 | 87d | 0 | 0 | 0 | 1127.52 | 0% | Not Started | 0 | 273.78 | 100 |  | 0 | 100 |  | 0
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 |  | 0 | 0 | 2463.84 | 87d | 0 | 0 | 0 | 2463.84 | 0% | Not Started | 0 | 598.26 | 100 |  | 0 | 100 |  | 0
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 |  | 0 | 0 | 37338.4003 | 110d | 0 | 0 | 0 | 37338.4003 | 0% | Not Started | 0 | 7170.6701 | 100 |  | 0 | 100 |  | 0
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 22d | 201483.0469 | 741823.9453 | 81d | -66346.3516 | 0 | 135136.6953 | 741823.9453 | 21.36% | Started | 201483.0452 | 0 | 100 | 21.3592 | 21.3592 | 100 | 14.3258 | 21.3592
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 2h | 11143.0596 | 33429.1787 | 6h | -4488.1499 | 0 | 6654.9097 | 33429.1787 | 25% | Started | 11143.0596 | 0 | 100 | 25 | 25 | 100 | 14.9306 | 25
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 |  | 0 | 0 | 64039.6816 | 48d | 0 | 0 | 0 | 64039.6816 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 |  | 0 | 0 | 752.88 | 3d | 0 | 0 | 0 | 752.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2010-09-30 16:00 |  | TP Name | periode 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 43d 7h | [5 empty] | 443907.193 |  | 37.7% |  | 421709.1497 | 224775.4972
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 42d | 7348.3203 | 7873.2003 | 45d | -1376.1 | 0 | 5972.2203 | 7873.2003 | 48.28% | Started | 7348.3201 | 7676.3703 | 100 | 48.2759 | 48.2759 | 100 | 39.2354 | 48.2759
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 |  | 0 | 0 | 1127.52 | 87d | 0 | 0 | 0 | 1127.52 | 0% | Not Started | 0 | 568.62 | 100 |  | 0 | 100 |  | 0
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 |  | 0 | 0 | 2463.84 | 87d | 0 | 0 | 0 | 2463.84 | 0% | Not Started | 0 | 1242.54 | 100 |  | 0 | 100 |  | 0
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 21d 7h | 7425.2501 | 29913.1502 | 88d 1h | 4031.6699 | 0 | 11456.92 | 29913.1502 | 19.89% | Started | 7425.2502 | 14892.9301 | 100 | 19.8864 | 19.8864 | 100 | 30.684 | 19.8864
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 42d | 384649.4531 | 558657.5391 | 61d | 22121.4805 | 0 | 406770.9336 | 558657.5391 | 40.78% | Started | 384649.4602 | 200338.2568 | 100 | 40.7767 | 40.7767 | 100 | 43.1218 | 40.7767
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 56.78 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 4h | 22286.1191 | 22286.1191 | 4h | -2579 | 0 | 19707.1191 | 22286.1191 | 50% | Started | 22286.1191 | 0 | 100 | 50 | 50 | 100 | 44.2139 | 50
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 |  | 0 | 0 | 64039.6816 | 48d | 0 | 0 | 0 | 64039.6816 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 |  | 0 | 0 | 752.88 | 3d | 0 | 0 | 0 | 752.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2010-10-31 16:00 |  | TP Name | periode 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 65d | [5 empty] | 665786.7198 |  | 56% |  | 626349.0543 | 430041.214
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 62d | 10847.5204 | 4374.0002 | 25d | -1889.1899 | 0 | 8958.3305 | 4374.0002 | 71.26% | Started | 10847.5205 | 11372.4004 | 100 | 71.2644 | 71.2644 | 100 | 58.8531 | 71.2644
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 |  | 0 | 0 | 1127.52 | 87d | 0 | 0 | 0 | 1127.52 | 0% | Not Started | 0 | 842.4 | 100 |  | 0 | 100 |  | 0
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 |  | 0 | 0 | 2463.84 | 87d | 0 | 0 | 0 | 2463.84 | 0% | Not Started | 0 | 1840.8 | 100 |  | 0 | 100 |  | 0
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 42d | 14256.4801 | 23081.9202 | 68d | 2928.8999 | 0 | 17185.38 | 23081.9202 | 38.18% | Started | 14256.4799 | 22063.6002 | 100 | 38.1818 | 38.1818 | 100 | 46.026 | 38.1818
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 62d | 567815.8594 | 375491.1328 | 41d | 42426.8711 | 0 | 610242.7305 | 375491.1328 | 60.19% | Started | 567815.8752 | 393807.7734 | 100 | 60.1942 | 60.1942 | 100 | 64.6918 | 60.1942
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 114.24 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 6h | 33429.1787 | 11143.0596 | 2h | -4028.8999 | 0 | 29400.2788 | 11143.0596 | 75% | Started | 33429.1787 | 0 | 100 | 75 | 75 | 100 | 65.961 | 75
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 |  | 0 | 0 | 64039.6816 | 48d | 0 | 0 | 0 | 64039.6816 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 |  | 0 | 0 | 752.88 | 3d | 0 | 0 | 0 | 752.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2010-11-30 16:00 |  | TP Name | periode 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 86d 7h | [5 empty] | 751640.3662 |  | 73.79% |  | 825375.4402 | 687166.7093
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 82d | 14346.7206 | 874.8 | 5d | -4193.9399 | 0 | 10152.7806 | 874.8 | 94.25% | Started | 14346.7249 | 15199.6506 | 100 | 94.2529 | 94.2529 | 100 | 66.7002 | 94.2529
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 |  | 0 | 0 | 1127.52 | 87d | 0 | 0 | 0 | 1127.52 | 0% | Not Started | 0 | 1125.9 | 100 |  | 0 | 100 |  | 0
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 |  | 0 | 0 | 2463.84 | 87d | 0 | 0 | 0 | 2463.84 | 0% | Not Started | 0 | 2460.3 | 100 |  | 0 | 100 |  | 0
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 62d | 21045.2802 | 16293.1201 | 48d | -3859.8899 | 0 | 17185.3903 | 16293.1201 | 56.36% | Started | 21045.2668 | 29488.8502 | 100 | 56.3636 | 56.3636 | 100 | 46.026 | 56.3636
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 82d | 750982.2656 | 192324.7266 | 21d | -59944.9688 | 0 | 691037.2969 | 192324.7266 | 79.61% | Started | 750982.74 | 594146.0303 | 100 | 79.6117 | 79.6117 | 100 | 73.2569 | 79.6117
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 173.74 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 7h | 39000.7085 | 5571.5298 | 1h | -5735.8101 | 0 | 33264.8984 | 5571.5298 | 87.5% | Started | 39000.7085 | 44572.2383 | 100 | 87.5 | 87.5 | 100 | 74.6314 | 87.5
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 |  | 0 | 0 | 64039.6816 | 48d | 0 | 0 | 0 | 64039.6816 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 |  | 0 | 0 | 752.88 | 3d | 0 | 0 | 0 | 752.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2010-12-31 17:00 |  | TP Name | periode 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 110d | [5 empty] | 940069.9143 |  | 97.9% |  | 1094974.5131 | 906873.3066
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 87d | 15221.5206 | 0 | 0 | -3280.3701 | 0 | 11941.1505 | 0 | 100% | Finished | 15221.5206 | 15221.5206 | 100 | 100 | 100 | 100 | 78.4491 | 100
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 |  | 0 | 0 | 1127.52 | 87d | 0 | 0 | 0 | 1127.52 | 0% | Not Started | 0 | 1127.52 | 100 |  | 0 | 100 |  | 0
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 |  | 0 | 0 | 2463.84 | 87d | 0 | 0 | 0 | 2463.84 | 0% | Not Started | 0 | 2463.84 | 100 |  | 0 | 100 |  | 0
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 82d | 27834.0802 | 9504.3201 | 28d | -4915.3101 | 0 | 22918.7701 | 9504.3201 | 74.55% | Started | 27834.0804 | 37338.4003 | 100 | 74.5455 | 74.5455 | 100 | 61.3812 | 74.5455
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 103d | 943306.9922 | 0 | 0 | -130851.0781 | 0 | 812455.9141 | 0 | 100% | Finished | 943306.9922 | 805932.1875 | 100 | 100 | 100 | 100 | 86.1285 | 100
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 217.6 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 1d | 44572.2383 | 0 | 0 | -5120.0801 | 0 | 39452.1582 | 0 | 100% | Finished | 44572.2383 | 44572.2383 | 100 | 100 | 100 | 100 | 88.5128 | 100
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 | 2010-12-01 08:00 | 20d | 26683.2007 | 0 | 0 | 26618.7207 | 0 | 53301.9214 | 0 | 100% | Finished | 64039.6816 | 0 | 100 | 41.6667 | 100 | 100 | 83.2326 | 100
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 |  | 0 | 0 | 752.88 | 3d | 0 | 0 | 0 | 752.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2011-02-28 17:00 |  | TP Name | periode 6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 151d | [5 empty] | 944444.9143 |  | 98.58% |  | 1102641.2333 | 1074272.1118
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 87d | 15221.5206 | 0 | 0 | -3280.3701 | 0 | 11941.1505 | 0 | 100% | Finished | 15221.5206 | 15221.5206 | 100 | 100 | 100 | 100 | 78.4491 | 100
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 |  | 0 | 0 | 1127.52 | 87d | 0 | 0 | 0 | 1127.52 | 0% | Not Started | 0 | 1127.52 | 100 |  | 0 | 100 |  | 0
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 | 2011-01-17 08:00 | 31d | 877.92 | 1585.92 | 56d | -314.72 | 0 | 563.2 | 1585.92 | 35.63% | Started | 877.92 | 2463.84 | 100 | 35.6322 | 35.6322 | 100 | 22.8586 | 35.6322
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 102d | 34622.8802 | 2715.52 | 8d | -7892.3101 | 0 | 26730.5702 | 2715.52 | 92.73% | Started | 34622.8806 | 37338.4003 | 100 | 92.7273 | 92.7273 | 100 | 71.59 | 92.7273
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 103d | 943306.9922 | 0 | 0 | -130851.0781 | 0 | 812455.9141 | 0 | 100% | Finished | 943306.9922 | 943306.9922 | 100 | 100 | 100 | 100 | 86.1285 | 100
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 217.6 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 1d | 44572.2383 | 0 | 0 | -5120.0801 | 0 | 39452.1582 | 0 | 100% | Finished | 44572.2383 | 44572.2383 | 100 | 100 | 100 | 100 | 88.5128 | 100
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 | 2010-12-01 08:00 | 20d | 26683.2007 | 0 | 0 | 26618.7207 | 0 | 53301.9214 | 0 | 100% | Finished | 64039.6816 | 26683.2007 | 100 | 41.6667 | 100 | 100 | 83.2326 | 100
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 3340.7999 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 |  | 0 | 0 | 752.88 | 3d | 0 | 0 | 0 | 752.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2011-03-31 17:00 |  | TP Name | periode 7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 174d | [5 empty] | 945556.3443 |  | 98.88% |  | 1105923.153 | 1109301.6325
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 87d | 15221.5206 | 0 | 0 | -3280.3701 | 0 | 11941.1505 | 0 | 100% | Finished | 15221.5206 | 15221.5206 | 100 | 100 | 100 | 100 | 78.4491 | 100
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 |  | 0 | 0 | 1127.52 | 87d | 0 | 0 | 0 | 1127.52 | 0% | Not Started | 0 | 1127.52 | 100 |  | 0 | 100 |  | 0
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 | 2011-01-17 08:00 | 51d | 1444.32 | 1019.52 | 36d | 230.31 | 0 | 1674.63 | 1019.52 | 58.62% | Started | 1444.32 | 2463.84 | 100 | 58.6207 | 58.6207 | 100 | 67.9683 | 58.6207
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 110d | 37338.4003 | 0 | 0 | -10607.8301 | 0 | 26730.5702 | 0 | 100% | Finished | 37338.4003 | 37338.4003 | 100 | 100 | 100 | 100 | 71.59 | 100
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 103d | 943306.9922 | 0 | 0 | -130851.0781 | 0 | 812455.9141 | 0 | 100% | Finished | 943306.9922 | 943306.9922 | 100 | 100 | 100 | 100 | 86.1285 | 100
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 217.6 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 1d | 44572.2383 | 0 | 0 | -5120.0801 | 0 | 39452.1582 | 0 | 100% | Finished | 44572.2383 | 44572.2383 | 100 | 100 | 100 | 100 | 88.5128 | 100
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 | 2010-12-01 08:00 | 20d | 26683.2007 | 0 | 0 | 26618.7207 | 0 | 53301.9214 | 0 | 100% | Finished | 64039.6816 | 57368.8815 | 100 | 41.6667 | 100 | 100 | 83.2326 | 100
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 7182.7197 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 |  | 0 | 0 | 752.88 | 3d | 0 | 0 | 0 | 752.88 | 0% | Not Started | 0 | 501.92 | 100 |  | 0 | 100 |  | 0
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2011-04-30 17:00 |  | TP Name | periode 8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 195d | [5 empty] | 947112.0343 |  | 99.09% |  | 1108369.953 | 1117058.5926
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 87d | 15221.5206 | 0 | 0 | -3280.3701 | 0 | 11941.1505 | 0 | 100% | Finished | 15221.5206 | 15221.5206 | 100 | 100 | 100 | 100 | 78.4491 | 100
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 | 2011-04-01 08:00 | 21d | 272.16 | 0 | 0 | 661.96 | 0 | 934.12 | 0 | 100% | Finished | 1127.52 | 1127.52 | 100 | 24.1379 | 100 | 100 | 82.8473 | 100
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 | 2011-01-17 08:00 | 71d | 2010.72 | 453.12 | 16d | -336.09 | 0 | 1674.63 | 453.12 | 81.61% | Started | 2010.72 | 2463.84 | 100 | 81.6092 | 81.6092 | 100 | 67.9683 | 81.6092
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 110d | 37338.4003 | 0 | 0 | -10607.8301 | 0 | 26730.5702 | 0 | 100% | Finished | 37338.4003 | 37338.4003 | 100 | 100 | 100 | 100 | 71.59 | 100
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 103d | 943306.9922 | 0 | 0 | -130851.0781 | 0 | 812455.9141 | 0 | 100% | Finished | 943306.9922 | 943306.9922 | 100 | 100 | 100 | 100 | 86.1285 | 100
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 |  | 0 | 0 | 217.6 | 80d | 0 | 0 | 0 | 217.6 | 0% | Not Started | 0 | 217.6 | 100 |  | 0 | 100 |  | 0
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 1d | 44572.2383 | 0 | 0 | -5120.0801 | 0 | 39452.1582 | 0 | 100% | Finished | 44572.2383 | 44572.2383 | 100 | 100 | 100 | 100 | 88.5128 | 100
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 | 2010-12-01 08:00 | 20d | 26683.2007 | 0 | 0 | 26618.7207 | 0 | 53301.9214 | 0 | 100% | Finished | 64039.6816 | 64039.6816 | 100 | 41.6667 | 100 | 100 | 83.2326 | 100
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 |  | 0 | 0 | 8017.9197 | 48d | 0 | 0 | 0 | 8017.9197 | 0% | Not Started | 0 | 8017.9197 | 100 |  | 0 | 100 |  | 0
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 | 2011-04-01 08:00 | 3d | 752.88 | 0 | 0 | -131.31 | 0 | 621.57 | 0 | 100% | Finished | 752.88 | 752.88 | 100 | 100 | 100 | 100 | 82.559 | 100
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 |  | 0 | 0 | 1438 | 25d | 0 | 0 | 0 | 1438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2011-05-31 17:00 |  | TP Name | periode 9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (1) | 2010-08-02 08:00 | 2011-06-27 17:00 | 236d |  |  | 0 |  |  | 1118496.5927 |  | 217d | [5 empty] | 955929.2243 |  | 100% |  | 1118496.5927 | 1117403.7126
3 | Diversen | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 21.87 | 15221.5206 | 15221.5206 | 2010-08-02 08:00 | 87d | 15221.5206 | 0 | 0 | -3280.3701 | 0 | 11941.1505 | 0 | 100% | Finished | 15221.5206 | 15221.5206 | 100 | 100 | 100 | 100 | 78.4491 | 100
10 | Regiewerken | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 1.62 | 1127.52 | 1127.52 | 2011-04-01 08:00 | 21d | 272.16 | 0 | 0 | 661.96 | 0 | 934.12 | 0 | 100% | Finished | 1127.52 | 1127.52 | 100 | 24.1379 | 100 | 100 | 82.8473 | 100
11 | Zuivere OA (1) | 2010-08-02 08:00 | 2010-11-30 17:00 | 87d |  | 0 | 0 | 3.54 | 2463.84 | 2463.84 | 2011-01-17 08:00 | 87d | 2463.84 | 0 | 0 | -317.37 | 0 | 2146.47 | 0 | 100% | Finished | 2463.84 | 2463.84 | 100 | 100 | 100 | 100 | 87.1189 | 100
4 | Zuivere OA (2) | 2010-08-02 08:00 | 2010-12-31 17:00 | 110d |  | 0 | 0 | 42.43 | 37338.4003 | 37338.4003 | 2010-09-01 08:00 | 110d | 37338.4003 | 0 | 0 | -10607.8301 | 0 | 26730.5702 | 0 | 100% | Finished | 37338.4003 | 37338.4003 | 100 | 100 | 100 | 100 | 71.59 | 100
1 | Verplaatsbare wanden (1) | 2010-09-01 08:00 | 2011-01-21 17:00 | 103d |  | 0 | 0 | 1144.79 | 943306.9922 | 943306.9922 | 2010-08-02 08:00 | 103d | 943306.9922 | 0 | 0 | -130851.0781 | 0 | 812455.9141 | 0 | 100% | Finished | 943306.9922 | 943306.9922 | 100 | 100 | 100 | 100 | 86.1285 | 100
5 | Coördinatie OA | 2010-09-02 08:00 | 2010-12-22 17:00 | 80d |  | 0 | 0 | 0.34 | 217.6 | 217.6 | 2011-05-02 08:00 | 22d | 59.84 | 0 | 0 | 103.18 | 0 | 163.02 | 0 | 100% | Finished | 217.6 | 217.6 | 100 | 27.5 | 100 | 100 | 74.9173 | 100
2 | Verplaatsbare wanden (2) | 2010-11-19 08:00 | 2010-11-19 17:00 | 1d |  | 0 | 0 | 5571.5298 | 44572.2383 | 44572.2383 | 2010-08-31 08:00 | 1d | 44572.2383 | 0 | 0 | -5120.0801 | 0 | 39452.1582 | 0 | 100% | Finished | 44572.2383 | 44572.2383 | 100 | 100 | 100 | 100 | 88.5128 | 100
6 | Coördinatie opmerkingen | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 166.77 | 64039.6816 | 64039.6816 | 2010-12-01 08:00 | 20d | 26683.2007 | 0 | 0 | 26618.7207 | 0 | 53301.9214 | 0 | 100% | Finished | 64039.6816 | 64039.6816 | 100 | 41.6667 | 100 | 100 | 83.2326 | 100
8 | Systeemwanden | 2011-02-01 08:00 | 2011-04-07 17:00 | 48d |  | 0 | 0 | 20.88 | 8017.9197 | 8017.9197 | 2011-05-02 08:00 | 22d | 3674.8799 | 0 | 0 | 3318.8501 | 0 | 6993.7299 | 0 | 100% | Finished | 8017.9197 | 8017.9197 | 100 | 45.8333 | 100 | 100 | 87.2262 | 100
9 | Opmerkingen | 2011-03-30 08:00 | 2011-04-01 17:00 | 3d |  | 0 | 0 | 31.37 | 752.88 | 752.88 | 2011-04-01 08:00 | 3d | 752.88 | 0 | 0 | -131.31 | 0 | 621.57 | 0 | 100% | Finished | 752.88 | 752.88 | 100 | 100 | 100 | 100 | 82.559 | 100
7 | Verplaatsbare wanden (3) | 2011-05-24 08:00 | 2011-06-27 17:00 | 25d |  | 0 | 0 | 7.19 | 1438 | 1438 | 2011-05-02 08:00 | 22d | 1265.44 | 0 | 0 | -76.84 | 0 | 1188.6 | 0 | 100% | Finished | 1438 | 345.12 | 100 | 88 | 100 | 100 | 82.6565 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
periode 1 | 2010-08-02 08:00 | 2010-08-31 09:00 | 11738.7402 | 216475.2251 | 143782.3451 | 2010-09-30 09:00 | 204736.4849 | 1844% | 72692.8799 | 150.6% | 22d | 204.1% | 90.73% | 2011-04-27 15:00 | 2010-08-18 15:00 | 2010-08-12 12:00 | 2010-07-30 17:00 | 2010-08-18 15:00 | 2010-08-23 14:00 | 2011-05-26 17:00 | 2011-01-10 14:00 | 2010-11-25 16:00 | 1045803.7127 | 742902.8567 | 192696.0001 | 585642.0875 | 176270.682 | 437264.5667 | 328143.7629 | 703090.5667 | 2.0414 | 1.5056 | 18.4411 | 0.90726 | 22 | 1.5056 | 1 | 2.0414 | 1
periode 2 | 2010-08-31 09:00 | 2010-09-30 16:00 | 224775.4972 | 421709.1497 | 443907.193 | 2010-10-29 10:00 | 196933.6525 | 187.6% | -22198.0433 | 95% | 20d 3h | 146.4% | 94.48% | 2011-04-29 12:00 | 2011-01-24 15:00 | 2011-02-02 11:00 | 2011-05-04 12:00 | 2011-01-24 15:00 | 2011-01-31 09:00 | 2011-05-30 14:00 | 2011-03-15 09:00 | 2011-03-23 11:00 | 1140694.636 | 1177372.3268 | 815302.3692 | 919728.9683 | 834851.9716 | 944775.407 | 1057696.7053 | 1105703.6968 | 1.4644 | 0.94999 | 1.8761 | 0.94481 | 20.375 | 0.94999 | 1 | 1.4644 | 1
periode 3 | 2010-09-30 16:00 | 2010-10-31 16:00 | 430041.214 | 626349.0543 | 665786.7198 | 2010-11-22 14:00 | 196307.8402 | 145.6% | -39437.6655 | 94.08% | 15d 5h | 124% | 95.05% | 2011-04-29 14:00 | 2011-03-15 17:00 | 2011-03-30 10:00 | 2011-05-17 11:00 | 2011-03-15 17:00 | 2011-03-24 09:00 | 2011-06-06 11:00 | 2011-04-25 10:00 | 2011-05-05 09:00 | 1157934.2581 | 1188922.0115 | 1003687.3256 | 1062556.8282 | 1024963.02 | 1087539.203 | 1137233.2869 | 1157595.3152 | 1.2404 | 0.94077 | 1.4565 | 0.95052 | 15.625 | 0.94077 | 1 | 1.2404 | 1
periode 4 | 2010-10-31 16:00 | 2010-11-30 16:00 | 687166.7093 | 825375.4402 | 751640.3662 | 2010-12-21 12:00 | 138208.7308 | 120.1% | 73735.074 | 109.8% | 14d 5h | 116.8% | 97.14% | 2011-05-17 16:00 | 2011-05-03 12:00 | 2011-04-07 16:00 | 2011-06-02 12:00 | 2011-05-03 12:00 | 2011-04-19 15:00 | 2011-06-07 11:00 | 2011-05-10 17:00 | 2011-04-26 15:00 | 1044761.5187 | 1018575.484 | 995678.519 | 1002526.0817 | 973877.3236 | 980113.1579 | 1013658.6918 | 1015203.4074 | 1.1683 | 1.0981 | 1.2011 | 0.97136 | 14.625 | 1.0981 | 1 | 1.1683 | 1
periode 5 | 2010-11-30 16:00 | 2010-12-31 17:00 | 906873.3066 | 1094974.5131 | 940069.9143 | 2011-03-18 16:00 | 188101.2064 | 120.7% | 154904.5988 | 116.5% | 54d 7h | 149.9% | 98.27% | 2011-05-03 10:00 | 2011-05-02 12:00 | 2011-03-23 15:00 | 2011-05-26 09:00 | 2011-05-02 12:00 | 2011-04-14 11:00 | 2011-04-12 09:00 | 2011-03-09 12:00 | 2011-02-28 15:00 | 963591.9939 | 960264.3563 | 959551.2317 | 955763.1895 | 956795.2355 | 953543.0826 | 960117.5851 | 959168.7646 | 1.4989 | 1.1648 | 1.2074 | 0.98268 | 54.875 | 1.1648 | 1 | 1.4989 | 1
periode 6 | 2010-12-31 17:00 | 2011-02-28 17:00 | 1074272.1118 | 1102641.2333 | 944444.9143 | 2011-03-25 17:00 | 28369.1215 | 102.6% | 158196.319 | 116.8% | 19d | 112.6% | 98.9% | 2011-06-17 17:00 | 2011-06-17 16:00 | 2011-05-03 17:00 | 2011-06-21 17:00 | 2011-06-17 16:00 | 2011-06-02 14:00 | 2011-05-31 17:00 | 2011-05-20 14:00 | 2011-05-10 10:00 | 960300.2736 | 958025.4998 | 959892.3417 | 958528.2041 | 957676.0939 | 956507.6696 | 958361.8764 | 958123.1489 | 1.1258 | 1.1675 | 1.0264 | 0.98897 | 19 | 1.1675 | 1 | 1.1258 | 1
periode 7 | 2011-02-28 17:00 | 2011-03-31 17:00 | 1109301.6325 | 1105923.153 | 945556.3443 | 2011-03-29 17:00 | -3378.4795 | 99.7% | 160366.8087 | 117% | -2d | 98.85% | 99.17% | 2011-06-28 15:00 | 2011-06-28 15:00 | 2011-05-11 11:00 | 2011-06-28 12:00 | 2011-06-28 15:00 | 2011-06-15 14:00 | 2011-06-29 17:00 | 2011-06-30 15:00 | 2011-06-17 11:00 | 958129.784 | 956306.5448 | 958168.1945 | 958275.9867 | 956339.3855 | 956431.5471 | 956633.5692 | 956650.084 | 0.98851 | 1.1696 | 0.99695 | 0.99167 | -2 | 1.1696 | 1 | 0.98851 | 1
periode 8 | 2011-03-31 17:00 | 2011-04-30 17:00 | 1117058.5926 | 1108369.953 | 947112.0343 | 2011-03-31 11:00 | -8688.6397 | 99.22% | 161257.9186 | 117% | -21d 5h | 88.91% | 99.3% | 2011-06-29 16:00 | 2011-06-29 16:00 | 2011-05-12 10:00 | 2011-06-29 12:00 | 2011-06-29 16:00 | 2011-06-21 14:00 | 2011-07-27 14:00 | 2011-08-08 11:00 | 2011-07-25 10:00 | 957238.674 | 955765.3385 | 957318.0579 | 958501.7661 | 955833.1727 | 956844.6619 | 956036.8999 | 956202.1244 | 0.8891 | 1.1703 | 0.99222 | 0.99301 | -21.625 | 1.1703 | 1 | 0.8891 | 1
periode 9 | 2011-04-30 17:00 | 2011-05-31 17:00 | 1117403.7126 | 1118496.5927 | 955929.2243 | 2011-06-27 17:00 | 1092.88 | 100.1% | 162567.3684 | 117% | 19d | 108.8% | 100% | 2011-06-27 15:00 | 2011-06-27 15:00 | 2011-05-10 12:00 | 2011-06-27 15:00 | 2011-06-27 15:00 | 2011-06-22 17:00 | 2011-05-31 17:00 | 2011-05-31 17:00 | 2011-05-31 17:00 | 955929.2243 | 955929.2243 | 955929.2243 | 955929.2243 | 955929.2243 | 955929.2243 | 955929.2243 | 955929.2243 | 1.0876 | 1.1701 | 1.001 | 1 | 19 | 1.1701 | 1 | 1.0876 | 1