## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Sea Electricity | 1 |  |  | 2013-02-04 06:00 | 2014-05-18 07:00 | 468d 1h |  |  | 90099450 |  |  | 139062138.0046 | 468.0417
20 | Pin-piles | 1.1 |  |  | 2013-02-04 06:00 | 2013-08-25 22:00 | 203d |  |  | 10260850 |  |  | 21715090 | 202.6667
1 | Fabrication of pre-piling template | 1.1.1 |  | FS2 | 2013-04-20 06:00 | 2013-05-04 22:00 | 15d |  | 0 | 1044000 | 0 | 0 | 1044000 | 14.6667
2 | Transportation of template and mounting on Jack Up Platform Buzzard | 1.1.2 | 1FS | FS3 | 2013-05-05 06:00 | 2013-05-14 22:00 | 10d |  | 0 | 58000 | 0 | 0 | 58000 | 9.6667
3 | Mobilisation of Jack Up Platform Buzzard | 1.1.3 | 2FS | FS526;FS527;FS528;FS529;FS530;FS531;FS532;FS533;FS534;FS535;FS536;FS537;FS538;FS539;FS540;FS541;FS542;FS543;FS544;FS545;FS546;FS548;FS547;FS549;FS550 | 2013-05-15 06:00 | 2013-05-15 22:00 | 1d | Laborer[5.00 #60];Skipper;Engineer[3.00 #18];Vessel Buzzard | 63040 | 0 | 0 | 0 | 63040 | 0.66667
551 | Purchasing of pin-piles | 1.1.4 |  | SS11+3w 4d | 2013-02-04 06:00 | 2013-03-25 22:00 | 50d |  | 0 | 6264000 | 0 | 0 | 6264000 | 49.6667
11 | Continious delivery of pin-piles | 1.1.5 | 551SS+3w 4d | SS526+3d;SS527+3d;SS528+3d;SS529+3d;SS530+3d;SS531+3d;SS532+3d;SS533+3d;SS534+3d;SS535+3d;SS536+3d;SS537+3d;SS538+3d;SS539+3d;SS540+3d;SS541+3d;SS542+3d;SS543+3d;SS544+3d;SS545+3d;SS546+3d;SS548+3d;SS547+3d;SS549+3d;SS550+3d | 2013-03-01 06:00 | 2013-03-25 22:00 | 25d |  | 0 | 19200 | 0 | 0 | 19200 | 24.6667
10 | Seabed preparations | 1.1.6 |  |  | 2013-04-06 06:00 | 2013-05-15 22:00 | 40d |  |  | 0 |  |  | 2947200 | 39.6667
6 | Mobilisation of vessels | 1.1.6.1 |  | FS7 | 2013-04-06 06:00 | 2013-04-20 22:00 | 15d | Laborer[5.00 #60];Skipper;Vessel Pompei | 859200 | 0 | 0 | 0 | 859200 | 14.6667
7 | Seabed preparations | 1.1.6.2 | 6FS | FS526;FS527;FS528;FS529;FS530;FS531;FS532;FS533;FS534;FS535;FS536;FS537;FS538;FS539;FS540;FS541;FS542;FS543;FS544;FS545;FS546;FS548;FS547;FS549;FS550 | 2013-04-21 06:00 | 2013-05-15 22:00 | 25d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 2088000 | 0 | 0 | 0 | 2088000 | 24.6667
15 | Pile driving works | 1.1.7 |  |  | 2013-05-16 06:00 | 2013-08-23 22:00 | 100d |  |  | 101250 |  |  | 4513250 | 99.6667
526 | Delivery of pin-piles OTS | 1.1.7.1 | 3FS;7FS;11SS+3d | FS12 | 2013-05-16 06:00 | 2013-05-16 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
527 | Delivery of pin-piles 1 | 1.1.7.2 | 3FS;7FS;11SS+3d | FS13 | 2013-05-20 06:00 | 2013-05-20 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
528 | Delivery of pin-piles 2 | 1.1.7.3 | 3FS;7FS;11SS+3d | FS14 | 2013-05-24 06:00 | 2013-05-24 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
529 | Delivery of pin-piles 3 | 1.1.7.4 | 3FS;7FS;11SS+3d | FS196 | 2013-05-28 06:00 | 2013-05-28 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
530 | Delivery of pin-piles 4 | 1.1.7.5 | 3FS;7FS;11SS+3d | FS197 | 2013-06-01 06:00 | 2013-06-01 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
531 | Delivery of pin-piles 5 | 1.1.7.6 | 3FS;7FS;11SS+3d | FS198 | 2013-06-05 06:00 | 2013-06-05 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
532 | Delivery of pin-piles 6 | 1.1.7.7 | 3FS;7FS;11SS+3d | FS199 | 2013-06-10 06:00 | 2013-06-10 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
533 | Delivery of pin-piles 7 | 1.1.7.8 | 3FS;7FS;11SS+3d | FS200 | 2013-06-14 06:00 | 2013-06-14 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
534 | Delivery of pin-piles 8 | 1.1.7.9 | 3FS;7FS;11SS+3d | FS201 | 2013-06-18 06:00 | 2013-06-18 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
535 | Delivery of pin-piles 9 | 1.1.7.10 | 3FS;7FS;11SS+3d | FS202 | 2013-06-22 06:00 | 2013-06-22 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
536 | Delivery of pin-piles 10 | 1.1.7.11 | 3FS;7FS;11SS+3d | FS203 | 2013-06-26 06:00 | 2013-06-26 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
537 | Delivery of pin-piles 11 | 1.1.7.12 | 3FS;7FS;11SS+3d | FS204 | 2013-06-30 06:00 | 2013-06-30 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
538 | Delivery of pin-piles 12 | 1.1.7.13 | 3FS;7FS;11SS+3d | FS205 | 2013-07-04 06:00 | 2013-07-04 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
539 | Delivery of pin-piles 13 | 1.1.7.14 | 3FS;7FS;11SS+3d | FS206 | 2013-07-08 06:00 | 2013-07-08 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
540 | Delivery of pin-piles 14 | 1.1.7.15 | 3FS;7FS;11SS+3d | FS207 | 2013-07-12 06:00 | 2013-07-12 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
541 | Delivery of pin-piles 15 | 1.1.7.16 | 3FS;7FS;11SS+3d | FS208 | 2013-07-16 06:00 | 2013-07-16 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
542 | Delivery of pin-piles 16 | 1.1.7.17 | 3FS;7FS;11SS+3d | FS209 | 2013-07-20 06:00 | 2013-07-20 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
543 | Delivery of pin-piles 17 | 1.1.7.18 | 3FS;7FS;11SS+3d | FS210 | 2013-07-24 06:00 | 2013-07-24 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
544 | Delivery of pin-piles 18 | 1.1.7.19 | 3FS;7FS;11SS+3d | FS211 | 2013-07-28 06:00 | 2013-07-28 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
545 | Delivery of pin-piles 19 | 1.1.7.20 | 3FS;7FS;11SS+3d | FS212 | 2013-08-01 06:00 | 2013-08-01 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
546 | Delivery of pin-piles 20 | 1.1.7.21 | 3FS;7FS;11SS+3d | FS213 | 2013-08-05 06:00 | 2013-08-05 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
547 | Delivery of pin-piles 21 | 1.1.7.22 | 3FS;7FS;11SS+3d | FS214 | 2013-08-13 06:00 | 2013-08-13 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
548 | Delivery of pin-piles 22 | 1.1.7.23 | 3FS;7FS;11SS+3d | FS215 | 2013-08-09 06:00 | 2013-08-09 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
549 | Delivery of pin-piles 23 | 1.1.7.24 | 3FS;7FS;11SS+3d | FS216 | 2013-08-17 06:00 | 2013-08-17 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
550 | Delivery of pin-piles 24 | 1.1.7.25 | 3FS;7FS;11SS+3d | FS217 | 2013-08-21 06:00 | 2013-08-21 22:00 | 1d | Laborer[5.00 #60];Skipper[0.50 #4];Vessel Maersk[0.50 #1];Crane | 13280 | 4050 | 0 | 0 | 17330 | 0.66667
12 | OTS: drive 4 pin-piles for OTS foundation into seabed | 1.1.7.26 | 526FS | FS16 | 2013-05-17 06:00 | 2013-05-18 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
13 | Turbine1: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.27 | 527FS | FS162 | 2013-05-21 06:00 | 2013-05-22 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
14 | Turbine2: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.28 | 528FS | FS218 | 2013-05-25 06:00 | 2013-05-26 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
196 | Turbine3: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.29 | 529FS | FS219 | 2013-05-29 06:00 | 2013-05-30 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
197 | Turbine4: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.30 | 530FS | FS220 | 2013-06-02 06:00 | 2013-06-03 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
198 | Turbine5: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.31 | 531FS | FS221 | 2013-06-06 06:00 | 2013-06-07 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
199 | Turbine6: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.32 | 532FS | FS222 | 2013-06-11 06:00 | 2013-06-12 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
200 | Turbine7: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.33 | 533FS | FS223 | 2013-06-15 06:00 | 2013-06-16 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
201 | Turbine8: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.34 | 534FS | FS224 | 2013-06-19 06:00 | 2013-06-20 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
202 | Turbine9: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.35 | 535FS | FS225 | 2013-06-23 06:00 | 2013-06-24 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
203 | Turbine10: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.36 | 536FS | FS226 | 2013-06-27 06:00 | 2013-06-28 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
204 | Turbine11: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.37 | 537FS | FS227 | 2013-07-01 06:00 | 2013-07-02 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
205 | Turbine12: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.38 | 538FS | FS228 | 2013-07-05 06:00 | 2013-07-06 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
206 | Turbine13: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.39 | 539FS | FS229 | 2013-07-09 06:00 | 2013-07-10 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
207 | Turbine14: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.40 | 540FS | FS230 | 2013-07-13 06:00 | 2013-07-14 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
208 | Turbine15: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.41 | 541FS | FS231 | 2013-07-17 06:00 | 2013-07-18 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
209 | Turbine16: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.42 | 542FS | FS232 | 2013-07-21 06:00 | 2013-07-22 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
210 | Turbine17: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.43 | 543FS | FS233 | 2013-07-25 06:00 | 2013-07-26 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
211 | Turbine18: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.44 | 544FS | FS234 | 2013-07-29 06:00 | 2013-07-30 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
212 | Turbine19: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.45 | 545FS | FS235 | 2013-08-02 06:00 | 2013-08-03 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
213 | Turbine20: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.46 | 546FS | FS236 | 2013-08-06 06:00 | 2013-08-07 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
214 | Turbine21: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.47 | 547FS | FS237 | 2013-08-14 06:00 | 2013-08-15 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
215 | Turbine22: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.48 | 548FS | FS238 | 2013-08-10 06:00 | 2013-08-11 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
216 | Turbine23: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.49 | 549FS | FS239 | 2013-08-18 06:00 | 2013-08-19 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
217 | Turbine24: drive 4 pin-piles for jacket foundation into seabed | 1.1.7.50 | 550FS | FS240 | 2013-08-22 06:00 | 2013-08-23 22:00 | 2d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 163200 | 0 | 0 | 0 | 163200 | 1.6667
19 | Dredging and cleaning of the pin-piles (Pompei) | 1.1.8 |  |  | 2013-05-19 06:00 | 2013-08-25 22:00 | 99d |  |  | 2774400 |  |  | 6806400 | 98.6667
165 | OTS | 1.1.8.1 |  |  | 2013-05-19 06:00 | 2013-05-20 22:00 | 2d |  |  | 0 |  |  | 161280 | 1.6667
16 | Dredging and cleaning of pin-piles | 1.1.8.1.1 | 12FS | FS17 | 2013-05-19 06:00 | 2013-05-19 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 0 | 0 | 0 | 80960 | 0.66667
17 | Install pin-pile covers on the piles | 1.1.8.1.2 | 16FS | FS82+1w 5d | 2013-05-20 06:00 | 2013-05-20 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 0 | 0 | 0 | 80320 | 0.66667
166 | Turbines | 1.1.8.2 |  |  | 2013-05-23 06:00 | 2013-08-25 22:00 | 95d |  |  | 2774400 |  |  | 6645120 | 94.6667
162 | Dredging and cleaning of pin-piles 1 | 1.1.8.2.1 | 13FS | FS241 | 2013-05-23 06:00 | 2013-05-23 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
218 | Dredging and cleaning of pin-piles 2 | 1.1.8.2.2 | 14FS | FS242 | 2013-05-27 06:00 | 2013-05-27 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
219 | Dredging and cleaning of pin-piles 3 | 1.1.8.2.3 | 196FS | FS243 | 2013-05-31 06:00 | 2013-05-31 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
220 | Dredging and cleaning of pin-piles 4 | 1.1.8.2.4 | 197FS | FS244 | 2013-06-04 06:00 | 2013-06-04 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
221 | Dredging and cleaning of pin-piles 5 | 1.1.8.2.5 | 198FS | FS245 | 2013-06-08 06:00 | 2013-06-08 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
222 | Dredging and cleaning of pin-piles 6 | 1.1.8.2.6 | 199FS | FS246 | 2013-06-13 06:00 | 2013-06-13 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
223 | Dredging and cleaning of pin-piles 7 | 1.1.8.2.7 | 200FS | FS247 | 2013-06-17 06:00 | 2013-06-17 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
224 | Dredging and cleaning of pin-piles 8 | 1.1.8.2.8 | 201FS | FS248 | 2013-06-21 06:00 | 2013-06-21 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
225 | Dredging and cleaning of pin-piles 9 | 1.1.8.2.9 | 202FS | FS249 | 2013-06-25 06:00 | 2013-06-25 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
226 | Dredging and cleaning of pin-piles 10 | 1.1.8.2.10 | 203FS | FS250 | 2013-06-29 06:00 | 2013-06-29 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
227 | Dredging and cleaning of pin-piles 11 | 1.1.8.2.11 | 204FS | FS251 | 2013-07-03 06:00 | 2013-07-03 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
228 | Dredging and cleaning of pin-piles 12 | 1.1.8.2.12 | 205FS | FS252 | 2013-07-07 06:00 | 2013-07-07 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
229 | Dredging and cleaning of pin-piles 13 | 1.1.8.2.13 | 206FS | FS253 | 2013-07-11 06:00 | 2013-07-11 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
230 | Dredging and cleaning of pin-piles 14 | 1.1.8.2.14 | 207FS | FS254 | 2013-07-15 06:00 | 2013-07-15 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
231 | Dredging and cleaning of pin-piles 15 | 1.1.8.2.15 | 208FS | FS255 | 2013-07-19 06:00 | 2013-07-19 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
232 | Dredging and cleaning of pin-piles 16 | 1.1.8.2.16 | 209FS | FS256 | 2013-07-23 06:00 | 2013-07-23 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
233 | Dredging and cleaning of pin-piles 17 | 1.1.8.2.17 | 210FS | FS257 | 2013-07-27 06:00 | 2013-07-27 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
234 | Dredging and cleaning of pin-piles 18 | 1.1.8.2.18 | 211FS | FS258 | 2013-07-31 06:00 | 2013-07-31 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
235 | Dredging and cleaning of pin-piles 19 | 1.1.8.2.19 | 212FS | FS259 | 2013-08-04 06:00 | 2013-08-04 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
236 | Dredging and cleaning of pin-piles 20 | 1.1.8.2.20 | 213FS | FS260 | 2013-08-08 06:00 | 2013-08-08 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
237 | Dredging and cleaning of pin-piles 21 | 1.1.8.2.21 | 214FS | FS261 | 2013-08-16 06:00 | 2013-08-16 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
238 | Dredging and cleaning of pin-piles 22 | 1.1.8.2.22 | 215FS | FS262 | 2013-08-12 06:00 | 2013-08-12 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
239 | Dredging and cleaning of pin-piles 23 | 1.1.8.2.23 | 216FS | FS263 | 2013-08-20 06:00 | 2013-08-20 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
240 | Dredging and cleaning of pin-piles 24 | 1.1.8.2.24 | 217FS | FS264 | 2013-08-24 06:00 | 2013-08-24 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Pompei | 80960 | 63000 | 0 | 0 | 143960 | 0.66667
241 | Install pin-pile covers on the piles 1 | 1.1.8.2.25 | 162FS | FS289+2w 1d | 2013-05-24 06:00 | 2013-05-24 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
242 | Install pin-pile covers on the piles 2 | 1.1.8.2.26 | 218FS | FS290+2w 1d | 2013-05-28 06:00 | 2013-05-28 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
243 | Install pin-pile covers on the piles 3 | 1.1.8.2.27 | 219FS | FS291+2w 1d | 2013-06-01 06:00 | 2013-06-01 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
244 | Install pin-pile covers on the piles 4 | 1.1.8.2.28 | 220FS | FS292+2w 1d | 2013-06-05 06:00 | 2013-06-05 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
245 | Install pin-pile covers on the piles 5 | 1.1.8.2.29 | 221FS | FS293+2w 1d | 2013-06-10 06:00 | 2013-06-10 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
246 | Install pin-pile covers on the piles 6 | 1.1.8.2.30 | 222FS | FS294+2w 1d | 2013-06-14 06:00 | 2013-06-14 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
247 | Install pin-pile covers on the piles 7 | 1.1.8.2.31 | 223FS | FS295+2w 1d | 2013-06-18 06:00 | 2013-06-18 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
248 | Install pin-pile covers on the piles 8 | 1.1.8.2.32 | 224FS | FS296+2w 1d | 2013-06-22 06:00 | 2013-06-22 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
249 | Install pin-pile covers on the piles 9 | 1.1.8.2.33 | 225FS | FS297+2w 1d | 2013-06-26 06:00 | 2013-06-26 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
250 | Install pin-pile covers on the piles 10 | 1.1.8.2.34 | 226FS | FS298+2w 1d | 2013-06-30 06:00 | 2013-06-30 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
251 | Install pin-pile covers on the piles 11 | 1.1.8.2.35 | 227FS | FS299+2w 1d | 2013-07-04 06:00 | 2013-07-04 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
252 | Install pin-pile covers on the piles 12 | 1.1.8.2.36 | 228FS | FS300+2w 1d | 2013-07-08 06:00 | 2013-07-08 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
253 | Install pin-pile covers on the piles 13 | 1.1.8.2.37 | 229FS | FS301+2w 1d | 2013-07-12 06:00 | 2013-07-12 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
254 | Install pin-pile covers on the piles 14 | 1.1.8.2.38 | 230FS | FS302+2w 1d | 2013-07-16 06:00 | 2013-07-16 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
255 | Install pin-pile covers on the piles 15 | 1.1.8.2.39 | 231FS | FS303+2w 1d | 2013-07-20 06:00 | 2013-07-20 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
256 | Install pin-pile covers on the piles 16 | 1.1.8.2.40 | 232FS | FS304+2w 1d | 2013-07-24 06:00 | 2013-07-24 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
257 | Install pin-pile covers on the piles 17 | 1.1.8.2.41 | 233FS | FS305+2w 1d | 2013-07-28 06:00 | 2013-07-28 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
258 | Install pin-pile covers on the piles 18 | 1.1.8.2.42 | 234FS | FS306+2w 1d | 2013-08-01 06:00 | 2013-08-01 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
259 | Install pin-pile covers on the piles 19 | 1.1.8.2.43 | 235FS | FS307+2w 1d | 2013-08-05 06:00 | 2013-08-05 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
260 | Install pin-pile covers on the piles 20 | 1.1.8.2.44 | 236FS | FS308+2w 1d | 2013-08-09 06:00 | 2013-08-09 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
261 | Install pin-pile covers on the piles 21 | 1.1.8.2.45 | 237FS | FS309+2w 1d | 2013-08-17 06:00 | 2013-08-17 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
262 | Install pin-pile covers on the piles 22 | 1.1.8.2.46 | 238FS | FS310+2w 1d | 2013-08-13 06:00 | 2013-08-13 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
263 | Install pin-pile covers on the piles 23 | 1.1.8.2.47 | 239FS | FS311+2w 1d | 2013-08-21 06:00 | 2013-08-21 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
264 | Install pin-pile covers on the piles 24 | 1.1.8.2.48 | 240FS | FS312+2w 1d | 2013-08-25 06:00 | 2013-08-25 22:00 | 1d | Laborer[20.00 #60];Skipper;Engineer[6.00 #18];Vessel Buzzard | 80320 | 52600 | 0 | 0 | 132920 | 0.66667
45 | Jacket foundations of wind turbines | 1.2 |  |  | 2013-02-04 06:00 | 2013-10-30 22:00 | 269d |  |  | 5576800 |  |  | 10603504 | 268.6667
35 | Fabrication and assemblage of steel structure for jacket foundations | 1.2.1 |  |  | 2013-02-04 06:00 | 2013-10-27 22:00 | 266d |  |  | 3224800 |  |  | 3224944 | 265.6667
21 | Purshase of tubulars | 1.2.1.1 |  | SS25+5w 5d | 2013-02-04 06:00 | 2013-06-03 22:00 | 120d |  | 0 | 80000 | 0 | 0 | 80000 | 119.6667
23 | Purchase of castings and pile stoppers | 1.2.1.2 |  | SS25+5w 5d | 2013-02-04 06:00 | 2013-06-03 22:00 | 120d |  | 0 | 150000 | 0 | 0 | 150000 | 119.6667
25 | Assembly of midsection 1 | 1.2.1.3 | 21SS+5w 5d;23SS+5w 5d | FS337;FS29 | 2013-03-16 06:00 | 2013-03-24 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
337 | Assembly of midsection 2 | 1.2.1.4 | 25FS | FS338;FS360 | 2013-03-25 06:00 | 2013-04-02 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
338 | Assembly of midsection 3 | 1.2.1.5 | 337FS | FS339;FS361 | 2013-04-03 06:00 | 2013-04-11 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
339 | Assembly of midsection 4 | 1.2.1.6 | 338FS | FS340;FS362 | 2013-04-12 06:00 | 2013-04-20 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
340 | Assembly of midsection 5 | 1.2.1.7 | 339FS | FS341;FS363 | 2013-04-21 06:00 | 2013-04-29 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
341 | Assembly of midsection 6 | 1.2.1.8 | 340FS | FS342;FS364 | 2013-04-30 06:00 | 2013-05-08 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
342 | Assembly of midsection 7 | 1.2.1.9 | 341FS | FS343;FS365 | 2013-05-09 06:00 | 2013-05-17 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
343 | Assembly of midsection 8 | 1.2.1.10 | 342FS | FS344;FS366 | 2013-05-18 06:00 | 2013-05-26 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
344 | Assembly of midsection 9 | 1.2.1.11 | 343FS | FS345;FS367 | 2013-05-27 06:00 | 2013-06-04 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
345 | Assembly of midsection 10 | 1.2.1.12 | 344FS | FS346;FS368 | 2013-06-05 06:00 | 2013-06-13 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
346 | Assembly of midsection 11 | 1.2.1.13 | 345FS | FS347;FS369 | 2013-06-14 06:00 | 2013-06-22 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
347 | Assembly of midsection 12 | 1.2.1.14 | 346FS | FS348;FS370 | 2013-06-23 06:00 | 2013-07-01 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
348 | Assembly of midsection 13 | 1.2.1.15 | 347FS | FS349;FS371 | 2013-07-02 06:00 | 2013-07-10 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
349 | Assembly of midsection 14 | 1.2.1.16 | 348FS | FS350;FS372 | 2013-07-11 06:00 | 2013-07-19 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
350 | Assembly of midsection 15 | 1.2.1.17 | 349FS | FS351;FS373 | 2013-07-20 06:00 | 2013-07-28 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
351 | Assembly of midsection 16 | 1.2.1.18 | 350FS | FS352;FS374 | 2013-07-29 06:00 | 2013-08-06 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
352 | Assembly of midsection 17 | 1.2.1.19 | 351FS | FS353;FS375 | 2013-08-07 06:00 | 2013-08-15 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
353 | Assembly of midsection 18 | 1.2.1.20 | 352FS | FS354;FS376 | 2013-08-16 06:00 | 2013-08-24 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
354 | Assembly of midsection 19 | 1.2.1.21 | 353FS | FS355;FS377 | 2013-08-25 06:00 | 2013-09-02 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
355 | Assembly of midsection 20 | 1.2.1.22 | 354FS | FS356;FS378 | 2013-09-03 06:00 | 2013-09-11 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
356 | Assembly of midsection 21 | 1.2.1.23 | 355FS | FS357;FS379 | 2013-09-12 06:00 | 2013-09-20 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
357 | Assembly of midsection 22 | 1.2.1.24 | 356FS | FS358;FS380 | 2013-09-21 06:00 | 2013-09-29 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
358 | Assembly of midsection 23 | 1.2.1.25 | 357FS | FS359;FS381 | 2013-09-30 06:00 | 2013-10-08 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
359 | Assembly of midsection 24 | 1.2.1.26 | 358FS | FS382 | 2013-10-09 06:00 | 2013-10-17 22:00 | 9d |  | 0 | 55100 | 0 | 0 | 55100 | 8.6667
27 | Purchase of secondary steel items | 1.2.1.27 |  | SS29+5w 5d;SS360+5w 5d;SS361+5w 5d;SS362+5w 5d;SS363+5w 5d;SS364+5w 5d;SS365+5w 5d;SS366+5w 5d;SS367+5w 5d;SS368+5w 5d;SS369+5w 5d;SS370+5w 5d;SS371+5w 5d;SS372+5w 5d;SS373+5w 5d;SS374+5w 5d;SS375+5w 5d;SS376+5w 5d;SS377+5w 5d;SS378+5w 5d;SS379+5w 5d;SS380+5w 5d;SS381+5w 5d;SS382+5w 5d | 2013-02-13 06:00 | 2013-05-03 22:00 | 80d |  | 0 | 350000 | 0 | 0 | 350000 | 79.6667
29 | Final jacket assembly 1 | 1.2.1.28 | 25FS;27SS+5w 5d | FS31 | 2013-03-25 06:00 | 2013-04-02 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
360 | Final jacket assembly 2 | 1.2.1.29 | 337FS;27SS+5w 5d | FS383 | 2013-04-03 06:00 | 2013-04-11 22:00 | 9d |  | 0 | 40600 | 1 | 144 | 40744 | 8.6667
361 | Final jacket assembly 3 | 1.2.1.30 | 338FS;27SS+5w 5d | FS384 | 2013-04-12 06:00 | 2013-04-20 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
362 | Final jacket assembly 4 | 1.2.1.31 | 339FS;27SS+5w 5d | FS385 | 2013-04-21 06:00 | 2013-04-29 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
363 | Final jacket assembly 5 | 1.2.1.32 | 340FS;27SS+5w 5d | FS386 | 2013-04-30 06:00 | 2013-05-08 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
364 | Final jacket assembly 6 | 1.2.1.33 | 341FS;27SS+5w 5d | FS387 | 2013-05-09 06:00 | 2013-05-17 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
365 | Final jacket assembly 7 | 1.2.1.34 | 342FS;27SS+5w 5d | FS388 | 2013-05-18 06:00 | 2013-05-26 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
366 | Final jacket assembly 8 | 1.2.1.35 | 343FS;27SS+5w 5d | FS389 | 2013-05-27 06:00 | 2013-06-04 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
367 | Final jacket assembly 9 | 1.2.1.36 | 344FS;27SS+5w 5d | FS390 | 2013-06-05 06:00 | 2013-06-13 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
368 | Final jacket assembly 10 | 1.2.1.37 | 345FS;27SS+5w 5d | FS391 | 2013-06-14 06:00 | 2013-06-22 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
369 | Final jacket assembly 11 | 1.2.1.38 | 346FS;27SS+5w 5d | FS392 | 2013-06-23 06:00 | 2013-07-01 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
370 | Final jacket assembly 12 | 1.2.1.39 | 347FS;27SS+5w 5d | FS393 | 2013-07-02 06:00 | 2013-07-10 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
371 | Final jacket assembly 13 | 1.2.1.40 | 348FS;27SS+5w 5d | FS394 | 2013-07-11 06:00 | 2013-07-19 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
372 | Final jacket assembly 14 | 1.2.1.41 | 349FS;27SS+5w 5d | FS395 | 2013-07-20 06:00 | 2013-07-28 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
373 | Final jacket assembly 15 | 1.2.1.42 | 350FS;27SS+5w 5d | FS396 | 2013-07-29 06:00 | 2013-08-06 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
374 | Final jacket assembly 16 | 1.2.1.43 | 351FS;27SS+5w 5d | FS397 | 2013-08-07 06:00 | 2013-08-15 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
375 | Final jacket assembly 17 | 1.2.1.44 | 352FS;27SS+5w 5d | FS398 | 2013-08-16 06:00 | 2013-08-24 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
376 | Final jacket assembly 18 | 1.2.1.45 | 353FS;27SS+5w 5d | FS399 | 2013-08-25 06:00 | 2013-09-02 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
377 | Final jacket assembly 19 | 1.2.1.46 | 354FS;27SS+5w 5d | FS400 | 2013-09-03 06:00 | 2013-09-11 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
378 | Final jacket assembly 20 | 1.2.1.47 | 355FS;27SS+5w 5d | FS401 | 2013-09-12 06:00 | 2013-09-20 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
379 | Final jacket assembly 21 | 1.2.1.48 | 356FS;27SS+5w 5d | FS402 | 2013-09-21 06:00 | 2013-09-29 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
380 | Final jacket assembly 22 | 1.2.1.49 | 357FS;27SS+5w 5d | FS403 | 2013-09-30 06:00 | 2013-10-08 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
381 | Final jacket assembly 23 | 1.2.1.50 | 358FS;27SS+5w 5d | FS404 | 2013-10-09 06:00 | 2013-10-17 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
382 | Final jacket assembly 24 | 1.2.1.51 | 359FS;27SS+5w 5d | FS405 | 2013-10-18 06:00 | 2013-10-26 22:00 | 9d |  | 0 | 40600 | 0 | 0 | 40600 | 8.6667
31 | Transport (Hoboken to Vlissingen) 1 | 1.2.1.52 | 29FS | FS313 | 2013-04-03 06:00 | 2013-04-03 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
383 | Transport (Hoboken to Vlissingen) 2 | 1.2.1.53 | 360FS | FS314 | 2013-04-12 06:00 | 2013-04-12 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
384 | Transport (Hoboken to Vlissingen) 3 | 1.2.1.54 | 361FS | FS315 | 2013-04-21 06:00 | 2013-04-21 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
385 | Transport (Hoboken to Vlissingen) 4 | 1.2.1.55 | 362FS | FS316 | 2013-04-30 06:00 | 2013-04-30 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
386 | Transport (Hoboken to Vlissingen) 5 | 1.2.1.56 | 363FS | FS317 | 2013-05-09 06:00 | 2013-05-09 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
387 | Transport (Hoboken to Vlissingen) 6 | 1.2.1.57 | 364FS | FS318 | 2013-05-18 06:00 | 2013-05-18 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
388 | Transport (Hoboken to Vlissingen) 7 | 1.2.1.58 | 365FS | FS319 | 2013-05-27 06:00 | 2013-05-27 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
389 | Transport (Hoboken to Vlissingen) 8 | 1.2.1.59 | 366FS | FS320 | 2013-06-05 06:00 | 2013-06-05 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
390 | Transport (Hoboken to Vlissingen) 9 | 1.2.1.60 | 367FS | FS321 | 2013-06-14 06:00 | 2013-06-14 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
391 | Transport (Hoboken to Vlissingen) 10 | 1.2.1.61 | 368FS | FS322 | 2013-06-23 06:00 | 2013-06-23 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
392 | Transport (Hoboken to Vlissingen) 11 | 1.2.1.62 | 369FS | FS323 | 2013-07-02 06:00 | 2013-07-02 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
393 | Transport (Hoboken to Vlissingen) 12 | 1.2.1.63 | 370FS | FS324 | 2013-07-11 06:00 | 2013-07-11 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
394 | Transport (Hoboken to Vlissingen) 13 | 1.2.1.64 | 371FS | FS325 | 2013-07-20 06:00 | 2013-07-20 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
395 | Transport (Hoboken to Vlissingen) 14 | 1.2.1.65 | 372FS | FS326 | 2013-07-29 06:00 | 2013-07-29 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
396 | Transport (Hoboken to Vlissingen) 15 | 1.2.1.66 | 373FS | FS327 | 2013-08-07 06:00 | 2013-08-07 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
397 | Transport (Hoboken to Vlissingen) 16 | 1.2.1.67 | 374FS | FS328 | 2013-08-16 06:00 | 2013-08-16 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
398 | Transport (Hoboken to Vlissingen) 17 | 1.2.1.68 | 375FS | FS329 | 2013-08-25 06:00 | 2013-08-25 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
399 | Transport (Hoboken to Vlissingen) 18 | 1.2.1.69 | 376FS | FS330 | 2013-09-03 06:00 | 2013-09-03 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
400 | Transport (Hoboken to Vlissingen) 19 | 1.2.1.70 | 377FS | FS331 | 2013-09-12 06:00 | 2013-09-12 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
401 | Transport (Hoboken to Vlissingen) 20 | 1.2.1.71 | 378FS | FS332 | 2013-09-21 06:00 | 2013-09-21 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
402 | Transport (Hoboken to Vlissingen) 21 | 1.2.1.72 | 379FS | FS333 | 2013-09-30 06:00 | 2013-09-30 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
403 | Transport (Hoboken to Vlissingen) 22 | 1.2.1.73 | 380FS | FS334 | 2013-10-09 06:00 | 2013-10-09 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
404 | Transport (Hoboken to Vlissingen) 23 | 1.2.1.74 | 381FS | FS335 | 2013-10-18 06:00 | 2013-10-18 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
405 | Transport (Hoboken to Vlissingen) 24 | 1.2.1.75 | 382FS | FS336 | 2013-10-27 06:00 | 2013-10-27 22:00 | 1d |  | 0 | 14500 | 0 | 0 | 14500 | 0.66667
44 | Transportation and installation of the jacket foundations | 1.2.2 |  |  | 2013-04-29 06:00 | 2013-10-30 22:00 | 185d |  |  | 2352000 |  |  | 7378560 | 184.6667
313 | Transport of the jacket foundations 1 | 1.2.2.1 | 31FS | FS289 | 2013-05-04 06:00 | 2013-05-04 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
314 | Transport of the jacket foundations 2 | 1.2.2.2 | 383FS | FS290 | 2013-05-03 06:00 | 2013-05-03 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
315 | Transport of the jacket foundations 3 | 1.2.2.3 | 384FS | FS291 | 2013-04-29 06:00 | 2013-04-29 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
316 | Transport of the jacket foundations 4 | 1.2.2.4 | 385FS | FS292 | 2013-05-02 06:00 | 2013-05-02 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
317 | Transport of the jacket foundations 5 | 1.2.2.5 | 386FS | FS293 | 2013-05-14 06:00 | 2013-05-14 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
318 | Transport of the jacket foundations 6 | 1.2.2.6 | 387FS | FS294 | 2013-05-19 06:00 | 2013-05-19 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
319 | Transport of the jacket foundations 7 | 1.2.2.7 | 388FS | FS295 | 2013-05-28 06:00 | 2013-05-28 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
320 | Transport of the jacket foundations 8 | 1.2.2.8 | 389FS | FS296 | 2013-06-06 06:00 | 2013-06-06 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
321 | Transport of the jacket foundations 9 | 1.2.2.9 | 390FS | FS297 | 2013-06-15 06:00 | 2013-06-15 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
322 | Transport of the jacket foundations 10 | 1.2.2.10 | 391FS | FS298 | 2013-06-24 06:00 | 2013-06-24 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
323 | Transport of the jacket foundations 11 | 1.2.2.11 | 392FS | FS299 | 2013-07-03 06:00 | 2013-07-03 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
324 | Transport of the jacket foundations 12 | 1.2.2.12 | 393FS | FS300 | 2013-07-12 06:00 | 2013-07-12 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
325 | Transport of the jacket foundations 13 | 1.2.2.13 | 394FS | FS301 | 2013-07-21 06:00 | 2013-07-21 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
326 | Transport of the jacket foundations 14 | 1.2.2.14 | 395FS | FS302 | 2013-07-30 06:00 | 2013-07-30 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
327 | Transport of the jacket foundations 15 | 1.2.2.15 | 396FS | FS303 | 2013-08-08 06:00 | 2013-08-08 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
328 | Transport of the jacket foundations 16 | 1.2.2.16 | 397FS | FS304 | 2013-08-17 06:00 | 2013-08-17 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
329 | Transport of the jacket foundations 17 | 1.2.2.17 | 398FS | FS305 | 2013-08-26 06:00 | 2013-08-26 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
330 | Transport of the jacket foundations 18 | 1.2.2.18 | 399FS | FS306 | 2013-09-04 06:00 | 2013-09-04 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
331 | Transport of the jacket foundations 19 | 1.2.2.19 | 400FS | FS307 | 2013-09-13 06:00 | 2013-09-13 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
332 | Transport of the jacket foundations 20 | 1.2.2.20 | 401FS | FS308 | 2013-09-22 06:00 | 2013-09-22 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
333 | Transport of the jacket foundations 21 | 1.2.2.21 | 402FS | FS309 | 2013-10-01 06:00 | 2013-10-01 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
334 | Transport of the jacket foundations 22 | 1.2.2.22 | 403FS | FS310 | 2013-10-10 06:00 | 2013-10-10 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
335 | Transport of the jacket foundations 23 | 1.2.2.23 | 404FS | FS311 | 2013-10-19 06:00 | 2013-10-19 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
336 | Transport of the jacket foundations 24 | 1.2.2.24 | 405FS | FS312 | 2013-10-28 06:00 | 2013-10-28 22:00 | 1d | Laborer[6.00 #60];Skipper;Towning tugs;Transport barges;Crane[2.00 #3] | 24800 | 0 | 0 | 0 | 24800 | 0.66667
289 | Installation of the jacket foundations 1 | 1.2.2.25 | 313FS;241FS+2w 1d | FS265 | 2013-06-09 06:00 | 2013-06-09 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
290 | Installation of the jacket foundations 2 | 1.2.2.26 | 314FS;242FS+2w 1d | FS266 | 2013-06-13 06:00 | 2013-06-13 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
291 | Installation of the jacket foundations 3 | 1.2.2.27 | 315FS;243FS+2w 1d | FS267 | 2013-06-17 06:00 | 2013-06-17 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
292 | Installation of the jacket foundations 4 | 1.2.2.28 | 316FS;244FS+2w 1d | FS268 | 2013-06-21 06:00 | 2013-06-21 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
293 | Installation of the jacket foundations 5 | 1.2.2.29 | 317FS;245FS+2w 1d | FS269 | 2013-06-26 06:00 | 2013-06-26 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
294 | Installation of the jacket foundations 6 | 1.2.2.30 | 318FS;246FS+2w 1d | FS270 | 2013-06-30 06:00 | 2013-06-30 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
295 | Installation of the jacket foundations 7 | 1.2.2.31 | 319FS;247FS+2w 1d | FS271 | 2013-07-04 06:00 | 2013-07-04 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
296 | Installation of the jacket foundations 8 | 1.2.2.32 | 320FS;248FS+2w 1d | FS272 | 2013-07-08 06:00 | 2013-07-08 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
297 | Installation of the jacket foundations 9 | 1.2.2.33 | 321FS;249FS+2w 1d | FS273 | 2013-07-12 06:00 | 2013-07-12 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
298 | Installation of the jacket foundations 10 | 1.2.2.34 | 322FS;250FS+2w 1d | FS274 | 2013-07-16 06:00 | 2013-07-16 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
299 | Installation of the jacket foundations 11 | 1.2.2.35 | 323FS;251FS+2w 1d | FS275 | 2013-07-20 06:00 | 2013-07-20 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
300 | Installation of the jacket foundations 12 | 1.2.2.36 | 324FS;252FS+2w 1d | FS276 | 2013-07-24 06:00 | 2013-07-24 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
301 | Installation of the jacket foundations 13 | 1.2.2.37 | 325FS;253FS+2w 1d | FS277 | 2013-07-28 06:00 | 2013-07-28 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
302 | Installation of the jacket foundations 14 | 1.2.2.38 | 326FS;254FS+2w 1d | FS278 | 2013-08-01 06:00 | 2013-08-01 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
303 | Installation of the jacket foundations 15 | 1.2.2.39 | 327FS;255FS+2w 1d | FS279 | 2013-08-09 06:00 | 2013-08-09 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
304 | Installation of the jacket foundations 16 | 1.2.2.40 | 328FS;256FS+2w 1d | FS280 | 2013-08-18 06:00 | 2013-08-18 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
305 | Installation of the jacket foundations 17 | 1.2.2.41 | 329FS;257FS+2w 1d | FS281 | 2013-08-27 06:00 | 2013-08-27 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
306 | Installation of the jacket foundations 18 | 1.2.2.42 | 330FS;258FS+2w 1d | FS282 | 2013-09-05 06:00 | 2013-09-05 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
307 | Installation of the jacket foundations 19 | 1.2.2.43 | 331FS;259FS+2w 1d | FS283 | 2013-09-14 06:00 | 2013-09-14 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
308 | Installation of the jacket foundations 20 | 1.2.2.44 | 332FS;260FS+2w 1d | FS284 | 2013-09-23 06:00 | 2013-09-23 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
309 | Installation of the jacket foundations 21 | 1.2.2.45 | 333FS;261FS+2w 1d | FS285 | 2013-10-02 06:00 | 2013-10-02 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
310 | Installation of the jacket foundations 22 | 1.2.2.46 | 334FS;262FS+2w 1d | FS286 | 2013-10-11 06:00 | 2013-10-11 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
311 | Installation of the jacket foundations 23 | 1.2.2.47 | 335FS;263FS+2w 1d | FS287 | 2013-10-20 06:00 | 2013-10-20 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
312 | Installation of the jacket foundations 24 | 1.2.2.48 | 336FS;264FS+2w 1d | FS288 | 2013-10-29 06:00 | 2013-10-29 22:00 | 1d | Laborer[22.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 88320 | 0 | 0 | 0 | 88320 | 0.66667
265 | Grouting of foundation to the pin-piles 1 | 1.2.2.49 | 289FS | FS108;FS478+6d 4h | 2013-06-10 06:00 | 2013-06-10 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
266 | Grouting of foundation to the pin-piles 2 | 1.2.2.50 | 290FS | FS108;FS479+6d 4h | 2013-06-14 06:00 | 2013-06-14 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
267 | Grouting of foundation to the pin-piles 3 | 1.2.2.51 | 291FS | FS108;FS480+6d 4h | 2013-06-18 06:00 | 2013-06-18 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
268 | Grouting of foundation to the pin-piles 4 | 1.2.2.52 | 292FS | FS108;FS481+6d 4h | 2013-06-22 06:00 | 2013-06-22 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
269 | Grouting of foundation to the pin-piles 5 | 1.2.2.53 | 293FS | FS108;FS482+6d 4h | 2013-06-27 06:00 | 2013-06-27 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
270 | Grouting of foundation to the pin-piles 6 | 1.2.2.54 | 294FS | FS108;FS483+6d 4h | 2013-07-01 06:00 | 2013-07-01 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
271 | Grouting of foundation to the pin-piles 7 | 1.2.2.55 | 295FS | FS108;FS484+6d 4h | 2013-07-05 06:00 | 2013-07-05 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
272 | Grouting of foundation to the pin-piles 8 | 1.2.2.56 | 296FS | FS108;FS485+6d 4h | 2013-07-09 06:00 | 2013-07-09 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
273 | Grouting of foundation to the pin-piles 9 | 1.2.2.57 | 297FS | FS108;FS486+6d 4h | 2013-07-13 06:00 | 2013-07-13 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
274 | Grouting of foundation to the pin-piles 10 | 1.2.2.58 | 298FS | FS108;FS487+6d 4h | 2013-07-17 06:00 | 2013-07-17 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
275 | Grouting of foundation to the pin-piles 11 | 1.2.2.59 | 299FS | FS108;FS488+6d 4h | 2013-07-21 06:00 | 2013-07-21 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
276 | Grouting of foundation to the pin-piles 12 | 1.2.2.60 | 300FS | FS108;FS489+6d 4h | 2013-07-25 06:00 | 2013-07-25 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
277 | Grouting of foundation to the pin-piles 13 | 1.2.2.61 | 301FS | FS108;FS490+6d 4h | 2013-07-29 06:00 | 2013-07-29 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
278 | Grouting of foundation to the pin-piles 14 | 1.2.2.62 | 302FS | FS108;FS491+6d 4h | 2013-08-02 06:00 | 2013-08-02 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
279 | Grouting of foundation to the pin-piles 15 | 1.2.2.63 | 303FS | FS108;FS492+6d 4h | 2013-08-10 06:00 | 2013-08-10 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
280 | Grouting of foundation to the pin-piles 16 | 1.2.2.64 | 304FS | FS108;FS493+6d 4h | 2013-08-19 06:00 | 2013-08-19 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
281 | Grouting of foundation to the pin-piles 17 | 1.2.2.65 | 305FS | FS108;FS494+6d 4h | 2013-08-28 06:00 | 2013-08-28 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
282 | Grouting of foundation to the pin-piles 18 | 1.2.2.66 | 306FS | FS108;FS495+6d 4h | 2013-09-06 06:00 | 2013-09-06 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
283 | Grouting of foundation to the pin-piles 19 | 1.2.2.67 | 307FS | FS108;FS496+6d 4h | 2013-09-15 06:00 | 2013-09-15 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
284 | Grouting of foundation to the pin-piles 20 | 1.2.2.68 | 308FS | FS108;FS497+6d 4h | 2013-09-24 06:00 | 2013-09-24 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
285 | Grouting of foundation to the pin-piles 21 | 1.2.2.69 | 309FS | FS108;FS498+6d 4h | 2013-10-03 06:00 | 2013-10-03 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
286 | Grouting of foundation to the pin-piles 22 | 1.2.2.70 | 310FS | FS108;FS499+6d 4h | 2013-10-12 06:00 | 2013-10-12 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
287 | Grouting of foundation to the pin-piles 23 | 1.2.2.71 | 311FS | FS108;FS500+6d | 2013-10-21 06:00 | 2013-10-21 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
288 | Grouting of foundation to the pin-piles 24 | 1.2.2.72 | 312FS | FS108;FS501+6d | 2013-10-30 06:00 | 2013-10-30 22:00 | 1d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Diving team;Vessel Rambiz | 96320 | 98000 | 0 | 0 | 194320 | 0.66667
74 | Wind turbines | 1.3 |  |  | 2013-02-04 18:00 | 2014-05-18 07:00 | 467d 5h |  |  | 60902000 |  |  | 82096544.0046 | 467.5417
62 | Purchasing parts of wind turbines | 1.3.1 |  |  | 2013-02-04 18:00 | 2014-01-14 22:00 | 344d 4h |  |  | 60902000 |  |  | 64477040 | 344.1667
54 | Purchasing and production of parts of wind turbines | 1.3.1.1 |  |  | 2013-02-04 18:00 | 2014-01-06 22:00 | 336d 4h |  |  | 57600000 |  |  | 57600000 | 336.1667
46 | Towers by AMAU-Cuxhaven Germany | 1.3.1.1.1 |  | SS53+28w 4d | 2013-05-12 06:00 | 2014-01-06 22:00 | 240d |  | 0 | 14400000 | 0 | 0 | 14400000 | 239.6667
47 | Blades by LM Denmark | 1.3.1.1.2 |  | SS52+28w 4d | 2013-02-04 18:00 | 2013-10-02 18:00 | 240d |  | 0 | 8640000 | 0 | 0 | 8640000 | 240
48 | Generators by VEM Germany | 1.3.1.1.3 |  | SS51+28w 4d | 2013-03-16 07:00 | 2013-11-11 07:00 | 240d |  | 0 | 12096000 | 0 | 0 | 12096000 | 240
49 | Gearboxes by WINERGY-Vörde Germany and Hansen Belgium | 1.3.1.1.4 |  | SS50+28w 4d | 2013-03-16 07:00 | 2013-11-11 07:00 | 240d |  | 0 | 22464000 | 0 | 0 | 22464000 | 240
55 | Transportation of parts from respective factories to Ostend | 1.3.1.2 |  |  | 2013-08-23 18:00 | 2014-01-14 22:00 | 144d 4h |  |  | 3302000 |  |  | 3302000 | 144.1667
53 | Towers Germany-Ostend | 1.3.1.2.1 | 46SS+28w 4d | SS502+2w 6d;SS503+2w 6d;SS504+2w 6d;SS505+2w 6d;SS506+2w 6d;SS507+2w 6d;SS508+2w 6d;SS509+2w 6d;SS510+2w 6d;SS511+2w 6d;SS512+2w 6d;SS513+2w 6d;SS514+2w 6d;SS515+2w 6d;SS516+2w 6d;SS517+2w 6d;SS518+2w 6d;SS519+2w 6d;SS520+2w 6d;SS521+2w 6d;SS522+2w 6d;SS523+2w 6d;SS524+2w 6d;SS525+2w 6d | 2013-11-28 06:00 | 2014-01-14 22:00 | 48d |  | 0 | 624000 | 0 | 0 | 624000 | 47.6667
52 | Blades Denmark-Ostend | 1.3.1.2.2 | 47SS+28w 4d | FS58 | 2013-08-23 18:00 | 2013-10-02 07:00 | 39d 5h |  | 0 | 624000 | 0 | 0 | 624000 | 39.5417
51 | Generators Germany-Ostend | 1.3.1.2.3 | 48SS+28w 4d | FS57 | 2013-10-02 07:00 | 2013-11-19 07:00 | 48d |  | 0 | 1027000 | 0 | 0 | 1027000 | 48
50 | Gearboxes Germany-Ostend/Antwerp-Ostend | 1.3.1.2.4 | 49SS+28w 4d | FS57 | 2013-10-02 07:00 | 2013-11-19 07:00 | 48d |  | 0 | 1027000 | 0 | 0 | 1027000 | 48
56 | Preparation of the onshore site | 1.3.1.3 |  | FS58;FS57 | 2013-03-18 06:00 | 2013-04-16 22:00 | 30d | Laborer[32.00 #60];Engineer[6.00 #18];Crane[3.00 #3] | 1363200 | 0 | 0 | 0 | 1363200 | 29.6667
61 | Assembly of wind turbines on site in Ostend | 1.3.1.4 |  |  | 2013-10-02 07:00 | 2014-01-06 07:00 | 96d |  |  | 0 |  |  | 2211840 | 96
57 | Assembly of gearbox and generator | 1.3.1.4.1 | 51FS;50FS;56FS | SS502+2w 6d;SS503+2w 6d;SS504+2w 6d;SS505+2w 6d;SS506+2w 6d;SS507+2w 6d;SS508+2w 6d;SS509+2w 6d;SS510+2w 6d;SS511+2w 6d;SS512+2w 6d;SS513+2w 6d;SS514+2w 6d;SS515+2w 6d;SS516+2w 6d;SS517+2w 6d;SS518+2w 6d;SS519+2w 6d;SS520+2w 6d;SS521+2w 6d;SS522+2w 6d;SS523+2w 6d;SS524+2w 6d;SS525+2w 6d | 2013-11-19 07:00 | 2014-01-06 07:00 | 48d | Laborer[16.00 #60];Welder;Engineer[3.00 #18];Crane | 1059840 | 0 | 0 | 0 | 1059840 | 48
58 | Assembly of blades | 1.3.1.4.2 | 52FS;56FS | SS502+2w 6d;SS503+2w 6d;SS504+2w 6d;SS505+2w 6d;SS506+2w 6d;SS507+2w 6d;SS508+2w 6d;SS509+2w 6d;SS510+2w 6d;SS511+2w 6d;SS512+2w 6d;SS513+2w 6d;SS514+2w 6d;SS515+2w 6d;SS516+2w 6d;SS517+2w 6d;SS518+2w 6d;SS519+2w 6d;SS520+2w 6d;SS521+2w 6d;SS522+2w 6d;SS523+2w 6d;SS524+2w 6d;SS525+2w 6d | 2013-10-02 07:00 | 2013-11-19 07:00 | 48d | Laborer[19.00 #60];Welder;Engineer[3.00 #18];Crane | 1152000 | 0 | 0 | 0 | 1152000 | 48
73 | Installation wind turbines | 1.3.2 |  |  | 2013-12-18 06:00 | 2014-05-18 07:00 | 151d 1h |  |  | 0 |  |  | 17619504.0046 | 151.0417
502 | Loading jack up transport and installation platform 1 | 1.3.2.1 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS478 | 2013-12-18 06:00 | 2013-12-20 22:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 13225 | 634800 | 1074960 | 2.6667
503 | Loading jack up transport and installation platform 2 | 1.3.2.2 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS479 | 2014-01-06 07:00 | 2014-01-09 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
504 | Loading jack up transport and installation platform 3 | 1.3.2.3 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS480 | 2014-01-10 07:00 | 2014-01-13 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
505 | Loading jack up transport and installation platform 4 | 1.3.2.4 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS481 | 2014-01-14 07:00 | 2014-01-17 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
506 | Loading jack up transport and installation platform 5 | 1.3.2.5 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS482 | 2014-01-18 07:00 | 2014-01-21 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
507 | Loading jack up transport and installation platform 6 | 1.3.2.6 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS483 | 2014-01-22 07:00 | 2014-01-25 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
508 | Loading jack up transport and installation platform 7 | 1.3.2.7 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS484 | 2014-01-26 07:00 | 2014-01-29 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
509 | Loading jack up transport and installation platform 8 | 1.3.2.8 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS485 | 2014-01-30 07:00 | 2014-02-02 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
510 | Loading jack up transport and installation platform 9 | 1.3.2.9 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS486 | 2014-02-03 07:00 | 2014-02-06 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
511 | Loading jack up transport and installation platform 10 | 1.3.2.10 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS487 | 2014-02-07 07:00 | 2014-02-10 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
512 | Loading jack up transport and installation platform 11 | 1.3.2.11 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS488 | 2014-02-11 07:00 | 2014-02-14 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
513 | Loading jack up transport and installation platform 12 | 1.3.2.12 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS489 | 2014-02-15 07:00 | 2014-02-18 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
514 | Loading jack up transport and installation platform 13 | 1.3.2.13 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS490 | 2014-02-19 07:00 | 2014-02-22 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
515 | Loading jack up transport and installation platform 14 | 1.3.2.14 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS491 | 2014-02-23 07:00 | 2014-02-26 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
516 | Loading jack up transport and installation platform 15 | 1.3.2.15 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS492 | 2014-02-27 07:00 | 2014-03-02 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
517 | Loading jack up transport and installation platform 16 | 1.3.2.16 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS493 | 2014-03-03 07:00 | 2014-03-06 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
518 | Loading jack up transport and installation platform 17 | 1.3.2.17 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS494 | 2014-03-07 07:00 | 2014-03-10 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
519 | Loading jack up transport and installation platform 18 | 1.3.2.18 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS495 | 2014-03-11 07:00 | 2014-03-14 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
520 | Loading jack up transport and installation platform 19 | 1.3.2.19 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS496 | 2014-03-15 07:00 | 2014-03-18 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
521 | Loading jack up transport and installation platform 20 | 1.3.2.20 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS497 | 2014-03-19 07:00 | 2014-03-22 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
522 | Loading jack up transport and installation platform 21 | 1.3.2.21 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS498 | 2014-03-23 07:00 | 2014-03-26 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
523 | Loading jack up transport and installation platform 22 | 1.3.2.22 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS499 | 2014-03-27 07:00 | 2014-03-30 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
524 | Loading jack up transport and installation platform 23 | 1.3.2.23 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS500 | 2014-03-31 07:00 | 2014-04-03 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
525 | Loading jack up transport and installation platform 24 | 1.3.2.24 | 53SS+2w 6d;57SS+2w 6d;58SS+2w 6d | FS501 | 2014-04-04 07:00 | 2014-04-07 07:00 | 3d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant;Crane | 440160 | 0 | 0 | 0 | 440160 | 3
478 | Offshore assembly of wind turbines 1 | 1.3.2.25 | 502FS;265FS+6d 4h | SS454+3d | 2013-12-21 06:00 | 2013-12-21 22:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 13224 | 211584 | 355104 | 0.66667
479 | Offshore assembly of wind turbines 2 | 1.3.2.26 | 503FS;266FS+6d 4h | SS455+3d | 2014-01-09 07:00 | 2014-01-10 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
480 | Offshore assembly of wind turbines 3 | 1.3.2.27 | 504FS;267FS+6d 4h | SS456+3d | 2014-01-13 07:00 | 2014-01-14 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
481 | Offshore assembly of wind turbines 4 | 1.3.2.28 | 505FS;268FS+6d 4h | SS457+3d | 2014-01-17 07:00 | 2014-01-18 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
482 | Offshore assembly of wind turbines 5 | 1.3.2.29 | 506FS;269FS+6d 4h | SS458+3d | 2014-01-21 07:00 | 2014-01-22 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
483 | Offshore assembly of wind turbines 6 | 1.3.2.30 | 507FS;270FS+6d 4h | SS459+3d | 2014-01-25 07:00 | 2014-01-26 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
484 | Offshore assembly of wind turbines 7 | 1.3.2.31 | 508FS;271FS+6d 4h | FS460+3d | 2014-01-29 07:00 | 2014-01-30 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
485 | Offshore assembly of wind turbines 8 | 1.3.2.32 | 509FS;272FS+6d 4h | SS461+3d | 2014-02-02 07:00 | 2014-02-03 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
486 | Offshore assembly of wind turbines 9 | 1.3.2.33 | 510FS;273FS+6d 4h | SS462+3d | 2014-02-06 07:00 | 2014-02-07 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
487 | Offshore assembly of wind turbines 10 | 1.3.2.34 | 511FS;274FS+6d 4h | SS463+3d | 2014-02-10 07:00 | 2014-02-11 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
488 | Offshore assembly of wind turbines 11 | 1.3.2.35 | 512FS;275FS+6d 4h | SS464+3d | 2014-02-14 07:00 | 2014-02-15 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
489 | Offshore assembly of wind turbines 12 | 1.3.2.36 | 513FS;276FS+6d 4h | SS465+3d | 2014-02-18 07:00 | 2014-02-19 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
490 | Offshore assembly of wind turbines 13 | 1.3.2.37 | 514FS;277FS+6d 4h | SS466+3d | 2014-02-22 07:00 | 2014-02-23 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
491 | Offshore assembly of wind turbines 14 | 1.3.2.38 | 515FS;278FS+6d 4h | SS467+3d | 2014-02-26 07:00 | 2014-02-27 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
492 | Offshore assembly of wind turbines 15 | 1.3.2.39 | 516FS;279FS+6d 4h | SS468+3d | 2014-03-02 07:00 | 2014-03-03 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
493 | Offshore assembly of wind turbines 16 | 1.3.2.40 | 517FS;280FS+6d 4h | SS469+3d | 2014-03-06 07:00 | 2014-03-07 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
494 | Offshore assembly of wind turbines 17 | 1.3.2.41 | 518FS;281FS+6d 4h | SS470+3d | 2014-03-10 07:00 | 2014-03-11 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
495 | Offshore assembly of wind turbines 18 | 1.3.2.42 | 519FS;282FS+6d 4h | SS471+3d | 2014-03-14 07:00 | 2014-03-15 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
496 | Offshore assembly of wind turbines 19 | 1.3.2.43 | 520FS;283FS+6d 4h | SS472+3d | 2014-03-18 07:00 | 2014-03-19 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
497 | Offshore assembly of wind turbines 20 | 1.3.2.44 | 521FS;284FS+6d 4h | SS473+3d | 2014-03-22 07:00 | 2014-03-23 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
498 | Offshore assembly of wind turbines 21 | 1.3.2.45 | 522FS;285FS+6d 4h | SS474+3d | 2014-03-26 07:00 | 2014-03-27 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
499 | Offshore assembly of wind turbines 22 | 1.3.2.46 | 523FS;286FS+6d 4h | SS475+3d | 2014-03-30 07:00 | 2014-03-31 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
500 | Offshore assembly of wind turbines 23 | 1.3.2.47 | 524FS;287FS+6d | SS476+3d | 2014-04-03 07:00 | 2014-04-04 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
501 | Offshore assembly of wind turbines 24 | 1.3.2.48 | 525FS;288FS+6d | SS477+3d | 2014-04-07 07:00 | 2014-04-08 07:00 | 1d | Laborer[16.00 #60];Skipper[2.00 #4];Engineer[8.00 #18];Vessel Neptune;Vessel Vagant | 143520 | 0 | 0 | 0 | 143520 | 1
454 | Terminations of infield cables 1 | 1.3.2.49 | 112FS;478SS+3d | FS430 | 2014-01-08 06:00 | 2014-01-10 22:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 2.6667
455 | Terminations of infield cables 2 | 1.3.2.50 | 112FS;479SS+3d | FS431 | 2014-01-12 07:00 | 2014-01-15 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
456 | Terminations of infield cables 3 | 1.3.2.51 | 112FS;480SS+3d | FS432 | 2014-01-16 07:00 | 2014-01-19 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
457 | Terminations of infield cables 4 | 1.3.2.52 | 112FS;481SS+3d | FS433 | 2014-01-20 07:00 | 2014-01-23 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
458 | Terminations of infield cables 5 | 1.3.2.53 | 112FS;482SS+3d | FS434 | 2014-01-24 07:00 | 2014-01-27 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
459 | Terminations of infield cables 6 | 1.3.2.54 | 112FS;483SS+3d | FS435 | 2014-01-28 07:00 | 2014-01-31 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
460 | Terminations of infield cables 7 | 1.3.2.55 | 112FS;484FS+3d | FS436 | 2014-02-02 07:00 | 2014-02-05 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
461 | Terminations of infield cables 8 | 1.3.2.56 | 112FS;485SS+3d | FS437 | 2014-02-05 07:00 | 2014-02-08 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
462 | Terminations of infield cables 9 | 1.3.2.57 | 112FS;486SS+3d | FS438 | 2014-02-09 07:00 | 2014-02-12 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
463 | Terminations of infield cables 10 | 1.3.2.58 | 112FS;487SS+3d | FS439 | 2014-02-13 07:00 | 2014-02-16 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
464 | Terminations of infield cables 11 | 1.3.2.59 | 112FS;488SS+3d | FS440 | 2014-02-17 07:00 | 2014-02-20 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
465 | Terminations of infield cables 12 | 1.3.2.60 | 112FS;489SS+3d | FS441 | 2014-02-21 07:00 | 2014-02-24 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
466 | Terminations of infield cables 13 | 1.3.2.61 | 112FS;490SS+3d | FS442 | 2014-02-25 07:00 | 2014-02-28 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
467 | Terminations of infield cables 14 | 1.3.2.62 | 112FS;491SS+3d | FS443 | 2014-03-01 07:00 | 2014-03-04 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
468 | Terminations of infield cables 15 | 1.3.2.63 | 112FS;492SS+3d | FS444 | 2014-03-05 07:00 | 2014-03-08 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
469 | Terminations of infield cables 16 | 1.3.2.64 | 112FS;493SS+3d | FS445 | 2014-03-09 07:00 | 2014-03-12 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
470 | Terminations of infield cables 17 | 1.3.2.65 | 112FS;494SS+3d | FS446 | 2014-03-13 07:00 | 2014-03-16 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
471 | Terminations of infield cables 18 | 1.3.2.66 | 112FS;495SS+3d | FS447 | 2014-03-17 07:00 | 2014-03-20 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
472 | Terminations of infield cables 19 | 1.3.2.67 | 112FS;496SS+3d | FS448 | 2014-03-21 07:00 | 2014-03-24 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
473 | Terminations of infield cables 20 | 1.3.2.68 | 112FS;497SS+3d | FS449 | 2014-03-25 07:00 | 2014-03-28 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
474 | Terminations of infield cables 21 | 1.3.2.69 | 112FS;498SS+3d | FS450 | 2014-03-29 07:00 | 2014-04-01 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
475 | Terminations of infield cables 22 | 1.3.2.70 | 112FS;499SS+3d | FS451 | 2014-04-02 07:00 | 2014-04-05 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
476 | Terminations of infield cables 23 | 1.3.2.71 | 112FS;500SS+3d | FS452 | 2014-04-06 07:00 | 2014-04-09 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
477 | Terminations of infield cables 24 | 1.3.2.72 | 112FS;501SS+3d | FS453 | 2014-04-10 07:00 | 2014-04-13 07:00 | 3d | Special team | 38400 | 0 | 0 | 0 | 38400 | 3
430 | Commissioning of wind turbines 1 | 1.3.2.73 | 154FS;454FS | FS406 | 2014-01-11 06:00 | 2014-01-15 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
431 | Commissioning of wind turbines 2 | 1.3.2.74 | 154FS;455FS | FS407 | 2014-01-16 06:00 | 2014-01-20 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
432 | Commissioning of wind turbines 3 | 1.3.2.75 | 154FS;456FS | FS408 | 2014-01-21 06:00 | 2014-01-25 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
433 | Commissioning of wind turbines 4 | 1.3.2.76 | 154FS;457FS | FS409 | 2014-01-26 06:00 | 2014-01-30 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
434 | Commissioning of wind turbines 5 | 1.3.2.77 | 154FS;458FS | FS410 | 2014-01-31 06:00 | 2014-02-04 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
435 | Commissioning of wind turbines 6 | 1.3.2.78 | 154FS;459FS | FS411 | 2014-02-05 06:00 | 2014-02-09 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
436 | Commissioning of wind turbines 7 | 1.3.2.79 | 154FS;460FS | FS412 | 2014-02-10 06:00 | 2014-02-14 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
437 | Commissioning of wind turbines 8 | 1.3.2.80 | 154FS;461FS | FS413 | 2014-02-15 06:00 | 2014-02-19 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
438 | Commissioning of wind turbines 9 | 1.3.2.81 | 154FS;462FS | FS414 | 2014-02-20 06:00 | 2014-02-24 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
439 | Commissioning of wind turbines 10 | 1.3.2.82 | 154FS;463FS | FS415 | 2014-02-25 06:00 | 2014-03-01 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
440 | Commissioning of wind turbines 11 | 1.3.2.83 | 154FS;464FS | FS416 | 2014-03-02 06:00 | 2014-03-06 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
441 | Commissioning of wind turbines 12 | 1.3.2.84 | 154FS;465FS | FS417 | 2014-03-07 06:00 | 2014-03-11 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
442 | Commissioning of wind turbines 13 | 1.3.2.85 | 154FS;466FS | FS418 | 2014-03-12 06:00 | 2014-03-16 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
443 | Commissioning of wind turbines 14 | 1.3.2.86 | 154FS;467FS | FS419 | 2014-03-17 06:00 | 2014-03-21 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
444 | Commissioning of wind turbines 15 | 1.3.2.87 | 154FS;468FS | FS420 | 2014-03-22 06:00 | 2014-03-26 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
445 | Commissioning of wind turbines 16 | 1.3.2.88 | 154FS;469FS | FS421 | 2014-03-27 06:00 | 2014-03-31 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
446 | Commissioning of wind turbines 17 | 1.3.2.89 | 154FS;470FS | FS422 | 2014-04-01 06:00 | 2014-04-05 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
447 | Commissioning of wind turbines 18 | 1.3.2.90 | 154FS;471FS | FS423 | 2014-04-06 06:00 | 2014-04-10 22:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 4.6667
448 | Commissioning of wind turbines 19 | 1.3.2.91 | 154FS;472FS | FS424 | 2014-04-18 07:00 | 2014-04-23 07:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 5
449 | Commissioning of wind turbines 20 | 1.3.2.92 | 154FS;473FS | FS425 | 2014-04-23 07:00 | 2014-04-28 07:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 5
450 | Commissioning of wind turbines 21 | 1.3.2.93 | 154FS;474FS | FS426 | 2014-04-28 07:00 | 2014-05-03 07:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 5
451 | Commissioning of wind turbines 22 | 1.3.2.94 | 154FS;475FS | FS427 | 2014-05-03 07:00 | 2014-05-08 07:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 5
452 | Commissioning of wind turbines 23 | 1.3.2.95 | 154FS;476FS | FS428 | 2014-05-08 07:00 | 2014-05-13 07:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 5
453 | Commissioning of wind turbines 24 | 1.3.2.96 | 154FS;477FS | FS429 | 2014-04-13 07:00 | 2014-04-18 07:00 | 5d | Commissioning team | 64000 | 0 | 0 | 0 | 64000 | 5
406 | Reliability tests 1 | 1.3.2.97 | 430FS |  | 2014-01-16 06:00 | 2014-01-20 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
407 | Reliability tests 2 | 1.3.2.98 | 431FS |  | 2014-01-21 06:00 | 2014-01-25 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
408 | Reliability tests 3 | 1.3.2.99 | 432FS |  | 2014-01-26 06:00 | 2014-01-30 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
409 | Reliability tests 4 | 1.3.2.100 | 433FS |  | 2014-01-31 06:00 | 2014-02-04 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
410 | Reliability tests 5 | 1.3.2.101 | 434FS |  | 2014-02-05 06:00 | 2014-02-09 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
411 | Reliability tests 6 | 1.3.2.102 | 435FS |  | 2014-02-10 06:00 | 2014-02-14 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
412 | Reliability tests 7 | 1.3.2.103 | 436FS |  | 2014-02-15 06:00 | 2014-02-19 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
413 | Reliability tests 8 | 1.3.2.104 | 437FS |  | 2014-02-20 06:00 | 2014-02-24 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
414 | Reliability tests 9 | 1.3.2.105 | 438FS |  | 2014-02-25 06:00 | 2014-03-01 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
415 | Reliability tests 10 | 1.3.2.106 | 439FS |  | 2014-03-02 06:00 | 2014-03-06 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
416 | Reliability tests 11 | 1.3.2.107 | 440FS |  | 2014-03-07 06:00 | 2014-03-11 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
417 | Reliability tests 12 | 1.3.2.108 | 441FS |  | 2014-03-12 06:00 | 2014-03-16 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
418 | Reliability tests 13 | 1.3.2.109 | 442FS |  | 2014-03-17 06:00 | 2014-03-21 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
419 | Reliability tests 14 | 1.3.2.110 | 443FS |  | 2014-03-22 06:00 | 2014-03-26 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
421 | Reliability tests 15 | 1.3.2.111 | 445FS |  | 2014-04-01 06:00 | 2014-04-05 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
420 | Reliability tests 16 | 1.3.2.112 | 444FS |  | 2014-03-27 06:00 | 2014-03-31 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
422 | Reliability tests 17 | 1.3.2.113 | 446FS |  | 2014-04-06 06:00 | 2014-04-10 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
423 | Reliability tests 18 | 1.3.2.114 | 447FS |  | 2014-04-11 06:00 | 2014-04-15 22:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 4.6667
424 | Reliability tests 19 | 1.3.2.115 | 448FS |  | 2014-04-23 07:00 | 2014-04-28 07:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 5
425 | Reliability tests 20 | 1.3.2.116 | 449FS |  | 2014-04-28 07:00 | 2014-05-03 07:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 5
426 | Reliability tests 21 | 1.3.2.117 | 450FS |  | 2014-05-03 07:00 | 2014-05-08 07:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 5
427 | Reliability tests 22 | 1.3.2.118 | 451FS |  | 2014-05-08 07:00 | 2014-05-13 07:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 5
428 | Reliability tests 23 | 1.3.2.119 | 452FS |  | 2014-05-13 07:00 | 2014-05-18 07:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 5
429 | Reliability tests 24 | 1.3.2.120 | 453FS |  | 2014-04-18 07:00 | 2014-04-23 07:00 | 5d | Testing team[0.20 #1] | 12800.0002 | 0 | 0 | 0 | 12800.0002 | 5
98 | Offshore Transformer Station | 1.4 |  |  | 2013-02-04 06:00 | 2013-09-18 07:00 | 226d 1h |  |  | 7433000 |  |  | 7706280 | 226.0417
80 | Construction of jacket foundation of OTS | 1.4.1 |  |  | 2013-02-04 06:00 | 2013-06-01 22:00 | 118d |  |  | 454000 |  |  | 499760 | 117.6667
75 | Purchase of base materials | 1.4.1.1 |  | FS76 | 2013-02-04 06:00 | 2013-03-15 22:00 | 40d |  | 0 | 176000 | 0 | 0 | 176000 | 39.6667
76 | Construction of jacket foundation for OTS | 1.4.1.2 | 75FS | FS77 | 2013-03-16 06:00 | 2013-03-25 22:00 | 10d |  | 0 | 278000 | 0 | 0 | 278000 | 9.6667
77 | Transport of jacket foundation to Ostend | 1.4.1.3 | 76FS | FS82 | 2013-05-31 06:00 | 2013-06-01 22:00 | 2d | Laborer[8.00 #60];Skipper;Towning tugs;Transport barges;Crane | 45760 | 0 | 0 | 0 | 45760 | 1.6667
83 | Installation of jacket foundation of OTS | 1.4.2 |  |  | 2013-06-02 06:00 | 2013-06-03 22:00 | 2d |  |  | 0 |  |  | 118880 | 1.6667
82 | Transport of jacket foundation in sea | 1.4.2.1 | 77FS;17FS+1w 5d | FS81 | 2013-06-02 06:00 | 2013-06-02 22:00 | 1d | Laborer[8.00 #60];Skipper;Engineer[4.00 #18];Towning tugs;Transport barges;Crane | 33120 | 0 | 0 | 0 | 33120 | 0.66667
81 | Installation of jacket foundation of OTS | 1.4.2.2 | 82FS | FS94 | 2013-06-03 06:00 | 2013-06-03 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 85760 | 0 | 0 | 0 | 85760 | 0.66667
93 | Steelstructure of Offshore OTS | 1.4.3 |  |  | 2013-02-04 06:00 | 2013-09-16 07:00 | 224d 1h |  |  | 6979000 |  |  | 6979000 | 224.0417
84 | Purchase of base materials | 1.4.3.1 |  | SS85+8w 4d | 2013-02-04 06:00 | 2013-07-03 22:00 | 150d |  | 0 | 3045000 | 0 | 0 | 3045000 | 149.6667
85 | Erection of 1st main deck section | 1.4.3.2 | 84SS+8w 4d | FS86 | 2013-04-05 06:00 | 2013-05-04 22:00 | 30d |  | 0 | 696000 | 0 | 0 | 696000 | 29.6667
86 | Erection of 2st main deck section | 1.4.3.3 | 85FS | FS87 | 2013-05-05 06:00 | 2013-06-03 22:00 | 30d |  | 0 | 696000 | 0 | 0 | 696000 | 29.6667
87 | Erection of mezzanine deck | 1.4.3.4 | 86FS | FS88 | 2013-06-04 06:00 | 2013-06-19 22:00 | 16d |  | 0 | 654000 | 0 | 0 | 654000 | 15.6667
88 | Construction of roof deck | 1.4.3.5 | 87FS | FS89 | 2013-06-20 06:00 | 2013-07-05 22:00 | 16d |  | 0 | 696000 | 0 | 0 | 696000 | 15.6667
89 | Internal finishings | 1.4.3.6 | 88FS | FS90 | 2013-07-06 06:00 | 2013-07-08 07:00 | 2d 1h |  | 0 | 205000 | 0 | 0 | 205000 | 2.0417
90 | Installation of transformer equipment | 1.4.3.7 | 89FS | FS91 | 2013-07-08 07:00 | 2013-09-06 07:00 | 60d |  | 0 | 864000 | 0 | 0 | 864000 | 60
91 | Preparation for upcoming transport | 1.4.3.8 | 90FS | FS94 | 2013-09-06 07:00 | 2013-09-16 07:00 | 10d |  | 0 | 123000 | 0 | 0 | 123000 | 10
97 | Transport and installation | 1.4.4 |  |  | 2013-09-16 07:00 | 2013-09-18 07:00 | 2d |  |  | 0 |  |  | 108640 | 2
94 | Transport of OTS | 1.4.4.1 | 81FS;91FS | FS95 | 2013-09-16 07:00 | 2013-09-17 07:00 | 1d | Laborer[4.00 #60];Skipper;Engineer;Towning tugs;Transport barges;Crane | 22880 | 0 | 0 | 0 | 22880 | 1
95 | Installation of OTS foundation | 1.4.4.2 | 94FS | FS100;FS152 | 2013-09-17 07:00 | 2013-09-18 07:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[6.00 #18];Vessel Rambiz | 85760 | 0 | 0 | 0 | 85760 | 1
125 | Infield cables (33 kV) | 1.5 |  |  | 2013-02-04 06:00 | 2014-01-07 22:00 | 338d |  |  | 2369600 |  |  | 9400480 | 337.6667
103 | Preparatory works for infield cable laying | 1.5.1 |  |  | 2013-09-18 07:00 | 2013-10-04 07:00 | 16d |  |  | 0 |  |  | 1075200 | 16
100 | Rock dumping as scour protection around the OTS foundation | 1.5.1.1 | 95FS | FS101 | 2013-09-18 07:00 | 2013-09-20 07:00 | 2d | Laborer[5.00 #60];Skipper;Engineer[4.00 #18];Vessel Pompei | 135040 | 0 | 0 | 0 | 135040 | 2
101 | GOSA mattresses installations above existing underground cables as protection | 1.5.1.2 | 100FS | FS102 | 2013-09-20 07:00 | 2013-10-02 07:00 | 12d | Laborer[5.00 #60];Skipper;Engineer[4.00 #18];Vessel Pompei | 810240 | 0 | 0 | 0 | 810240 | 12
102 | Pre-grapnel run to remove obstacles from cable trajectories | 1.5.1.3 | 101FS | FS108 | 2013-10-02 07:00 | 2013-10-04 07:00 | 2d | Laborer[5.00 #60];Skipper;Engineer[3.00 #18];Vessel Pompei | 129920 | 0 | 0 | 0 | 129920 | 2
124 | Infield cables: production, transport and installation | 1.5.2 |  |  | 2013-02-04 06:00 | 2014-01-07 22:00 | 338d |  |  | 2369600 |  |  | 8325280 | 337.6667
104 | Production in Karlskrona Sweden | 1.5.2.1 |  | FS105 | 2013-02-04 06:00 | 2013-06-03 22:00 | 120d |  | 0 | 2205000 | 0 | 0 | 2205000 | 119.6667
105 | Transport | 1.5.2.2 | 104FS | FS106 | 2013-06-06 06:00 | 2013-06-10 22:00 | 5d | Laborer[10.00 #60];Skipper;Vessel Souverreign;Crane | 312800 | 127000 | 0 | 0 | 439800 | 4.6667
106 | Pre-grapnel runs to remove obstacles | 1.5.2.3 | 105FS | FS107 | 2013-06-11 06:00 | 2013-06-11 22:00 | 1d | Laborer[18.00 #60];Skipper;Engineer[3.00 #18];Vessel Pompei | 73280 | 0 | 0 | 0 | 73280 | 0.66667
107 | Wet trials | 1.5.2.4 | 106FS | FS108 | 2013-06-12 06:00 | 2013-06-12 22:00 | 1d | Laborer[12.00 #60];Testing team | 20480 | 37600 | 0 | 0 | 58080 | 0.66667
108 | Cable laying works | 1.5.2.5 | 102FS;107FS;265FS;266FS;267FS;268FS;269FS;270FS;271FS;272FS;273FS;274FS;275FS;276FS;277FS;278FS;279FS;280FS;281FS;282FS;283FS;284FS;285FS;286FS;287FS;288FS | SS109+5d | 2013-10-31 06:00 | 2013-12-17 22:00 | 48d | Laborer[22.00 #60];Skipper;Vessel Innovator | 3217920 | 0 | 0 | 0 | 3217920 | 47.6667
109 | Final hang off of the cables in the WTG foundations | 1.5.2.6 | 108SS+5d | FS110 | 2013-11-05 06:00 | 2013-12-22 22:00 | 48d | Special team[2.00 #2] | 1228800 | 0 | 0 | 0 | 1228800 | 47.6667
110 | Burial of cables | 1.5.2.7 | 109FS | FS111 | 2013-12-23 06:00 | 2014-01-01 22:00 | 10d | Laborer[22.00 #60];Skipper;Engineer[4.00 #18];Vessel Innovator | 772800 | 0 | 0 | 0 | 772800 | 9.6667
111 | Survey of burial depths | 1.5.2.8 | 110FS | FS112 | 2014-01-02 06:00 | 2014-01-03 22:00 | 2d | Engineer[4.00 #18] | 20480 | 0 | 0 | 0 | 20480 | 1.6667
112 | Second remedial burial pass if necessary | 1.5.2.9 | 111FS | FS454;FS455;FS456;FS457;FS458;FS459;FS460;FS461;FS462;FS463;FS464;FS465;FS466;FS467;FS468;FS469;FS470;FS471;FS472;FS473;FS474;FS475;FS476;FS477 | 2014-01-04 06:00 | 2014-01-07 22:00 | 4d | Laborer[22.00 #60];Skipper;Engineer[4.00 #18];Vessel Innovator | 309120 | 0 | 0 | 0 | 309120 | 3.6667
161 | Export cables (150 kV) | 1.6 |  |  | 2013-02-04 06:00 | 2013-09-22 07:00 | 230d 1h |  |  | 3557200 |  |  | 7540240 | 230.0417
126 | Pre-lay grapnel run on trajectory | 1.6.1 |  | FS149 | 2013-02-04 06:00 | 2013-02-05 22:00 | 2d | Laborer[5.00 #60];Skipper;Engineer[3.00 #18];Vessel Pompei | 129920 | 0 | 0 | 0 | 129920 | 1.6667
132 | Production and transport of export cable | 1.6.2 |  |  | 2013-02-09 06:00 | 2013-05-13 22:00 | 94d |  |  | 2127630 |  |  | 2664430 | 93.6667
128 | Purchase of raw materials | 1.6.2.1 |  | SS129+7w 1d | 2013-02-09 06:00 | 2013-04-19 22:00 | 70d |  | 0 | 1470000 | 0 | 0 | 1470000 | 69.6667
129 | Manufacturing in Karlskrona Sweden | 1.6.2.2 | 128SS+7w 1d | FS131 | 2013-03-31 06:00 | 2013-05-09 22:00 | 40d |  | 0 | 625600 | 0 | 0 | 625600 | 39.6667
130 | Mobilisation of Stemat Spirit | 1.6.2.3 |  | FS131 | 2013-05-05 06:00 | 2013-05-09 22:00 | 5d | Laborer[6.00 #60];Skipper;Vessel Sternat Spirit | 284000 | 16570 | 0 | 0 | 300570 | 4.6667
131 | Transport Sweden-Ostend | 1.6.2.4 | 129FS;130FS | FS149 | 2013-05-10 06:00 | 2013-05-13 22:00 | 4d | Laborer[6.00 #60];Skipper;Vessel Sternat Spirit;Crane[2.00 #3] | 252800 | 15460 | 0 | 0 | 268260 | 3.6667
135 | Dredging shipping lane and preparing trench | 1.6.3 |  |  | 2013-05-04 06:00 | 2013-05-13 22:00 | 10d |  |  | 331000 |  |  | 1070200 | 9.6667
133 | Dredging to widen shipping lane Vaargeul1 | 1.6.3.1 |  | FS134 | 2013-05-04 06:00 | 2013-05-08 22:00 | 5d | Laborer[18.00 #60];Skipper;Engineer[4.00 #18];Vessel Breughel | 369600 | 112000 | 0 | 0 | 481600 | 4.6667
134 | Prepare trench where export cable B (150kV) is crossing Vaargeul1 | 1.6.3.2 | 133FS | FS149 | 2013-05-09 06:00 | 2013-05-13 22:00 | 5d | Laborer[18.00 #60];Skipper;Engineer[4.00 #18];Vessel Breughel | 369600 | 219000 | 0 | 0 | 588600 | 4.6667
142 | Directional drillings and 150kV cable laying onshore | 1.6.4 |  |  | 2013-02-18 06:00 | 2013-05-19 22:00 | 91d |  |  | 604470 |  |  | 1990070 | 90.6667
136 | Delivery of pipes to be drilled | 1.6.4.1 |  | FS193 | 2013-02-18 06:00 | 2013-04-18 22:00 | 60d |  | 0 | 103570 | 0 | 0 | 103570 | 59.6667
193 | Welding pipes together | 1.6.4.2 | 136FS | FS138 | 2013-04-19 06:00 | 2013-04-23 22:00 | 5d | Laborer[12.00 #60];Welder[8.00 #8];Crane;Engineer | 105600 | 138000 | 0 | 0 | 243600 | 4.6667
137 | Directional drillings on land | 1.6.4.3 |  | FS138 | 2013-04-09 06:00 | 2013-04-23 22:00 | 15d | Laborer[16.00 #60];Engineer[4.00 #18];Drilling machine[2.00 #2] | 883200 | 223000 | 0 | 0 | 1106200 | 14.6667
138 | Pulling welded pipe in through drilling hole | 1.6.4.4 | 137FS;193FS | FS139;FS150 | 2013-04-24 06:00 | 2013-04-26 22:00 | 3d | Laborer[14.00 #60];Engineer[4.00 #18];Pulling machine | 120000 | 0 | 0 | 0 | 120000 | 2.6667
139 | Factory Acceptance Tests on land cables | 1.6.4.5 | 138FS | FS140 | 2013-04-27 06:00 | 2013-04-28 22:00 | 2d | Testing team | 25600 | 12500 | 0 | 0 | 38100 | 1.6667
140 | Cable laying onshore between export cable landing and Elia sub-station | 1.6.4.6 | 139FS | FS141 | 2013-05-12 06:00 | 2013-05-16 22:00 | 5d | Laborer[13.00 #60];Engineer[4.00 #18];Pulling machine;Crane | 212800 | 18200 | 0 | 0 | 231000 | 4.6667
141 | Connection of the cables into Elia sub-station | 1.6.4.7 | 140FS | FS194 | 2013-05-17 06:00 | 2013-05-18 22:00 | 2d | Disconnecting team | 25600 | 54600 | 0 | 0 | 80200 | 1.6667
194 | Electrical commissioning tests on the onshore cable connections | 1.6.4.8 | 141FS | FS154 | 2013-05-19 06:00 | 2013-05-19 22:00 | 1d | Testing team | 12800 | 54600 | 0 | 0 | 67400 | 0.66667
155 | Export cable was laid down | 1.6.5 |  |  | 2013-05-14 06:00 | 2013-09-22 07:00 | 131d 1h |  |  | 169100 |  |  | 1246060 | 131.0417
149 | Export cable laying on sea bed between coast and OTS | 1.6.5.1 | 126FS;131FS;134FS | SS150 | 2013-05-14 06:00 | 2013-05-23 22:00 | 10d | Laborer[17.00 #60];Skipper;Engineer[4.00 #18];Vessel Breydel | 732800 | 0 | 0 | 0 | 732800 | 9.6667
150 | Landfall cable pull | 1.6.5.2 | 149SS;138FS | FS195 | 2013-05-24 06:00 | 2013-05-24 22:00 | 1d | Laborer[13.00 #60];Engineer[3.00 #18];Pulling machine | 36800 | 0 | 0 | 0 | 36800 | 0.66667
195 | Making joint between sea cable and land cable | 1.6.5.3 | 150FS | FS151 | 2013-05-25 06:00 | 2013-05-25 22:00 | 1d | Disconnecting team | 12800 | 12500 | 0 | 0 | 25300 | 0.66667
151 | Backfilling of cable trench | 1.6.5.4 | 195FS | FS152;FS157 | 2013-05-26 06:00 | 2013-05-28 22:00 | 3d | Laborer[12.00 #60];Skipper;Engineer[6.00 #18];Vessel Pearl River | 228000 | 97000 | 0 | 0 | 325000 | 2.6667
152 | Export cable pull in OTS | 1.6.5.5 | 95FS;151FS | FS153 | 2013-09-18 07:00 | 2013-09-19 07:00 | 1d | Laborer[20.00 #60];Engineer[6.00 #18] | 28160 | 12500 | 0 | 0 | 40660 | 1
153 | Complete connection of cable conductors and fibre optics | 1.6.5.6 | 152FS | FS154 | 2013-09-19 07:00 | 2013-09-21 07:00 | 2d | Disconnecting team | 25600 | 12500 | 0 | 0 | 38100 | 2
154 | Testing 24 hours connection of cable conductors and fibre optics | 1.6.5.7 | 153FS;194FS | FS430;FS431;FS432;FS433;FS434;FS435;FS436;FS437;FS438;FS439;FS440;FS441;FS442;FS443;FS444;FS445;FS446;FS447;FS448;FS449;FS450;FS451;FS452;FS453 | 2013-09-21 07:00 | 2013-09-22 07:00 | 1d | Testing team | 12800 | 34600 | 0 | 0 | 47400 | 1
160 | Protection of internal communication cables and gas pipes | 1.6.6 |  |  | 2013-05-28 06:00 | 2013-05-30 22:00 | 3d |  |  | 325000 |  |  | 439560 | 2.6667
156 | Delivery of rock on Halve Maan site | 1.6.6.1 |  | FS157 | 2013-05-28 06:00 | 2013-05-28 22:00 | 1d |  | 0 | 325000 | 0 | 0 | 325000 | 0.66667
157 | Mobilizing rock dumping vessel | 1.6.6.2 | 156FS;151FS | FS158 | 2013-05-29 06:00 | 2013-05-29 22:00 | 1d | Laborer[5.00 #60];Skipper;Vessel Pompei | 57280 | 0 | 0 | 0 | 57280 | 0.66667
158 | Rock dumping on PEC crossing and Interconnector South | 1.6.6.3 | 157FS |  | 2013-05-30 06:00 | 2013-05-30 22:00 | 1d | Laborer[5.00 #60];Skipper;Vessel Pompei | 57280 | 0 | 0 | 0 | 57280 | 0.66667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Skipper | Renewable | 4 s | 0 | 60 | 3;6;7;526[0.50 Skipper];527[0.50 Skipper];528[0.50 Skipper];529[0.50 Skipper];530[0.50 Skipper];531[0.50 Skipper];532[0.50 Skipper];533[0.50 Skipper];534[0.50 Skipper];535[0.50 Skipper];536[0.50 Skipper];537[0.50 Skipper];538[0.50 Skipper];539[0.50 Skipper];540[0.50 Skipper];541[0.50 Skipper];542[0.50 Skipper];543[0.50 Skipper];544[0.50 Skipper];545[0.50 Skipper];546[0.50 Skipper];547[0.50 Skipper];548[0.50 Skipper];549[0.50 Skipper];550[0.50 Skipper];12;13;14;196;197;198;199;200;201;202;203;204;205;206;207;208;209;210;211;212;213;214;215;216;217;16;17;162;218;219;220;221;222;223;224;225;226;227;228;229;230;231;232;233;234;235;236;237;238;239;240;241;242;243;244;245;246;247;248;249;250;251;252;253;254;255;256;257;258;259;260;261;262;263;264;313;314;315;316;317;318;319;320;321;322;323;324;325;326;327;328;329;330;331;332;333;334;335;336;289;290;291;292;293;294;295;296;297;298;299;300;301;302;303;304;305;306;307;308;309;310;311;312;265;266;267;268;269;270;271;272;273;274;275;276;277;278;279;280;281;282;283;284;285;286;287;288;502[2.00 Skipper];503[2.00 Skipper];504[2.00 Skipper];505[2.00 Skipper];506[2.00 Skipper];507[2.00 Skipper];508[2.00 Skipper];509[2.00 Skipper];510[2.00 Skipper];511[2.00 Skipper];512[2.00 Skipper];513[2.00 Skipper];514[2.00 Skipper];515[2.00 Skipper];516[2.00 Skipper];517[2.00 Skipper];518[2.00 Skipper];519[2.00 Skipper];520[2.00 Skipper];521[2.00 Skipper];522[2.00 Skipper];523[2.00 Skipper];524[2.00 Skipper];525[2.00 Skipper];478[2.00 Skipper];479[2.00 Skipper];480[2.00 Skipper];481[2.00 Skipper];482[2.00 Skipper];483[2.00 Skipper];484[2.00 Skipper];485[2.00 Skipper];486[2.00 Skipper];487[2.00 Skipper];488[2.00 Skipper];489[2.00 Skipper];490[2.00 Skipper];491[2.00 Skipper];492[2.00 Skipper];493[2.00 Skipper];494[2.00 Skipper];495[2.00 Skipper];496[2.00 Skipper];497[2.00 Skipper];498[2.00 Skipper];499[2.00 Skipper];500[2.00 Skipper];501[2.00 Skipper];77;82;81;94;95;100;101;102;105;106;108;110;112;126;130;131;133;134;149;151;157;158; | 521760
2 | Welder | Renewable | 8 w | 0 | 60 | 57;58;193[8.00 Welder]; | 130560
3 | Engineer | Renewable | 18 e | 0 | 160 | 3[3.00 Engineer];7[6.00 Engineer];12[6.00 Engineer];13[6.00 Engineer];14[6.00 Engineer];196[6.00 Engineer];197[6.00 Engineer];198[6.00 Engineer];199[6.00 Engineer];200[6.00 Engineer];201[6.00 Engineer];202[6.00 Engineer];203[6.00 Engineer];204[6.00 Engineer];205[6.00 Engineer];206[6.00 Engineer];207[6.00 Engineer];208[6.00 Engineer];209[6.00 Engineer];210[6.00 Engineer];211[6.00 Engineer];212[6.00 Engineer];213[6.00 Engineer];214[6.00 Engineer];215[6.00 Engineer];216[6.00 Engineer];217[6.00 Engineer];16[6.00 Engineer];17[6.00 Engineer];162[6.00 Engineer];218[6.00 Engineer];219[6.00 Engineer];220[6.00 Engineer];221[6.00 Engineer];222[6.00 Engineer];223[6.00 Engineer];224[6.00 Engineer];225[6.00 Engineer];226[6.00 Engineer];227[6.00 Engineer];228[6.00 Engineer];229[6.00 Engineer];230[6.00 Engineer];231[6.00 Engineer];232[6.00 Engineer];233[6.00 Engineer];234[6.00 Engineer];235[6.00 Engineer];236[6.00 Engineer];237[6.00 Engineer];238[6.00 Engineer];239[6.00 Engineer];240[6.00 Engineer];241[6.00 Engineer];242[6.00 Engineer];243[6.00 Engineer];244[6.00 Engineer];245[6.00 Engineer];246[6.00 Engineer];247[6.00 Engineer];248[6.00 Engineer];249[6.00 Engineer];250[6.00 Engineer];251[6.00 Engineer];252[6.00 Engineer];253[6.00 Engineer];254[6.00 Engineer];255[6.00 Engineer];256[6.00 Engineer];257[6.00 Engineer];258[6.00 Engineer];259[6.00 Engineer];260[6.00 Engineer];261[6.00 Engineer];262[6.00 Engineer];263[6.00 Engineer];264[6.00 Engineer];289[6.00 Engineer];290[6.00 Engineer];291[6.00 Engineer];292[6.00 Engineer];293[6.00 Engineer];294[6.00 Engineer];295[6.00 Engineer];296[6.00 Engineer];297[6.00 Engineer];298[6.00 Engineer];299[6.00 Engineer];300[6.00 Engineer];301[6.00 Engineer];302[6.00 Engineer];303[6.00 Engineer];304[6.00 Engineer];305[6.00 Engineer];306[6.00 Engineer];307[6.00 Engineer];308[6.00 Engineer];309[6.00 Engineer];310[6.00 Engineer];311[6.00 Engineer];312[6.00 Engineer];265[6.00 Engineer];266[6.00 Engineer];267[6.00 Engineer];268[6.00 Engineer];269[6.00 Engineer];270[6.00 Engineer];271[6.00 Engineer];272[6.00 Engineer];273[6.00 Engineer];274[6.00 Engineer];275[6.00 Engineer];276[6.00 Engineer];277[6.00 Engineer];278[6.00 Engineer];279[6.00 Engineer];280[6.00 Engineer];281[6.00 Engineer];282[6.00 Engineer];283[6.00 Engineer];284[6.00 Engineer];285[6.00 Engineer];286[6.00 Engineer];287[6.00 Engineer];288[6.00 Engineer];56[6.00 Engineer];57[3.00 Engineer];58[3.00 Engineer];502[8.00 Engineer];503[8.00 Engineer];504[8.00 Engineer];505[8.00 Engineer];506[8.00 Engineer];507[8.00 Engineer];508[8.00 Engineer];509[8.00 Engineer];510[8.00 Engineer];511[8.00 Engineer];512[8.00 Engineer];513[8.00 Engineer];514[8.00 Engineer];515[8.00 Engineer];516[8.00 Engineer];517[8.00 Engineer];518[8.00 Engineer];519[8.00 Engineer];520[8.00 Engineer];521[8.00 Engineer];522[8.00 Engineer];523[8.00 Engineer];524[8.00 Engineer];525[8.00 Engineer];478[8.00 Engineer];479[8.00 Engineer];480[8.00 Engineer];481[8.00 Engineer];482[8.00 Engineer];483[8.00 Engineer];484[8.00 Engineer];485[8.00 Engineer];486[8.00 Engineer];487[8.00 Engineer];488[8.00 Engineer];489[8.00 Engineer];490[8.00 Engineer];491[8.00 Engineer];492[8.00 Engineer];493[8.00 Engineer];494[8.00 Engineer];495[8.00 Engineer];496[8.00 Engineer];497[8.00 Engineer];498[8.00 Engineer];499[8.00 Engineer];500[8.00 Engineer];501[8.00 Engineer];82[4.00 Engineer];81[6.00 Engineer];94;95[6.00 Engineer];100[4.00 Engineer];101[4.00 Engineer];102[3.00 Engineer];106[3.00 Engineer];110[4.00 Engineer];111[4.00 Engineer];112[4.00 Engineer];126[3.00 Engineer];133[4.00 Engineer];134[4.00 Engineer];193;137[4.00 Engineer];138[4.00 Engineer];140[4.00 Engineer];149[4.00 Engineer];150[3.00 Engineer];151[6.00 Engineer];152[6.00 Engineer]; | 6740480
4 | Special team | Renewable | 2 st | 0 | 800 | 454;455;456;457;458;459;460;461;462;463;464;465;466;467;468;469;470;471;472;473;474;475;476;477;109[2.00 Special team]; | 2150400
5 | Disconnecting team | Renewable | 1 dct | 0 | 800 | 141;195;153; | 64000
6 | Commissioning team | Renewable | 1 ct | 0 | 800 | 430;431;432;433;434;435;436;437;438;439;440;441;442;443;444;445;446;447;448;449;450;451;452;453; | 1536000
7 | Testing team | Renewable | 1 tt | 0 | 800 | 406[0.20 Testing team];407[0.20 Testing team];408[0.20 Testing team];409[0.20 Testing team];410[0.20 Testing team];411[0.20 Testing team];412[0.20 Testing team];413[0.20 Testing team];414[0.20 Testing team];415[0.20 Testing team];416[0.20 Testing team];417[0.20 Testing team];418[0.20 Testing team];419[0.20 Testing team];421[0.20 Testing team];420[0.20 Testing team];422[0.20 Testing team];423[0.20 Testing team];424[0.20 Testing team];425[0.20 Testing team];426[0.20 Testing team];427[0.20 Testing team];428[0.20 Testing team];429[0.20 Testing team];107;139;194;154; | 371200
8 | Diving team | Renewable | 1 dvt | 0 | 900 | 265;266;267;268;269;270;271;272;273;274;275;276;277;278;279;280;281;282;283;284;285;286;287;288; | 345600
9 | Crane | Renewable | 3 c | 0 | 200 | 526;527;528;529;530;531;532;533;534;535;536;537;538;539;540;541;542;543;544;545;546;547;548;549;550;313[2.00 Crane];314[2.00 Crane];315[2.00 Crane];316[2.00 Crane];317[2.00 Crane];318[2.00 Crane];319[2.00 Crane];320[2.00 Crane];321[2.00 Crane];322[2.00 Crane];323[2.00 Crane];324[2.00 Crane];325[2.00 Crane];326[2.00 Crane];327[2.00 Crane];328[2.00 Crane];329[2.00 Crane];330[2.00 Crane];331[2.00 Crane];332[2.00 Crane];333[2.00 Crane];334[2.00 Crane];335[2.00 Crane];336[2.00 Crane];56[3.00 Crane];57;58;502;503;504;505;506;507;508;509;510;511;512;513;514;515;516;517;518;519;520;521;522;523;524;525;77;82;94;105;131[2.00 Crane];193;140; | 1145600
10 | Vessel Pompei | Renewable | 1 vp | 0 | 3320 | 6;7;16;162;218;219;220;221;222;223;224;225;226;227;228;229;230;231;232;233;234;235;236;237;238;239;240;100;101;102;106;126;157;158; | 4568320
11 | Vessel Neptune | Renewable | 1 vn | 0 | 3750 | 502;503;504;505;506;507;508;509;510;511;512;513;514;515;516;517;518;519;520;521;522;523;524;525;478;479;480;481;482;483;484;485;486;487;488;489;490;491;492;493;494;495;496;497;498;499;500;501; | 5760000
12 | Vessel Vagant | Renewable | 1 vv | 0 | 3180 | 502;503;504;505;506;507;508;509;510;511;512;513;514;515;516;517;518;519;520;521;522;523;524;525;478;479;480;481;482;483;484;485;486;487;488;489;490;491;492;493;494;495;496;497;498;499;500;501; | 4884480
13 | Vessel Sternat Spirit | Renewable | 1 vss | 0 | 3250 | 130;131; | 468000
14 | Vessel Souverreign | Renewable | 1 vs | 0 | 3250 | 105; | 260000
15 | Vessel Rambiz | Renewable | 1 vr | 0 | 3620 | 289;290;291;292;293;294;295;296;297;298;299;300;301;302;303;304;305;306;307;308;309;310;311;312;265;266;267;268;269;270;271;272;273;274;275;276;277;278;279;280;281;282;283;284;285;286;287;288;81;95; | 2896000
16 | Vessel Buzzard | Renewable | 1 vbz | 0 | 3200 | 3;12;13;14;196;197;198;199;200;201;202;203;204;205;206;207;208;209;210;211;212;213;214;215;216;217;17;241;242;243;244;245;246;247;248;249;250;251;252;253;254;255;256;257;258;259;260;261;262;263;264; | 3891200
17 | Vessel Breydel | Renewable | 2 vbd | 0 | 3200 | 149; | 512000
18 | Vessel Breughel | Renewable | 1 vbg | 0 | 3200 | 133;134; | 512000
19 | Vessel Pearl River | Renewable | 1 vpr | 0 | 3250 | 151; | 156000
20 | Vessel Maersk | Renewable | 1 vm | 0 | 800 | 526[0.50 Vessel Maersk];527[0.50 Vessel Maersk];528[0.50 Vessel Maersk];529[0.50 Vessel Maersk];530[0.50 Vessel Maersk];531[0.50 Vessel Maersk];532[0.50 Vessel Maersk];533[0.50 Vessel Maersk];534[0.50 Vessel Maersk];535[0.50 Vessel Maersk];536[0.50 Vessel Maersk];537[0.50 Vessel Maersk];538[0.50 Vessel Maersk];539[0.50 Vessel Maersk];540[0.50 Vessel Maersk];541[0.50 Vessel Maersk];542[0.50 Vessel Maersk];543[0.50 Vessel Maersk];544[0.50 Vessel Maersk];545[0.50 Vessel Maersk];546[0.50 Vessel Maersk];547[0.50 Vessel Maersk];548[0.50 Vessel Maersk];549[0.50 Vessel Maersk];550[0.50 Vessel Maersk]; | 160000
21 | Vessel Innovator | Renewable | 1 vi | 0 | 3250 | 108;110;112; | 3224000
22 | Pre-piling template | Renewable | 1 pt | 0 | 200 |  | 0
23 | Towning tugs | Renewable | 2 twt | 0 | 450 | 313;314;315;316;317;318;319;320;321;322;323;324;325;326;327;328;329;330;331;332;333;334;335;336;77;82;94; | 201600
24 | Transport barges | Renewable | 2 tb | 0 | 400 | 313;314;315;316;317;318;319;320;321;322;323;324;325;326;327;328;329;330;331;332;333;334;335;336;77;82;94; | 179200
25 | Drilling machine | Renewable | 2 dm | 0 | 1200 | 137[2.00 Drilling machine]; | 576000
26 | Pulling machine | Renewable | 1 pm | 0 | 1300 | 138;140;150; | 187200
27 | Laborer | Renewable | 60 l | 0 | 40 | 3[5.00 Laborer];6[5.00 Laborer];7[22.00 Laborer];526[5.00 Laborer];527[5.00 Laborer];528[5.00 Laborer];529[5.00 Laborer];530[5.00 Laborer];531[5.00 Laborer];532[5.00 Laborer];533[5.00 Laborer];534[5.00 Laborer];535[5.00 Laborer];536[5.00 Laborer];537[5.00 Laborer];538[5.00 Laborer];539[5.00 Laborer];540[5.00 Laborer];541[5.00 Laborer];542[5.00 Laborer];543[5.00 Laborer];544[5.00 Laborer];545[5.00 Laborer];546[5.00 Laborer];547[5.00 Laborer];548[5.00 Laborer];549[5.00 Laborer];550[5.00 Laborer];12[22.00 Laborer];13[22.00 Laborer];14[22.00 Laborer];196[22.00 Laborer];197[22.00 Laborer];198[22.00 Laborer];199[22.00 Laborer];200[22.00 Laborer];201[22.00 Laborer];202[22.00 Laborer];203[22.00 Laborer];204[22.00 Laborer];205[22.00 Laborer];206[22.00 Laborer];207[22.00 Laborer];208[22.00 Laborer];209[22.00 Laborer];210[22.00 Laborer];211[22.00 Laborer];212[22.00 Laborer];213[22.00 Laborer];214[22.00 Laborer];215[22.00 Laborer];216[22.00 Laborer];217[22.00 Laborer];16[18.00 Laborer];17[20.00 Laborer];162[18.00 Laborer];218[18.00 Laborer];219[18.00 Laborer];220[18.00 Laborer];221[18.00 Laborer];222[18.00 Laborer];223[18.00 Laborer];224[18.00 Laborer];225[18.00 Laborer];226[18.00 Laborer];227[18.00 Laborer];228[18.00 Laborer];229[18.00 Laborer];230[18.00 Laborer];231[18.00 Laborer];232[18.00 Laborer];233[18.00 Laborer];234[18.00 Laborer];235[18.00 Laborer];236[18.00 Laborer];237[18.00 Laborer];238[18.00 Laborer];239[18.00 Laborer];240[18.00 Laborer];241[20.00 Laborer];242[20.00 Laborer];243[20.00 Laborer];244[20.00 Laborer];245[20.00 Laborer];246[20.00 Laborer];247[20.00 Laborer];248[20.00 Laborer];249[20.00 Laborer];250[20.00 Laborer];251[20.00 Laborer];252[20.00 Laborer];253[20.00 Laborer];254[20.00 Laborer];255[20.00 Laborer];256[20.00 Laborer];257[20.00 Laborer];258[20.00 Laborer];259[20.00 Laborer];260[20.00 Laborer];261[20.00 Laborer];262[20.00 Laborer];263[20.00 Laborer];264[20.00 Laborer];313[6.00 Laborer];314[6.00 Laborer];315[6.00 Laborer];316[6.00 Laborer];317[6.00 Laborer];318[6.00 Laborer];319[6.00 Laborer];320[6.00 Laborer];321[6.00 Laborer];322[6.00 Laborer];323[6.00 Laborer];324[6.00 Laborer];325[6.00 Laborer];326[6.00 Laborer];327[6.00 Laborer];328[6.00 Laborer];329[6.00 Laborer];330[6.00 Laborer];331[6.00 Laborer];332[6.00 Laborer];333[6.00 Laborer];334[6.00 Laborer];335[6.00 Laborer];336[6.00 Laborer];289[22.00 Laborer];290[22.00 Laborer];291[22.00 Laborer];292[22.00 Laborer];293[22.00 Laborer];294[22.00 Laborer];295[22.00 Laborer];296[22.00 Laborer];297[22.00 Laborer];298[22.00 Laborer];299[22.00 Laborer];300[22.00 Laborer];301[22.00 Laborer];302[22.00 Laborer];303[22.00 Laborer];304[22.00 Laborer];305[22.00 Laborer];306[22.00 Laborer];307[22.00 Laborer];308[22.00 Laborer];309[22.00 Laborer];310[22.00 Laborer];311[22.00 Laborer];312[22.00 Laborer];265[12.00 Laborer];266[12.00 Laborer];267[12.00 Laborer];268[12.00 Laborer];269[12.00 Laborer];270[12.00 Laborer];271[12.00 Laborer];272[12.00 Laborer];273[12.00 Laborer];274[12.00 Laborer];275[12.00 Laborer];276[12.00 Laborer];277[12.00 Laborer];278[12.00 Laborer];279[12.00 Laborer];280[12.00 Laborer];281[12.00 Laborer];282[12.00 Laborer];283[12.00 Laborer];284[12.00 Laborer];285[12.00 Laborer];286[12.00 Laborer];287[12.00 Laborer];288[12.00 Laborer];56[32.00 Laborer];57[16.00 Laborer];58[19.00 Laborer];502[16.00 Laborer];503[16.00 Laborer];504[16.00 Laborer];505[16.00 Laborer];506[16.00 Laborer];507[16.00 Laborer];508[16.00 Laborer];509[16.00 Laborer];510[16.00 Laborer];511[16.00 Laborer];512[16.00 Laborer];513[16.00 Laborer];514[16.00 Laborer];515[16.00 Laborer];516[16.00 Laborer];517[16.00 Laborer];518[16.00 Laborer];519[16.00 Laborer];520[16.00 Laborer];521[16.00 Laborer];522[16.00 Laborer];523[16.00 Laborer];524[16.00 Laborer];525[16.00 Laborer];478[16.00 Laborer];479[16.00 Laborer];480[16.00 Laborer];481[16.00 Laborer];482[16.00 Laborer];483[16.00 Laborer];484[16.00 Laborer];485[16.00 Laborer];486[16.00 Laborer];487[16.00 Laborer];488[16.00 Laborer];489[16.00 Laborer];490[16.00 Laborer];491[16.00 Laborer];492[16.00 Laborer];493[16.00 Laborer];494[16.00 Laborer];495[16.00 Laborer];496[16.00 Laborer];497[16.00 Laborer];498[16.00 Laborer];499[16.00 Laborer];500[16.00 Laborer];501[16.00 Laborer];77[8.00 Laborer];82[8.00 Laborer];81[18.00 Laborer];94[4.00 Laborer];95[18.00 Laborer];100[5.00 Laborer];101[5.00 Laborer];102[5.00 Laborer];105[10.00 Laborer];106[18.00 Laborer];107[12.00 Laborer];108[22.00 Laborer];110[22.00 Laborer];112[22.00 Laborer];126[5.00 Laborer];130[6.00 Laborer];131[6.00 Laborer];133[18.00 Laborer];134[18.00 Laborer];193[12.00 Laborer];137[16.00 Laborer];138[14.00 Laborer];140[13.00 Laborer];149[17.00 Laborer];150[13.00 Laborer];151[12.00 Laborer];152[20.00 Laborer];157[5.00 Laborer];158[5.00 Laborer]; | 6674560

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Sea Electricity | 7489h |  |  |  |  | 99 | 100 | 101
20 | Pin-piles | 3248h |  |  |  |  | 99 | 100 | 101
1 | Fabrication of pre-piling template | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Transportation of template and mounting on Jack Up Platform Buzzard | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Mobilisation of Jack Up Platform Buzzard | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
551 | Purchasing of pin-piles | 800h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Continious delivery of pin-piles | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Seabed preparations | 640h |  |  |  |  | 99 | 100 | 101
6 | Mobilisation of vessels | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Seabed preparations | 400h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
15 | Pile driving works | 1600h |  |  |  |  | 99 | 100 | 101
526 | Delivery of pin-piles OTS | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
527 | Delivery of pin-piles 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
528 | Delivery of pin-piles 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
529 | Delivery of pin-piles 3 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
530 | Delivery of pin-piles 4 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
531 | Delivery of pin-piles 5 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
532 | Delivery of pin-piles 6 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
533 | Delivery of pin-piles 7 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
534 | Delivery of pin-piles 8 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
535 | Delivery of pin-piles 9 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
536 | Delivery of pin-piles 10 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
537 | Delivery of pin-piles 11 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
538 | Delivery of pin-piles 12 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
539 | Delivery of pin-piles 13 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
540 | Delivery of pin-piles 14 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
541 | Delivery of pin-piles 15 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
542 | Delivery of pin-piles 16 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
543 | Delivery of pin-piles 17 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
544 | Delivery of pin-piles 18 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
545 | Delivery of pin-piles 19 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
546 | Delivery of pin-piles 20 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
547 | Delivery of pin-piles 21 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
548 | Delivery of pin-piles 22 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
549 | Delivery of pin-piles 23 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
550 | Delivery of pin-piles 24 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | OTS: drive 4 pin-piles for OTS foundation into seabed | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Turbine1: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
14 | Turbine2: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
196 | Turbine3: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
197 | Turbine4: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
198 | Turbine5: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
199 | Turbine6: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
200 | Turbine7: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
201 | Turbine8: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
202 | Turbine9: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
203 | Turbine10: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
204 | Turbine11: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
205 | Turbine12: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
206 | Turbine13: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
207 | Turbine14: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
208 | Turbine15: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
209 | Turbine16: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
210 | Turbine17: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
211 | Turbine18: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
212 | Turbine19: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
213 | Turbine20: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
214 | Turbine21: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
215 | Turbine22: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
216 | Turbine23: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
217 | Turbine24: drive 4 pin-piles for jacket foundation into seabed | 32h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
19 | Dredging and cleaning of the pin-piles (Pompei) | 1584h |  |  |  |  | 99 | 100 | 101
165 | OTS | 32h |  |  |  |  | 99 | 100 | 101
16 | Dredging and cleaning of pin-piles | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Install pin-pile covers on the piles | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
166 | Turbines | 1520h |  |  |  |  | 99 | 100 | 101
162 | Dredging and cleaning of pin-piles 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | Dredging and cleaning of pin-piles 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
219 | Dredging and cleaning of pin-piles 3 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
220 | Dredging and cleaning of pin-piles 4 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
221 | Dredging and cleaning of pin-piles 5 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
222 | Dredging and cleaning of pin-piles 6 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
223 | Dredging and cleaning of pin-piles 7 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
224 | Dredging and cleaning of pin-piles 8 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
225 | Dredging and cleaning of pin-piles 9 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
226 | Dredging and cleaning of pin-piles 10 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
227 | Dredging and cleaning of pin-piles 11 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
228 | Dredging and cleaning of pin-piles 12 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
229 | Dredging and cleaning of pin-piles 13 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
230 | Dredging and cleaning of pin-piles 14 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
231 | Dredging and cleaning of pin-piles 15 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
232 | Dredging and cleaning of pin-piles 16 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
233 | Dredging and cleaning of pin-piles 17 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
234 | Dredging and cleaning of pin-piles 18 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
235 | Dredging and cleaning of pin-piles 19 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
236 | Dredging and cleaning of pin-piles 20 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
237 | Dredging and cleaning of pin-piles 21 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
238 | Dredging and cleaning of pin-piles 22 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
239 | Dredging and cleaning of pin-piles 23 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
240 | Dredging and cleaning of pin-piles 24 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
241 | Install pin-pile covers on the piles 1 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
242 | Install pin-pile covers on the piles 2 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
243 | Install pin-pile covers on the piles 3 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
244 | Install pin-pile covers on the piles 4 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
245 | Install pin-pile covers on the piles 5 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
246 | Install pin-pile covers on the piles 6 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
247 | Install pin-pile covers on the piles 7 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
248 | Install pin-pile covers on the piles 8 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
249 | Install pin-pile covers on the piles 9 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
250 | Install pin-pile covers on the piles 10 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
251 | Install pin-pile covers on the piles 11 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
252 | Install pin-pile covers on the piles 12 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
253 | Install pin-pile covers on the piles 13 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
254 | Install pin-pile covers on the piles 14 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
255 | Install pin-pile covers on the piles 15 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
256 | Install pin-pile covers on the piles 16 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
257 | Install pin-pile covers on the piles 17 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
258 | Install pin-pile covers on the piles 18 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
259 | Install pin-pile covers on the piles 19 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
260 | Install pin-pile covers on the piles 20 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
261 | Install pin-pile covers on the piles 21 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
262 | Install pin-pile covers on the piles 22 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
263 | Install pin-pile covers on the piles 23 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
264 | Install pin-pile covers on the piles 24 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
45 | Jacket foundations of wind turbines | 4304h |  |  |  |  | 99 | 100 | 101
35 | Fabrication and assemblage of steel structure for jacket foundations | 4256h |  |  |  |  | 99 | 100 | 101
21 | Purshase of tubulars | 1920h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
23 | Purchase of castings and pile stoppers | 1920h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
25 | Assembly of midsection 1 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
337 | Assembly of midsection 2 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
338 | Assembly of midsection 3 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
339 | Assembly of midsection 4 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
340 | Assembly of midsection 5 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
341 | Assembly of midsection 6 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
342 | Assembly of midsection 7 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
343 | Assembly of midsection 8 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
344 | Assembly of midsection 9 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
345 | Assembly of midsection 10 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
346 | Assembly of midsection 11 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
347 | Assembly of midsection 12 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
348 | Assembly of midsection 13 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
349 | Assembly of midsection 14 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
350 | Assembly of midsection 15 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
351 | Assembly of midsection 16 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
352 | Assembly of midsection 17 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
353 | Assembly of midsection 18 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
354 | Assembly of midsection 19 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
355 | Assembly of midsection 20 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
356 | Assembly of midsection 21 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
357 | Assembly of midsection 22 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
358 | Assembly of midsection 23 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
359 | Assembly of midsection 24 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Purchase of secondary steel items | 1280h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
29 | Final jacket assembly 1 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
360 | Final jacket assembly 2 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
361 | Final jacket assembly 3 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
362 | Final jacket assembly 4 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
363 | Final jacket assembly 5 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
364 | Final jacket assembly 6 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
365 | Final jacket assembly 7 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
366 | Final jacket assembly 8 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
367 | Final jacket assembly 9 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
368 | Final jacket assembly 10 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
369 | Final jacket assembly 11 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
370 | Final jacket assembly 12 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
371 | Final jacket assembly 13 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
372 | Final jacket assembly 14 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
373 | Final jacket assembly 15 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
374 | Final jacket assembly 16 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
375 | Final jacket assembly 17 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
376 | Final jacket assembly 18 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
377 | Final jacket assembly 19 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
378 | Final jacket assembly 20 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
379 | Final jacket assembly 21 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
380 | Final jacket assembly 22 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
381 | Final jacket assembly 23 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
382 | Final jacket assembly 24 | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Transport (Hoboken to Vlissingen) 1 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
383 | Transport (Hoboken to Vlissingen) 2 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
384 | Transport (Hoboken to Vlissingen) 3 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
385 | Transport (Hoboken to Vlissingen) 4 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
386 | Transport (Hoboken to Vlissingen) 5 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
387 | Transport (Hoboken to Vlissingen) 6 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
388 | Transport (Hoboken to Vlissingen) 7 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
389 | Transport (Hoboken to Vlissingen) 8 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
390 | Transport (Hoboken to Vlissingen) 9 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
391 | Transport (Hoboken to Vlissingen) 10 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
392 | Transport (Hoboken to Vlissingen) 11 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
393 | Transport (Hoboken to Vlissingen) 12 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
394 | Transport (Hoboken to Vlissingen) 13 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
395 | Transport (Hoboken to Vlissingen) 14 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
396 | Transport (Hoboken to Vlissingen) 15 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
397 | Transport (Hoboken to Vlissingen) 16 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
398 | Transport (Hoboken to Vlissingen) 17 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
399 | Transport (Hoboken to Vlissingen) 18 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
400 | Transport (Hoboken to Vlissingen) 19 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
401 | Transport (Hoboken to Vlissingen) 20 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
402 | Transport (Hoboken to Vlissingen) 21 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
403 | Transport (Hoboken to Vlissingen) 22 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
404 | Transport (Hoboken to Vlissingen) 23 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
405 | Transport (Hoboken to Vlissingen) 24 | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
44 | Transportation and installation of the jacket foundations | 2960h |  |  |  |  | 99 | 100 | 101
313 | Transport of the jacket foundations 1 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
314 | Transport of the jacket foundations 2 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
315 | Transport of the jacket foundations 3 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
316 | Transport of the jacket foundations 4 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
317 | Transport of the jacket foundations 5 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
318 | Transport of the jacket foundations 6 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
319 | Transport of the jacket foundations 7 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
320 | Transport of the jacket foundations 8 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
321 | Transport of the jacket foundations 9 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
322 | Transport of the jacket foundations 10 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
323 | Transport of the jacket foundations 11 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
324 | Transport of the jacket foundations 12 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
325 | Transport of the jacket foundations 13 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
326 | Transport of the jacket foundations 14 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
327 | Transport of the jacket foundations 15 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
328 | Transport of the jacket foundations 16 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
329 | Transport of the jacket foundations 17 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
330 | Transport of the jacket foundations 18 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
331 | Transport of the jacket foundations 19 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
332 | Transport of the jacket foundations 20 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
333 | Transport of the jacket foundations 21 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
334 | Transport of the jacket foundations 22 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
335 | Transport of the jacket foundations 23 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
336 | Transport of the jacket foundations 24 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
289 | Installation of the jacket foundations 1 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
290 | Installation of the jacket foundations 2 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
291 | Installation of the jacket foundations 3 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
292 | Installation of the jacket foundations 4 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
293 | Installation of the jacket foundations 5 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
294 | Installation of the jacket foundations 6 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
295 | Installation of the jacket foundations 7 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
296 | Installation of the jacket foundations 8 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
297 | Installation of the jacket foundations 9 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
298 | Installation of the jacket foundations 10 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
299 | Installation of the jacket foundations 11 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
300 | Installation of the jacket foundations 12 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
301 | Installation of the jacket foundations 13 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
302 | Installation of the jacket foundations 14 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
303 | Installation of the jacket foundations 15 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
304 | Installation of the jacket foundations 16 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
305 | Installation of the jacket foundations 17 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
306 | Installation of the jacket foundations 18 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
307 | Installation of the jacket foundations 19 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
308 | Installation of the jacket foundations 20 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
309 | Installation of the jacket foundations 21 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
310 | Installation of the jacket foundations 22 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
311 | Installation of the jacket foundations 23 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
312 | Installation of the jacket foundations 24 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
265 | Grouting of foundation to the pin-piles 1 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
266 | Grouting of foundation to the pin-piles 2 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
267 | Grouting of foundation to the pin-piles 3 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
268 | Grouting of foundation to the pin-piles 4 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
269 | Grouting of foundation to the pin-piles 5 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
270 | Grouting of foundation to the pin-piles 6 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
271 | Grouting of foundation to the pin-piles 7 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
272 | Grouting of foundation to the pin-piles 8 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
273 | Grouting of foundation to the pin-piles 9 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
274 | Grouting of foundation to the pin-piles 10 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
275 | Grouting of foundation to the pin-piles 11 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
276 | Grouting of foundation to the pin-piles 12 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
277 | Grouting of foundation to the pin-piles 13 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
278 | Grouting of foundation to the pin-piles 14 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
279 | Grouting of foundation to the pin-piles 15 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
280 | Grouting of foundation to the pin-piles 16 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
281 | Grouting of foundation to the pin-piles 17 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
282 | Grouting of foundation to the pin-piles 18 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
283 | Grouting of foundation to the pin-piles 19 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
284 | Grouting of foundation to the pin-piles 20 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
285 | Grouting of foundation to the pin-piles 21 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
286 | Grouting of foundation to the pin-piles 22 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
287 | Grouting of foundation to the pin-piles 23 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
288 | Grouting of foundation to the pin-piles 24 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
74 | Wind turbines | 7477h |  |  |  |  | 99 | 100 | 101
62 | Purchasing parts of wind turbines | 5508h |  |  |  |  | 99 | 100 | 101
54 | Purchasing and production of parts of wind turbines | 5380h |  |  |  |  | 99 | 100 | 101
46 | Towers by AMAU-Cuxhaven Germany | 3840h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
47 | Blades by LM Denmark | 3840h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
48 | Generators by VEM Germany | 3840h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
49 | Gearboxes by WINERGY-Vörde Germany and Hansen Belgium | 3840h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
55 | Transportation of parts from respective factories to Ostend | 2308h |  |  |  |  | 99 | 100 | 101
53 | Towers Germany-Ostend | 768h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
52 | Blades Denmark-Ostend | 629h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
51 | Generators Germany-Ostend | 768h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
50 | Gearboxes Germany-Ostend/Antwerp-Ostend | 768h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
56 | Preparation of the onshore site | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Assembly of wind turbines on site in Ostend | 1536h |  |  |  |  | 99 | 100 | 101
57 | Assembly of gearbox and generator | 768h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Assembly of blades | 768h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Installation wind turbines | 2417h |  |  |  |  | 99 | 100 | 101
502 | Loading jack up transport and installation platform 1 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
503 | Loading jack up transport and installation platform 2 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
504 | Loading jack up transport and installation platform 3 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
505 | Loading jack up transport and installation platform 4 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
506 | Loading jack up transport and installation platform 5 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
507 | Loading jack up transport and installation platform 6 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
508 | Loading jack up transport and installation platform 7 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
509 | Loading jack up transport and installation platform 8 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
510 | Loading jack up transport and installation platform 9 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
511 | Loading jack up transport and installation platform 10 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
512 | Loading jack up transport and installation platform 11 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
513 | Loading jack up transport and installation platform 12 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
514 | Loading jack up transport and installation platform 13 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
515 | Loading jack up transport and installation platform 14 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
516 | Loading jack up transport and installation platform 15 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
517 | Loading jack up transport and installation platform 16 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
518 | Loading jack up transport and installation platform 17 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
519 | Loading jack up transport and installation platform 18 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
520 | Loading jack up transport and installation platform 19 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
521 | Loading jack up transport and installation platform 20 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
522 | Loading jack up transport and installation platform 21 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
523 | Loading jack up transport and installation platform 22 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
524 | Loading jack up transport and installation platform 23 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
525 | Loading jack up transport and installation platform 24 | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
478 | Offshore assembly of wind turbines 1 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
479 | Offshore assembly of wind turbines 2 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
480 | Offshore assembly of wind turbines 3 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
481 | Offshore assembly of wind turbines 4 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
482 | Offshore assembly of wind turbines 5 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
483 | Offshore assembly of wind turbines 6 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
484 | Offshore assembly of wind turbines 7 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
485 | Offshore assembly of wind turbines 8 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
486 | Offshore assembly of wind turbines 9 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
487 | Offshore assembly of wind turbines 10 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
488 | Offshore assembly of wind turbines 11 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
489 | Offshore assembly of wind turbines 12 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
490 | Offshore assembly of wind turbines 13 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
491 | Offshore assembly of wind turbines 14 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
492 | Offshore assembly of wind turbines 15 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
493 | Offshore assembly of wind turbines 16 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
494 | Offshore assembly of wind turbines 17 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
495 | Offshore assembly of wind turbines 18 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
496 | Offshore assembly of wind turbines 19 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
497 | Offshore assembly of wind turbines 20 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
498 | Offshore assembly of wind turbines 21 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
499 | Offshore assembly of wind turbines 22 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
500 | Offshore assembly of wind turbines 23 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
501 | Offshore assembly of wind turbines 24 | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
454 | Terminations of infield cables 1 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
455 | Terminations of infield cables 2 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
456 | Terminations of infield cables 3 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
457 | Terminations of infield cables 4 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
458 | Terminations of infield cables 5 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
459 | Terminations of infield cables 6 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
460 | Terminations of infield cables 7 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
461 | Terminations of infield cables 8 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
462 | Terminations of infield cables 9 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
463 | Terminations of infield cables 10 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
464 | Terminations of infield cables 11 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
465 | Terminations of infield cables 12 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
466 | Terminations of infield cables 13 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
467 | Terminations of infield cables 14 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
468 | Terminations of infield cables 15 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
469 | Terminations of infield cables 16 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
470 | Terminations of infield cables 17 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
471 | Terminations of infield cables 18 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
472 | Terminations of infield cables 19 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
473 | Terminations of infield cables 20 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
474 | Terminations of infield cables 21 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
475 | Terminations of infield cables 22 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
476 | Terminations of infield cables 23 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
477 | Terminations of infield cables 24 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
430 | Commissioning of wind turbines 1 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
431 | Commissioning of wind turbines 2 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
432 | Commissioning of wind turbines 3 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
433 | Commissioning of wind turbines 4 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
434 | Commissioning of wind turbines 5 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
435 | Commissioning of wind turbines 6 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
436 | Commissioning of wind turbines 7 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
437 | Commissioning of wind turbines 8 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
438 | Commissioning of wind turbines 9 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
439 | Commissioning of wind turbines 10 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
440 | Commissioning of wind turbines 11 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
441 | Commissioning of wind turbines 12 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
442 | Commissioning of wind turbines 13 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
443 | Commissioning of wind turbines 14 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
444 | Commissioning of wind turbines 15 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
445 | Commissioning of wind turbines 16 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
446 | Commissioning of wind turbines 17 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
447 | Commissioning of wind turbines 18 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
448 | Commissioning of wind turbines 19 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
449 | Commissioning of wind turbines 20 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
450 | Commissioning of wind turbines 21 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
451 | Commissioning of wind turbines 22 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
452 | Commissioning of wind turbines 23 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
453 | Commissioning of wind turbines 24 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
406 | Reliability tests 1 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
407 | Reliability tests 2 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
408 | Reliability tests 3 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
409 | Reliability tests 4 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
410 | Reliability tests 5 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
411 | Reliability tests 6 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
412 | Reliability tests 7 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
413 | Reliability tests 8 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
414 | Reliability tests 9 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
415 | Reliability tests 10 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
416 | Reliability tests 11 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
417 | Reliability tests 12 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
418 | Reliability tests 13 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
419 | Reliability tests 14 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
421 | Reliability tests 15 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
420 | Reliability tests 16 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
422 | Reliability tests 17 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
423 | Reliability tests 18 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
424 | Reliability tests 19 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
425 | Reliability tests 20 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
426 | Reliability tests 21 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
427 | Reliability tests 22 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
428 | Reliability tests 23 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
429 | Reliability tests 24 | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
98 | Offshore Transformer Station | 3617h |  |  |  |  | 99 | 100 | 101
80 | Construction of jacket foundation of OTS | 1888h |  |  |  |  | 99 | 100 | 101
75 | Purchase of base materials | 640h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
76 | Construction of jacket foundation for OTS | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | Transport of jacket foundation to Ostend | 32h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
83 | Installation of jacket foundation of OTS | 32h |  |  |  |  | 99 | 100 | 101
82 | Transport of jacket foundation in sea | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
81 | Installation of jacket foundation of OTS | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
93 | Steelstructure of Offshore OTS | 3585h |  |  |  |  | 99 | 100 | 101
84 | Purchase of base materials | 2400h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
85 | Erection of 1st main deck section | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Erection of 2st main deck section | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | Erection of mezzanine deck | 256h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | Construction of roof deck | 256h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | Internal finishings | 33h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
90 | Installation of transformer equipment | 960h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
91 | Preparation for upcoming transport | 160h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
97 | Transport and installation | 32h |  |  |  |  | 99 | 100 | 101
94 | Transport of OTS | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
95 | Installation of OTS foundation | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
125 | Infield cables (33 kV) | 5408h |  |  |  |  | 99 | 100 | 101
103 | Preparatory works for infield cable laying | 256h |  |  |  |  | 99 | 100 | 101
100 | Rock dumping as scour protection around the OTS foundation | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | GOSA mattresses installations above existing underground cables as protection | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | Pre-grapnel run to remove obstacles from cable trajectories | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | Infield cables: production, transport and installation | 5408h |  |  |  |  | 99 | 100 | 101
104 | Production in Karlskrona Sweden | 1920h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
105 | Transport | 80h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
106 | Pre-grapnel runs to remove obstacles | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | Wet trials | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | Cable laying works | 768h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
109 | Final hang off of the cables in the WTG foundations | 768h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
110 | Burial of cables | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | Survey of burial depths | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | Second remedial burial pass if necessary | 64h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
161 | Export cables (150 kV) | 3681h |  |  |  |  | 99 | 100 | 101
126 | Pre-lay grapnel run on trajectory | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Production and transport of export cable | 1504h |  |  |  |  | 99 | 100 | 101
128 | Purchase of raw materials | 1120h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
129 | Manufacturing in Karlskrona Sweden | 640h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
130 | Mobilisation of Stemat Spirit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | Transport Sweden-Ostend | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | Dredging shipping lane and preparing trench | 160h |  |  |  |  | 99 | 100 | 101
133 | Dredging to widen shipping lane Vaargeul1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | Prepare trench where export cable B (150kV) is crossing Vaargeul1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | Directional drillings and 150kV cable laying onshore | 1456h |  |  |  |  | 99 | 100 | 101
136 | Delivery of pipes to be drilled | 960h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
193 | Welding pipes together | 80h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
137 | Directional drillings on land | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | Pulling welded pipe in through drilling hole | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | Factory Acceptance Tests on land cables | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | Cable laying onshore between export cable landing and Elia sub-station | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
141 | Connection of the cables into Elia sub-station | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
194 | Electrical commissioning tests on the onshore cable connections | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
155 | Export cable was laid down | 2097h |  |  |  |  | 99 | 100 | 101
149 | Export cable laying on sea bed between coast and OTS | 160h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
150 | Landfall cable pull | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | Making joint between sea cable and land cable | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | Backfilling of cable trench | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
152 | Export cable pull in OTS | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | Complete connection of cable conductors and fibre optics | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | Testing 24 hours connection of cable conductors and fibre optics | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | Protection of internal communication cables and gas pipes | 48h |  |  |  |  | 99 | 100 | 101
156 | Delivery of rock on Halve Maan site | 16h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
157 | Mobilizing rock dumping vessel | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | Rock dumping on PEC crossing and Interconnector South | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | Yes
6:00 - 7:00 | Yes | Sunday | Yes
7:00 - 8:00 | Yes
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | Yes
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | Yes
18:00 - 19:00 | Yes
19:00 - 20:00 | Yes
20:00 - 21:00 | Yes
21:00 - 22:00 | Yes
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold