## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Firenze race team | 1 |  |  | 2020-02-05 08:00 | 2020-04-07 17:00 | 45d |  |  | 0 |  |  | 0
1 | New wing Design | 1.1 |  | FS2 | 2020-02-05 08:00 | 2020-02-11 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
2 | CFD simulation | 1.2 | 1FS | FS3;FS7;FS8 | 2020-02-12 08:00 | 2020-02-13 10:00 | 1d 2h |  | 0 | 0 | 0 | 0 | 0
3 | Clamping to Chassis (Desing and FEManalysis) | 1.3 | 2FS | FS9 | 2020-02-13 10:00 | 2020-02-19 10:00 | 4d |  | 0 | 0 | 0 | 0 | 0
4 | New brackets (desing and FEM) | 1.4 | 6FS | FS9 | 2020-03-17 08:00 | 2020-03-23 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
5 | New endplate design | 1.5 |  | FS6 | 2020-02-12 08:00 | 2020-02-27 17:00 | 12d |  | 0 | 0 | 0 | 0 | 0
6 | CFD simulation | 1.6 | 5FS | FS4;FS7;FS8 | 2020-02-28 08:00 | 2020-03-16 17:00 | 12d |  | 0 | 0 | 0 | 0 | 0
7 | Resin & Carbon | 1.7 | 2FS;6FS | FS11 | 2020-03-17 08:00 | 2020-03-24 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0
8 | Molds | 1.8 | 2FS;6FS | FS11 | 2020-03-25 08:00 | 2020-04-01 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0
9 | Sheet metal Steel C45 | 1.9 | 3FS;4FS | FS10 | 2020-03-24 08:00 | 2020-03-24 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
10 | Laser Cut and Steel Weld | 1.10 | 9FS |  | 2020-03-25 08:00 | 2020-03-26 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
11 | Lamination | 1.11 | 7FS;8FS |  | 2020-04-02 08:00 | 2020-04-07 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
12 | Design | 1.12 |  | FS17 | 2020-02-12 08:00 | 2020-02-19 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0
13 | Design | 1.13 |  | FS14 | 2020-02-12 08:00 | 2020-02-17 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
14 | Dynamic Simulation | 1.14 | 13FS |  | 2020-02-18 08:00 | 2020-02-21 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
15 | Pipes and cables | 1.15 |  | FS17 | 2020-02-12 08:00 | 2020-02-19 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0
16 | Sheet metal C45 | 1.16 |  | FS17 | 2020-02-12 08:00 | 2020-02-12 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
17 | Laser Cut and Steel Weld | 1.17 | 12FS;15FS;16FS |  | 2020-02-20 08:00 | 2020-02-21 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
18 | Definition | 1.18 |  | FS19 | 2020-02-12 08:00 | 2020-02-17 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
19 | Sizing | 1.19 | 18FS | FS21;FS35;FS38 | 2020-02-18 08:00 | 2020-02-25 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0
20 | Design | 1.20 |  | FS22 | 2020-02-12 08:00 | 2020-02-14 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
21 | Gearbox components | 1.21 | 19FS | FS23 | 2020-02-26 08:00 | 2020-03-06 17:00 | 8d |  | 0 | 0 | 0 | 0 | 0
22 | Rear Sprocket | 1.22 | 20FS |  | 2020-02-17 08:00 | 2020-02-18 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
23 | Metal cut and machining | 1.23 | 21FS |  | 2020-03-09 08:00 | 2020-03-13 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
24 | Upper shaft design | 1.24 |  | FS25;FS29 | 2020-02-12 08:00 | 2020-02-17 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
25 | Steering support design | 1.25 | 24FS |  | 2020-02-18 08:00 | 2020-02-20 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
26 | Dashboard desing | 1.26 |  | FS30 | 2020-02-05 08:00 | 2020-02-07 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
27 | Development (external company) | 1.27 |  | FS28 | 2020-02-05 08:00 | 2020-02-25 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0
28 | Steering wheel | 1.28 | 27FS |  | 2020-02-26 08:00 | 2020-03-02 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
29 | Universal joints | 1.29 | 24FS | FS31 | 2020-02-18 08:00 | 2020-02-19 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
30 | Metal | 1.30 | 26FS | FS32 | 2020-02-10 08:00 | 2020-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
31 | Machining 1 | 1.31 | 29FS |  | 2020-02-20 08:00 | 2020-02-24 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
32 | Machining 2 | 1.32 | 30FS |  | 2020-02-11 08:00 | 2020-02-12 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
33 | Design | 1.33 |  | FS36 | 2020-02-05 08:00 | 2020-02-05 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
34 | Design | 1.34 |  |  | 2020-02-05 08:00 | 2020-02-11 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
35 | Design | 1.35 | 19FS |  | 2020-02-26 08:00 | 2020-03-05 17:00 | 7d |  | 0 | 0 | 0 | 0 | 0
36 | tubes | 1.36 | 33FS |  | 2020-02-06 08:00 | 2020-02-13 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0
37 | New pipes structure | 1.37 |  | FS38 | 2020-02-05 08:00 | 2020-02-14 17:00 | 8d |  | 0 | 0 | 0 | 0 | 0
38 | Actuators clamping | 1.38 | 37FS;19FS | FS39 | 2020-02-26 08:00 | 2020-03-02 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
39 | Cut and welding | 1.39 | 38FS |  | 2020-03-03 08:00 | 2020-03-03 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
40 | Spring design | 1.40 |  | FS43 | 2020-02-05 08:00 | 2020-02-07 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
41 | Push rod design | 1.41 |  | FS42 | 2020-02-05 08:00 | 2020-02-06 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
42 | round stock Steel C45 | 1.42 | 41FS | FS44 | 2020-02-07 08:00 | 2020-02-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
43 | Spring (ext) | 1.43 | 40FS |  | 2020-02-10 08:00 | 2020-02-11 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
44 | Push rod cut and welding | 1.44 | 42FS |  | 2020-02-10 08:00 | 2020-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
45 | Update | 1.45 |  | FS51;FS52 | 2020-02-05 08:00 | 2020-02-20 17:00 | 12d |  | 0 | 0 | 0 | 0 | 0
46 | Build & Test | 1.46 |  |  | 2020-02-05 08:00 | 2020-02-18 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
47 | Update | 1.47 |  | FS51;FS52 | 2020-02-05 08:00 | 2020-02-20 17:00 | 12d |  | 0 | 0 | 0 | 0 | 0
48 | Build & Test | 1.48 |  |  | 2020-02-05 08:00 | 2020-02-19 17:00 | 11d |  | 0 | 0 | 0 | 0 | 0
49 | Design | 1.49 |  | FS50 | 2020-02-05 08:00 | 2020-02-10 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
50 | Test | 1.50 | 49FS |  | 2020-02-11 08:00 | 2020-02-11 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
51 | Board components | 1.51 | 45FS;47FS | FS53;FS54 | 2020-02-21 08:00 | 2020-02-26 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
52 | Boards | 1.52 | 45FS;47FS | FS53;FS54 | 2020-02-21 08:00 | 2020-02-26 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
53 | Laser Cut | 1.53 | 51FS;52FS |  | 2020-02-27 08:00 | 2020-02-27 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
54 | 3D print | 1.54 | 51FS;52FS |  | 2020-02-27 08:00 | 2020-02-27 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Firenze race team | 360h
1 | New wing Design | 40h | standard - symmetric | 80 | 100 | 120
2 | CFD simulation | 10h | standard - symmetric | 80 | 100 | 120
3 | Clamping to Chassis (Desing and FEManalysis) | 32h | standard - symmetric | 80 | 100 | 120
4 | New brackets (desing and FEM) | 40h | standard - symmetric | 80 | 100 | 120
5 | New endplate design | 96h | standard - symmetric | 80 | 100 | 120
6 | CFD simulation | 96h | standard - symmetric | 80 | 100 | 120
7 | Resin & Carbon | 48h | standard - symmetric | 80 | 100 | 120
8 | Molds | 48h | standard - symmetric | 80 | 100 | 120
9 | Sheet metal Steel C45 | 8h | standard - symmetric | 80 | 100 | 120
10 | Laser Cut and Steel Weld | 16h | standard - symmetric | 80 | 100 | 120
11 | Lamination | 32h | standard - symmetric | 80 | 100 | 120
12 | Design | 48h | standard - symmetric | 80 | 100 | 120
13 | Design | 32h | standard - symmetric | 80 | 100 | 120
14 | Dynamic Simulation | 32h | standard - symmetric | 80 | 100 | 120
15 | Pipes and cables | 48h | standard - symmetric | 80 | 100 | 120
16 | Sheet metal C45 | 8h | standard - symmetric | 80 | 100 | 120
17 | Laser Cut and Steel Weld | 16h | standard - symmetric | 80 | 100 | 120
18 | Definition | 32h | standard - symmetric | 80 | 100 | 120
19 | Sizing | 48h | standard - symmetric | 80 | 100 | 120
20 | Design | 24h | standard - symmetric | 80 | 100 | 120
21 | Gearbox components | 64h | standard - symmetric | 80 | 100 | 120
22 | Rear Sprocket | 16h | standard - symmetric | 80 | 100 | 120
23 | Metal cut and machining | 40h | standard - symmetric | 80 | 100 | 120
24 | Upper shaft design | 32h | standard - symmetric | 80 | 100 | 120
25 | Steering support design | 24h | standard - symmetric | 80 | 100 | 120
26 | Dashboard desing | 24h | standard - symmetric | 80 | 100 | 120
27 | Development (external company) | 120h | standard - symmetric | 80 | 100 | 120
28 | Steering wheel | 32h | standard - symmetric | 80 | 100 | 120
29 | Universal joints | 16h | standard - symmetric | 80 | 100 | 120
30 | Metal | 8h | standard - symmetric | 80 | 100 | 120
31 | Machining 1 | 24h | standard - symmetric | 80 | 100 | 120
32 | Machining 2 | 16h | standard - symmetric | 80 | 100 | 120
33 | Design | 8h | standard - symmetric | 80 | 100 | 120
34 | Design | 40h | standard - symmetric | 80 | 100 | 120
35 | Design | 56h | standard - symmetric | 80 | 100 | 120
36 | tubes | 48h | standard - symmetric | 80 | 100 | 120
37 | New pipes structure | 64h | standard - symmetric | 80 | 100 | 120
38 | Actuators clamping | 32h | standard - symmetric | 80 | 100 | 120
39 | Cut and welding | 8h | standard - symmetric | 80 | 100 | 120
40 | Spring design | 24h | standard - symmetric | 80 | 100 | 120
41 | Push rod design | 16h | standard - symmetric | 80 | 100 | 120
42 | round stock Steel C45 | 8h | standard - symmetric | 80 | 100 | 120
43 | Spring (ext) | 16h | standard - symmetric | 80 | 100 | 120
44 | Push rod cut and welding | 8h | standard - symmetric | 80 | 100 | 120
45 | Update | 96h | standard - symmetric | 80 | 100 | 120
46 | Build & Test | 80h | standard - symmetric | 80 | 100 | 120
47 | Update | 96h | standard - symmetric | 80 | 100 | 120
48 | Build & Test | 88h | standard - symmetric | 80 | 100 | 120
49 | Design | 32h | standard - symmetric | 80 | 100 | 120
50 | Test | 8h | standard - symmetric | 80 | 100 | 120
51 | Board components | 32h | standard - symmetric | 80 | 100 | 120
52 | Boards | 32h | standard - symmetric | 80 | 100 | 120
53 | Laser Cut | 8h | standard - symmetric | 80 | 100 | 120
54 | 3D print | 8h | standard - symmetric | 80 | 100 | 120

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3